## FS1 format
Row Labels | FS1 - November | FS1 - December | FS1 - January | FS1 - February
1.2.8.5.10 END NPX FS1
EN
1.2.8.5.5.1 SES: Drillers Support for SES Layout |  | 18 | 18 | 4
EN |  | 18 | 18 | 4
1.2.8.5.5.2 SES: Layout - Hoses, Cables, Interconnects and Cable trays |  |  | 288
TE |  |  | 288
1.2.8.5.5.3.1 SES: Deliver, Upgrade,/Repair, Connect, Test Fuel Tower |  | 16 | 4
EN |  | 16 | 4
1.2.8.5.5.4 SES: Temp power from backup generator (CRELL, ONAN) |  | 1 | 2 | 1
EN |  | 1 | 2 | 1
1.2.8.5.6.1 Gens/PDM: Lift generators onto Skis with Crane |  | 8
TE |  | 8
1.2.8.5.6.3 Gens/PDM: Generators - Misc Repairs |  | 40 | 40
EN |  | 40 | 40
1.2.8.5.6.5 Gens/PDM: Preliminary GEN Testing |  |  | 16
EN |  |  | 16
1.2.8.5.7.1.1 Computing/Controls: Install Retrofit Kits | 48 | 60 | 36
EN | 48 | 60 | 36
1.2.8.5.7.1.2 Computing/Controls: Install Modbus & DGH Modules (EE) |  | 8 | 8
EN |  | 8 | 8
1.2.8.5.7.1.2 Computing/Controls: Misc. Controls Tasking (EE) |  | 8 | 8
EN |  | 8 | 8
1.2.8.5.7.1.3 Computing/Controls: Conduit wiring
TE
1.2.8.5.7.10.1 RWCR: Integrate & Test (EE) |  | 8
EN |  | 8
1.2.8.5.7.10.1 RWCR: Integrate & Test (TE) |  | 8
TE |  | 8
1.2.8.5.7.11.1 Winches/Reels: Repair/Retrofit Winches & Reels (EE) |  | 48
EN |  | 48
1.2.8.5.7.11.1 Winches/Reels: Repair/Retrofit Winches & Reels (ME) |  | 8
EN |  | 8
1.2.8.5.7.11.1 Winches/Reels: Repair/Retrofit Winches & Reels (TE) |  | 48
TE |  | 48
1.2.8.5.7.12.1 Hoses/Cables/Etc.: Inventory & Repair |  |  | 40 | 40
TE |  |  | 40 | 40
1.2.8.5.7.13.1 IFD: Repair/Refit/Test (EE) |  | 32
TE |  | 32
1.2.8.5.7.13.1 IFD: Repair/Refit/Test (ME) |  | 32
TE |  | 32
1.2.8.5.7.13.1 IFD: Repair/Refit/Test (TE w/ ASC Electrician Support) |  | 16
TE |  | 16
1.2.8.5.7.14.1 ARA Drill: Repair and Upgrade ARA Drill (EE) |  |  | 80
EN |  |  | 80
1.2.8.5.7.14.1 ARA Drill: Repair and Upgrade ARA Drill (ME) |  |  | 96
EN |  |  | 96
1.2.8.5.7.14.1 ARA Drill: Repair and Upgrade ARA Drill (TE) |  |  | 48
TE |  |  | 48
1.2.8.5.7.14.2 ARA Drill: Preliminary Integration (EE) |  |  | 8
EN |  |  | 8
1.2.8.5.7.14.2 ARA Drill: Preliminary Integration (ME) |  |  | 8
EN |  |  | 8
1.2.8.5.7.14.2 ARA Drill: Preliminary Integration (TE) |  |  | 8
TE |  |  | 8
1.2.8.5.7.14.3 ARA Drill: Winterize & Store ARA Drill |  |  | 32
EN |  |  | 32
1.2.8.5.7.2.1 DCC: Controls Retrofit (EE) |  |  | 24
EN |  |  | 24
1.2.8.5.7.2.1 DCC: Repairs, Electrical Upgrades, Install Racks (EE) |  |  | 32
TE |  |  | 32
1.2.8.5.7.3.1 MHP: Controls Retrofit (EE) | 128 | 128
EN | 128 | 128
1.2.8.5.7.3.1 MHP: Retrofit MHPs | 116 | 116
EN | 20 | 20
TE | 96 | 96
1.2.8.5.7.3.2 MHP subsystem evaluation |  | 32
EN |  | 32
1.2.8.5.7.4.1 PHS: Controls Retrofit (EE) |  | 106
EN |  | 106
1.2.8.5.7.4.1 PHS: Mechanical Retrofit (EN) |  | 32
EN |  | 32
1.2.8.5.7.4.1 PHS: Mechanical Retrofit (TE) |  | 40
TE |  | 40
1.2.8.5.7.4.2 PHS: Subsystem Evaluation |  | 16
EN |  | 16
1.2.8.5.7.4.3 PHS: Install Filtration System |  | 48
EN |  | 48
1.2.8.5.7.5.1 Water Tanks: Retrofit (Railings, Ladders, Vert pumps, Submersible Pumps, Manifolds, etc.) |  | 176
EN |  | 40
TE |  | 136
1.2.8.5.7.5.2 Water Tank: Subsystem Evaluation |  | 16
EN |  | 16
1.2.8.5.7.6.1 HPP: Controls Retrofit (Sensors, Motor Drives, Air Handling, Etc.) |  | 96
EN |  | 96
1.2.8.5.7.6.1 HPP: Controls Retrofit (Sensors, Motor Drives, Air Handling, Etc.) |  | 16
TE |  | 16
1.2.8.5.7.6.1 HPP: Mechanical Refit |  | 120
EN |  | 24
TE |  | 96
1.2.8.5.7.6.2 HPP: Pump Evaluated |  | 16
EN |  | 16
1.2.8.5.7.7.1 Shops: Repair/Retrofit SHOP | 16 | 16 | 16
EN | 16 | 16 | 16
1.2.8.5.7.7.1 Shops: Repair/Retrofit Shops, MECC | 16 | 16 | 16
TE | 16 | 16 | 16
1.2.8.5.7.7.1 Shops: Repair/Retrofit Shops, OML |  | 8
EN |  | 8
1.2.8.5.7.7.1 Shops: Repair/Retrofit Shops, SEW |  | 8 | 8
EN |  | 8 | 8
1.2.8.5.7.8.1 TOS/Towers: Inspect/Test Controls (EE) |  | 8 | 16
EN |  | 8 | 16
1.2.8.5.7.8.1 TOS/Towers: Inspect/Test Mechanical Systems (ME) |  | 8 | 8
EN |  | 8 | 8
1.2.8.5.7.8.1 TOS/Towers: Repair/Retrofit |  | 64 | 64
TE |  | 64 | 64
1.2.8.5.7.8.1 TOS/Towers: Repair/Retrofit Controls (EE) |  | 392 | 392
EN |  | 392 | 392
1.2.8.5.7.8.1 TOS/Towers: Repair/Retrofit Mechanical (ME) |  | 32 | 32
EN |  | 32 | 32
1.2.8.5.7.9.1 MSHR: Repair/Replace Components, Energize & Test (EE) |  | 48
EN |  | 48
1.2.8.5.7.9.1 MSHR: Repair/Replace Components, Energize & Test (ME) |  | 24
EN |  | 24
1.2.8.5.7.9.1 MSHR:Repair/Replace Components, Energize & Test |  | 56
TE |  | 56
1.2.8.5.8.1 Close-out: Document, Photograph Equip & Upgrade Work, Further Req's |  |  | 120
TE |  |  | 120
1.2.8.5.8.2 Winterize/Close/Store all EHWD Equipment |  |  | 44 | 40
TE |  |  | 44 | 40
1.2.8.5.8.3 Retro all components, crate, pack and deliver to cargo |  |  |  | 32
TE |  |  |  | 32
1.2.8.5.9.1 MCM Logistics Rep (driller) | 144
TE | 144
Grand Total | 468 | 1997 | 1512 | 117

## FS2 format
Row Labels | FS2 - November | FS2 - December | FS2 - January
1.2.8.6.1 START NPX FS2 - Team Arrives [Comm/WTst/FirnDr]
EN
1.2.8.6.10.1 Rod Well: Develop & Maintain (Using ARA Drill) |  | 250 | 150
EN |  | 250 | 150
1.2.8.6.11.1 IFD: Integration and Commissioning |  | 32
TE |  | 32
1.2.8.6.11.2 IFD: Drill 8 Firn Holes |  | 48 | 48
EN |  | 48 | 48
1.2.8.6.11.4 IFD: Winterize & Store |  |  | 48
EN |  |  | 48
1.2.8.6.12.1 Wet Test: Readiness Review, Safety Refresher, Emergency & Safety Systems Tested |  |  | 112
EN |  |  | 112
1.2.8.6.12.2 Wet Test: Fire Boilers, Circulate Water or Glycol |  |  | 32
EN |  |  | 32
1.2.8.6.12.3 Wet Test: Perform Systems Tests (Wet Test & Comm.) |  |  | 672
TE |  |  | 672
1.2.8.6.12.4 Wet Test: Blow Out Systems (need ASC compressor) |  |  | 180
TE |  |  | 180
1.2.8.6.13.1 Close-out: Document, Photograph Equip & Upgrade Work, Further Req's |  |  | 44
EN |  |  | 44
1.2.8.6.13.2 Close-out: Remove DNF, Computer Equip, Drives, Capacitors, Etc |  |  | 144
TE |  |  | 144
1.2.8.6.13.3 Close-out: Winterize/Close/Store all EHWD Equipment |  |  | 96
EN |  |  | 96
1.2.8.6.13.4 Close-out: Prepare Retrograde for Shipment |  |  | 32
TE |  |  | 32
1.2.8.6.13.5.1 Winterize: Remove & Retro/Store All DNF |  |  | 48
TE |  |  | 48
1.2.8.6.13.5.2 Winterize: Winterize SES & TOS, Disconnect all Cables, Hoses, Connections |  |  | 144
TE |  |  | 144
1.2.8.6.13.5.3 Winterize: All EHWD Equipment Winterized
EN
1.2.8.6.14.1 MCM Logistics Rep (driller) | 144
EN | 144
1.2.8.6.15 END NPX FS2 Season
EN
1.2.8.6.5.1 SES: Fuel Tower: Connect, Test and Make Ready | 32
TE | 32
1.2.8.6.5.2 SES: Make Ready all SES Modules (DCC, PHS, MHPs, MECC, WTs, All) | 48
TE | 48
1.2.8.6.5.3 SES: Furnace Checkout & Fire Up (All modules) | 32
EN | 32
1.2.8.6.5.4 SES: Perform Emergency Incident Drill & Safety Training |  | 112
EN |  | 112
1.2.8.6.5.5 SES: Maintenance Activities | 56 | 56
TE | 56 | 56
1.2.8.6.5.6 SES: Site Snow Removal |  | 96
TE |  | 96
1.2.8.6.6.1 Generators/PDM: Charge Generator Batteries | 1
EN | 1
1.2.8.6.6.2 Generators/PDM: Prime/Commission Fuel System | 24
EN | 24
1.2.8.6.6.3 Generators/PDM: GEN-1, 2, 3 - Install GEN hoods | 96
EN | 96
1.2.8.6.6.4 GEN-1, 2, 3, PDM - Repairs & Tests w/Contract Tech Support | 96 | 48
EN | 96 | 48
1.2.8.6.6.5 Generator & PDM: Commission & Final Testing |  | 32
EN |  | 32
1.2.8.6.6.7 Generators/PDM: Change from Temporary Power to IceCube Grid |  | 8
EN |  | 8
1.2.8.6.7.1.1 DCC: Install Racks, Networks, Computers | 32
TE | 32
1.2.8.6.7.10.1 TOS/Tower Equipment - Retrofit & Testing |  |  | 128
TE |  |  | 128
1.2.8.6.7.11.1 Computing/Control: System Integration, Verification, Test at NPX | 250 | 350 | 360
TE | 250 | 350 | 360
1.2.8.6.7.11.2 Computing/Control: Testing and Reprogramming Motor Drives | 160 | 160
TE | 160 | 160
1.2.8.6.7.11.3 Computing/Controls: Install Retrofit Kits | 48 | 60 | 40
TE | 48 | 60 | 40
1.2.8.6.7.11.4 Computing/Controls: Misc. Controls Tasking (EE) | 8 | 25 | 8
EN | 8 | 25 | 8
1.2.8.6.7.11.4 Computing/Controls: Misc. Controls Tasking (TE) | 48 | 60 | 36
TE | 48 | 60 | 36
1.2.8.6.7.11.5 Computing/Controls: Conduit wiring | 72 | 48 | 48
TE | 72 | 48 | 48
1.2.8.6.7.12.1 ARA Drill: Integrate HPU-2 & Commission | 144
EN | 96
TE | 48
1.2.8.6.7.12.2 ARA Drill: Decommission & Store ARA Drill |  |  | 32
TE |  |  | 32
1.2.8.6.7.2.1 MHP: Final Upgrade & Replacement Activities | 64
EN | 64
1.2.8.6.7.2.2 MHP: Final Testing | 32
TE | 32
1.2.8.6.7.3.1 PHS: Install Filters in H2O System | 4
TE | 4
1.2.8.6.7.3.2 PHS: Final Upgrade & Replacement Activities | 32
TE | 32
1.2.8.6.7.3.3 PHS: Final Testing | 32
EN | 32
1.2.8.6.7.4.1 Water Tanks: Install Railings, Ladders, Pumps, Plumbing, Doghouses - Final Upgrades | 176
EN | 40
TE | 136
1.2.8.6.7.4.2 Water Tanks: Integrate, Verify, Test | 64
EN | 64
1.2.8.6.7.5.1 HPP: Final Upgrade & Replacement Activities | 32
TE | 32
1.2.8.6.7.5.2 HPP: Pump Testing | 32
EN | 32
1.2.8.6.7.6.1 Shops: Final Upgrade/Retrofit Shops, MECC | 8
TE | 8
1.2.8.6.7.6.1 Shops: Final Upgrade/Retrofit Shops, OML, TOW, SEW | 16
TE | 16
1.2.8.6.7.7.1 MSHR: Install Drill Hose on Reel |  |  | 128
TE |  |  | 128
1.2.8.6.7.7.2 MSHR: Final Upgrades & Testing |  | 48
EN |  | 48
1.2.8.6.7.7.3 MSHR: Install Blankets, |  |  | 54
TE |  |  | 54
1.2.8.6.7.7.3 MSHR: Install Blankets, Connect to Power, Heating Control and Test |  |  | 32
EN |  |  | 32
1.2.8.6.7.8.1 Winches/Reels: Final Integration & Testing |  | 192
EN |  | 144
TE |  | 48
1.2.8.6.7.9.1 Fuel Storage/Delivery: Commission Fuel Tower | 32 | 96
TE | 32 | 96
1.2.8.6.8.1 Sensor Handling Facility: Assemble Skis and Deck, Erect Walls, Construct Walls, Construct Roof |  | 168
EN |  | 168
1.2.8.6.8.2 Sensor Handling Facility: Final Assembly with ASC-provided Crane |  | 24
TE |  | 24
1.2.8.6.9.1 Condensate Bulb: Drill and Pump |  | 240
EN |  | 240
1.2.9.5.5 String: On-ice Sensor Handling Training
SS
TE
1.2.9.5.6.10 String: Install SJB's in Pits (2); Connect cables (ASC & UW) |  | 8
SC |  | 8
1.2.9.5.6.3 String: Prep/Uncrate Cable Spools; Load onto TU20 (ASC & UW) |  | 24
TE |  | 24
1.2.9.5.6.4 String: Install 7 Surface Cables into ICL Tower, Across Bridge, into ICL (ASC & UW) |  | 16
SC |  | 16
1.2.9.5.6.5 String: Prep Cables & Attach to Grounding System in ICL (ASC & UW) |  | 8
SE |  | 8
1.2.9.5.6.6 String: Connect Surface Cables into ICL Patch Panels (UW) |  | 8
SE |  | 8
1.2.9.5.6.9 String: Unspool & Lay Surface Cables from Tower to SJB Pits (ASC, UW & MSU) |  | 32
SC |  | 32
Grand Total | 1815 | 2249 | 2616

## FS3 format
Row Labels | FS3 - November | FS3 - December | FS3 - January | FS3 - February
1.2.8.7.1 START NPX FS3 - Team Arrives [Drilling/Installation]
TE
1.2.8.7.10.1 Installation: DRILL HOLE # 1 |  | 522
EN |  | 522
1.2.8.7.10.10 Installation: Deployment - String 2 |  | 72
EN |  | 72
1.2.8.7.10.11 Installation: String # 2 Deployed & Complete |  | 0
EN |  | 0
1.2.8.7.10.12 Installation: Closeout & Relocate Tower & TOS to Hole 4 |  | 32
EN |  | 32
1.2.8.7.10.13 Installation: Trench & Install Reel Anchors (Hole 3) |  | 16
EN |  | 16
1.2.8.7.10.14 Installation: Relocate Hose, Cable Reels, Sensor Handling Structure (at end of installation) |  | 28
TE |  | 28
1.2.8.7.10.15 Installation: Prepare SFC-DOM Cable (Mount on TU20, test slip ring) - Prep for String 4 |  | 8
EN |  | 8
1.2.8.7.10.16 Installation: DRILL HOLE # 3 |  | 522
TE |  | 522
1.2.8.7.10.17 Installation: Deployment - String 3 |  | 72
EN |  | 72
1.2.8.7.10.18 Installation: String # 3 Deployed & Complete
TE
1.2.8.7.10.19 Installation: Closeout & Relocate Tower & TOS for Hole 5 |  |  | 32
EN |  |  | 32
1.2.8.7.10.2 Installation: Deployment - String 1 |  | 72
TE |  | 72
1.2.8.7.10.20 Installation: Trench & Install Reel Anchors (Hole 4) |  | 16
TE |  | 16
1.2.8.7.10.21 Installation: Relocate Hose, Cable Reels, Sensor Handling Structure (at end of installation) |  | 28
EN |  | 28
1.2.8.7.10.22 Installation: Hole Excavation, Trench & Install Cable Anchor (Hole 4) |  | 16
EN |  | 16
1.2.8.7.10.23 Installation: Prepare SFC-Sensor Cable (Mount on TU20, test slip ring) - Prep for String 5 |  |  | 8
TE |  |  | 8
1.2.8.7.10.24 Installation: DRILL HOLE # 4 |  |  | 522
EN |  |  | 522
1.2.8.7.10.25 Installation: Deployment |  |  | 72
EN |  |  | 72
1.2.8.7.10.26 Installation: String # 4 Deployed & Complete
TE
1.2.8.7.10.27 Installation: Closeout & Relocate Tower & TOS for Hole 6 |  |  | 32
TE |  |  | 32
1.2.8.7.10.28 Installation: Trench & Install Reel Anchors (Hole 5) |  |  | 16
EN |  |  | 16
1.2.8.7.10.29 Installation: Relocate Hose, Cable Reels, Sensor Handling Structure (at end of installation) |  |  | 28
EN |  |  | 28
1.2.8.7.10.3 Installation: String # 1 Deployed & Complete
EN
1.2.8.7.10.30 Installation: Hole Excavation, Trench & Install Cable Anchor (Hole 5) |  |  | 16
TE |  |  | 16
1.2.8.7.10.31 Installation: Prepare SFC-Sensor Cable (Mount on TU20, test slip ring) - Prep for String 6 |  |  | 8
EN |  |  | 8
1.2.8.7.10.32 Installation: DRILL HOLE # 5 |  |  | 522
EN |  |  | 522
1.2.8.7.10.33 Installation: Deployment - String 5 |  |  | 72
TE |  |  | 72
1.2.8.7.10.34 Installation: String # 5 Deployed & Complete
EN
1.2.8.7.10.35 Installation: Closeout & Relocate Tower & TOS for Hole 7 |  |  | 32
EN |  |  | 32
1.2.8.7.10.36 Installation: Trench & Install Reel Anchors (Hole 6) |  |  | 16
TE |  |  | 16
1.2.8.7.10.37 Installation: Relocate Hose, Cable Reels, Sensor Handling Structure (at end of installation) |  |  | 28
EN |  |  | 28
1.2.8.7.10.38 Installation: Hole Excavation, Trench & Install Cable Anchor (Hole 6) |  |  | 16
TE |  |  | 16
1.2.8.7.10.39 Installation: Prepare SFC-Sensor Cable (Mount on TU20, test slip ring) - Prep for String 7 |  |  | 8
EN |  |  | 8
1.2.8.7.10.4 Installation: Closeout & Relocate Tower & TOS to Hole 3 |  | 32
TE |  | 32
1.2.8.7.10.40 Installation: DRILL HOLE # 6 |  |  | 522
EN |  |  | 522
1.2.8.7.10.41 Installation: Driller Support for Dust Logging Activities |  |  | 16
TE |  |  | 16
1.2.8.7.10.42 Installation: Deployment - String 6 |  |  | 72
EN |  |  | 72
1.2.8.7.10.43 Installation: String # 6 Deployed & Complete
EN
1.2.8.7.10.44 Installation: Closeout & Relocate Tower & TOS to Storage |  |  | 32
EN |  |  | 32
1.2.8.7.10.45 Installation: Trench & Install Reel Anchors (Hole 7) |  |  | 16
TE |  |  | 16
1.2.8.7.10.46 Installation: Relocate Hose, Cable Reels, Sensor Handling Structure (at end of installation) |  |  | 28
EN |  |  | 28
1.2.8.7.10.47 Installation: Hole Excavation, Trench & Install Cable Anchor (Hole 7) |  |  | 16
EN |  |  | 16
1.2.8.7.10.48 Installation: DRILL HOLE # 7 |  |  | 522
TE |  |  | 522
1.2.8.7.10.49 Installation: Deployment - String 7 |  |  | 72
EN |  |  | 72
1.2.8.7.10.5 Installation: Trench & Install Reel Anchors (Hole 2) |  | 16
TE |  | 16
1.2.8.7.10.50 Installation: String # 7 Deployed & Complete
TE
1.2.8.7.10.51 Installation: Closeout & Relocate Tower & TOS to Storage Change duration 7 days |  |  | 32
EN |  |  | 32
1.2.8.7.10.52 Installation: Drilling & Installation Complete
TE
1.2.8.7.10.6 Installation: Relocate Hose, Cable Reels, Sensor Handling Structure (at end of installation) |  | 28
EN |  | 28
1.2.8.7.10.7 Installation: Prepare SFC-DOM Cable (Mount on TU20, test slip ring) Prep for String 3 |  | 8
EN |  | 8
1.2.8.7.10.8 Installation: Operational Debrief |  | 112
EN |  | 112
1.2.8.7.10.9 Installation: DRILL HOLE # 2 |  | 522
TE |  | 522
1.2.8.7.11.1 Decommission and Store: Remove & Retro/Store All DNF |  |  | 375
TE |  |  | 375
1.2.8.7.11.2 Decommission and Store:Decommission SES & TOS, Disconnect all cables hoses, connections |  |  | 485
EN |  |  | 485
1.2.8.7.11.3 Decommission and Store: Winterize all EHWD equipment |  |  | 585
TE |  |  | 585
1.2.8.7.11.4 Decommission and Store: Remove Drill Hose from MSHR, Respool & Ship to ZCM |  |  | 217
EN |  |  | 217
1.2.8.7.11.5 Decommission and Store: Shipment of Drill Hose to ZCM |  |  | 40
TE |  |  | 40
1.2.8.7.11.6 Decommission and Store: Inventory & Photograph EHWD, Document Repairs needed |  |  | 325
EN |  |  | 325
1.2.8.7.11.7 Decommission and Store: UNL Equipment - Deliver to Cargo for Retro or Redistribution |  |  | 80
TE |  |  | 80
1.2.8.7.11.8 Decommission and Store: Crate and Deliver EHWD Equipment to Cargo for Retrograde or Redistribution |  |  | 225
EN |  |  | 225
1.2.8.7.11.9 Decommission and Store: Cargo Retro FS3
EN
1.2.8.7.5.1 SES: Make Ready all Drill Modules (DCC, PHS, MHPs, TOS 1&2, WTs, Handling Facility) | 244
EN | 244
1.2.8.7.5.2 SES: Furnace Checkout & Fire Up (All modules) | 32
TE | 32
1.2.8.7.5.3 SES: Perform Emergency Incident Drill & Safety Training |  | 672
EN |  | 672
1.2.8.7.5.4 SES: Make ARA Drill Ready for Service |  | 80
EN |  | 40
TE |  | 40
1.2.8.7.5.5 SES: Re-Establish RodWell |  | 176 | 96
EN |  | 176 | 96
1.2.8.7.5.6 SES: SES and Equipment Maintenance | 60 | 124 | 124
TE | 60 | 124 | 124
1.2.8.7.5.7 SES: Ready for Drilling - (On Ice Final Readiness Assessment)
EN
1.2.8.7.5.8 SES: Dig-out | 96
EN | 96
1.2.8.7.6.1 Generator/PDM: Recommission | 96
TE | 96
1.2.8.7.6.2 Generator/PDM: Generators Ready | 0
TE | 0
1.2.8.7.6.3 Generator/PDM: Change from Temp Power to Generators (Stand Alone) | 8
EN | 8
1.2.8.7.7.1 TOS1/Tower1: Hole Excavation, Trench & Install Cable Anchor (Hole 1) |  | 16
EN |  | 16
1.2.8.7.7.10 TOS1/Tower1: Prepare SFC-DOM Cable (Mount on TU20, test slip ring) |  | 16
EN |  | 16
1.2.8.7.7.11 TOS1/Tower1: Pull Drill Heads from ICL, Final Testing in TOS |  | 16
TE |  | 16
1.2.8.7.7.12 TOS1/Tower1: Site Ready for Drilling
EN
1.2.8.7.7.2 TOS1/Tower1: Position & Level TOS1/Tower1 at Hole 1 | 16
EN | 16
1.2.8.7.7.3 TOS1/Tower1: Position Sensor Handling Structure | 8
TE | 8
1.2.8.7.7.4 TOS1/Tower1: Hose & Cable Delivery & Layout SES-TOS |  | 96
EN |  | 96
1.2.8.7.7.5 TOS1/Tower1: Trench & Install Reel Anchors (Hole 1) |  | 8
TE |  | 8
1.2.8.7.7.6 TOS1/Tower1: Position Hose & Cable Reels (Hole 1) |  | 8
EN |  | 8
1.2.8.7.7.7 TOS1/Tower1: Make TOS1 Operational, Deliver fuel, fire furnace |  | 16
TE |  | 16
1.2.8.7.7.8 TOS1/Tower1: TOS1 Network/Comms Install |  | 6
EN |  | 6
1.2.8.7.7.9 TOS1/Tower1: Connect Hose Loop, Circulate Water |  | 48
TE |  | 48
1.2.8.7.8.1 TOS2/Tower2: Position & Level TOS2/Tower2 at Hole 2 | 16
EN | 16
1.2.8.7.8.2 TOS2/Tower2: Cable Layout SES to TOS2 |  | 16
TE |  | 16
1.2.8.7.8.3 TOS2/Tower2:Make TOS2 Operational, Deliver fuel, fire furnace |  | 16
EN |  | 16
1.2.8.7.8.4 TOS2/Tower2: TOS2 Network/Comms Install |  | 6
EN |  | 6
1.2.8.7.8.5 TOS2/Tower2: TOS2/Tower2 in Position & Heated
TE
1.2.8.7.9.1 Wet Test: Readiness Review/Safety Refresher | 224
TE | 224
1.2.8.7.9.1 Wet Test: Training (Direct Hire Drillers -15) |  | 1200
TE |  | 1200
1.2.8.7.9.1 Wet Test: Training (Engineer/Drillers - 3) |  | 240
EN |  | 240
1.2.8.7.9.2 Wet Test: Emergency & Safety Systems Tested | 192
EN | 192
1.2.8.7.9.3 Wet Test: Fire Boilers, Circulate Water | 160
EN | 160
1.2.8.7.9.4 Wet Test: Perform Complete Systems Testing (Wet Test & Comm.) |  | 800
TE |  | 800
1.2.9.6.1 String: Plan & Coordinate Installation (FS3) | 80 | 80 | 80 | 80
SS | 80 | 80 | 80 | 80
1.2.9.6.2 String: On Ice Readiness Review for 1st Hole Drill / Deployment | 16
SC | 16
1.2.9.6.3 String: Erect Sensor Testing Tent - (ASC)
TE
1.2.9.6.4.1 String: Excavate Surface Junction Box (SJB #1) Vaults (hole side) (ASC)
SC
1.2.9.6.4.10 String: Spool Slack Cable in Pit/Trench, 4 times (UW & MSU) |  | 16
TE |  | 16
1.2.9.6.4.11 String: Connect Cables to SJB #2 x 4 (UW & MSU) |  | 8
SC |  | 8
1.2.9.6.4.12 String: Survey & Backfill Cable Trenches, 4 times (ASC & UW) |  | 8
SC |  | 8
1.2.9.6.4.2 String: Remove SJB #1 Vault Lid & Walls (ASC) |  | 8
SC |  | 8
1.2.9.6.4.3 String: Trench from Holes to SJB #2 Pits, 3 times (ASC)
TE
1.2.9.6.4.4 String: Spool Slack Cable in Pit/Trench, 3 times (UW & MSU) |  | 16
TE |  | 16
1.2.9.6.4.5 String: Connect Cables to SJB #1 x 3 (UW) |  | 112
SE |  | 112
1.2.9.6.4.6 String: Survey & Backfill Cable Trenches, 3 times (ASC & UW) |  | 48
SC |  | 48
1.2.9.6.4.7 String: Excavate Surface Junction Box (SJB #2) Vaults (hole side) (ASC & UW) |  | 8
SC |  | 8
1.2.9.6.4.8 String: Remove SJB #2 Vault Lid & Walls (ASC) |  | 16
SC |  | 16
1.2.9.6.4.9 String: Trench from Holes to SJB #2 Pit, 4 times (ASC)
SC
Grand Total | 1248 | 6002 | 5388 | 80