## Sheet1
Cargo Item respective WBS Level | Work Package | Item Description | Date of expected or actual completion | Date of expected or actual shipment | Float from article completion to transportation leg to MCM | Date/Month for Items needed at South Pole (based on assumed 7 year schedule) | Time from shipment to 'Needed at the South Pole' date (based on assumed 7 year schedule)
1.2 | Drill | Gen 1 - housed in 20' container | 2020-02-06 | Delivery to MCM complete | Delivery to MCM complete | 2023-12-01 | Shipping in process (Items awaiting last leg of shipment MCM-NPX)
1.2 | Drill | Gen 2 - housed in 20' container | 2020-01-15 |  |  | 2023-01-01
1.2 | Drill | Gen 3 - housed in 20' container | 2020-01-15 |  |  | 2022-12-01
1.2 | Drill | 287 Loader | 2019-10-15 |  |  | 2022-12-01
1.2 | Drill | Gen hoods Discharge Hoods - currently staged in McMurdo | 2019-12-15 |  |  | 2024-01-01
1.2 | Drill | Firn Drill | 2020-01-15 |  |  | 2023-12-01
1.2 | Drill | Firn Drill Components - 1 | 2020-01-15 |  |  | 2023-12-01
1.2 | Drill | Firn Drill Components - 2 | 2020-01-15 |  |  | 2023-12-01
1.2 | Drill | Weight stack and crates | 2020-01-15 |  |  | 2023-12-15
1.2 | Drill | Fuel Tower | 2020-01-15 |  |  | 2023-01-01
1.2 | Drill | HPU 1 | 2020-01-15 |  |  | 2024-01-01
Pt. Hueneme:
1.2 | Drill | Container Ski Stack (comprised of 5 sleds) - currently staged in Pt. Hueneme | 2020-12-28 | 2021-01-15 | 18 | 2022-12-15 | 699
1.2 | Drill | Generator Intake Hood - currently staged in Pt. Hueneme | 2020-10-08 | 2020-11-24 | 47 | 2024-01-01 | 1133
1.2 | Drill | Generator Discharge Hoods - currently staged in Pt. Hueneme | 2020-10-08 | 2020-11-24 | 47 | 2024-01-01 | 1133
1.2 | Drill | Drill Hose - currently staged in Pt. Hueneme | 2020-07-29 | 2020-08-15 | 17 | 2024-01-01 | 1234
1.2 | Drill | Drill Hose - currently staged in Pt. Hueneme | 2020-11-19 | 2021-01-15 | 57 | 2024-01-01 | 1081
U. Wisconsin:
1.2 | Drill | 8' Refit Container | 2021-11-02 | 2021-11-15 | 13 | 2022-11-15 | 365
1.2 | Drill | 20' Refit Container A | 2021-11-13 | 2021-11-15 | 2 | 2022-12-01 | 381
1.2 | Drill | 20' Refit Container B | 2021-11-02 | 2021-11-15 | 13 | 2022-12-15 | 395
1.2 | Drill | ARA Trailer | 2021-11-02 | 2021-11-15 | 13 | 2022-12-15 | 395
1.2 | Drill | Return Water Cable Reel (RWCR) | 2021-10-26 | 2021-11-15 | 20 | 2023-01-01 | 412
1.2 | Drill | Main Cable Reel (MCR) | 2021-11-08 | 2021-11-15 | 7 | 2023-01-01 | 412
1.2 | Drill | Controls infrastructure - Motor drives, PLCs, electrical hardware, and motor drive mounting kits | 2021-04-15 | 2022-05-01 | 381 | 2022-12-01 | 214
1.4 | Installation | ICL power and timing electronics | 2023-07-01 | 2023-08-01 | 31 | 2023-12-01 | 122
1.4 | Installation | ICL patch cables and patch panels | 2023-06-01 | 2023-08-01 | 61 | 2023-12-01 | 122
1.2 | Drill | ARA Drill System Components - Crate 1 | 2021-04-15 | 2022-05-01 | 381 | 2022-12-01 | 214
1.2 | Drill | ARA Drill System Components - Crate 2 | 2021-04-15 | 2022-05-01 | 381 | 2022-12-01 | 214
1.2 | Drill | Camp Hose - currently staged at PSL | 2021-06-11 | 2021-11-15 | 157 | 2023-12-01 | 746
1.2 | Drill | Bull wheel | 2021-12-01 | 2022-11-15 | 349 | 2024-02-01 | 443
1.2 | Drill | Load member cable reel | 2022-10-15 | 2022-11-15 | 31 | 2023-12-15 | 395
1.2 | Installation | DOM Handling Facility (DHF) | 2022-07-21 | 2022-11-15 | 117 | 2023-12-01 | 381
1.2 | Drill | Spare Combo cable | 2022-10-15 | 2022-11-15 | 31 | 2024-02-12 | 454
1.2 | Drill | Spare Drill Cable | 2022-10-15 | 2022-11-15 | 31 | 2024-02-12 | 454
1.2 | Drill | Computing/controls components | 2023-07-01 | 2023-08-01 | 31 | 2023-11-15 | 106
1.2 | Drill | Driller resupply/refit components - 8' Container | 2023-07-01 | 2023-08-01 | 31 | 2023-11-15 | 106
1.2 | Drill | Drill refit components | 2023-07-01 | 2023-08-01 | 31 | 2023-11-15 | 106
1.2 | Drill | Drill Heads DNF - X | 2021-09-01 | 2022-11-15 | 440 | 2023-02-12 | 89
1.2 | Drill | Drill Heads DNF - Y | 2021-09-01 | 2023-11-15 | 805 | 2024-02-12 | 89
1.2 | Drill | Drill Heads DNF - R | 2021-09-01 | 2023-11-15 | 805 | 2024-02-12 | 89
1.2 | Drill | Computing/controls components | 2024-07-01 | 2024-08-01 | 31 | 2024-11-15 | 106
1.2 | Installation | Installation Hardware 87-93 | 2023-07-15 | 2023-11-15 | 123 | 2024-02-15 | 92
1.2 | Installation | Installation Weights 87-93 | 2023-07-15 | 2023-11-15 | 123 | 2024-02-15 | 92
1.5 | Installation | Calibration/Special Devices 87-88 | 2022-11-30 | 2023-08-01 | 244 | 2023-12-15 | 136
1.3 | Installation | Special Devices 87-88 | 2023-01-01 | 2023-08-01 | 212 | 2023-12-15 | 136
1.2 | Installation | Misc. Science Equipment - FY24 | 2023-06-01 | 2023-08-01 | 61 | 2023-12-01 | 122
1.3 | Installation | Special Devices 89-93 | 2024-01-01 | 2024-08-01 | 213 | 2024-11-25 | 116
1.5 | Installation | Calibration/Special Devices 89-93 | 2023-08-15 | 2024-08-01 | 352 | 2024-11-25 | 116
1.2 | Installation | Misc. Science Equipment - FY25 | 2024-06-01 | 2024-08-01 | 61 | 2024-12-01 | 122
1.5 | Installation | Dust logging device | 2024-06-01 | 2024-08-01 | 61 | 2024-11-25 | 116
1.5 | Installation | Dust logging device | 2024-06-01 | 2024-08-01 | 61 | 2024-11-25 | 116
1.5 | Installation | Dust logging device | 2024-06-01 | 2024-08-01 | 61 | 2024-11-25 | 116
1.5 | Installation | Dust logging device | 2024-06-01 | 2024-08-01 | 61 | 2024-11-25 | 116
1.5 | Installation | Logging winch | 2024-06-01 | 2024-08-01 | 61 | 2024-11-25 | 116
1.5 | Installation | Logging winch control box | 2024-06-01 | 2024-08-01 | 61 | 2024-11-25 | 116
MSU:
1.4 | Installation | Surface Junction Boxes | 2022-11-01 | 2022-11-15 | 14 | 2023-12-10 | 390
1.4 | Installation | Surface Cable Assemblies | 2021-11-30 | 2022-12-01 | 366 | 2023-11-20 | 354
1.4 | Installation | Breakout cables for strings 87-88 | 2023-02-28 | 2023-04-15 | 46 | 2024-02-15 | 306
1.4 | Installation | Breakout cables for strings 89-93 | 2023-05-22 | 2023-06-15 | 24 | 2024-11-25 | 529
1.4 | Installation | Main (downhole) load members 87-93 | 2023-04-01 | 2023-04-15 | 14 | 2024-12-01 | 596
1.4 | Installation | Main (downhole) cables 87-93 | 2023-04-01 | 2023-04-15 | 14 | 2024-12-01 | 596
1.3 | Installation | String Sensors 89-93 | 2023-08-01 | 2024-08-01 | 366 | 2024-11-25 | 116
1.3 | Installation | String Sensors 89-93 | 2023-08-01 | 2024-08-01 | 366 | 2024-11-25 | 116
Other Institutions:
1.3 | Installation | DM-Ice | 2024-06-01 | 2024-08-01 | 61 | 2024-11-25 | 116
DESY/Aachen/TUM/Sweden etc :
1.3 | Installation | String Sensors 87-88 | 2023-04-01 | 2023-08-01 | 122 | 2024-01-15 | 167
1.3 | Installation | String Sensors 87-88 | 2023-04-01 | 2023-08-01 | 122 | 2024-01-15 | 167
1.3 | Installation | Special Devices 87-88 | 2023-01-01 | 2023-08-01 | 212 | 2024-01-15 | 167
1.5 | Installation | Calibration Devices 87-88 | 2022-06-01 | 2023-08-01 | 426 | 2024-01-15 | 167
1.4 | Installation | FieldHub electronics | 2023-08-01 | 2023-08-15 | 14 | 2023-12-01 | 108
1.3 | Installation | String Sensors 89-93 | 2023-07-01 | 2024-08-01 | 397 | 2024-11-25 | 116
1.3 | Installation | Special Devices 89-93 | 2024-01-01 | 2024-08-01 | 213 | 2024-11-25 | 116
1.5 | Installation | Calibration Devices 89-93 | 2022-06-01 | 2024-08-01 | 792 | 2024-11-25 | 116
Chiba:
1.3 | Installation | String Sensors 87 & 88 | 2022-06-01 | 2023-08-01 | 426 | 2024-01-15 | 167
1.3 | Installation | String Sensors 87 & 88 | 2022-06-01 | 2023-08-01 | 426 | 2024-01-15 | 167
1.3 | Installation | String Sensors 87 & 88 | 2022-06-01 | 2023-08-01 | 426 | 2024-01-15 | 167
1.3 | Installation | String Sensors 87 & 88 | 2022-06-01 | 2023-08-01 | 426 | 2024-01-15 | 167
1.3 | Installation | String Sensors 89-93 | 2023-06-01 | 2023-08-01 | 61 | 2024-11-25 | 482
1.3 | Installation | String Sensors 89-93 | 2023-06-01 | 2023-08-01 | 61 | 2024-11-25 | 482