## Cost Workbook AWP PY4
New Row | L2 | WBS | P/C | StrikeThrough | Institution | Task/Activity | Resource Name | FTE% | Type | Resource ID | M&O | BOE | Baseline Rate | Labor Rate | Fringe Rate | Start Date | End Date | Contingency | PY4 Funding | Change in Effort | Notes | 10-2021 | 11-2021 | 12-2021 | 01-2022 | 02-2022 | 03-2022 | 04-2022 | 05-2022 | 06-2022 | 07-2022 | 08-2022 | 09-2022 | S_10_21 | S_11_21 | S_12_21 | S_01_22 | S_02_22 | S_03_22 | S_04_22 | S_05_22 | S_06_22 | S_07_22 | S_08_22 | S_09_22 | 12mo Subtotal PY4 | Indirect PY4 | Indirect Subtotal PY4 | Complete Total PY4 | Diff (Total to PY4) | 10-2022 | 11-2022 | 12-2022 | 01-2023 | 02-2023 | 03-2023 | 04-2023 | 05-2023 | 06-2023 | 07-2023 | 08-2023 | 09-2023 | S_10_22 | S_11_22 | S_12_22 | S_01_23 | S_02_23 | S_03_23 | S_04_23 | S_05_23 | S_06_23 | S_07_23 | S_08_23 | S_09_23 | 12mo Subtotal PY5 | Indirect PY5 | Indirect Subtotal PY5 | Complete Total PY5 | Diff (Total to PY5) | 10-2023 | 11-2023 | 12-2023 | 01-2024 | 02-2024 | 03-2024 | 04-2024 | 05-2024 | 06-2024 | 07-2024 | 08-2024 | 09-2024 | S_10_23 | S_11_23 | S_12_23 | S_01_24 | S_02_24 | S_03_24 | S_04_24 | S_05_24 | S_06_24 | S_07_24 | S_08_24 | S_09_24 | 12mo Subtotal PY6 | Indirect PY6 | Indirect Subtotal PY6 | Complete Total PY6 | Diff (Total to PY6) | 10-2024 | 11-2024 | 12-2024 | 01-2025 | 02-2025 | 03-2025 | 04-2025 | 05-2025 | 06-2025 | 07-2025 | 08-2025 | 09-2025 | S_10_24 | S_11_24 | S_12_24 | S_01_25 | S_02_25 | S_03_25 | S_04_25 | S_05_25 | S_06_25 | S_07_25 | S_08_25 | S_09_25 | 12mo Subtotal PY7 | Indirect PY7 | Indirect Subtotal PY7 | Complete Total PY7 | PY1 | PY2 | PY3 | PY4 | PY4 Adj | PY5 | PY5 Adj | Total | Total Adj | Complete Total PY4-PY7 | Subtype | On/Off Ice | L21 | L2 Task Name | L2 namenum | L31 | L3 Task Name | L3 namenum | L4 | L4 Task Name | L4 namenum | Modified By | Modified | Predecessors | Duration | Escalation PY3 | Escalation PY4 | Escalation PY5 | Escalation PY6 | Escalation PY7 | Escalation PY8 | WBS2 | M1-PY4 | M2-PY4 | M3-PY4 | M4-PY4 | M5-PY4 | M6-PY4 | M7-PY4 | M8-PY4 | M9-PY4 | M10-PY4 | M11-PY4 | M12-PY4 | WBS05 | M1-PY5 | M2-PY5 | M3-PY5 | M4-PY5 | M5-PY5 | M6-PY5 | M7-PY5 | M8-PY5 | M9-PY5 | M10-PY5 | M11-PY5 | M12-PY5 | wbs06 | M1-PY6 | M2-PY6 | M3-PY6 | M4-PY6 | M5-PY6 | M6-PY6 | M7-PY6 | M8-PY6 | M9-PY6 | M10-PY6 | M11-PY6 | M12-PY6 | wbs07 | M1-PY7 | M2-PY7 | M3-PY7 | M4-PY7 | M5-PY7 | M6-PY7 | M7-PY7 | M8-PY7 | M9-PY7 | M10-PY7 | M11-PY7 | M12-PY7 | wbs04_Basic | Basic Cost PY4 - October 2021 | Basic Cost PY4 - November 2021 | Basic Cost PY4 - December 2021 | Basic Cost PY4 - January 2022 | Basic Cost PY4 - February 2022 | Basic Cost PY4 - March 2022 | Basic Cost PY4 - April 2022 | Basic Cost PY4 - May 2022 | Basic Cost PY4 - June 2022 | Basic Cost PY4 - July 2022 | Basic Cost PY4 - August 2022 | Basic Cost PY4 - September 2022 | Subtotal Basic PY4 1 | WBS Fringe PY4 | Fringe Cost PY4 October 2021 | Fringe Cost PY4 November 2021 | Fringe Cost PY4 December 2021 | Fringe Cost PY4 January 2022 | Fringe Cost PY4 February 2022 | Fringe Cost PY4 March 2022 | Fringe Cost PY4 April 2022 | Fringe Cost PY4 May 2022 | Fringe Cost PY4 June 2022 | Fringe Cost PY4 July 2022 | Fringe Cost PY4 August 2022 | Fringe Cost PY4 September 2022 | Subtotal Frng PY4 | WBS indirect PY4 | Indirect Cost PY4 October 2021 | Indirect Cost PY4 November 2021 | Indirect Cost PY4 December 2021 | Indirect Cost PY4 January 2022 | Indirect Cost PY4 February 2022 | Indirect Cost PY4 March 2022 | Indirect Cost PY4 April 2022 | Indirect Cost PY4 May 2022 | Indirect Cost PY4 June 2022 | Indirect Cost PY4 July 2022 | Indirect Cost PY4 August 2022 | Indirect Cost PY4 September 2022 | Subtotal Ind PY4 1 | check total | WBS 04 | TBPY4 | TBPY4tot | PV_M1 | PV_M2 | PV_M3 | PV_M4 | PV_M5 | PV_M6 | PV_M7 | PV_M8 | PV_M9 | PV_M10 | PV_M11 | PV_M12 | PV_M1_tot | PV_M2_tot | PV_M3_tot | PV_M4_tot | PV_M5_tot | PV_M6_tot | PV_M7_tot | PV_M8_tot | PV_M9_tot | PV_M10_tot | PV_M11_tot | PV_M12_tot
| 1.1 | 1.1.1.1 | C |  | UW | Project admin - interim project manager | Yeck | 0% | Labor Hours | KE |  |  | 100 | 122 | 35% | 2018-10-01 | 2025-09-26 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 76424 | 0 |  |  |  | 0 |  | 76424 |  | 0 | Labor - LoE | Off Ice | 1.1 | Project Office | 1.1 Project Office | 1.1.1 | Project Management | 1.1.1 Project Management | 1.1.1.1 | Project Administration | 1.1.1.1 Project Administration | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1564d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 501515.9615 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40662.9182 | 81612.8312 | 122562.7443 | 163512.6573 | 204462.5703 | 245412.4833 | 286362.3964 | 334962.3094 | 375912.2224 | 419616.1354 | 460566.0484 | 501515.9615
| 1.1 | 1.1.1.1 | C |  | UW | Project admin - principal investigator | Hanson | 15% | Labor Hours | KE |  |  | 100 | 103 | 35% | 2018-10-01 | 2025-09-26 |  | TRUE |  |  | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 3615.3 | 3615.3 | 3615.3 | 3615.3 | 3615.3 | 3615.3 | 3615.3 | 3615.3 | 3615.3 | 3615.3 | 3615.3 | 3615.3 | 43383.6 | 53% | 22993.308 | 69261.7978 | 4477.7978 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 3615.3 | 3615.3 | 3615.3 | 3615.3 | 3615.3 | 3615.3 | 3615.3 | 3615.3 | 3615.3 | 3615.3 | 3615.3 | 3615.3 | 43383.6 | 53% | 22993.308 | 70750.9264 | 4671.9264 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 3615.3 | 3615.3 | 3615.3 | 3615.3 | 3615.3 | 3615.3 | 3615.3 | 3615.3 | 3615.3 | 3615.3 | 3615.3 | 3615.3 | 43383.6 | 53% | 22993.308 | 72272.0713 | 72272.0713 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 3615.3 | 3615.3 | 3615.3 | 3615.3 | 3615.3 | 3615.3 | 3615.3 | 3615.3 | 3615.3 | 3615.3 | 3615.3 | 3615.3 | 43383.6 | 53% | 22993.308 | 73825.9209 | 45175 | 67021.344 | 63513 | 64784 |  | 66079 |  | 301819 |  | 286110.7164 | Labor - LoE | Off Ice | 1.1 | Project Office | 1.1 Project Office | 1.1.1 | Project Management | 1.1.1 Project Management | 1.1.1.1 | Project Administration | 1.1.1.1 Project Administration | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1564d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.1.1.1 | 5771.8165 | 5771.8165 | 5771.8165 | 5771.8165 | 5771.8165 | 5771.8165 | 5771.8165 | 5771.8165 | 5771.8165 | 5771.8165 | 5771.8165 | 5771.8165 | 1.1.1.1 | 5895.9105 | 5895.9105 | 5895.9105 | 5895.9105 | 5895.9105 | 5895.9105 | 5895.9105 | 5895.9105 | 5895.9105 | 5895.9105 | 5895.9105 | 5895.9105 | 1.1.1.1 | 6022.6726 | 6022.6726 | 6022.6726 | 6022.6726 | 6022.6726 | 6022.6726 | 6022.6726 | 6022.6726 | 6022.6726 | 6022.6726 | 6022.6726 | 6022.6726 | 1.1.1.1 | 6152.1601 | 6152.1601 | 6152.1601 | 6152.1601 | 6152.1601 | 6152.1601 | 6152.1601 | 6152.1601 | 6152.1601 | 6152.1601 | 6152.1601 | 6152.1601 | 1.1.1.1 | 2794.3919 | 2794.3919 | 2794.3919 | 2794.3919 | 2794.3919 | 2794.3919 | 2794.3919 | 2794.3919 | 2794.3919 | 2794.3919 | 2794.3919 | 2794.3919 | 33532.7029 | 1.1.1.1 | 978.0372 | 978.0372 | 978.0372 | 978.0372 | 978.0372 | 978.0372 | 978.0372 | 978.0372 | 978.0372 | 978.0372 | 978.0372 | 978.0372 | 11736.446 | 1.1.1.1 | 1999.3874 | 1999.3874 | 1999.3874 | 1999.3874 | 1999.3874 | 1999.3874 | 1999.3874 | 1999.3874 | 1999.3874 | 1999.3874 | 1999.3874 | 1999.3874 | 23992.6489 | 69261.7978 | 1.1.1.1 | 69261.7978 | 501515.9615 | 5771.8165 | 11543.633 | 17315.4494 | 23087.2659 | 28859.0824 | 34630.8989 | 40402.7154 | 46174.5318 | 51946.3483 | 57718.1648 | 63489.9813 | 69261.7978 | 40662.9182 | 81612.8312 | 122562.7443 | 163512.6573 | 204462.5703 | 245412.4833 | 286362.3964 | 334962.3094 | 375912.2224 | 419616.1354 | 460566.0484 | 501515.9615
| 1.1 | 1.1.1.1 | C |  | PSU | Project admin - Doug Cowen | Cowen | 3.462% | Labor Hours | KE |  |  | 100 | 100 | 40% | 2018-10-01 | 2025-09-26 |  | TRUE |  |  | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 840 | 840 | 840 | 840 | 840 | 840 | 840 | 840 | 840 | 840 | 840 | 840 | 10080 | 58.05% | 5851.44 | 16623.8562 | -491.1438 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 840 | 840 | 840 | 840 | 840 | 840 | 840 | 840 | 840 | 840 | 840 | 840 | 10080 | 58.05% | 5851.44 | 16981.2691 | -475.7309 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 840 | 840 | 840 | 840 | 840 | 840 | 840 | 840 | 840 | 840 | 840 | 840 | 10080 | 58.05% | 5851.44 | 17346.3664 | 17346.3664 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 840 | 840 | 840 | 840 | 840 | 840 | 840 | 840 | 840 | 840 | 840 | 840 | 10080 | 58.05% | 5851.44 | 17719.3133 | 16128 | 15931.44 | 16780 | 17115 |  | 17457 |  | 83931 |  | 68670.8051 | Labor - LoE | Off Ice | 1.1 | Project Office | 1.1 Project Office | 1.1.1 | Project Management | 1.1.1 Project Management | 1.1.1.1 | Project Administration | 1.1.1.1 Project Administration | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1564d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.1.1.1 | 1385.3214 | 1385.3214 | 1385.3214 | 1385.3214 | 1385.3214 | 1385.3214 | 1385.3214 | 1385.3214 | 1385.3214 | 1385.3214 | 1385.3214 | 1385.3214 | 1.1.1.1 | 1415.1058 | 1415.1058 | 1415.1058 | 1415.1058 | 1415.1058 | 1415.1058 | 1415.1058 | 1415.1058 | 1415.1058 | 1415.1058 | 1415.1058 | 1415.1058 | 1.1.1.1 | 1445.5305 | 1445.5305 | 1445.5305 | 1445.5305 | 1445.5305 | 1445.5305 | 1445.5305 | 1445.5305 | 1445.5305 | 1445.5305 | 1445.5305 | 1445.5305 | 1.1.1.1 | 1476.6094 | 1476.6094 | 1476.6094 | 1476.6094 | 1476.6094 | 1476.6094 | 1476.6094 | 1476.6094 | 1476.6094 | 1476.6094 | 1476.6094 | 1476.6094 | 1.1.1.1 | 626.0774 | 626.0774 | 626.0774 | 626.0774 | 626.0774 | 626.0774 | 626.0774 | 626.0774 | 626.0774 | 626.0774 | 626.0774 | 626.0774 | 7512.9282 | 1.1.1.1 | 250.4309 | 250.4309 | 250.4309 | 250.4309 | 250.4309 | 250.4309 | 250.4309 | 250.4309 | 250.4309 | 250.4309 | 250.4309 | 250.4309 | 3005.1713 | 1.1.1.1 | 508.8131 | 508.8131 | 508.8131 | 508.8131 | 508.8131 | 508.8131 | 508.8131 | 508.8131 | 508.8131 | 508.8131 | 508.8131 | 508.8131 | 6105.7567 | 16623.8562 | 1.1.1.1 | 16623.8562 | 432254.1637 | 1385.3214 | 2770.6427 | 4155.9641 | 5541.2854 | 6926.6068 | 8311.9281 | 9697.2495 | 11082.5708 | 12467.8922 | 13853.2135 | 15238.5349 | 16623.8562 | 34891.1017 | 70069.1983 | 105247.2948 | 140425.3914 | 175603.4879 | 210781.5844 | 245959.681 | 288787.7775 | 323965.8741 | 361897.9706 | 397076.0671 | 432254.1637
| 1.1 | 1.1.1.1 | C |  | UMD | Project admin - Greg Sullivan | Sullivan | 3.413% | Labor Hours | KE |  |  | 100 | 138 | 29% | 2018-10-01 | 2025-09-26 |  | TRUE |  | Added by Erik B from UMD | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 890.1 | 1068.12 | 1068.12 | 1068.12 | 1068.12 | 1068.12 | 1068.12 | 1068.12 | 1068.12 | 1068.12 | 1068.12 | 1068.12 | 12639.42 | 54.5% | 6888.4839 | 20376.6305 | 3987.6305 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 890.1 | 1068.12 | 1068.12 | 1068.12 | 1068.12 | 1068.12 | 1068.12 | 1068.12 | 1068.12 | 1068.12 | 1068.12 | 1068.12 | 12639.42 | 54.5% | 6888.4839 | 20814.7281 | 4097.7281 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 890.1 | 1068.12 | 1068.12 | 1068.12 | 1068.12 | 1068.12 | 1068.12 | 1068.12 | 1068.12 | 1068.12 | 1068.12 | 1068.12 | 12639.42 | 54.5% | 6888.4839 | 21262.2448 | 21262.2448 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 890.1 | 1068.12 | 1068.12 | 1068.12 | 1068.12 | 1068.12 | 1068.12 | 1068.12 | 1068.12 | 1068.12 | 1068.12 | 1068.12 | 12639.42 | 54.5% | 6888.4839 | 21719.383 | 15444 | 19515.9456 | 16068 | 16389 |  | 16717 |  | 80371 |  | 84172.9864 | Labor - LoE | Off Ice | 1.1 | Project Office | 1.1 Project Office | 1.1.1 | Project Management | 1.1.1 Project Management | 1.1.1.1 | Project Administration | 1.1.1.1 Project Administration | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1564d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.1.1.1 | 1434.974 | 1721.9688 | 1721.9688 | 1721.9688 | 1721.9688 | 1721.9688 | 1721.9688 | 1721.9688 | 1721.9688 | 1721.9688 | 1721.9688 | 1721.9688 | 1.1.1.1 | 1465.8259 | 1758.9911 | 1758.9911 | 1758.9911 | 1758.9911 | 1758.9911 | 1758.9911 | 1758.9911 | 1758.9911 | 1758.9911 | 1758.9911 | 1758.9911 | 1.1.1.1 | 1497.3412 | 1796.8094 | 1796.8094 | 1796.8094 | 1796.8094 | 1796.8094 | 1796.8094 | 1796.8094 | 1796.8094 | 1796.8094 | 1796.8094 | 1796.8094 | 1.1.1.1 | 1529.534 | 1835.4408 | 1835.4408 | 1835.4408 | 1835.4408 | 1835.4408 | 1835.4408 | 1835.4408 | 1835.4408 | 1835.4408 | 1835.4408 | 1835.4408 | 1.1.1.1 | 719.989 | 863.9867 | 863.9867 | 863.9867 | 863.9867 | 863.9867 | 863.9867 | 863.9867 | 863.9867 | 863.9867 | 863.9867 | 863.9867 | 10223.8431 | 1.1.1.1 | 208.7968 | 250.5562 | 250.5562 | 250.5562 | 250.5562 | 250.5562 | 250.5562 | 250.5562 | 250.5562 | 250.5562 | 250.5562 | 250.5562 | 2964.9145 | 1.1.1.1 | 506.1882 | 607.4259 | 607.4259 | 607.4259 | 607.4259 | 607.4259 | 607.4259 | 607.4259 | 607.4259 | 607.4259 | 607.4259 | 607.4259 | 7187.8729 | 20376.6305 | 1.1.1.1 | 20376.6305 | 415630.3075 | 1434.974 | 3156.9428 | 4878.9115 | 6600.8803 | 8322.8491 | 10044.8179 | 11766.7867 | 13488.7554 | 15210.7242 | 16932.693 | 18654.6618 | 20376.6305 | 33505.7804 | 67298.5556 | 101091.3308 | 134884.106 | 168676.8811 | 202469.6563 | 236262.4315 | 277705.2067 | 311497.9819 | 348044.7571 | 381837.5323 | 415630.3075
| 1.1 | 1.1.1.1 | C |  | UW | Project manager-Feyzi | Feyzi | 99.81% | Labor Hours | KE |  |  | 100 | 81 | 35% | 2018-10-01 | 2025-09-26 |  | TRUE |  |  | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 18917.55 | 18917.55 | 18917.55 | 18917.55 | 18917.55 | 18917.55 | 18917.55 | 18917.55 | 18917.55 | 18917.55 | 18917.55 | 18917.55 | 227010.6 | 53% | 120315.618 | 362421.7969 | 1063.5997 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 18917.55 | 18917.55 | 18917.55 | 18917.55 | 18917.55 | 18917.55 | 18917.55 | 18917.55 | 18917.55 | 18917.55 | 18917.55 | 18917.55 | 227010.6 | 53% | 120315.618 | 370213.8656 | 1628.5056 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 18917.55 | 18917.55 | 18917.55 | 18917.55 | 18917.55 | 18917.55 | 18917.55 | 18917.55 | 18917.55 | 18917.55 | 18917.55 | 18917.55 | 227010.6 | 53% | 120315.618 | 378173.4637 | 378173.4637 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 18917.55 | 18917.55 | 18917.55 | 18917.55 | 18917.55 | 18917.55 | 18917.55 | 18917.55 | 18917.55 | 18917.55 | 18917.55 | 18917.55 | 227010.6 | 53% | 120315.618 | 386304.1931 | 183141 | 347326.218 | 354272.7424 | 361358.1972 |  | 368585.36 |  | 1723005 |  | 1497113.3193 | Labor - LoE | Off Ice | 1.1 | Project Office | 1.1 Project Office | 1.1.1 | Project Management | 1.1.1 Project Management | 1.1.1.1 | Project Administration | 1.1.1.1 Project Administration | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1564d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.1.1.1 | 30201.8164 | 30201.8164 | 30201.8164 | 30201.8164 | 30201.8164 | 30201.8164 | 30201.8164 | 30201.8164 | 30201.8164 | 30201.8164 | 30201.8164 | 30201.8164 | 1.1.1.1 | 30851.1555 | 30851.1555 | 30851.1555 | 30851.1555 | 30851.1555 | 30851.1555 | 30851.1555 | 30851.1555 | 30851.1555 | 30851.1555 | 30851.1555 | 30851.1555 | 1.1.1.1 | 31514.4553 | 31514.4553 | 31514.4553 | 31514.4553 | 31514.4553 | 31514.4553 | 31514.4553 | 31514.4553 | 31514.4553 | 31514.4553 | 31514.4553 | 31514.4553 | 1.1.1.1 | 32192.0161 | 32192.0161 | 32192.0161 | 32192.0161 | 32192.0161 | 32192.0161 | 32192.0161 | 32192.0161 | 32192.0161 | 32192.0161 | 32192.0161 | 32192.0161 | 1.1.1.1 | 14622.0365 | 14622.0365 | 14622.0365 | 14622.0365 | 14622.0365 | 14622.0365 | 14622.0365 | 14622.0365 | 14622.0365 | 14622.0365 | 14622.0365 | 14622.0365 | 175464.4381 | 1.1.1.1 | 5117.7128 | 5117.7128 | 5117.7128 | 5117.7128 | 5117.7128 | 5117.7128 | 5117.7128 | 5117.7128 | 5117.7128 | 5117.7128 | 5117.7128 | 5117.7128 | 61412.5533 | 1.1.1.1 | 10462.0671 | 10462.0671 | 10462.0671 | 10462.0671 | 10462.0671 | 10462.0671 | 10462.0671 | 10462.0671 | 10462.0671 | 10462.0671 | 10462.0671 | 10462.0671 | 125544.8055 | 362421.7969 | 1.1.1.1 | 362421.7969 | 395253.6769 | 30201.8164 | 60403.6328 | 90605.4492 | 120807.2656 | 151009.082 | 181210.8985 | 211412.7149 | 241614.5313 | 271816.3477 | 302018.1641 | 332219.9805 | 362421.7969 | 32070.8064 | 64141.6128 | 96212.4192 | 128283.2256 | 160354.032 | 192424.8385 | 224495.6449 | 264216.4513 | 296287.2577 | 331112.0641 | 363182.8705 | 395253.6769
| 1.1 | 1.1.1.1 | C |  | UW | Admin M&S - IT Support |  |  | M & S |  |  |  | 1 | 1 | 0% | 2018-10-01 | 2025-09-26 |  | TRUE |  |  | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 5040 | 53% | 2671.2 | 7711.2 | 61.2 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 5040 | 53% | 2671.2 | 7711.2 | 7711.2 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 5040 | 53% | 2671.2 | 7711.2 | 7711.2 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 5040 | 53% | 2671.2 | 7711.2 |  | 7711.2 |  | 7650 |  | 0 |  | 15300 |  | 30844.8 | M & S | Off Ice | 1.1 | Project Office | 1.1 Project Office | 1.1.1 | Project Management | 1.1.1 Project Management | 1.1.1.1 | Project Administration | 1.1.1.1 Project Administration | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1564d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.1.1.1 | 642.6 | 642.6 | 642.6 | 642.6 | 642.6 | 642.6 | 642.6 | 642.6 | 642.6 | 642.6 | 642.6 | 642.6 | 1.1.1.1 | 642.6 | 642.6 | 642.6 | 642.6 | 642.6 | 642.6 | 642.6 | 642.6 | 642.6 | 642.6 | 642.6 | 642.6 | 1.1.1.1 | 642.6 | 642.6 | 642.6 | 642.6 | 642.6 | 642.6 | 642.6 | 642.6 | 642.6 | 642.6 | 642.6 | 642.6 | 1.1.1.1 | 642.6 | 642.6 | 642.6 | 642.6 | 642.6 | 642.6 | 642.6 | 642.6 | 642.6 | 642.6 | 642.6 | 642.6 | 1.1.1.1 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 5040 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 222.6 | 222.6 | 222.6 | 222.6 | 222.6 | 222.6 | 222.6 | 222.6 | 222.6 | 222.6 | 222.6 | 222.6 | 2671.2 | 7711.2 | 1.1.1.1 | 7711.2 | 32831.88 | 642.6 | 1285.2 | 1927.8 | 2570.4 | 3213 | 3855.6 | 4498.2 | 5140.8 | 5783.4 | 6426 | 7068.6 | 7711.2 | 1868.99 | 3737.98 | 5606.97 | 7475.96 | 9344.95 | 11213.94 | 13082.93 | 22601.92 | 24470.91 | 29093.9 | 30962.89 | 32831.88
| 1.1 | 1.1.1.1 | C |  | PSU | Admin M&S - IT Support |  |  | M & S |  |  |  | 1 | 1 | 0% | 2018-10-01 | 2025-09-26 |  | TRUE |  |  | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 4560 | 58.05% | 2647.08 | 7207.08 | 7.08 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 4560 | 58.05% | 2647.08 | 7207.08 | 7207.08 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 4560 | 58.05% | 2647.08 | 7207.08 | 7207.08 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 4560 | 58.05% | 2647.08 | 7207.08 |  | 7207.08 |  | 7200 |  | 0 |  | 14400 |  | 28828.32 | M & S | Off Ice | 1.1 | Project Office | 1.1 Project Office | 1.1.1 | Project Management | 1.1.1 Project Management | 1.1.1.1 | Project Administration | 1.1.1.1 Project Administration | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1564d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.1.1.1 | 600.59 | 600.59 | 600.59 | 600.59 | 600.59 | 600.59 | 600.59 | 600.59 | 600.59 | 600.59 | 600.59 | 600.59 | 1.1.1.1 | 600.59 | 600.59 | 600.59 | 600.59 | 600.59 | 600.59 | 600.59 | 600.59 | 600.59 | 600.59 | 600.59 | 600.59 | 1.1.1.1 | 600.59 | 600.59 | 600.59 | 600.59 | 600.59 | 600.59 | 600.59 | 600.59 | 600.59 | 600.59 | 600.59 | 600.59 | 1.1.1.1 | 600.59 | 600.59 | 600.59 | 600.59 | 600.59 | 600.59 | 600.59 | 600.59 | 600.59 | 600.59 | 600.59 | 600.59 | 1.1.1.1 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 4560 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 220.59 | 220.59 | 220.59 | 220.59 | 220.59 | 220.59 | 220.59 | 220.59 | 220.59 | 220.59 | 220.59 | 220.59 | 2647.08 | 7207.08 | 1.1.1.1 | 7207.08 | 25120.68 | 600.59 | 1201.18 | 1801.77 | 2402.36 | 3002.95 | 3603.54 | 4204.13 | 4804.72 | 5405.31 | 6005.9 | 6606.49 | 7207.08 | 1226.39 | 2452.78 | 3679.17 | 4905.56 | 6131.95 | 7358.34 | 8584.73 | 17461.12 | 18687.51 | 22667.9 | 23894.29 | 25120.68
| 1.1 | 1.1.1.1 | C |  | UA | Admin M&S - IT Support |  |  | M & S |  |  |  | 1 | 1 | 0% | 2018-10-01 | 2025-09-26 |  | TRUE |  |  | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 5040 | 49% | 2469.6 | 7509.6 | 9.6 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 5040 | 49% | 2469.6 | 7509.6 | 7509.6 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 5040 | 49% | 2469.6 | 7509.6 | 7509.6 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 5040 | 49% | 2469.6 | 7509.6 |  | 7509.6 |  | 7500 |  | 0 |  | 15000 |  | 30038.4 | M & S | Off Ice | 1.1 | Project Office | 1.1 Project Office | 1.1.1 | Project Management | 1.1.1 Project Management | 1.1.1.1 | Project Administration | 1.1.1.1 Project Administration | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1564d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.1.1.1 | 625.8 | 625.8 | 625.8 | 625.8 | 625.8 | 625.8 | 625.8 | 625.8 | 625.8 | 625.8 | 625.8 | 625.8 | 1.1.1.1 | 625.8 | 625.8 | 625.8 | 625.8 | 625.8 | 625.8 | 625.8 | 625.8 | 625.8 | 625.8 | 625.8 | 625.8 | 1.1.1.1 | 625.8 | 625.8 | 625.8 | 625.8 | 625.8 | 625.8 | 625.8 | 625.8 | 625.8 | 625.8 | 625.8 | 625.8 | 1.1.1.1 | 625.8 | 625.8 | 625.8 | 625.8 | 625.8 | 625.8 | 625.8 | 625.8 | 625.8 | 625.8 | 625.8 | 625.8 | 1.1.1.1 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 5040 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 205.8 | 205.8 | 205.8 | 205.8 | 205.8 | 205.8 | 205.8 | 205.8 | 205.8 | 205.8 | 205.8 | 205.8 | 2469.6 | 7509.6 | 1.1.1.1 | 7509.6 | 17913.6 | 625.8 | 1251.6 | 1877.4 | 2503.2 | 3129 | 3754.8 | 4380.6 | 5006.4 | 5632.2 | 6258 | 6883.8 | 7509.6 | 625.8 | 1251.6 | 1877.4 | 2503.2 | 3129 | 3754.8 | 4380.6 | 12656.4 | 13282.2 | 16662 | 17287.8 | 17913.6
| 1.1 | 1.1.1.1 | C |  | PSU | Project Advisory Panel Reviews - PSU |  |  | Travel |  |  |  | 1 | 1 | 0% | 2018-10-01 | 2025-09-26 |  | TRUE |  |  |  |  | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | -2751 |  |  | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | -2806 |  |  | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 |  |  | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 |  | 2844.9 | 2697 | 2751 |  | 2806 |  | 10897 |  | 0 | Travel | Off Ice | 1.1 | Project Office | 1.1 Project Office | 1.1.1 | Project Management | 1.1.1 Project Management | 1.1.1.1 | Project Administration | 1.1.1.1 Project Administration | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1564d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 10404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7650 | 7650 | 10404 | 10404 | 10404
| 1.1 | 1.1.1.1 | C |  | UA | Project Advisory Panel Reviews - UA |  |  | Travel |  |  |  | 1 | 1 | 0% | 2018-10-01 | 2025-09-26 |  | TRUE |  |  |  |  | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49% | 0 | 0 | -2865 |  |  | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49% | 0 | 0 | -2923 |  |  | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49% | 0 | 0 | 0 |  |  | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49% | 0 | 0 |  | 2682 | 2809 | 2865 |  | 2923 |  | 11351 |  | 0 | Travel | Off Ice | 1.1 | Project Office | 1.1 Project Office | 1.1.1 | Project Management | 1.1.1 Project Management | 1.1.1.1 | Project Administration | 1.1.1.1 Project Administration | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1564d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 10404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7650 | 7650 | 10404 | 10404 | 10404
| 1.1 | 1.1.1.1 | C |  | UMD | Project Advisory Panel Reviews - UMD |  |  | Travel |  |  |  | 1 | 1 | 0% | 2018-10-01 | 2025-09-26 |  | TRUE |  |  |  |  | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54.5% | 0 | 0 | -2837 |  |  | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54.5% | 0 | 0 | -2893 |  |  | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54.5% | 0 | 0 | 0 |  |  | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54.5% | 0 | 0 |  | 2781 | 2781 | 2837 |  | 2893 |  | 11237 |  | 0 | Travel | Off Ice | 1.1 | Project Office | 1.1 Project Office | 1.1.1 | Project Management | 1.1.1 Project Management | 1.1.1.1 | Project Administration | 1.1.1.1 Project Administration | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1564d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 10404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7650 | 7650 | 10404 | 10404 | 10404
| 1.1 | 1.1.1.1 | C |  | UW | Project Advisory Panel Reviews - Panel Members |  |  | Travel |  |  |  | 1 | 1 | 0% | 2018-10-01 | 2025-09-26 |  | TRUE |  |  |  |  | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | -11690 |  |  | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | -11924 |  |  | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 |  |  | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 11169 | 11461 | 11690 |  | 11924 |  | 46312 |  | 0 | Travel | Off Ice | 1.1 | Project Office | 1.1 Project Office | 1.1.1 | Project Management | 1.1.1 Project Management | 1.1.1.1 | Project Administration | 1.1.1.1 Project Administration | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1564d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 10404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7650 | 7650 | 10404 | 10404 | 10404
| 1.1 | 1.1.1.1 | C |  | UW | Collaboration Meeting Travel - PM |  |  | Travel |  |  |  | 1 | 1 | 0% | 2018-10-01 | 2025-09-26 |  | TRUE | [9 empty] | 3200 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3200 | 0 | 0 | 0 | 0 | 3200 | 53% | 1696 | 4896 | -3709 | [7 empty] | 3200 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3200 | 0 | 0 | 0 | 0 | 3200 | 53% | 1696 | 4896 | -3881 | [7 empty] | 3200 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3200 | 0 | 0 | 0 | 0 | 3200 | 53% | 1696 | 4896 | 4896 | [7 empty] | 3200 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3200 | 0 | 0 | 0 | 0 | 3200 | 53% | 1696 | 4896 |  | 4896 | 8437 | 8605 |  | 8777 |  | 34091 |  | 19584 | Travel | Off Ice | 1.1 | Project Office | 1.1 Project Office | 1.1.1 | Project Management | 1.1.1 Project Management | 1.1.1.1 | Project Administration | 1.1.1.1 Project Administration | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1564d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4896 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4896 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4896 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4896 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3200 | 0 | 0 | 0 | 0 | 3200 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1696 | 0 | 0 | 0 | 0 | 1696 | 4896 | 1.1.1.1 | 4896 | 10404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4896 | 4896 | 4896 | 4896 | 4896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7650 | 7650 | 10404 | 10404 | 10404
| 1.1 | 1.1.1.1 | C |  | PSU | Technical Review - PSU |  |  | Travel |  |  |  | 1 | 1 | 0% | 2018-10-01 | 2025-09-26 |  | TRUE | [7 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | -2751 | [5 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | -2806 | [5 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [5 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 |  | 2844.9 | 2697 | 2751 |  | 2806 |  | 10897 |  | 0 | Travel | Off Ice | 1.1 | Project Office | 1.1 Project Office | 1.1.1 | Project Management | 1.1.1 Project Management | 1.1.1.1 | Project Administration | 1.1.1.1 Project Administration | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1564d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 5508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2754 | 2754 | 5508 | 5508 | 5508
| 1.1 | 1.1.1.1 | C |  | UA | Technical Review - UA |  |  | Travel |  |  |  | 1 | 1 | 0% | 2018-10-01 | 2025-09-26 |  | TRUE | [7 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49% | 0 | 0 | -2865 | [5 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49% | 0 | 0 | -2923 | [5 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49% | 0 | 0 | 0 | [5 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49% | 0 | 0 |  | 2682 | 2809 | 2865 |  | 2923 |  | 11351 |  | 0 | Travel | Off Ice | 1.1 | Project Office | 1.1 Project Office | 1.1.1 | Project Management | 1.1.1 Project Management | 1.1.1.1 | Project Administration | 1.1.1.1 Project Administration | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1564d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 5508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2754 | 2754 | 5508 | 5508 | 5508
| 1.1 | 1.1.1.1 | C |  | UMD | Technical Review - UMD |  |  | Travel |  |  |  | 1 | 1 | 0% | 2018-10-01 | 2025-09-26 |  | TRUE | [7 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54.5% | 0 | 0 | -2837 | [5 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54.5% | 0 | 0 | -2893 | [5 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54.5% | 0 | 0 | 0 | [5 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54.5% | 0 | 0 |  | 2781 | 2781 | 2837 |  | 2893 |  | 11237 |  | 0 | Travel | Off Ice | 1.1 | Project Office | 1.1 Project Office | 1.1.1 | Project Management | 1.1.1 Project Management | 1.1.1.1 | Project Administration | 1.1.1.1 Project Administration | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1564d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 5508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2754 | 2754 | 5508 | 5508 | 5508
| 1.1 | 1.1.1.1 | C |  | UW | Technical Review - PM |  |  | Travel |  |  |  | 1 | 1 | 0% | 2018-10-01 | 2025-09-26 |  | TRUE |  | Feyzi |  |  |  | 0 |  | 0 |  | 1800 |  | 1800 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 1800 | 0 | 0 | 3600 | 53% | 1908 | 5508 | 2585 |  |  |  | 0 |  | 0 |  | 1800 |  | 1800 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 1800 | 0 | 0 | 3600 | 53% | 1908 | 5508 | 2527 |  |  |  | 0 |  | 0 |  | 1800 |  | 1800 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 1800 | 0 | 0 | 3600 | 53% | 1908 | 5508 | 5508 |  |  |  | 0 |  | 0 |  | 1800 |  | 1800 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 1800 | 0 | 0 | 3600 | 53% | 1908 | 5508 |  | 13158 | 2865 | 2923 |  | 2981 |  | 11578 |  | 22032 | Travel | Off Ice | 1.1 | Project Office | 1.1 Project Office | 1.1.1 | Project Management | 1.1.1 Project Management | 1.1.1.1 | Project Administration | 1.1.1.1 Project Administration | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1564d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2754 | 0 | 2754 | 0 | 0 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2754 | 0 | 2754 | 0 | 0 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2754 | 0 | 2754 | 0 | 0 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2754 | 0 | 2754 | 0 | 0 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 1800 | 0 | 0 | 3600 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 954 | 0 | 954 | 0 | 0 | 1908 | 5508 | 1.1.1.1 | 5508 | 5508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2754 | 2754 | 5508 | 5508 | 5508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2754 | 2754 | 5508 | 5508 | 5508
| 1.1 | 1.1.1.1 | C |  | PSL | Drill Advisory Panel, March 2020 |  |  | Travel |  |  |  |  | 1 | 0% | 2018-10-01 | 2025-09-26 |  | TRUE |  | 5-panel members (1-intl, 2-domestic, 2 local), 3 require some form of payment ~$1,000 each 1 x $3,500 - International travel = $3,500 2 x $1,800 - Domestic travel = $3,600 3 x $1,000 - Compensation = $3,000 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 15453 |  |  |  | 0 |  |  |  | 0 | Travel | Off Ice | 1.1 | Project Office | 1.1 Project Office | 1.1.1 | Project Management | 1.1.1 Project Management | 1.1.1.1 | Project Administration | 1.1.1.1 Project Administration | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.1 | 1.1.1.1 | C |  | PSL | Drill Advisory Panel, March 2021 |  |  | Travel |  |  |  |  | 1 | 0% | 2018-10-01 | 2025-09-26 |  | TRUE |  | 5-panel members (1-intl, 2-domestic, 2 local), 3 require some form of payment ~$1,000 each 1 x $3,500 - International travel = $3,500 2 x $1,800 - Domestic travel = $3,600 3 x $1,000 - Compensation = $3,000 | [5 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [5 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [5 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [5 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 | 10100 |  |  | 0 |  |  |  | 0 | Travel | Off Ice | 1.1 | Project Office | 1.1 Project Office | 1.1.1 | Project Management | 1.1.1 Project Management | 1.1.1.1 | Project Administration | 1.1.1.1 Project Administration | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.1 | 1.1.1.1 | C |  | PSL | Drill Advisory Panel, March 2022 |  |  | Travel |  |  |  |  | 1 | 0% | 2018-10-01 | 2025-09-26 |  | TRUE |  | 5-panel members (1-intl, 2-domestic, 2 local), 3 require some form of payment ~$1,000 each 1 x $3,500 - International travel = $3,500 2 x $1,800 - Domestic travel = $3,600 3 x $1,000 - Compensation = $3,000 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | -10100 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 |  | 10100 |  | 0 |  |  |  | 0 | Travel | Off Ice | 1.1 | Project Office | 1.1 Project Office | 1.1.1 | Project Management | 1.1.1 Project Management | 1.1.1.1 | Project Administration | 1.1.1.1 Project Administration | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.1 | 1.1.1.1 | C |  | UW | PMCS M&S - IT Support |  |  | M & S |  |  |  | 1 | 1 | 0% | 2018-10-01 | 2025-09-26 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | -3825 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 3825 | 0 |  | 3825 |  | 0 |  | 7650 |  | 0 | M & S | Off Ice | 1.1 | Project Office | 1.1 Project Office | 1.1.1 | Project Management | 1.1.1 Project Management | 1.1.1.1 | Project Administration | 1.1.1.1 Project Administration | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1564d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.1 | 1.1.1.1 | C |  | UW | PMCS M&S - IT Support |  |  | M & S |  |  |  | 1 | 1 | 0% | 2018-10-01 | 2025-09-26 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | -3825 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 3825 | 0 |  | 3825 |  | 0 |  | 7650 |  | 0 | M & S | Off Ice | 1.1 | Project Office | 1.1 Project Office | 1.1.1 | Project Management | 1.1.1 Project Management | 1.1.1.1 | Project Administration | 1.1.1.1 Project Administration | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1564d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.1 | 1.1.1.1 | C |  | UW | Collaboration Meetings |  |  | Travel |  |  |  | 1 | 1 | 0% | 2018-10-01 | 2025-09-26 |  | TRUE |  | Haugen, Sandstrom, added for foreign trips | [7 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | -8605 | [7 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | -8777 | [7 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [7 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 5355 | 9792 | 8437 | 8605 |  | 8777 |  | 39446 |  | 0 | Travel | Off Ice | 1.1 | Project Office | 1.1 Project Office | 1.1.1 | Project Management | 1.1.1 Project Management | 1.1.1.1 | Project Administration | 1.1.1.1 Project Administration | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1564d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.1 | 1.1.2.1 | P |  | UW | PMCS - Catherine Vakhnina | Vakhnina | 39.81% | Labor Hours | MA |  |  | 55 | 37 | 35% | 2018-10-01 | 2025-09-05 |  | TRUE |  |  | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 3446.55 | 3446.55 | 3446.55 | 3446.55 | 3446.55 | 3446.55 | 3446.55 | 3446.55 | 3446.55 | 3446.55 | 3446.55 | 3446.55 | 41358.6 | 53% | 21920.058 | 66028.8909 | -19224.1028 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 3446.55 | 3446.55 | 3446.55 | 3446.55 | 3446.55 | 3446.55 | 3446.55 | 3446.55 | 3446.55 | 3446.55 | 3446.55 | 3446.55 | 41358.6 | 53% | 21920.058 | 67448.512 | -19509.538 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 3446.55 | 3446.55 | 3446.55 | 3446.55 | 3446.55 | 3446.55 | 3446.55 | 3446.55 | 3446.55 | 3446.55 | 3446.55 | 3446.55 | 41358.6 | 53% | 21920.058 | 68898.655 | 68898.655 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 3446.55 | 3446.55 | 3446.55 | 3446.55 | 3446.55 | 3446.55 | 3446.55 | 3446.55 | 3446.55 | 3446.55 | 3446.55 | 3446.55 | 41358.6 | 53% | 21920.058 | 70379.9761 | 100728 | 81942.516 | 83581.3663 | 85252.9936 |  | 86958.05 |  | 524190 |  | 272756.034 | Labor - LoE | Off Ice | 1.1 | Project Office | 1.1 Project Office | 1.1.2 | Project Controls | 1.1.2 Project Controls | 1.1.2.1 | EVMS | 1.1.2.1 EVMS | cell-link@smartsheet.com | 2021-11-30 13:41 |  | 1544d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.1.2.1 | 5502.4076 | 5502.4076 | 5502.4076 | 5502.4076 | 5502.4076 | 5502.4076 | 5502.4076 | 5502.4076 | 5502.4076 | 5502.4076 | 5502.4076 | 5502.4076 | 1.1.2.1 | 5620.7093 | 5620.7093 | 5620.7093 | 5620.7093 | 5620.7093 | 5620.7093 | 5620.7093 | 5620.7093 | 5620.7093 | 5620.7093 | 5620.7093 | 5620.7093 | 1.1.2.1 | 5741.5546 | 5741.5546 | 5741.5546 | 5741.5546 | 5741.5546 | 5741.5546 | 5741.5546 | 5741.5546 | 5741.5546 | 5741.5546 | 5741.5546 | 5741.5546 | 1.1.2.1 | 5864.998 | 5864.998 | 5864.998 | 5864.998 | 5864.998 | 5864.998 | 5864.998 | 5864.998 | 5864.998 | 5864.998 | 5864.998 | 5864.998 | 1.1.2.1 | 2663.9591 | 2663.9591 | 2663.9591 | 2663.9591 | 2663.9591 | 2663.9591 | 2663.9591 | 2663.9591 | 2663.9591 | 2663.9591 | 2663.9591 | 2663.9591 | 31967.5095 | 1.1.2.1 | 932.3857 | 932.3857 | 932.3857 | 932.3857 | 932.3857 | 932.3857 | 932.3857 | 932.3857 | 932.3857 | 932.3857 | 932.3857 | 932.3857 | 11188.6283 | 1.1.2.1 | 1906.0628 | 1906.0628 | 1906.0628 | 1906.0628 | 1906.0628 | 1906.0628 | 1906.0628 | 1906.0628 | 1906.0628 | 1906.0628 | 1906.0628 | 1906.0628 | 22872.753 | 66028.8909 | 1.1.2.1 | 66028.8909 | 227526.9019 | 5502.4076 | 11004.8151 | 16507.2227 | 22009.6303 | 27512.0379 | 33014.4454 | 38516.853 | 44019.2606 | 49521.6681 | 55024.0757 | 60526.4833 | 66028.8909 | 18552.5752 | 37105.1503 | 55657.7255 | 74210.3006 | 92762.8758 | 111315.4509 | 129868.0261 | 153316.6012 | 171869.1764 | 190421.7516 | 208974.3267 | 227526.9019
| 1.1 | 1.1.2.1 | P |  | UW | Project Controls-Rogal | Rogal | 99.81% | Labor Hours | MA |  |  |  | 35 | 35% | 2018-10-01 | 2025-09-05 |  | TRUE |  | Rogal | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 8174.25 | 8174.25 | 8174.25 | 8174.25 | 8174.25 | 8174.25 | 8174.25 | 8174.25 | 8174.25 | 8174.25 | 8174.25 | 8174.25 | 98091 | 53% | 51988.23 | 156602.011 | 459.5801 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 8174.25 | 8174.25 | 8174.25 | 8174.25 | 8174.25 | 8174.25 | 8174.25 | 8174.25 | 8174.25 | 8174.25 | 8174.25 | 8174.25 | 98091 | 53% | 51988.23 | 159968.9543 | 703.6743 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 8174.25 | 8174.25 | 8174.25 | 8174.25 | 8174.25 | 8174.25 | 8174.25 | 8174.25 | 8174.25 | 8174.25 | 8174.25 | 8174.25 | 98091 | 53% | 51988.23 | 163408.2868 | 163408.2868 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 8174.25 | 8174.25 | 8174.25 | 8174.25 | 8174.25 | 8174.25 | 8174.25 | 8174.25 | 8174.25 | 8174.25 | 8174.25 | 8174.25 | 98091 | 53% | 51988.23 | 166921.5649 |  | 150079.23 | 153080.8146 | 156142.4309 |  | 159265.28 |  |  |  | 646900.817 | Labor - LoE | Off Ice | 1.1 | Project Office | 1.1 Project Office | 1.1.2 | Project Controls | 1.1.2 Project Controls | 1.1.2.1 | EVMS | 1.1.2.1 EVMS | cell-link@smartsheet.com | 2021-11-30 13:41 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.1.2.1 | 13050.1676 | 13050.1676 | 13050.1676 | 13050.1676 | 13050.1676 | 13050.1676 | 13050.1676 | 13050.1676 | 13050.1676 | 13050.1676 | 13050.1676 | 13050.1676 | 1.1.2.1 | 13330.7462 | 13330.7462 | 13330.7462 | 13330.7462 | 13330.7462 | 13330.7462 | 13330.7462 | 13330.7462 | 13330.7462 | 13330.7462 | 13330.7462 | 13330.7462 | 1.1.2.1 | 13617.3572 | 13617.3572 | 13617.3572 | 13617.3572 | 13617.3572 | 13617.3572 | 13617.3572 | 13617.3572 | 13617.3572 | 13617.3572 | 13617.3572 | 13617.3572 | 1.1.2.1 | 13910.1304 | 13910.1304 | 13910.1304 | 13910.1304 | 13910.1304 | 13910.1304 | 13910.1304 | 13910.1304 | 13910.1304 | 13910.1304 | 13910.1304 | 13910.1304 | 1.1.2.1 | 6318.1639 | 6318.1639 | 6318.1639 | 6318.1639 | 6318.1639 | 6318.1639 | 6318.1639 | 6318.1639 | 6318.1639 | 6318.1639 | 6318.1639 | 6318.1639 | 75817.9671 | 1.1.2.1 | 2211.3574 | 2211.3574 | 2211.3574 | 2211.3574 | 2211.3574 | 2211.3574 | 2211.3574 | 2211.3574 | 2211.3574 | 2211.3574 | 2211.3574 | 2211.3574 | 26536.2885 | 1.1.2.1 | 4520.6463 | 4520.6463 | 4520.6463 | 4520.6463 | 4520.6463 | 4520.6463 | 4520.6463 | 4520.6463 | 4520.6463 | 4520.6463 | 4520.6463 | 4520.6463 | 54247.7554 | 156602.011 | 1.1.2.1 | 156602.011 | 161498.011 | 13050.1676 | 26100.3352 | 39150.5028 | 52200.6703 | 65250.8379 | 78301.0055 | 91351.1731 | 104401.3407 | 117451.5083 | 130501.6758 | 143551.8434 | 156602.011 | 13050.1676 | 26100.3352 | 39150.5028 | 52200.6703 | 65250.8379 | 78301.0055 | 91351.1731 | 109297.3407 | 122347.5083 | 135397.6758 | 148447.8434 | 161498.011
| 1.1 | 1.1.2.1 | P |  | UW | Foreign Collaboration Meetings |  |  | Travel |  |  |  | 1 | 1 | 0% | 2018-10-01 | 2025-09-05 |  | TRUE |  | Vakhnina, added for foreign trip | [7 empty] | 3200 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3200 | 0 | 0 | 0 | 0 | 3200 | 53% | 1696 | 4896 | -787 | [7 empty] | 3200 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3200 | 0 | 0 | 0 | 0 | 3200 | 53% | 1696 | 4896 | -900 | [7 empty] | 3200 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3200 | 0 | 0 | 0 | 0 | 3200 | 53% | 1696 | 4896 | 4896 | [7 empty] | 3200 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3200 | 0 | 0 | 0 | 0 | 3200 | 53% | 1696 | 4896 | 5355 | 4896 | 5571 | 5683 |  | 5796 |  | 27868 |  | 19584 | Travel | Off Ice | 1.1 | Project Office | 1.1 Project Office | 1.1.2 | Project Controls | 1.1.2 Project Controls | 1.1.2.1 | EVMS | 1.1.2.1 EVMS | cell-link@smartsheet.com | 2021-11-30 13:41 |  | 1544d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.1.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4896 | 0 | 0 | 0 | 0 | 1.1.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4896 | 0 | 0 | 0 | 0 | 1.1.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4896 | 0 | 0 | 0 | 0 | 1.1.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4896 | 0 | 0 | 0 | 0 | 1.1.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3200 | 0 | 0 | 0 | 0 | 3200 | 1.1.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1696 | 0 | 0 | 0 | 0 | 1696 | 4896 | 1.1.2.1 | 4896 | 4896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4896 | 4896 | 4896 | 4896 | 4896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4896 | 4896 | 4896 | 4896 | 4896
| 1.1 | 1.1.2.1 | P |  | UW | US Collaboration Meetings |  |  | Travel |  |  |  | 1 | 1 | 0% | 2018-10-01 | 2025-09-05 |  | TRUE |  | None in PY2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | -2923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | -2981 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 | 2865 | 2923 |  | 2981 |  | 11578 |  | 0 | Travel | Off Ice | 1.1 | Project Office | 1.1 Project Office | 1.1.2 | Project Controls | 1.1.2 Project Controls | 1.1.2.1 | EVMS | 1.1.2.1 EVMS | cell-link@smartsheet.com | 2021-11-30 13:41 |  | 1544d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.1.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.1 | 1.1.3.1 | C |  | UW | Q&A / Safety - Zernick | Zernick | 75% | Labor Hours | MA |  |  | 55 | 49 | 35% | 2018-10-01 | 2025-09-26 |  | TRUE |  |  | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 8599.5 | 8599.5 | 8599.5 | 8599.5 | 8599.5 | 8599.5 | 8599.5 | 8599.5 | 8599.5 | 8599.5 | 8599.5 | 8599.5 | 103194 | 53% | 54692.82 | 164748.9364 | -2868.8672 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 8599.5 | 8599.5 | 8599.5 | 8599.5 | 8599.5 | 8599.5 | 8599.5 | 8599.5 | 8599.5 | 8599.5 | 8599.5 | 8599.5 | 103194 | 53% | 54692.82 | 168291.0386 | -2679.1214 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 8599.5 | 8599.5 | 8599.5 | 8599.5 | 8599.5 | 8599.5 | 8599.5 | 8599.5 | 8599.5 | 8599.5 | 8599.5 | 8599.5 | 103194 | 53% | 54692.82 | 171909.2959 | 171909.2959 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 8599.5 | 8599.5 | 8599.5 | 8599.5 | 8599.5 | 8599.5 | 8599.5 | 8599.5 | 8599.5 | 8599.5 | 8599.5 | 8599.5 | 103194 | 53% | 54692.82 | 175605.3458 | 49245 | 161109 | 164331.18 | 167617.8036 |  | 170970.16 |  | 260976 |  | 680554.6167 | Labor - LoE | Off Ice | 1.1 | Project Office | 1.1 Project Office | 1.1.3 | Quality and Safety | 1.1.3 Quality and Safety | 1.1.3.1 | Risk Management | 1.1.3.1 Risk Management | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1564d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.1.3.1 | 13729.078 | 13729.078 | 13729.078 | 13729.078 | 13729.078 | 13729.078 | 13729.078 | 13729.078 | 13729.078 | 13729.078 | 13729.078 | 13729.078 | 1.1.3.1 | 14024.2532 | 14024.2532 | 14024.2532 | 14024.2532 | 14024.2532 | 14024.2532 | 14024.2532 | 14024.2532 | 14024.2532 | 14024.2532 | 14024.2532 | 14024.2532 | 1.1.3.1 | 14325.7747 | 14325.7747 | 14325.7747 | 14325.7747 | 14325.7747 | 14325.7747 | 14325.7747 | 14325.7747 | 14325.7747 | 14325.7747 | 14325.7747 | 14325.7747 | 1.1.3.1 | 14633.7788 | 14633.7788 | 14633.7788 | 14633.7788 | 14633.7788 | 14633.7788 | 14633.7788 | 14633.7788 | 14633.7788 | 14633.7788 | 14633.7788 | 14633.7788 | 1.1.3.1 | 6646.8545 | 6646.8545 | 6646.8545 | 6646.8545 | 6646.8545 | 6646.8545 | 6646.8545 | 6646.8545 | 6646.8545 | 6646.8545 | 6646.8545 | 6646.8545 | 79762.2544 | 1.1.3.1 | 2326.3991 | 2326.3991 | 2326.3991 | 2326.3991 | 2326.3991 | 2326.3991 | 2326.3991 | 2326.3991 | 2326.3991 | 2326.3991 | 2326.3991 | 2326.3991 | 27916.789 | 1.1.3.1 | 4755.8244 | 4755.8244 | 4755.8244 | 4755.8244 | 4755.8244 | 4755.8244 | 4755.8244 | 4755.8244 | 4755.8244 | 4755.8244 | 4755.8244 | 4755.8244 | 57069.893 | 164748.9364 | 1.1.3.1 | 164748.9364 | 169644.9364 | 13729.078 | 27458.1561 | 41187.2341 | 54916.3121 | 68645.3902 | 82374.4682 | 96103.5463 | 109832.6243 | 123561.7023 | 137290.7804 | 151019.8584 | 164748.9364 | 13729.078 | 27458.1561 | 41187.2341 | 54916.3121 | 68645.3902 | 82374.4682 | 96103.5463 | 114728.6243 | 128457.7023 | 142186.7804 | 155915.8584 | 169644.9364
| 1.1 | 1.1.3.1 | C |  | UW | Technical Reviews |  |  | Travel |  |  |  | 1 | 1 | 0% | 2018-10-01 | 2025-09-26 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | -2923 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | -2981 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 2754 | 0 | 2865 | 2923 |  | 2981 |  | 14332 |  | 0 | Travel | Off Ice | 1.1 | Project Office | 1.1 Project Office | 1.1.3 | Quality and Safety | 1.1.3 Quality and Safety | 1.1.3.1 | Risk Management | 1.1.3.1 Risk Management | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1564d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.3.1 | 0 | 4896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4896 | 4896 | 4896 | 4896 | 4896
| 1.1 | 1.1.3.1 | C |  | UW | Collaboration Meetings |  |  | Travel |  |  |  | 1 | 1 | 0% | 2018-10-01 | 2025-09-26 |  | TRUE |  | Zernick | [7 empty] | 3200 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3200 | 0 | 0 | 0 | 0 | 3200 | 53% | 1696 | 4896 | -3709 | [7 empty] | 3200 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3200 | 0 | 0 | 0 | 0 | 3200 | 53% | 1696 | 4896 | -3881 | [7 empty] | 3200 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3200 | 0 | 0 | 0 | 0 | 3200 | 53% | 1696 | 4896 | 4896 | [7 empty] | 3200 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3200 | 0 | 0 | 0 | 0 | 3200 | 53% | 1696 | 4896 | 5355 | 4896 | 8437 | 8605 |  | 8777 |  | 39446 |  | 19584 | Travel | Off Ice | 1.1 | Project Office | 1.1 Project Office | 1.1.3 | Quality and Safety | 1.1.3 Quality and Safety | 1.1.3.1 | Risk Management | 1.1.3.1 Risk Management | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1564d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4896 | 0 | 0 | 0 | 0 | 1.1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4896 | 0 | 0 | 0 | 0 | 1.1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4896 | 0 | 0 | 0 | 0 | 1.1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4896 | 0 | 0 | 0 | 0 | 1.1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3200 | 0 | 0 | 0 | 0 | 3200 | 1.1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1696 | 0 | 0 | 0 | 0 | 1696 | 4896 | 1.1.3.1 | 4896 | 4896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4896 | 4896 | 4896 | 4896 | 4896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4896 | 4896 | 4896 | 4896 | 4896
| 1.1 | 1.1.3.1 | C |  | UW | Polar Season 2021-2022 Drill IV&T Travel |  |  | Travel |  |  |  | 1 | 1 | 0% | 2018-10-01 | 2025-09-26 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | -3491 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 |  | 3491 |  | 0 |  | 3491 |  | 0 | Travel | Off Ice | 1.1 | Project Office | 1.1 Project Office | 1.1.3 | Quality and Safety | 1.1.3 Quality and Safety | 1.1.3.1 | Risk Management | 1.1.3.1 Risk Management | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1564d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.1 | 1.1.3.1 | C |  | UW | Polar Season 2022-2023 Travel |  |  | Travel |  |  |  | 1 | 1 | 0% | 2018-10-01 | 2025-09-26 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | -3561 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 |  |  |  | 3561 |  | 3561 |  | 0 | Travel | Off Ice | 1.1 | Project Office | 1.1 Project Office | 1.1.3 | Quality and Safety | 1.1.3 Quality and Safety | 1.1.3.1 | Risk Management | 1.1.3.1 Risk Management | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1564d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.1 | 1.1.5.1 | C |  | UW | IT |  |  | M & S |  |  |  | 1 | 1 | 0% | 2018-10-01 | 2025-09-26 |  | TRUE |  |  | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 120 | 53% | 63.6 | 183.6 | -581.4 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 120 | 53% | 63.6 | 183.6 | -581.4 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 120 | 53% | 63.6 | 183.6 | 183.6 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 120 | 53% | 63.6 | 183.6 | 918 | 183.6 | 765 | 765 |  | 765 |  | 3978 |  | 734.4 | M & S | Off Ice | 1.1 | Project Office | 1.1 Project Office | 1.1.5 | Polar Operations | 1.1.5 Polar Operations | 1.1.5.1 | Logistics | 1.1.5.1 Logistics | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1564d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.1.5.1 | 15.3 | 15.3 | 15.3 | 15.3 | 15.3 | 15.3 | 15.3 | 15.3 | 15.3 | 15.3 | 15.3 | 15.3 | 1.1.5.1 | 15.3 | 15.3 | 15.3 | 15.3 | 15.3 | 15.3 | 15.3 | 15.3 | 15.3 | 15.3 | 15.3 | 15.3 | 1.1.5.1 | 15.3 | 15.3 | 15.3 | 15.3 | 15.3 | 15.3 | 15.3 | 15.3 | 15.3 | 15.3 | 15.3 | 15.3 | 1.1.5.1 | 15.3 | 15.3 | 15.3 | 15.3 | 15.3 | 15.3 | 15.3 | 15.3 | 15.3 | 15.3 | 15.3 | 15.3 | 1.1.5.1 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 120 | 1.1.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.5.1 | 5.3 | 5.3 | 5.3 | 5.3 | 5.3 | 5.3 | 5.3 | 5.3 | 5.3 | 5.3 | 5.3 | 5.3 | 63.6 | 183.6 | 1.1.5.1 | 183.6 | 47340.1592 | 15.3 | 30.6 | 45.9 | 61.2 | 76.5 | 91.8 | 107.1 | 122.4 | 137.7 | 153 | 168.3 | 183.6 | 3537.0133 | 7074.0265 | 10611.0398 | 14148.0531 | 17685.0663 | 21222.0796 | 24759.0929 | 33192.1061 | 36729.1194 | 40266.1327 | 43803.1459 | 47340.1592
| 1.1 | 1.1.5.1 | C |  | UW | Collaboration Meeting Travel |  |  | Travel |  |  |  | 1 | 1 | 0% | 2018-10-01 | 2025-09-26 |  | TRUE | [9 empty] | 3200 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3200 | 0 | 0 | 0 | 0 | 3200 | 53% | 1696 | 4896 | -3709 | [7 empty] | 3200 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3200 | 0 | 0 | 0 | 0 | 3200 | 53% | 1696 | 4896 | -3881 | [7 empty] | 3200 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3200 | 0 | 0 | 0 | 0 | 3200 | 53% | 1696 | 4896 | 4896 | [7 empty] | 3200 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3200 | 0 | 0 | 0 | 0 | 3200 | 53% | 1696 | 4896 | 5355 | 4896 | 8437 | 8605 |  | 8777 |  | 39446 |  | 19584 | Travel | Off Ice | 1.1 | Project Office | 1.1 Project Office | 1.1.5 | Polar Operations | 1.1.5 Polar Operations | 1.1.5.1 | Logistics | 1.1.5.1 Logistics | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1564d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.1.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4896 | 0 | 0 | 0 | 0 | 1.1.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4896 | 0 | 0 | 0 | 0 | 1.1.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4896 | 0 | 0 | 0 | 0 | 1.1.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4896 | 0 | 0 | 0 | 0 | 1.1.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3200 | 0 | 0 | 0 | 0 | 3200 | 1.1.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1696 | 0 | 0 | 0 | 0 | 1696 | 4896 | 1.1.5.1 | 4896 | 47156.5592 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4896 | 4896 | 4896 | 4896 | 4896 | 3521.7133 | 7043.4265 | 10565.1398 | 14086.8531 | 17608.5663 | 21130.2796 | 24651.9929 | 33069.7061 | 36591.4194 | 40113.1327 | 43634.8459 | 47156.5592
| 1.1 | 1.1.5.1 | C |  | UW | Logistics-Tosi | Tosi | 24.81% | Labor Hours | SS |  |  |  | 38 | 35% | 2018-10-01 | 2025-09-26 |  | TRUE |  |  | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 2205.9 | 2205.9 | 2205.9 | 2205.9 | 2205.9 | 2205.9 | 2205.9 | 2205.9 | 2205.9 | 2205.9 | 2205.9 | 2205.9 | 26470.8 | 53% | 14029.524 | 42260.5592 | 3450.5908 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 2205.9 | 2205.9 | 2205.9 | 2205.9 | 2205.9 | 2205.9 | 2205.9 | 2205.9 | 2205.9 | 2205.9 | 2205.9 | 2205.9 | 26470.8 | 53% | 14029.524 | 43169.1612 | 3582.9912 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 2205.9 | 2205.9 | 2205.9 | 2205.9 | 2205.9 | 2205.9 | 2205.9 | 2205.9 | 2205.9 | 2205.9 | 2205.9 | 2205.9 | 26470.8 | 53% | 14029.524 | 44097.2982 | 44097.2982 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 2205.9 | 2205.9 | 2205.9 | 2205.9 | 2205.9 | 2205.9 | 2205.9 | 2205.9 | 2205.9 | 2205.9 | 2205.9 | 2205.9 | 26470.8 | 53% | 14029.524 | 45045.3901 |  | 37302.93 | 38048.9886 | 38809.9684 |  | 39586.17 |  |  |  | 174572.4087 | Labor - LoE | Off Ice | 1.1 | Project Office | 1.1 Project Office | 1.1.5 | Polar Operations | 1.1.5 Polar Operations | 1.1.5.1 | Logistics | 1.1.5.1 Logistics | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.1.5.1 | 3521.7133 | 3521.7133 | 3521.7133 | 3521.7133 | 3521.7133 | 3521.7133 | 3521.7133 | 3521.7133 | 3521.7133 | 3521.7133 | 3521.7133 | 3521.7133 | 1.1.5.1 | 3597.4301 | 3597.4301 | 3597.4301 | 3597.4301 | 3597.4301 | 3597.4301 | 3597.4301 | 3597.4301 | 3597.4301 | 3597.4301 | 3597.4301 | 3597.4301 | 1.1.5.1 | 3674.7748 | 3674.7748 | 3674.7748 | 3674.7748 | 3674.7748 | 3674.7748 | 3674.7748 | 3674.7748 | 3674.7748 | 3674.7748 | 3674.7748 | 3674.7748 | 1.1.5.1 | 3753.7825 | 3753.7825 | 3753.7825 | 3753.7825 | 3753.7825 | 3753.7825 | 3753.7825 | 3753.7825 | 3753.7825 | 3753.7825 | 3753.7825 | 3753.7825 | 1.1.5.1 | 1705.0173 | 1705.0173 | 1705.0173 | 1705.0173 | 1705.0173 | 1705.0173 | 1705.0173 | 1705.0173 | 1705.0173 | 1705.0173 | 1705.0173 | 1705.0173 | 20460.2078 | 1.1.5.1 | 596.7561 | 596.7561 | 596.7561 | 596.7561 | 596.7561 | 596.7561 | 596.7561 | 596.7561 | 596.7561 | 596.7561 | 596.7561 | 596.7561 | 7161.0727 | 1.1.5.1 | 1219.9399 | 1219.9399 | 1219.9399 | 1219.9399 | 1219.9399 | 1219.9399 | 1219.9399 | 1219.9399 | 1219.9399 | 1219.9399 | 1219.9399 | 1219.9399 | 14639.2787 | 42260.5592 | 1.1.5.1 | 42260.5592 | 42260.5592 | 3521.7133 | 7043.4265 | 10565.1398 | 14086.8531 | 17608.5663 | 21130.2796 | 24651.9929 | 28173.7061 | 31695.4194 | 35217.1327 | 38738.8459 | 42260.5592 | 3521.7133 | 7043.4265 | 10565.1398 | 14086.8531 | 17608.5663 | 21130.2796 | 24651.9929 | 28173.7061 | 31695.4194 | 35217.1327 | 38738.8459 | 42260.5592
| 1.1 | 1.1.4.1 | P |  | UW | System Engineering-Sandstrom | Sandstrom | 50.19% | Labor Hours | SE |  |  | 55 | 54 | 35% | 2018-10-01 | 2025-09-26 |  | TRUE |  |  | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 6342.3 | 6342.3 | 6342.3 | 6342.3 | 6342.3 | 6342.3 | 6342.3 | 6342.3 | 6342.3 | 6342.3 | 6342.3 | 6342.3 | 76107.6 | 53% | 40337.028 | 121505.5735 | 2735.5735 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 6342.3 | 6342.3 | 6342.3 | 6342.3 | 6342.3 | 6342.3 | 6342.3 | 6342.3 | 6342.3 | 6342.3 | 6342.3 | 6342.3 | 76107.6 | 53% | 40337.028 | 124117.9434 | 2972.9434 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 6342.3 | 6342.3 | 6342.3 | 6342.3 | 6342.3 | 6342.3 | 6342.3 | 6342.3 | 6342.3 | 6342.3 | 6342.3 | 6342.3 | 76107.6 | 53% | 40337.028 | 126786.4791 | 126786.4791 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 6342.3 | 6342.3 | 6342.3 | 6342.3 | 6342.3 | 6342.3 | 6342.3 | 6342.3 | 6342.3 | 6342.3 | 6342.3 | 6342.3 | 76107.6 | 53% | 40337.028 | 129512.3884 | 112815 | 107819.1 | 109975.482 | 118770 |  | 121145 |  | 583329 |  | 501922.3845 | Labor - LoE | Off Ice | 1.1 | Project Office | 1.1 Project Office | 1.1.4 | Project Engineering | 1.1.4 Project Engineering | 1.1.4.1 | System Engineering | 1.1.4.1 System Engineering | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1564d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.1.4.1 | 10125.4645 | 10125.4645 | 10125.4645 | 10125.4645 | 10125.4645 | 10125.4645 | 10125.4645 | 10125.4645 | 10125.4645 | 10125.4645 | 10125.4645 | 10125.4645 | 1.1.4.1 | 10343.1619 | 10343.1619 | 10343.1619 | 10343.1619 | 10343.1619 | 10343.1619 | 10343.1619 | 10343.1619 | 10343.1619 | 10343.1619 | 10343.1619 | 10343.1619 | 1.1.4.1 | 10565.5399 | 10565.5399 | 10565.5399 | 10565.5399 | 10565.5399 | 10565.5399 | 10565.5399 | 10565.5399 | 10565.5399 | 10565.5399 | 10565.5399 | 10565.5399 | 1.1.4.1 | 10792.699 | 10792.699 | 10792.699 | 10792.699 | 10792.699 | 10792.699 | 10792.699 | 10792.699 | 10792.699 | 10792.699 | 10792.699 | 10792.699 | 1.1.4.1 | 4902.1857 | 4902.1857 | 4902.1857 | 4902.1857 | 4902.1857 | 4902.1857 | 4902.1857 | 4902.1857 | 4902.1857 | 4902.1857 | 4902.1857 | 4902.1857 | 58826.2278 | 1.1.4.1 | 1715.765 | 1715.765 | 1715.765 | 1715.765 | 1715.765 | 1715.765 | 1715.765 | 1715.765 | 1715.765 | 1715.765 | 1715.765 | 1715.765 | 20589.1797 | 1.1.4.1 | 3507.5138 | 3507.5138 | 3507.5138 | 3507.5138 | 3507.5138 | 3507.5138 | 3507.5138 | 3507.5138 | 3507.5138 | 3507.5138 | 3507.5138 | 3507.5138 | 42090.166 | 121505.5735 | 1.1.4.1 | 121505.5735 | 259465.9214 | 10125.4645 | 20250.9289 | 30376.3934 | 40501.8578 | 50627.3223 | 60752.7868 | 70878.2512 | 81003.7157 | 91129.1801 | 101254.6446 | 111380.1091 | 121505.5735 | 18766.1601 | 37532.3202 | 56298.4803 | 75064.6405 | 93830.8006 | 112596.9607 | 131363.1208 | 159921.2809 | 188479.441 | 221933.6011 | 240699.7612 | 259465.9214
| 1.1 | 1.1.4.1 | P |  | UW | IT |  |  | M & S |  |  |  | 1 | 1 | 0% | 2018-10-01 | 2025-09-26 |  | TRUE |  |  | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 120 | 53% | 63.6 | 183.6 | -581.4 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 120 | 53% | 63.6 | 183.6 | -581.4 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 120 | 53% | 63.6 | 183.6 | 183.6 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 120 | 53% | 63.6 | 183.6 | 918 | 183.6 | 765 | 765 |  | 765 |  | 3978 |  | 734.4 | M & S | Off Ice | 1.1 | Project Office | 1.1 Project Office | 1.1.4 | Project Engineering | 1.1.4 Project Engineering | 1.1.4.1 | System Engineering | 1.1.4.1 System Engineering | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1564d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.1.4.1 | 15.3 | 15.3 | 15.3 | 15.3 | 15.3 | 15.3 | 15.3 | 15.3 | 15.3 | 15.3 | 15.3 | 15.3 | 1.1.4.1 | 15.3 | 15.3 | 15.3 | 15.3 | 15.3 | 15.3 | 15.3 | 15.3 | 15.3 | 15.3 | 15.3 | 15.3 | 1.1.4.1 | 15.3 | 15.3 | 15.3 | 15.3 | 15.3 | 15.3 | 15.3 | 15.3 | 15.3 | 15.3 | 15.3 | 15.3 | 1.1.4.1 | 15.3 | 15.3 | 15.3 | 15.3 | 15.3 | 15.3 | 15.3 | 15.3 | 15.3 | 15.3 | 15.3 | 15.3 | 1.1.4.1 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 120 | 1.1.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.4.1 | 5.3 | 5.3 | 5.3 | 5.3 | 5.3 | 5.3 | 5.3 | 5.3 | 5.3 | 5.3 | 5.3 | 5.3 | 63.6 | 183.6 | 1.1.4.1 | 183.6 | 137960.3478 | 15.3 | 30.6 | 45.9 | 61.2 | 76.5 | 91.8 | 107.1 | 122.4 | 137.7 | 153 | 168.3 | 183.6 | 8640.6957 | 17281.3913 | 25922.087 | 34562.7826 | 43203.4783 | 51844.1739 | 60484.8696 | 78917.5652 | 97350.2609 | 120678.9565 | 129319.6522 | 137960.3478
| 1.1 | 1.1.4.1 | P |  | UW | Technical Reviews |  |  | Travel |  |  |  | 1 | 1 | 0% | 2018-10-01 | 2025-09-26 |  | TRUE |  |  |  | 0 | 0 | 0 |  | 0 |  | 6400 | 6400 | 9600 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6400 | 6400 | 9600 | 0 | 0 | 22400 | 53% | 11872 | 34272 | 31349 |  | 0 | 0 | 0 |  | 0 |  | 6400 | 6400 | 9600 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6400 | 6400 | 9600 | 0 | 0 | 22400 | 53% | 11872 | 34272 | 31291 |  | 0 | 0 | 0 |  | 0 |  | 6400 | 6400 | 9600 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6400 | 6400 | 9600 | 0 | 0 | 22400 | 53% | 11872 | 34272 | 34272 |  | 0 | 0 | 0 |  | 0 |  | 6400 | 6400 | 9600 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6400 | 6400 | 9600 | 0 | 0 | 22400 | 53% | 11872 | 34272 |  | 58752 | 2865 | 2923 |  | 2981 |  | 11578 |  | 137088 | Travel | Off Ice | 1.1 | Project Office | 1.1 Project Office | 1.1.4 | Project Engineering | 1.1.4 Project Engineering | 1.1.4.1 | System Engineering | 1.1.4.1 System Engineering | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1564d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.1.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9792 | 9792 | 14688 | 0 | 0 | 1.1.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9792 | 9792 | 14688 | 0 | 0 | 1.1.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9792 | 9792 | 14688 | 0 | 0 | 1.1.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9792 | 9792 | 14688 | 0 | 0 | 1.1.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6400 | 6400 | 9600 | 0 | 0 | 22400 | 1.1.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3392 | 3392 | 5088 | 0 | 0 | 11872 | 34272 | 1.1.4.1 | 34272 | 137776.7478 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9792 | 19584 | 34272 | 34272 | 34272 | 8625.3957 | 17250.7913 | 25876.187 | 34501.5826 | 43126.9783 | 51752.3739 | 60377.7696 | 78795.1652 | 97212.5609 | 120525.9565 | 129151.3522 | 137776.7478
| 1.1 | 1.1.4.1 | P |  | UW | System engineering-DuVernois | DuVernois | 39.81% | Labor Hours | SE |  |  |  | 58 | 35% | 2018-10-01 | 2025-09-26 |  | TRUE |  |  | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 5402.7 | 5402.7 | 5402.7 | 5402.7 | 5402.7 | 5402.7 | 5402.7 | 5402.7 | 5402.7 | 5402.7 | 5402.7 | 5402.7 | 64832.4 | 53% | 34361.172 | 103504.7478 | 3862.4104 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 5402.7 | 5402.7 | 5402.7 | 5402.7 | 5402.7 | 5402.7 | 5402.7 | 5402.7 | 5402.7 | 5402.7 | 5402.7 | 5402.7 | 64832.4 | 53% | 34361.172 | 105730.0999 | 4094.9199 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 5402.7 | 5402.7 | 5402.7 | 5402.7 | 5402.7 | 5402.7 | 5402.7 | 5402.7 | 5402.7 | 5402.7 | 5402.7 | 5402.7 | 64832.4 | 53% | 34361.172 | 108003.2971 | 108003.2971 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 5402.7 | 5402.7 | 5402.7 | 5402.7 | 5402.7 | 5402.7 | 5402.7 | 5402.7 | 5402.7 | 5402.7 | 5402.7 | 5402.7 | 64832.4 | 53% | 34361.172 | 110325.3679 |  | 95773.104 | 97688.5661 | 99642.3374 |  | 101635.18 |  |  |  | 427563.5127 | Labor - LoE | Off Ice | 1.1 | Project Office | 1.1 Project Office | 1.1.4 | Project Engineering | 1.1.4 Project Engineering | 1.1.4.1 | System Engineering | 1.1.4.1 System Engineering | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.1.4.1 | 8625.3957 | 8625.3957 | 8625.3957 | 8625.3957 | 8625.3957 | 8625.3957 | 8625.3957 | 8625.3957 | 8625.3957 | 8625.3957 | 8625.3957 | 8625.3957 | 1.1.4.1 | 8810.8417 | 8810.8417 | 8810.8417 | 8810.8417 | 8810.8417 | 8810.8417 | 8810.8417 | 8810.8417 | 8810.8417 | 8810.8417 | 8810.8417 | 8810.8417 | 1.1.4.1 | 9000.2748 | 9000.2748 | 9000.2748 | 9000.2748 | 9000.2748 | 9000.2748 | 9000.2748 | 9000.2748 | 9000.2748 | 9000.2748 | 9000.2748 | 9000.2748 | 1.1.4.1 | 9193.7807 | 9193.7807 | 9193.7807 | 9193.7807 | 9193.7807 | 9193.7807 | 9193.7807 | 9193.7807 | 9193.7807 | 9193.7807 | 9193.7807 | 9193.7807 | 1.1.4.1 | 4175.9359 | 4175.9359 | 4175.9359 | 4175.9359 | 4175.9359 | 4175.9359 | 4175.9359 | 4175.9359 | 4175.9359 | 4175.9359 | 4175.9359 | 4175.9359 | 50111.2311 | 1.1.4.1 | 1461.5776 | 1461.5776 | 1461.5776 | 1461.5776 | 1461.5776 | 1461.5776 | 1461.5776 | 1461.5776 | 1461.5776 | 1461.5776 | 1461.5776 | 1461.5776 | 17538.9309 | 1.1.4.1 | 2987.8822 | 2987.8822 | 2987.8822 | 2987.8822 | 2987.8822 | 2987.8822 | 2987.8822 | 2987.8822 | 2987.8822 | 2987.8822 | 2987.8822 | 2987.8822 | 35854.5858 | 103504.7478 | 1.1.4.1 | 103504.7478 | 103504.7478 | 8625.3957 | 17250.7913 | 25876.187 | 34501.5826 | 43126.9783 | 51752.3739 | 60377.7696 | 69003.1652 | 77628.5609 | 86253.9565 | 94879.3522 | 103504.7478 | 8625.3957 | 17250.7913 | 25876.187 | 34501.5826 | 43126.9783 | 51752.3739 | 60377.7696 | 69003.1652 | 77628.5609 | 86253.9565 | 94879.3522 | 103504.7478
| 1.2 | 1.2.1.1 | C |  | UW | EHWD Project Management and Controls (PSL_Drill_Manager) | McEwen | 99.81% | Labor Hours | SE |  |  | 115 | 50 | 35% | 2018-10-01 | 2025-05-28 |  | TRUE |  |  | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 11677.5 | 11677.5 | 11677.5 | 11677.5 | 11677.5 | 11677.5 | 11677.5 | 11677.5 | 11677.5 | 11677.5 | 11677.5 | 11677.5 | 140130 | 53% | 74268.9 | 223717.1586 | -2534.8414 | 154.32 | 154.32 | 154.32 | 154.32 | 154.32 | 154.32 | 154.32 | 154.32 | 154.32 | 154.32 | 154.32 | 154.325 | 10416.6 | 10416.6 | 10416.6 | 10416.6 | 10416.6 | 10416.6 | 10416.6 | 10416.6 | 10416.6 | 10416.6 | 10416.6 | 10416.9375 | 124999.5375 | 53% | 66249.7549 | 203851.9874 | 74988.9874 | 154.32 | 154.32 | 154.32 | 154.32 | 154.32 | 154.32 | 154.32 | 154.32 | 154.32 | 154.32 | 154.32 | 154.325 | 10416.6 | 10416.6 | 10416.6 | 10416.6 | 10416.6 | 10416.6 | 10416.6 | 10416.6 | 10416.6 | 10416.6 | 10416.6 | 10416.9375 | 124999.5375 | 53% | 66249.7549 | 208234.8051 | 208234.8051 | 154.32 | 154.32 | 154.32 | 154.32 | 154.32 | 154.32 | 154.32 | 154.32 |  |  |  |  | 10416.6 | 10416.6 | 10416.6 | 10416.6 | 10416.6 | 10416.6 | 10416.6 | 10416.6 | 0 | 0 | 0 | 0 | 83332.8 | 53% | 44166.384 | 141807.5194 | 206761 | 218063 | 221815 | 226252 |  | 128863 |  | 1001753 |  | 777611.4705 | Labor - LoE | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.1 | EHWD Project Management and Controls | 1.2.1.1 EHWD Project Management and Controls | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1487d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.1 | 18643.0965 | 18643.0965 | 18643.0965 | 18643.0965 | 18643.0965 | 18643.0965 | 18643.0965 | 18643.0965 | 18643.0965 | 18643.0965 | 18643.0965 | 18643.0965 | 1.2.1.1 | 16987.6197 | 16987.6197 | 16987.6197 | 16987.6197 | 16987.6197 | 16987.6197 | 16987.6197 | 16987.6197 | 16987.6197 | 16987.6197 | 16987.6197 | 16988.1702 | 1.2.1.1 | 17352.8536 | 17352.8536 | 17352.8536 | 17352.8536 | 17352.8536 | 17352.8536 | 17352.8536 | 17352.8536 | 17352.8536 | 17352.8536 | 17352.8536 | 17353.4158 | 1.2.1.1 | 17725.9399 | 17725.9399 | 17725.9399 | 17725.9399 | 17725.9399 | 17725.9399 | 17725.9399 | 17725.9399 | 0 | 0 | 0 | 0 | 1.2.1.1 | 9025.9485 | 9025.9485 | 9025.9485 | 9025.9485 | 9025.9485 | 9025.9485 | 9025.9485 | 9025.9485 | 9025.9485 | 9025.9485 | 9025.9485 | 9025.9485 | 108311.3816 | 1.2.1.1 | 3159.082 | 3159.082 | 3159.082 | 3159.082 | 3159.082 | 3159.082 | 3159.082 | 3159.082 | 3159.082 | 3159.082 | 3159.082 | 3159.082 | 37908.9835 | 1.2.1.1 | 6458.0661 | 6458.0661 | 6458.0661 | 6458.0661 | 6458.0661 | 6458.0661 | 6458.0661 | 6458.0661 | 6458.0661 | 6458.0661 | 6458.0661 | 6458.0661 | 77496.7935 | 223717.1586 | 1.2.1.1 | 223717.1586 | 225247.1586 | 18643.0965 | 37286.1931 | 55929.2896 | 74572.3862 | 93215.4827 | 111858.5793 | 130501.6758 | 149144.7724 | 167787.8689 | 186430.9655 | 205074.062 | 223717.1586 | 18643.0965 | 37286.1931 | 55929.2896 | 74572.3862 | 93215.4827 | 111858.5793 | 130501.6758 | 149144.7724 | 167787.8689 | 186430.9655 | 205074.062 | 225247.1586
| 1.2 | 1.2.1.1 | C |  | UW | EHWD Project Management and Controls (PSL_Drill_Manager) | McEwen |  | M & S |  |  |  | 1 | 1 | 0% | 2018-10-01 | 2025-05-28 |  | TRUE | [13 empty] | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 1000 | 53% | 530 | 1530 | -3060 |  |  | 1000 |  |  |  | 1000 |  |  |  | 1000 |  | 0 | 0 | 1000 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 1000 | 0 | 3000 | 53% | 1590 | 4590 | 0 |  |  | 1000 |  |  |  | 1000 |  |  |  | 1000 |  | 0 | 0 | 1000 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 1000 | 0 | 3000 | 53% | 1590 | 4590 | 4590 |  |  | 1000 | [9 empty] | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 53% | 530 | 1530 | 4590 | 4590 | 4590 | 4590 |  | 4590 |  | 22950 |  | 12240 | M & S | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.1 | EHWD Project Management and Controls | 1.2.1.1 EHWD Project Management and Controls | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1487d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1530 | 1.2.1.1 | 0 | 0 | 1530 | 0 | 0 | 0 | 1530 | 0 | 0 | 0 | 1530 | 0 | 1.2.1.1 | 0 | 0 | 1530 | 0 | 0 | 0 | 1530 | 0 | 0 | 0 | 1530 | 0 | 1.2.1.1 | 0 | 0 | 1530 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 1000 | 1.2.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 530 | 530 | 1530 | 1.2.1.1 | 1530 | 1530 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1530 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1530
| 1.2 | 1.2.1.2 | C |  | PSL | Logistics Review and Rebaselining Support (PSL_Drill_Manager) | Gibson | 7.333% | Labor Hours | EN |  |  |  | 115 | 0% | 2021-10-01 | 2022-03-17 |  |  |  |  | 20 | 20 | 20 | 20 | 20 | 32 | [6 empty] | 2300 | 2300 | 2300 | 2300 | 2300 | 3680 | 0 | 0 | 0 | 0 | 0 | 0 | 15180 | 0% | 0 | 15839.757 | 15839.757 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [6 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | [9 empty] | 15839.757 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.2 | EHWD Project Management and Controls | 1.2.1.2 EHWD Project Management and Controls | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1487d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.2 | 2399.9632 | 2399.9632 | 2399.9632 | 2399.9632 | 2399.9632 | 3839.9411 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.2 | 2399.9632 | 2399.9632 | 2399.9632 | 2399.9632 | 2399.9632 | 3839.9411 | 0 | 0 | 0 | 0 | 0 | 0 | 15839.757 | 1.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15839.757 | 1.2.1.2 | 15839.757 | 15839.757 | 2399.9632 | 4799.9263 | 7199.8895 | 9599.8527 | 11999.8159 | 15839.757 | 15839.757 | 15839.757 | 15839.757 | 15839.757 | 15839.757 | 15839.757 | 2399.9632 | 4799.9263 | 7199.8895 | 9599.8527 | 11999.8159 | 15839.757 | 15839.757 | 15839.757 | 15839.757 | 15839.757 | 15839.757 | 15839.757
| 1.2 | 1.2.1.2.4.1 | P |  | PSL | 2021-22 Systems Engineering (Terry Benson) | Benson | 60% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2022-02-15 | 2022-08-15 |  |  |  |  | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 10350 | 10350 | 10350 | 10350 | 10350 | 10350 | 10350 | 10350 | 10350 | 10350 | 10350 | 10350 | 124200 | 0% | 0 | 129598.0115 | -1501.9885 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 131100 |  |  |  | 85427 |  | 129598.0115 | Labor - LoE | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.2 | Systems Engineering | 1.2.1.2 Systems Engineering | cell-link@smartsheet.com | 2021-12-01 20:45 |  | 258d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.2.4.1 | 10799.8343 | 10799.8343 | 10799.8343 | 10799.8343 | 10799.8343 | 10799.8343 | 10799.8343 | 10799.8343 | 10799.8343 | 10799.8343 | 10799.8343 | 10799.8343 | 1.2.1.2.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.2.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.2.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.2.4.1 | 10799.8343 | 10799.8343 | 10799.8343 | 10799.8343 | 10799.8343 | 10799.8343 | 10799.8343 | 10799.8343 | 10799.8343 | 10799.8343 | 10799.8343 | 10799.8343 | 129598.0115 | 1.2.1.2.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.2.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 129598.0115 | 1.2.1.2.4.1 | 129598.0115 | 245396.2346 | 10799.8343 | 21599.6686 | 32399.5029 | 43199.3371 | 53999.1714 | 64799.0057 | 75598.84 | 86398.6743 | 97198.5086 | 107998.3429 | 118798.1772 | 129598.0115 | 19799.6962 | 39599.3924 | 59399.0886 | 79198.7848 | 98998.481 | 118798.1772 | 146397.7537 | 166197.4499 | 185997.1461 | 205796.8423 | 225596.5384 | 245396.2346
| 1.2 | 1.2.1.2.4.1 | P |  | PSL | 2021-22 Systems Engineering Support | Birrittella | 53.61% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2022-02-15 | 2022-08-15 |  |  |  |  | 75 | 75 | 75 | 75 | 75 | 75 | 140 | 75 | 75 | 75 | 75 | 75 | 8625 | 8625 | 8625 | 8625 | 8625 | 8625 | 16100 | 8625 | 8625 | 8625 | 8625 | 8625 | 110975 | 0% | 0 | 115798.2232 | 74398.2232 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 41400 |  |  |  | 61019 |  | 115798.2232 | Labor - LoE | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.2 | Systems Engineering | 1.2.1.2 Systems Engineering | cell-link@smartsheet.com | 2021-12-01 20:45 |  | 258d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.2.4.1 | 8999.8619 | 8999.8619 | 8999.8619 | 8999.8619 | 8999.8619 | 8999.8619 | 16799.7422 | 8999.8619 | 8999.8619 | 8999.8619 | 8999.8619 | 8999.8619 | 1.2.1.2.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.2.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.2.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.2.4.1 | 8999.8619 | 8999.8619 | 8999.8619 | 8999.8619 | 8999.8619 | 8999.8619 | 16799.7422 | 8999.8619 | 8999.8619 | 8999.8619 | 8999.8619 | 8999.8619 | 115798.2232 | 1.2.1.2.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.2.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115798.2232 | 1.2.1.2.4.1 | 115798.2232 | 115798.2232 | 8999.8619 | 17999.7238 | 26999.5857 | 35999.4476 | 44999.3095 | 53999.1714 | 70798.9137 | 79798.7756 | 88798.6375 | 97798.4994 | 106798.3613 | 115798.2232 | 8999.8619 | 17999.7238 | 26999.5857 | 35999.4476 | 44999.3095 | 53999.1714 | 70798.9137 | 79798.7756 | 88798.6375 | 97798.4994 | 106798.3613 | 115798.2232
| 1.2 | 1.2.1.2.4.1.1 | C |  | PSL | Compile Parameters Documentation |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2022-04-15 | 2022-04-15 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | [9 empty] | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.2 | Systems Engineering | 1.2.1.2 Systems Engineering | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 258d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.2.4.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.2.4.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.2.4.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.2.4.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.2.4.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.2.4.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.2.4.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.2.4.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.1.2.4.1.2 | C |  | PSL | P&ID and Instrumentation List Development |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2022-04-15 | 2022-04-15 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | [9 empty] | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.2 | Systems Engineering | 1.2.1.2 Systems Engineering | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 258d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.2.4.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.2.4.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.2.4.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.2.4.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.2.4.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.2.4.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.2.4.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.2.4.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.1.2.4.1.3 | C |  | PSL | Close-out IV&T |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2022-04-15 | 2022-04-15 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | [9 empty] | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.2 | Systems Engineering | 1.2.1.2 Systems Engineering | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 258d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.2.4.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.2.4.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.2.4.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.2.4.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.2.4.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.2.4.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.2.4.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.2.4.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.1.2.4.1.4 | C |  | PSL | Review/Edit Drill Procedures |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2022-02-15 | 2022-08-15 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | [9 empty] | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.2 | Systems Engineering | 1.2.1.2 Systems Engineering | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 258d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.2.4.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.2.4.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.2.4.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.2.4.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.2.4.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.2.4.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.2.4.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.2.4.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.1.2.4.1.5 | C |  | PSL | Develop Process Control Narrative |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2022-02-15 | 2022-08-15 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | [9 empty] | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.2 | Systems Engineering | 1.2.1.2 Systems Engineering | cell-link@smartsheet.com | 2021-12-01 20:45 |  | 258d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.2.4.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.2.4.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.2.4.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.2.4.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.2.4.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.2.4.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.2.4.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.2.4.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.1.2.4.1.6 | C |  | PSL | Drill Advisory Panel |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2022-04-15 | 2022-04-15 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | [9 empty] | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.2 | Systems Engineering | 1.2.1.2 Systems Engineering | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 258d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.2.4.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.2.4.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.2.4.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.2.4.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.2.4.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.2.4.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.2.4.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.2.4.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.1.2.5 | P |  | PSL | 2022-23 Systems Engineering (Terry Benson) | Benson | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2022-09-26 | 2023-09-25 |  |  |  | 600 hrs - off ice, 500 hrs on-ice | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 10350 | 10350 | 10350 | 10350 | 10350 | 10350 | 10350 | 10350 | 10350 | 10350 | 10350 | 10350 | 124200 | 0% | 0 | 132384.3687 | 5884.3687 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  |  |  | 126500 |  | 105808 |  | 132384.3687 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.2 | Systems Engineering | 1.2.1.2 Systems Engineering | cell-link@smartsheet.com | 2021-12-01 20:45 |  | 234d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.2.5 | 11032.0307 | 11032.0307 | 11032.0307 | 11032.0307 | 11032.0307 | 11032.0307 | 11032.0307 | 11032.0307 | 11032.0307 | 11032.0307 | 11032.0307 | 11032.0307 | 1.2.1.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.1.2.5 | P |  | PSL | 2022-23 Systems Engineering Support | Birrittella | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2022-09-26 | 2023-09-25 |  |  |  | 150 hrs - off-ice, 300 hrs on-ice | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 15 | 15 | 15 | 15 | 15 | 15 | 80 | 15 | 15 | 15 | 15 | 15 | 1725 | 1725 | 1725 | 1725 | 1725 | 1725 | 9200 | 1725 | 1725 | 1725 | 1725 | 1725 | 28175 | 0% | 0 | 30031.6392 | -21718.3608 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  |  |  | 51750 |  | 43568 |  | 30031.6392 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.2 | Systems Engineering | 1.2.1.2 Systems Engineering | cell-link@smartsheet.com | 2021-12-01 20:45 |  | 234d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.2.5 | 1838.6718 | 1838.6718 | 1838.6718 | 1838.6718 | 1838.6718 | 1838.6718 | 9806.2495 | 1838.6718 | 1838.6718 | 1838.6718 | 1838.6718 | 1838.6718 | 1.2.1.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.1.2.6 | P |  | PSL | 2023-24 Systems Engineering (Terry Benson) | Benson | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2023-09-26 | 2024-09-24 |  |  |  | 600 hrs - off ice, 500 hrs on-ice | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -126500 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 10350 | 10350 | 10350 | 10350 | 10350 | 10350 | 10350 | 10350 | 10350 | 10350 | 10350 | 10350 | 124200 | 0% | 0 | 135230.6326 | 135230.6326 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  |  |  | 126500 |  | 105808 |  | 135230.6326 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.2 | Systems Engineering | 1.2.1.2 Systems Engineering | cell-link@smartsheet.com | 2021-12-01 20:45 |  | 234d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.2.6 | 11269.2194 | 11269.2194 | 11269.2194 | 11269.2194 | 11269.2194 | 11269.2194 | 11269.2194 | 11269.2194 | 11269.2194 | 11269.2194 | 11269.2194 | 11269.2194 | 1.2.1.2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.1.2.6 | P |  | PSL | 2023-24 Systems Engineering Support | Birrittella | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2023-09-26 | 2024-09-24 |  |  |  | 150 hrs - off-ice, 300 hrs on-ice | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -51750 | 15 | 15 | 15 | 15 | 15 | 15 | 80 | 15 | 15 | 15 | 15 | 15 | 1725 | 1725 | 1725 | 1725 | 1725 | 1725 | 9200 | 1725 | 1725 | 1725 | 1725 | 1725 | 28175 | 0% | 0 | 30677.3194 | 30677.3194 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  |  |  | 51750 |  | 43568 |  | 30677.3194 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.2 | Systems Engineering | 1.2.1.2 Systems Engineering | cell-link@smartsheet.com | 2021-12-01 20:45 |  | 234d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.2.6 | 1878.2032 | 1878.2032 | 1878.2032 | 1878.2032 | 1878.2032 | 1878.2032 | 10017.0839 | 1878.2032 | 1878.2032 | 1878.2032 | 1878.2032 | 1878.2032 | 1.2.1.2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.1.2.7 | P |  | PSL | 2024-25 Systems Engineering (Terry Benson) | Benson | 0% | Labor Hours | EN |  |  |  | 115 | 0% | 2024-09-25 | 2025-05-26 |  |  |  | 600 hrs - off ice, 500 hrs on-ice | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 90 | 90 | 90 | 90 | 90 | 45 | 45 | 45 |  |  |  |  | 10350 | 10350 | 10350 | 10350 | 10350 | 5175 | 5175 | 5175 | 0 | 0 | 0 | 0 | 67275 | 0% | 0 | 74824.7994 | [9 empty] | 74824.7994 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.2 | Systems Engineering | 1.2.1.2 Systems Engineering | cell-link@smartsheet.com | 2021-12-01 20:45 |  | 234d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.2.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.2.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.2.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.2.7 | 11511.5076 | 11511.5076 | 11511.5076 | 11511.5076 | 11511.5076 | 5755.7538 | 5755.7538 | 5755.7538 | 0 | 0 | 0 | 0 | 1.2.1.2.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.2.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.2.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.2.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.1.2.7.1 | P |  | PSL | 2024-25 Systems Engineering Support | Birrittella | 0% | Labor Hours | EN |  |  |  | 115 | 0% | 2024-09-25 | 2025-05-26 |  |  |  | 150 hrs - off-ice, 300 hrs on-ice | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 15 | 15 | 15 | 15 | 15 | 15 | [6 empty] | 1725 | 1725 | 1725 | 1725 | 1725 | 1725 | 0 | 0 | 0 | 0 | 0 | 0 | 10350 | 0% | 0 | 11511.5076 | [9 empty] | 11511.5076 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.2 | Systems Engineering | 1.2.1.2 Systems Engineering | cell-link@smartsheet.com | 2021-12-01 20:45 |  | 234d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.2.7.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.2.7.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.2.7.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.2.7.1 | 1918.5846 | 1918.5846 | 1918.5846 | 1918.5846 | 1918.5846 | 1918.5846 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.2.7.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.2.7.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.2.7.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.2.7.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.1.3.1 | C |  | PSL | 2018-19 Quality & Safety (PSL_Safety_Mgr) | Zernick | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2018-10-01 | 2019-09-30 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 86250 | 0 | [5 empty] | 86250 |  | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.3 | Drill Quality and Safety | 1.2.1.3 Drill Quality and Safety | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 313d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.1.3.1 | C |  | PSL | Training & Safety Equipment |  |  | M & S |  |  |  | 1 | 1 | 0% | 2018-10-01 | 2019-09-30 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 7650 | 0 | [5 empty] | 7650 |  | 0 | M & S | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.3 | Drill Quality and Safety | 1.2.1.3 Drill Quality and Safety | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 313d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.1.3.2 | C |  | PSL | 2019-20 Quality & Safety (PSL_Safety_Mgr) | Zernick | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2019-10-01 | 2020-09-30 |  |  |  | Removed all of Safety Manager from 1.2. Moved all to 1.1 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | [5 empty] | 105570 |  | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.3 | Drill Quality and Safety | 1.2.1.3 Drill Quality and Safety | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 314d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.1.3.2 | C |  | PSL | Training & Safety Equipment |  |  | M & S |  |  |  | 1 | 1 | 0% | 2019-10-01 | 2020-09-30 |  |  |  | $4,500 - Added sub-contract safety training (MATC for Electrical, Rigging, Plumbing) $4,500 - Safety equipment (hard hats, shoes, safety glasses, gloves, hearing protection, heat pads, FA kits, etc) | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 13770 | [5 empty] | 9180 |  | 0 | M & S | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.3 | Drill Quality and Safety | 1.2.1.3 Drill Quality and Safety | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 314d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.1.3.3 | C |  | PSL | 2020-21 Quality & Safety (PSL_Safety_Mgr) | Zernick | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2020-10-01 | 2021-09-30 |  | TRUE |  | Removed all of Safety Manager from 1.2. Moved all to 1.1 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | 0 |  |  |  |  | 107681 |  | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.3 | Drill Quality and Safety | 1.2.1.3 Drill Quality and Safety | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 313d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.1.3.3 | C |  | PSL | Training & Safety Equipment |  |  | M & S |  |  |  | 1 | 1 | 0% | 2020-10-01 | 2021-09-30 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 | 10710 |  |  |  |  | 10710 |  | 0 | M & S | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.3 | Drill Quality and Safety | 1.2.1.3 Drill Quality and Safety | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 313d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.1.3.4 | C |  | PSL | 2021-22 Quality & Safety (PSL_Safety_Mgr) | Zernick | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2021-10-01 | 2022-09-30 |  |  |  | Removed all of Safety Manager from 1.2. Moved all to 1.1 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 0 |  |  |  | 109835 |  | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.3 | Drill Quality and Safety | 1.2.1.3 Drill Quality and Safety | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 313d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.3.4 | 0 | 7650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3825 | 3825 | 3825 | 7650 | 7650
| 1.2 | 1.2.1.3.4 | C |  | PSL | Training & Safety Equipment |  |  | M & S |  |  |  | 1 | 1 | 0% | 2021-10-01 | 2022-09-30 | [11 empty] | 2500 |  |  | 2500 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 0 | 0 | 2500 | 0 | 5000 | 53% | 2650 | 7650 | -6120 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 |  | 13770 |  |  |  | 13770 |  | 7650 | M & S | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.3 | Drill Quality and Safety | 1.2.1.3 Drill Quality and Safety | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 313d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3825 | 0 | 0 | 3825 | 0 | 1.2.1.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 0 | 0 | 2500 | 0 | 5000 | 1.2.1.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1325 | 0 | 0 | 1325 | 0 | 2650 | 7650 | 1.2.1.3.4 | 7650 | 7650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3825 | 3825 | 3825 | 7650 | 7650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3825 | 3825 | 3825 | 7650 | 7650
| 1.2 | 1.2.1.3.5 | C |  | PSL | 2022-23 Quality & Safety (PSL_Safety_Mgr) | Zernick | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2022-10-03 | 2023-10-02 |  |  |  | Removed all of Safety Manager from 1.2. Moved all to 1.1 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  |  |  | 0 |  | 112032 |  | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.3 | Drill Quality and Safety | 1.2.1.3 Drill Quality and Safety | cell-link@smartsheet.com | 2021-11-30 14:06 |  | 234d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.1.3.5 | C |  | PSL | Training & Safety Equipment |  |  | M & S |  |  |  | 1 | 1 | 0% | 2022-10-03 | 2023-10-02 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [7 empty] | 2500 | 2500 |  | 2500 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 2500 | 0 | 2500 | 0 | 7500 | 53% | 3975 | 11475 | 6885 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 |  |  |  | 4590 |  | 4590 |  | 11475 | M & S | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.3 | Drill Quality and Safety | 1.2.1.3 Drill Quality and Safety | cell-link@smartsheet.com | 2021-11-30 14:06 |  | 234d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3825 | 3825 | 0 | 3825 | 0 | 1.2.1.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.1.3.6 | C |  | PSL | 2023-24 Quality & Safety (PSL_Safety_Mgr) | Zernick | 0% | Labor Hours | EN |  |  |  | 115 | 0% | 2023-10-03 | 2024-10-01 |  |  |  | Removed all of Safety Manager from 1.2. Moved all to 1.1 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | [9 empty] | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.3 | Drill Quality and Safety | 1.2.1.3 Drill Quality and Safety | cell-link@smartsheet.com | 2021-11-30 14:06 |  | 234d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.1.3.6 | C |  | PSL | Training & Safety Equipment |  |  | M & S |  |  |  |  | 1 | 0% | 2023-10-03 | 2024-10-01 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [6 empty] | 2500 | 2500 |  | 5000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 2500 | 0 | 5000 | 0 | 0 | 10000 | 53% | 5300 | 15300 | 15300 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 15300 | M & S | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.3 | Drill Quality and Safety | 1.2.1.3 Drill Quality and Safety | cell-link@smartsheet.com | 2021-11-30 14:06 |  | 234d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 3825 | 3825 | 0 | 7650 | 0 | 0 | 1.2.1.3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.1.3.7 | C |  | PSL | 2024-25 Quality & Safety (PSL_Safety_Mgr) | Zernick | 0% | Labor Hours | EN |  |  |  | 115 | 0% | 2024-10-02 | 2025-04-01 |  |  |  | Removed all of Safety Manager from 1.2. Moved all to 1.1 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | [9 empty] | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.3 | Drill Quality and Safety | 1.2.1.3 Drill Quality and Safety | cell-link@smartsheet.com | 2021-11-30 14:06 |  | 234d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.3.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.3.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.3.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.3.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.3.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.3.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.3.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.3.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.1.3.7 | C |  | PSL | Training & Safety Equipment |  |  | M & S |  |  |  |  | 1 | 0% | 2024-10-02 | 2025-04-01 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 0 | M & S | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.3 | Drill Quality and Safety | 1.2.1.3 Drill Quality and Safety | cell-link@smartsheet.com | 2021-11-30 14:06 |  | 234d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.3.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.3.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.3.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.3.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.3.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.3.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.3.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.3.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.1.4.1 | C |  | PSL | 2018-19 Travel |  |  | Travel |  |  |  | 1 | 1 | 0% | 2018-10-01 | 2019-09-30 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 16065 | 0 | [5 empty] | 16065 |  | 0 | Travel | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.4 | Travel | 1.2.1.4 Travel | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 313d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.1.4.2 | C |  | PSL | 2019-20 Travel |  |  | Travel |  |  |  | 1 | 1 | 0% | 2019-10-01 | 2020-09-30 |  |  |  | IVG Acceptance Visit (Italy) (2x1) - April, 2020 (total $7,000) Denver, CO, ASC (5x1) - April (total $9,000) Vendor Visits, Misc (2x2) - May & July (total $7,200) | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 35496 | [5 empty] | 16542 |  | 0 | Travel | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.4 | Travel | 1.2.1.4 Travel | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 314d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.1.4.3 | C |  | PSL | 2020-21 Travel |  |  | Travel |  |  |  | 1 | 1 | 0% | 2020-10-01 | 2021-09-30 |  | TRUE |  | Vendor Visits, Misc (2x2) - May & July (total $7,200) | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 | 16200 |  |  |  |  | 16873 |  | 0 | Travel | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.4 | Travel | 1.2.1.4 Travel | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 313d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.1.4.4 | C |  | PSL | 2021-22 Travel |  |  | Travel |  |  |  | 1 | 1 | 0% | 2021-10-01 | 2022-09-30 |  |  |  | Collab Mtg (Foreign) (1x1), Sept ($3,500) Denver, CO, ASC (5x1) - April (total $9,000) Vendor Visits, Misc (2x2) - May & July (total $7,200) | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | -19700 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 |  | 19700 |  |  |  | 17211 |  | 0 | Travel | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.4 | Travel | 1.2.1.4 Travel | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 313d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.1.4.5 | C |  | PSL | 2022-23 Travel |  |  | Travel |  |  |  | 1 | 1 | 0% | 2022-10-03 | 2023-07-03 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [5 empty] | 9000 | 3600 |  | 3600 |  |  |  | 3600 | 0 | 0 | 0 | 0 | 9000 | 3600 | 0 | 3600 | 0 | 0 | 0 | 19800 | 53% | 10494 | 30294 | 30294 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 |  |  |  | 0 |  | 17555 |  | 30294 | Travel | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.4 | Travel | 1.2.1.4 Travel | cell-link@smartsheet.com | 2021-11-30 14:06 |  | 234d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.4.5 | 5508 | 0 | 0 | 0 | 0 | 13770 | 5508 | 0 | 5508 | 0 | 0 | 0 | 1.2.1.4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.1.4.6 | C |  | PSL | 2023-24 Travel |  |  | Travel |  |  |  | 1 | 1 | 0% | 2023-10-04 | 2024-07-03 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [5 empty] | 9000 | 3600 |  | 3600 |  |  |  | 0 | 0 | 0 | 0 | 0 | 9000 | 3600 | 0 | 3600 | 0 | 0 | 0 | 16200 | 53% | 8586 | 24786 | 24786 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 |  |  |  | 0 |  | 17555 |  | 24786 | Travel | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.4 | Travel | 1.2.1.4 Travel | cell-link@smartsheet.com | 2021-11-30 14:06 |  | 234d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.4.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.4.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.4.6 | 0 | 0 | 0 | 0 | 0 | 13770 | 5508 | 0 | 5508 | 0 | 0 | 0 | 1.2.1.4.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.4.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.4.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.4.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.4.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.1.5.1.1 | C |  | PSL | Crate: MHP Replacements & Spares to PTH (Comsur) |  | 0.8889% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2021-10-15 | 2021-11-01 | [13 empty] | 8 | 8 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 920 | 920 | 0 | 1840 | 0% | 0 | 1919.9705 | 1919.9705 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | [9 empty] | 1919.9705 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.5 | Transportation and Logistics | 1.2.1.5 Transportation and Logistics | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 3d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.5.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 959.9853 | 959.9853 | 0 | 1.2.1.5.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 959.9853 | 959.9853 | 0 | 1919.9705 | 1.2.1.5.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1919.9705 | 1.2.1.5.1.1 | 1919.9705 | 3143.9705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 959.9853 | 1919.9705 | 1919.9705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1571.9853 | 3143.9705 | 3143.9705
| 1.2 | 1.2.1.5.1.1 | C |  | PSL | Crate: MHP Replacements & Spares to PTH (Comsur) |  |  | M & S |  |  |  | 1 | 1 | 0% | 2021-10-15 | 2021-11-01 | [13 empty] | 400 | 400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 400 | 0 | 800 | 53% | 424 | 1224 | 1224 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 1224 | M & S | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.5 | Transportation and Logistics | 1.2.1.5 Transportation and Logistics | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 3d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.5.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 612 | 612 | 0 | 1.2.1.5.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 400 | 0 | 800 | 1.2.1.5.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 212 | 212 | 0 | 424 | 1224 | 1.2.1.5.1.1 | 1224 | 1224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 612 | 1224 | 1224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 612 | 1224 | 1224
| 1.2 | 1.2.1.5.1.2 | C |  | PSL | Crate: PHS Replacements & Spares to PTH (Comsur) |  | 0.8889% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2021-10-15 | 2021-11-04 | [13 empty] | 8 | 8 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 920 | 920 | 0 | 1840 | 0% | 0 | 1919.9705 | 1919.9705 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | [9 empty] | 1919.9705 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.5 | Transportation and Logistics | 1.2.1.5 Transportation and Logistics | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 3d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.5.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 959.9853 | 959.9853 | 0 | 1.2.1.5.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 959.9853 | 959.9853 | 0 | 1919.9705 | 1.2.1.5.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1919.9705 | 1.2.1.5.1.2 | 1919.9705 | 2149.4705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 959.9853 | 1919.9705 | 1919.9705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1074.7353 | 2149.4705 | 2149.4705
| 1.2 | 1.2.1.5.1.2 | C |  | PSL | Crate: PHS Replacements & Spares to PTH (Comsur) |  |  | M & S | EN |  |  | 115 | 1 | 0% | 2021-10-15 | 2021-11-04 | [13 empty] | 75 | 75 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75 | 75 | 0 | 150 | 53% | 79.5 | 229.5 | 229.5 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 229.5 | M & S | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.5 | Transportation and Logistics | 1.2.1.5 Transportation and Logistics | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 3d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.5.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 114.75 | 114.75 | 0 | 1.2.1.5.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75 | 75 | 0 | 150 | 1.2.1.5.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39.75 | 39.75 | 0 | 79.5 | 229.5 | 1.2.1.5.1.2 | 229.5 | 229.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 114.75 | 229.5 | 229.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 114.75 | 229.5 | 229.5
| 1.2 | 1.2.1.5.1.3 | C |  | PSL | Crate: Fuel Systems & Tower Components to PTH (Comsur) |  | 1% | Labor Hours | TE |  |  | 115 | 77 | 0% | 2021-10-15 | 2021-11-04 | [13 empty] | 9 | 9 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 693 | 693 | 0 | 1386 | 0% | 0 | 1446.2387 | 1446.2387 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | [9 empty] | 1446.2387 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.5 | Transportation and Logistics | 1.2.1.5 Transportation and Logistics | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.5.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 723.1193 | 723.1193 | 0 | 1.2.1.5.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 723.1193 | 723.1193 | 0 | 1446.2387 | 1.2.1.5.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1446.2387 | 1.2.1.5.1.3 | 1446.2387 | 1446.2387 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 723.1193 | 1446.2387 | 1446.2387 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 723.1193 | 1446.2387 | 1446.2387
| 1.2 | 1.2.1.5.1.4 | C |  | PSL | Crate: TOS Components & Spares to PTH (Comsur) |  | 1.333% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2021-10-15 | 2021-11-04 | [13 empty] | 12 | 12 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1380 | 1380 | 0 | 2760 | 0% | 0 | 2879.9558 | 2879.9558 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | [5 empty] | 2815 |  | 2879.9558 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.5 | Transportation and Logistics | 1.2.1.5 Transportation and Logistics | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 3d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.5.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1439.9779 | 1439.9779 | 0 | 1.2.1.5.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1439.9779 | 1439.9779 | 0 | 2879.9558 | 1.2.1.5.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2879.9558 | 1.2.1.5.1.4 | 2879.9558 | 2879.9558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1439.9779 | 2879.9558 | 2879.9558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1439.9779 | 2879.9558 | 2879.9558
| 1.2 | 1.2.1.5.1.5 | C |  | PSL | Crate: Control Systems Components to PTH (Comsur) |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2021-07-15 | 2021-07-23 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 16 | [11 empty] | 1840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1840 | 0% | 0 | 2003.4168 | 2003.4168 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | [5 empty] | 2815 |  | 2003.4168 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.5 | Transportation and Logistics | 1.2.1.5 Transportation and Logistics | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 3d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.5.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.5 | 2003.4168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.1.5.1.5 | C |  | PSL | Crate: Control Systems Components to PTH (Comsur) |  |  | M & S |  |  |  |  | 1 | 0% | 2021-07-15 | 2021-07-23 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | 16 | [11 empty] | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 53% | 8.48 | 24.48 | 24.48 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 24.48 | M & S | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.5 | Transportation and Logistics | 1.2.1.5 Transportation and Logistics | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 3d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.5.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.5 | 24.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.1.5.1.6 | C |  | PSL | Crate: ARA Drill Subsystem Parts to PTH (Comsur) |  | 0.8889% | Labor Hours | TE |  |  | 81 | 77 | 0% | 2021-07-15 | 2021-07-23 | [13 empty] | 8 | 8 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 616 | 616 | 0 | 1232 | 0% | 0 | 1285.5455 | 1285.5455 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | [5 empty] | 1983 |  | 1285.5455 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.5 | Transportation and Logistics | 1.2.1.5 Transportation and Logistics | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 3d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.5.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 642.7727 | 642.7727 | 0 | 1.2.1.5.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 642.7727 | 642.7727 | 0 | 1285.5455 | 1.2.1.5.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1285.5455 | 1.2.1.5.1.6 | 1285.5455 | 1438.5455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 642.7727 | 1285.5455 | 1285.5455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 719.2727 | 1438.5455 | 1438.5455
| 1.2 | 1.2.1.5.1.6 | C |  | PSL | Crate: ARA Drill Subsystem Parts to PTH (Comsur) |  |  | M & S |  |  |  |  | 1 | 0% | 2021-07-15 | 2021-07-23 | [13 empty] | 50 | 50 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 0 | 100 | 53% | 53 | 153 | 153 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 153 | M & S | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.5 | Transportation and Logistics | 1.2.1.5 Transportation and Logistics | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 3d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.5.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76.5 | 76.5 | 0 | 1.2.1.5.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 0 | 100 | 1.2.1.5.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26.5 | 26.5 | 0 | 53 | 153 | 1.2.1.5.1.6 | 153 | 153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76.5 | 153 | 153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76.5 | 153 | 153
| 1.2 | 1.2.1.5.1.7 | C |  | PSL | Crate: Shop Parts, Spares, etc. to PTH (Comsur) |  | 0.8889% | Labor Hours | TE |  |  | 81 | 77 | 0% | 2021-10-15 | 2021-11-04 |  | TRUE | [11 empty] | 8 | 8 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 616 | 616 | 0 | 1232 | 0% | 0 | 1285.5455 | 1285.5455 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | 0 |  |  |  |  | 3305 |  | 1285.5455 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.5 | Transportation and Logistics | 1.2.1.5 Transportation and Logistics | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 18d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.5.1.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 642.7727 | 642.7727 | 0 | 1.2.1.5.1.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 642.7727 | 642.7727 | 0 | 1285.5455 | 1.2.1.5.1.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1285.5455 | 1.2.1.5.1.7 | 1285.5455 | 1285.5455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 642.7727 | 1285.5455 | 1285.5455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 642.7727 | 1285.5455 | 1285.5455
| 1.2 | 1.2.1.5.1.8 | C |  | PSL | Crate: GEN-2, 3, PDM - Ship Components, Repair Parts to PTH (Comsur) |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2021-01-07 | 2021-01-27 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | [5 empty] | 1877 |  | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.5 | Transportation and Logistics | 1.2.1.5 Transportation and Logistics | cell-link@smartsheet.com | 2021-12-02 12:32 |  | 2d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.5.1.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.1.5.1.9 | C |  | PSL | Crate: Elect. Distribution System Components to PTH (Comsur) |  | 1.778% | Labor Hours | TE |  |  | 115 | 77 | 0% | 2021-10-15 | 2021-11-04 |  | TRUE | [11 empty] | 16 | 16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1232 | 1232 | 0 | 2464 | 0% | 0 | 2571.091 | 2571.091 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | [5 empty] | 1322 |  | 2571.091 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.5 | Transportation and Logistics | 1.2.1.5 Transportation and Logistics | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 2d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.5.1.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1285.5455 | 1285.5455 | 0 | 1.2.1.5.1.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1285.5455 | 1285.5455 | 0 | 2571.091 | 1.2.1.5.1.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2571.091 | 1.2.1.5.1.9 | 2571.091 | 5019.091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1285.5455 | 2571.091 | 2571.091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2509.5455 | 5019.091 | 5019.091
| 1.2 | 1.2.1.5.1.9 | C |  | PSL | Crate: Elect. Distribution System Components to PTH (Comsur) |  |  | M & S |  |  |  |  | 1 | 0% | 2021-10-15 | 2021-11-04 | [13 empty] | 800 | 800 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800 | 800 | 0 | 1600 | 53% | 848 | 2448 | 2448 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 2448 | M & S | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.5 | Transportation and Logistics | 1.2.1.5 Transportation and Logistics | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 2d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.5.1.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1224 | 1224 | 0 | 1.2.1.5.1.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800 | 800 | 0 | 1600 | 1.2.1.5.1.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 424 | 424 | 0 | 848 | 2448 | 1.2.1.5.1.9 | 2448 | 2448 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1224 | 2448 | 2448 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1224 | 2448 | 2448
| 1.2 | 1.2.1.5.1.10 | C |  | PSL | Crate: WT Repair Parts, Replacements to PTH (Comsur) |  | 0% | Labor Hours | TE |  |  | 1 | 77 | 0% | 2021-09-27 | 2021-10-15 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | [5 empty] | 1224 |  | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.5 | Transportation and Logistics | 1.2.1.5 Transportation and Logistics | cell-link@smartsheet.com | 2021-12-02 12:32 |  | 2d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.5.1.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.1.5.1.10 | C |  | PSL | Crate: WT Repair Parts, Replacements to PTH (Comsur) |  |  | M & S |  |  |  |  | 1 | 0% | 2021-09-27 | 2021-10-15 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 0 | M & S | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.5 | Transportation and Logistics | 1.2.1.5 Transportation and Logistics | cell-link@smartsheet.com | 2021-12-02 12:32 |  | 2d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.5.1.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.1.5.1.11 | C |  | PSL | Crate: MDS Internal Hoses & Spares to PTH (Comsur) |  | 1.333% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2021-10-15 | 2021-11-04 | [13 empty] | 12 | 12 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1380 | 1380 | 0 | 2760 | 0% | 0 | 2879.9558 | 2879.9558 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | [5 empty] | 2815 |  | 2879.9558 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.5 | Transportation and Logistics | 1.2.1.5 Transportation and Logistics | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 3d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.5.1.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1439.9779 | 1439.9779 | 0 | 1.2.1.5.1.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1439.9779 | 1439.9779 | 0 | 2879.9558 | 1.2.1.5.1.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2879.9558 | 1.2.1.5.1.11 | 2879.9558 | 4394.6558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1439.9779 | 2879.9558 | 2879.9558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2197.3279 | 4394.6558 | 4394.6558
| 1.2 | 1.2.1.5.1.11 | C |  | PSL | Crate: MDS Internal Hoses & Spares to PTH (Comsur) |  |  | M & S |  |  |  |  | 1 | 0% | 2021-10-15 | 2021-11-04 | [13 empty] | 495 | 495 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 495 | 495 | 0 | 990 | 53% | 524.7 | 1514.7 | 1514.7 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 1514.7 | M & S | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.5 | Transportation and Logistics | 1.2.1.5 Transportation and Logistics | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 3d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.5.1.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 757.35 | 757.35 | 0 | 1.2.1.5.1.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 495 | 495 | 0 | 990 | 1.2.1.5.1.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 262.35 | 262.35 | 0 | 524.7 | 1514.7 | 1.2.1.5.1.11 | 1514.7 | 1514.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 757.35 | 1514.7 | 1514.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 757.35 | 1514.7 | 1514.7
| 1.2 | 1.2.1.5.1.12 | C |  | PSL | Crate: Condensate Management Components to PTH (Comsur) |  | 1.778% | Labor Hours | TE |  |  | 81 | 77 | 0% | 2022-10-14 | 2022-11-03 | [13 empty] | 16 | 16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1232 | 1232 | 0 | 2464 | 0% | 0 | 2571.091 | 2571.091 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | [5 empty] | 1983 |  | 2571.091 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.5 | Transportation and Logistics | 1.2.1.5 Transportation and Logistics | cell-link@smartsheet.com | 2021-12-02 12:32 |  | 3d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.5.1.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1285.5455 | 1285.5455 | 0 | 1.2.1.5.1.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1285.5455 | 1285.5455 | 0 | 2571.091 | 1.2.1.5.1.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2571.091 | 1.2.1.5.1.12 | 2571.091 | 2571.091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1285.5455 | 2571.091 | 2571.091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1285.5455 | 2571.091 | 2571.091
| 1.2 | 1.2.1.5.1.13 | C |  | PSL | Crate: Pump Repair/Replace Components to PTH (Comsur) |  | 0% | Labor Hours | EN |  |  | 1 | 115 | 0% | 2021-10-15 | 2021-11-04 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | [5 empty] | 918 |  | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.5 | Transportation and Logistics | 1.2.1.5 Transportation and Logistics | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 3d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.5.1.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.1.5.1.13 | C |  | PSL | Crate: Pump Repair/Replace Components to PTH (Comsur) |  |  | M & S | EN |  |  |  | 1 | 0% | 2021-10-15 | 2021-11-04 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 0 | M & S | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.5 | Transportation and Logistics | 1.2.1.5 Transportation and Logistics | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 3d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.5.1.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.1.5.1.14 | C |  | PSL | Crate: Hose Reel Heating System to PTH (Vessel) |  | 0% | Labor Hours | TE |  |  | 81 | 77 | 0% | 2022-10-14 | 2022-11-01 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 8 | [11 empty] | 616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 616 | 0% | 0 | 656.5924 | 656.5924 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | 0 |  |  |  |  | 1983 |  | 656.5924 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.5 | Transportation and Logistics | 1.2.1.5 Transportation and Logistics | cell-link@smartsheet.com | 2021-12-02 12:36 |  | 4d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.5.1.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.14 | 656.5924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.1.5.1.14 | C |  | PSL | Crate: Hose Reel Heating System to PTH (Vessel) |  |  | M & S |  |  |  |  | 1 | 0% | 2022-10-14 | 2022-11-01 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | 1200 | [11 empty] | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 53% | 636 | 1836 | 1836 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 1836 | M & S | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.5 | Transportation and Logistics | 1.2.1.5 Transportation and Logistics | cell-link@smartsheet.com | 2021-12-02 12:36 |  | 4d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.5.1.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.14 | 1836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.1.5.1.15 | C |  | PSL | Prepare: Cable Reels Main and RWCR to PTH (Vessel) |  | 0.8889% | Labor Hours | TE |  |  |  | 77 | 0% | 2021-10-15 | 2021-11-12 |  |  |  |  | 16 | [11 empty] | 1232 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1232 | 0% | 0 | 1285.5455 | 1285.5455 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | [9 empty] | 1285.5455 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.5 | Transportation and Logistics | 1.2.1.5 Transportation and Logistics | cell-link@smartsheet.com | 2021-12-02 13:21 |  | 4d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.5.1.15 | 1285.5455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.15 | 1285.5455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1285.5455 | 1.2.1.5.1.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1285.5455 | 1.2.1.5.1.15 | 1285.5455 | 5875.5455 | 1285.5455 | 1285.5455 | 1285.5455 | 1285.5455 | 1285.5455 | 1285.5455 | 1285.5455 | 1285.5455 | 1285.5455 | 1285.5455 | 1285.5455 | 1285.5455 | 5875.5455 | 5875.5455 | 5875.5455 | 5875.5455 | 5875.5455 | 5875.5455 | 5875.5455 | 5875.5455 | 5875.5455 | 5875.5455 | 5875.5455 | 5875.5455
| 1.2 | 1.2.1.5.1.15 | C |  | PSL | Prepare: Cable Reels Main and RWCR to PTH (Vessel) |  |  | M & S |  |  |  |  | 1 | 0% | 2021-10-15 | 2021-11-12 |  |  |  |  | 3000 | [11 empty] | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 53% | 1590 | 4590 | 4590 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 4590 | M & S | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.5 | Transportation and Logistics | 1.2.1.5 Transportation and Logistics | cell-link@smartsheet.com | 2021-12-02 13:21 |  | 2d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.5.1.15 | 4590 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.15 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 1.2.1.5.1.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.15 | 1590 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1590 | 4590 | 1.2.1.5.1.15 | 4590 | 4590 | 4590 | 4590 | 4590 | 4590 | 4590 | 4590 | 4590 | 4590 | 4590 | 4590 | 4590 | 4590 | 4590 | 4590 | 4590 | 4590 | 4590 | 4590 | 4590 | 4590 | 4590 | 4590 | 4590 | 4590
| 1.2 | 1.2.1.5.1.16 | C |  | PSL | Prepare: Surface Hose to PTH Outdoor Storage MCM (Vessel) |  | 0% | Labor Hours | EN |  |  |  | 115 | 0% | 2020-11-06 | 2020-11-16 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | [9 empty] | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.5 | Transportation and Logistics | 1.2.1.5 Transportation and Logistics | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.5.1.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.1.5.1.17 | C |  | PSL | Crate: Spare Main Drill & Combo Cables to PTH (Vessel) |  | 0% | Labor Hours | EN |  |  |  | 115 | 0% | 2022-10-14 | 2022-11-16 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 8 | 8 | [10 empty] | 920 | 920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1840 | 0% | 0 | 1961.2499 | 1961.2499 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | [9 empty] | 1961.2499 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.5 | Transportation and Logistics | 1.2.1.5 Transportation and Logistics | cell-link@smartsheet.com | 2021-12-02 12:41 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.5.1.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.17 | 980.625 | 980.625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.1.5.1.17 | C |  | PSL | Crate: Spare Main Drill & Combo Cables to PTH (Vessel) |  |  | M & S |  |  |  |  | 1 | 0% | 2022-10-14 | 2022-11-16 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | 25 | 25 | [10 empty] | 25 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 53% | 26.5 | 76.5 | 76.5 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 76.5 | M & S | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.5 | Transportation and Logistics | 1.2.1.5 Transportation and Logistics | cell-link@smartsheet.com | 2021-12-02 12:41 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.5.1.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.17 | 38.25 | 38.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.1.5.1.18 | C |  | PSL | Prepare: GEN-2, 3, PDM - Skis from to PTH (Vessel) |  | 0% | Labor Hours | EN |  |  |  | 115 | 0% | 2020-12-06 | 2021-01-06 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | [9 empty] | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.5 | Transportation and Logistics | 1.2.1.5 Transportation and Logistics | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.5.1.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.1.5.1.18 | C |  | PSL | Prepare: GEN-2, 3, PDM - Skis from to PTH (Vessel) |  |  | M & S |  |  |  |  | 1 | 0% | 2020-12-06 | 2021-01-06 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 0 | M & S | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.5 | Transportation and Logistics | 1.2.1.5 Transportation and Logistics | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.5.1.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.1.5.1.19 | C |  | PSL | Crate: Generator Hoods to PTH (Vessel) |  | 0% | Labor Hours | TE |  |  |  | 77 | 0% | 2020-11-06 | 2020-11-16 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | [9 empty] | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.5 | Transportation and Logistics | 1.2.1.5 Transportation and Logistics | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.5.1.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.1.5.1.20 | C |  | PSL | Crate: Drill Heads, Spare Parts to PTH (Vessel) Store in ICL |  | 0% | Labor Hours | EN |  |  |  | 115 | 0% | 2023-09-28 | 2023-10-20 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [11 empty] | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2760 | 2760 | 0% | 0 | 2941.8749 | 2941.8749 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | [9 empty] | 2941.8749 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.5 | Transportation and Logistics | 1.2.1.5 Transportation and Logistics | cell-link@smartsheet.com | 2021-12-02 12:41 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.5.1.20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2941.8749 | 1.2.1.5.1.20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.1.5.1.20 | C |  | PSL | Crate: Drill Heads, Spare Parts to PTH (Vessel) Store in ICL |  |  | M & S |  |  |  |  | 1 | 0% | 2023-09-28 | 2023-10-20 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [11 empty] | 1005 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1005 | 1005 | 53% | 532.65 | 1537.65 | 1537.65 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 1537.65 | M & S | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.5 | Transportation and Logistics | 1.2.1.5 Transportation and Logistics | cell-link@smartsheet.com | 2021-12-02 12:41 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.5.1.20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1537.65 | 1.2.1.5.1.20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.1.5.1.21 | C |  | PSL | Crate: Repair/Replacement Components to PTH (Comsur) |  | 0.8889% | Labor Hours | TE |  |  |  | 77 | 0% | 2023-07-03 | 2023-07-20 | [13 empty] | 8 | 8 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 616 | 616 | 0 | 1232 | 0% | 0 | 1285.5455 | 1285.5455 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | [9 empty] | 1285.5455 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.5 | Transportation and Logistics | 1.2.1.5 Transportation and Logistics | cell-link@smartsheet.com | 2021-12-02 12:47 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.5.1.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 642.7727 | 642.7727 | 0 | 1.2.1.5.1.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 642.7727 | 642.7727 | 0 | 1285.5455 | 1.2.1.5.1.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1285.5455 | 1.2.1.5.1.21 | 1285.5455 | 1668.0455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 642.7727 | 1285.5455 | 1285.5455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 834.0227 | 1668.0455 | 1668.0455
| 1.2 | 1.2.1.5.1.21 | C |  | PSL | Crate: Repair/Replacement Components to PTH (Comsur) |  |  | M & S |  |  |  |  | 1 | 0% | 2023-07-03 | 2023-07-20 | [13 empty] | 125 | 125 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125 | 125 | 0 | 250 | 53% | 132.5 | 382.5 | 382.5 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 382.5 | M & S | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.5 | Transportation and Logistics | 1.2.1.5 Transportation and Logistics | cell-link@smartsheet.com | 2021-12-02 12:47 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.5.1.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 191.25 | 191.25 | 0 | 1.2.1.5.1.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125 | 125 | 0 | 250 | 1.2.1.5.1.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66.25 | 66.25 | 0 | 132.5 | 382.5 | 1.2.1.5.1.21 | 382.5 | 382.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 191.25 | 382.5 | 382.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 191.25 | 382.5 | 382.5
| 1.2 | 1.2.1.5.1.22 | C |  | PSL | Crate: SES Interconnect Materials/Parts to PTH (Comsur) |  | 1.778% | Labor Hours | EN |  |  |  | 115 | 0% | 2023-10-05 | 2023-10-24 | [13 empty] | 16 | 16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1840 | 1840 | 0 | 3680 | 0% | 0 | 3839.9411 | 3839.9411 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | [9 empty] | 3839.9411 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.5 | Transportation and Logistics | 1.2.1.5 Transportation and Logistics | cell-link@smartsheet.com | 2021-12-02 12:52 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.5.1.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1919.9705 | 1919.9705 | 0 | 1.2.1.5.1.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1919.9705 | 1919.9705 | 0 | 3839.9411 | 1.2.1.5.1.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3839.9411 | 1.2.1.5.1.22 | 3839.9411 | 4298.9411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1919.9705 | 3839.9411 | 3839.9411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2149.4705 | 4298.9411 | 4298.9411
| 1.2 | 1.2.1.5.1.22 | C |  | PSL | Crate: SES Interconnect Materials/Parts to PTH (Comsur) |  |  | M & S |  |  |  |  | 1 | 0% | 2023-10-05 | 2023-10-24 | [13 empty] | 150 | 150 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 150 | 0 | 300 | 53% | 159 | 459 | 459 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 459 | M & S | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.5 | Transportation and Logistics | 1.2.1.5 Transportation and Logistics | cell-link@smartsheet.com | 2021-12-02 12:52 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.5.1.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 229.5 | 229.5 | 0 | 1.2.1.5.1.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 150 | 0 | 300 | 1.2.1.5.1.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79.5 | 79.5 | 0 | 159 | 459 | 1.2.1.5.1.22 | 459 | 459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 229.5 | 459 | 459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 229.5 | 459 | 459
| 1.2 | 1.2.1.5.1.23 | C |  | PSL | Crate: Control Systems Components to PTH (Comsur) |  | 2.222% | Labor Hours | EN |  |  |  | 115 | 0% | 2022-07-08 | 2022-07-27 | [13 empty] | 20 | 20 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2300 | 2300 | 0 | 4600 | 0% | 0 | 4799.9263 | 4799.9263 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | [9 empty] | 4799.9263 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.5 | Transportation and Logistics | 1.2.1.5 Transportation and Logistics | cell-link@smartsheet.com | 2021-12-02 12:56 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.5.1.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2399.9632 | 2399.9632 | 0 | 1.2.1.5.1.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2399.9632 | 2399.9632 | 0 | 4799.9263 | 1.2.1.5.1.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4799.9263 | 1.2.1.5.1.23 | 4799.9263 | 6672.6463 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2399.9632 | 4799.9263 | 4799.9263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3336.3232 | 6672.6463 | 6672.6463
| 1.2 | 1.2.1.5.1.23 | C |  | PSL | Crate: Control Systems Components to PTH (Comsur) |  |  | M & S |  |  |  |  | 1 | 0% | 2022-07-08 | 2022-07-27 | [13 empty] | 612 | 612 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 612 | 612 | 0 | 1224 | 53% | 648.72 | 1872.72 | 1872.72 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 1872.72 | M & S | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.5 | Transportation and Logistics | 1.2.1.5 Transportation and Logistics | cell-link@smartsheet.com | 2021-12-02 12:56 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.5.1.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 936.36 | 936.36 | 0 | 1.2.1.5.1.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 612 | 612 | 0 | 1224 | 1.2.1.5.1.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 324.36 | 324.36 | 0 | 648.72 | 1872.72 | 1.2.1.5.1.23 | 1872.72 | 1872.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 936.36 | 1872.72 | 1872.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 936.36 | 1872.72 | 1872.72
| 1.2 | 1.2.1.5.1.24 | C |  | PSL | Crate: Drill Filtration & Degassing Equipment to PTH (Comsur) |  | 0% | Labor Hours | EN |  |  |  | 115 | 0% | 2021-10-15 | 2021-11-04 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [7 empty] | 8 | 8 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 920 | 920 | 0 | 0 | 0 | 1840 | 0% | 0 | 1961.2499 | 1961.2499 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | [9 empty] | 1961.2499 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.5 | Transportation and Logistics | 1.2.1.5 Transportation and Logistics | cell-link@smartsheet.com | 2021-12-02 12:56 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.5.1.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 980.625 | 980.625 | 0 | 0 | 0 | 1.2.1.5.1.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.1.5.1.24 | C |  | PSL | Crate: Drill Filtration & Degassing Equipment to PTH (Comsur) |  |  | M & S | EN |  |  |  | 1 | 0% | 2021-10-15 | 2021-11-04 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [7 empty] | 25 | 25 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 25 | 0 | 0 | 0 | 50 | 53% | 26.5 | 76.5 | 76.5 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 76.5 | M & S | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.5 | Transportation and Logistics | 1.2.1.5 Transportation and Logistics | cell-link@smartsheet.com | 2021-12-02 12:56 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.5.1.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38.25 | 38.25 | 0 | 0 | 0 | 1.2.1.5.1.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.1.5.1.25 | C |  | PSL | Crate: Resupply to PTH (Vessel) |  | 0% | Labor Hours | EN |  |  |  | 115 | 0% | 2023-06-06 | 2023-07-04 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [8 empty] | 250 | 250 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28750 | 28750 | 0 | 0 | 57500 | 0% | 0 | 61289.0596 | 61289.0596 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | [9 empty] | 61289.0596 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.5 | Transportation and Logistics | 1.2.1.5 Transportation and Logistics | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.5.1.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30644.5298 | 30644.5298 | 0 | 0 | 1.2.1.5.1.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.1.5.1.25 | C |  | PSL | Crate: Resupply to PTH (Vessel) |  |  | M & S | EN |  |  |  | 1 | 0% | 2023-06-06 | 2023-07-04 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 0 | M & S | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.5 | Transportation and Logistics | 1.2.1.5 Transportation and Logistics | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.5.1.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.1.5.2.1 | C |  | PSL | Ship: MHP Replacements & Spares to PTH (Comsur) |  |  | M & S |  |  |  | 1 | 1 | 0% | 2021-11-15 | 2021-11-15 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 | [5 empty] | 1683 |  | 0 | M & S | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.5 | Transportation and Logistics | 1.2.1.5 Transportation and Logistics | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.5.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.1.5.2.2 | C |  | PSL | Ship: PHS Replacements & Spares to PTH (Comsur) |  |  | M & S |  |  |  | 1 | 1 | 0% | 2021-11-15 | 2021-11-15 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 | [5 empty] | 1683 |  | 0 | M & S | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.5 | Transportation and Logistics | 1.2.1.5 Transportation and Logistics | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.5.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.1.5.2.3 | C |  | PSL | Ship: Fuel Systems & Tower Components to PTH (Comsur) |  |  | M & S |  |  |  | 1 | 1 | 0% | 2021-11-15 | 2021-11-15 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 | [5 empty] | 1683 |  | 0 | M & S | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.5 | Transportation and Logistics | 1.2.1.5 Transportation and Logistics | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.5.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.1.5.2.4 | C |  | PSL | Ship: TOS Components & Spares to PTH (Comsur) |  |  | M & S |  |  |  | 1 | 1 | 0% | 2021-11-15 | 2021-11-15 | [15 empty] | 3672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3672 | 3672 | 53% | 1946.16 | 5618.16 | 5618.16 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 | [5 empty] | 3672 |  | 5618.16 | M & S | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.5 | Transportation and Logistics | 1.2.1.5 Transportation and Logistics | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.5.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5618.16 | 1.2.1.5.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3672 | 3672 | 1.2.1.5.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1946.16 | 1946.16 | 5618.16 | 1.2.1.5.2.4 | 5618.16 | 5618.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5618.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5618.16
| 1.2 | 1.2.1.5.2.5 | C |  | PSL | Ship: GEN-2, 3, PDM - Ship Components, Repair Parts to PTH (Comsur) |  |  | M & S |  |  |  | 81 | 1 | 0% | 2021-11-15 | 2021-11-15 |  | TRUE | [13 empty] | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 500 | 53% | 265 | 765 | 765 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 | 0 |  |  |  |  | 3371 |  | 765 | M & S | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.5 | Transportation and Logistics | 1.2.1.5 Transportation and Logistics | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 5d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.5.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 765 | 1.2.1.5.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 500 | 1.2.1.5.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 265 | 265 | 765 | 1.2.1.5.2.5 | 765 | 765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 765
| 1.2 | 1.2.1.5.2.6 | C |  | PSL | Ship: Control Systems Components to PTH (Comsur) |  |  | M & S |  |  |  | 1 | 1 | 0% | 2022-08-01 | 2022-08-01 |  | TRUE | [13 empty] | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 1000 | 53% | 530 | 1530 | 1530 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 | [5 empty] | 1377 |  | 1530 | M & S | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.5 | Transportation and Logistics | 1.2.1.5 Transportation and Logistics | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 5d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.5.2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1530 | 1.2.1.5.2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 1000 | 1.2.1.5.2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 530 | 530 | 1530 | 1.2.1.5.2.6 | 1530 | 1530 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1530 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1530
| 1.2 | 1.2.1.5.2.7 | C |  | PSL | Ship: Elec. Distribution System to PTH (Comsur) |  |  | M & S |  |  |  | 1 | 1 | 0% | 2022-11-15 | 2022-11-15 |  | TRUE | [13 empty] | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 1000 | 53% | 530 | 1530 | 1530 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 | [5 empty] | 22950 |  | 1530 | M & S | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.5 | Transportation and Logistics | 1.2.1.5 Transportation and Logistics | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.5.2.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1530 | 1.2.1.5.2.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 1000 | 1.2.1.5.2.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 530 | 530 | 1530 | 1.2.1.5.2.7 | 1530 | 1530 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1530 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1530
| 1.2 | 1.2.1.5.2.8 | C |  | PSL | Ship: WT Repair Parts, Replacements to PTH (Comsur) |  |  | M & S |  |  |  |  | 1 | 0% | 2022-11-15 | 2022-11-15 | [15 empty] | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 1000 | 53% | 530 | 1530 | 1530 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 1530 | M & S | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.5 | Transportation and Logistics | 1.2.1.5 Transportation and Logistics | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.5.2.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1530 | 1.2.1.5.2.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 1000 | 1.2.1.5.2.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 530 | 530 | 1530 | 1.2.1.5.2.8 | 1530 | 1530 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1530 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1530
| 1.2 | 1.2.1.5.2.9 | C |  | PSL | Ship: Pump Repair/Replace Components to PTH (Comsur) |  |  | M & S |  |  |  |  | 1 | 0% | 2022-11-15 | 2022-11-15 | [15 empty] | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 1000 | 53% | 530 | 1530 | 1530 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 1530 | M & S | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.5 | Transportation and Logistics | 1.2.1.5 Transportation and Logistics | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.5.2.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1530 | 1.2.1.5.2.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 1000 | 1.2.1.5.2.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 530 | 530 | 1530 | 1.2.1.5.2.9 | 1530 | 1530 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1530 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1530
| 1.2 | 1.2.1.5.2.10 | C |  | PSL | Ship: Condensate Management Components to PTH (Comsur) |  |  | M & S |  |  |  |  | 1 | 0% | 2022-11-15 | 2022-11-15 | [15 empty] | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 1500 | 53% | 795 | 2295 | 2295 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 2295 | M & S | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.5 | Transportation and Logistics | 1.2.1.5 Transportation and Logistics | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.5.2.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2295 | 1.2.1.5.2.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 1500 | 1.2.1.5.2.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 795 | 795 | 2295 | 1.2.1.5.2.10 | 2295 | 2295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2295
| 1.2 | 1.2.1.5.2.11 | C |  | PSL | Ship: MDS Internal Hoses & Spares to PTH (Comsur) |  |  | M & S |  |  |  |  | 1 | 0% | 2022-11-15 | 2022-11-15 | [15 empty] | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2200 | 2200 | 53% | 1166 | 3366 | 3366 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 3366 | M & S | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.5 | Transportation and Logistics | 1.2.1.5 Transportation and Logistics | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.5.2.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3366 | 1.2.1.5.2.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2200 | 2200 | 1.2.1.5.2.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1166 | 1166 | 3366 | 1.2.1.5.2.11 | 3366 | 3366 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3366 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3366
| 1.2 | 1.2.1.5.2.12 | C |  | PSL | Ship: ARA Drill Subsystem Parts to PTH (Comsur) |  |  | M & S |  |  |  |  | 1 | 0% | 2022-08-01 | 2022-08-01 | [15 empty] | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 500 | 53% | 265 | 765 | 765 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 765 | M & S | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.5 | Transportation and Logistics | 1.2.1.5 Transportation and Logistics | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.5.2.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 765 | 1.2.1.5.2.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 500 | 1.2.1.5.2.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 265 | 265 | 765 | 1.2.1.5.2.12 | 765 | 765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 765
| 1.2 | 1.2.1.5.2.13 | C |  | PSL | Ship: Shop Parts, Spares, etc. to PTH (Comsur) |  |  | M & S |  |  |  |  | 1 | 0% | 2021-11-15 | 2021-11-15 | [15 empty] | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 1000 | 53% | 530 | 1530 | 1530 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 1530 | M & S | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.5 | Transportation and Logistics | 1.2.1.5 Transportation and Logistics | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.5.2.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1530 | 1.2.1.5.2.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 1000 | 1.2.1.5.2.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 530 | 530 | 1530 | 1.2.1.5.2.13 | 1530 | 1530 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1530 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1530
| 1.2 | 1.2.1.5.2.14 | C |  | PSL | Ship: Cable Reels Main and RWCR to PTH (Vessel) |  | 0.8889% | Labor Hours | EN |  |  |  | 115 | 0% | 2021-11-15 | 2021-11-15 | [5 empty] | 16 | [10 empty] | 0 | 1840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1840 | 0% | 0 | 1919.9705 | 1919.9705 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | [9 empty] | 1919.9705 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.5 | Transportation and Logistics | 1.2.1.5 Transportation and Logistics | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.5.2.14 | 0 | 1919.9705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.14 | 0 | 1919.9705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1919.9705 | 1.2.1.5.2.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1919.9705 | 1.2.1.5.2.14 | 1919.9705 | 7274.9705 | 0 | 1919.9705 | 1919.9705 | 1919.9705 | 1919.9705 | 1919.9705 | 1919.9705 | 1919.9705 | 1919.9705 | 1919.9705 | 1919.9705 | 1919.9705 | 0 | 7274.9705 | 7274.9705 | 7274.9705 | 7274.9705 | 7274.9705 | 7274.9705 | 7274.9705 | 7274.9705 | 7274.9705 | 7274.9705 | 7274.9705
| 1.2 | 1.2.1.5.2.14 | C |  | PSL | Ship: Cable Reels Main and RWCR to PTH (Vessel) |  |  | M & S |  |  |  |  | 1 | 0% | 2021-11-15 | 2021-11-15 | [5 empty] | 3500 | [10 empty] | 0 | 3500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3500 | 53% | 1855 | 5355 | 5355 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 5355 | M & S | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.5 | Transportation and Logistics | 1.2.1.5 Transportation and Logistics | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.5.2.14 | 0 | 5355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.14 | 0 | 3500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3500 | 1.2.1.5.2.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.14 | 0 | 1855 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1855 | 5355 | 1.2.1.5.2.14 | 5355 | 5355 | 0 | 5355 | 5355 | 5355 | 5355 | 5355 | 5355 | 5355 | 5355 | 5355 | 5355 | 5355 | 0 | 5355 | 5355 | 5355 | 5355 | 5355 | 5355 | 5355 | 5355 | 5355 | 5355 | 5355
| 1.2 | 1.2.1.5.2.15 | C |  | PSL | Ship: Surface Hose to PTH Outdoor Storage MCM (Vessel) |  |  | M & S |  |  |  |  | 1 | 0% | 2021-02-15 | 2021-02-15 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 0 | M & S | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.5 | Transportation and Logistics | 1.2.1.5 Transportation and Logistics | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.5.2.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.1.5.2.16 | C |  | PSL | Ship: Spare Main Drill & Combo Cables to PTH (Vessel) |  |  | M & S |  |  |  | 1 | 1 | 0% | 2022-11-17 | 2022-11-17 | [5 empty] | 1500 | [10 empty] | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 53% | 795 | 2295 | 2295 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 | [5 empty] | 1683 |  | 2295 | M & S | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.5 | Transportation and Logistics | 1.2.1.5 Transportation and Logistics | cell-link@smartsheet.com | 2021-12-02 13:21 |  | 1d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.5.2.16 | 0 | 2295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.16 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 1.2.1.5.2.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.16 | 0 | 795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 795 | 2295 | 1.2.1.5.2.16 | 2295 | 2295 | 0 | 2295 | 2295 | 2295 | 2295 | 2295 | 2295 | 2295 | 2295 | 2295 | 2295 | 2295 | 0 | 2295 | 2295 | 2295 | 2295 | 2295 | 2295 | 2295 | 2295 | 2295 | 2295 | 2295
| 1.2 | 1.2.1.5.2.17 | C |  | PSL | Ship: GEN-2, 3, PDM - Skis from to PTH (Vessel) |  |  | M & S |  |  |  | 1 | 1 | 0% | 2021-02-15 | 2021-02-15 |  | TRUE |  | Heavy shipment | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 | 0 |  |  |  |  | 1683 |  | 0 | M & S | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.5 | Transportation and Logistics | 1.2.1.5 Transportation and Logistics | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.5.2.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.1.5.2.18 | C |  | PSL | Ship: Generator Hoods to PTH (Vessel) |  |  | M & S |  |  |  | 1 | 1 | 0% | 2020-11-15 | 2020-11-15 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 | [5 empty] | 1683 |  | 0 | M & S | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.5 | Transportation and Logistics | 1.2.1.5 Transportation and Logistics | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.5.2.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.1.5.2.19 | C |  | PSL | Ship: Hose Reel Heating System to PTH (Vessel) |  |  | M & S |  |  |  | 1 | 1 | 0% | 2022-11-17 | 2022-11-17 | [5 empty] | 1100 | [10 empty] | 0 | 1100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1100 | 53% | 583 | 1683 | 1683 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 | 0 |  |  |  |  | 3366 |  | 1683 | M & S | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.5 | Transportation and Logistics | 1.2.1.5 Transportation and Logistics | cell-link@smartsheet.com | 2021-12-02 13:21 |  | 1d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.5.2.19 | 0 | 1683 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.19 | 0 | 1100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1100 | 1.2.1.5.2.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.19 | 0 | 583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 583 | 1683 | 1.2.1.5.2.19 | 1683 | 1683 | 0 | 1683 | 1683 | 1683 | 1683 | 1683 | 1683 | 1683 | 1683 | 1683 | 1683 | 1683 | 0 | 1683 | 1683 | 1683 | 1683 | 1683 | 1683 | 1683 | 1683 | 1683 | 1683 | 1683
| 1.2 | 1.2.1.5.2.20 | C |  | PSL | Ship: SES Interconnect Materials/Parts to PTH (Comsur) |  |  | M & S |  |  |  | 1 | 1 | 0% | 2022-11-15 | 2022-11-15 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [11 empty] | 3500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3500 | 3500 | 53% | 1855 | 5355 | 5355 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 | [5 empty] | 3366 |  | 5355 | M & S | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.5 | Transportation and Logistics | 1.2.1.5 Transportation and Logistics | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.5.2.20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5355 | 1.2.1.5.2.20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.1.5.2.21 | C |  | PSL | Ship: Repair/Replacement Components to PTH (Comsur) |  |  | M & S |  |  |  | 1 | 1 | 0% | 2023-08-01 | 2023-08-01 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [11 empty] | 1100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1100 | 1100 | 53% | 583 | 1683 | 1683 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 | [5 empty] | 1683 |  | 1683 | M & S | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.5 | Transportation and Logistics | 1.2.1.5 Transportation and Logistics | cell-link@smartsheet.com | 2021-12-02 13:21 |  | 1d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.5.2.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1683 | 1.2.1.5.2.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.1.5.2.22 | C |  | PSL | Ship: Drill Filtration & Degassing Equipment to PTH (Comsur) |  |  | M & S |  |  |  |  | 1 | 0% | 2021-11-15 | 2021-11-15 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [11 empty] | 1100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1100 | 1100 | 53% | 583 | 1683 | 1683 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 1683 | M & S | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.5 | Transportation and Logistics | 1.2.1.5 Transportation and Logistics | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.5.2.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1683 | 1.2.1.5.2.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.1.5.2.23 | C |  | PSL | Ship: Control Systems Components to PTH (Comsur) |  |  | M & S |  |  |  |  | 1 | 0% | 2023-09-01 | 2023-09-01 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [11 empty] | 3500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3500 | 3500 | 53% | 1855 | 5355 | 5355 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 5355 | M & S | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.5 | Transportation and Logistics | 1.2.1.5 Transportation and Logistics | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.5.2.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5355 | 1.2.1.5.2.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.1.5.2.24 | C |  | PSL | Ship: Drill Heads, Spare Parts to PTH (Vessel) Store in ICL |  |  | M & S |  |  |  |  | 1 | 0% | 2023-11-15 | 2023-11-15 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 |  | 1500 | [10 empty] | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 53% | 795 | 2295 | 2295 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 2295 | M & S | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.5 | Transportation and Logistics | 1.2.1.5 Transportation and Logistics | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.5.2.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.24 | 0 | 2295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.1.5.2.25 | C |  | PSL | Ship: Resupply to PTH (Vessel) |  |  | M & S |  |  |  |  | 1 | 0% | 2024-08-01 | 2024-08-01 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [10 empty] | 3500 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3500 | 0 | 3500 | 53% | 1855 | 5355 | 5355 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 5355 | M & S | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.1 | Drill Management & Systems Engineering | 1.2.1 Drill Management & Systems Engineering | 1.2.1.5 | Transportation and Logistics | 1.2.1.5 Transportation and Logistics | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.1.5.2.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5355 | 0 | 1.2.1.5.2.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.2.1.1 | C |  | PSL | MHP: Identify Parts - Upgrade & Spares (Driller_PSL_Lead) | Gibson | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2021-02-04 | 2021-04-28 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 4600 | 0 | [5 empty] | 4600 |  | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.2 | Thermal Plant | 1.2.2 Thermal Plant | 1.2.2.1 | Main Heating Plants | 1.2.2.1 Main Heating Plants | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 95d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.2.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.2.1.2 | C |  | PSL | MHP: Procure Parts Upgrade & Spares - (Driller_PSL_Lead) | Gibson | 0.4444% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2021-04-15 | 2021-08-18 | [10 empty] | 8 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 920 | 0 | 0 | 0 | 0 | 0 | 920 | 0% | 0 | 959.9853 | 959.9853 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 4601 | 0 | [5 empty] | 4601 |  | 959.9853 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.2 | Thermal Plant | 1.2.2 Thermal Plant | 1.2.2.1 | Main Heating Plants | 1.2.2.1 Main Heating Plants | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 143d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 959.9853 | 0 | 0 | 0 | 0 | 0 | 1.2.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 959.9853 | 0 | 0 | 0 | 0 | 0 | 959.9853 | 1.2.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 959.9853 | 1.2.2.1.2 | 959.9853 | 55871.6081 | 0 | 0 | 0 | 0 | 0 | 0 | 959.9853 | 959.9853 | 959.9853 | 959.9853 | 959.9853 | 959.9853 | 0 | 0 | 0 | 0 | 0 | 0 | 28415.7967 | 55871.6081 | 55871.6081 | 55871.6081 | 55871.6081 | 55871.6081
| 1.2 | 1.2.2.1.2 | C |  | PSL | MHP: Procure Parts Upgrade & Spares - (Driller_PSL_Lead) |  | 0.8889% | Labor Hours | TE |  |  | 115 | 77 | 0% | 2021-04-15 | 2021-08-18 | [10 empty] | 8 | 8 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 616 | 616 | 0 | 0 | 0 | 0 | 1232 | 0% | 0 | 1285.5455 | 1285.5455 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 4601 | 0 | [5 empty] | 4601 |  | 1285.5455 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.2 | Thermal Plant | 1.2.2 Thermal Plant | 1.2.2.1 | Main Heating Plants | 1.2.2.1 Main Heating Plants | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 143d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 642.7727 | 642.7727 | 0 | 0 | 0 | 0 | 1.2.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 642.7727 | 642.7727 | 0 | 0 | 0 | 0 | 1285.5455 | 1.2.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1285.5455 | 1.2.2.1.2 | 1285.5455 | 54911.6228 | 0 | 0 | 0 | 0 | 0 | 0 | 642.7727 | 1285.5455 | 1285.5455 | 1285.5455 | 1285.5455 | 1285.5455 | 0 | 0 | 0 | 0 | 0 | 0 | 27455.8114 | 54911.6228 | 54911.6228 | 54911.6228 | 54911.6228 | 54911.6228
| 1.2 | 1.2.2.1.2 | C |  | PSL | MHP: Procure Parts Upgrade & Spares - (Driller_PSL_Lead) | Undergrad | 2.222% | Labor Hours | UG |  |  | 115 | 15 | 0% | 2021-04-15 | 2021-08-18 | [10 empty] | 20 | 20 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 300 | 0 | 0 | 0 | 0 | 600 | 0% | 0 | 626.0774 | 626.0774 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 4601 | 0 | [5 empty] | 4601 |  | 626.0774 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.2 | Thermal Plant | 1.2.2 Thermal Plant | 1.2.2.1 | Main Heating Plants | 1.2.2.1 Main Heating Plants | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 143d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 313.0387 | 313.0387 | 0 | 0 | 0 | 0 | 1.2.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 313.0387 | 313.0387 | 0 | 0 | 0 | 0 | 626.0774 | 1.2.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 626.0774 | 1.2.2.1.2 | 626.0774 | 53626.0773 | 0 | 0 | 0 | 0 | 0 | 0 | 313.0387 | 626.0774 | 626.0774 | 626.0774 | 626.0774 | 626.0774 | 0 | 0 | 0 | 0 | 0 | 0 | 26813.0387 | 53626.0773 | 53626.0773 | 53626.0773 | 53626.0773 | 53626.0773
| 1.2 | 1.2.2.1.2 | C |  | PSL | MHP: Procure Parts Upgrade & Spares - Stacks Driller_PSL_Lead) |  |  | CapEx | UG |  |  | 115 | 1 | 0% | 2021-04-15 | 2021-08-18 | [10 empty] | 26500 | 26500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 26500 | 26500 | 0 | 0 | 0 | 0 | 53000 | 53% | 0 | 53000 | 53000 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 4601 | 0 | [5 empty] | 4601 |  | 53000 | CapEx | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.2 | Thermal Plant | 1.2.2 Thermal Plant | 1.2.2.1 | Main Heating Plants | 1.2.2.1 Main Heating Plants | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 143d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 26500 | 26500 | 0 | 0 | 0 | 0 | 1.2.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 26500 | 26500 | 0 | 0 | 0 | 0 | 53000 | 1.2.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53000 | 1.2.2.1.2 | 53000 | 53000 | 0 | 0 | 0 | 0 | 0 | 0 | 26500 | 53000 | 53000 | 53000 | 53000 | 53000 | 0 | 0 | 0 | 0 | 0 | 0 | 26500 | 53000 | 53000 | 53000 | 53000 | 53000
| 1.2 | 1.2.2.1.3 | C |  | PSL | MHP: Assemble and Test Components (flowmeters. PRV, control boxes) |  | 4.222% | Labor Hours | EN |  | HD | 1 | 115 | 0% | 2022-04-15 | 2022-08-18 | [10 empty] | 20 | 24 | 26 | 6 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 2300 | 2760 | 2990 | 690 | 0 | 0 | 8740 | 0% | 0 | 9119.8601 | 9119.8601 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 43176 | 0 | [5 empty] | 43176 |  | 9119.8601 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.2 | Thermal Plant | 1.2.2 Thermal Plant | 1.2.2.1 | Main Heating Plants | 1.2.2.1 Main Heating Plants | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 143d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.2.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 2399.9632 | 2879.9558 | 3119.9521 | 719.989 | 0 | 0 | 1.2.2.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 2399.9632 | 2879.9558 | 3119.9521 | 719.989 | 0 | 0 | 9119.8601 | 1.2.2.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9119.8601 | 1.2.2.1.3 | 9119.8601 | 14622.951 | 0 | 0 | 0 | 0 | 0 | 0 | 2399.9632 | 5279.919 | 8399.8711 | 9119.8601 | 9119.8601 | 9119.8601 | 0 | 0 | 0 | 0 | 0 | 0 | 5974.7359 | 9497.4645 | 13260.1894 | 14622.951 | 14622.951 | 14622.951
| 1.2 | 1.2.2.1.3 | C |  | PSL | MHP: Assemble and Test Components (flowmeters. PRV, control boxes) |  | 1.778% | Labor Hours | TE |  | HD | 1 | 77 | 0% | 2022-04-15 | 2022-08-18 | [10 empty] | 8 | 8 | 8 | 8 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 616 | 616 | 616 | 616 | 0 | 0 | 2464 | 0% | 0 | 2571.091 | 2571.091 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 43176 | 0 | [5 empty] | 43176 |  | 2571.091 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.2 | Thermal Plant | 1.2.2 Thermal Plant | 1.2.2.1 | Main Heating Plants | 1.2.2.1 Main Heating Plants | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 143d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.2.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 642.7727 | 642.7727 | 642.7727 | 642.7727 | 0 | 0 | 1.2.2.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 642.7727 | 642.7727 | 642.7727 | 642.7727 | 0 | 0 | 2571.091 | 1.2.2.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2571.091 | 1.2.2.1.3 | 2571.091 | 5503.091 | 0 | 0 | 0 | 0 | 0 | 0 | 642.7727 | 1285.5455 | 1928.3182 | 2571.091 | 2571.091 | 2571.091 | 0 | 0 | 0 | 0 | 0 | 0 | 3574.7727 | 4217.5455 | 4860.3182 | 5503.091 | 5503.091 | 5503.091
| 1.2 | 1.2.2.1.3 | C |  | PSL | MHP: Assemble and Test Components (flowmeters. PRV, control boxes) |  |  | CapEx | TE |  | HD | 1 | 1 | 0% | 2022-04-15 | 2022-08-18 | [10 empty] | 2932 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 2932 | 0 | 0 | 0 | 0 | 0 | 2932 | 53% | 0 | 2932 | 2932 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 43176 | 0 | [5 empty] | 43176 |  | 2932 | CapEx | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.2 | Thermal Plant | 1.2.2 Thermal Plant | 1.2.2.1 | Main Heating Plants | 1.2.2.1 Main Heating Plants | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 143d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.2.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 2932 | 0 | 0 | 0 | 0 | 0 | 1.2.2.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 2932 | 0 | 0 | 0 | 0 | 0 | 2932 | 1.2.2.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2932 | 1.2.2.1.3 | 2932 | 2932 | 0 | 0 | 0 | 0 | 0 | 0 | 2932 | 2932 | 2932 | 2932 | 2932 | 2932 | 0 | 0 | 0 | 0 | 0 | 0 | 2932 | 2932 | 2932 | 2932 | 2932 | 2932
| 1.2 | 1.2.2.1.4 | C |  | PSL | MHP: Design and Construct MHP Flush & Pressure Test Kit | Benson | 0.8889% | Labor Hours | EN |  |  |  | 115 | 0% | 2022-04-15 | 2022-08-18 | [10 empty] | 8 | 8 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 920 | 920 | 0 | 0 | 0 | 0 | 1840 | 0% | 0 | 1919.9705 | 1919.9705 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | [9 empty] | 1919.9705 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.2 | Thermal Plant | 1.2.2 Thermal Plant | 1.2.2.1 | Main Heating Plants | 1.2.2.1 Main Heating Plants | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 143d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.2.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 959.9853 | 959.9853 | 0 | 0 | 0 | 0 | 1.2.2.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 959.9853 | 959.9853 | 0 | 0 | 0 | 0 | 1919.9705 | 1.2.2.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1919.9705 | 1.2.2.1.4 | 1919.9705 | 6498.2888 | 0 | 0 | 0 | 0 | 0 | 0 | 959.9853 | 1919.9705 | 1919.9705 | 1919.9705 | 1919.9705 | 1919.9705 | 0 | 0 | 0 | 0 | 0 | 0 | 4574.1444 | 6498.2888 | 6498.2888 | 6498.2888 | 6498.2888 | 6498.2888
| 1.2 | 1.2.2.1.4 | C |  | PSL | MHP: Design and Construct MHP Flush & Pressure Test Kit | Benson | 1.333% | Labor Hours | TE |  |  |  | 77 | 0% | 2022-04-15 | 2022-08-18 | [10 empty] | 12 | 12 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 924 | 924 | 0 | 0 | 0 | 0 | 1848 | 0% | 0 | 1928.3182 | 1928.3182 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | [9 empty] | 1928.3182 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.2 | Thermal Plant | 1.2.2 Thermal Plant | 1.2.2.1 | Main Heating Plants | 1.2.2.1 Main Heating Plants | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 143d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.2.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 964.1591 | 964.1591 | 0 | 0 | 0 | 0 | 1.2.2.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 964.1591 | 964.1591 | 0 | 0 | 0 | 0 | 1928.3182 | 1.2.2.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1928.3182 | 1.2.2.1.4 | 1928.3182 | 4578.3182 | 0 | 0 | 0 | 0 | 0 | 0 | 964.1591 | 1928.3182 | 1928.3182 | 1928.3182 | 1928.3182 | 1928.3182 | 0 | 0 | 0 | 0 | 0 | 0 | 3614.1591 | 4578.3182 | 4578.3182 | 4578.3182 | 4578.3182 | 4578.3182
| 1.2 | 1.2.2.1.4 | C |  | PSL | MHP: Design and Construct MHP Flush & Pressure Test Kit |  |  | CapEx | EN |  |  |  | 1 | 0% | 2022-04-15 | 2022-08-18 | [10 empty] | 2650 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 2650 | 0 | 0 | 0 | 0 | 0 | 2650 | 53% | 0 | 2650 | 2650 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 2650 | CapEx | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.2 | Thermal Plant | 1.2.2 Thermal Plant | 1.2.2.1 | Main Heating Plants | 1.2.2.1 Main Heating Plants | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 143d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.2.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 2650 | 0 | 0 | 0 | 0 | 0 | 1.2.2.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 2650 | 0 | 0 | 0 | 0 | 0 | 2650 | 1.2.2.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2650 | 1.2.2.1.4 | 2650 | 2650 | 0 | 0 | 0 | 0 | 0 | 0 | 2650 | 2650 | 2650 | 2650 | 2650 | 2650 | 0 | 0 | 0 | 0 | 0 | 0 | 2650 | 2650 | 2650 | 2650 | 2650 | 2650
| 1.2 | 1.2.2.1.5 | C |  | PSL | MHP: Build Electronics Kit for MHP1, Heater 7 |  | 0% | Labor Hours | EN |  | HD |  | 115 | 0% | 2022-04-15 | 2022-08-18 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | [9 empty] | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.2 | Thermal Plant | 1.2.2 Thermal Plant | 1.2.2.1 | Main Heating Plants | 1.2.2.1 Main Heating Plants | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 143d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.2.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.2.1.5 | C |  | PSL | MHP: Build Electronics Kit for MHP1, Heater 7 |  |  | CapEx |  |  | HD |  | 1 | 0% | 2022-04-15 | 2022-08-18 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 0 | CapEx | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.2 | Thermal Plant | 1.2.2 Thermal Plant | 1.2.2.1 | Main Heating Plants | 1.2.2.1 Main Heating Plants | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 143d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.2.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.2.1.6 | C |  | PSL | MHP: Procure Upgrade, Sub-Components, Spares (2022-23) | Gibson | 0% | Labor Hours | EN |  |  |  | 115 | 0% | 2023-04-15 | 2023-08-17 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [6 empty] | 20 | 20 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 2300 | 2300 | 0 | 0 | 0 | 0 | 4600 | 0% | 0 | 4903.1248 | 4903.1248 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | [9 empty] | 4903.1248 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.2 | Thermal Plant | 1.2.2 Thermal Plant | 1.2.2.1 | Main Heating Plants | 1.2.2.1 Main Heating Plants | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 143d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.2.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 2451.5624 | 2451.5624 | 0 | 0 | 0 | 0 | 1.2.2.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.2.1.6 | C |  | PSL | MHP: Procure Parts Upgrade & Spares - (Driller_PSL_Lead) |  |  | CapEx |  |  | HD | 1 | 1 | 0% | 2023-04-15 | 2023-08-17 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [6 empty] | 1500 | 1500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 1500 | 0 | 0 | 0 | 0 | 3000 | 53% | 0 | 3000 | 3000 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 43177 | [5 empty] | 43177 |  | 3000 | CapEx | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.2 | Thermal Plant | 1.2.2 Thermal Plant | 1.2.2.1 | Main Heating Plants | 1.2.2.1 Main Heating Plants | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 144d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.2.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 1500 | 0 | 0 | 0 | 0 | 1.2.2.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.2.1.8 | C |  | PSL | MHP: Procure and Assemble HPU2 Integration Components |  | 2.222% | Labor Hours | EN |  | HD |  | 115 | 0% | 2022-06-20 | 2022-10-21 | [10 empty] | 5 | 5 | 10 | 10 | 10 |  | 0 | 0 | 0 | 0 | 0 | 0 | 575 | 575 | 1150 | 1150 | 1150 | 0 | 4600 | 0% | 0 | 4799.9263 | 4799.9263 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | [9 empty] | 4799.9263 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.2 | Thermal Plant | 1.2.2 Thermal Plant | 1.2.2.1 | Main Heating Plants | 1.2.2.1 Main Heating Plants | cell-link@smartsheet.com | 2021-11-30 14:12 |  | 144d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.2.1.8 | 0 | 0 | 0 | 0 | 0 | 0 | 599.9908 | 599.9908 | 1199.9816 | 1199.9816 | 1199.9816 | 0 | 1.2.2.1.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.1.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.1.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.1.8 | 0 | 0 | 0 | 0 | 0 | 0 | 599.9908 | 599.9908 | 1199.9816 | 1199.9816 | 1199.9816 | 0 | 4799.9263 | 1.2.2.1.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.1.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4799.9263 | 1.2.2.1.8 | 4799.9263 | 4799.9263 | 0 | 0 | 0 | 0 | 0 | 0 | 599.9908 | 1199.9816 | 2399.9632 | 3599.9448 | 4799.9263 | 4799.9263 | 0 | 0 | 0 | 0 | 0 | 0 | 599.9908 | 1199.9816 | 2399.9632 | 3599.9448 | 4799.9263 | 4799.9263
| 1.2 | 1.2.2.2.1 | C |  | PSL | PHS: Refine PHS Plumbing Upgrade Design | Benson | 0.4444% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2020-10-02 | 2021-02-18 |  | TRUE | [10 empty] | 4 | 4 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 460 | 460 | 0 | 0 | 920 | 0% | 0 | 959.9853 | 959.9853 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 9384 | [5 empty] | 9384 |  | 959.9853 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.2 | Thermal Plant | 1.2.2 Thermal Plant | 1.2.2.2 | Pre Heat System | 1.2.2.2 Pre Heat System | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 236d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.2.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 479.9926 | 479.9926 | 0 | 0 | 1.2.2.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 479.9926 | 479.9926 | 0 | 0 | 959.9853 | 1.2.2.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 959.9853 | 1.2.2.2.1 | 959.9853 | 3459.9853 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 479.9926 | 959.9853 | 959.9853 | 959.9853 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2979.9926 | 3459.9853 | 3459.9853 | 3459.9853
| 1.2 | 1.2.2.2.1 | C |  | PSL | PHS: Refine PHS Plumbing Upgrade Design | Benson |  | CapEx | EN |  |  | 115 | 1 | 0% | 2020-10-02 | 2021-02-18 |  | TRUE | [10 empty] | 2500 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 0 | 0 | 0 | 2500 | 53% | 0 | 2500 | 2500 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 9384 | [5 empty] | 9384 |  | 2500 | CapEx | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.2 | Thermal Plant | 1.2.2 Thermal Plant | 1.2.2.2 | Pre Heat System | 1.2.2.2 Pre Heat System | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 236d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.2.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 0 | 0 | 0 | 1.2.2.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 0 | 0 | 0 | 2500 | 1.2.2.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 1.2.2.2.1 | 2500 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 2500 | 2500 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 2500 | 2500 | 2500
| 1.2 | 1.2.2.2.2 | C |  | PSL | PHS: Identify Parts Upgrade & Spares | Duling | 0.4444% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2021-10-01 | 2023-06-16 | [13 empty] | 4 | 4 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 460 | 460 | 0 | 920 | 0% | 0 | 959.9853 | 959.9853 | [7 empty] | 8 | 8 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 920 | 920 | 0 | 0 | 0 | 1840 | 0% | 0 | 1961.2499 | 1961.2499 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 4692 | [5 empty] | 4692 |  | 2921.2352 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.2 | Thermal Plant | 1.2.2 Thermal Plant | 1.2.2.2 | Pre Heat System | 1.2.2.2 Pre Heat System | cell-link@smartsheet.com | 2021-11-30 14:28 |  | 143d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.2.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 479.9926 | 479.9926 | 0 | 1.2.2.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 980.625 | 980.625 | 0 | 0 | 0 | 1.2.2.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 479.9926 | 479.9926 | 0 | 959.9853 | 1.2.2.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 959.9853 | 1.2.2.2.2 | 959.9853 | 959.9853 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 479.9926 | 959.9853 | 959.9853 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 479.9926 | 959.9853 | 959.9853
| 1.2 | 1.2.2.2.3 | C |  | PSL | PHS: Procure and Upgrade Control Boxes |  | 1.333% | Labor Hours | EN |  |  | 81 | 115 | 0% | 2022-05-17 | 2022-08-17 | [11 empty] | 12 | 12 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1380 | 1380 | 0 | 0 | 0 | 2760 | 0% | 0 | 2879.9558 | 2879.9558 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 3305 | [5 empty] | 3305 |  | 2879.9558 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.2 | Thermal Plant | 1.2.2 Thermal Plant | 1.2.2.2 | Pre Heat System | 1.2.2.2 Pre Heat System | cell-link@smartsheet.com | 2021-11-30 14:32 |  | 143d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1439.9779 | 1439.9779 | 0 | 0 | 0 | 1.2.2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1439.9779 | 1439.9779 | 0 | 0 | 0 | 2879.9558 | 1.2.2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2879.9558 | 1.2.2.2.3 | 2879.9558 | 10808.274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1439.9779 | 2879.9558 | 2879.9558 | 2879.9558 | 2879.9558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2404.137 | 7808.274 | 7808.274 | 10808.274 | 10808.274
| 1.2 | 1.2.2.2.3 | C |  | PSL | PHS: Procure and Upgrade Control Boxes |  | 1.333% | Labor Hours | TE |  |  | 81 | 77 | 0% | 2022-05-17 | 2022-08-17 | [11 empty] | 12 | 12 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 924 | 924 | 0 | 0 | 0 | 1848 | 0% | 0 | 1928.3182 | 1928.3182 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 3305 | [5 empty] | 3305 |  | 1928.3182 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.2 | Thermal Plant | 1.2.2 Thermal Plant | 1.2.2.2 | Pre Heat System | 1.2.2.2 Pre Heat System | cell-link@smartsheet.com | 2021-11-30 14:32 |  | 143d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 964.1591 | 964.1591 | 0 | 0 | 0 | 1.2.2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 964.1591 | 964.1591 | 0 | 0 | 0 | 1928.3182 | 1.2.2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1928.3182 | 1.2.2.2.3 | 1928.3182 | 7928.3182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 964.1591 | 1928.3182 | 1928.3182 | 1928.3182 | 1928.3182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 964.1591 | 4928.3182 | 4928.3182 | 7928.3182 | 7928.3182
| 1.2 | 1.2.2.2.3 | C |  | PSL | PHS: Procure and Upgrade Control Boxes |  |  | CapEx |  |  | HD |  | 1 | 0% | 2022-05-17 | 2022-08-17 | [12 empty] | 3000 |  | 3000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 0 | 3000 | 0 | 6000 | 53% | 0 | 6000 | 6000 | [7 empty] | 500 | 500 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 500 | 0 | 0 | 0 | 1000 | 53% | 0 | 1000 | 1000 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 7000 | CapEx | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.2 | Thermal Plant | 1.2.2 Thermal Plant | 1.2.2.2 | Pre Heat System | 1.2.2.2 Pre Heat System | cell-link@smartsheet.com | 2021-11-30 14:32 |  | 236d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 0 | 3000 | 0 | 1.2.2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 500 | 0 | 0 | 0 | 1.2.2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 0 | 3000 | 0 | 6000 | 1.2.2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 1.2.2.2.3 | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 3000 | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 3000 | 6000 | 6000
| 1.2 | 1.2.2.3.1 | C |  | PSL | Fuel Systems: Review & Redesign (5k Tank-Tower) (PSL_Engineer) | Benson | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2020-10-01 | 2021-01-20 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 9384 | [5 empty] | 9384 |  | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.2 | Thermal Plant | 1.2.2 Thermal Plant | 1.2.2.3 | Fuel Storage and Delivery | 1.2.2.3 Fuel Storage and Delivery | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 95d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.2.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.2.3.2 | C |  | PSL | Fuel Systems: Procurement (Hose, Valves, Sensors, Controls Etc.) | Benson | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2021-10-05 | 2022-08-19 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [9 empty] | 16 | 20 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1840 | 2300 | 0 | 4140 | 0% | 0 | 4412.8123 | 4412.8123 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 4692 | [5 empty] | 4692 |  | 4412.8123 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.2 | Thermal Plant | 1.2.2 Thermal Plant | 1.2.2.3 | Fuel Storage and Delivery | 1.2.2.3 Fuel Storage and Delivery | cell-link@smartsheet.com | 2021-11-30 14:28 |  | 95d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.2.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1961.2499 | 2451.5624 | 0 | 1.2.2.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.2.3.2 | C |  | PSL | Fuel Systems: Procurement (Hose, Valves, Sensors, Controls, Etc.) |  |  | CapEx |  |  |  | 1 | 1 | 0% | 2021-10-05 | 2022-08-19 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [9 empty] | 1800 | 1800 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 1800 | 0 | 3600 | 53% | 0 | 3600 | 3600 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 6863.5 | [5 empty] | 13727 |  | 3600 | CapEx | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.2 | Thermal Plant | 1.2.2 Thermal Plant | 1.2.2.3 | Fuel Storage and Delivery | 1.2.2.3 Fuel Storage and Delivery | cell-link@smartsheet.com | 2021-11-30 14:28 |  | 95d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.2.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 1800 | 0 | 1.2.2.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.2.3.3 | C |  | PSL | Fuel Tower: Review Design & Specs, Field Inputs - Develop Plan (PSL_Engineer) | Benson | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2020-11-02 | 2020-12-11 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 14076 | [5 empty] | 14076 |  | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.2 | Thermal Plant | 1.2.2 Thermal Plant | 1.2.2.3 | Fuel Storage and Delivery | 1.2.2.3 Fuel Storage and Delivery | cell-link@smartsheet.com | 2021-11-30 14:34 |  | 47d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.2.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.2.3.4 | C |  | PSL | Fuel Tower: Redesign Components (PSL_Engineer) | Benson | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2020-11-02 | 2020-12-11 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 9384 | [5 empty] | 18768 |  | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.2 | Thermal Plant | 1.2.2 Thermal Plant | 1.2.2.3 | Fuel Storage and Delivery | 1.2.2.3 Fuel Storage and Delivery | cell-link@smartsheet.com | 2021-11-30 14:17 |  | 47d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.2.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.2.3.6 | C |  | PSL | Fuel Tower: Procure Upgrade-Replacements, Spares (PSL_Engineer) | Benson | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2021-03-23 | 2023-05-02 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 4692 | [5 empty] | 9384 |  | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.2 | Thermal Plant | 1.2.2 Thermal Plant | 1.2.2.3 | Fuel Storage and Delivery | 1.2.2.3 Fuel Storage and Delivery | cell-link@smartsheet.com | 2021-11-30 14:17 |  | 47d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.2.3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.2.3.6 | C |  | PSL | Fuel Tower: Procure Upgrade-Replacements, Spares |  |  | CapEx |  |  |  | 1 | 1 | 0% | 2021-03-23 | 2023-05-02 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 10083.5 | [5 empty] | 20167 |  | 0 | CapEx | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.2 | Thermal Plant | 1.2.2 Thermal Plant | 1.2.2.3 | Fuel Storage and Delivery | 1.2.2.3 Fuel Storage and Delivery | cell-link@smartsheet.com | 2021-11-30 14:17 |  | 47d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.2.3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.2.3.7 | C |  | PSL | Fuel Tower: Fuel Sled Panel Updates - Interface Integration | Laundrie | 10.83% | Labor Hours | EN |  |  |  | 115 | 0% | 2022-05-31 | 2022-09-22 | [12 empty] | 40 | 55 | 50 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4600 | 6325 | 5750 | 5750 | 22425 | 0% | 0 | 23399.641 | 23399.641 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | [9 empty] | 23399.641 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.2 | Thermal Plant | 1.2.2 Thermal Plant | 1.2.2.3 | Fuel Storage and Delivery | 1.2.2.3 Fuel Storage and Delivery | cell-link@smartsheet.com | 2021-11-30 14:28 |  | 47d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.2.3.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4799.9263 | 6599.8987 | 5999.9079 | 5999.9079 | 1.2.2.3.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.3.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.3.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.3.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4799.9263 | 6599.8987 | 5999.9079 | 5999.9079 | 23399.641 | 1.2.2.3.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.3.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23399.641 | 1.2.2.3.7 | 23399.641 | 23399.641 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4799.9263 | 11399.8251 | 17399.733 | 23399.641 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4799.9263 | 11399.8251 | 17399.733 | 23399.641
| 1.2 | 1.2.2.3.7 | C |  | PSL | Fuel Tower: Fuel Sled Panel Updates - Interface Integration |  |  | CapEx |  |  |  |  | 1 | 0% | 2022-05-31 | 2022-09-22 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 0 | CapEx | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.2 | Thermal Plant | 1.2.2 Thermal Plant | 1.2.2.3 | Fuel Storage and Delivery | 1.2.2.3 Fuel Storage and Delivery | cell-link@smartsheet.com | 2021-11-30 14:28 |  | 47d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.2.3.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.3.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.3.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.3.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.3.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.3.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.3.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2.3.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.3.1.1 | C |  | PSL | Tower Ops: Reassess Down Hole Loads - String/DOM Configurations (PSL_Engineer) | Greenler | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2019-03-01 | 2020-05-01 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 9038 | 167 | [5 empty] | 9204 |  | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.3 | Tower Operations Site | 1.2.3 Tower Operations Site | 1.2.3.1 | Tower Operations Structures (TOS and Tower) | 1.2.3.1 Tower Operations Structures (TOS and Tower) | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 216d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.3.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.3.1.2 | C |  | PSL | Tower Ops: Perform Structural Review of Tower & Components (PSL_Drafter) |  | 0% | Labor Hours | TE |  |  | 81 | 77 | 0% | 2021-05-03 | 2021-06-11 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 6610 | [5 empty] | 6610 |  | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.3 | Tower Operations Site | 1.2.3 Tower Operations Site | 1.2.3.1 | Tower Operations Structures (TOS and Tower) | 1.2.3.1 Tower Operations Structures (TOS and Tower) | cell-link@smartsheet.com | 2021-11-30 14:45 |  | 72d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.3.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.3.1.2 | C |  | PSL | Tower Ops: Perform Structural Review of Tower & Components (PSL_Engineer) | Benson | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2021-05-03 | 2021-06-11 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 9384 | [5 empty] | 9384 |  | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.3 | Tower Operations Site | 1.2.3 Tower Operations Site | 1.2.3.1 | Tower Operations Structures (TOS and Tower) | 1.2.3.1 Tower Operations Structures (TOS and Tower) | cell-link@smartsheet.com | 2021-11-30 14:45 |  | 72d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.3.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.3.1.3 | C |  | PSL | Tower Ops: Crescent & Belt Refurbishment (4 ea) (PSL_Shop) |  | 0.4444% | Labor Hours | EN |  |  | 81 | 115 | 0% | 2022-06-01 | 2022-06-28 |  | TRUE | [10 empty] | 8 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 920 | 0 | 0 | 0 | 920 | 0% | 0 | 959.9853 | 959.9853 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 33048 | [5 empty] | 33048 |  | 959.9853 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.3 | Tower Operations Site | 1.2.3 Tower Operations Site | 1.2.3.1 | Tower Operations Structures (TOS and Tower) | 1.2.3.1 Tower Operations Structures (TOS and Tower) | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 144d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.3.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 959.9853 | 0 | 0 | 0 | 1.2.3.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 959.9853 | 0 | 0 | 0 | 959.9853 | 1.2.3.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 959.9853 | 1.2.3.1.3 | 959.9853 | 5928.8354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 959.9853 | 959.9853 | 959.9853 | 959.9853 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5928.8354 | 5928.8354 | 5928.8354 | 5928.8354
| 1.2 | 1.2.3.1.3 | C |  | PSL | Tower Ops: Crescent & Belt Refurbishment (4 ea) (PSL_Shop) |  | 0.4444% | Labor Hours | TE |  |  | 81 | 77 | 0% | 2022-06-01 | 2022-06-28 |  | TRUE | [10 empty] | 8 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 616 | 0 | 0 | 0 | 616 | 0% | 0 | 642.7727 | 642.7727 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 33048 | [5 empty] | 33048 |  | 642.7727 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.3 | Tower Operations Site | 1.2.3 Tower Operations Site | 1.2.3.1 | Tower Operations Structures (TOS and Tower) | 1.2.3.1 Tower Operations Structures (TOS and Tower) | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 144d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.3.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 642.7727 | 0 | 0 | 0 | 1.2.3.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 642.7727 | 0 | 0 | 0 | 642.7727 | 1.2.3.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 642.7727 | 1.2.3.1.3 | 642.7727 | 4968.8501 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 642.7727 | 642.7727 | 642.7727 | 642.7727 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4968.8501 | 4968.8501 | 4968.8501 | 4968.8501
| 1.2 | 1.2.3.1.3 | C |  | PSL | Tower Ops: Crescent & Belt Refurbishment (4 ea) |  | 2.222% | Labor Hours | UG |  |  | 81 | 15 | 0% | 2022-06-01 | 2022-06-28 |  | TRUE | [10 empty] | 40 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600 | 0 | 0 | 0 | 600 | 0% | 0 | 626.0774 | 626.0774 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 3305 | [5 empty] | 3305 |  | 626.0774 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.3 | Tower Operations Site | 1.2.3 Tower Operations Site | 1.2.3.1 | Tower Operations Structures (TOS and Tower) | 1.2.3.1 Tower Operations Structures (TOS and Tower) | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 144d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.3.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 626.0774 | 0 | 0 | 0 | 1.2.3.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 626.0774 | 0 | 0 | 0 | 626.0774 | 1.2.3.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 626.0774 | 1.2.3.1.3 | 626.0774 | 4326.0773 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 626.0774 | 626.0774 | 626.0774 | 626.0774 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4326.0773 | 4326.0773 | 4326.0773 | 4326.0773
| 1.2 | 1.2.3.1.3 | C |  | PSL | Tower Ops: Crescent & Belt Refurbishment (4 ea) |  |  | CapEx |  |  | EE | 1 | 1 | 0% | 2022-06-01 | 2022-06-28 |  | TRUE | [10 empty] | 3700 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3700 | 0 | 0 | 0 | 3700 | 53% | 0 | 3700 | 3700 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 31608 | [5 empty] | 31608 |  | 3700 | CapEx | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.3 | Tower Operations Site | 1.2.3 Tower Operations Site | 1.2.3.1 | Tower Operations Structures (TOS and Tower) | 1.2.3.1 Tower Operations Structures (TOS and Tower) | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 144d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.3.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3700 | 0 | 0 | 0 | 1.2.3.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3700 | 0 | 0 | 0 | 3700 | 1.2.3.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3700 | 1.2.3.1.3 | 3700 | 3700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3700 | 3700 | 3700 | 3700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3700 | 3700 | 3700 | 3700
| 1.2 | 1.2.3.1.5 | P |  | PSL | Tower Ops: Test Replacement Load Cells & Encoders (PSL_Engineer) | Laundrie | 3.333% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2022-03-15 | 2022-03-15 |  | TRUE | [6 empty] | 30 | 30 | [6 empty] | 0 | 0 | 0 | 0 | 3450 | 3450 | 0 | 0 | 0 | 0 | 0 | 0 | 6900 | 0% | 0 | 7199.8895 | 7199.8895 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 4692 | [5 empty] | 4692 |  | 7199.8895 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.3 | Tower Operations Site | 1.2.3 Tower Operations Site | 1.2.3.1 | Tower Operations Structures (TOS and Tower) | 1.2.3.1 Tower Operations Structures (TOS and Tower) | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 72d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.3.1.5 | 0 | 0 | 0 | 0 | 3599.9448 | 3599.9448 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.1.5 | 0 | 0 | 0 | 0 | 3599.9448 | 3599.9448 | 0 | 0 | 0 | 0 | 0 | 0 | 7199.8895 | 1.2.3.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7199.8895 | 1.2.3.1.5 | 7199.8895 | 7199.8895 | 0 | 0 | 0 | 0 | 3599.9448 | 7199.8895 | 7199.8895 | 7199.8895 | 7199.8895 | 7199.8895 | 7199.8895 | 7199.8895 | 0 | 0 | 0 | 0 | 3599.9448 | 7199.8895 | 7199.8895 | 7199.8895 | 7199.8895 | 7199.8895 | 7199.8895 | 7199.8895
| 1.2 | 1.2.3.1.5 | P |  | PSL | Tower Ops: Test Replacement Load Cells & Encoders |  |  | CapEx |  |  | VQ | 1 | 1 | 0% | 2022-03-15 | 2022-03-15 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 15168 | [5 empty] | 15168 |  | 0 | CapEx | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.3 | Tower Operations Site | 1.2.3 Tower Operations Site | 1.2.3.1 | Tower Operations Structures (TOS and Tower) | 1.2.3.1 Tower Operations Structures (TOS and Tower) | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 72d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.3.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.3.1.6 | C |  | PSL | Tower Ops: Identify/Procure: TOS & Tower Hardware, Repair Parts (Driller_PSL_Lead) | Gibson | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2021-10-08 | 2023-07-04 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [9 empty] | 18 | 20 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2070 | 2300 | 0 | 4370 | 0% | 0 | 4657.9685 | 4657.9685 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | 4692 |  |  |  |  | 4692 |  | 4657.9685 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.3 | Tower Operations Site | 1.2.3 Tower Operations Site | 1.2.3.1 | Tower Operations Structures (TOS and Tower) | 1.2.3.1 Tower Operations Structures (TOS and Tower) | cell-link@smartsheet.com | 2021-11-30 14:45 |  | 24d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.3.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2206.4061 | 2451.5624 | 0 | 1.2.3.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.3.1.6 | C |  | PSL | Tower Ops: Identify/Procure: TOS & Tower Hardware, Repair Parts |  |  | CapEx |  |  | HD | 1 | 1 | 0% | 2021-10-08 | 2023-07-04 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [9 empty] | 1200 | 1200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 1200 | 0 | 2400 | 53% | 0 | 2400 | 2400 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 26214 | [5 empty] | 26214 |  | 2400 | CapEx | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.3 | Tower Operations Site | 1.2.3 Tower Operations Site | 1.2.3.1 | Tower Operations Structures (TOS and Tower) | 1.2.3.1 Tower Operations Structures (TOS and Tower) | cell-link@smartsheet.com | 2021-11-30 14:45 |  | 24d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.3.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 1200 | 0 | 1.2.3.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.3.2.2 | C |  | PSL | Drillhead: Software subsystem testing (PSL_Engineer) | Xiang | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2021-04-16 | 2021-05-13 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 5803 | 3465 | [5 empty] | 9268 |  | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.3 | Tower Operations Site | 1.2.3 Tower Operations Site | 1.2.3.2 | Drillheads | 1.2.3.2 Drillheads | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 47d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.3.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.3.2.2 | C |  | PSL | Drillhead: Software subsystem testing (PSL_Technician) |  | 0% | Labor Hours | TE |  |  | 81 | 77 | 0% | 2021-04-16 | 2021-05-13 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 2044 | 1220 | [5 empty] | 3264 |  | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.3 | Tower Operations Site | 1.2.3 Tower Operations Site | 1.2.3.2 | Drillheads | 1.2.3.2 Drillheads | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 47d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.3.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.3.2.2 | C |  | PSL | Drillhead: Software subsystem testing |  |  | CapEx |  |  | HD | 1 | 1 | 0% | 2021-04-16 | 2021-05-13 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 3154 | 1846 | [5 empty] | 5000 |  | 0 | CapEx | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.3 | Tower Operations Site | 1.2.3 Tower Operations Site | 1.2.3.2 | Drillheads | 1.2.3.2 Drillheads | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 47d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.3.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.3.2.3 | C |  | PSL | Drillhead: Rework/rewrite drillhead software (PSL_Engineer) |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2021-03-12 | 2021-05-13 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 18768 | [5 empty] | 18768 |  | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.3 | Tower Operations Site | 1.2.3 Tower Operations Site | 1.2.3.2 | Drillheads | 1.2.3.2 Drillheads | cell-link@smartsheet.com | 2021-11-30 14:50 |  | 95d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.3.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.3.2.7 | C |  | PSL | Drillhead: Update Drillheads for Cable |  | 0% | Labor Hours | EN |  | HD |  | 115 | 0% | 2022-03-16 | 2022-05-17 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | [9 empty] | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.3 | Tower Operations Site | 1.2.3 Tower Operations Site | 1.2.3.2 | Drillheads | 1.2.3.2 Drillheads | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 47d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.3.2.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.3.2.7 | C |  | PSL | Drillhead: Update Drillheads for Cable |  | 0% | Labor Hours | TE |  | HD |  | 77 | 0% | 2022-03-16 | 2022-05-17 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | [9 empty] | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.3 | Tower Operations Site | 1.2.3 Tower Operations Site | 1.2.3.2 | Drillheads | 1.2.3.2 Drillheads | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 47d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.3.2.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.3.2.8 | C |  | PSL | Drillhead: Pressure Test Drillhead Hanger & Spare Hose |  | 0% | Labor Hours | EN |  |  |  | 115 | 0% | 2022-03-16 | 2022-05-17 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  | 8 | [9 empty] | 0 | 0 | 920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 920 | 0% | 0 | 980.625 | 980.625 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | [9 empty] | 980.625 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.3 | Tower Operations Site | 1.2.3 Tower Operations Site | 1.2.3.2 | Drillheads | 1.2.3.2 Drillheads | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 95d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.3.2.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.8 | 0 | 0 | 980.625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.3.2.8 | C |  | PSL | Drillhead: Pressure Test Drillhead Hanger & Spare Hose |  |  | CapEx | TE |  |  |  | 1 | 0% | 2022-03-16 | 2022-05-17 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 |  |  | 1000 | [9 empty] | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 53% | 0 | 1000 | 1000 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 1000 | CapEx | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.3 | Tower Operations Site | 1.2.3 Tower Operations Site | 1.2.3.2 | Drillheads | 1.2.3.2 Drillheads | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 95d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.3.2.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.8 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.3.3.1 | C |  | PSL | Reels & Winches: MCR - Rebuild & Upgrade (PSL_Mechanical_Engineer) |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2020-11-02 | 2021-02-19 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 2544 | 16173 | [5 empty] | 18717 |  | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.3 | Tower Operations Site | 1.2.3 Tower Operations Site | 1.2.3.3 | Reels & Winches | 1.2.3.3 Reels & Winches | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 239d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.3.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.3.3.1 | C |  | PSL | Reels & Winches: MCR - Rebuild & Upgrade (PSL_ Electrical_Engineer) |  | 0% | Labor Hours | EN |  |  | 81 | 115 | 0% | 2020-11-02 | 2021-02-19 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 1792 | 11392 | [5 empty] | 13183 |  | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.3 | Tower Operations Site | 1.2.3 Tower Operations Site | 1.2.3.3 | Reels & Winches | 1.2.3.3 Reels & Winches | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 239d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.3.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.3.3.1 | C |  | PSL | Reels & Winches: MCR - Test (PSL_Engineer) |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2020-11-02 | 2021-02-19 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 2544 | 16173 | [5 empty] | 18717 |  | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.3 | Tower Operations Site | 1.2.3 Tower Operations Site | 1.2.3.3 | Reels & Winches | 1.2.3.3 Reels & Winches | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 239d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.3.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.3.3.1 | C |  | PSL | Reels & Winches: MCR - Test (PSL_ Software_Engineer) |  | 0% | Labor Hours | TE |  |  | 81 | 77 | 0% | 2020-11-02 | 2021-02-19 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 3583 | 22783 | [5 empty] | 26367 |  | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.3 | Tower Operations Site | 1.2.3 Tower Operations Site | 1.2.3.3 | Reels & Winches | 1.2.3.3 Reels & Winches | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 239d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.3.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.3.3.2 | C |  | PSL | Reels & Winches: Return Water Cable Reel - Rebuild & Upgrade (PSL_Mechanical_Engineer) |  | 0.8889% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2020-11-02 | 2021-03-05 |  |  |  |  | 8 | 8 | [10 empty] | 920 | 920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1840 | 0% | 0 | 1919.9705 | 1919.9705 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 3903.0796 | 5481 |  |  |  |  | 9384 |  | 1919.9705 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.3 | Tower Operations Site | 1.2.3 Tower Operations Site | 1.2.3.3 | Reels & Winches | 1.2.3.3 Reels & Winches | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 47d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.3.3.2 | 959.9853 | 959.9853 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.3.2 | 959.9853 | 959.9853 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1919.9705 | 1.2.3.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1919.9705 | 1.2.3.3.2 | 1919.9705 | 1919.9705 | 959.9853 | 1919.9705 | 1919.9705 | 1919.9705 | 1919.9705 | 1919.9705 | 1919.9705 | 1919.9705 | 1919.9705 | 1919.9705 | 1919.9705 | 1919.9705 | 959.9853 | 1919.9705 | 1919.9705 | 1919.9705 | 1919.9705 | 1919.9705 | 1919.9705 | 1919.9705 | 1919.9705 | 1919.9705 | 1919.9705 | 1919.9705
| 1.2 | 1.2.3.3.2 | C |  | PSL | Reels & Winches: Return Water Cable Reel - Rebuild & Upgrade (PSL_ Electrical_Engineer) |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2020-11-02 | 2021-03-05 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 3903.0796 | 5481 |  |  |  |  | 9384 |  | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.3 | Tower Operations Site | 1.2.3 Tower Operations Site | 1.2.3.3 | Reels & Winches | 1.2.3.3 Reels & Winches | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 47d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.3.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.3.3.2 | C |  | PSL | Reels & Winches: Return Water Cable Reel - Test (PSL_Software_Engineer) |  | 0% | Labor Hours | EN |  | EE | 1 | 115 | 0% | 2020-11-02 | 2021-03-05 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 25000 | [5 empty] | 25000 |  | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.3 | Tower Operations Site | 1.2.3 Tower Operations Site | 1.2.3.3 | Reels & Winches | 1.2.3.3 Reels & Winches | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 47d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.3.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.3.3.2 | C |  | PSL | Reels & Winches: Return Water Cable Reel - Test (PSL_Electrical_Engineer) |  | 0% | Labor Hours | EN |  | EE |  | 115 | 0% | 2020-11-02 | 2021-03-05 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | [9 empty] | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.3 | Tower Operations Site | 1.2.3 Tower Operations Site | 1.2.3.3 | Reels & Winches | 1.2.3.3 Reels & Winches | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 47d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.3.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.3.3.3 | C |  | PSL | Reels & Winches: MSHR - Procure Replacement Parts (Driller_PSL_Lead) | Duling | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2021-04-05 | 2023-06-27 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [7 empty] | 25 | 25 | 25 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2875 | 2875 | 2875 | 0 | 0 | 8625 | 0% | 0 | 9193.3589 | 9193.3589 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 3986.1239 | 5398 |  |  |  |  | 9384 |  | 9193.3589 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.3 | Tower Operations Site | 1.2.3 Tower Operations Site | 1.2.3.3 | Reels & Winches | 1.2.3.3 Reels & Winches | cell-link@smartsheet.com | 2021-11-30 14:58 |  | 47d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.3.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3064.453 | 3064.453 | 3064.453 | 0 | 0 | 1.2.3.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.3.3.3 | C |  | PSL | Reels & Winches: MSHR - Procure Replacement Parts (PSL_Engineer) | Benson |  | CapEx | EN |  |  | 115 | 1 | 0% | 2021-04-05 | 2023-06-27 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 3986.1239 | 5398 |  |  |  |  | 9384 |  | 0 | CapEx | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.3 | Tower Operations Site | 1.2.3 Tower Operations Site | 1.2.3.3 | Reels & Winches | 1.2.3.3 Reels & Winches | cell-link@smartsheet.com | 2021-11-30 14:58 |  | 47d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.3.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.3.3.3 | C |  | PSL | Reels & Winches: MSHR - Procure Replacement Parts |  |  | CapEx |  |  | EE | 1 | 1 | 0% | 2021-04-05 | 2023-06-27 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [7 empty] | 1200 | 1200 | 1200 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 1200 | 1200 | 0 | 0 | 3600 | 53% | 0 | 3600 | 3600 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 11973 | [5 empty] | 11973 |  | 3600 | CapEx | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.3 | Tower Operations Site | 1.2.3 Tower Operations Site | 1.2.3.3 | Reels & Winches | 1.2.3.3 Reels & Winches | cell-link@smartsheet.com | 2021-11-30 14:58 |  | 47d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.3.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 1200 | 1200 | 0 | 0 | 1.2.3.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.3.3.5 | C |  | PSL | Reels & Winches: TU-20 Winches (at NPX) - Plan/Procure Replacement Parts (Driller_PSL_Lead) |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2021-02-01 | 2021-04-23 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [8 empty] | 15 | 15 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1725 | 1725 | 0 | 0 | 3450 | 0% | 0 | 3677.3436 | 3677.3436 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 9384 | [5 empty] | 9384 |  | 3677.3436 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.3 | Tower Operations Site | 1.2.3 Tower Operations Site | 1.2.3.3 | Reels & Winches | 1.2.3.3 Reels & Winches | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 119d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.3.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1838.6718 | 1838.6718 | 0 | 0 | 1.2.3.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.3.3.5 | C |  | PSL | Reels & Winches: TU-20 Winches - Plan/Procure Replacement Parts |  |  | CapEx |  |  | EE | 1 | 1 | 0% | 2021-02-01 | 2021-04-23 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [8 empty] | 500 | 500 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 500 | 0 | 0 | 1000 | 53% | 0 | 1000 | 1000 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 25000 | [5 empty] | 25000 |  | 1000 | CapEx | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.3 | Tower Operations Site | 1.2.3 Tower Operations Site | 1.2.3.3 | Reels & Winches | 1.2.3.3 Reels & Winches | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 119d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.3.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 500 | 0 | 0 | 1.2.3.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.3.3.7 | C |  | PSL | Reels & Winches: Main Drill Cable Reel/Main Hose Reel Load Sharing Testing |  | 67.61% | Labor Hours | EN |  | EE |  | 115 | 0% | 2021-12-01 | 2022-09-30 | [6 empty] | 121.7 | 121.7 | 121.7 | 121.7 | 121.7 | 121.7 | 121.7 | 121.7 | 121.7 | 121.7 | 0 | 0 | 13995.5 | 13995.5 | 13995.5 | 13995.5 | 13995.5 | 13995.5 | 13995.5 | 13995.5 | 13995.5 | 13995.5 | 139955 | 0% | 0 | 146037.7592 | 146037.7592 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | [9 empty] | 146037.7592 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.3 | Tower Operations Site | 1.2.3 Tower Operations Site | 1.2.3.3 | Reels & Winches | 1.2.3.3 Reels & Winches | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 119d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.3.3.7 | 0 | 0 | 14603.7759 | 14603.7759 | 14603.7759 | 14603.7759 | 14603.7759 | 14603.7759 | 14603.7759 | 14603.7759 | 14603.7759 | 14603.7759 | 1.2.3.3.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.3.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.3.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.3.7 | 0 | 0 | 14603.7759 | 14603.7759 | 14603.7759 | 14603.7759 | 14603.7759 | 14603.7759 | 14603.7759 | 14603.7759 | 14603.7759 | 14603.7759 | 146037.7592 | 1.2.3.3.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.3.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 146037.7592 | 1.2.3.3.7 | 146037.7592 | 200540.7372 | 0 | 0 | 14603.7759 | 29207.5518 | 43811.3278 | 58415.1037 | 73018.8796 | 87622.6555 | 102226.4314 | 116830.2074 | 131433.9833 | 146037.7592 | 0 | 0 | 27147.1737 | 54294.3474 | 81441.5212 | 98455.6949 | 115469.8686 | 132484.0423 | 149498.216 | 166512.3897 | 183526.5635 | 200540.7372
| 1.2 | 1.2.3.3.7 | C |  | PSL | Reels & Winches: Main Drill Cable Reel/Main Hose Reel Load Sharing Testing |  | 16.67% | Labor Hours | TE |  | EE |  | 77 | 0% | 2021-12-01 | 2022-09-30 | [6 empty] | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 0 | 0 | 2310 | 2310 | 2310 | 2310 | 2310 | 2310 | 2310 | 2310 | 2310 | 2310 | 23100 | 0% | 0 | 24103.978 | 24103.978 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | [9 empty] | 24103.978 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.3 | Tower Operations Site | 1.2.3 Tower Operations Site | 1.2.3.3 | Reels & Winches | 1.2.3.3 Reels & Winches | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 119d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.3.3.7 | 0 | 0 | 2410.3978 | 2410.3978 | 2410.3978 | 2410.3978 | 2410.3978 | 2410.3978 | 2410.3978 | 2410.3978 | 2410.3978 | 2410.3978 | 1.2.3.3.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.3.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.3.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.3.7 | 0 | 0 | 2410.3978 | 2410.3978 | 2410.3978 | 2410.3978 | 2410.3978 | 2410.3978 | 2410.3978 | 2410.3978 | 2410.3978 | 2410.3978 | 24103.978 | 1.2.3.3.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.3.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24103.978 | 1.2.3.3.7 | 24103.978 | 54502.978 | 0 | 0 | 2410.3978 | 4820.7956 | 7231.1934 | 9641.5912 | 12051.989 | 14462.3868 | 16872.7846 | 19283.1824 | 21693.5802 | 24103.978 | 0 | 0 | 12543.3978 | 25086.7956 | 37630.1934 | 40040.5912 | 42450.989 | 44861.3868 | 47271.7846 | 49682.1824 | 52092.5802 | 54502.978
| 1.2 | 1.2.3.3.7 | C |  | PSL | Reels & Winches: Main Drill Cable Reel/Main Hose Reel Load Sharing Testing |  |  | CapEx | EN |  | EE |  | 1 | 0% | 2021-12-01 | 2022-09-30 | [6 empty] | 10133 | 10133 | 10133 | [7 empty] | 0 | 0 | 10133 | 10133 | 10133 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30399 | 53% | 0 | 30399 | 30399 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 30399 | CapEx | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.3 | Tower Operations Site | 1.2.3 Tower Operations Site | 1.2.3.3 | Reels & Winches | 1.2.3.3 Reels & Winches | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 119d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.3.3.7 | 0 | 0 | 10133 | 10133 | 10133 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.3.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.3.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.3.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.3.7 | 0 | 0 | 10133 | 10133 | 10133 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30399 | 1.2.3.3.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.3.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30399 | 1.2.3.3.7 | 30399 | 30399 | 0 | 0 | 10133 | 20266 | 30399 | 30399 | 30399 | 30399 | 30399 | 30399 | 30399 | 30399 | 0 | 0 | 10133 | 20266 | 30399 | 30399 | 30399 | 30399 | 30399 | 30399 | 30399 | 30399
| 1.2 | 1.2.3.4.2 | C |  | PSL | Main Drill Hose: Confirm & Specify Drill Hose (PSL_Engineer) |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2019-10-01 | 2019-11-25 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 9384 | [5 empty] | 9384 |  | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.3 | Tower Operations Site | 1.2.3 Tower Operations Site | 1.2.3.4 | Downhole Main Drill Hose | 1.2.3.4 Downhole Main Drill Hose | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 48d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.3.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.3.4.3 | C |  | PSL | Main Drill Hose: Procure Hose (Manufacture by IVG) (PSL_Engineer) |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2019-09-17 | 2020-08-17 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 4662 | [5 empty] | 4662 |  | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.3 | Tower Operations Site | 1.2.3 Tower Operations Site | 1.2.3.4 | Downhole Main Drill Hose | 1.2.3.4 Downhole Main Drill Hose | cell-link@smartsheet.com | 2021-11-30 15:05 |  | 288d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.3.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.3.4.6 | C |  | PSL | Main Drill Hose: Manufacture Strain Reliefs (at PSL) (PSL_Drafter) |  | 0% | Labor Hours | TE |  |  | 81 | 77 | 0% | 2019-09-13 | 2020-01-02 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 6610 | [5 empty] | 6610 |  | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.3 | Tower Operations Site | 1.2.3 Tower Operations Site | 1.2.3.4 | Downhole Main Drill Hose | 1.2.3.4 Downhole Main Drill Hose | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 96d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.3.4.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.4.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.4.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.4.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.4.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.4.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.4.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.4.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.3.4.6 | C |  | PSL | Main Drill Hose: Manufacture Strain Reliefs (at PSL) (PSL_Shop) |  | 0% | Labor Hours | TE |  |  | 81 | 77 | 0% | 2019-09-13 | 2020-01-02 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 49572 | [5 empty] | 49572 |  | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.3 | Tower Operations Site | 1.2.3 Tower Operations Site | 1.2.3.4 | Downhole Main Drill Hose | 1.2.3.4 Downhole Main Drill Hose | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 96d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.3.4.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.4.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.4.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.4.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.4.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.4.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.4.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.4.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.3.4.6 | C |  | PSL | Main Drill Hose: Manufacture Strain Reliefs (at PSL) (PSL_Engineer) |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2019-09-13 | 2020-01-02 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 9384 | [5 empty] | 9384 |  | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.3 | Tower Operations Site | 1.2.3 Tower Operations Site | 1.2.3.4 | Downhole Main Drill Hose | 1.2.3.4 Downhole Main Drill Hose | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 96d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.3.4.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.4.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.4.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.4.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.4.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.4.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.4.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.4.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.3.4.7 | C |  | PSL | Main Drill Hose: Ship Strain Reliefs to Italy (Mnftr Install on Hose) (Driller_PSL_DirectHire) |  | 0% | Labor Hours | TE |  |  | 81 | 77 | 0% | 2020-01-03 | 2020-07-16 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 1322 | [5 empty] | 1322 |  | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.3 | Tower Operations Site | 1.2.3 Tower Operations Site | 1.2.3.4 | Downhole Main Drill Hose | 1.2.3.4 Downhole Main Drill Hose | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 168d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.3.4.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.4.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.4.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.4.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.4.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.4.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.4.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.4.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.3.4.8 | C |  | PSL | Main Drill Hose: Prepare Hose at PSL, Crate for Shipment, Hold 1 Year (Driller_PSL_Lead) |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2020-11-17 | 2020-11-23 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 1877 | [5 empty] | 1877 |  | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.3 | Tower Operations Site | 1.2.3 Tower Operations Site | 1.2.3.4 | Downhole Main Drill Hose | 1.2.3.4 Downhole Main Drill Hose | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 2d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.3.4.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.4.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.4.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.4.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.4.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.4.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.4.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.4.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.3.5.1 | C |  | PSL | Drill Cables: Main Drill Cable Spec Review & Revisions (PSL_Engineer) |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2019-10-01 | 2020-03-13 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 4692 | [5 empty] | 4692 |  | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.3 | Tower Operations Site | 1.2.3 Tower Operations Site | 1.2.3.5 | Downhole Main Cables | 1.2.3.5 Downhole Main Cables | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 72d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.3.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.3.5.2 | C |  | PSL | Drill Cables: Combo Cable - Spec Review & Revisions (PSL_Engineer) |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2019-10-01 | 2020-03-13 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 4692 | [5 empty] | 4692 |  | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.3 | Tower Operations Site | 1.2.3 Tower Operations Site | 1.2.3.5 | Downhole Main Cables | 1.2.3.5 Downhole Main Cables | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 72d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.3.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.3.5.3 | C |  | PSL | Drill Cables: Test Combo Cable (2 at PSL) (PSL_Engineer) |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2020-03-16 | 2020-05-08 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 4692 | [5 empty] | 4692 |  | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.3 | Tower Operations Site | 1.2.3 Tower Operations Site | 1.2.3.5 | Downhole Main Cables | 1.2.3.5 Downhole Main Cables | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 48d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.3.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.3.5.3 | C |  | PSL | Drill Cables: Test Combo Cable (2 at PSL) (PSL_Technician) |  | 0% | Labor Hours | TE |  |  | 81 | 77 | 0% | 2020-03-16 | 2020-05-08 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 3305 | [5 empty] | 3305 |  | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.3 | Tower Operations Site | 1.2.3 Tower Operations Site | 1.2.3.5 | Downhole Main Cables | 1.2.3.5 Downhole Main Cables | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 48d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.3.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.3.5.5 | C |  | PSL | Drill Cables: Procure Main Drill Cable (PSL_Engineer) |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2020-10-08 | 2021-06-16 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 4692 | [5 empty] | 4692 |  | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.3 | Tower Operations Site | 1.2.3 Tower Operations Site | 1.2.3.5 | Downhole Main Cables | 1.2.3.5 Downhole Main Cables | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 120d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.3.5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.3.5.5 | C |  | PSL | Drill Cables: Procure Main Drill Cable |  |  | CapEx |  |  | VQ | 1 | 1 | 0% | 2020-10-08 | 2021-06-16 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 151520 | [5 empty] | 151520 |  | 0 | CapEx | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.3 | Tower Operations Site | 1.2.3 Tower Operations Site | 1.2.3.5 | Downhole Main Cables | 1.2.3.5 Downhole Main Cables | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 120d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.3.5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.3.5.7 | C |  | PSL | Drill Cables: Drill Cable Connectors |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2021-03-25 | 2021-06-16 |  | TRUE |  | Installed by Fibron (manufacturer) | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 4692 | [5 empty] | 4692 |  | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.3 | Tower Operations Site | 1.2.3 Tower Operations Site | 1.2.3.5 | Downhole Main Cables | 1.2.3.5 Downhole Main Cables | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 72d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.3.5.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.5.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.5.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.5.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.5.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.5.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.5.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.5.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.3.5.8 | C |  | PSL | Drill Cables: Spool Main Drill Cable onto Winch/Spool |  | 0% | Labor Hours | EN |  |  |  | 115 | 0% | 2020-08-31 | 2020-09-18 |  |  |  | New activity | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 2760 | [7 empty] | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.3 | Tower Operations Site | 1.2.3 Tower Operations Site | 1.2.3.5 | Downhole Main Cables | 1.2.3.5 Downhole Main Cables | cell-link@smartsheet.com | 2021-11-30 16:42 |  | 18d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.3.5.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.5.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.5.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.5.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.5.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.5.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.5.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.5.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.3.5.8 | C |  | PSL | Drill Cables: Spool Main Drill Cable onto Winch/Spool |  | 0% | Labor Hours | TE |  |  |  | 77 | 0% | 2020-08-31 | 2020-09-18 |  |  |  | New activity | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 1848 | [7 empty] | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.3 | Tower Operations Site | 1.2.3 Tower Operations Site | 1.2.3.5 | Downhole Main Cables | 1.2.3.5 Downhole Main Cables | cell-link@smartsheet.com | 2021-11-30 16:42 |  | 18d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.3.5.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.5.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.5.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.5.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.5.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.5.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.5.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.5.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.3.6.1 | C |  | PSL | Hose Reel Heating System: Design, Fabricate and Test | Laundry | 0% | Labor Hours | EN |  |  |  | 115 | 0% | 2020-11-02 | 2021-03-05 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | [9 empty] | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.3 | Tower Operations Site | 1.2.3 Tower Operations Site | 1.2.3.6 | Design and Construct Main Hose Reel Heating System | 1.2.3.6 Design and Construct Main Hose Reel Heating System | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 47d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.3.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.3.6.2 | C |  | PSL | Hose Reel Heating System: Procure Components (Insulated Blankets & Tarps) |  | 0.8889% | Labor Hours | EN |  | EE |  | 115 | 0% | 2020-12-01 | 2021-04-05 | [10 empty] | 16 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1840 | 0 | 0 | 0 | 0 | 0 | 1840 | 0% | 0 | 1919.9705 | 1919.9705 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | [9 empty] | 1919.9705 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.3 | Tower Operations Site | 1.2.3 Tower Operations Site | 1.2.3.6 | Design and Construct Main Hose Reel Heating System | 1.2.3.6 Design and Construct Main Hose Reel Heating System | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 47d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.3.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 1919.9705 | 0 | 0 | 0 | 0 | 0 | 1.2.3.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 1919.9705 | 0 | 0 | 0 | 0 | 0 | 1919.9705 | 1.2.3.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1919.9705 | 1.2.3.6.2 | 1919.9705 | 5919.9705 | 0 | 0 | 0 | 0 | 0 | 0 | 1919.9705 | 1919.9705 | 1919.9705 | 1919.9705 | 1919.9705 | 1919.9705 | 0 | 0 | 0 | 0 | 0 | 0 | 5919.9705 | 5919.9705 | 5919.9705 | 5919.9705 | 5919.9705 | 5919.9705
| 1.2 | 1.2.3.6.2 | C |  | PSL | Hose Reel Heating System: Procure Components (Insulated Blankets & Tarps) |  |  | CapEx |  |  | EE |  | 1 | 0% | 2020-12-01 | 2021-04-05 | [10 empty] | 4000 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 4000 | 53% | 0 | 4000 | 4000 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 4000 | CapEx | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.3 | Tower Operations Site | 1.2.3 Tower Operations Site | 1.2.3.6 | Design and Construct Main Hose Reel Heating System | 1.2.3.6 Design and Construct Main Hose Reel Heating System | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 47d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.3.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 1.2.3.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 4000 | 1.2.3.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 1.2.3.6.2 | 4000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000
| 1.2 | 1.2.3.6.3 | C |  | PSL | Hose Reel Heating System: System Testing |  | 4.5% | Labor Hours | EN |  | EE |  | 115 | 0% | 2022-01-05 | 2022-02-25 | [7 empty] | 40.5 | 40.5 | [7 empty] | 0 | 0 | 0 | 4657.5 | 4657.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9315 | 0% | 0 | 9719.8509 | 9719.8509 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | [9 empty] | 9719.8509 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.3 | Tower Operations Site | 1.2.3 Tower Operations Site | 1.2.3.6 | Design and Construct Main Hose Reel Heating System | 1.2.3.6 Design and Construct Main Hose Reel Heating System | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 47d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.3.6.3 | 0 | 0 | 0 | 4859.9254 | 4859.9254 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.6.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.6.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.6.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.6.3 | 0 | 0 | 0 | 4859.9254 | 4859.9254 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9719.8509 | 1.2.3.6.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.6.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9719.8509 | 1.2.3.6.3 | 9719.8509 | 9719.8509 | 0 | 0 | 0 | 4859.9254 | 9719.8509 | 9719.8509 | 9719.8509 | 9719.8509 | 9719.8509 | 9719.8509 | 9719.8509 | 9719.8509 | 0 | 0 | 0 | 4859.9254 | 9719.8509 | 9719.8509 | 9719.8509 | 9719.8509 | 9719.8509 | 9719.8509 | 9719.8509 | 9719.8509
| 1.2 | 1.2.4.1.2 | C |  | PSL | Architecture: ICUD Requirements & Architecture Plan (PSL_Software Engineer) |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2019-04-24 | 2019-08-13 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 36800 | 0 | [5 empty] | 36800 |  | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.4 | Computing and Control System | 1.2.4 Computing and Control System | 1.2.4.1 | Architecture | 1.2.4.1 Architecture | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 96d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.4.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.4.1.2 | C |  | PSL | Architecture: ICUD Requirements & Architecture Plan (PSL_Engineer) |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2019-04-24 | 2019-08-13 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 36800 | 0 | [5 empty] | 36800 |  | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.4 | Computing and Control System | 1.2.4 Computing and Control System | 1.2.4.1 | Architecture | 1.2.4.1 Architecture | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 96d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.4.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.4.1.4 | C |  | PSL | Architecture: System Design (PSL_Software Engineer) |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2019-08-15 | 2020-01-29 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 18361 | 18808 | [5 empty] | 37169 |  | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.4 | Computing and Control System | 1.2.4 Computing and Control System | 1.2.4.1 | Architecture | 1.2.4.1 Architecture | cell-link@smartsheet.com | 2021-11-30 20:45 |  | 144d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.4.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.4.1.4 | C |  | PSL | Architecture: System Design (PSL_Engineer) |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2019-08-15 | 2020-01-29 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 18361 | 18808 | [5 empty] | 37169 |  | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.4 | Computing and Control System | 1.2.4 Computing and Control System | 1.2.4.1 | Architecture | 1.2.4.1 Architecture | cell-link@smartsheet.com | 2021-11-30 20:45 |  | 144d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.4.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.4.1.5 | C |  | PSL | Architecture: Final Design Review (PSL_Engineer) |  | 2.222% | Labor Hours | EN |  |  |  | 115 | 0% | 2022-04-15 | 2022-04-15 | [10 empty] | 40 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 4600 | 0 | 0 | 0 | 0 | 0 | 4600 | 0% | 0 | 4799.9263 | 4799.9263 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | [9 empty] | 4799.9263 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.4 | Computing and Control System | 1.2.4 Computing and Control System | 1.2.4.1 | Architecture | 1.2.4.1 Architecture | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 144d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.4.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 4799.9263 | 0 | 0 | 0 | 0 | 0 | 1.2.4.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 4799.9263 | 0 | 0 | 0 | 0 | 0 | 4799.9263 | 1.2.4.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4799.9263 | 1.2.4.1.5 | 4799.9263 | 4799.9263 | 0 | 0 | 0 | 0 | 0 | 0 | 4799.9263 | 4799.9263 | 4799.9263 | 4799.9263 | 4799.9263 | 4799.9263 | 0 | 0 | 0 | 0 | 0 | 0 | 4799.9263 | 4799.9263 | 4799.9263 | 4799.9263 | 4799.9263 | 4799.9263
| 1.2 | 1.2.4.1.6 | C |  | PSL | Architecture: Control Systems - Electrical Schematic Update |  | 8.889% | Labor Hours | EN |  |  |  | 115 | 0% | 2022-02-15 | 2022-07-18 | [8 empty] | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 0 | 0 | 0 | 0 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300 | 18400 | 0% | 0 | 19199.7054 | 19199.7054 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | [9 empty] | 19199.7054 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.4 | Computing and Control System | 1.2.4 Computing and Control System | 1.2.4.1 | Architecture | 1.2.4.1 Architecture | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 144d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.4.1.6 | 0 | 0 | 0 | 0 | 2399.9632 | 2399.9632 | 2399.9632 | 2399.9632 | 2399.9632 | 2399.9632 | 2399.9632 | 2399.9632 | 1.2.4.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.1.6 | 0 | 0 | 0 | 0 | 2399.9632 | 2399.9632 | 2399.9632 | 2399.9632 | 2399.9632 | 2399.9632 | 2399.9632 | 2399.9632 | 19199.7054 | 1.2.4.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19199.7054 | 1.2.4.1.6 | 19199.7054 | 19199.7054 | 0 | 0 | 0 | 0 | 2399.9632 | 4799.9263 | 7199.8895 | 9599.8527 | 11999.8159 | 14399.779 | 16799.7422 | 19199.7054 | 0 | 0 | 0 | 0 | 2399.9632 | 4799.9263 | 7199.8895 | 9599.8527 | 11999.8159 | 14399.779 | 16799.7422 | 19199.7054
| 1.2 | 1.2.4.2.1 | P |  | PSL | Controls Hardware: PLC Motor Controllers and Readouts (PSL_Software Engineer) |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2022-04-18 | 2023-07-07 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 15 |  |  |  | 15 | 20 | [6 empty] | 1725 | 0 | 0 | 0 | 1725 | 2300 | 0 | 0 | 0 | 0 | 0 | 0 | 5750 | 0% | 0 | 6128.906 | 6128.906 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 37536 | [5 empty] | 37536 |  | 6128.906 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.4 | Computing and Control System | 1.2.4 Computing and Control System | 1.2.4.2 | Control System Hardware | 1.2.4.2 Control System Hardware | cell-link@smartsheet.com | 2021-11-30 20:45 |  | 72d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.4.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.1 | 1838.6718 | 0 | 0 | 0 | 1838.6718 | 2451.5624 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.1 | 0 | 5500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5500 | 5500 | 5500 | 5500 | 5500 | 5500 | 5500 | 5500 | 5500 | 5500 | 5500
| 1.2 | 1.2.4.2.1 | P |  | PSL | Controls Hardware: PLC Motor Controllers and Readouts (PSL_Engineer) |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2022-04-18 | 2023-07-07 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 15 |  |  |  | 15 | 20 | [6 empty] | 1725 | 0 | 0 | 0 | 1725 | 2300 | 0 | 0 | 0 | 0 | 0 | 0 | 5750 | 0% | 0 | 6128.906 | 6128.906 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 37536 | [5 empty] | 37536 |  | 6128.906 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.4 | Computing and Control System | 1.2.4 Computing and Control System | 1.2.4.2 | Control System Hardware | 1.2.4.2 Control System Hardware | cell-link@smartsheet.com | 2021-11-30 20:45 |  | 72d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.4.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.1 | 1838.6718 | 0 | 0 | 0 | 1838.6718 | 2451.5624 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.1 | 0 | 5500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5500 | 5500 | 5500 | 5500 | 5500 | 5500 | 5500 | 5500 | 5500 | 5500 | 5500
| 1.2 | 1.2.4.2.1 | P |  | PSL | Controls Hardware: PLC Motor Controllers and Readouts (Touch Screen) |  |  | CapEx |  |  | VQ | 1 | 1 | 0% | 2022-04-18 | 2023-07-07 | [5 empty] | 5500 | [10 empty] | 0 | 5500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5500 | 53% | 0 | 5500 | 5500 |  | 5500 | 5500 | 5500 | [8 empty] | 0 | 5500 | 5500 | 5500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16500 | 53% | 0 | 16500 | 16500 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 48000 | [5 empty] | 48000 |  | 22000 | CapEx | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.4 | Computing and Control System | 1.2.4 Computing and Control System | 1.2.4.2 | Control System Hardware | 1.2.4.2 Control System Hardware | cell-link@smartsheet.com | 2021-11-30 20:45 |  | 72d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.4.2.1 | 0 | 5500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.1 | 0 | 5500 | 5500 | 5500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.1 | 0 | 5500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5500 | 1.2.4.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5500 | 1.2.4.2.1 | 5500 | 5500 | 0 | 5500 | 5500 | 5500 | 5500 | 5500 | 5500 | 5500 | 5500 | 5500 | 5500 | 5500 | 0 | 5500 | 5500 | 5500 | 5500 | 5500 | 5500 | 5500 | 5500 | 5500 | 5500 | 5500
| 1.2 | 1.2.4.2.1.1 | C |  | PSL | Design, build and test new PLC and network box for HPP |  | 9.056% | Labor Hours | EN |  | VQ | 1 | 115 | 0% | 2022-04-18 | 2022-06-22 | [11 empty] | 50 | 50 | 63 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5750 | 5750 | 7245 | 0 | 0 | 18745 | 0% | 0 | 19559.6999 | 19559.6999 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 48000 | [5 empty] | 48000 |  | 19559.6999 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.4 | Computing and Control System | 1.2.4 Computing and Control System | 1.2.4.2 | Control System Hardware | 1.2.4.2 Control System Hardware | cell-link@smartsheet.com | 2021-11-30 20:45 |  | 72d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.4.2.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5999.9079 | 5999.9079 | 7559.884 | 0 | 0 | 1.2.4.2.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5999.9079 | 5999.9079 | 7559.884 | 0 | 0 | 19559.6999 | 1.2.4.2.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19559.6999 | 1.2.4.2.1.1 | 19559.6999 | 23759.6999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5999.9079 | 11999.8159 | 19559.6999 | 19559.6999 | 19559.6999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10199.9079 | 16199.8159 | 23759.6999 | 23759.6999 | 23759.6999
| 1.2 | 1.2.4.2.1.1 | C |  | PSL | Design, build and test new PLC and network box for HPP |  |  | CapEx | EN |  | VQ | 1 | 1 | 0% | 2022-04-18 | 2022-06-22 | [11 empty] | 4200 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4200 | 0 | 0 | 0 | 0 | 4200 | 53% | 0 | 4200 | 4200 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 48000 | [5 empty] | 48000 |  | 4200 | CapEx | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.4 | Computing and Control System | 1.2.4 Computing and Control System | 1.2.4.2 | Control System Hardware | 1.2.4.2 Control System Hardware | cell-link@smartsheet.com | 2021-11-30 20:45 |  | 72d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.4.2.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4200 | 0 | 0 | 0 | 0 | 1.2.4.2.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4200 | 0 | 0 | 0 | 0 | 4200 | 1.2.4.2.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4200 | 1.2.4.2.1.1 | 4200 | 4200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4200 | 4200 | 4200 | 4200 | 4200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4200 | 4200 | 4200 | 4200 | 4200
| 1.2 | 1.2.4.2.1.2 | C |  | PSL | Design, build and test RWCR control box |  | 0% | Labor Hours | EN |  | VQ | 1 | 115 | 0% | 2023-05-03 | 2023-07-07 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [7 empty] | 39 | 39 | 39 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4485 | 4485 | 4485 | 0 | 0 | 13455 | 0% | 0 | 14341.6399 | 14341.6399 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 48000 | [5 empty] | 48000 |  | 14341.6399 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.4 | Computing and Control System | 1.2.4 Computing and Control System | 1.2.4.2 | Control System Hardware | 1.2.4.2 Control System Hardware | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 72d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.4.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4780.5466 | 4780.5466 | 4780.5466 | 0 | 0 | 1.2.4.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.4.2.2 | P |  | PSL | Controls Hardware: System Sensors (PSL_Software Engineer) |  | 6.667% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2020-12-01 | 2023-07-07 |  |  |  |  | 45 | 45 | 30 | [9 empty] | 5175 | 5175 | 3450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13800 | 0% | 0 | 14399.779 | 14399.779 | [7 empty] | 20 | 20 | 20 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2300 | 2300 | 2300 | 0 | 0 | 6900 | 0% | 0 | 7354.6871 | 7354.6871 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 37536 | [5 empty] | 37536 |  | 21754.4662 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.4 | Computing and Control System | 1.2.4 Computing and Control System | 1.2.4.2 | Control System Hardware | 1.2.4.2 Control System Hardware | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 48d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.4.2.2 | 5399.9171 | 5399.9171 | 3599.9448 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2451.5624 | 2451.5624 | 2451.5624 | 0 | 0 | 1.2.4.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.2 | 5399.9171 | 5399.9171 | 3599.9448 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14399.779 | 1.2.4.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14399.779 | 1.2.4.2.2 | 14399.779 | 34399.779 | 5399.9171 | 10799.8343 | 14399.779 | 14399.779 | 14399.779 | 14399.779 | 14399.779 | 14399.779 | 14399.779 | 14399.779 | 14399.779 | 14399.779 | 10499.9171 | 20899.8343 | 34399.779 | 34399.779 | 34399.779 | 34399.779 | 34399.779 | 34399.779 | 34399.779 | 34399.779 | 34399.779 | 34399.779
| 1.2 | 1.2.4.2.2 | P |  | PSL | Controls Hardware: System Sensors |  |  | CapEx |  |  | VQ | 1 | 1 | 0% | 2020-12-01 | 2023-07-07 |  |  |  |  | 5100 | 5000 | 9900 | [9 empty] | 5100 | 5000 | 9900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 53% | 0 | 20000 | 20000 | [9 empty] | 6000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 0 | 0 | 6000 | 53% | 0 | 6000 | 6000 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 69468 | [5 empty] | 69468 |  | 26000 | CapEx | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.4 | Computing and Control System | 1.2.4 Computing and Control System | 1.2.4.2 | Control System Hardware | 1.2.4.2 Control System Hardware | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 48d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.4.2.2 | 5100 | 5000 | 9900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 0 | 0 | 1.2.4.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.2 | 5100 | 5000 | 9900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 1.2.4.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 1.2.4.2.2 | 20000 | 20000 | 5100 | 10100 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 5100 | 10100 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000
| 1.2 | 1.2.4.2.2.1 | C |  | PSL | HPP sensor box testing |  | 6.389% | Labor Hours | EN |  | VQ | 1 | 115 | 0% | 2020-12-01 | 2023-07-07 |  |  |  |  | 30 | 30 | 30 | 25 | [8 empty] | 3450 | 3450 | 3450 | 2875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13225 | 0% | 0 | 13799.7883 | 13799.7883 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 69468 | [5 empty] | 69468 |  | 13799.7883 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.4 | Computing and Control System | 1.2.4 Computing and Control System | 1.2.4.2 | Control System Hardware | 1.2.4.2 Control System Hardware | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 48d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.4.2.2.1 | 3599.9448 | 3599.9448 | 3599.9448 | 2999.954 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.2.1 | 3599.9448 | 3599.9448 | 3599.9448 | 2999.954 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13799.7883 | 1.2.4.2.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13799.7883 | 1.2.4.2.2.1 | 13799.7883 | 13799.7883 | 3599.9448 | 7199.8895 | 10799.8343 | 13799.7883 | 13799.7883 | 13799.7883 | 13799.7883 | 13799.7883 | 13799.7883 | 13799.7883 | 13799.7883 | 13799.7883 | 3599.9448 | 7199.8895 | 10799.8343 | 13799.7883 | 13799.7883 | 13799.7883 | 13799.7883 | 13799.7883 | 13799.7883 | 13799.7883 | 13799.7883 | 13799.7883
| 1.2 | 1.2.4.2.2.2 | C |  | PSL | Specify, Procure and Test Water Tank depth and temp sensor box testing |  | 5.278% | Labor Hours | EN |  | VQ | 1 | 115 | 0% | 2020-12-01 | 2023-07-07 |  |  |  |  | 30 | 30 | 35 | [9 empty] | 3450 | 3450 | 4025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10925 | 0% | 0 | 11399.8251 | 11399.8251 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 69468 | [5 empty] | 69468 |  | 11399.8251 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.4 | Computing and Control System | 1.2.4 Computing and Control System | 1.2.4.2 | Control System Hardware | 1.2.4.2 Control System Hardware | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 48d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.4.2.2.2 | 3599.9448 | 3599.9448 | 4199.9356 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.2.2 | 3599.9448 | 3599.9448 | 4199.9356 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11399.8251 | 1.2.4.2.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11399.8251 | 1.2.4.2.2.2 | 11399.8251 | 11399.8251 | 3599.9448 | 7199.8895 | 11399.8251 | 11399.8251 | 11399.8251 | 11399.8251 | 11399.8251 | 11399.8251 | 11399.8251 | 11399.8251 | 11399.8251 | 11399.8251 | 3599.9448 | 7199.8895 | 11399.8251 | 11399.8251 | 11399.8251 | 11399.8251 | 11399.8251 | 11399.8251 | 11399.8251 | 11399.8251 | 11399.8251 | 11399.8251
| 1.2 | 1.2.4.2.3 | P |  | PSL | Controls Hardware: Network Controllers (PSL_Software Engineer) |  | 2.222% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2022-04-18 | 2022-07-18 | [10 empty] | 10 | 10 | 10 | 10 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1150 | 1150 | 1150 | 1150 | 0 | 0 | 4600 | 0% | 0 | 4799.9263 | 4799.9263 | [5 empty] | 20 | 20 | 20 |  | 20 |  |  | 0 | 0 | 0 | 0 | 0 | 2300 | 2300 | 2300 | 0 | 2300 | 0 | 0 | 9200 | 0% | 0 | 9806.2495 | 9806.2495 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 23460 | [5 empty] | 23460 |  | 14606.1759 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.4 | Computing and Control System | 1.2.4 Computing and Control System | 1.2.4.2 | Control System Hardware | 1.2.4.2 Control System Hardware | cell-link@smartsheet.com | 2021-11-30 20:45 |  | 72d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.4.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 1199.9816 | 1199.9816 | 1199.9816 | 1199.9816 | 0 | 0 | 1.2.4.2.3 | 0 | 0 | 0 | 0 | 0 | 2451.5624 | 2451.5624 | 2451.5624 | 0 | 2451.5624 | 0 | 0 | 1.2.4.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 1199.9816 | 1199.9816 | 1199.9816 | 1199.9816 | 0 | 0 | 4799.9263 | 1.2.4.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4799.9263 | 1.2.4.2.3 | 4799.9263 | 8799.9263 | 0 | 0 | 0 | 0 | 0 | 0 | 1199.9816 | 2399.9632 | 3599.9448 | 4799.9263 | 4799.9263 | 4799.9263 | 0 | 0 | 0 | 0 | 0 | 1000 | 3199.9816 | 5399.9632 | 7599.9448 | 8799.9263 | 8799.9263 | 8799.9263
| 1.2 | 1.2.4.2.3 | P |  | PSL | Controls Hardware: Network Controllers (PSL_Engineer) |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2022-04-18 | 2022-07-18 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [7 empty] | 20 |  | 20 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2300 | 0 | 2300 | 0 | 0 | 4600 | 0% | 0 | 4903.1248 | 4903.1248 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 23460 | [5 empty] | 23460 |  | 4903.1248 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.4 | Computing and Control System | 1.2.4 Computing and Control System | 1.2.4.2 | Control System Hardware | 1.2.4.2 Control System Hardware | cell-link@smartsheet.com | 2021-11-30 20:45 |  | 72d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.4.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2451.5624 | 0 | 2451.5624 | 0 | 0 | 1.2.4.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.3 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 2000 | 3000 | 4000 | 4000 | 4000 | 4000
| 1.2 | 1.2.4.2.3 | P |  | PSL | Controls Hardware: Network Controllers |  |  | CapEx |  |  | VQ | 1 | 1 | 0% | 2022-04-18 | 2022-07-18 | [9 empty] | 1000 | 1000 | 1000 | 1000 |  |  |  | 0 | 0 | 0 | 0 | 0 | 1000 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 4000 | 53% | 0 | 4000 | 4000 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 39213 | [5 empty] | 39213 |  | 4000 | CapEx | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.4 | Computing and Control System | 1.2.4 Computing and Control System | 1.2.4.2 | Control System Hardware | 1.2.4.2 Control System Hardware | cell-link@smartsheet.com | 2021-11-30 20:45 |  | 72d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.4.2.3 | 0 | 0 | 0 | 0 | 0 | 1000 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 1.2.4.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.3 | 0 | 0 | 0 | 0 | 0 | 1000 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 4000 | 1.2.4.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 1.2.4.2.3 | 4000 | 4000 | 0 | 0 | 0 | 0 | 0 | 1000 | 2000 | 3000 | 4000 | 4000 | 4000 | 4000 | 0 | 0 | 0 | 0 | 0 | 1000 | 2000 | 3000 | 4000 | 4000 | 4000 | 4000
| 1.2 | 1.2.4.2.3.1 | C |  | PSL | Plan MHP network box upgrade |  | 4.111% | Labor Hours | EN |  | VQ | 1 | 115 | 0% | 2022-04-18 | 2022-07-15 | [8 empty] | 37 | 37 | [6 empty] | 0 | 0 | 0 | 0 | 4255 | 4255 | 0 | 0 | 0 | 0 | 0 | 0 | 8510 | 0% | 0 | 8879.8637 | 8879.8637 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 39213 | [5 empty] | 39213 |  | 8879.8637 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.4 | Computing and Control System | 1.2.4 Computing and Control System | 1.2.4.2 | Control System Hardware | 1.2.4.2 Control System Hardware | cell-link@smartsheet.com | 2021-11-30 20:45 |  | 72d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.4.2.3.1 | 0 | 0 | 0 | 0 | 4439.9319 | 4439.9319 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.3.1 | 0 | 0 | 0 | 0 | 4439.9319 | 4439.9319 | 0 | 0 | 0 | 0 | 0 | 0 | 8879.8637 | 1.2.4.2.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8879.8637 | 1.2.4.2.3.1 | 8879.8637 | 8879.8637 | 0 | 0 | 0 | 0 | 4439.9319 | 8879.8637 | 8879.8637 | 8879.8637 | 8879.8637 | 8879.8637 | 8879.8637 | 8879.8637 | 0 | 0 | 0 | 0 | 4439.9319 | 8879.8637 | 8879.8637 | 8879.8637 | 8879.8637 | 8879.8637 | 8879.8637 | 8879.8637
| 1.2 | 1.2.4.2.3.2 | C |  | PSL | Redesign, build and test network box for PHS |  | 6.833% | Labor Hours | EN |  | VQ | 1 | 115 | 0% | 2022-04-18 | 2022-07-18 | [8 empty] | 62 | 61 | [6 empty] | 0 | 0 | 0 | 0 | 7130 | 7015 | 0 | 0 | 0 | 0 | 0 | 0 | 14145 | 0% | 0 | 14759.7735 | 14759.7735 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 39213 | [5 empty] | 39213 |  | 14759.7735 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.4 | Computing and Control System | 1.2.4 Computing and Control System | 1.2.4.2 | Control System Hardware | 1.2.4.2 Control System Hardware | cell-link@smartsheet.com | 2021-11-30 20:45 |  | 72d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.4.2.3.2 | 0 | 0 | 0 | 0 | 7439.8858 | 7319.8877 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.3.2 | 0 | 0 | 0 | 0 | 7439.8858 | 7319.8877 | 0 | 0 | 0 | 0 | 0 | 0 | 14759.7735 | 1.2.4.2.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14759.7735 | 1.2.4.2.3.2 | 14759.7735 | 14759.7735 | 0 | 0 | 0 | 0 | 7439.8858 | 14759.7735 | 14759.7735 | 14759.7735 | 14759.7735 | 14759.7735 | 14759.7735 | 14759.7735 | 0 | 0 | 0 | 0 | 7439.8858 | 14759.7735 | 14759.7735 | 14759.7735 | 14759.7735 | 14759.7735 | 14759.7735 | 14759.7735
| 1.2 | 1.2.4.2.4 | C |  | PSL | Network Controllers: Indoor Cables (sensor and network) (PSL_Software Engineer) |  | 3.333% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2020-10-09 | 2023-09-08 |  |  |  |  | 10 |  |  |  | 5 | 5 | 5 | 5 | 10 | 10 | 10 |  | 1150 | 0 | 0 | 0 | 575 | 575 | 575 | 575 | 1150 | 1150 | 1150 | 0 | 6900 | 0% | 0 | 7199.8895 | 7199.8895 | [6 empty] | 10 |  | 10 | 10 |  | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 1150 | 0 | 1150 | 1150 | 0 | 1150 | 4600 | 0% | 0 | 4903.1248 | 4903.1248 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 2699 | 6819 |  |  |  |  | 9518 |  | 12103.0143 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.4 | Computing and Control System | 1.2.4 Computing and Control System | 1.2.4.2 | Control System Hardware | 1.2.4.2 Control System Hardware | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 48d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.4.2.4 | 1199.9816 | 0 | 0 | 0 | 599.9908 | 599.9908 | 599.9908 | 599.9908 | 1199.9816 | 1199.9816 | 1199.9816 | 0 | 1.2.4.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 1225.7812 | 0 | 1225.7812 | 1225.7812 | 0 | 1225.7812 | 1.2.4.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.4 | 1199.9816 | 0 | 0 | 0 | 599.9908 | 599.9908 | 599.9908 | 599.9908 | 1199.9816 | 1199.9816 | 1199.9816 | 0 | 7199.8895 | 1.2.4.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7199.8895 | 1.2.4.2.4 | 7199.8895 | 12853.8695 | 1199.9816 | 1199.9816 | 1199.9816 | 1199.9816 | 1799.9724 | 2399.9632 | 2999.954 | 3599.9448 | 4799.9263 | 5999.9079 | 7199.8895 | 7199.8895 | 3084.6416 | 3084.6416 | 3084.6416 | 3084.6416 | 5569.2924 | 8053.9432 | 8653.934 | 9253.9248 | 10453.9063 | 11653.8879 | 12853.8695 | 12853.8695
| 1.2 | 1.2.4.2.4 | C |  | PSL | Network Controllers: Indoor Cables (sensor and network) (PSL_Engineer) |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2020-10-09 | 2023-09-08 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [6 empty] | 10 |  | 10 | 10 |  | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 1150 | 0 | 1150 | 1150 | 0 | 1150 | 4600 | 0% | 0 | 4903.1248 | 4903.1248 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 2699 | 6819 |  |  |  |  | 9518 |  | 4903.1248 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.4 | Computing and Control System | 1.2.4 Computing and Control System | 1.2.4.2 | Control System Hardware | 1.2.4.2 Control System Hardware | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 48d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.4.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 1225.7812 | 0 | 1225.7812 | 1225.7812 | 0 | 1225.7812 | 1.2.4.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.4 | 0 | 5653.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1884.66 | 1884.66 | 1884.66 | 1884.66 | 3769.32 | 5653.98 | 5653.98 | 5653.98 | 5653.98 | 5653.98 | 5653.98 | 5653.98
| 1.2 | 1.2.4.2.4 | C |  | PSL | Network Controllers: Indoor Cables (sensor and network) |  |  | CapEx |  |  | VQ | 1 | 1 | 0% | 2020-10-09 | 2023-09-08 |  |  |  |  | 1884.66 |  |  |  | 1884.66 | 1884.66 | [6 empty] | 1884.66 | 0 | 0 | 0 | 1884.66 | 1884.66 | 0 | 0 | 0 | 0 | 0 | 0 | 5653.98 | 53% | 0 | 5653.98 | 5653.98 | [7 empty] | 1884.66 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1884.66 | 0 | 1884.66 | 0 | 0 | 0 | 0 | 3769.32 | 53% | 0 | 3769.32 | 3769.32 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 1726 | 4274 |  |  |  |  | 6000 |  | 9423.3 | CapEx | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.4 | Computing and Control System | 1.2.4 Computing and Control System | 1.2.4.2 | Control System Hardware | 1.2.4.2 Control System Hardware | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 48d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.4.2.4 | 1884.66 | 0 | 0 | 0 | 1884.66 | 1884.66 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.4 | 0 | 0 | 0 | 0 | 0 | 1884.66 | 0 | 1884.66 | 0 | 0 | 0 | 0 | 1.2.4.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.4 | 1884.66 | 0 | 0 | 0 | 1884.66 | 1884.66 | 0 | 0 | 0 | 0 | 0 | 0 | 5653.98 | 1.2.4.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5653.98 | 1.2.4.2.4 | 5653.98 | 5653.98 | 1884.66 | 1884.66 | 1884.66 | 1884.66 | 3769.32 | 5653.98 | 5653.98 | 5653.98 | 5653.98 | 5653.98 | 5653.98 | 5653.98 | 1884.66 | 1884.66 | 1884.66 | 1884.66 | 3769.32 | 5653.98 | 5653.98 | 5653.98 | 5653.98 | 5653.98 | 5653.98 | 5653.98
| 1.2 | 1.2.4.2.5 | C |  | PSL | Network Controllers: Infrastructure Repair & Upgrade (w/sub-tasks) |  | 0% | Labor Hours | EN |  |  |  | 115 | 0% | 2020-09-25 | 2024-03-04 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -103500 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -38525 | 25 |  |  |  | 25 | [7 empty] | 2875 | 0 | 0 | 0 | 2875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5750 | 0% | 0 | 6260.6774 | 6260.6774 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | 103500 | 103500 |  | 38525 |  |  |  | 6260.6774 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.4 | Computing and Control System | 1.2.4 Computing and Control System | 1.2.4.2 | Control System Hardware | 1.2.4.2 Control System Hardware | cell-link@smartsheet.com | 2021-11-30 20:45 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.4.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.5 | 3130.3387 | 0 | 0 | 0 | 3130.3387 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.4.2.6 | C |  | PSL | Network Controllers: Return Water Pump Noise Mitigation Subsys testing |  | 8.667% | Labor Hours | EN |  | VQ | 1 | 115 | 0% | 2022-04-01 | 2023-06-14 | [10 empty] | 78 | 78 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 8970 | 8970 | 0 | 0 | 0 | 0 | 17940 | 0% | 0 | 18719.7128 | 18719.7128 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 69468 | [5 empty] | 69468 |  | 18719.7128 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.4 | Computing and Control System | 1.2.4 Computing and Control System | 1.2.4.2 | Control System Hardware | 1.2.4.2 Control System Hardware | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 48d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.4.2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 9359.8564 | 9359.8564 | 0 | 0 | 0 | 0 | 1.2.4.2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 9359.8564 | 9359.8564 | 0 | 0 | 0 | 0 | 18719.7128 | 1.2.4.2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18719.7128 | 1.2.4.2.6 | 18719.7128 | 18719.7128 | 0 | 0 | 0 | 0 | 0 | 0 | 9359.8564 | 18719.7128 | 18719.7128 | 18719.7128 | 18719.7128 | 18719.7128 | 0 | 0 | 0 | 0 | 0 | 0 | 9359.8564 | 18719.7128 | 18719.7128 | 18719.7128 | 18719.7128 | 18719.7128
| 1.2 | 1.2.4.2.7 | C |  | PSL | Network Controllers: TOS pendant I/O box rebuild and testing - (one finished, 7 remaining) |  | 13.06% | Labor Hours | EN |  | VQ |  | 115 | 0% | 2022-04-01 | 2023-06-14 |  |  |  |  | 46 | 48 | 48 | 48 | 45 | [7 empty] | 5290 | 5520 | 5520 | 5520 | 5175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27025 | 0% | 0 | 28199.5673 | 28199.5673 | [7 empty] | 8 |  | 8 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 920 | 0 | 920 | 0 | 0 | 1840 | 0% | 0 | 1961.2499 | 1961.2499 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | [9 empty] | 30160.8172 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.4 | Computing and Control System | 1.2.4 Computing and Control System | 1.2.4.2 | Control System Hardware | 1.2.4.2 Control System Hardware | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 48d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.4.2.7 | 5519.9153 | 5759.9116 | 5759.9116 | 5759.9116 | 5399.9171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 980.625 | 0 | 980.625 | 0 | 0 | 1.2.4.2.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.7 | 5519.9153 | 5759.9116 | 5759.9116 | 5759.9116 | 5399.9171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28199.5673 | 1.2.4.2.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28199.5673 | 1.2.4.2.7 | 28199.5673 | 28199.5673 | 5519.9153 | 11279.8269 | 17039.7385 | 22799.6502 | 28199.5673 | 28199.5673 | 28199.5673 | 28199.5673 | 28199.5673 | 28199.5673 | 28199.5673 | 28199.5673 | 5519.9153 | 11279.8269 | 17039.7385 | 22799.6502 | 28199.5673 | 28199.5673 | 28199.5673 | 28199.5673 | 28199.5673 | 28199.5673 | 28199.5673 | 28199.5673
| 1.2 | 1.2.4.2.8 | C |  | PSL | Network Controllers: TOS and DCC PLC box design, build, test (three new boxes) |  | 38.33% | Labor Hours | EN |  | VQ |  | 115 | 0% | 2022-01-11 | 2022-09-30 | [5 empty] | 77 | 77 | 77 | 77 | 77 | 77 | 77 | 77 |  |  | 74 | 0 | 8855 | 8855 | 8855 | 8855 | 8855 | 8855 | 8855 | 8855 | 0 | 0 | 8510 | 79350 | 0% | 0 | 82798.7295 | 82798.7295 | [6 empty] | 29 |  | 32 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 3335 | 0 | 3680 | 0 | 0 | 0 | 7015 | 0% | 0 | 7477.2653 | 7477.2653 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | [9 empty] | 90275.9948 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.4 | Computing and Control System | 1.2.4 Computing and Control System | 1.2.4.2 | Control System Hardware | 1.2.4.2 Control System Hardware | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 48d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.4.2.8 | 0 | 9239.8582 | 9239.8582 | 9239.8582 | 9239.8582 | 9239.8582 | 9239.8582 | 9239.8582 | 9239.8582 | 0 | 0 | 8879.8637 | 1.2.4.2.8 | 0 | 0 | 0 | 0 | 0 | 0 | 3554.7655 | 0 | 3922.4998 | 0 | 0 | 0 | 1.2.4.2.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.8 | 0 | 9239.8582 | 9239.8582 | 9239.8582 | 9239.8582 | 9239.8582 | 9239.8582 | 9239.8582 | 9239.8582 | 0 | 0 | 8879.8637 | 82798.7295 | 1.2.4.2.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82798.7295 | 1.2.4.2.8 | 82798.7295 | 82798.7295 | 0 | 9239.8582 | 18479.7164 | 27719.5747 | 36959.4329 | 46199.2911 | 55439.1493 | 64679.0076 | 73918.8658 | 73918.8658 | 73918.8658 | 82798.7295 | 0 | 9239.8582 | 18479.7164 | 27719.5747 | 36959.4329 | 46199.2911 | 55439.1493 | 64679.0076 | 73918.8658 | 73918.8658 | 73918.8658 | 82798.7295
| 1.2 | 1.2.4.2.9 | C |  | PSL | Network Controllers: Rodwell control interface definition (new I/O box for this unit) |  | 10.83% | Labor Hours | EN |  | VQ |  | 115 | 0% | 2021-10-01 | 2022-09-30 | [5 empty] | 40 | 60 | 60 | 35 | [7 empty] | 0 | 4600 | 6900 | 6900 | 4025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22425 | 0% | 0 | 23399.641 | 23399.641 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | [9 empty] | 23399.641 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.4 | Computing and Control System | 1.2.4 Computing and Control System | 1.2.4.2 | Control System Hardware | 1.2.4.2 Control System Hardware | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 48d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.4.2.9 | 0 | 4799.9263 | 7199.8895 | 7199.8895 | 4199.9356 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.9 | 0 | 4799.9263 | 7199.8895 | 7199.8895 | 4199.9356 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23399.641 | 1.2.4.2.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23399.641 | 1.2.4.2.9 | 23399.641 | 23399.641 | 0 | 4799.9263 | 11999.8159 | 19199.7054 | 23399.641 | 23399.641 | 23399.641 | 23399.641 | 23399.641 | 23399.641 | 23399.641 | 23399.641 | 0 | 4799.9263 | 11999.8159 | 19199.7054 | 23399.641 | 23399.641 | 23399.641 | 23399.641 | 23399.641 | 23399.641 | 23399.641 | 23399.641
| 1.2 | 1.2.4.3.1 | C |  | PSL | Controls Software: Motor Controllers and Readouts (PSL_Software Engineer) |  | 2.222% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2020-11-04 | 2023-07-26 |  | TRUE | [8 empty] | 10 | 10 | 10 | 10 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1150 | 1150 | 1150 | 1150 | 0 | 0 | 4600 | 0% | 0 | 4799.9263 | 4799.9263 | 20 |  |  |  |  | 20 |  | 20 |  | 20 |  |  | 2300 | 0 | 0 | 0 | 0 | 2300 | 0 | 2300 | 0 | 2300 | 0 | 0 | 9200 | 0% | 0 | 9806.2495 | 9806.2495 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | 76573 |  |  |  |  | 76573 |  | 14606.1759 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.4 | Computing and Control System | 1.2.4 Computing and Control System | 1.2.4.3 | Control System Software | 1.2.4.3 Control System Software | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 72d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.4.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 1199.9816 | 1199.9816 | 1199.9816 | 1199.9816 | 0 | 0 | 1.2.4.3.1 | 2451.5624 | 0 | 0 | 0 | 0 | 2451.5624 | 0 | 2451.5624 | 0 | 2451.5624 | 0 | 0 | 1.2.4.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 1199.9816 | 1199.9816 | 1199.9816 | 1199.9816 | 0 | 0 | 4799.9263 | 1.2.4.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4799.9263 | 1.2.4.3.1 | 4799.9263 | 4799.9263 | 0 | 0 | 0 | 0 | 0 | 0 | 1199.9816 | 2399.9632 | 3599.9448 | 4799.9263 | 4799.9263 | 4799.9263 | 0 | 0 | 0 | 0 | 0 | 0 | 1199.9816 | 2399.9632 | 3599.9448 | 4799.9263 | 4799.9263 | 4799.9263
| 1.2 | 1.2.4.3.1 | C |  | PSL | Controls Software: Motor Controllers and Readouts |  |  | CapEx |  |  | VQ | 1 | 1 | 0% | 2020-11-04 | 2023-07-26 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [9 empty] | 2940 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2940 | 0 | 0 | 2940 | 53% | 0 | 2940 | 2940 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 | 14700 |  |  |  |  | 14700 |  | 2940 | CapEx | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.4 | Computing and Control System | 1.2.4 Computing and Control System | 1.2.4.3 | Control System Software | 1.2.4.3 Control System Software | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 72d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.4.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2940 | 0 | 0 | 1.2.4.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.4.3.2 | P |  | PSL | Controls Software: Data Acquisition (PSL_Software Engineer) |  | 2.222% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2021-10-01 | 2022-02-24 |  | TRUE |  |  | 10 | 10 |  | 10 | 10 | [7 empty] | 1150 | 1150 | 0 | 1150 | 1150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4600 | 0% | 0 | 4799.9263 | 4799.9263 |  |  |  |  | 20 |  | 20 |  | 20 |  | 20 |  | 0 | 0 | 0 | 0 | 2300 | 0 | 2300 | 0 | 2300 | 0 | 2300 | 0 | 9200 | 0% | 0 | 9806.2495 | 9806.2495 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | 57430 |  |  |  |  | 57430 |  | 14606.1759 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.4 | Computing and Control System | 1.2.4 Computing and Control System | 1.2.4.3 | Control System Software | 1.2.4.3 Control System Software | cell-link@smartsheet.com | 2021-11-30 20:45 |  | 96d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.4.3.2 | 1199.9816 | 1199.9816 | 0 | 1199.9816 | 1199.9816 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.3.2 | 0 | 0 | 0 | 0 | 2451.5624 | 0 | 2451.5624 | 0 | 2451.5624 | 0 | 2451.5624 | 0 | 1.2.4.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.3.2 | 1199.9816 | 1199.9816 | 0 | 1199.9816 | 1199.9816 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4799.9263 | 1.2.4.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4799.9263 | 1.2.4.3.2 | 4799.9263 | 17906.9264 | 1199.9816 | 2399.9632 | 2399.9632 | 3599.9448 | 4799.9263 | 4799.9263 | 4799.9263 | 4799.9263 | 4799.9263 | 4799.9263 | 4799.9263 | 4799.9263 | 1199.9816 | 2399.9632 | 2399.9632 | 3599.9448 | 4799.9263 | 9168.9263 | 9168.9263 | 13537.9263 | 13537.9263 | 17906.9264 | 17906.9264 | 17906.9264
| 1.2 | 1.2.4.3.2 | P |  | PSL | Controls Software: Data Acquisition |  |  | CapEx |  |  | VQ | 1 | 1 | 0% | 2021-10-01 | 2022-02-24 |  | TRUE | [7 empty] | 4369 |  | 4369 |  | 4369 |  |  | 0 | 0 | 0 | 0 | 0 | 4369 | 0 | 4369 | 0 | 4369 | 0 | 0 | 13107 | 53% | 0 | 13107 | 13107 | [6 empty] | 4369 |  |  |  | 4369 |  | 0 | 0 | 0 | 0 | 0 | 0 | 4369 | 0 | 0 | 0 | 4369 | 0 | 8738 | 53% | 0 | 8738 | 8738 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 | 26214 |  |  |  |  | 26214 |  | 21845 | CapEx | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.4 | Computing and Control System | 1.2.4 Computing and Control System | 1.2.4.3 | Control System Software | 1.2.4.3 Control System Software | cell-link@smartsheet.com | 2021-11-30 20:45 |  | 96d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.4.3.2 | 0 | 0 | 0 | 0 | 0 | 4369 | 0 | 4369 | 0 | 4369 | 0 | 0 | 1.2.4.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 4369 | 0 | 0 | 0 | 4369 | 0 | 1.2.4.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.3.2 | 0 | 0 | 0 | 0 | 0 | 4369 | 0 | 4369 | 0 | 4369 | 0 | 0 | 13107 | 1.2.4.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13107 | 1.2.4.3.2 | 13107 | 13107 | 0 | 0 | 0 | 0 | 0 | 4369 | 4369 | 8738 | 8738 | 13107 | 13107 | 13107 | 0 | 0 | 0 | 0 | 0 | 4369 | 4369 | 8738 | 8738 | 13107 | 13107 | 13107
| 1.2 | 1.2.4.3.2.1 | C |  | PSL | Controls Software: DGH programming, testing and cataloging |  | 4.5% | Labor Hours | EN |  | VQ | 1 | 115 | 0% | 2021-12-08 | 2022-02-24 |  | TRUE |  |  |  |  | 40 | 41 | [8 empty] | 0 | 0 | 4600 | 4715 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9315 | 0% | 0 | 9719.8509 | 9719.8509 | [7 empty] | 15 |  | 30 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1725 | 0 | 3450 | 0 | 0 | 5175 | 0% | 0 | 5516.0154 | 5516.0154 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | 26214 |  |  |  |  | 26214 |  | 15235.8662 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.4 | Computing and Control System | 1.2.4 Computing and Control System | 1.2.4.3 | Control System Software | 1.2.4.3 Control System Software | cell-link@smartsheet.com | 2021-11-30 20:45 |  | 96d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.4.3.2.1 | 0 | 0 | 4799.9263 | 4919.9245 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.3.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1838.6718 | 0 | 3677.3436 | 0 | 0 | 1.2.4.3.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.3.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.3.2.1 | 0 | 0 | 4799.9263 | 4919.9245 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9719.8509 | 1.2.4.3.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.3.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9719.8509 | 1.2.4.3.2.1 | 9719.8509 | 9719.8509 | 0 | 0 | 4799.9263 | 9719.8509 | 9719.8509 | 9719.8509 | 9719.8509 | 9719.8509 | 9719.8509 | 9719.8509 | 9719.8509 | 9719.8509 | 0 | 0 | 4799.9263 | 9719.8509 | 9719.8509 | 9719.8509 | 9719.8509 | 9719.8509 | 9719.8509 | 9719.8509 | 9719.8509 | 9719.8509
| 1.2 | 1.2.4.3.2.2 | C |  | PSL | Controls Software: Payout Encoder Specify, Procure, and Test |  | 3.889% | Labor Hours | EN |  | VQ |  | 115 | 0% | 2021-10-01 | 2021-11-30 |  | TRUE |  |  | 35 | 35 | [10 empty] | 4025 | 4025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8050 | 0% | 0 | 8399.8711 | 8399.8711 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | [9 empty] | 8399.8711 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.4 | Computing and Control System | 1.2.4 Computing and Control System | 1.2.4.3 | Control System Software | 1.2.4.3 Control System Software | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 96d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.4.3.2.2 | 4199.9356 | 4199.9356 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.3.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.3.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.3.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.3.2.2 | 4199.9356 | 4199.9356 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8399.8711 | 1.2.4.3.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.3.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8399.8711 | 1.2.4.3.2.2 | 8399.8711 | 17999.8711 | 4199.9356 | 8399.8711 | 8399.8711 | 8399.8711 | 8399.8711 | 8399.8711 | 8399.8711 | 8399.8711 | 8399.8711 | 8399.8711 | 8399.8711 | 8399.8711 | 13799.9356 | 17999.8711 | 17999.8711 | 17999.8711 | 17999.8711 | 17999.8711 | 17999.8711 | 17999.8711 | 17999.8711 | 17999.8711 | 17999.8711 | 17999.8711
| 1.2 | 1.2.4.3.2.2 | C |  | PSL | Controls Software: Payout Encoder Specify, Procure, and Test |  |  | CapEx | EN |  | VQ |  | 1 | 0% | 2021-10-01 | 2021-11-30 |  | TRUE |  |  | 9600 | [11 empty] | 9600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9600 | 53% | 0 | 9600 | 9600 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 9600 | CapEx | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.4 | Computing and Control System | 1.2.4 Computing and Control System | 1.2.4.3 | Control System Software | 1.2.4.3 Control System Software | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 96d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.4.3.2.2 | 9600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.3.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.3.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.3.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.3.2.2 | 9600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9600 | 1.2.4.3.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.3.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9600 | 1.2.4.3.2.2 | 9600 | 9600 | 9600 | 9600 | 9600 | 9600 | 9600 | 9600 | 9600 | 9600 | 9600 | 9600 | 9600 | 9600 | 9600 | 9600 | 9600 | 9600 | 9600 | 9600 | 9600 | 9600 | 9600 | 9600 | 9600 | 9600
| 1.2 | 1.2.4.3.2.3 | C |  | PSL | Controls Software: HPP Sensor DGH Box Testing |  | 6.833% | Labor Hours | EN |  | VQ |  | 115 | 0% | 2021-10-13 | 2021-11-23 |  | TRUE |  |  | 63 | 60 | [10 empty] | 7245 | 6900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14145 | 0% | 0 | 14759.7735 | 14759.7735 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | [9 empty] | 14759.7735 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.4 | Computing and Control System | 1.2.4 Computing and Control System | 1.2.4.3 | Control System Software | 1.2.4.3 Control System Software | cell-link@smartsheet.com | 2021-11-30 20:45 |  | 96d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.4.3.2.3 | 7559.884 | 7199.8895 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.3.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.3.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.3.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.3.2.3 | 7559.884 | 7199.8895 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14759.7735 | 1.2.4.3.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.3.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14759.7735 | 1.2.4.3.2.3 | 14759.7735 | 14759.7735 | 7559.884 | 14759.7735 | 14759.7735 | 14759.7735 | 14759.7735 | 14759.7735 | 14759.7735 | 14759.7735 | 14759.7735 | 14759.7735 | 14759.7735 | 14759.7735 | 7559.884 | 14759.7735 | 14759.7735 | 14759.7735 | 14759.7735 | 14759.7735 | 14759.7735 | 14759.7735 | 14759.7735 | 14759.7735 | 14759.7735 | 14759.7735
| 1.2 | 1.2.4.3.3 | C |  | PSL | Controls Software: System Operator Functions (PSL Software Engineer) |  | 13.33% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2022-04-19 | 2022-08-29 |  | TRUE | [9 empty] | 40 | 50 | 50 | 50 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4600 | 5750 | 5750 | 5750 | 5750 | 27600 | 0% | 0 | 28799.5581 | 28799.5581 | [6 empty] | 40 |  | 50 |  | 50 |  | 0 | 0 | 0 | 0 | 4600 | 0 | 5750 | 0 | 5750 | 0 | 5750 | 0 | 21850 | 0% | 0 | 23289.8426 | 23289.8426 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | 86145 |  |  |  |  | 86145 |  | 52089.4007 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.4 | Computing and Control System | 1.2.4 Computing and Control System | 1.2.4.3 | Control System Software | 1.2.4.3 Control System Software | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 96d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.4.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4799.9263 | 5999.9079 | 5999.9079 | 5999.9079 | 5999.9079 | 1.2.4.3.3 | 0 | 0 | 0 | 0 | 4903.1248 | 0 | 6128.906 | 0 | 6128.906 | 0 | 6128.906 | 0 | 1.2.4.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4799.9263 | 5999.9079 | 5999.9079 | 5999.9079 | 5999.9079 | 28799.5581 | 1.2.4.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28799.5581 | 1.2.4.3.3 | 28799.5581 | 34799.5581 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4799.9263 | 10799.8343 | 16799.7422 | 22799.6502 | 28799.5581 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6799.9263 | 12799.8343 | 20799.7422 | 26799.6502 | 34799.5581
| 1.2 | 1.2.4.3.3 | C |  | PSL | Controls Software: System Operator Functions |  |  | CapEx |  |  | VQ | 1 | 1 | 0% | 2022-04-19 | 2022-08-29 |  | TRUE | [9 empty] | 2000 |  | 2000 |  | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 2000 | 0 | 2000 | 6000 | 53% | 0 | 6000 | 6000 | [5 empty] | 1000 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 53% | 0 | 1000 | 1000 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 | 6000 |  |  |  |  | 6000 |  | 7000 | CapEx | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.4 | Computing and Control System | 1.2.4 Computing and Control System | 1.2.4.3 | Control System Software | 1.2.4.3 Control System Software | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 96d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.4.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 2000 | 0 | 2000 | 1.2.4.3.3 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 2000 | 0 | 2000 | 6000 | 1.2.4.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 1.2.4.3.3 | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 2000 | 4000 | 4000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 2000 | 4000 | 4000 | 6000
| 1.2 | 1.2.4.3.4 | C |  | PSL | Controls Software: PLC & Software Development (w/sub-tasks) |  | 0% | Labor Hours | EN |  |  |  | 115 | 0% | 2020-09-29 | 2024-03-06 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -103500 | 10 | [5 empty] | 50 |  | 50 |  |  |  | 1150 | 5750 | 0 | 0 | 5750 | 0 | 5750 | 0 | 5750 | 0 | 0 | 0 | 24150 | 0% | 0 | 25741.405 | -12783.595 | 25 |  |  |  | 25 | [7 empty] | 2875 | 0 | 0 | 0 | 2875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5750 | 0% | 0 | 6260.6774 | 6260.6774 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | 103500 | 103500 |  | 38525 |  |  |  | 32002.0825 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.4 | Computing and Control System | 1.2.4 Computing and Control System | 1.2.4.3 | Control System Software | 1.2.4.3 Control System Software | cell-link@smartsheet.com | 2021-11-30 20:45 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.4.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.3.4 | 1225.7812 | 6128.906 | 0 | 0 | 6128.906 | 0 | 6128.906 | 0 | 6128.906 | 0 | 0 | 0 | 1.2.4.3.4 | 3130.3387 | 0 | 0 | 0 | 3130.3387 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.4.3.5 | C |  | PSL | Controls Software: SCADA Monitoring Software Procurement - Server |  | 1.111% | Labor Hours | EN |  |  |  | 115 | 0% | 2022-02-01 | 2022-04-04 |  | TRUE | [13 empty] | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2300 | 2300 | 0% | 0 | 2399.9632 | 2399.9632 | 10 | 10 | [10 empty] | 1150 | 1150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2300 | 0% | 0 | 2451.5624 | 2451.5624 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | [9 empty] | 4851.5256 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.4 | Computing and Control System | 1.2.4 Computing and Control System | 1.2.4.3 | Control System Software | 1.2.4.3 Control System Software | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.4.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2399.9632 | 1.2.4.3.5 | 1225.7812 | 1225.7812 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2399.9632 | 2399.9632 | 1.2.4.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2399.9632 | 1.2.4.3.5 | 2399.9632 | 4799.9263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2399.9632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4799.9263
| 1.2 | 1.2.4.3.5 | C |  | PSL | Controls Software: SCADA Monitoring Software - Server |  |  | CapEx | EN |  |  |  | 1 | 0% | 2022-02-01 | 2022-04-04 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | 5000 | 5000 | [10 empty] | 5000 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 53% | 0 | 10000 | 10000 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 10000 | CapEx | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.4 | Computing and Control System | 1.2.4 Computing and Control System | 1.2.4.3 | Control System Software | 1.2.4.3 Control System Software | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.4.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.3.5 | 5000 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.3.5 | 0 | 2399.9632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2399.9632
| 1.2 | 1.2.4.3.5 | C |  | PSL | Controls Software: SCADA Monitoring Software Procurement Ignition 25K |  | 1.111% | Labor Hours | EN |  |  |  | 115 | 0% | 2022-02-01 | 2022-04-04 |  | TRUE | [13 empty] | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2300 | 2300 | 0% | 0 | 2399.9632 | 2399.9632 | 10 | 10 | [10 empty] | 1150 | 1150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2300 | 0% | 0 | 2451.5624 | 2451.5624 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | [9 empty] | 4851.5256 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.4 | Computing and Control System | 1.2.4 Computing and Control System | 1.2.4.3 | Control System Software | 1.2.4.3 Control System Software | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.4.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2399.9632 | 1.2.4.3.5 | 1225.7812 | 1225.7812 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2399.9632 | 2399.9632 | 1.2.4.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2399.9632 | 1.2.4.3.5 | 2399.9632 | 2399.9632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2399.9632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2399.9632
| 1.2 | 1.2.4.3.5 | C |  | PSL | Controls Software: SCADA Monitoring Software - Ignition 25K |  |  | CapEx | EN |  |  |  | 1 | 0% | 2022-02-01 | 2022-04-04 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | 12500 | 12500 | [10 empty] | 12500 | 12500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 53% | 0 | 25000 | 25000 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 25000 | CapEx | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.4 | Computing and Control System | 1.2.4 Computing and Control System | 1.2.4.3 | Control System Software | 1.2.4.3 Control System Software | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.4.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.3.5 | 12500 | 12500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.4.3.6 | C |  | PSL | Controls Software: SCADA Screen Development |  | 0% | Labor Hours | EN |  |  |  | 115 | 0% | 2022-04-05 | 2022-09-19 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [6 empty] | 40 | 40 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 4600 | 4600 | 0 | 0 | 0 | 0 | 9200 | 0% | 0 | 9806.2495 | 9806.2495 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | [9 empty] | 9806.2495 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.4 | Computing and Control System | 1.2.4 Computing and Control System | 1.2.4.3 | Control System Software | 1.2.4.3 Control System Software | cell-link@smartsheet.com | 2021-11-30 20:45 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.4.3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 4903.1248 | 4903.1248 | 0 | 0 | 0 | 0 | 1.2.4.3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.4.4.1 | C |  | PSL | Motor Drives: Functional Requirements (PSL_Engineer) |  | 13.33% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2020-11-14 | 2021-03-18 | [10 empty] | 45 | 45 | 45 | 45 | 45 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 5175 | 5175 | 5175 | 5175 | 5175 | 1725 | 27600 | 0% | 0 | 28799.5581 | 28799.5581 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 2690 | 16024 | [5 empty] | 18714 |  | 28799.5581 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.4 | Computing and Control System | 1.2.4 Computing and Control System | 1.2.4.4 | Motor Drives | 1.2.4.4 Motor Drives | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 288d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.4.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 5399.9171 | 5399.9171 | 5399.9171 | 5399.9171 | 5399.9171 | 1799.9724 | 1.2.4.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 5399.9171 | 5399.9171 | 5399.9171 | 5399.9171 | 5399.9171 | 1799.9724 | 28799.5581 | 1.2.4.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28799.5581 | 1.2.4.4.1 | 28799.5581 | 28799.5581 | 0 | 0 | 0 | 0 | 0 | 0 | 5399.9171 | 10799.8343 | 16199.7514 | 21599.6686 | 26999.5857 | 28799.5581 | 0 | 0 | 0 | 0 | 0 | 0 | 5399.9171 | 10799.8343 | 16199.7514 | 21599.6686 | 26999.5857 | 28799.5581
| 1.2 | 1.2.4.4.1 | C |  | PSL | Motor Drives: Functional Requirements (PSL_Software Engineer) |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2020-11-14 | 2021-03-18 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 2690 | 16024 | [5 empty] | 18714 |  | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.4 | Computing and Control System | 1.2.4 Computing and Control System | 1.2.4.4 | Motor Drives | 1.2.4.4 Motor Drives | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 288d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.4.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.4.4.2 | C |  | PSL | Motor Drives: Electrical Requirements (PSL_Engineer) |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2020-12-28 | 2021-06-11 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 16162 | 5051 |  |  |  |  | 21213 |  | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.4 | Computing and Control System | 1.2.4 Computing and Control System | 1.2.4.4 | Motor Drives | 1.2.4.4 Motor Drives | cell-link@smartsheet.com | 2021-11-30 20:52 |  | 216d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.4.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.4.4.2 | C |  | PSL | Motor Drives: Electrical Requirements (PSL_Software Engineer) |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2020-12-28 | 2021-06-11 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 16162 | 5051 |  |  |  |  | 21213 |  | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.4 | Computing and Control System | 1.2.4 Computing and Control System | 1.2.4.4 | Motor Drives | 1.2.4.4 Motor Drives | cell-link@smartsheet.com | 2021-11-30 20:52 |  | 216d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.4.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.4.4.3 | C |  | PSL | Motor Drives: Specify and Procure (PSL_Engineer) |  | 0.8889% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2020-12-07 | 2023-06-16 |  | TRUE | [7 empty] | 8 | 8 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 920 | 920 | 0 | 0 | 0 | 0 | 0 | 1840 | 0% | 0 | 1919.9705 | 1919.9705 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | 21536 |  |  |  |  | 21536 |  | 1919.9705 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.4 | Computing and Control System | 1.2.4 Computing and Control System | 1.2.4.4 | Motor Drives | 1.2.4.4 Motor Drives | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 216d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.4.4.3 | 0 | 0 | 0 | 0 | 0 | 959.9853 | 959.9853 | 0 | 0 | 0 | 0 | 0 | 1.2.4.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.4.3 | 0 | 0 | 0 | 0 | 0 | 959.9853 | 959.9853 | 0 | 0 | 0 | 0 | 0 | 1919.9705 | 1.2.4.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1919.9705 | 1.2.4.4.3 | 1919.9705 | 3839.9411 | 0 | 0 | 0 | 0 | 0 | 959.9853 | 1919.9705 | 1919.9705 | 1919.9705 | 1919.9705 | 1919.9705 | 1919.9705 | 0 | 0 | 0 | 0 | 0 | 1919.9705 | 3839.9411 | 3839.9411 | 3839.9411 | 3839.9411 | 3839.9411 | 3839.9411
| 1.2 | 1.2.4.4.3 | C |  | PSL | Motor Drives: Specify and Procure (PSL_Software Engineer) |  | 0.8889% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2020-12-07 | 2023-06-16 |  | TRUE | [7 empty] | 8 | 8 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 920 | 920 | 0 | 0 | 0 | 0 | 0 | 1840 | 0% | 0 | 1919.9705 | 1919.9705 | 4 | 4 | [10 empty] | 460 | 460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 920 | 0% | 0 | 980.625 | 980.625 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | 21536 |  |  |  |  | 21536 |  | 2900.5955 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.4 | Computing and Control System | 1.2.4 Computing and Control System | 1.2.4.4 | Motor Drives | 1.2.4.4 Motor Drives | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 216d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.4.4.3 | 0 | 0 | 0 | 0 | 0 | 959.9853 | 959.9853 | 0 | 0 | 0 | 0 | 0 | 1.2.4.4.3 | 490.3125 | 490.3125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.4.3 | 0 | 0 | 0 | 0 | 0 | 959.9853 | 959.9853 | 0 | 0 | 0 | 0 | 0 | 1919.9705 | 1.2.4.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1919.9705 | 1.2.4.4.3 | 1919.9705 | 1919.9705 | 0 | 0 | 0 | 0 | 0 | 959.9853 | 1919.9705 | 1919.9705 | 1919.9705 | 1919.9705 | 1919.9705 | 1919.9705 | 0 | 0 | 0 | 0 | 0 | 959.9853 | 1919.9705 | 1919.9705 | 1919.9705 | 1919.9705 | 1919.9705 | 1919.9705
| 1.2 | 1.2.4.4.3 | C |  | PSL | Motor Drives: Specify and Procure |  |  | CapEx |  |  | VQ | 1 | 1 | 0% | 2020-12-07 | 2023-06-16 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | 25000 | 25000 | [10 empty] | 25000 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 53% | 0 | 50000 | 50000 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 | 140071 |  |  |  |  | 140071 |  | 50000 | CapEx | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.4 | Computing and Control System | 1.2.4 Computing and Control System | 1.2.4.4 | Motor Drives | 1.2.4.4 Motor Drives | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 216d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.4.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.4.3 | 25000 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.4.4.4 | C |  | PSL | Motor Drives: Programming and Testing at PSL (PSL_Engineer) |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2020-10-07 | 2023-09-27 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [5 empty] | 40 | 40 |  | 40 |  | 30 |  | 0 | 0 | 0 | 0 | 4600 | 4600 | 4600 | 0 | 4600 | 0 | 3450 | 0 | 21850 | 0% | 0 | 23289.8426 | 23289.8426 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | 47858 |  |  |  |  | 47858 |  | 23289.8426 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.4 | Computing and Control System | 1.2.4 Computing and Control System | 1.2.4.4 | Motor Drives | 1.2.4.4 Motor Drives | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 288d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.4.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.4.4 | 0 | 0 | 0 | 0 | 4903.1248 | 4903.1248 | 4903.1248 | 0 | 4903.1248 | 0 | 3677.3436 | 0 | 1.2.4.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.4.4 | 0 | 8999.8619 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 599.9908 | 599.9908 | 599.9908 | 599.9908 | 1799.9724 | 2999.954 | 4199.9356 | 5399.9171 | 6599.8987 | 7799.8803 | 8999.8619 | 8999.8619
| 1.2 | 1.2.4.4.4 | C |  | PSL | Motor Drives: Programming and Testing at PSL (PSL_Software Engineer) |  | 4.167% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2020-10-07 | 2023-09-27 |  | TRUE |  |  | 5 |  |  |  | 10 | 10 | 10 | 10 | 10 | 10 | 10 |  | 575 | 0 | 0 | 0 | 1150 | 1150 | 1150 | 1150 | 1150 | 1150 | 1150 | 0 | 8625 | 0% | 0 | 8999.8619 | 8999.8619 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | 47858 |  |  |  |  | 47858 |  | 8999.8619 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.4 | Computing and Control System | 1.2.4 Computing and Control System | 1.2.4.4 | Motor Drives | 1.2.4.4 Motor Drives | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 288d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.4.4.4 | 599.9908 | 0 | 0 | 0 | 1199.9816 | 1199.9816 | 1199.9816 | 1199.9816 | 1199.9816 | 1199.9816 | 1199.9816 | 0 | 1.2.4.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.4.4 | 599.9908 | 0 | 0 | 0 | 1199.9816 | 1199.9816 | 1199.9816 | 1199.9816 | 1199.9816 | 1199.9816 | 1199.9816 | 0 | 8999.8619 | 1.2.4.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8999.8619 | 1.2.4.4.4 | 8999.8619 | 8999.8619 | 599.9908 | 599.9908 | 599.9908 | 599.9908 | 1799.9724 | 2999.954 | 4199.9356 | 5399.9171 | 6599.8987 | 7799.8803 | 8999.8619 | 8999.8619 | 599.9908 | 599.9908 | 599.9908 | 599.9908 | 1799.9724 | 2999.954 | 4199.9356 | 5399.9171 | 6599.8987 | 7799.8803 | 8999.8619 | 8999.8619
| 1.2 | 1.2.4.4.5 | C |  | PSL | Motor Drives: Plan Installations of New Motor Drives in Former Unico Locations |  | 4.444% | Labor Hours | EN |  |  |  | 115 | 0% | 2021-12-09 | 2022-04-19 |  | TRUE |  |  |  |  | 40 | 40 | [8 empty] | 0 | 0 | 4600 | 4600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9200 | 0% | 0 | 9599.8527 | 9599.8527 | [7 empty] | 16 |  | 16 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1840 | 0 | 1840 | 0 | 0 | 3680 | 0% | 0 | 3922.4998 | 3922.4998 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | [9 empty] | 13522.3525 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.4 | Computing and Control System | 1.2.4 Computing and Control System | 1.2.4.4 | Motor Drives | 1.2.4.4 Motor Drives | cell-link@smartsheet.com | 2021-11-30 20:52 |  | 288d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.4.4.5 | 0 | 0 | 4799.9263 | 4799.9263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1961.2499 | 0 | 1961.2499 | 0 | 0 | 1.2.4.4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.4.5 | 0 | 0 | 4799.9263 | 4799.9263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9599.8527 | 1.2.4.4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9599.8527 | 1.2.4.4.5 | 9599.8527 | 9599.8527 | 0 | 0 | 4799.9263 | 9599.8527 | 9599.8527 | 9599.8527 | 9599.8527 | 9599.8527 | 9599.8527 | 9599.8527 | 9599.8527 | 9599.8527 | 0 | 0 | 4799.9263 | 9599.8527 | 9599.8527 | 9599.8527 | 9599.8527 | 9599.8527 | 9599.8527 | 9599.8527 | 9599.8527 | 9599.8527
| 1.2 | 1.2.4.5.1 | C |  | PSL | E-Stop: Evaluate EHWD system (PSL_Engineer) |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2021-01-29 | 2021-04-22 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 9384 | [5 empty] | 9384 |  | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.4 | Computing and Control System | 1.2.4 Computing and Control System | 1.2.4.5 | E-Stop System | 1.2.4.5 E-Stop System | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 48d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.4.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.4.5.1 | C |  | PSL | E-Stop: Evaluate EHWD system (PSL_Software Engineer) |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2021-01-29 | 2021-04-22 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 9384 | [5 empty] | 9384 |  | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.4 | Computing and Control System | 1.2.4 Computing and Control System | 1.2.4.5 | E-Stop System | 1.2.4.5 E-Stop System | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 48d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.4.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.4.5.2 | C |  | PSL | E-Stop: Define Requirements (PSL_Engineer) |  | 4.444% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2021-10-01 | 2022-01-19 |  |  |  |  | 20 | 20 | 20 | 20 | [8 empty] | 2300 | 2300 | 2300 | 2300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9200 | 0% | 0 | 9599.8527 | 9599.8527 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 9384 | [5 empty] | 9384 |  | 9599.8527 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.4 | Computing and Control System | 1.2.4 Computing and Control System | 1.2.4.5 | E-Stop System | 1.2.4.5 E-Stop System | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 48d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.4.5.2 | 2399.9632 | 2399.9632 | 2399.9632 | 2399.9632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.5.2 | 2399.9632 | 2399.9632 | 2399.9632 | 2399.9632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9599.8527 | 1.2.4.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9599.8527 | 1.2.4.5.2 | 9599.8527 | 9599.8527 | 2399.9632 | 4799.9263 | 7199.8895 | 9599.8527 | 9599.8527 | 9599.8527 | 9599.8527 | 9599.8527 | 9599.8527 | 9599.8527 | 9599.8527 | 9599.8527 | 2399.9632 | 4799.9263 | 7199.8895 | 9599.8527 | 9599.8527 | 9599.8527 | 9599.8527 | 9599.8527 | 9599.8527 | 9599.8527 | 9599.8527 | 9599.8527
| 1.2 | 1.2.4.5.3 | C |  | PSL | E-Stop: TOS E-stop Box Analysis, Documentation Updates |  | 5.667% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2021-12-16 | 2022-03-24 | [6 empty] | 25 | 38 | 39 | [7 empty] | 0 | 0 | 2875 | 4370 | 4485 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11730 | 0% | 0 | 12239.8122 | 12239.8122 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 9384 | [5 empty] | 9384 |  | 12239.8122 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.4 | Computing and Control System | 1.2.4 Computing and Control System | 1.2.4.5 | E-Stop System | 1.2.4.5 E-Stop System | cell-link@smartsheet.com | 2021-11-30 20:45 |  | 72d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.4.5.3 | 0 | 0 | 2999.954 | 4559.93 | 4679.9282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.5.3 | 0 | 0 | 2999.954 | 4559.93 | 4679.9282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12239.8122 | 1.2.4.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12239.8122 | 1.2.4.5.3 | 12239.8122 | 12239.8122 | 0 | 0 | 2999.954 | 7559.884 | 12239.8122 | 12239.8122 | 12239.8122 | 12239.8122 | 12239.8122 | 12239.8122 | 12239.8122 | 12239.8122 | 0 | 0 | 2999.954 | 7559.884 | 12239.8122 | 12239.8122 | 12239.8122 | 12239.8122 | 12239.8122 | 12239.8122 | 12239.8122 | 12239.8122
| 1.2 | 1.2.4.5.4 | C |  | PSL | E-Stop: System E-stop Controller Redesign, Build, Test |  | 9.778% | Labor Hours | EN |  |  |  | 115 | 0% | 2021-12-16 | 2022-03-24 | [6 empty] | 20 | 28 | 35 | 43 | 50 | [5 empty] | 0 | 0 | 2300 | 3220 | 4025 | 4945 | 5750 | 0 | 0 | 0 | 0 | 0 | 20240 | 0% | 0 | 21119.6759 | 21119.6759 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | [9 empty] | 21119.6759 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.4 | Computing and Control System | 1.2.4 Computing and Control System | 1.2.4.5 | E-Stop System | 1.2.4.5 E-Stop System | cell-link@smartsheet.com | 2021-11-30 20:45 |  | 72d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.4.5.4 | 0 | 0 | 2399.9632 | 3359.9484 | 4199.9356 | 5159.9208 | 5999.9079 | 0 | 0 | 0 | 0 | 0 | 1.2.4.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.5.4 | 0 | 0 | 2399.9632 | 3359.9484 | 4199.9356 | 5159.9208 | 5999.9079 | 0 | 0 | 0 | 0 | 0 | 21119.6759 | 1.2.4.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21119.6759 | 1.2.4.5.4 | 21119.6759 | 21119.6759 | 0 | 0 | 2399.9632 | 5759.9116 | 9959.8472 | 15119.768 | 21119.6759 | 21119.6759 | 21119.6759 | 21119.6759 | 21119.6759 | 21119.6759 | 0 | 0 | 2399.9632 | 5759.9116 | 9959.8472 | 15119.768 | 21119.6759 | 21119.6759 | 21119.6759 | 21119.6759 | 21119.6759 | 21119.6759
| 1.2 | 1.2.4.5.5 | C |  | PSL | E-Stop: TOS E-stop Controller Redesign, Build, Test |  | 11.39% | Labor Hours | EN |  |  |  | 115 | 0% | 2021-10-01 | 2022-02-21 |  |  |  |  | 45 | 35 | 25 | 50 | 50 | [7 empty] | 5175 | 4025 | 2875 | 5750 | 5750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23575 | 0% | 0 | 24599.6225 | 24599.6225 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | [9 empty] | 24599.6225 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.4 | Computing and Control System | 1.2.4 Computing and Control System | 1.2.4.5 | E-Stop System | 1.2.4.5 E-Stop System | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 72d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.4.5.5 | 5399.9171 | 4199.9356 | 2999.954 | 5999.9079 | 5999.9079 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.5.5 | 5399.9171 | 4199.9356 | 2999.954 | 5999.9079 | 5999.9079 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24599.6225 | 1.2.4.5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24599.6225 | 1.2.4.5.5 | 24599.6225 | 24599.6225 | 5399.9171 | 9599.8527 | 12599.8067 | 18599.7146 | 24599.6225 | 24599.6225 | 24599.6225 | 24599.6225 | 24599.6225 | 24599.6225 | 24599.6225 | 24599.6225 | 5399.9171 | 9599.8527 | 12599.8067 | 18599.7146 | 24599.6225 | 24599.6225 | 24599.6225 | 24599.6225 | 24599.6225 | 24599.6225 | 24599.6225 | 24599.6225
| 1.2 | 1.2.4.6.1 | C |  | PSL | DCC: Computing System (PSL_Engineer) |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2021-04-29 | 2023-07-27 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [5 empty] | 39.152 |  | 39.152 |  | 39.152 |  |  | 0 | 0 | 0 | 0 | 0 | 4502.48 | 0 | 4502.48 | 0 | 4502.48 | 0 | 0 | 13507.44 | 0% | 0 | 14397.5356 | 14397.5356 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 37521 | 16 |  |  |  |  | 37536 |  | 14397.5356 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.4 | Computing and Control System | 1.2.4 Computing and Control System | 1.2.4.6 | Drill Control Center | 1.2.4.6 Drill Control Center | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 216d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.4.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.6.1 | 0 | 0 | 0 | 0 | 0 | 4799.1785 | 0 | 4799.1785 | 0 | 4799.1785 | 0 | 0 | 1.2.4.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.4.6.1 | C |  | PSL | DCC: Computing System (PSL_Software Engineer) |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2021-04-29 | 2023-07-27 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [6 empty] | 39.152 |  | 39.152 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 4502.48 | 0 | 4502.48 | 0 | 0 | 0 | 9004.96 | 0% | 0 | 9598.357 | 9598.357 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 37521 | 16 |  |  |  |  | 37536 |  | 9598.357 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.4 | Computing and Control System | 1.2.4 Computing and Control System | 1.2.4.6 | Drill Control Center | 1.2.4.6 Drill Control Center | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 216d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.4.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 4799.1785 | 0 | 4799.1785 | 0 | 0 | 0 | 1.2.4.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.4.6.1 | C |  | PSL | DCC: Computing System |  |  | CapEx |  |  | VQ | 1 | 1 | 0% | 2021-04-29 | 2023-07-27 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 7997 | 3 |  |  |  |  | 8000 |  | 0 | CapEx | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.4 | Computing and Control System | 1.2.4 Computing and Control System | 1.2.4.6 | Drill Control Center | 1.2.4.6 Drill Control Center | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 216d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.4.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.4.6.2 | C |  | PSL | DCC: Electrical Improvements - Heater Upgrade Design and Procure |  | 1.111% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2021-08-07 | 2021-08-26 |  | TRUE | [12 empty] | 20 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2300 | 0 | 2300 | 0% | 0 | 2399.9632 | 2399.9632 |  |  |  |  | 20 |  | 10 | [5 empty] | 0 | 0 | 0 | 0 | 2300 | 0 | 1150 | 0 | 0 | 0 | 0 | 0 | 3450 | 0% | 0 | 3677.3436 | 3677.3436 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | 14358 |  |  |  |  | 14358 |  | 6077.3067 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.4 | Computing and Control System | 1.2.4 Computing and Control System | 1.2.4.6 | Drill Control Center | 1.2.4.6 Drill Control Center | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 216d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.4.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2399.9632 | 0 | 1.2.4.6.2 | 0 | 0 | 0 | 0 | 2451.5624 | 0 | 1225.7812 | 0 | 0 | 0 | 0 | 0 | 1.2.4.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2399.9632 | 0 | 2399.9632 | 1.2.4.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2399.9632 | 1.2.4.6.2 | 2399.9632 | 6899.9632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2399.9632 | 2399.9632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6899.9632 | 6899.9632
| 1.2 | 1.2.4.6.2 | C |  | PSL | DCC: Electrical Improvements - Heater Upgrade Design and Procure |  |  | CapEx |  |  | VQ | 1 | 1 | 0% | 2021-08-07 | 2021-08-26 |  | TRUE | [12 empty] | 4500 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500 | 0 | 4500 | 53% | 0 | 4500 | 4500 | [5 empty] | 1200 | 1200 | [5 empty] | 0 | 0 | 0 | 0 | 1200 | 1200 | 1200 | 0 | 0 | 0 | 0 | 0 | 3600 | 53% | 0 | 3600 | 3600 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 | 3600 |  |  |  |  | 3600 |  | 8100 | CapEx | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.4 | Computing and Control System | 1.2.4 Computing and Control System | 1.2.4.6 | Drill Control Center | 1.2.4.6 Drill Control Center | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 216d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.4.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500 | 0 | 1.2.4.6.2 | 0 | 0 | 0 | 0 | 1200 | 1200 | 1200 | 0 | 0 | 0 | 0 | 0 | 1.2.4.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500 | 0 | 4500 | 1.2.4.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500 | 1.2.4.6.2 | 4500 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500 | 4500
| 1.2 | 1.2.4.7.1 | C |  | PSL | Outdoor Cables: Evaluate/inventory SES & SES to TOS Cables - Signal |  | 2.222% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2022-01-15 | 2022-02-24 | [8 empty] | 40 | [7 empty] | 0 | 0 | 0 | 0 | 4600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4600 | 0% | 0 | 4799.9263 | 4799.9263 | [7 empty] | 20 | 20 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2300 | 2300 | 0 | 0 | 0 | 4600 | 0% | 0 | 4903.1248 | 4903.1248 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 9384 | [5 empty] | 9384 |  | 9703.0511 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.4 | Computing and Control System | 1.2.4 Computing and Control System | 1.2.4.7 | Outdoor Cables | 1.2.4.7 Outdoor Cables | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 48d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.4.7.1 | 0 | 0 | 0 | 0 | 4799.9263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.7.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2451.5624 | 2451.5624 | 0 | 0 | 0 | 1.2.4.7.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.7.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.7.1 | 0 | 0 | 0 | 0 | 4799.9263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4799.9263 | 1.2.4.7.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.7.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4799.9263 | 1.2.4.7.1 | 4799.9263 | 4799.9263 | 0 | 0 | 0 | 0 | 4799.9263 | 4799.9263 | 4799.9263 | 4799.9263 | 4799.9263 | 4799.9263 | 4799.9263 | 4799.9263 | 0 | 0 | 0 | 0 | 4799.9263 | 4799.9263 | 4799.9263 | 4799.9263 | 4799.9263 | 4799.9263 | 4799.9263 | 4799.9263
| 1.2 | 1.2.4.7.2 | C |  | PSL | Outdoor Cables: Design and Procure Replacement Components - Signal |  | 3.278% | Labor Hours | EN |  | EE |  | 115 | 0% | 2022-02-25 | 2022-03-29 | [9 empty] | 15 | 15 | 19 | 10 |  |  |  |  | 0 | 0 | 0 | 1725 | 1725 | 2185 | 1725 | 2185 | 0 | 0 | 0 | 9545 | 0% | 0 | 9959.8472 | 9959.8472 |  |  |  | 8 | 8 | 8 | [6 empty] | 0 | 0 | 0 | 920 | 920 | 920 | 0 | 0 | 0 | 0 | 0 | 0 | 2760 | 0% | 0 | 2941.8749 | 2941.8749 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | [9 empty] | 12901.722 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.4 | Computing and Control System | 1.2.4 Computing and Control System | 1.2.4.7 | Outdoor Cables | 1.2.4.7 Outdoor Cables | cell-link@smartsheet.com | 2021-11-30 20:52 |  | 216d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.4.7.2 | 0 | 0 | 0 | 0 | 1799.9724 | 1799.9724 | 2279.965 | 1799.9724 | 2279.965 | 0 | 0 | 0 | 1.2.4.7.2 | 0 | 0 | 0 | 980.625 | 980.625 | 980.625 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.7.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.7.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.7.2 | 0 | 0 | 0 | 0 | 0 | 1799.9724 | 1799.9724 | 2279.965 | 1199.9816 | 0 | 0 | 0 | 7079.8914 | 1.2.4.7.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.7.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7079.8914 | 1.2.4.7.2 | 9959.8472 | 37159.8472 | 0 | 0 | 0 | 0 | 1799.9724 | 3599.9448 | 5879.9098 | 7679.8822 | 9959.8472 | 9959.8472 | 9959.8472 | 9959.8472 | 0 | 0 | 0 | 0 | 1799.9724 | 10399.9448 | 19479.9098 | 28079.8822 | 37159.8472 | 37159.8472 | 37159.8472 | 37159.8472
| 1.2 | 1.2.4.7.2 | C |  | PSL | Outdoor Cables: Design and Procure Replacement Components - Signal |  |  | CapEx |  |  | EE | 1 | 1 | 0% | 2022-02-25 | 2022-03-29 | [9 empty] | 6800 | 6800 | 6800 | 6800 |  |  |  |  | 0 | 0 | 0 | 0 | 6800 | 6800 | 6800 | 6800 | 0 | 0 | 0 | 27200 | 53% | 0 | 27200 | 27200 |  |  |  | 3400 | 3400 | 3400 | [6 empty] | 0 | 0 | 0 | 3400 | 3400 | 3400 | 0 | 0 | 0 | 0 | 0 | 0 | 10200 | 53% | 0 | 10200 | 10200 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 27163 | 2837 |  |  |  |  | 30000 |  | 37400 | CapEx | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.4 | Computing and Control System | 1.2.4 Computing and Control System | 1.2.4.7 | Outdoor Cables | 1.2.4.7 Outdoor Cables | cell-link@smartsheet.com | 2021-11-30 20:52 |  | 216d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.4.7.2 |  | 0 | 0 | 0 | 0 | 6800 | 6800 | 6800 | 6800 | 0 | 0 | 0 | 1.2.4.7.2 | 0 | 0 | 0 | 3400 | 3400 | 3400 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.7.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.7.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.7.2 | 0 | 0 | 0 | 0 | 0 | 6800 | 6800 | 6800 | 6800 | 0 | 0 | 0 | 27200 | 1.2.4.7.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.7.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27200 | 1.2.4.7.2 | 27200 | 27200 |  | 0 | 0 | 0 | 0 | 6800 | 13600 | 20400 | 27200 | 27200 | 27200 | 27200 |  | 0 | 0 | 0 | 0 | 6800 | 13600 | 20400 | 27200 | 27200 | 27200 | 27200
| 1.2 | 1.2.4.7.3 | C |  | PSL | Outdoor Cables: Fabricate and Test SES & SES to TOS Cables - Signal |  | 4.5% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2022-05-27 | 2023-07-27 |  | TRUE | [9 empty] | 40 | 41 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4600 | 4715 | 0 | 0 | 0 | 9315 | 0% | 0 | 9719.8509 | 9719.8509 |  |  |  |  | 8 | 8 |  | 8 |  |  |  |  | 0 | 0 | 0 | 0 | 920 | 920 | 0 | 920 | 0 | 0 | 0 | 0 | 2760 | 0% | 0 | 2941.8749 | 2941.8749 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 16993 | 1810 |  |  |  |  | 18803 |  | 12661.7257 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.4 | Computing and Control System | 1.2.4 Computing and Control System | 1.2.4.7 | Outdoor Cables | 1.2.4.7 Outdoor Cables | cell-link@smartsheet.com | 2021-11-30 20:52 |  | 216d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.4.7.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4799.9263 | 4919.9245 | 0 | 0 | 0 | 1.2.4.7.3 | 0 | 0 | 0 | 0 | 980.625 | 980.625 | 0 | 980.625 | 0 | 0 | 0 | 0 | 1.2.4.7.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.7.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.7.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4799.9263 | 4919.9245 | 0 | 0 | 0 | 9719.8509 | 1.2.4.7.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4.7.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9719.8509 | 1.2.4.7.3 | 9719.8509 | 9719.8509 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4799.9263 | 9719.8509 | 9719.8509 | 9719.8509 | 9719.8509 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4799.9263 | 9719.8509 | 9719.8509 | 9719.8509 | 9719.8509
| 1.2 | 1.2.5.2.2 | C |  | PSL | GEN-2, 3, PDM - Write/Implement Subcontract for CAT Gen Tech/Electrician (PSL_Engineer) |  | 2.222% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2022-03-22 | 2024-04-16 | [9 empty] | 25 | 15 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 2875 | 1725 | 0 | 0 | 0 | 0 | 0 | 4600 | 0% | 0 | 4799.9263 | 4799.9263 | [5 empty] | 15 | 15 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 1725 | 1725 | 0 | 0 | 0 | 0 | 0 | 3450 | 0% | 0 | 3677.3436 | 3677.3436 | [5 empty] | 8 | 8 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 920 | 920 | 0 | 0 | 0 | 0 | 0 | 1840 | 0% | 0 | 2003.4168 | 2003.4168 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 9200 | 0 | [5 empty] | 9200 |  | 10480.6867 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.5 | Electrical Generation and Distribution System | 1.2.5 Electrical Generation and Distribution System | 1.2.5.2 | Generators 2, 3, and PDM | 1.2.5.2 Generators 2, 3, and PDM | cell-link@smartsheet.com | 2021-11-30 13:43 |  | 47d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.5.2.2 | 0 | 0 | 0 | 0 | 0 | 2999.954 | 1799.9724 | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.2 | 0 | 0 | 0 | 0 | 0 | 1838.6718 | 1838.6718 | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.2 | 0 | 0 | 0 | 0 | 0 | 1001.7084 | 1001.7084 | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.2 | 0 | 0 | 0 | 0 | 0 | 2999.954 | 1799.9724 | 0 | 0 | 0 | 0 | 0 | 4799.9263 | 1.2.5.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4799.9263 | 1.2.5.2.2 | 4799.9263 | 4799.9263 | 0 | 0 | 0 | 0 | 0 | 2999.954 | 4799.9263 | 4799.9263 | 4799.9263 | 4799.9263 | 4799.9263 | 4799.9263 | 0 | 0 | 0 | 0 | 0 | 2999.954 | 4799.9263 | 4799.9263 | 4799.9263 | 4799.9263 | 4799.9263 | 4799.9263
| 1.2 | 1.2.5.2.2 | C |  | PSL | GEN-2, 3, PDM - Subcontract for CAT Gen Tech and Electrician (PSL_Engineer) |  |  | CapEx |  |  |  |  | 1 | 0% | 2022-03-22 | 2024-04-16 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [6 empty] | 37500 | 37500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 37500 | 37500 | 0 | 0 | 0 | 0 | 75000 | 53% | 0 | 75000 | 75000 | [5 empty] | 37500 | 37500 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 37500 | 37500 | 0 | 0 | 0 | 0 | 0 | 75000 | 53% | 0 | 75000 | 75000 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 150000 | CapEx | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.5 | Electrical Generation and Distribution System | 1.2.5 Electrical Generation and Distribution System | 1.2.5.2 | Generators 2, 3, and PDM | 1.2.5.2 Generators 2, 3, and PDM | cell-link@smartsheet.com | 2021-11-30 13:43 |  | 47d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.5.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 37500 | 37500 | 0 | 0 | 0 | 0 | 1.2.5.2.2 | 0 | 0 | 0 | 0 | 0 | 37500 | 37500 | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.5.2.3 | C |  | PSL | GEN-2, 3, PDM - Procure Testing Equipment/Repair Parts (PSL_Engineer) |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2020-10-01 | 2021-08-13 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 9199 | 0 | [5 empty] | 9199 |  | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.5 | Electrical Generation and Distribution System | 1.2.5 Electrical Generation and Distribution System | 1.2.5.2 | Generators 2, 3, and PDM | 1.2.5.2 Generators 2, 3, and PDM | cell-link@smartsheet.com | 2021-12-02 12:24 |  | 167d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.5.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.5.2.3 | C |  | PSL | GEN-2, 3, PDM - Procure Testing Equipment/Repair Parts |  |  | M & S |  |  |  | 1 | 1 | 0% | 2020-10-01 | 2021-08-13 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 15300 | 0 | [5 empty] | 15300 |  | 0 | M & S | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.5 | Electrical Generation and Distribution System | 1.2.5 Electrical Generation and Distribution System | 1.2.5.2 | Generators 2, 3, and PDM | 1.2.5.2 Generators 2, 3, and PDM | cell-link@smartsheet.com | 2021-12-02 12:24 |  | 167d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.5.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TRUE | 1.2 | 1.2.5.2.3 | C |  | PSL | GEN-2, 3, PDM - Procure Testing Equipment/Repair Parts - procure generator hoods |  |  | CapEx |  |  |  | 1 | 1 | 0% | 2020-10-01 | 2021-08-13 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 15300 | 0 | [5 empty] | 15300 |  | 0 | CapEx | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.5 | Electrical Generation and Distribution System | 1.2.5 Electrical Generation and Distribution System | 1.2.5.2 | Generators 2, 3, and PDM | 1.2.5.2 Generators 2, 3, and PDM | cell-link@smartsheet.com | 2021-12-02 12:24 |  | 167d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.5.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TRUE | 1.2 | 1.2.5.2.3 | C |  | PSL | GEN-2, 3, PDM - Procure Testing Equipment/Repair Parts - procure generator hoods |  |  | M & S |  |  |  | 1 | 1 | 0% | 2020-10-01 | 2021-08-13 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 0 | M & S | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.5 | Electrical Generation and Distribution System | 1.2.5 Electrical Generation and Distribution System | 1.2.5.2 | Generators 2, 3, and PDM | 1.2.5.2 Generators 2, 3, and PDM | cell-link@smartsheet.com | 2021-12-02 12:24 |  | 167d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.5.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.5.2.4 | C |  | PSL | GEN 1, 2, 3, PDM - Procure/Fabricate Aluminum Skis (PSL_Engineer) |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2020-10-01 | 2020-12-02 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 4600 | 0 | [5 empty] | 4600 |  | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.5 | Electrical Generation and Distribution System | 1.2.5 Electrical Generation and Distribution System | 1.2.5.2 | Generators 2, 3, and PDM | 1.2.5.2 Generators 2, 3, and PDM | cell-link@smartsheet.com | 2021-11-30 13:43 |  | 167d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.5.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.5.2.4 | C |  | PSL | GEN 1, 2, 3, PDM - Procure/Fabricate Aluminum Skis (PSL_Shop) |  | 0% | Labor Hours | TE |  |  | 81 | 77 | 0% | 2020-10-01 | 2020-12-02 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 12960 | 0 | [5 empty] | 12960 |  | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.5 | Electrical Generation and Distribution System | 1.2.5 Electrical Generation and Distribution System | 1.2.5.2 | Generators 2, 3, and PDM | 1.2.5.2 Generators 2, 3, and PDM | cell-link@smartsheet.com | 2021-11-30 13:43 |  | 167d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.5.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.5.2.4 | C |  | PSL | GEN 1, 2, 3, PDM - Procure/Fabricate Aluminum Skis |  |  | CapEx |  |  | HD | 1 | 1 | 0% | 2020-10-01 | 2020-12-02 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 20000 | 0 | [5 empty] | 20000 |  | 0 | CapEx | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.5 | Electrical Generation and Distribution System | 1.2.5 Electrical Generation and Distribution System | 1.2.5.2 | Generators 2, 3, and PDM | 1.2.5.2 Generators 2, 3, and PDM | cell-link@smartsheet.com | 2021-11-30 13:43 |  | 167d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.5.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.5.2.5 | C |  | PSL | GEN-2, 3, PDM - Repair Parts (PSL_Engineer) |  | 0% | Labor Hours | EN |  |  |  | 115 | 0% | 2023-03-03 | 2023-08-08 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [6 empty] | 8 |  | 8 |  | 8 |  | 0 | 0 | 0 | 0 | 0 | 0 | 920 | 0 | 920 | 0 | 920 | 0 | 2760 | 0% | 0 | 2941.8749 | 2941.8749 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | [9 empty] | 2941.8749 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.5 | Electrical Generation and Distribution System | 1.2.5 Electrical Generation and Distribution System | 1.2.5.2 | Generators 2, 3, and PDM | 1.2.5.2 Generators 2, 3, and PDM | cell-link@smartsheet.com | 2021-11-30 13:43 |  | 167d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.5.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 980.625 | 0 | 980.625 | 0 | 980.625 | 0 | 1.2.5.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.5.2.5 | C |  | PSL | GEN-2, 3, PDM - Repair Parts |  |  | M & S |  |  |  |  | 1 | 0% | 2023-03-03 | 2023-08-08 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [6 empty] | 1500 |  | 2000 |  | 1000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 2000 | 0 | 1000 | 0 | 4500 | 53% | 2385 | 6885 | 6885 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 6885 | M & S | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.5 | Electrical Generation and Distribution System | 1.2.5 Electrical Generation and Distribution System | 1.2.5.2 | Generators 2, 3, and PDM | 1.2.5.2 Generators 2, 3, and PDM | cell-link@smartsheet.com | 2021-11-30 13:43 |  | 167d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.5.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 2295 | 0 | 3060 | 0 | 1530 | 0 | 1.2.5.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.5.4.1 | C |  | PSL | Elec Dist. System: Evaluate EHWD system (PSL_Engineer) |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2020-12-01 | 2021-01-25 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 13800 | 0 | [5 empty] | 13800 |  | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.5 | Electrical Generation and Distribution System | 1.2.5 Electrical Generation and Distribution System | 1.2.5.4 | System Electrical Distribution | 1.2.5.4 System Electrical Distribution | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 47d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.5.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.5.4.2 | C |  | PSL | Elec Dist. System: Define Requirements (PSL_Engineer) |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2021-01-26 | 2021-04-19 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 13802 | 0 | [5 empty] | 13802 |  | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.5 | Electrical Generation and Distribution System | 1.2.5 Electrical Generation and Distribution System | 1.2.5.4 | System Electrical Distribution | 1.2.5.4 System Electrical Distribution | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 95d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.5.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.5.4.3 | C |  | PSL | Elec Dist. System: Design & Procure (PSL_Engineer) |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2021-04-20 | 2021-08-23 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [6 empty] | 10 |  | 10 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1150 | 0 | 1150 | 0 | 0 | 0 | 2300 | 0% | 0 | 2451.5624 | 2451.5624 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 3012 | 11004 | [5 empty] | 14016 |  | 2451.5624 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.5 | Electrical Generation and Distribution System | 1.2.5 Electrical Generation and Distribution System | 1.2.5.4 | System Electrical Distribution | 1.2.5.4 System Electrical Distribution | cell-link@smartsheet.com | 2021-11-30 13:35 |  | 95d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.5.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 1225.7812 | 0 | 1225.7812 | 0 | 0 | 0 | 1.2.5.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.5.4.3 | C |  | PSL | Elec Dist. System: Design & Procure |  |  | CapEx |  |  | VQ | 1 | 1 | 0% | 2021-04-20 | 2021-08-23 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [7 empty] | 3500 |  | 3500 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3500 | 0 | 3500 | 0 | 0 | 7000 | 53% | 0 | 7000 | 7000 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 17460 | 62540 | [5 empty] | 80000 |  | 7000 | CapEx | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.5 | Electrical Generation and Distribution System | 1.2.5 Electrical Generation and Distribution System | 1.2.5.4 | System Electrical Distribution | 1.2.5.4 System Electrical Distribution | cell-link@smartsheet.com | 2021-11-30 13:35 |  | 95d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.5.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3500 | 0 | 3500 | 0 | 0 | 1.2.5.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.5.4 | C |  | PSL | Elec Dist. System: Design Review (PSL_Engineers) |  | 0% | Labor Hours | EN |  |  |  | 115 | 0% | 2020-12-01 | 2021-10-12 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | [9 empty] | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.5 | Electrical Generation and Distribution System | 1.2.5 Electrical Generation and Distribution System | 1.2.5.4 | System Electrical Distribution | 1.2.5.4 System Electrical Distribution | cell-link@smartsheet.com | 2021-12-02 12:18 |  | 143d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.5.4.5 | C |  | PSL | Elec Dist. System: Build and Test Subcomponents (PSL_Engineer) |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2021-06-01 | 2021-10-12 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [8 empty] | 18 |  | 18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2070 | 0 | 2070 | 0 | 4140 | 0% | 0 | 4412.8123 | 4412.8123 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 14076 | [5 empty] | 14076 |  | 4412.8123 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.5 | Electrical Generation and Distribution System | 1.2.5 Electrical Generation and Distribution System | 1.2.5.4 | System Electrical Distribution | 1.2.5.4 System Electrical Distribution | cell-link@smartsheet.com | 2021-12-02 12:18 |  | 143d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.5.4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2206.4061 | 0 | 2206.4061 | 0 | 1.2.5.4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.6.1.1 | C |  | PSL | Water Tanks: Identify Upgrades, Replacements & Spares (Driller_PSL_Lead) |  | 0% | Labor Hours | EN |  |  | 1 | 115 | 0% | 2021-01-04 | 2021-03-26 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 2448 | [5 empty] | 2448 |  | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.6 | Water Handling Systems | 1.2.6 Water Handling Systems | 1.2.6.1 | Water Tanks | 1.2.6.1 Water Tanks | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 496d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.6.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.6.1.2 | C |  | PSL | Water Tanks: Procure Repair, Replacements & Spares Parts (Driller_PSL_Lead) |  | 0% | Labor Hours | EN |  |  | 81 | 115 | 0% | 2021-03-29 | 2021-06-18 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [6 empty] | 16 | 16 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1840 | 1840 | 0 | 0 | 0 | 0 | 3680 | 0% | 0 | 3922.4998 | 3922.4998 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 6480 | 0 | [5 empty] | 6480 |  | 3922.4998 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.6 | Water Handling Systems | 1.2.6 Water Handling Systems | 1.2.6.1 | Water Tanks | 1.2.6.1 Water Tanks | cell-link@smartsheet.com | 2021-11-30 13:35 |  | 95d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 1961.2499 | 1961.2499 | 0 | 0 | 0 | 0 | 1.2.6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.6.1.2 | C |  | PSL | Water Tanks: Procure Repair, Replacements & Spares Parts (Driller_PSL_Lead) |  |  | CapEx |  |  | EE | 1 | 1 | 0% | 2021-03-29 | 2021-06-18 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [6 empty] | 750 | 750 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 750 | 0 | 0 | 0 | 0 | 1500 | 53% | 0 | 1500 | 1500 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 7500 | [5 empty] | 7500 |  | 1500 | CapEx | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.6 | Water Handling Systems | 1.2.6 Water Handling Systems | 1.2.6.1 | Water Tanks | 1.2.6.1 Water Tanks | cell-link@smartsheet.com | 2021-11-30 13:35 |  | 96d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 750 | 0 | 0 | 0 | 0 | 1.2.6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.6.2.1 | C |  | PSL | Pumps: Identify Upgrades, Replacements & Spares (Driller_PSL_Lead) |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2020-12-04 | 2021-03-25 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 9201 | 0 | [5 empty] | 9201 |  | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.6 | Water Handling Systems | 1.2.6 Water Handling Systems | 1.2.6.2 | Pumps | 1.2.6.2 Pumps | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 71d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.6.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.6.2.2 | C |  | PSL | Pumps: Procure Upgrades, Replacements & Spares (2020-21) (Driller_PSL_Lead) |  | 2.222% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2021-03-26 | 2021-03-29 |  |  |  |  | 40 | [11 empty] | 4600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4600 | 0% | 0 | 4799.9263 | 4799.9263 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 9201 | 0 | [5 empty] | 9201 |  | 4799.9263 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.6 | Water Handling Systems | 1.2.6 Water Handling Systems | 1.2.6.2 | Pumps | 1.2.6.2 Pumps | cell-link@smartsheet.com | 2021-11-30 13:35 |  | 143d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.6.2.2 | 4799.9263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.2.2 | 4799.9263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4799.9263 | 1.2.6.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4799.9263 | 1.2.6.2.2 | 4799.9263 | 18406.8582 | 4799.9263 | 4799.9263 | 4799.9263 | 4799.9263 | 4799.9263 | 4799.9263 | 4799.9263 | 4799.9263 | 4799.9263 | 4799.9263 | 4799.9263 | 4799.9263 | 18406.8582 | 18406.8582 | 18406.8582 | 18406.8582 | 18406.8582 | 18406.8582 | 18406.8582 | 18406.8582 | 18406.8582 | 18406.8582 | 18406.8582 | 18406.8582
| 1.2 | 1.2.6.2.2 | C |  | PSL | Pumps: Procure Upgrades, Replacements & Spares (2020-21) (Driller_PSL_Lead) |  | 1.111% | Labor Hours | TE |  |  | 115 | 77 | 0% | 2021-03-26 | 2021-03-29 |  |  |  |  | 20 | [11 empty] | 1540 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1540 | 0% | 0 | 1606.9319 | 1606.9319 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 9201 | 0 | [5 empty] | 9201 |  | 1606.9319 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.6 | Water Handling Systems | 1.2.6 Water Handling Systems | 1.2.6.2 | Pumps | 1.2.6.2 Pumps | cell-link@smartsheet.com | 2021-11-30 13:35 |  | 143d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.6.2.2 | 1606.9319 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.2.2 | 1606.9319 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1606.9319 | 1.2.6.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1606.9319 | 1.2.6.2.2 | 1606.9319 | 13606.9319 | 1606.9319 | 1606.9319 | 1606.9319 | 1606.9319 | 1606.9319 | 1606.9319 | 1606.9319 | 1606.9319 | 1606.9319 | 1606.9319 | 1606.9319 | 1606.9319 | 13606.9319 | 13606.9319 | 13606.9319 | 13606.9319 | 13606.9319 | 13606.9319 | 13606.9319 | 13606.9319 | 13606.9319 | 13606.9319 | 13606.9319 | 13606.9319
| 1.2 | 1.2.6.2.2 | C |  | PSL | Pumps: Procure Repair/Replacement Components (2020-21) |  |  | CapEx |  |  | HD |  | 1 | 0% | 2021-03-26 | 2021-03-29 |  |  |  |  | 2000 | [11 empty] | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 53% | 0 | 2000 | 2000 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 2000 | CapEx | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.6 | Water Handling Systems | 1.2.6 Water Handling Systems | 1.2.6.2 | Pumps | 1.2.6.2 Pumps | cell-link@smartsheet.com | 2021-11-30 13:35 |  | 144d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.6.2.2 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.2.2 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 1.2.6.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 1.2.6.2.2 | 2000 | 12000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000
| 1.2 | 1.2.6.2.2 | C |  | PSL | Pumps: Procure Replacement Charge and Transfer Pumps |  |  | CapEx |  |  | HD |  | 1 | 0% | 2021-03-26 | 2021-03-29 |  |  |  |  | 10000 | [11 empty] | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 53% | 0 | 10000 | 10000 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 10000 | CapEx | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.6 | Water Handling Systems | 1.2.6 Water Handling Systems | 1.2.6.2 | Pumps | 1.2.6.2 Pumps | cell-link@smartsheet.com | 2021-11-30 13:35 |  | 144d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.6.2.2 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.2.2 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 1.2.6.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 1.2.6.2.2 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000
| 1.2 | 1.2.6.2.3 | C |  | PSL | Pumps: Configure Pumps/Plumbing |  | 0.8889% | Labor Hours | EN |  |  |  | 115 | 0% | 2021-03-30 | 2021-08-02 |  |  |  |  | 16 | [11 empty] | 1840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1840 | 0% | 0 | 1919.9705 | 1919.9705 | [6 empty] | 20 | 20 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 2300 | 2300 | 0 | 0 | 0 | 0 | 4600 | 0% | 0 | 4903.1248 | 4903.1248 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | [9 empty] | 6823.0953 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.6 | Water Handling Systems | 1.2.6 Water Handling Systems | 1.2.6.2 | Pumps | 1.2.6.2 Pumps | cell-link@smartsheet.com | 2021-11-30 13:35 |  | 144d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.6.2.3 | 1919.9705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 2451.5624 | 2451.5624 | 0 | 0 | 0 | 0 | 1.2.6.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.2.3 | 1919.9705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1919.9705 | 1.2.6.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1919.9705 | 1.2.6.2.3 | 1919.9705 | 1919.9705 | 1919.9705 | 1919.9705 | 1919.9705 | 1919.9705 | 1919.9705 | 1919.9705 | 1919.9705 | 1919.9705 | 1919.9705 | 1919.9705 | 1919.9705 | 1919.9705 | 1919.9705 | 1919.9705 | 1919.9705 | 1919.9705 | 1919.9705 | 1919.9705 | 1919.9705 | 1919.9705 | 1919.9705 | 1919.9705 | 1919.9705 | 1919.9705
| 1.2 | 1.2.6.2.4 | C |  | PSL | Pumps: Charge pump soft-starter box rebuild (four units) |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2021-08-03 | 2021-11-30 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [5 empty] | 32 | 42 | 25 | 47 |  |  |  | 0 | 0 | 0 | 0 | 0 | 3680 | 4830 | 2875 | 5405 | 0 | 0 | 0 | 16790 | 0% | 0 | 17896.4054 | 17896.4054 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 9384 | [5 empty] | 9384 |  | 17896.4054 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.6 | Water Handling Systems | 1.2.6 Water Handling Systems | 1.2.6.2 | Pumps | 1.2.6.2 Pumps | cell-link@smartsheet.com | 2021-11-30 13:35 |  | 144d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.6.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.2.4 | 0 | 0 | 0 | 0 | 0 | 3922.4998 | 5148.281 | 3064.453 | 5761.1716 | 0 | 0 | 0 | 1.2.6.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.6.2.4 | C |  | PSL | Pumps: Charge pump soft-starter box rebuild (four units) |  |  | CapEx | EN |  |  |  | 1 | 0% | 2021-08-03 | 2021-11-30 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [6 empty] | 7200 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 7200 | 0 | 0 | 0 | 0 | 0 | 7200 | 53% | 0 | 7200 | 7200 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 7200 | CapEx | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.6 | Water Handling Systems | 1.2.6 Water Handling Systems | 1.2.6.2 | Pumps | 1.2.6.2 Pumps | cell-link@smartsheet.com | 2021-11-30 13:35 |  | 144d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.6.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 7200 | 0 | 0 | 0 | 0 | 0 | 1.2.6.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.6.2.5 | C |  | PSL | Pumps: Procure Repair/Replacement Components (2022-23) (Driller_PSL_Lead) |  | 0% | Labor Hours | EN |  |  |  | 115 | 0% | 2023-04-01 | 2023-08-03 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [6 empty] | 20 | 20 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 2300 | 2300 | 0 | 0 | 0 | 0 | 4600 | 0% | 0 | 4903.1248 | 4903.1248 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | [9 empty] | 4903.1248 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.6 | Water Handling Systems | 1.2.6 Water Handling Systems | 1.2.6.2 | Pumps | 1.2.6.2 Pumps | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 144d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.6.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 2451.5624 | 2451.5624 | 0 | 0 | 0 | 0 | 1.2.6.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.6.2.5 | C |  | PSL | Pumps: Procure Repair/Replacement Components (2022-23) |  |  | CapEx |  |  | HD | 1 | 1 | 0% | 2023-04-01 | 2023-08-03 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [7 empty] | 6250 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6250 | 0 | 0 | 0 | 0 | 6250 | 53% | 0 | 6250 | 6250 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 30481 | [5 empty] | 30481 |  | 6250 | CapEx | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.6 | Water Handling Systems | 1.2.6 Water Handling Systems | 1.2.6.2 | Pumps | 1.2.6.2 Pumps | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 144d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.6.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6250 | 0 | 0 | 0 | 0 | 1.2.6.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.6.3.1 | C |  | PSL | Filtration: Define Requirements/Research Methodologies (PSL_Engineer) |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2020-11-01 | 2020-12-31 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 9201 | 0 | [5 empty] | 9201 |  | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.6 | Water Handling Systems | 1.2.6 Water Handling Systems | 1.2.6.3 | Filtration and Degassing | 1.2.6.3 Filtration and Degassing | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 96d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.6.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.6.3.2 | C |  | PSL | Filtration: Confirm w/ASC & NSF - Disposal of Condensate (14,000 gals) (PSL_Engineer) |  | 0.6667% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2021-01-01 | 2021-03-25 | [5 empty] | 6 |  | 6 | [8 empty] | 0 | 690 | 0 | 690 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1380 | 0% | 0 | 1439.9779 | 1439.9779 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 2760 | 0 | [5 empty] | 2760 |  | 1439.9779 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.6 | Water Handling Systems | 1.2.6 Water Handling Systems | 1.2.6.3 | Filtration and Degassing | 1.2.6.3 Filtration and Degassing | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 72d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.6.3.2 | 0 | 719.989 | 0 | 719.989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.3.2 | 0 | 719.989 | 0 | 719.989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1439.9779 | 1.2.6.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1439.9779 | 1.2.6.3.2 | 1439.9779 | 1439.9779 | 0 | 719.989 | 719.989 | 1439.9779 | 1439.9779 | 1439.9779 | 1439.9779 | 1439.9779 | 1439.9779 | 1439.9779 | 1439.9779 | 1439.9779 | 0 | 719.989 | 719.989 | 1439.9779 | 1439.9779 | 1439.9779 | 1439.9779 | 1439.9779 | 1439.9779 | 1439.9779 | 1439.9779 | 1439.9779
| 1.2 | 1.2.6.3.3 | C |  | PSL | Filtration: Develop Drilling Algorithms (PSL_Engineer) |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2021-01-01 | 2021-04-15 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 18400 | 0 | [5 empty] | 18400 |  | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.6 | Water Handling Systems | 1.2.6 Water Handling Systems | 1.2.6.3 | Filtration and Degassing | 1.2.6.3 Filtration and Degassing | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 72d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.6.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.6.3.4 | C |  | PSL | FIltration: Review & Identify Filtration Sub-System Upgrades (PSL_Engineer) |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2021-04-16 | 2021-07-29 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 9200 | 0 | [5 empty] | 9200 |  | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.6 | Water Handling Systems | 1.2.6 Water Handling Systems | 1.2.6.3 | Filtration and Degassing | 1.2.6.3 Filtration and Degassing | cell-link@smartsheet.com | 2021-11-30 13:35 |  | 72d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.6.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.6.3.5 | C |  | PSL | Filtration: Procure Upgrade/Replacement Components (Driller_PSL_Lead) |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2021-07-30 | 2021-10-21 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 4256 | 5043 | [5 empty] | 9299 |  | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.6 | Water Handling Systems | 1.2.6 Water Handling Systems | 1.2.6.3 | Filtration and Degassing | 1.2.6.3 Filtration and Degassing | cell-link@smartsheet.com | 2021-11-30 13:35 |  | 72d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.6.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.6.3.5 | C |  | PSL | Filtration: Procure Upgrade-Replacement Components |  |  | CapEx |  |  | EE | 1 | 1 | 0% | 2021-07-30 | 2021-10-21 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 23132 | 26868 | [5 empty] | 50000 |  | 0 | CapEx | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.6 | Water Handling Systems | 1.2.6 Water Handling Systems | 1.2.6.3 | Filtration and Degassing | 1.2.6.3 Filtration and Degassing | cell-link@smartsheet.com | 2021-11-30 13:35 |  | 72d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.6.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.6.3.6 | C |  | PSL | Filtration: Build & Test Filtration System |  | 1.333% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2021-10-22 | 2021-11-22 |  | TRUE |  |  | 12 | 12 | [10 empty] | 1380 | 1380 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2760 | 0% | 0 | 2879.9558 | 2879.9558 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 18768 | [5 empty] | 18768 |  | 2879.9558 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.6 | Water Handling Systems | 1.2.6 Water Handling Systems | 1.2.6.3 | Filtration and Degassing | 1.2.6.3 Filtration and Degassing | cell-link@smartsheet.com | 2021-11-30 13:35 |  | 72d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.6.3.6 | 1439.9779 | 1439.9779 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.3.6 | 1439.9779 | 1439.9779 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2879.9558 | 1.2.6.3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2879.9558 | 1.2.6.3.6 | 2879.9558 | 4791.5787 | 1439.9779 | 2879.9558 | 2879.9558 | 2879.9558 | 2879.9558 | 2879.9558 | 2879.9558 | 2879.9558 | 2879.9558 | 2879.9558 | 2879.9558 | 2879.9558 | 2395.7893 | 4791.5787 | 4791.5787 | 4791.5787 | 4791.5787 | 4791.5787 | 4791.5787 | 4791.5787 | 4791.5787 | 4791.5787 | 4791.5787 | 4791.5787
| 1.2 | 1.2.6.3.6 | C |  | PSL | Filtration: Build & Test Filtration System |  | 0.8889% | Labor Hours | TE |  |  | 115 | 77 | 0% | 2021-10-22 | 2021-11-22 |  | TRUE |  |  | 8 | 8 | [10 empty] | 616 | 616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1232 | 0% | 0 | 1285.5455 | 1285.5455 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 18768 | [5 empty] | 18768 |  | 1285.5455 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.6 | Water Handling Systems | 1.2.6 Water Handling Systems | 1.2.6.3 | Filtration and Degassing | 1.2.6.3 Filtration and Degassing | cell-link@smartsheet.com | 2021-11-30 13:35 |  | 72d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.6.3.6 | 642.7727 | 642.7727 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.3.6 | 642.7727 | 642.7727 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1285.5455 | 1.2.6.3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1285.5455 | 1.2.6.3.6 | 1285.5455 | 1911.6228 | 642.7727 | 1285.5455 | 1285.5455 | 1285.5455 | 1285.5455 | 1285.5455 | 1285.5455 | 1285.5455 | 1285.5455 | 1285.5455 | 1285.5455 | 1285.5455 | 955.8114 | 1911.6228 | 1911.6228 | 1911.6228 | 1911.6228 | 1911.6228 | 1911.6228 | 1911.6228 | 1911.6228 | 1911.6228 | 1911.6228 | 1911.6228
| 1.2 | 1.2.6.3.6 | C |  | PSL | Filtration: Build & Test Filtration System |  | 2.222% | Labor Hours | UG |  |  | 115 | 15 | 0% | 2021-10-22 | 2021-11-22 |  | TRUE |  |  | 20 | 20 | [10 empty] | 300 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600 | 0% | 0 | 626.0774 | 626.0774 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 18768 | [5 empty] | 18768 |  | 626.0774 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.6 | Water Handling Systems | 1.2.6 Water Handling Systems | 1.2.6.3 | Filtration and Degassing | 1.2.6.3 Filtration and Degassing | cell-link@smartsheet.com | 2021-11-30 13:35 |  | 72d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.6.3.6 | 313.0387 | 313.0387 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.3.6 | 313.0387 | 313.0387 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 626.0774 | 1.2.6.3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 626.0774 | 1.2.6.3.6 | 626.0774 | 626.0774 | 313.0387 | 626.0774 | 626.0774 | 626.0774 | 626.0774 | 626.0774 | 626.0774 | 626.0774 | 626.0774 | 626.0774 | 626.0774 | 626.0774 | 313.0387 | 626.0774 | 626.0774 | 626.0774 | 626.0774 | 626.0774 | 626.0774 | 626.0774 | 626.0774 | 626.0774 | 626.0774 | 626.0774
| 1.2 | 1.2.6.3.7 | C |  | PSL | Filtration: Design Condensate Collection, Treatment, and Disposal System |  | 0.4444% | Labor Hours | EN |  |  |  | 115 | 0% | 2021-11-23 | 2022-10-17 |  |  |  |  | 4 | 4 | [10 empty] | 460 | 460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 920 | 0% | 0 | 959.9853 | 959.9853 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | [9 empty] | 959.9853 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.6 | Water Handling Systems | 1.2.6 Water Handling Systems | 1.2.6.3 | Filtration and Degassing | 1.2.6.3 Filtration and Degassing | cell-link@smartsheet.com | 2021-11-30 13:35 |  | 72d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.6.3.7 | 479.9926 | 479.9926 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.3.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.3.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.3.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.3.7 | 479.9926 | 479.9926 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 959.9853 | 1.2.6.3.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.3.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 959.9853 | 1.2.6.3.7 | 959.9853 | 1899.1013 | 479.9926 | 959.9853 | 959.9853 | 959.9853 | 959.9853 | 959.9853 | 959.9853 | 959.9853 | 959.9853 | 959.9853 | 959.9853 | 959.9853 | 949.5506 | 1899.1013 | 1899.1013 | 1899.1013 | 1899.1013 | 1899.1013 | 1899.1013 | 1899.1013 | 1899.1013 | 1899.1013 | 1899.1013 | 1899.1013
| 1.2 | 1.2.6.3.7 | C |  | PSL | Filtration: Design Condensate Collection, Treatment, and Disposal System |  | 3.333% | Labor Hours | UG |  |  |  | 15 | 0% | 2021-11-23 | 2022-10-17 |  |  |  |  | 30 | 30 | [10 empty] | 450 | 450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 900 | 0% | 0 | 939.116 | 939.116 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | [9 empty] | 939.116 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.6 | Water Handling Systems | 1.2.6 Water Handling Systems | 1.2.6.3 | Filtration and Degassing | 1.2.6.3 Filtration and Degassing | cell-link@smartsheet.com | 2021-11-30 13:35 |  | 72d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.6.3.7 | 469.558 | 469.558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.3.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.3.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.3.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.3.7 | 469.558 | 469.558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.116 | 1.2.6.3.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.3.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.116 | 1.2.6.3.7 | 939.116 | 939.116 | 469.558 | 939.116 | 939.116 | 939.116 | 939.116 | 939.116 | 939.116 | 939.116 | 939.116 | 939.116 | 939.116 | 939.116 | 469.558 | 939.116 | 939.116 | 939.116 | 939.116 | 939.116 | 939.116 | 939.116 | 939.116 | 939.116 | 939.116 | 939.116
| 1.2 | 1.2.6.3.8 | C |  | PSL | Filtration: Procure Condensate System Components |  | 0.8889% | Labor Hours | UG |  |  |  | 15 | 0% | 2022-10-18 | 2022-11-17 | [8 empty] | 8 | 8 | [6 empty] | 0 | 0 | 0 | 0 | 120 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 240 | 0% | 0 | 250.4309 | 250.4309 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | [9 empty] | 250.4309 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.6 | Water Handling Systems | 1.2.6 Water Handling Systems | 1.2.6.3 | Filtration and Degassing | 1.2.6.3 Filtration and Degassing | cell-link@smartsheet.com | 2021-11-30 13:35 |  | 72d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.6.3.8 | 0 | 0 | 0 | 0 | 125.2155 | 125.2155 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.3.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.3.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.3.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.3.8 | 0 | 0 | 0 | 0 | 125.2155 | 125.2155 | 0 | 0 | 0 | 0 | 0 | 0 | 250.4309 | 1.2.6.3.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.3.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250.4309 | 1.2.6.3.8 | 250.4309 | 15750.8251 | 0 | 0 | 0 | 0 | 125.2155 | 250.4309 | 250.4309 | 250.4309 | 250.4309 | 250.4309 | 250.4309 | 250.4309 | 0 | 0 | 0 | 0 | 125.2155 | 1450.4125 | 15750.8251 | 15750.8251 | 15750.8251 | 15750.8251 | 15750.8251 | 15750.8251
| 1.2 | 1.2.6.3.8 | C |  | PSL | Filtration: Procure Condensate Disposal System Components |  | 1.111% | Labor Hours | EN |  |  |  | 115 | 0% | 2022-10-18 | 2022-11-17 | [9 empty] | 10 | 10 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 1150 | 1150 | 0 | 0 | 0 | 0 | 0 | 2300 | 0% | 0 | 2399.9632 | 2399.9632 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | [9 empty] | 2399.9632 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.6 | Water Handling Systems | 1.2.6 Water Handling Systems | 1.2.6.3 | Filtration and Degassing | 1.2.6.3 Filtration and Degassing | cell-link@smartsheet.com | 2021-11-30 13:35 |  | 72d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.6.3.8 | 0 | 0 | 0 | 0 | 0 | 1199.9816 | 1199.9816 | 0 | 0 | 0 | 0 | 0 | 1.2.6.3.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.3.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.3.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.3.8 | 0 | 0 | 0 | 0 | 0 | 1199.9816 | 1199.9816 | 0 | 0 | 0 | 0 | 0 | 2399.9632 | 1.2.6.3.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.3.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2399.9632 | 1.2.6.3.8 | 2399.9632 | 15500.3941 | 0 | 0 | 0 | 0 | 0 | 1199.9816 | 2399.9632 | 2399.9632 | 2399.9632 | 2399.9632 | 2399.9632 | 2399.9632 | 0 | 0 | 0 | 0 | 0 | 1199.9816 | 15500.3941 | 15500.3941 | 15500.3941 | 15500.3941 | 15500.3941 | 15500.3941
| 1.2 | 1.2.6.3.8 | C |  | PSL | Filtration: Procure Condensate Disposal System Components |  | 0.8889% | Labor Hours | UG |  |  |  | 15 | 0% | 2022-10-18 | 2022-11-17 | [10 empty] | 16 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 240 | 0 | 0 | 0 | 0 | 0 | 240 | 0% | 0 | 250.4309 | 250.4309 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | [9 empty] | 250.4309 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.6 | Water Handling Systems | 1.2.6 Water Handling Systems | 1.2.6.3 | Filtration and Degassing | 1.2.6.3 Filtration and Degassing | cell-link@smartsheet.com | 2021-11-30 13:35 |  | 72d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.6.3.8 | 0 | 0 | 0 | 0 | 0 | 0 | 250.4309 | 0 | 0 | 0 | 0 | 0 | 1.2.6.3.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.3.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.3.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.3.8 | 0 | 0 | 0 | 0 | 0 | 0 | 250.4309 | 0 | 0 | 0 | 0 | 0 | 250.4309 | 1.2.6.3.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.3.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250.4309 | 1.2.6.3.8 | 250.4309 | 13100.4309 | 0 | 0 | 0 | 0 | 0 | 0 | 250.4309 | 250.4309 | 250.4309 | 250.4309 | 250.4309 | 250.4309 | 0 | 0 | 0 | 0 | 0 | 0 | 13100.4309 | 13100.4309 | 13100.4309 | 13100.4309 | 13100.4309 | 13100.4309
| 1.2 | 1.2.6.3.8 | C |  | PSL | Filtration: Procure Condensate Disposal System Components |  |  | CapEx |  |  |  |  | 1 | 0% | 2022-10-18 | 2022-11-17 | [10 empty] | 12850 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 12850 | 0 | 0 | 0 | 0 | 0 | 12850 | 53% | 0 | 12850 | 12850 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 12850 | CapEx | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.6 | Water Handling Systems | 1.2.6 Water Handling Systems | 1.2.6.3 | Filtration and Degassing | 1.2.6.3 Filtration and Degassing | cell-link@smartsheet.com | 2021-11-30 13:35 |  | 72d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.6.3.8 | 0 | 0 | 0 | 0 | 0 | 0 | 12850 | 0 | 0 | 0 | 0 | 0 | 1.2.6.3.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.3.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.3.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.3.8 | 0 | 0 | 0 | 0 | 0 | 0 | 12850 | 0 | 0 | 0 | 0 | 0 | 12850 | 1.2.6.3.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.3.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12850 | 1.2.6.3.8 | 12850 | 12850 | 0 | 0 | 0 | 0 | 0 | 0 | 12850 | 12850 | 12850 | 12850 | 12850 | 12850 | 0 | 0 | 0 | 0 | 0 | 0 | 12850 | 12850 | 12850 | 12850 | 12850 | 12850
| 1.2 | 1.2.6.4.2 | C |  | PSL | Interconnect: Identify/Spec Replacements & Spare Heated Hose 2020-2021 (PSL_Engineer) |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2021-03-03 | 2023-05-25 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 9384 | [5 empty] | 9384 |  | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.6 | Water Handling Systems | 1.2.6 Water Handling Systems | 1.2.6.4 | Interconnects - External | 1.2.6.4 Interconnects - External | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 47d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.6.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.4.2 | 0 | 4799.9263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2399.9632 | 4799.9263 | 4799.9263 | 4799.9263 | 4799.9263 | 4799.9263 | 4799.9263 | 4799.9263
| 1.2 | 1.2.6.4.2 | C |  | PSL | Interconnect: Identify/Spec Replacements 2022-2023 (PSL_Engineer) |  | 2.222% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2021-03-03 | 2023-05-25 | [8 empty] | 20 | 20 | [6 empty] | 0 | 0 | 0 | 0 | 2300 | 2300 | 0 | 0 | 0 | 0 | 0 | 0 | 4600 | 0% | 0 | 4799.9263 | 4799.9263 | [6 empty] | 30 | 25 |  | 25 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 3450 | 2875 | 0 | 2875 | 0 | 0 | 9200 | 0% | 0 | 9806.2495 | 9806.2495 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 9384 | [5 empty] | 9384 |  | 14606.1759 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.6 | Water Handling Systems | 1.2.6 Water Handling Systems | 1.2.6.4 | Interconnects - External | 1.2.6.4 Interconnects - External | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 47d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.6.4.2 | 0 | 0 | 0 | 0 | 2399.9632 | 2399.9632 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 3677.3436 | 3064.453 | 0 | 3064.453 | 0 | 0 | 1.2.6.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.4.2 | 0 | 0 | 0 | 0 | 2399.9632 | 2399.9632 | 0 | 0 | 0 | 0 | 0 | 0 | 4799.9263 | 1.2.6.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4799.9263 | 1.2.6.4.2 | 4799.9263 | 4799.9263 | 0 | 0 | 0 | 0 | 2399.9632 | 4799.9263 | 4799.9263 | 4799.9263 | 4799.9263 | 4799.9263 | 4799.9263 | 4799.9263 | 0 | 0 | 0 | 0 | 2399.9632 | 4799.9263 | 4799.9263 | 4799.9263 | 4799.9263 | 4799.9263 | 4799.9263 | 4799.9263
| 1.2 | 1.2.6.4.3 | C |  | PSL | Interconnect: Procure Replacements/Spares (PSL_Engineer) |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2021-11-05 | 2023-03-09 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [8 empty] | 20 | 20 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2300 | 2300 | 0 | 0 | 4600 | 0% | 0 | 4903.1248 | 4903.1248 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 9384 | [5 empty] | 9384 |  | 4903.1248 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.6 | Water Handling Systems | 1.2.6 Water Handling Systems | 1.2.6.4 | Interconnects - External | 1.2.6.4 Interconnects - External | cell-link@smartsheet.com | 2021-11-30 20:56 |  | 143d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.6.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2451.5624 | 2451.5624 | 0 | 0 | 1.2.6.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.4.3 | 0 | 9799.9263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2399.9632 | 9799.9263 | 9799.9263 | 9799.9263 | 9799.9263 | 9799.9263
| 1.2 | 1.2.6.4.3 | C |  | PSL | Interconnect: Procure Replacements/Spares PSL_Drill_Manager) |  | 2.222% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2021-11-05 | 2023-03-09 | [10 empty] | 20 | 20 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 2300 | 2300 | 0 | 0 | 0 | 0 | 4600 | 0% | 0 | 4799.9263 | 4799.9263 | [8 empty] | 10 | 10 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1150 | 1150 | 0 | 0 | 2300 | 0% | 0 | 2451.5624 | 2451.5624 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 9384 | [5 empty] | 9384 |  | 7251.4887 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.6 | Water Handling Systems | 1.2.6 Water Handling Systems | 1.2.6.4 | Interconnects - External | 1.2.6.4 Interconnects - External | cell-link@smartsheet.com | 2021-11-30 20:56 |  | 143d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.6.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 2399.9632 | 2399.9632 | 0 | 0 | 0 | 0 | 1.2.6.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1225.7812 | 1225.7812 | 0 | 0 | 1.2.6.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 2399.9632 | 2399.9632 | 0 | 0 | 0 | 0 | 4799.9263 | 1.2.6.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4799.9263 | 1.2.6.4.3 | 4799.9263 | 9799.9263 | 0 | 0 | 0 | 0 | 0 | 0 | 2399.9632 | 4799.9263 | 4799.9263 | 4799.9263 | 4799.9263 | 4799.9263 | 0 | 0 | 0 | 0 | 0 | 0 | 2399.9632 | 9799.9263 | 9799.9263 | 9799.9263 | 9799.9263 | 9799.9263
| 1.2 | 1.2.6.4.3 | C |  | PSL | Interconnect: Procure Replacements and Spares/Heated |  |  | CapEx |  |  | EE | 1 | 1 | 0% | 2021-11-05 | 2023-03-09 | [11 empty] | 5000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 5000 | 53% | 0 | 5000 | 5000 | [7 empty] | 5000 | 5000 | 5000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 5000 | 5000 | 0 | 0 | 15000 | 53% | 0 | 15000 | 15000 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 50000 | [5 empty] | 50000 |  | 20000 | CapEx | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.6 | Water Handling Systems | 1.2.6 Water Handling Systems | 1.2.6.4 | Interconnects - External | 1.2.6.4 Interconnects - External | cell-link@smartsheet.com | 2021-11-30 20:56 |  | 143d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.6.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 1.2.6.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 5000 | 5000 | 0 | 0 | 1.2.6.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 5000 | 1.2.6.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 1.2.6.4.3 | 5000 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 5000 | 5000 | 5000 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 5000 | 5000 | 5000 | 5000
| 1.2 | 1.2.6.4.4 | C |  | PSL | Interconnect: Procure Remaining Materials & Fabricate Heated Hose |  | 4.444% | Labor Hours | EN |  |  |  | 115 | 0% | 2021-03-10 | 2021-06-15 | [11 empty] | 20 | 20 | 40 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2300 | 2300 | 4600 | 0 | 0 | 9200 | 0% | 0 | 9599.8527 | 9599.8527 | [6 empty] | 10 | 10 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1150 | 1150 | 0 | 0 | 0 | 0 | 2300 | 0% | 0 | 2451.5624 | 2451.5624 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | [9 empty] | 12051.4151 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.6 | Water Handling Systems | 1.2.6 Water Handling Systems | 1.2.6.4 | Interconnects - External | 1.2.6.4 Interconnects - External | cell-link@smartsheet.com | 2021-11-30 20:56 |  | 143d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.6.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2399.9632 | 2399.9632 | 4799.9263 | 0 | 0 | 1.2.6.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 1225.7812 | 1225.7812 | 0 | 0 | 0 | 0 | 1.2.6.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2399.9632 | 2399.9632 | 4799.9263 | 0 | 0 | 9599.8527 | 1.2.6.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9599.8527 | 1.2.6.4.4 | 9599.8527 | 14599.8527 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2399.9632 | 4799.9263 | 9599.8527 | 9599.8527 | 9599.8527 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2399.9632 | 9799.9263 | 14599.8527 | 14599.8527 | 14599.8527
| 1.2 | 1.2.6.4.4 | C |  | PSL | Interconnect: Procure Remaining Materials & Fabricate Heated Hose |  |  | CapEx | EN |  |  |  | 1 | 0% | 2021-03-10 | 2021-06-15 | [12 empty] | 5000 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 5000 | 53% | 0 | 5000 | 5000 | [6 empty] | 650 | 650 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 650 | 650 | 0 | 0 | 0 | 0 | 1300 | 53% | 0 | 1300 | 1300 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 6300 | CapEx | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.6 | Water Handling Systems | 1.2.6 Water Handling Systems | 1.2.6.4 | Interconnects - External | 1.2.6.4 Interconnects - External | cell-link@smartsheet.com | 2021-11-30 20:56 |  | 143d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.6.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 1.2.6.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 650 | 650 | 0 | 0 | 0 | 0 | 1.2.6.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 5000 | 1.2.6.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 1.2.6.4.4 | 5000 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 5000 | 5000 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 5000 | 5000 | 5000
| 1.2 | 1.2.6.4.5 | C |  | PSL | Interconnect: Procure Parts & Assemble Hose End Ball Valves |  | 0% | Labor Hours | EN |  | EE |  | 115 | 0% | 2023-04-14 | 2023-05-25 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [7 empty] | 8 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 920 | 0 | 0 | 0 | 0 | 920 | 0% | 0 | 980.625 | 980.625 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | [9 empty] | 980.625 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.6 | Water Handling Systems | 1.2.6 Water Handling Systems | 1.2.6.4 | Interconnects - External | 1.2.6.4 Interconnects - External | cell-link@smartsheet.com | 2021-11-30 20:56 |  | 143d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.6.4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 980.625 | 0 | 0 | 0 | 0 | 1.2.6.4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.6.4.5 | C |  | PSL | Interconnect: Procure Parts & Assemble Hose End Ball Valves |  |  | CapEx |  |  | EE |  | 1 | 0% | 2023-04-14 | 2023-05-25 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 0 | CapEx | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.6 | Water Handling Systems | 1.2.6 Water Handling Systems | 1.2.6.4 | Interconnects - External | 1.2.6.4 Interconnects - External | cell-link@smartsheet.com | 2021-11-30 20:56 |  | 143d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.6.4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.6.4.6 | C |  | PSL | Interconnect: Finalize Design Gen Water Loop |  | 0% | Labor Hours | EN |  |  |  | 115 | 0% | 2022-07-08 | 2022-08-18 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [6 empty] | 8 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 920 | 0 | 0 | 0 | 0 | 0 | 920 | 0% | 0 | 980.625 | 980.625 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | [9 empty] | 980.625 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.6 | Water Handling Systems | 1.2.6 Water Handling Systems | 1.2.6.4 | Interconnects - External | 1.2.6.4 Interconnects - External | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 143d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.6.4.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.4.6 | 0 | 0 | 0 | 0 | 0 | 0 | 980.625 | 0 | 0 | 0 | 0 | 0 | 1.2.6.4.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.4.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.4.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.4.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.4.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.4.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.6.4.7 | C |  | PSL | Interconnect: Procure Gen Water Loop Materials & Assemble |  | 0% | Labor Hours | EN |  | EE |  | 115 | 0% | 2022-08-19 | 2022-10-03 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [7 empty] | 8 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 920 | 0 | 0 | 0 | 0 | 920 | 0% | 0 | 980.625 | 980.625 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | [9 empty] | 980.625 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.6 | Water Handling Systems | 1.2.6 Water Handling Systems | 1.2.6.4 | Interconnects - External | 1.2.6.4 Interconnects - External | cell-link@smartsheet.com | 2021-11-30 20:56 |  | 143d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.6.4.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.4.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 980.625 | 0 | 0 | 0 | 0 | 1.2.6.4.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.4.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.4.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.4.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.4.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.4.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.6.4.7 | C |  | PSL | Interconnect: Procure Gen Water Loop Materials & Assemble |  |  | CapEx |  |  | EE |  | 1 | 0% | 2022-08-19 | 2022-10-03 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [7 empty] | 3500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3500 | 0 | 0 | 0 | 0 | 3500 | 53% | 0 | 3500 | 3500 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 3500 | CapEx | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.6 | Water Handling Systems | 1.2.6 Water Handling Systems | 1.2.6.4 | Interconnects - External | 1.2.6.4 Interconnects - External | cell-link@smartsheet.com | 2021-11-30 20:56 |  | 143d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.6.4.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.4.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3500 | 0 | 0 | 0 | 0 | 1.2.6.4.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.4.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.4.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.4.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.4.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.4.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.6.4.8 | C |  | PSL | Interconnect: Procure Camp and Surface Hose Insulation |  | 0.2222% | Labor Hours | EN |  | EE |  | 115 | 0% | 2022-07-02 | 2022-08-18 | [13 empty] | 4 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 460 | 0 | 0 | 460 | 0% | 0 | 479.9926 | 479.9926 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | [9 empty] | 479.9926 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.6 | Water Handling Systems | 1.2.6 Water Handling Systems | 1.2.6.4 | Interconnects - External | 1.2.6.4 Interconnects - External | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 143d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.6.4.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 479.9926 | 0 | 0 | 1.2.6.4.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.4.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.4.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.4.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 479.9926 | 0 | 0 | 479.9926 | 1.2.6.4.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.4.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 479.9926 | 1.2.6.4.8 | 479.9926 | 1479.9926 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 479.9926 | 479.9926 | 479.9926 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1479.9926 | 1479.9926 | 1479.9926
| 1.2 | 1.2.6.4.8 | C |  | PSL | Interconnect: Procure Camp and Surface Hose Insulation |  |  | CapEx |  |  | EE |  | 1 | 0% | 2022-07-02 | 2022-08-18 | [13 empty] | 1000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 1000 | 53% | 0 | 1000 | 1000 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 1000 | CapEx | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.6 | Water Handling Systems | 1.2.6 Water Handling Systems | 1.2.6.4 | Interconnects - External | 1.2.6.4 Interconnects - External | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 143d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.6.4.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 1.2.6.4.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.4.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.4.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.4.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 1000 | 1.2.6.4.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.4.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 1.2.6.4.8 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 1000 | 1000
| 1.2 | 1.2.6.5.1 | C |  | PSL | MDS: Evaluate Water Hoses (1-1/2", 3/4", and 1/2" Hose) |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2021-01-01 | 2023-04-14 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 9200 | 0 | [5 empty] | 9200 |  | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.6 | Water Handling Systems | 1.2.6 Water Handling Systems | 1.2.6.5 | MDS Internal Hoses | 1.2.6.5 MDS Internal Hoses | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 48d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.6.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.6.5.2 | C |  | PSL | MDS: Evaluate Fuel Hoses (Driller_PSL_Lead) |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2021-01-01 | 2023-04-14 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 9200 | 0 | [5 empty] | 9200 |  | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.6 | Water Handling Systems | 1.2.6 Water Handling Systems | 1.2.6.5 | MDS Internal Hoses | 1.2.6.5 MDS Internal Hoses | cell-link@smartsheet.com | 2021-11-30 20:59 |  | 48d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.6.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.6.5.2 | C |  | PSL | MDS: Evaluate Fuel Hoses (PSL_Engineer) |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2021-01-01 | 2023-04-14 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 9200 | 0 | [5 empty] | 9200 |  | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.6 | Water Handling Systems | 1.2.6 Water Handling Systems | 1.2.6.5 | MDS Internal Hoses | 1.2.6.5 MDS Internal Hoses | cell-link@smartsheet.com | 2021-11-30 20:59 |  | 48d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.6.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.6.5.3 | C |  | PSL | MDS: Procure Replacements Internal Hoses and Spares (PSL_Engineer) |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2021-01-01 | 2023-05-05 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 9200 | 0 | [5 empty] | 9200 |  | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.6 | Water Handling Systems | 1.2.6 Water Handling Systems | 1.2.6.5 | MDS Internal Hoses | 1.2.6.5 MDS Internal Hoses | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 72d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.6.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.5.3 | 0 | 5179.9742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5179.9742 | 5179.9742 | 5179.9742 | 5179.9742
| 1.2 | 1.2.6.5.3 | C |  | PSL | MDS: Procure Replacements Internal Hoses and Spares (Driller_PSL_Lead) |  | 0.7778% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2021-01-01 | 2023-05-05 | [12 empty] | 14 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1610 | 0 | 0 | 0 | 1610 | 0% | 0 | 1679.9742 | 1679.9742 | [6 empty] | 14 | 14 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1610 | 1610 | 0 | 0 | 0 | 0 | 3220 | 0% | 0 | 3432.1873 | 3432.1873 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 9200 | 0 | [5 empty] | 9200 |  | 5112.1616 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.6 | Water Handling Systems | 1.2.6 Water Handling Systems | 1.2.6.5 | MDS Internal Hoses | 1.2.6.5 MDS Internal Hoses | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 72d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.6.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1679.9742 | 0 | 0 | 0 | 1.2.6.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 1716.0937 | 1716.0937 | 0 | 0 | 0 | 0 | 1.2.6.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1679.9742 | 0 | 0 | 0 | 1679.9742 | 1.2.6.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1679.9742 | 1.2.6.5.3 | 1679.9742 | 5179.9742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1679.9742 | 1679.9742 | 1679.9742 | 1679.9742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5179.9742 | 5179.9742 | 5179.9742 | 5179.9742
| 1.2 | 1.2.6.5.3 | C |  | PSL | MDS: Procure Replacements Internal Hoses and Spares |  |  | CapEx |  |  | EE | 1 | 1 | 0% | 2021-01-01 | 2023-05-05 | [12 empty] | 3500 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3500 | 0 | 0 | 0 | 3500 | 53% | 0 | 3500 | 3500 | [7 empty] | 7500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | 0 | 0 | 0 | 0 | 7500 | 53% | 0 | 7500 | 7500 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 54228 | 0 | [5 empty] | 54228 |  | 11000 | CapEx | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.6 | Water Handling Systems | 1.2.6 Water Handling Systems | 1.2.6.5 | MDS Internal Hoses | 1.2.6.5 MDS Internal Hoses | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 72d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.6.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3500 | 0 | 0 | 0 | 1.2.6.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | 0 | 0 | 0 | 0 | 1.2.6.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3500 | 0 | 0 | 0 | 3500 | 1.2.6.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3500 | 1.2.6.5.3 | 3500 | 3500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3500 | 3500 | 3500 | 3500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3500 | 3500 | 3500 | 3500
| 1.2 | 1.2.6.6.1 | C |  | PSL | ARA Drill: Identify Upgrade & Replacement Parts |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2021-02-03 | 2023-04-06 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 9384 | [5 empty] | 9384 |  | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.6 | Water Handling Systems | 1.2.6 Water Handling Systems | 1.2.6.6 | ARA Hot Water Drill Subsystem | 1.2.6.6 ARA Hot Water Drill Subsystem | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 83d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.6.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.6.1 | 0 | 3759.9853 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3759.9853 | 3759.9853 | 3759.9853 | 3759.9853
| 1.2 | 1.2.6.6.1 | C |  | PSL | ARA Drill: Identify and Procure Rodwell level and temp sensors |  | 0.4444% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2021-02-03 | 2023-04-06 | [12 empty] | 8 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 920 | 0 | 0 | 0 | 920 | 0% | 0 | 959.9853 | 959.9853 | [6 empty] | 8 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 920 | 0 | 0 | 0 | 0 | 0 | 920 | 0% | 0 | 980.625 | 980.625 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 9384 | [5 empty] | 9384 |  | 1940.6102 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.6 | Water Handling Systems | 1.2.6 Water Handling Systems | 1.2.6.6 | ARA Hot Water Drill Subsystem | 1.2.6.6 ARA Hot Water Drill Subsystem | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 83d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.6.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 959.9853 | 0 | 0 | 0 | 1.2.6.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 980.625 | 0 | 0 | 0 | 0 | 0 | 1.2.6.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 959.9853 | 0 | 0 | 0 | 959.9853 | 1.2.6.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 959.9853 | 1.2.6.6.1 | 959.9853 | 3759.9853 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 959.9853 | 959.9853 | 959.9853 | 959.9853 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3759.9853 | 3759.9853 | 3759.9853 | 3759.9853
| 1.2 | 1.2.6.6.1 | C |  | PSL | ARA Drill: Identify and Procure Rodwell level and temp sensors |  |  | CapEx | EN |  |  | 115 | 1 | 0% | 2021-02-03 | 2023-04-06 | [12 empty] | 2800 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2800 | 0 | 0 | 0 | 2800 | 53% | 0 | 2800 | 2800 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 9384 | [5 empty] | 9384 |  | 2800 | CapEx | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.6 | Water Handling Systems | 1.2.6 Water Handling Systems | 1.2.6.6 | ARA Hot Water Drill Subsystem | 1.2.6.6 ARA Hot Water Drill Subsystem | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 83d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.6.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2800 | 0 | 0 | 0 | 1.2.6.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2800 | 0 | 0 | 0 | 2800 | 1.2.6.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2800 | 1.2.6.6.1 | 2800 | 2800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2800 | 2800 | 2800 | 2800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2800 | 2800 | 2800 | 2800
| 1.2 | 1.2.6.6.2 | C |  | PSL | ARA Drill: Procure Upgrade, Integration, & Replacement Parts |  | 3.333% | Labor Hours | EN |  |  | 81 | 115 | 0% | 2021-03-31 | 2023-10-31 | [6 empty] | 30 | 30 | [8 empty] | 0 | 0 | 3450 | 3450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6900 | 0% | 0 | 7199.8895 | 7199.8895 | [8 empty] | 20 | 20 | 20 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2300 | 2300 | 2300 | 0 | 6900 | 0% | 0 | 7354.6871 | 7354.6871 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 6610 | [5 empty] | 6610 |  | 14554.5767 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.6 | Water Handling Systems | 1.2.6 Water Handling Systems | 1.2.6.6 | ARA Hot Water Drill Subsystem | 1.2.6.6 ARA Hot Water Drill Subsystem | cell-link@smartsheet.com | 2021-11-30 20:59 |  | 47d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.6.6.2 | 0 | 0 | 3599.9448 | 3599.9448 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2451.5624 | 2451.5624 | 2451.5624 | 0 | 1.2.6.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.6.2 | 0 | 0 | 3599.9448 | 3599.9448 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7199.8895 | 1.2.6.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7199.8895 | 1.2.6.6.2 | 7199.8895 | 46579.8453 | 0 | 0 | 3599.9448 | 7199.8895 | 7199.8895 | 7199.8895 | 7199.8895 | 7199.8895 | 7199.8895 | 7199.8895 | 7199.8895 | 7199.8895 | 7939.9779 | 15879.9558 | 19479.9006 | 34829.8453 | 46579.8453 | 46579.8453 | 46579.8453 | 46579.8453 | 46579.8453 | 46579.8453 | 46579.8453 | 46579.8453
| 1.2 | 1.2.6.6.2 | C |  | PSL | ARA Drill: Procure Upgrade, Integration, & Replacement Parts |  |  | CapEx |  |  | EE | 1 | 1 | 0% | 2021-03-31 | 2023-10-31 | [7 empty] | 11750 | 11750 | [7 empty] | 0 | 0 | 0 | 11750 | 11750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23500 | 53% | 0 | 23500 | 23500 | [9 empty] | 3500 | 3500 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3500 | 3500 | 0 | 7000 | 53% | 0 | 7000 | 7000 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 17627 | [5 empty] | 17627 |  | 30500 | CapEx | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.6 | Water Handling Systems | 1.2.6 Water Handling Systems | 1.2.6.6 | ARA Hot Water Drill Subsystem | 1.2.6.6 ARA Hot Water Drill Subsystem | cell-link@smartsheet.com | 2021-11-30 20:59 |  | 47d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.6.6.2 | 0 | 0 | 0 | 11750 | 11750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3500 | 3500 | 0 | 1.2.6.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.6.2 | 0 | 0 | 0 | 11750 | 11750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23500 | 1.2.6.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23500 | 1.2.6.6.2 | 23500 | 39379.9558 | 0 | 0 | 0 | 11750 | 23500 | 23500 | 23500 | 23500 | 23500 | 23500 | 23500 | 23500 | 7939.9779 | 15879.9558 | 15879.9558 | 27629.9558 | 39379.9558 | 39379.9558 | 39379.9558 | 39379.9558 | 39379.9558 | 39379.9558 | 39379.9558 | 39379.9558
| 1.2 | 1.2.6.6.2 | C |  | PSL | ARA Drill: Procure Replacement Rodwell Pump |  | 1.333% | Labor Hours | EN |  | EE |  | 115 | 0% | 2021-03-31 | 2023-10-31 |  |  |  |  | 12 | 12 | [10 empty] | 1380 | 1380 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2760 | 0% | 0 | 2879.9558 | 2879.9558 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | [9 empty] | 2879.9558 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.6 | Water Handling Systems | 1.2.6 Water Handling Systems | 1.2.6.6 | ARA Hot Water Drill Subsystem | 1.2.6.6 ARA Hot Water Drill Subsystem | cell-link@smartsheet.com | 2021-11-30 20:59 |  | 47d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.6.6.2 | 1439.9779 | 1439.9779 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.6.2 | 1439.9779 | 1439.9779 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2879.9558 | 1.2.6.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2879.9558 | 1.2.6.6.2 | 2879.9558 | 15879.9558 | 1439.9779 | 2879.9558 | 2879.9558 | 2879.9558 | 2879.9558 | 2879.9558 | 2879.9558 | 2879.9558 | 2879.9558 | 2879.9558 | 2879.9558 | 2879.9558 | 7939.9779 | 15879.9558 | 15879.9558 | 15879.9558 | 15879.9558 | 15879.9558 | 15879.9558 | 15879.9558 | 15879.9558 | 15879.9558 | 15879.9558 | 15879.9558
| 1.2 | 1.2.6.6.2 | C |  | PSL | ARA Drill: Procure Replacement Rodwell Pump |  |  | CapEx |  |  | EE |  | 1 | 0% | 2021-03-31 | 2023-10-31 |  |  |  |  | 6500 | 6500 | [10 empty] | 6500 | 6500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13000 | 53% | 0 | 13000 | 13000 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 13000 | CapEx | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.6 | Water Handling Systems | 1.2.6 Water Handling Systems | 1.2.6.6 | ARA Hot Water Drill Subsystem | 1.2.6.6 ARA Hot Water Drill Subsystem | cell-link@smartsheet.com | 2021-11-30 20:59 |  | 47d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.6.6.2 | 6500 | 6500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.6.2 | 6500 | 6500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13000 | 1.2.6.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13000 | 1.2.6.6.2 | 13000 | 13000 | 6500 | 13000 | 13000 | 13000 | 13000 | 13000 | 13000 | 13000 | 13000 | 13000 | 13000 | 13000 | 6500 | 13000 | 13000 | 13000 | 13000 | 13000 | 13000 | 13000 | 13000 | 13000 | 13000 | 13000
| 1.2 | 1.2.6.6.3 | C |  | PSL | ARA Drill: Subsystem Assembly, Integration & Testing at PSL (Driller_PSL_Lead) |  | 1.333% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2021-07-01 | 2023-09-01 | [10 empty] | 8 | 8 | 8 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 920 | 920 | 920 | 0 | 0 | 0 | 2760 | 0% | 0 | 2879.9558 | 2879.9558 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 14076 | [5 empty] | 14076 |  | 2879.9558 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.6 | Water Handling Systems | 1.2.6 Water Handling Systems | 1.2.6.6 | ARA Hot Water Drill Subsystem | 1.2.6.6 ARA Hot Water Drill Subsystem | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 71d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.6.6.3 | 0 | 0 | 0 | 0 | 0 | 0 | 959.9853 | 959.9853 | 959.9853 | 0 | 0 | 0 | 1.2.6.6.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.6.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.6.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.6.3 | 0 | 0 | 0 | 0 | 0 | 0 | 959.9853 | 959.9853 | 959.9853 | 0 | 0 | 0 | 2879.9558 | 1.2.6.6.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.6.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2879.9558 | 1.2.6.6.3 | 2879.9558 | 2879.9558 | 0 | 0 | 0 | 0 | 0 | 0 | 959.9853 | 1919.9705 | 2879.9558 | 2879.9558 | 2879.9558 | 2879.9558 | 0 | 0 | 0 | 0 | 0 | 0 | 959.9853 | 1919.9705 | 2879.9558 | 2879.9558 | 2879.9558 | 2879.9558
| 1.2 | 1.2.6.6.3 | C |  | PSL | ARA Drill: Subsystem Assembly, Integration & Testing at PSL (Driller_PSL_DirectHire) |  | 0% | Labor Hours | TE |  |  | 81 | 77 | 0% | 2021-07-01 | 2023-09-01 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 9914 | [5 empty] | 9914 |  | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.6 | Water Handling Systems | 1.2.6 Water Handling Systems | 1.2.6.6 | ARA Hot Water Drill Subsystem | 1.2.6.6 ARA Hot Water Drill Subsystem | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 71d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.6.6.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.6.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.6.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.6.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.6.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.6.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.6.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6.6.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.7.1.6 | C |  | PSL | ARA Drill: Procure Brake Solenoid |  | 0.4444% | Labor Hours | EN |  |  |  | 115 | 0% | 2019-10-22 | 2019-10-28 |  |  |  |  | 8 | [11 empty] | 920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 920 | 0% | 0 | 959.9853 | 959.9853 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | [9 empty] | 959.9853 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.7 | Support Equipment | 1.2.7 Support Equipment | 1.2.7.1 | Independent Firn Drill | 1.2.7.1 Independent Firn Drill | cell-link@smartsheet.com | 2021-11-30 13:35 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.7.1.6 | 959.9853 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.1.6 | 959.9853 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 959.9853 | 1.2.7.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 959.9853 | 1.2.7.1.6 | 959.9853 | 1359.9853 | 959.9853 | 959.9853 | 959.9853 | 959.9853 | 959.9853 | 959.9853 | 959.9853 | 959.9853 | 959.9853 | 959.9853 | 959.9853 | 959.9853 | 1359.9853 | 1359.9853 | 1359.9853 | 1359.9853 | 1359.9853 | 1359.9853 | 1359.9853 | 1359.9853 | 1359.9853 | 1359.9853 | 1359.9853 | 1359.9853
| 1.2 | 1.2.7.1.6 | C |  | PSL | ARA Drill: Procure Brake Solenoid |  |  | CapEx | EN |  |  |  | 1 | 0% | 2019-10-22 | 2019-10-28 |  |  |  |  | 400 | [11 empty] | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 53% | 0 | 400 | 400 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 400 | CapEx | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.7 | Support Equipment | 1.2.7 Support Equipment | 1.2.7.1 | Independent Firn Drill | 1.2.7.1 Independent Firn Drill | cell-link@smartsheet.com | 2021-11-30 13:35 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.7.1.6 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.1.6 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 1.2.7.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 1.2.7.1.6 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400
| 1.2 | 1.2.7.2.1 | C |  | PSL | Support Equipment: Identify Spares and Replacements (Driller_PSL_Lead) |  | 1.333% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2021-01-01 | 2024-04-05 |  |  |  |  | 8 | 8 | 8 | [9 empty] | 920 | 920 | 920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2760 | 0% | 0 | 2879.9558 | 189.9558 | [5 empty] | 8 |  | 8 | 8 |  |  |  | 0 | 0 | 0 | 0 | 0 | 920 | 0 | 920 | 920 | 0 | 0 | 0 | 2760 | 0% | 0 | 2941.8749 | 2780.8749 | 8 | [5 empty] | 8 | [5 empty] | 920 | 0 | 0 | 0 | 0 | 0 | 920 | 0 | 0 | 0 | 0 | 0 | 1840 | 0% | 0 | 2003.4168 | 2003.4168 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 1444 | 2583.7452 | 2637 | 2690 |  | 161 |  | 9524 |  | 7825.2474 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.7 | Support Equipment | 1.2.7 Support Equipment | 1.2.7.2 | Maintenance/Repair Inventory | 1.2.7.2 Maintenance/Repair Inventory | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1199d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.7.2.1 | 959.9853 | 959.9853 | 959.9853 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.2.1 | 0 | 0 | 0 | 0 | 0 | 980.625 | 0 | 980.625 | 980.625 | 0 | 0 | 0 | 1.2.7.2.1 | 1001.7084 | 0 | 0 | 0 | 0 | 0 | 1001.7084 | 0 | 0 | 0 | 0 | 0 | 1.2.7.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.2.1 | 959.9853 | 959.9853 | 959.9853 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2879.9558 | 1.2.7.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2879.9558 | 1.2.7.2.1 | 2879.9558 | 2879.9558 | 959.9853 | 1919.9705 | 2879.9558 | 2879.9558 | 2879.9558 | 2879.9558 | 2879.9558 | 2879.9558 | 2879.9558 | 2879.9558 | 2879.9558 | 2879.9558 | 959.9853 | 1919.9705 | 2879.9558 | 2879.9558 | 2879.9558 | 2879.9558 | 2879.9558 | 2879.9558 | 2879.9558 | 2879.9558 | 2879.9558 | 2879.9558
| 1.2 | 1.2.7.2.2 | C |  | PSL | Support Equipment: Procure Spares and Replacements (Driller_PSL_Lead) |  | 1.333% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2021-03-01 | 2024-06-03 | [5 empty] | 8 | 8 | 8 | [8 empty] | 0 | 920 | 920 | 920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2760 | 0% | 0 | 2879.9558 | 189.9558 | [8 empty] | 8 | 16 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 920 | 1840 | 0 | 0 | 2760 | 0% | 0 | 2941.8749 | 2780.8749 | 8 | [6 empty] | 16 | 16 |  |  |  | 920 | 0 | 0 | 0 | 0 | 0 | 0 | 1840 | 1840 | 0 | 0 | 0 | 4600 | 0% | 0 | 5008.5419 | 5008.5419 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 1444 | 2583.7452 | 2637 | 2690 |  | 161 |  | 9524 |  | 10830.3726 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.7 | Support Equipment | 1.2.7 Support Equipment | 1.2.7.2 | Maintenance/Repair Inventory | 1.2.7.2 Maintenance/Repair Inventory | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1199d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.7.2.2 | 0 | 959.9853 | 959.9853 | 959.9853 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 980.625 | 1961.2499 | 0 | 0 | 1.2.7.2.2 | 1001.7084 | 0 | 0 | 0 | 0 | 0 | 0 | 2003.4168 | 2003.4168 | 0 | 0 | 0 | 1.2.7.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.2.2 | 0 | 959.9853 | 959.9853 | 959.9853 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2879.9558 | 1.2.7.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2879.9558 | 1.2.7.2.2 | 2879.9558 | 12879.9558 | 0 | 959.9853 | 1919.9705 | 2879.9558 | 2879.9558 | 2879.9558 | 2879.9558 | 2879.9558 | 2879.9558 | 2879.9558 | 2879.9558 | 2879.9558 | 0 | 5959.9853 | 11919.9705 | 12879.9558 | 12879.9558 | 12879.9558 | 12879.9558 | 12879.9558 | 12879.9558 | 12879.9558 | 12879.9558 | 12879.9558
| 1.2 | 1.2.7.2.2 | C |  | PSL | Support Equipment: Procure Spares and Replacements |  |  | CapEx |  |  |  | 1 | 1 | 0% | 2021-03-01 | 2024-06-03 | [5 empty] | 5000 | 5000 | [9 empty] | 0 | 5000 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 53% | 0 | 10000 | -3775 | [9 empty] | 5000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 5000 | 53% | 0 | 5000 | 4195 | 7500 | [6 empty] | 5000 | 5000 |  |  |  | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 5000 | 0 | 0 | 0 | 17500 | 53% | 0 | 17500 | 17500 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 7833 | 13812 | 13775 | 13775 |  | 805 |  | 50000 |  | 32500 | CapEx | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.7 | Support Equipment | 1.2.7 Support Equipment | 1.2.7.2 | Maintenance/Repair Inventory | 1.2.7.2 Maintenance/Repair Inventory | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1199d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.7.2.2 | 0 | 5000 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 1.2.7.2.2 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 5000 | 0 | 0 | 0 | 1.2.7.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.2.2 | 0 | 5000 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 1.2.7.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 1.2.7.2.2 | 10000 | 10000 | 0 | 5000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 0 | 5000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000
| 1.2 | 1.2.7.2.3 | C |  | PSL | Support Equipment: Procure Hose Stock and Fittings |  | 1.111% | Labor Hours | EN |  |  |  | 115 | 0% | 2021-02-01 | 2021-03-12 | [8 empty] | 20 | [7 empty] | 0 | 0 | 0 | 0 | 2300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2300 | 0% | 0 | 2399.9632 | 2399.9632 | [8 empty] | 8 | 16 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 920 | 1840 | 0 | 0 | 2760 | 0% | 0 | 2941.8749 | 2941.8749 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | [9 empty] | 5341.838 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.7 | Support Equipment | 1.2.7 Support Equipment | 1.2.7.2 | Maintenance/Repair Inventory | 1.2.7.2 Maintenance/Repair Inventory | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1199d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.7.2.3 | 0 | 0 | 0 | 0 | 2399.9632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 980.625 | 1961.2499 | 0 | 0 | 1.2.7.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.2.3 | 0 | 0 | 0 | 0 | 2399.9632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2399.9632 | 1.2.7.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2399.9632 | 1.2.7.2.3 | 2399.9632 | 17399.9632 | 0 | 0 | 0 | 0 | 2399.9632 | 2399.9632 | 2399.9632 | 2399.9632 | 2399.9632 | 2399.9632 | 2399.9632 | 2399.9632 | 0 | 0 | 0 | 0 | 17399.9632 | 17399.9632 | 17399.9632 | 17399.9632 | 17399.9632 | 17399.9632 | 17399.9632 | 17399.9632
| 1.2 | 1.2.7.2.3 | C |  | PSL | Support Equipment: Procure Hose Stock and Fittings |  |  | CapEx |  |  |  |  | 1 | 0% | 2021-02-01 | 2021-03-12 | [8 empty] | 15000 | [7 empty] | 0 | 0 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 53% | 0 | 15000 | 15000 | [9 empty] | 5000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 5000 | 53% | 0 | 5000 | 5000 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 20000 | CapEx | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.7 | Support Equipment | 1.2.7 Support Equipment | 1.2.7.2 | Maintenance/Repair Inventory | 1.2.7.2 Maintenance/Repair Inventory | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1199d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.7.2.3 | 0 | 0 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 1.2.7.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.2.3 | 0 | 0 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 1.2.7.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 1.2.7.2.3 | 15000 | 15000 | 0 | 0 | 0 | 0 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 0 | 0 | 0 | 0 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000
| 1.2 | 1.2.7.2.4 | C |  | PSL | Support Equipment: Spare Parts Inventory and Catalog - Electrical/Controls |  | 2.222% | Labor Hours | EN |  |  |  | 115 | 0% | 2021-02-01 | 2021-09-24 | [8 empty] | 8 |  | 8 |  | 8 |  | 8 | 8 | 0 | 0 | 0 | 0 | 920 | 0 | 920 | 0 | 920 | 0 | 920 | 920 | 4600 | 0% | 0 | 4799.9263 | 4799.9263 | [8 empty] | 8 | 8 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 920 | 920 | 0 | 0 | 1840 | 0% | 0 | 1961.2499 | 1961.2499 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | [9 empty] | 6761.1763 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.7 | Support Equipment | 1.2.7 Support Equipment | 1.2.7.2 | Maintenance/Repair Inventory | 1.2.7.2 Maintenance/Repair Inventory | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1199d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.7.2.4 | 0 | 0 | 0 | 0 | 959.9853 | 0 | 959.9853 | 0 | 959.9853 | 0 | 959.9853 | 959.9853 | 1.2.7.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 980.625 | 980.625 | 0 | 0 | 1.2.7.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.2.4 | 0 | 0 | 0 | 0 | 959.9853 | 0 | 959.9853 | 0 | 959.9853 | 0 | 959.9853 | 959.9853 | 4799.9263 | 1.2.7.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4799.9263 | 1.2.7.2.4 | 4799.9263 | 4799.9263 | 0 | 0 | 0 | 0 | 959.9853 | 959.9853 | 1919.9705 | 1919.9705 | 2879.9558 | 2879.9558 | 3839.9411 | 4799.9263 | 0 | 0 | 0 | 0 | 959.9853 | 959.9853 | 1919.9705 | 1919.9705 | 2879.9558 | 2879.9558 | 3839.9411 | 4799.9263
| 1.2 | 1.2.7.3.1 | C |  | PSL | Shops: Identify Upgrade-Replacements, Spares (Driller_PSL_Lead) |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2022-06-01 | 2023-06-28 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [6 empty] | 8 | 8 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 920 | 920 | 0 | 0 | 0 | 0 | 1840 | 0% | 0 | 1961.2499 | 1961.2499 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 4692 | [5 empty] | 4692 |  | 1961.2499 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.7 | Support Equipment | 1.2.7 Support Equipment | 1.2.7.3 | Shops (MECC, SEW, TOW, OML) | 1.2.7.3 Shops (MECC, SEW, TOW, OML) | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 72d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.7.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 980.625 | 980.625 | 0 | 0 | 0 | 0 | 1.2.7.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.7.3.2 | C |  | PSL | Shops: Procure Upgrade-Replacements, Spares (Driller_PSL_Lead) |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2022-11-01 | 2023-08-11 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [7 empty] | 16 | 8 | 8 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1840 | 920 | 920 | 0 | 0 | 3680 | 0% | 0 | 3922.4998 | 3922.4998 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 4692 | [5 empty] | 4692 |  | 3922.4998 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.7 | Support Equipment | 1.2.7 Support Equipment | 1.2.7.3 | Shops (MECC, SEW, TOW, OML) | 1.2.7.3 Shops (MECC, SEW, TOW, OML) | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 72d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.7.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1961.2499 | 980.625 | 980.625 | 0 | 0 | 1.2.7.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.7.3.2 | C |  | PSL | Shops: Procure Upgrade-Replacements, Spares |  |  | CapEx |  |  | EE | 1 | 1 | 0% | 2022-11-01 | 2023-08-11 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [7 empty] | 1500 | 1000 | 1000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 1000 | 1000 | 0 | 0 | 3500 | 53% | 0 | 3500 | 3500 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 10000 | [5 empty] | 10000 |  | 3500 | CapEx | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.7 | Support Equipment | 1.2.7 Support Equipment | 1.2.7.3 | Shops (MECC, SEW, TOW, OML) | 1.2.7.3 Shops (MECC, SEW, TOW, OML) | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 72d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.7.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 1000 | 1000 | 0 | 0 | 1.2.7.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.7.4.2 | C |  | PSL | Testbed: Identify & Procure Upgrade & Replacement Parts (PSL_Technician) |  | 0% | Labor Hours | TE |  |  | 81 | 77 | 0% | 2019-03-18 | 2019-10-25 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 6424 | 57 | [5 empty] | 6481 |  | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.7 | Support Equipment | 1.2.7 Support Equipment | 1.2.7.4 | TestBed | 1.2.7.4 TestBed | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 191d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.7.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.7.4.2 | C |  | PSL | Testbed: Identify & Procure Upgrade & Replacement Parts (PSL_Engineer) |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2019-03-18 | 2019-10-25 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 9121 | 81 | [5 empty] | 9202 |  | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.7 | Support Equipment | 1.2.7 Support Equipment | 1.2.7.4 | TestBed | 1.2.7.4 TestBed | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 191d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.7.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.7.4.2 | C |  | PSL | Testbed: Identify & Procure Upgrade & Replacement Parts |  |  | CapEx |  |  | EE | 1 | 1 | 0% | 2019-03-18 | 2019-10-25 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 19829 | 171 | [5 empty] | 20000 |  | 0 | CapEx | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.7 | Support Equipment | 1.2.7 Support Equipment | 1.2.7.4 | TestBed | 1.2.7.4 TestBed | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 191d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.7.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.7.4.4 | C |  | PSL | Testbed: Commission/Maintenance/Decommission (2020) (PSL_Technician) |  | 0% | Labor Hours | TE |  |  | 81 | 77 | 0% | 2020-04-13 | 2020-11-20 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 9123 | 807 |  |  |  |  | 9930 |  | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.7 | Support Equipment | 1.2.7 Support Equipment | 1.2.7.4 | TestBed | 1.2.7.4 TestBed | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 191d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.7.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.7.4.4 | C |  | PSL | Testbed: Commission/Maintenance/Decommission (2020) (PSL_Engineer) |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2020-04-13 | 2020-11-20 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 12952 | 1146 |  |  |  |  | 14098 |  | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.7 | Support Equipment | 1.2.7 Support Equipment | 1.2.7.4 | TestBed | 1.2.7.4 TestBed | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 191d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.7.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.7.4.4 | C |  | PSL | Testbed: Commission/Maintenance/Decommission (2020) |  |  | CapEx |  |  | HD | 1 | 1 | 0% | 2020-04-13 | 2020-11-20 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 2761 | 239 |  |  |  |  | 3000 |  | 0 | CapEx | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.7 | Support Equipment | 1.2.7 Support Equipment | 1.2.7.4 | TestBed | 1.2.7.4 TestBed | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 191d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.7.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.7.4.5 | C |  | PSL | Testbed: Commission/Maintenance/Decommission (2021) (PSL_Technician) |  | 0.8889% | Labor Hours | TE |  |  | 81 | 77 | 0% | 2021-04-12 | 2021-11-19 |  | TRUE |  |  | 8 | 8 | [10 empty] | 616 | 616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1232 | 0% | 0 | 1285.5455 | 502.5455 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | 9345 | 783 |  |  |  | 10128 |  | 1285.5455 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.7 | Support Equipment | 1.2.7 Support Equipment | 1.2.7.4 | TestBed | 1.2.7.4 TestBed | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 191d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.7.4.5 | 642.7727 | 642.7727 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.4.5 | 642.7727 | 642.7727 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1285.5455 | 1.2.7.4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1285.5455 | 1.2.7.4.5 | 1285.5455 | 2822.2255 | 642.7727 | 1285.5455 | 1285.5455 | 1285.5455 | 1285.5455 | 1285.5455 | 1285.5455 | 1285.5455 | 1285.5455 | 1285.5455 | 1285.5455 | 1285.5455 | 1411.1127 | 2822.2255 | 2822.2255 | 2822.2255 | 2822.2255 | 2822.2255 | 2822.2255 | 2822.2255 | 2822.2255 | 2822.2255 | 2822.2255 | 2822.2255
| 1.2 | 1.2.7.4.5 | C |  | PSL | Testbed: Commission/Maintenance/Decommission (2021) (PSL_Engineer) |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2021-04-12 | 2021-11-19 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -1112 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | 13268 | 1112 |  |  |  | 14379 |  | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.7 | Support Equipment | 1.2.7 Support Equipment | 1.2.7.4 | TestBed | 1.2.7.4 TestBed | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 191d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.7.4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.4.5 | 0 | 1536.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 768.34 | 1536.68 | 1536.68 | 1536.68 | 1536.68 | 1536.68 | 1536.68 | 1536.68 | 1536.68 | 1536.68 | 1536.68 | 1536.68
| 1.2 | 1.2.7.4.5 | C |  | PSL | Testbed: Commission/Maintenance/Decommission (2021) |  |  | CapEx |  |  | HD | 1 | 1 | 0% | 2021-04-12 | 2021-11-19 |  | TRUE |  |  | 768.34 | 768.34 | [10 empty] | 768.34 | 768.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1536.68 | 53% | 0 | 1536.68 | 1308.68 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 | 2772 | 228 |  |  |  | 3000 |  | 1536.68 | CapEx | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.7 | Support Equipment | 1.2.7 Support Equipment | 1.2.7.4 | TestBed | 1.2.7.4 TestBed | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 191d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.7.4.5 | 768.34 | 768.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.4.5 | 768.34 | 768.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1536.68 | 1.2.7.4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1536.68 | 1.2.7.4.5 | 1536.68 | 1536.68 | 768.34 | 1536.68 | 1536.68 | 1536.68 | 1536.68 | 1536.68 | 1536.68 | 1536.68 | 1536.68 | 1536.68 | 1536.68 | 1536.68 | 768.34 | 1536.68 | 1536.68 | 1536.68 | 1536.68 | 1536.68 | 1536.68 | 1536.68 | 1536.68 | 1536.68 | 1536.68 | 1536.68
| 1.2 | 1.2.7.4.6 | C |  | PSL | Testbed: Commission/Maintenance/Decommission (2022) (PSL_Technician) |  | 0% | Labor Hours | TE |  |  | 81 | 77 | 0% | 2022-04-11 | 2022-11-17 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -9598 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -731 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 9598 |  | 731 |  | 10329 |  | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.7 | Support Equipment | 1.2.7 Support Equipment | 1.2.7.4 | TestBed | 1.2.7.4 TestBed | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 190d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.7.4.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.4.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.4.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.4.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.4.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.4.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.4.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.4.6 | 0 | 8531.9116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1883.9853 | 2843.9705 | 4727.9558 | 5687.9411 | 7571.9263 | 8531.9116
| 1.2 | 1.2.7.4.6 | C |  | PSL | Testbed:Commission/Maintenance/Decommission (2022) (PSL_Engineer) |  | 2.667% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2022-04-11 | 2022-11-17 | [10 empty] | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 920 | 920 | 920 | 920 | 920 | 920 | 5520 | 0% | 0 | 5759.9116 | -7867.0884 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -1038 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 13627 |  | 1038 |  | 14665 |  | 5759.9116 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.7 | Support Equipment | 1.2.7 Support Equipment | 1.2.7.4 | TestBed | 1.2.7.4 TestBed | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 190d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.7.4.6 | 0 | 0 | 0 | 0 | 0 | 0 | 959.9853 | 959.9853 | 959.9853 | 959.9853 | 959.9853 | 959.9853 | 1.2.7.4.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.4.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.4.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.4.6 | 0 | 0 | 0 | 0 | 0 | 0 | 959.9853 | 959.9853 | 959.9853 | 959.9853 | 959.9853 | 959.9853 | 5759.9116 | 1.2.7.4.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.4.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5759.9116 | 1.2.7.4.6 | 5759.9116 | 8531.9116 | 0 | 0 | 0 | 0 | 0 | 0 | 959.9853 | 1919.9705 | 2879.9558 | 3839.9411 | 4799.9263 | 5759.9116 | 0 | 0 | 0 | 0 | 0 | 0 | 1883.9853 | 2843.9705 | 4727.9558 | 5687.9411 | 7571.9263 | 8531.9116
| 1.2 | 1.2.7.4.6 | C |  | PSL | Testbed: Commission/Maintenance/Decommission (2022) |  |  | CapEx |  |  | HD | 1 | 1 | 0% | 2022-04-11 | 2022-11-17 | [10 empty] | 924 |  | 924 |  | 924 |  | 0 | 0 | 0 | 0 | 0 | 0 | 924 | 0 | 924 | 0 | 924 | 0 | 2772 | 53% | 0 | 2772 | -20 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | -208 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 |  | 2792 |  | 208 |  | 3000 |  | 2772 | CapEx | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.7 | Support Equipment | 1.2.7 Support Equipment | 1.2.7.4 | TestBed | 1.2.7.4 TestBed | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 190d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.7.4.6 | 0 | 0 | 0 | 0 | 0 | 0 | 924 | 0 | 924 | 0 | 924 | 0 | 1.2.7.4.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.4.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.4.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.4.6 | 0 | 0 | 0 | 0 | 0 | 0 | 924 | 0 | 924 | 0 | 924 | 0 | 2772 | 1.2.7.4.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.4.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2772 | 1.2.7.4.6 | 2772 | 2772 | 0 | 0 | 0 | 0 | 0 | 0 | 924 | 924 | 1848 | 1848 | 2772 | 2772 | 0 | 0 | 0 | 0 | 0 | 0 | 924 | 924 | 1848 | 1848 | 2772 | 2772
| 1.2 | 1.2.7.5.4 | C |  | PSL | Tools & Equipment: Identify Tools & Consumables (Driller_PSL_Lead) |  | 3.111% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2019-03-01 | 2022-12-28 |  | TRUE | [7 empty] | 16 | 8 | 8 | 8 | 8 | 8 |  | 0 | 0 | 0 | 0 | 0 | 1840 | 920 | 920 | 920 | 920 | 920 | 0 | 6440 | 0% | 0 | 6719.8969 | 4029.8969 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -161 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 1444 | 2583.7452 | 2637 | 2690 |  | 161 |  | 9524 |  | 6719.8969 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.7 | Support Equipment | 1.2.7 Support Equipment | 1.2.7.5 | Tools and Equipment | 1.2.7.5 Tools and Equipment | marek.rogal@icecube.wisc.edu | 2021-11-01 09:59 |  | 1199d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.7.5.4 | 0 | 0 | 0 | 0 | 0 | 1919.9705 | 959.9853 | 959.9853 | 959.9853 | 959.9853 | 959.9853 | 0 | 1.2.7.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.5.4 | 0 | 0 | 0 | 0 | 0 | 1919.9705 | 959.9853 | 959.9853 | 959.9853 | 959.9853 | 959.9853 | 0 | 6719.8969 | 1.2.7.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6719.8969 | 1.2.7.5.4 | 6719.8969 | 6719.8969 | 0 | 0 | 0 | 0 | 0 | 1919.9705 | 2879.9558 | 3839.9411 | 4799.9263 | 5759.9116 | 6719.8969 | 6719.8969 | 0 | 0 | 0 | 0 | 0 | 1919.9705 | 2879.9558 | 3839.9411 | 4799.9263 | 5759.9116 | 6719.8969 | 6719.8969
| 1.2 | 1.2.7.5.5 | C |  | PSL | Tools & Equipment: Procure Tools & Consumables (Driller_PSL_Lead) |  | 0.4444% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2019-03-01 | 2023-12-28 |  | TRUE | [7 empty] | 4 | 4 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 460 | 460 | 0 | 0 | 0 | 0 | 0 | 920 | 0% | 0 | 959.9853 | -1730.0147 | [6 empty] | 8 | 8 | 8 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 920 | 920 | 920 | 0 | 0 | 0 | 2760 | 0% | 0 | 2941.8749 | 2780.8749 | 16 | [5 empty] | 8 |  | 8 |  |  |  | 1840 | 0 | 0 | 0 | 0 | 0 | 920 | 0 | 920 | 0 | 0 | 0 | 3680 | 0% | 0 | 4006.8336 | 4006.8336 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 1444 | 2583.7452 | 2637 | 2690 |  | 161 |  | 9524 |  | 7908.6937 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.7 | Support Equipment | 1.2.7 Support Equipment | 1.2.7.5 | Tools and Equipment | 1.2.7.5 Tools and Equipment | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1199d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.7.5.5 | 0 | 0 | 0 | 0 | 0 | 479.9926 | 479.9926 | 0 | 0 | 0 | 0 | 0 | 1.2.7.5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 980.625 | 980.625 | 980.625 | 0 | 0 | 0 | 1.2.7.5.5 | 2003.4168 | 0 | 0 | 0 | 0 | 0 | 1001.7084 | 0 | 1001.7084 | 0 | 0 | 0 | 1.2.7.5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.5.5 | 0 | 0 | 0 | 0 | 0 | 479.9926 | 479.9926 | 0 | 0 | 0 | 0 | 0 | 959.9853 | 1.2.7.5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 959.9853 | 1.2.7.5.5 | 959.9853 | 11669.9853 | 0 | 0 | 0 | 0 | 0 | 479.9926 | 959.9853 | 959.9853 | 959.9853 | 959.9853 | 959.9853 | 959.9853 | 0 | 0 | 0 | 0 | 0 | 5834.9926 | 11669.9853 | 11669.9853 | 11669.9853 | 11669.9853 | 11669.9853 | 11669.9853
| 1.2 | 1.2.7.5.5 | C |  | PSL | Tools & Equipment: Procure Tools & Consumables |  |  | M & S |  |  |  | 1 | 1 | 0% | 2019-03-01 | 2023-12-28 |  | TRUE | [7 empty] | 3500 | 3500 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 3500 | 3500 | 0 | 0 | 0 | 0 | 0 | 7000 | 53% | 3710 | 10710 | -1935 | [5 empty] | 5000 | 5000 | 5000 | 2500 |  |  |  | 0 | 0 | 0 | 0 | 0 | 5000 | 5000 | 5000 | 2500 | 0 | 0 | 0 | 17500 | 53% | 9275 | 26775 | 6775 | [6 empty] | 5000 | 5000 | 5000 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 5000 | 5000 | 0 | 0 | 0 | 15000 | 53% | 7950 | 22950 | 22950 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 7191 | 12680 | 12645 | 12645 |  | 20000 |  | 45900 |  | 60435 | M & S | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.7 | Support Equipment | 1.2.7 Support Equipment | 1.2.7.5 | Tools and Equipment | 1.2.7.5 Tools and Equipment | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1199d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.7.5.5 | 0 | 0 | 0 | 0 | 0 | 5355 | 5355 | 0 | 0 | 0 | 0 | 0 | 1.2.7.5.5 | 0 | 0 | 0 | 0 | 0 | 7650 | 7650 | 7650 | 3825 | 0 | 0 | 0 | 1.2.7.5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 7650 | 7650 | 7650 | 0 | 0 | 0 | 1.2.7.5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.5.5 | 0 | 0 | 0 | 0 | 0 | 3500 | 3500 | 0 | 0 | 0 | 0 | 0 | 7000 | 1.2.7.5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.5.5 | 0 | 0 | 0 | 0 | 0 | 1855 | 1855 | 0 | 0 | 0 | 0 | 0 | 3710 | 10710 | 1.2.7.5.5 | 10710 | 10710 | 0 | 0 | 0 | 0 | 0 | 5355 | 10710 | 10710 | 10710 | 10710 | 10710 | 10710 | 0 | 0 | 0 | 0 | 0 | 5355 | 10710 | 10710 | 10710 | 10710 | 10710 | 10710
| 1.2 | 1.2.7.5.6 | C |  | PSL | Tools & Equipment: Calibrate Crimper |  | 0.4444% | Labor Hours | EN |  |  |  | 115 | 0% | 2021-10-10 | 2021-10-18 |  |  |  |  | 8 | [11 empty] | 920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 920 | 0% | 0 | 959.9853 | 959.9853 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | [9 empty] | 959.9853 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.7 | Support Equipment | 1.2.7 Support Equipment | 1.2.7.5 | Tools and Equipment | 1.2.7.5 Tools and Equipment | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1199d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.7.5.6 | 959.9853 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.5.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.5.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.5.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.5.6 | 959.9853 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 959.9853 | 1.2.7.5.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.5.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 959.9853 | 1.2.7.5.6 | 959.9853 | 1602.758 | 959.9853 | 959.9853 | 959.9853 | 959.9853 | 959.9853 | 959.9853 | 959.9853 | 959.9853 | 959.9853 | 959.9853 | 959.9853 | 959.9853 | 1602.758 | 1602.758 | 1602.758 | 1602.758 | 1602.758 | 1602.758 | 1602.758 | 1602.758 | 1602.758 | 1602.758 | 1602.758 | 1602.758
| 1.2 | 1.2.7.5.6 | C |  | PSL | Tools & Equipment: Calibrate Crimper |  | 0.4444% | Labor Hours | TE |  |  |  | 77 | 0% | 2021-10-10 | 2021-10-18 |  |  |  |  | 8 | [11 empty] | 616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 616 | 0% | 0 | 642.7727 | 642.7727 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | [9 empty] | 642.7727 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.7 | Support Equipment | 1.2.7 Support Equipment | 1.2.7.5 | Tools and Equipment | 1.2.7.5 Tools and Equipment | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1199d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.7.5.6 | 642.7727 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.5.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.5.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.5.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.5.6 | 642.7727 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 642.7727 | 1.2.7.5.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7.5.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 642.7727 | 1.2.7.5.6 | 642.7727 | 642.7727 | 642.7727 | 642.7727 | 642.7727 | 642.7727 | 642.7727 | 642.7727 | 642.7727 | 642.7727 | 642.7727 | 642.7727 | 642.7727 | 642.7727 | 642.7727 | 642.7727 | 642.7727 | 642.7727 | 642.7727 | 642.7727 | 642.7727 | 642.7727 | 642.7727 | 642.7727 | 642.7727 | 642.7727
| 1.2 | 1.2.8.1.2 | C |  | PSL | 2022-23 Off-Ice EHWD & Safety Training - 3 Drillers incl. 1 alternates (Driller_PSL_DirectHire) |  | 9.333% | Labor Hours | TE |  |  | 81 | 77 | 0% | 2022-07-24 | 2022-08-05 |  | TRUE |  | Training/travel 3 Direct Hire (1 alternate) - assuming 7 days @ 8 hours per | [9 empty] | 84 | 84 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6468 | 6468 | 0 | 12936 | 0% | 0 | 13498.2277 | 13498.2277 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | 53934 |  |  |  |  | 53934 |  | 13498.2277 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.1 | Seasonal Staffing & Training, Off-Ice Coordination | 1.2.8.1 Seasonal Staffing & Training, Off-Ice Coordination | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 12d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6749.1138 | 6749.1138 | 0 | 1.2.8.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6749.1138 | 6749.1138 | 0 | 13498.2277 | 1.2.8.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13498.2277 | 1.2.8.1.2 | 13498.2277 | 47643.8962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6749.1138 | 13498.2277 | 13498.2277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23821.9481 | 47643.8962 | 47643.8962
| 1.2 | 1.2.8.1.2 | C |  | PSL | 2022-23 Off-Ice EHWD & Safety Training - 6 PSL (Driller Lead/Engineers) |  | 10% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2022-07-24 | 2022-08-05 |  | TRUE |  | Assuming 30 hours per PSL team member for training | [9 empty] | 90 | 90 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10350 | 10350 | 0 | 20700 | 0% | 0 | 21599.6686 | 21599.6686 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | 9572 |  |  |  |  | 9572 |  | 21599.6686 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.1 | Seasonal Staffing & Training, Off-Ice Coordination | 1.2.8.1 Seasonal Staffing & Training, Off-Ice Coordination | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 12d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10799.8343 | 10799.8343 | 0 | 1.2.8.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10799.8343 | 10799.8343 | 0 | 21599.6686 | 1.2.8.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21599.6686 | 1.2.8.1.2 | 21599.6686 | 34145.6686 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10799.8343 | 21599.6686 | 21599.6686 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17072.8343 | 34145.6686 | 34145.6686
| 1.2 | 1.2.8.1.2 | C |  | PSL | 2022-23 Off-Ice EHWD & Safety Training - 3 DH Drillers - (Direct Hire Travel -1 Domestic, 2 International) |  |  | Travel |  |  |  | 1 | 1 | 0% | 2022-07-24 | 2022-08-05 |  | TRUE |  | Attendance 3 Direct Hire - 2 deploy w/ 1 alternates (estimating 0 local, 1 domestic, 2 intl). Duration 7 days with travel. 1 Local - No travel costs 1 Domestic - $1800 2 International - $6400 | [9 empty] | 4100 | 4100 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4100 | 4100 | 0 | 8200 | 53% | 4346 | 12546 | 12546 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 | 58031 |  |  |  |  | 58031 |  | 12546 | Travel | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.1 | Seasonal Staffing & Training, Off-Ice Coordination | 1.2.8.1 Seasonal Staffing & Training, Off-Ice Coordination | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 12d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6273 | 6273 | 0 | 1.2.8.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4100 | 4100 | 0 | 8200 | 1.2.8.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2173 | 2173 | 0 | 4346 | 12546 | 1.2.8.1.2 | 12546 | 12546 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6273 | 12546 | 12546 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6273 | 12546 | 12546
| 1.2 | 1.2.8.1.3 | C |  | PSL | 2023-24 Off-Ice EHWD & Safety Training - 5 Drillers incl. 1 alternates (Driller_PSL_DirectHire) |  | 0% | Labor Hours | TE |  |  | 81 | 77 | 0% | 2023-07-24 | 2023-08-07 |  |  |  | Training/travel 5 Direct Hire (w/ 1 alternate) - assuming 7 days @ 8 hours per | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -137533 | [9 empty] | 140 | 140 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10780 | 10780 | 0 | 21560 | 0% | 0 | 22980.7326 | 22980.7326 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 137533 |  |  |  | 137533 |  | 22980.7326 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.1 | Seasonal Staffing & Training, Off-Ice Coordination | 1.2.8.1 Seasonal Staffing & Training, Off-Ice Coordination | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 12d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11490.3663 | 11490.3663 | 0 | 1.2.8.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.1.3 | C |  | PSL | 2023-24 Off-Ice EHWD & Safety Training - 10 PSL (Driller_Lead/Engineer) |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2023-07-24 | 2023-08-07 |  |  |  | Assuming 30 hours per PSL team member for training | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -9763 | [9 empty] | 150 | 150 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17250 | 17250 | 0 | 34500 | 0% | 0 | 36773.4357 | 36773.4357 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 9763 |  |  |  | 9763 |  | 36773.4357 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.1 | Seasonal Staffing & Training, Off-Ice Coordination | 1.2.8.1 Seasonal Staffing & Training, Off-Ice Coordination | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 12d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18386.7179 | 18386.7179 | 0 | 1.2.8.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.1.3 | C |  | PSL | 2023-24 Off-Ice EHWD & Safety Training - 5 DH Drillers w/ 1 alternates - (Direct Hire Travel -1 Domestic 2 International) |  |  | Travel |  |  |  | 1 | 1 | 0% | 2023-07-24 | 2023-08-07 |  |  |  | Attendance 5 Direct Hire - 4 deploy w/ 1 alternates Duration 7 days with travel. 0 Local - No travel costs 3 Domestic - $5400 2 International - $6400 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | -124190 | [9 empty] | 5900 | 5900 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5900 | 5900 | 0 | 11800 | 53% | 6254 | 18054 | 18054 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 |  | 124190 |  |  |  | 124190 |  | 18054 | Travel | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.1 | Seasonal Staffing & Training, Off-Ice Coordination | 1.2.8.1 Seasonal Staffing & Training, Off-Ice Coordination | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 12d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9027 | 9027 | 0 | 1.2.8.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.1.4 | C |  | PSL | 2024-25 Off-Ice EHWD & Safety Training - 22 Drillers (w/2 alternates) (Driller_PSL_DirectHire) |  | 0% | Labor Hours | TE |  |  | 81 | 77 | 0% | 2024-07-24 | 2024-08-07 |  |  |  | Attendance 22 Direct Hire - 20 deploy w/ 2 alternates Duration 7 days with travel. 2 Local - No travel costs 3 Domestic - $5400 3 International - $9600 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -137533 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [9 empty] | 616 | 616 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47432 | 47432 | 0 | 94864 | 0% | 0 | 103289.2008 | 103289.2008 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 137533 |  |  |  | 137533 |  | 103289.2008 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.1 | Seasonal Staffing & Training, Off-Ice Coordination | 1.2.8.1 Seasonal Staffing & Training, Off-Ice Coordination | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 12d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51644.6004 | 51644.6004 | 0 | 1.2.8.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.1.4 | C |  | PSL | 2024-25 Off-Ice EHWD & Safety Training - 8 Drillers (Engineer/Driller PSL_Lead) |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2024-07-24 | 2024-08-07 |  |  |  | Assuming 30 hours per PSL team member for training | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -9763 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [9 empty] | 120 | 120 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13800 | 13800 | 0 | 27600 | 0% | 0 | 30051.2517 | 30051.2517 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 9763 |  |  |  | 9763 |  | 30051.2517 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.1 | Seasonal Staffing & Training, Off-Ice Coordination | 1.2.8.1 Seasonal Staffing & Training, Off-Ice Coordination | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 12d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15025.6258 | 15025.6258 | 0 | 1.2.8.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.1.4 | C |  | PSL | 2024-25 Off-Ice EHWD & Safety Training - 22 Drillers (Direct Hire Travel) |  |  | Travel |  |  |  | 1 | 1 | 0% | 2024-07-24 | 2024-08-07 |  |  |  | Attendance 22 Direct Hire - 20 deploy w/ 2 alternates Duration 7 days with travel. 4 Local - No travel costs 12 Domestic - $21600 6 International - $19200 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | -124190 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [9 empty] | 20400 | 20400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20400 | 20400 | 0 | 40800 | 53% | 21624 | 62424 | 62424 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 |  | 124190 |  |  |  | 124190 |  | 62424 | Travel | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.1 | Seasonal Staffing & Training, Off-Ice Coordination | 1.2.8.1 Seasonal Staffing & Training, Off-Ice Coordination | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 12d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31212 | 31212 | 0 | 1.2.8.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.1.7 | C |  | PSL | 2024-25 Off-Ice Logging Winch Training - 2 Drillers 1 day |  | 0% | Labor Hours | EN |  |  | 1 | 115 | 0% | 2019-09-02 | 2019-09-02 |  |  |  | 2 Drillers 1 day training with IDP support | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [10 empty] | 16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1840 | 0 | 1840 | 0% | 0 | 2003.4168 | 2003.4168 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | [9 empty] | 2003.4168 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.1 | Seasonal Staffing & Training, Off-Ice Coordination | 1.2.8.1 Seasonal Staffing & Training, Off-Ice Coordination | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 12d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.1.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.1.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.1.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2003.4168 | 0 | 1.2.8.1.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.1.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.1.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.1.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.1.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.5.2 | C |  | PSL | Deployment Travel & PQ Costs (22/23) (Driller_PSL_Lead) |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2022-06-02 | 2023-02-24 |  |  |  | 1 (Drill Leads), 5 days deployment travel 3 days redeployment | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -5858 |  | 40 |  |  | 24 | [7 empty] | 0 | 4600 | 0 | 0 | 2760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7360 | 0% | 0 | 7844.9996 | 7844.9996 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 5858 |  |  |  | 5858 |  | 7844.9996 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.5 | 2022/23 On-Ice Activities | 1.2.8.5 2022/23 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 103d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.2 | 0 | 4903.1248 | 0 | 0 | 2941.8749 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.2 | 0 | 63496.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4845.51 | 34171.02 | 63496.53 | 63496.53
| 1.2 | 1.2.8.5.2 | C |  | PSL | Deployment Travel & PQ Costs (22/23) (Driller_PSL_DirectHire) |  | 0% | Labor Hours | TE |  |  | 81 | 77 | 0% | 2022-06-02 | 2023-02-24 |  |  |  | 3 (Seasonal drillers), 5 days deployment travel 3 days redeployment 0 Contributed drillers (planned - $0 cost) | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -24756 |  | 80 |  |  | 72 | [7 empty] | 0 | 6160 | 0 | 0 | 5544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11704 | 0% | 0 | 12475.2548 | 12475.2548 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 24756 |  |  |  | 24756 |  | 12475.2548 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.5 | 2022/23 On-Ice Activities | 1.2.8.5 2022/23 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 103d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.2 | 0 | 6565.9236 | 0 | 0 | 5909.3312 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.2 | 0 | 63496.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4845.51 | 34171.02 | 63496.53 | 63496.53
| 1.2 | 1.2.8.5.2 | C |  | PSL | Deployment Travel & PQ Costs (22/23) (PSL_Engineer) |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2022-06-02 | 2023-02-24 |  |  |  | 5 (PSL Engineers), 5 days deployment travel 3 days redeployment | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -11716 |  | 240 |  |  | 144 | [7 empty] | 0 | 27600 | 0 | 0 | 16560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44160 | 0% | 0 | 47069.9978 | 47069.9978 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 11716 |  |  |  | 11716 |  | 47069.9978 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.5 | 2022/23 On-Ice Activities | 1.2.8.5 2022/23 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 103d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.2 | 0 | 29418.7486 | 0 | 0 | 17651.2492 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.2 | 0 | 63496.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4845.51 | 34171.02 | 63496.53 | 63496.53
| 1.2 | 1.2.8.5.2 | C |  | PSL | Deployment Travel & PQ Costs (22/23) |  |  | M & S |  |  |  | 1 | 1 | 0% | 2022-06-02 | 2023-02-24 |  |  |  | 10 - PQ's 1 Drill Lead, 3 Direct Hire (1 alternate) 6 PSL Engineers @ $950/each (anticipated cost) | [8 empty] | 3167 | 3167 | 3167 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3167 | 3167 | 3167 | 0 | 9501 | 53% | 5035.53 | 14536.53 | -7266.47 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 |  | 21803 |  |  |  | 21803 |  | 14536.53 | M & S | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.5 | 2022/23 On-Ice Activities | 1.2.8.5 2022/23 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 103d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4845.51 | 4845.51 | 4845.51 | 0 | 1.2.8.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3167 | 3167 | 3167 | 0 | 9501 | 1.2.8.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1678.51 | 1678.51 | 1678.51 | 0 | 5035.53 | 14536.53 | 1.2.8.5.2 | 14536.53 | 63496.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4845.51 | 9691.02 | 14536.53 | 14536.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4845.51 | 34171.02 | 63496.53 | 63496.53
| 1.2 | 1.2.8.5.2 | C |  | PSL | Deployment Travel & PQ Costs (22/23) |  |  | Travel |  |  |  | 1 | 1 | 0% | 2022-06-02 | 2023-02-24 |  |  |  | 8 - international travel | [9 empty] | 16000 | 16000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16000 | 16000 | 0 | 32000 | 53% | 16960 | 48960 | 19734 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 |  | 29226 |  |  |  | 29226 |  | 48960 | Travel | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.5 | 2022/23 On-Ice Activities | 1.2.8.5 2022/23 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 103d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24480 | 24480 | 0 | 1.2.8.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16000 | 16000 | 0 | 32000 | 1.2.8.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8480 | 8480 | 0 | 16960 | 48960 | 1.2.8.5.2 | 48960 | 48960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24480 | 48960 | 48960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24480 | 48960 | 48960
| 1.2 | 1.2.8.5.5.1 | C |  | PSL | SES: Drillers Support for SES Layout |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2022-12-01 | 2023-02-01 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -2929 |  |  | 18 | 18 | 4 | [7 empty] | 0 | 0 | 2070 | 2070 | 460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4600 | 0% | 0 | 4903.1248 | 4903.1248 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 2929 |  |  |  | 2929 |  | 4903.1248 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.5 | 2022/23 On-Ice Activities | 1.2.8.5 2022/23 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 3d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.5.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.5.1 | 0 | 0 | 2206.4061 | 2206.4061 | 490.3125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.5.5.2 | C |  | PSL | SES: Layout - Hoses, Cables, Interconnects and Cable trays |  | 0% | Labor Hours | TE |  |  | 81 | 77 | 0% | 2023-01-03 | 2023-02-01 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -10315 |  |  |  | 288 | [8 empty] | 0 | 0 | 0 | 22176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22176 | 0% | 0 | 23637.325 | 23637.325 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 10315 |  |  |  | 10315 |  | 23637.325 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.5 | 2022/23 On-Ice Activities | 1.2.8.5 2022/23 On-Ice Activities | cell-link@smartsheet.com | 2021-11-30 21:37 |  | 3d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.5.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.5.2 | 0 | 0 | 0 | 23637.325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.5.5.3.1 | C |  | PSL | SES: Deliver, Upgrade,/Repair, Connect, Test Fuel Tower |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2022-12-10 | 2023-01-02 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -5858 |  |  | 16 | 4 | [8 empty] | 0 | 0 | 1840 | 460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2300 | 0% | 0 | 2451.5624 | 2451.5624 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 5858 |  |  |  | 5858 |  | 2451.5624 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.5 | 2022/23 On-Ice Activities | 1.2.8.5 2022/23 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 3d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.5.5.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.5.3.1 | 0 | 0 | 1961.2499 | 490.3125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.5.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.5.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.5.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.5.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.5.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.5.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.5.5.4 | C |  | PSL | SES: Temp power from backup generator (CRELL, ONAN) |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2022-12-01 | 2023-02-01 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  | 1 | 2 | 1 | [7 empty] | 0 | 0 | 115 | 230 | 115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 460 | 0% | 0 | 490.3125 | 490.3125 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | 957 |  |  |  |  | 957 |  | 490.3125 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.5 | 2022/23 On-Ice Activities | 1.2.8.5 2022/23 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 4d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.5.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.5.4 | 0 | 0 | 122.5781 | 245.1562 | 122.5781 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.5.6.1 | C |  | PSL | Gens/PDM: Lift generators onto Skis with Crane |  | 0% | Labor Hours | TE |  |  | 81 | 77 | 0% | 2022-12-07 | 2022-12-08 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  | 8 | [9 empty] | 0 | 0 | 616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 616 | 0% | 0 | 656.5924 | 656.5924 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | 2023 |  |  |  |  | 2023 |  | 656.5924 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.5 | 2022/23 On-Ice Activities | 1.2.8.5 2022/23 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 4d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.5.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.6.1 | 0 | 0 | 656.5924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.5.6.3 | C |  | PSL | Gens/PDM: Generators - Misc Repairs |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2022-12-12 | 2023-01-13 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  | 40 | 40 | [8 empty] | 0 | 0 | 4600 | 4600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9200 | 0% | 0 | 9806.2495 | 9806.2495 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | 1914 |  |  |  |  | 1914 |  | 9806.2495 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.5 | 2022/23 On-Ice Activities | 1.2.8.5 2022/23 On-Ice Activities | cell-link@smartsheet.com | 2021-11-30 21:37 |  | 4d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.5.6.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.6.3 | 0 | 0 | 4903.1248 | 4903.1248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.6.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.6.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.6.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.6.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.6.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.6.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.5.6.5 | C |  | PSL | Gens/PDM: Preliminary GEN Testing |  | 0% | Labor Hours | EN |  |  | 1 | 115 | 0% | 2023-01-16 | 2023-01-27 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -21420 |  |  |  | 16 | [8 empty] | 0 | 0 | 0 | 1840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1840 | 0% | 0 | 1961.2499 | 1961.2499 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 21420 |  |  |  | 21420 |  | 1961.2499 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.5 | 2022/23 On-Ice Activities | 1.2.8.5 2022/23 On-Ice Activities | cell-link@smartsheet.com | 2021-11-30 21:37 |  | 182d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.5.6.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.6.5 | 0 | 0 | 0 | 1961.2499 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.6.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.6.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.6.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.6.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.6.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.6.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.5.7.1.1 | C |  | PSL | Computing/Controls: Install Retrofit Kits |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2022-11-22 | 2023-01-23 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  | 48 | 60 | 36 | [8 empty] | 0 | 5520 | 6900 | 4140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16560 | 0% | 0 | 17651.2492 | 17651.2492 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | 9572 |  |  |  |  | 9572 |  | 17651.2492 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.5 | 2022/23 On-Ice Activities | 1.2.8.5 2022/23 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 9d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.5.7.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.1.1 | 0 | 5883.7497 | 7354.6871 | 4412.8123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.5.7.1.2 | C |  | PSL | Computing/Controls: Misc. Controls Tasking (EE) |  | 0% | Labor Hours | EN |  |  | 81 | 115 | 0% | 2022-12-01 | 2023-01-23 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -13753 |  |  | 8 | 8 | [8 empty] | 0 | 0 | 920 | 920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1840 | 0% | 0 | 1961.2499 | 1961.2499 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 13753 |  |  |  | 13753 |  | 1961.2499 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.5 | 2022/23 On-Ice Activities | 1.2.8.5 2022/23 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.5.7.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.1.2 | 0 | 0 | 980.625 | 980.625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.5.7.1.2 | C |  | PSL | Computing/Controls: Install Modbus & DGH Modules (EE) |  | 0% | Labor Hours | EN |  |  | 81 | 115 | 0% | 2022-12-01 | 2023-01-23 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -27507 |  |  | 8 | 8 | [8 empty] | 0 | 0 | 920 | 920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1840 | 0% | 0 | 1961.2499 | 1961.2499 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 27507 |  |  |  | 27507 |  | 1961.2499 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.5 | 2022/23 On-Ice Activities | 1.2.8.5 2022/23 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 16d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.5.7.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.1.2 | 0 | 0 | 980.625 | 980.625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.5.7.1.3 | C |  | PSL | Computing/Controls: Conduit wiring |  | 0% | Labor Hours | TE |  |  | 115 | 77 | 0% | 2022-11-22 | 2023-01-23 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -39052 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 39052 |  |  |  | 39052 |  | 0 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.5 | 2022/23 On-Ice Activities | 1.2.8.5 2022/23 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 16d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.5.7.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.5.7.2.1 | C |  | PSL | DCC: Controls Retrofit (EE) |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2023-01-05 | 2023-01-11 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  |  | 24 | [8 empty] | 0 | 0 | 0 | 2760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2760 | 0% | 0 | 2941.8749 | 2941.8749 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | 2872 |  |  |  |  | 2872 |  | 2941.8749 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.5 | 2022/23 On-Ice Activities | 1.2.8.5 2022/23 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 5d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.5.7.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.2.1 | 0 | 0 | 0 | 2941.8749 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.5.7.2.1 | C |  | PSL | DCC: Repairs, Electrical Upgrades, Install Racks (EE) |  | 0% | Labor Hours | TE |  |  | 81 | 77 | 0% | 2023-01-05 | 2023-01-11 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  |  | 32 | [8 empty] | 0 | 0 | 0 | 2464 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2464 | 0% | 0 | 2626.3694 | 2626.3694 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | 3371 |  |  |  |  | 3371 |  | 2626.3694 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.5 | 2022/23 On-Ice Activities | 1.2.8.5 2022/23 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 5d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.5.7.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.2.1 | 0 | 0 | 0 | 2626.3694 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.5.7.3.1 | C |  | PSL | MHP: Controls Retrofit (EE) |  | 0% | Labor Hours | EN |  |  | 81 | 115 | 0% | 2022-11-15 | 2022-12-07 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  | 128 | 128 | [9 empty] | 0 | 14720 | 14720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29440 | 0% | 0 | 31379.9985 | 31379.9985 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | 26967 |  |  |  |  | 26967 |  | 31379.9985 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.5 | 2022/23 On-Ice Activities | 1.2.8.5 2022/23 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 17d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.5.7.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.3.1 | 0 | 15689.9993 | 15689.9993 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.5.7.3.1 | C |  | PSL | MHP: Retrofit MHPs |  | 0% | Labor Hours | TE |  |  | 81 | 77 | 0% | 2022-11-15 | 2022-12-07 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  | 96 | 96 | [9 empty] | 0 | 7392 | 7392 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14784 | 0% | 0 | 15758.2166 | 15758.2166 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | 13484 |  |  |  |  | 13484 |  | 15758.2166 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.5 | 2022/23 On-Ice Activities | 1.2.8.5 2022/23 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 10d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.5.7.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.3.1 | 0 | 7879.1083 | 7879.1083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.5.7.3.1 | C |  | PSL | MHP: Retrofit MHPs |  | 0% | Labor Hours | EN |  |  | 81 | 115 | 0% | 2022-11-15 | 2022-12-07 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  | 20 | 20 | [9 empty] | 0 | 2300 | 2300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4600 | 0% | 0 | 4903.1248 | 4903.1248 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | 6742 |  |  |  |  | 6742 |  | 4903.1248 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.5 | 2022/23 On-Ice Activities | 1.2.8.5 2022/23 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 9d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.5.7.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.3.1 | 0 | 2451.5624 | 2451.5624 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.5.7.3.2 | C |  | PSL | MHP subsystem evaluation |  | 0% | Labor Hours | EN |  |  | 81 | 115 | 0% | 2022-12-08 | 2022-12-08 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  | 32 | [9 empty] | 0 | 0 | 3680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3680 | 0% | 0 | 3922.4998 | 3922.4998 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | 6742 |  |  |  |  | 6742 |  | 3922.4998 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.5 | 2022/23 On-Ice Activities | 1.2.8.5 2022/23 On-Ice Activities | cell-link@smartsheet.com | 2021-11-30 21:37 |  | 5d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.5.7.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.3.2 | 0 | 0 | 3922.4998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.5.7.4.1 | C |  | PSL | PHS: Mechanical Retrofit (TE) |  | 0% | Labor Hours | TE |  |  | 81 | 77 | 0% | 2022-11-30 | 2022-12-07 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  | 40 | [9 empty] | 0 | 0 | 3080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3080 | 0% | 0 | 3282.9618 | 3282.9618 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | 6742 |  |  |  |  | 6742 |  | 3282.9618 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.5 | 2022/23 On-Ice Activities | 1.2.8.5 2022/23 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 9d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.5.7.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.4.1 | 0 | 0 | 3282.9618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.5.7.4.1 | C |  | PSL | PHS: Controls Retrofit (EE) |  | 0% | Labor Hours | EN |  |  | 81 | 115 | 0% | 2022-11-30 | 2022-12-07 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  | 106 | [9 empty] | 0 | 0 | 12190 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12190 | 0% | 0 | 12993.2806 | 12993.2806 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | 3371 |  |  |  |  | 3371 |  | 12993.2806 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.5 | 2022/23 On-Ice Activities | 1.2.8.5 2022/23 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 5d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.5.7.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.4.1 | 0 | 0 | 12993.2806 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.5.7.4.1 | C |  | PSL | PHS: Mechanical Retrofit (EN) |  | 0% | Labor Hours | EN |  |  | 81 | 115 | 0% | 2022-11-30 | 2022-12-07 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  | 32 | [9 empty] | 0 | 0 | 3680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3680 | 0% | 0 | 3922.4998 | 3922.4998 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | 13484 |  |  |  |  | 13484 |  | 3922.4998 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.5 | 2022/23 On-Ice Activities | 1.2.8.5 2022/23 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 10d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.5.7.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.4.1 | 0 | 0 | 3922.4998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.5.7.4.2 | C |  | PSL | PHS: Subsystem Evaluation |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2022-12-08 | 2022-12-08 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  | 16 | [9 empty] | 0 | 0 | 1840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1840 | 0% | 0 | 1961.2499 | 1961.2499 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | 4188 |  |  |  |  | 4188 |  | 1961.2499 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.5 | 2022/23 On-Ice Activities | 1.2.8.5 2022/23 On-Ice Activities | cell-link@smartsheet.com | 2021-11-30 21:37 |  | 9d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.5.7.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.4.2 | 0 | 0 | 1961.2499 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.5.7.4.3 | C |  | PSL | PHS: Install Filtration System |  | 0% | Labor Hours | EN |  |  | 81 | 115 | 0% | 2022-12-05 | 2022-12-07 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  | 48 | [9 empty] | 0 | 0 | 5520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5520 | 0% | 0 | 5883.7497 | 5883.7497 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | 11798 |  |  |  |  | 11798 |  | 5883.7497 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.5 | 2022/23 On-Ice Activities | 1.2.8.5 2022/23 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 9d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.5.7.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.4.3 | 0 | 0 | 5883.7497 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.5.7.5.1 | C |  | PSL | Water Tanks: Retrofit (Railings, Ladders, Vert pumps, Submersible Pumps, Manifolds, etc.) |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2022-12-07 | 2022-12-23 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  | 40 | [9 empty] | 0 | 0 | 4600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4600 | 0% | 0 | 4903.1248 | 4903.1248 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | 4786 |  |  |  |  | 4786 |  | 4903.1248 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.5 | 2022/23 On-Ice Activities | 1.2.8.5 2022/23 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 9d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.5.7.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.5.1 | 0 | 0 | 4903.1248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.5.7.5.1 | C |  | PSL | Water Tanks: Retrofit (Railings, Ladders, Vert pumps, Submersible Pumps, Manifolds, etc.) |  | 0% | Labor Hours | TE |  |  | 81 | 77 | 0% | 2022-12-07 | 2022-12-23 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  | 136 | [9 empty] | 0 | 0 | 10472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10472 | 0% | 0 | 11162.0701 | 11162.0701 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | 13484 |  |  |  |  | 13484 |  | 11162.0701 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.5 | 2022/23 On-Ice Activities | 1.2.8.5 2022/23 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 9d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.5.7.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.5.1 | 0 | 0 | 11162.0701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.5.7.5.2 | C |  | PSL | Water Tank: Subsystem Evaluation |  | 0% | Labor Hours | EN |  |  | 81 | 115 | 0% | 2022-12-23 | 2022-12-23 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  | 16 | [9 empty] | 0 | 0 | 1840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1840 | 0% | 0 | 1961.2499 | 1961.2499 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | 6742 |  |  |  |  | 6742 |  | 1961.2499 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.5 | 2022/23 On-Ice Activities | 1.2.8.5 2022/23 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 6d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.5.7.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.5.2 | 0 | 0 | 1961.2499 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.5.7.6.1 | C |  | PSL | HPP: Mechanical Refit |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2022-11-30 | 2022-12-14 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  | 24 | [9 empty] | 0 | 0 | 2760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2760 | 0% | 0 | 2941.8749 | 2941.8749 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | 4786 |  |  |  |  | 4786 |  | 2941.8749 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.5 | 2022/23 On-Ice Activities | 1.2.8.5 2022/23 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 10d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.5.7.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.6.1 | 0 | 0 | 2941.8749 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.5.7.6.1 | C |  | PSL | HPP: Mechanical Refit |  | 0% | Labor Hours | TE |  |  | 81 | 77 | 0% | 2022-11-30 | 2022-12-14 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  | 96 | [9 empty] | 0 | 0 | 7392 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7392 | 0% | 0 | 7879.1083 | 7879.1083 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | 10113 |  |  |  |  | 10113 |  | 7879.1083 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.5 | 2022/23 On-Ice Activities | 1.2.8.5 2022/23 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 10d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.5.7.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.6.1 | 0 | 0 | 7879.1083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.5.7.6.1 | C |  | PSL | HPP: Controls Retrofit (Sensors, Motor Drives, Air Handling, Etc.) |  | 0% | Labor Hours | EN |  |  | 81 | 115 | 0% | 2022-11-30 | 2022-12-14 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  | 96 | [9 empty] | 0 | 0 | 11040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11040 | 0% | 0 | 11767.4994 | 11767.4994 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | 10113 |  |  |  |  | 10113 |  | 11767.4994 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.5 | 2022/23 On-Ice Activities | 1.2.8.5 2022/23 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 5d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.5.7.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.6.1 | 0 | 0 | 11767.4994 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.5.7.6.1 | C |  | PSL | HPP: Controls Retrofit (Sensors, Motor Drives, Air Handling, Etc.) |  | 0% | Labor Hours | TE |  |  | 81 | 77 | 0% | 2022-11-30 | 2022-12-14 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -6877 |  |  | 16 | [9 empty] | 0 | 0 | 1232 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1232 | 0% | 0 | 1313.1847 | 1313.1847 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 6877 |  |  |  | 6877 |  | 1313.1847 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.5 | 2022/23 On-Ice Activities | 1.2.8.5 2022/23 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.5.7.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.6.1 | 0 | 0 | 1313.1847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.5.7.6.2 | C |  | PSL | HPP: Pump Evaluated |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2022-12-14 | 2022-12-14 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -9763 |  |  | 16 | [9 empty] | 0 | 0 | 1840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1840 | 0% | 0 | 1961.2499 | 1961.2499 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 9763 |  |  |  | 9763 |  | 1961.2499 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.5 | 2022/23 On-Ice Activities | 1.2.8.5 2022/23 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.5.7.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.6.2 | 0 | 0 | 1961.2499 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.5.7.7.1 | C |  | PSL | Shops: Repair/Retrofit Shops, MECC |  | 0% | Labor Hours | TE |  |  | 115 | 77 | 0% | 2022-11-13 | 2023-01-31 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -9763 |  | 16 | 16 | 16 | [8 empty] | 0 | 1232 | 1232 | 1232 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3696 | 0% | 0 | 3939.5542 | 3939.5542 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 9763 |  |  |  | 9763 |  | 3939.5542 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.5 | 2022/23 On-Ice Activities | 1.2.8.5 2022/23 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.5.7.7.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.7.1 | 0 | 1313.1847 | 1313.1847 | 1313.1847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.7.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.7.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.7.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.7.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.7.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.7.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.5.7.7.1 | C |  | PSL | Shops: Repair/Retrofit SHOP |  | 0% | Labor Hours | EN |  |  | 81 | 115 | 0% | 2022-11-13 | 2023-01-31 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -6877 |  | 16 | 16 | 16 | [8 empty] | 0 | 1840 | 1840 | 1840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5520 | 0% | 0 | 5883.7497 | 5883.7497 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 6877 |  |  |  | 6877 |  | 5883.7497 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.5 | 2022/23 On-Ice Activities | 1.2.8.5 2022/23 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.5.7.7.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.7.1 | 0 | 1961.2499 | 1961.2499 | 1961.2499 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.7.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.7.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.7.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.7.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.7.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.7.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.5.7.7.1 | C |  | PSL | Shops: Repair/Retrofit Shops, SEW |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2022-11-13 | 2023-01-31 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -1953 |  |  | 8 | 8 | [8 empty] | 0 | 0 | 920 | 920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1840 | 0% | 0 | 1961.2499 | 1961.2499 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 1953 |  |  |  | 1953 |  | 1961.2499 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.5 | 2022/23 On-Ice Activities | 1.2.8.5 2022/23 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.5.7.7.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.7.1 | 0 | 0 | 980.625 | 980.625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.7.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.7.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.7.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.7.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.7.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.7.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.5.7.7.1 | C |  | PSL | Shops: Repair/Retrofit Shops, OML |  | 0% | Labor Hours | EN |  |  | 81 | 115 | 0% | 2022-11-13 | 2023-01-31 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -1375 |  |  | 8 | [9 empty] | 0 | 0 | 920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 920 | 0% | 0 | 980.625 | 980.625 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 1375 |  |  |  | 1375 |  | 980.625 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.5 | 2022/23 On-Ice Activities | 1.2.8.5 2022/23 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.5.7.7.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.7.1 | 0 | 0 | 980.625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.7.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.7.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.7.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.7.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.7.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.7.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.5.7.8.1 | C |  | PSL | TOS/Towers: Repair/Retrofit |  | 0% | Labor Hours | TE |  |  | 115 | 77 | 0% | 2022-12-22 | 2023-01-20 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  | 64 | 64 | [8 empty] | 0 | 0 | 4928 | 4928 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9856 | 0% | 0 | 10505.4778 | 10505.4778 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | 3829 |  |  |  |  | 3829 |  | 10505.4778 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.5 | 2022/23 On-Ice Activities | 1.2.8.5 2022/23 On-Ice Activities | cell-link@smartsheet.com | 2021-12-02 13:46 |  | 4d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.5.7.8.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.8.1 | 0 | 0 | 5252.7389 | 5252.7389 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.8.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.8.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.8.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.8.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.8.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.8.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.5.7.8.1 | C |  | PSL | TOS/Towers: Repair/Retrofit Controls (EE) |  | 0% | Labor Hours | EN |  |  | 81 | 115 | 0% | 2022-12-22 | 2023-01-20 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  | 392 | 392 | [8 empty] | 0 | 0 | 45080 | 45080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90160 | 0% | 0 | 96101.2454 | 96101.2454 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | 2697 |  |  |  |  | 2697 |  | 96101.2454 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.5 | 2022/23 On-Ice Activities | 1.2.8.5 2022/23 On-Ice Activities | cell-link@smartsheet.com | 2021-12-02 13:46 |  | 4d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.5.7.8.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.8.1 | 0 | 0 | 48050.6227 | 48050.6227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.8.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.8.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.8.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.8.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.8.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.8.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.5.7.8.1 | C |  | PSL | TOS/Towers: Repair/Retrofit Mechanical (ME) |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2022-12-22 | 2023-01-20 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  | 32 | 32 | [8 empty] | 0 | 0 | 3680 | 3680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7360 | 0% | 0 | 7844.9996 | 7844.9996 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | 3829 |  |  |  |  | 3829 |  | 7844.9996 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.5 | 2022/23 On-Ice Activities | 1.2.8.5 2022/23 On-Ice Activities | cell-link@smartsheet.com | 2021-12-02 13:46 |  | 4d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.5.7.8.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.8.1 | 0 | 0 | 3922.4998 | 3922.4998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.8.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.8.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.8.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.8.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.8.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.8.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.5.7.8.1 | C |  | PSL | TOS/Towers: Inspect/Test Controls (EE) |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2022-12-22 | 2023-01-20 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  | 8 | 16 | [8 empty] | 0 | 0 | 920 | 1840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2760 | 0% | 0 | 2941.8749 | 2941.8749 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | 3829 |  |  |  |  | 3829 |  | 2941.8749 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.5 | 2022/23 On-Ice Activities | 1.2.8.5 2022/23 On-Ice Activities | cell-link@smartsheet.com | 2021-12-02 13:46 |  | 5d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.5.7.8.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.8.1 | 0 | 0 | 980.625 | 1961.2499 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.8.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.8.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.8.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.8.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.8.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.8.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.5.7.8.1 | C |  | PSL | TOS/Towers: Inspect/Test Mechanical Systems (ME) |  | 0% | Labor Hours | EN |  |  | 81 | 115 | 0% | 2022-12-22 | 2023-01-20 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  | 8 | 8 | [8 empty] | 0 | 0 | 920 | 920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1840 | 0% | 0 | 1961.2499 | 1961.2499 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | 5393 |  |  |  |  | 5393 |  | 1961.2499 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.5 | 2022/23 On-Ice Activities | 1.2.8.5 2022/23 On-Ice Activities | cell-link@smartsheet.com | 2021-12-02 13:46 |  | 5d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.5.7.8.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.8.1 | 0 | 0 | 980.625 | 980.625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.8.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.8.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.8.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.8.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.8.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.8.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.5.7.9.1 | C |  | PSL | MSHR: Repair/Replace Components, Energize & Test (EE) |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2022-12-07 | 2022-12-21 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  | 48 | [9 empty] | 0 | 0 | 5520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5520 | 0% | 0 | 5883.7497 | 5883.7497 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | 3829 |  |  |  |  | 3829 |  | 5883.7497 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.5 | 2022/23 On-Ice Activities | 1.2.8.5 2022/23 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 5d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.5.7.9.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.9.1 | 0 | 0 | 5883.7497 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.9.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.9.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.9.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.9.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.9.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.9.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.5.7.9.1 | C |  | PSL | MSHR:Repair/Replace Components, Energize & Test |  | 0% | Labor Hours | TE |  |  | 115 | 77 | 0% | 2022-12-07 | 2022-12-21 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  | 56 | [9 empty] | 0 | 0 | 4312 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4312 | 0% | 0 | 4596.1465 | 4596.1465 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | 3829 |  |  |  |  | 3829 |  | 4596.1465 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.5 | 2022/23 On-Ice Activities | 1.2.8.5 2022/23 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 5d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.5.7.9.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.9.1 | 0 | 0 | 4596.1465 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.9.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.9.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.9.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.9.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.9.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.9.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.5.7.9.1 | C |  | PSL | MSHR: Repair/Replace Components, Energize & Test (ME) |  | 0% | Labor Hours | EN |  |  |  | 115 | 0% | 2022-12-07 | 2022-12-21 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  | 24 | [9 empty] | 0 | 0 | 2760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2760 | 0% | 0 | 2941.8749 | 2941.8749 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | [9 empty] | 2941.8749 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.5 | 2022/23 On-Ice Activities | 1.2.8.5 2022/23 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 5d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.5.7.9.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.9.1 | 0 | 0 | 2941.8749 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.9.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.9.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.9.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.9.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.9.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.9.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.5.7.10.1 | C |  | PSL | RWCR: Integrate & Test (EE) |  | 0% | Labor Hours | EN |  |  | 81 | 115 | 0% | 2022-12-07 | 2022-12-21 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  | 8 | [9 empty] | 0 | 0 | 920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 920 | 0% | 0 | 980.625 | 980.625 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | 6742 |  |  |  |  | 6742 |  | 980.625 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.5 | 2022/23 On-Ice Activities | 1.2.8.5 2022/23 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 5d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.5.7.10.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.10.1 | 0 | 0 | 980.625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.10.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.10.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.10.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.10.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.10.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.10.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.5.7.10.1 | C |  | PSL | RWCR: Integrate & Test (TE) |  | 0% | Labor Hours | TE |  |  | 115 | 77 | 0% | 2022-12-07 | 2022-12-21 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -9763 |  |  | 8 | [9 empty] | 0 | 0 | 616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 616 | 0% | 0 | 656.5924 | 656.5924 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 9763 |  |  |  | 9763 |  | 656.5924 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.5 | 2022/23 On-Ice Activities | 1.2.8.5 2022/23 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.5.7.10.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.10.1 | 0 | 0 | 656.5924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.10.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.10.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.10.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.10.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.10.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.10.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.5.7.11.1 | C |  | PSL | Winches/Reels: Repair/Retrofit Winches & Reels (EE) |  | 0% | Labor Hours | EN |  |  | 81 | 115 | 0% | 2022-12-22 | 2022-12-29 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -6877 |  |  | 48 | [9 empty] | 0 | 0 | 5520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5520 | 0% | 0 | 5883.7497 | 5883.7497 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 6877 |  |  |  | 6877 |  | 5883.7497 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.5 | 2022/23 On-Ice Activities | 1.2.8.5 2022/23 On-Ice Activities | cell-link@smartsheet.com | 2021-12-02 13:46 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.5.7.11.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.11.1 | 0 | 0 | 5883.7497 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.11.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.11.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.11.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.11.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.11.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.11.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.5.7.11.1 | C |  | PSL | Winches/Reels: Repair/Retrofit Winches & Reels (TE) |  | 0% | Labor Hours | TE |  |  | 115 | 77 | 0% | 2022-12-22 | 2022-12-29 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -1953 |  |  | 48 | [9 empty] | 0 | 0 | 3696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3696 | 0% | 0 | 3939.5542 | 3939.5542 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 1953 |  |  |  | 1953 |  | 3939.5542 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.5 | 2022/23 On-Ice Activities | 1.2.8.5 2022/23 On-Ice Activities | cell-link@smartsheet.com | 2021-12-02 13:46 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.5.7.11.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.11.1 | 0 | 0 | 3939.5542 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.11.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.11.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.11.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.11.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.11.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.11.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.5.7.11.1 | C |  | PSL | Winches/Reels: Repair/Retrofit Winches & Reels (ME) |  | 0% | Labor Hours | EN |  |  |  | 115 | 0% | 2022-12-22 | 2022-12-29 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  | 8 | [9 empty] | 0 | 0 | 920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 920 | 0% | 0 | 980.625 | 980.625 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | [9 empty] | 980.625 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.5 | 2022/23 On-Ice Activities | 1.2.8.5 2022/23 On-Ice Activities | cell-link@smartsheet.com | 2021-12-02 13:46 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.5.7.11.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.11.1 | 0 | 0 | 980.625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.11.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.11.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.11.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.11.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.11.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.11.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.5.7.12.1 | C |  | PSL | Hoses/Cables/Etc.: Inventory & Repair |  | 0% | Labor Hours | TE |  |  | 81 | 77 | 0% | 2022-12-30 | 2023-01-30 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -1375 |  |  |  | 40 | 40 | [7 empty] | 0 | 0 | 0 | 3080 | 3080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6160 | 0% | 0 | 6565.9236 | 6565.9236 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 1375 |  |  |  | 1375 |  | 6565.9236 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.5 | 2022/23 On-Ice Activities | 1.2.8.5 2022/23 On-Ice Activities | cell-link@smartsheet.com | 2021-12-02 13:46 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.5.7.12.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.12.1 | 0 | 0 | 0 | 3282.9618 | 3282.9618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.12.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.12.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.12.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.12.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.12.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.12.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.5.7.13.1 | C |  | PSL | IFD: Repair/Refit/Test (TE w/ ASC Electrician Support) |  | 0% | Labor Hours | TE |  |  | 115 | 77 | 0% | 2022-12-14 | 2022-12-28 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  | 16 | [9 empty] | 0 | 0 | 1232 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1232 | 0% | 0 | 1313.1847 | 1313.1847 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | 3829 |  |  |  |  | 3829 |  | 1313.1847 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.5 | 2022/23 On-Ice Activities | 1.2.8.5 2022/23 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 4d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.5.7.13.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.13.1 | 0 | 0 | 1313.1847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.13.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.13.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.13.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.13.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.13.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.13.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.5.7.13.1 | C |  | PSL | IFD: Repair/Refit/Test (ME) |  | 0% | Labor Hours | TE |  |  | 81 | 77 | 0% | 2022-12-14 | 2022-12-28 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  | 32 | [9 empty] | 0 | 0 | 2464 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2464 | 0% | 0 | 2626.3694 | 2626.3694 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | 2697 |  |  |  |  | 2697 |  | 2626.3694 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.5 | 2022/23 On-Ice Activities | 1.2.8.5 2022/23 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 4d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.5.7.13.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.13.1 | 0 | 0 | 2626.3694 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.13.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.13.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.13.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.13.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.13.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.13.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.5.7.13.1 | C |  | PSL | IFD: Repair/Refit/Test (EE) |  | 0% | Labor Hours | TE |  |  |  | 77 | 0% | 2022-12-14 | 2022-12-28 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  | 32 | [9 empty] | 0 | 0 | 2464 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2464 | 0% | 0 | 2626.3694 | 2626.3694 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | [9 empty] | 2626.3694 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.5 | 2022/23 On-Ice Activities | 1.2.8.5 2022/23 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 4d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.5.7.13.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.13.1 | 0 | 0 | 2626.3694 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.13.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.13.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.13.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.13.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.13.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.13.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.5.7.14.1 | C |  | PSL | ARA Drill: Repair and Upgrade ARA Drill (EE) |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2023-01-03 | 2023-01-16 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  |  | 80 | [8 empty] | 0 | 0 | 0 | 9200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9200 | 0% | 0 | 9806.2495 | 9806.2495 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | 3829 |  |  |  |  | 3829 |  | 9806.2495 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.5 | 2022/23 On-Ice Activities | 1.2.8.5 2022/23 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 4d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.5.7.14.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.14.1 | 0 | 0 | 0 | 9806.2495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.14.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.14.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.14.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.14.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.14.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.14.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.5.7.14.1 | C |  | PSL | ARA Drill: Repair and Upgrade ARA Drill (TE) |  | 0% | Labor Hours | TE |  |  | 115 | 77 | 0% | 2023-01-03 | 2023-01-16 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  |  | 48 | [8 empty] | 0 | 0 | 0 | 3696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3696 | 0% | 0 | 3939.5542 | 3939.5542 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | 3829 |  |  |  |  | 3829 |  | 3939.5542 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.5 | 2022/23 On-Ice Activities | 1.2.8.5 2022/23 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 5d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.5.7.14.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.14.1 | 0 | 0 | 0 | 3939.5542 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.14.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.14.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.14.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.14.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.14.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.14.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.5.7.14.1 | C |  | PSL | ARA Drill: Repair and Upgrade ARA Drill (ME) |  | 0% | Labor Hours | EN |  |  |  | 115 | 0% | 2023-01-03 | 2023-01-16 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  |  | 96 | [8 empty] | 0 | 0 | 0 | 11040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11040 | 0% | 0 | 11767.4994 | 11767.4994 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | [9 empty] | 11767.4994 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.5 | 2022/23 On-Ice Activities | 1.2.8.5 2022/23 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 4d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.5.7.14.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.14.1 | 0 | 0 | 0 | 11767.4994 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.14.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.14.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.14.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.14.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.14.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.14.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.5.7.14.2 | C |  | PSL | ARA Drill: Preliminary Integration (EE) |  | 0% | Labor Hours | EN |  |  | 81 | 115 | 0% | 2023-01-12 | 2023-01-16 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  |  | 8 | [8 empty] | 0 | 0 | 0 | 920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 920 | 0% | 0 | 980.625 | 980.625 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | 5393 |  |  |  |  | 5393 |  | 980.625 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.5 | 2022/23 On-Ice Activities | 1.2.8.5 2022/23 On-Ice Activities | cell-link@smartsheet.com | 2021-11-30 21:37 |  | 5d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.5.7.14.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.14.2 | 0 | 0 | 0 | 980.625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.14.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.14.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.14.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.14.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.14.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.14.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.5.7.14.2 | C |  | PSL | ARA Drill: Preliminary Integration (TE) |  | 0% | Labor Hours | TE |  |  | 115 | 77 | 0% | 2023-01-12 | 2023-01-16 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  |  | 8 | [8 empty] | 0 | 0 | 0 | 616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 616 | 0% | 0 | 656.5924 | 656.5924 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | 3829 |  |  |  |  | 3829 |  | 656.5924 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.5 | 2022/23 On-Ice Activities | 1.2.8.5 2022/23 On-Ice Activities | cell-link@smartsheet.com | 2021-11-30 21:37 |  | 5d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.5.7.14.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.14.2 | 0 | 0 | 0 | 656.5924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.14.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.14.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.14.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.14.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.14.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.14.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.5.7.14.2 | C |  | PSL | ARA Drill: Preliminary Integration (ME) |  | 0% | Labor Hours | EN |  |  |  | 115 | 0% | 2023-01-12 | 2023-01-16 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  |  | 8 | [8 empty] | 0 | 0 | 0 | 920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 920 | 0% | 0 | 980.625 | 980.625 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | [9 empty] | 980.625 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.5 | 2022/23 On-Ice Activities | 1.2.8.5 2022/23 On-Ice Activities | cell-link@smartsheet.com | 2021-11-30 21:37 |  | 5d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.5.7.14.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.14.2 | 0 | 0 | 0 | 980.625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.14.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.14.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.14.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.14.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.14.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.14.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.5.7.14.3 | C |  | PSL | ARA Drill: Winterize & Store ARA Drill |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2023-01-17 | 2023-01-20 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  |  | 32 | [8 empty] | 0 | 0 | 0 | 3680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3680 | 0% | 0 | 3922.4998 | 3922.4998 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | 3829 |  |  |  |  | 3829 |  | 3922.4998 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.5 | 2022/23 On-Ice Activities | 1.2.8.5 2022/23 On-Ice Activities | cell-link@smartsheet.com | 2021-11-30 21:37 |  | 5d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.5.7.14.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.14.3 | 0 | 0 | 0 | 3922.4998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.14.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.14.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.14.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.14.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.14.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.7.14.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.5.8.1 | C |  | PSL | Close-out: Document, Photograph Equip & Upgrade Work, Further Req's |  | 0% | Labor Hours | TE |  |  | 115 | 77 | 0% | 2023-01-23 | 2023-01-26 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  |  | 120 | [8 empty] | 0 | 0 | 0 | 9240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9240 | 0% | 0 | 9848.8854 | 9848.8854 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | 3829 |  |  |  |  | 3829 |  | 9848.8854 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.5 | 2022/23 On-Ice Activities | 1.2.8.5 2022/23 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 4d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.5.8.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.8.1 | 0 | 0 | 0 | 9848.8854 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.8.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.8.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.8.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.8.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.8.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.8.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.5.8.2 | C |  | PSL | Winterize/Close/Store all EHWD Equipment |  | 0% | Labor Hours | TE |  |  | 115 | 77 | 0% | 2023-01-27 | 2023-02-01 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  |  | 44 | 40 | [7 empty] | 0 | 0 | 0 | 3388 | 3080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6468 | 0% | 0 | 6894.2198 | 6894.2198 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | 3829 |  |  |  |  | 3829 |  | 6894.2198 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.5 | 2022/23 On-Ice Activities | 1.2.8.5 2022/23 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 5d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.5.8.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.8.2 | 0 | 0 | 0 | 3611.258 | 3282.9618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.8.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.8.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.8.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.8.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.8.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.8.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.5.8.3 | C |  | PSL | Retro all components, crate, pack and deliver to cargo |  | 0% | Labor Hours | TE |  |  | 81 | 77 | 0% | 2023-01-24 | 2023-02-01 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  |  |  | 32 | [7 empty] | 0 | 0 | 0 | 0 | 2464 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2464 | 0% | 0 | 2626.3694 | 2626.3694 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | 5393 |  |  |  |  | 5393 |  | 2626.3694 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.5 | 2022/23 On-Ice Activities | 1.2.8.5 2022/23 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 5d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.5.8.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.8.3 | 0 | 0 | 0 | 0 | 2626.3694 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.8.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.8.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.8.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.8.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.8.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.8.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.5.9.1 | C |  | PSL | MCM Logistics Rep (driller) |  | 0% | Labor Hours | TE |  |  | 115 | 77 | 0% | 2022-10-25 | 2022-11-17 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  | 144 | [10 empty] | 0 | 11088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11088 | 0% | 0 | 11818.6625 | 11818.6625 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | 3829 |  |  |  |  | 3829 |  | 11818.6625 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.5 | 2022/23 On-Ice Activities | 1.2.8.5 2022/23 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 5d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.5.9.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.9.1 | 0 | 11818.6625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.9.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.9.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.9.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.9.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.9.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.9.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.5.10 | C |  | PSL | END NPX 2022/23 Season |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2023-02-05 | 2023-02-05 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | 3829 |  |  |  |  | 3829 |  | 0 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.5 | 2022/23 On-Ice Activities | 1.2.8.5 2022/23 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 5d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.5.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.5.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.6.1 | C |  | PSL | START NPX 2023/24 Season - Team Arrives [Comm/WTst/FirnDr] |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2023-11-11 | 2023-11-11 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -1953 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 1953 |  |  |  | 1953 |  | 0 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.6 | 2023/24 On-Ice Activities | 1.2.8.6 2023/24 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 3d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.6.2 | C |  | PSL | Deployment Travel & PQ Costs (23/24) Team (14) |  | 0% | Labor Hours | TE |  |  | 81 | 77 | 0% | 2023-07-01 | 2024-02-05 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -6877 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 6877 |  |  |  | 6877 |  | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.6 | 2023/24 On-Ice Activities | 1.2.8.6 2023/24 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 3d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.6.2 | C |  | PSL | Deployment Travel & PQ Costs (23/24) (Driller_PSL_Lead) |  | 0% | Labor Hours | EN |  |  |  | 115 | 0% | 2023-07-01 | 2024-02-05 |  |  |  | 1 (Drill Leads), 5 days deployment travel 3 days redeployment | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  | 40 |  |  | 24 | [7 empty] | 0 | 4600 | 0 | 0 | 2760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7360 | 0% | 0 | 8013.6671 | 8013.6671 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | [9 empty] | 8013.6671 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.6 | 2023/24 On-Ice Activities | 1.2.8.6 2023/24 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 96d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.2 | 0 | 5008.5419 | 0 | 0 | 3005.1252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.6.2 | C |  | PSL | Deployment Travel & PQ Costs (23/24) (PSL_Direct_Hire) |  | 0% | Labor Hours | TE |  |  |  | 77 | 0% | 2023-07-01 | 2024-02-05 |  |  |  | 4 (PSL Direct Hire), 5 days deployment travel 3 days redeployment | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  | 160 |  |  | 96 | [7 empty] | 0 | 12320 | 0 | 0 | 7392 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19712 | 0% | 0 | 21462.6911 | 21462.6911 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | [9 empty] | 21462.6911 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.6 | 2023/24 On-Ice Activities | 1.2.8.6 2023/24 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.2 | 0 | 13414.1819 | 0 | 0 | 8048.5091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.6.2 | C |  | PSL | Deployment Travel & PQ Costs (23/24) (PSL_Engineer) |  | 0% | Labor Hours | EN |  |  |  | 115 | 0% | 2023-07-01 | 2024-02-05 |  |  |  | 10 (PSL Engineers), 5 days deployment travel 3 days redeployment | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  | 400 |  |  | 240 | [7 empty] | 0 | 46000 | 0 | 0 | 27600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73600 | 0% | 0 | 80136.6712 | 80136.6712 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | [9 empty] | 80136.6712 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.6 | 2023/24 On-Ice Activities | 1.2.8.6 2023/24 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 96d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.2 | 0 | 50085.4195 | 0 | 0 | 30051.2517 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.6.2 | C |  | PSL | Deployment Travel & PQ Costs (23/24) |  |  | M & S |  |  |  |  | 1 | 0% | 2023-07-01 | 2024-02-05 |  |  |  | 16 - PQ's @ $950/each (anticipated cost) - 1 Alternate and 1 PSL Rotator | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [9 empty] | 7600 | 7600 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7600 | 7600 | 0 | 15200 | 53% | 8056 | 23256 | 23256 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 23256 | M & S | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.6 | 2023/24 On-Ice Activities | 1.2.8.6 2023/24 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 96d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11628 | 11628 | 0 | 1.2.8.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.6.2 | C |  | PSL | Deployment Travel & PQ Costs (23/24) |  |  | Travel |  |  |  |  | 1 | 0% | 2023-07-01 | 2024-02-05 |  |  |  | 15 - Deploy travel costs 1 PSL rotator | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [10 empty] | 24000 | 24000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24000 | 24000 | 48000 | 53% | 25440 | 73440 | 73440 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 73440 | Travel | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.6 | 2023/24 On-Ice Activities | 1.2.8.6 2023/24 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 96d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36720 | 36720 | 1.2.8.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.6.5.1 | C |  | PSL | SES: Fuel Tower: Connect, Test and Make Ready |  | 0% | Labor Hours | TE |  |  | 115 | 77 | 0% | 2023-11-21 | 2023-11-22 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -3905 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  | 32 | [10 empty] | 0 | 2464 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2464 | 0% | 0 | 2682.8364 | 2682.8364 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 3905 |  |  |  | 3905 |  | 2682.8364 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.6 | 2023/24 On-Ice Activities | 1.2.8.6 2023/24 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 3d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.6.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.5.1 | 0 | 2682.8364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.6.5.2 | C |  | PSL | SES: Make Ready all SES Modules (DCC, PHS, MHPs, MECC, WTs, All) |  | 0% | Labor Hours | TE |  |  | 115 | 77 | 0% | 2023-11-14 | 2023-11-24 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -976 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  | 48 | [10 empty] | 0 | 3696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3696 | 0% | 0 | 4024.2546 | 4024.2546 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 976 |  |  |  | 976 |  | 4024.2546 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.6 | 2023/24 On-Ice Activities | 1.2.8.6 2023/24 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 3d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.6.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.5.2 | 0 | 4024.2546 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.6.5.3 | C |  | PSL | SES: Furnace Checkout & Fire Up (All modules) |  | 0% | Labor Hours | EN |  |  | 81 | 115 | 0% | 2023-11-14 | 2023-11-16 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -3438 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  | 32 | [10 empty] | 0 | 3680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3680 | 0% | 0 | 4006.8336 | 4006.8336 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 3438 |  |  |  | 3438 |  | 4006.8336 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.6 | 2023/24 On-Ice Activities | 1.2.8.6 2023/24 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 3d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.6.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.5.3 | 0 | 4006.8336 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.6.5.4 | C |  | PSL | SES: Perform Emergency Incident Drill & Safety Training |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2023-12-08 | 2023-12-11 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -1953 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  | 112 | [9 empty] | 0 | 0 | 12880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12880 | 0% | 0 | 14023.9175 | 14023.9175 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 1953 |  |  |  | 1953 |  | 14023.9175 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.6 | 2023/24 On-Ice Activities | 1.2.8.6 2023/24 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 3d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.6.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.5.4 | 0 | 0 | 14023.9175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.6.5.5 | C |  | PSL | SES: Maintenance Activities |  | 0% | Labor Hours | TE |  |  | 115 | 77 | 0% | 2023-11-15 | 2024-01-31 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -2929 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  | 56 | 56 | [9 empty] | 0 | 4312 | 4312 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8624 | 0% | 0 | 9389.9273 | 9389.9273 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 2929 |  |  |  | 2929 |  | 9389.9273 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.6 | 2023/24 On-Ice Activities | 1.2.8.6 2023/24 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 4d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.6.5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.5.5 | 0 | 4694.9637 | 4694.9637 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.6.5.6 | C |  | PSL | SES: Site Snow Removal |  | 0% | Labor Hours | TE |  |  | 81 | 77 | 0% | 2023-11-15 | 2024-01-31 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -2063 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  | 96 | [9 empty] | 0 | 0 | 7392 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7392 | 0% | 0 | 8048.5091 | 8048.5091 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 2063 |  |  |  | 2063 |  | 8048.5091 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.6 | 2023/24 On-Ice Activities | 1.2.8.6 2023/24 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 4d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.6.5.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.5.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.5.6 | 0 | 0 | 8048.5091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.5.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.5.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.5.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.5.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.5.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.6.6.1 | C |  | PSL | Generators/PDM: Charge Generator Batteries |  | 0% | Labor Hours | EN |  |  | 81 | 115 | 0% | 2023-11-21 | 2023-11-29 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -20630 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  | 1 | [10 empty] | 0 | 115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115 | 0% | 0 | 125.2135 | 125.2135 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 20630 |  |  |  | 20630 |  | 125.2135 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.6 | 2023/24 On-Ice Activities | 1.2.8.6 2023/24 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 14d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.6.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.6.1 | 0 | 125.2135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.6.6.2 | C |  | PSL | Generators/PDM: Prime/Commission Fuel System |  | 0% | Labor Hours | EN |  |  | 81 | 115 | 0% | 2023-11-21 | 2023-11-29 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -13753 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  | 24 | [10 empty] | 0 | 2760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2760 | 0% | 0 | 3005.1252 | 3005.1252 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 13753 |  |  |  | 13753 |  | 3005.1252 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.6 | 2023/24 On-Ice Activities | 1.2.8.6 2023/24 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 9d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.6.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.6.2 | 0 | 3005.1252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.6.6.3 | C |  | PSL | Generators/PDM: GEN-1, 2, 3 - Install GEN hoods |  | 0% | Labor Hours | EN |  |  | 81 | 115 | 0% | 2024-01-05 | 2024-01-11 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -6877 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  | 96 | [10 empty] | 0 | 11040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11040 | 0% | 0 | 12020.5007 | 12020.5007 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 6877 |  |  |  | 6877 |  | 12020.5007 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.6 | 2023/24 On-Ice Activities | 1.2.8.6 2023/24 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 10d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.6.6.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.6.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.6.3 | 0 | 12020.5007 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.6.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.6.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.6.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.6.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.6.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.6.6.4 | C |  | PSL | GEN-1, 2, 3, PDM - Repairs & Tests w/Contract Tech Support |  | 0% | Labor Hours | EN |  |  |  | 115 | 0% | 2023-11-20 | 2023-12-13 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  | 96 | 48 | [9 empty] | 0 | 11040 | 5520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16560 | 0% | 0 | 18030.751 | 18030.751 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | [9 empty] | 18030.751 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.6 | 2023/24 On-Ice Activities | 1.2.8.6 2023/24 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 5d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.6.6.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.6.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.6.4 | 0 | 12020.5007 | 6010.2503 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.6.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.6.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.6.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.6.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.6.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.6.6.5 | C |  | PSL | Generator & PDM: Commission & Final Testing |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2023-12-12 | 2023-12-13 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -2929 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  | 32 | [9 empty] | 0 | 0 | 3680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3680 | 0% | 0 | 4006.8336 | 4006.8336 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 2929 |  |  |  | 2929 |  | 4006.8336 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.6 | 2023/24 On-Ice Activities | 1.2.8.6 2023/24 On-Ice Activities | cell-link@smartsheet.com | 2021-11-30 21:59 |  | 5d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.6.6.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.6.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.6.5 | 0 | 0 | 4006.8336 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.6.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.6.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.6.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.6.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.6.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.6.6.7 | C |  | PSL | Generators/PDM: Change from Temporary Power to IceCube Grid |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2023-12-15 | 2023-12-18 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -2929 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  | 8 | [9 empty] | 0 | 0 | 920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 920 | 0% | 0 | 1001.7084 | 1001.7084 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 2929 |  |  |  | 2929 |  | 1001.7084 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.6 | 2023/24 On-Ice Activities | 1.2.8.6 2023/24 On-Ice Activities | cell-link@smartsheet.com | 2021-11-30 21:59 |  | 3d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.6.6.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.6.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.6.7 | 0 | 0 | 1001.7084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.6.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.6.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.6.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.6.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.6.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.6.7.1.1 | C |  | PSL | DCC: Install Racks, Networks, Computers |  | 0% | Labor Hours | TE |  |  | 81 | 77 | 0% | 2023-11-23 | 2023-11-28 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -2063 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  | 32 | [10 empty] | 0 | 2464 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2464 | 0% | 0 | 2682.8364 | 2682.8364 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 2063 |  |  |  | 2063 |  | 2682.8364 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.6 | 2023/24 On-Ice Activities | 1.2.8.6 2023/24 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 3d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.6.7.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.1.1 | 0 | 2682.8364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.6.7.2.1 | C |  | PSL | MHP: Final Upgrade & Replacement Activities |  | 0% | Labor Hours | EN |  |  | 81 | 115 | 0% | 2023-11-17 | 2023-11-24 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -6877 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  | 64 | [10 empty] | 0 | 7360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7360 | 0% | 0 | 8013.6671 | 8013.6671 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 6877 |  |  |  | 6877 |  | 8013.6671 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.6 | 2023/24 On-Ice Activities | 1.2.8.6 2023/24 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 10d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.6.7.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.2.1 | 0 | 8013.6671 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.6.7.2.2 | C |  | PSL | MHP: Final Testing |  | 0% | Labor Hours | TE |  |  | 81 | 77 | 0% | 2023-11-24 | 2023-11-30 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -3438 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  | 32 | [10 empty] | 0 | 2464 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2464 | 0% | 0 | 2682.8364 | 2682.8364 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 3438 |  |  |  | 3438 |  | 2682.8364 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.6 | 2023/24 On-Ice Activities | 1.2.8.6 2023/24 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 6d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.6.7.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.2.2 | 0 | 2682.8364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.6.7.3.1 | C |  | PSL | PHS: Install Filters in H2O System |  | 0% | Labor Hours | TE |  |  | 115 | 77 | 0% | 2023-11-24 | 2023-11-27 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -4882 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  | 4 | [10 empty] | 0 | 308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 308 | 0% | 0 | 335.3545 | 335.3545 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 4882 |  |  |  | 4882 |  | 335.3545 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.6 | 2023/24 On-Ice Activities | 1.2.8.6 2023/24 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 9d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.6.7.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.3.1 | 0 | 335.3545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.6.7.3.2 | C |  | PSL | PHS: Final Upgrade & Replacement Activities |  | 0% | Labor Hours | TE |  |  | 81 | 77 | 0% | 2023-11-17 | 2023-11-24 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -13753 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  | 32 | [10 empty] | 0 | 2464 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2464 | 0% | 0 | 2682.8364 | 2682.8364 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 13753 |  |  |  | 13753 |  | 2682.8364 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.6 | 2023/24 On-Ice Activities | 1.2.8.6 2023/24 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 9d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.6.7.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.3.2 | 0 | 2682.8364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.6.7.3.3 | C |  | PSL | PHS: Final Testing |  | 0% | Labor Hours | EN |  |  | 81 | 115 | 0% | 2023-11-24 | 2023-11-30 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -6877 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  | 32 | [10 empty] | 0 | 3680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3680 | 0% | 0 | 4006.8336 | 4006.8336 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 6877 |  |  |  | 6877 |  | 4006.8336 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.6 | 2023/24 On-Ice Activities | 1.2.8.6 2023/24 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 5d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.6.7.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.3.3 | 0 | 4006.8336 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.6.7.4.1 | C |  | PSL | Water Tanks: Install Railings, Ladders, Pumps, Plumbing, Doghouses - Final Upgrades |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2023-11-17 | 2023-11-24 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -4882 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  | 40 | [10 empty] | 0 | 4600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4600 | 0% | 0 | 5008.5419 | 5008.5419 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 4882 |  |  |  | 4882 |  | 5008.5419 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.6 | 2023/24 On-Ice Activities | 1.2.8.6 2023/24 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 5d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.6.7.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.4.1 | 0 | 5008.5419 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.6.7.4.1 | C |  | PSL | Water Tanks: Install Railings, Ladders, Pumps, Plumbing, Doghouses - Final Upgrades |  | 0% | Labor Hours | TE |  |  |  | 77 | 0% | 2023-11-17 | 2023-11-24 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  | 136 | [10 empty] | 0 | 10472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10472 | 0% | 0 | 11402.0546 | 11402.0546 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | [9 empty] | 11402.0546 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.6 | 2023/24 On-Ice Activities | 1.2.8.6 2023/24 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 5d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.6.7.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.4.1 | 0 | 11402.0546 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.6.7.4.2 | C |  | PSL | Water Tanks: Integrate, Verify, Test |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2023-11-24 | 2023-11-30 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -4882 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  | 64 | [10 empty] | 0 | 7360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7360 | 0% | 0 | 8013.6671 | 8013.6671 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 4882 |  |  |  | 4882 |  | 8013.6671 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.6 | 2023/24 On-Ice Activities | 1.2.8.6 2023/24 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 5d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.6.7.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.4.2 | 0 | 8013.6671 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.6.7.5.1 | C |  | PSL | HPP: Final Upgrade & Replacement Activities |  | 0% | Labor Hours | TE |  |  | 81 | 77 | 0% | 2023-11-17 | 2023-11-24 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -10315 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  | 32 | [10 empty] | 0 | 2464 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2464 | 0% | 0 | 2682.8364 | 2682.8364 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 10315 |  |  |  | 10315 |  | 2682.8364 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.6 | 2023/24 On-Ice Activities | 1.2.8.6 2023/24 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 47d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.6.7.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.5.1 | 0 | 2682.8364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.6.7.5.2 | C |  | PSL | HPP: Pump Testing |  | 0% | Labor Hours | EN |  |  | 81 | 115 | 0% | 2023-11-24 | 2023-11-30 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -6877 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  | 32 | [10 empty] | 0 | 3680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3680 | 0% | 0 | 4006.8336 | 4006.8336 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 6877 |  |  |  | 6877 |  | 4006.8336 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.6 | 2023/24 On-Ice Activities | 1.2.8.6 2023/24 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.6.7.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.5.2 | 0 | 4006.8336 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.6.7.6.1 | C |  | PSL | Shops: Final Upgrade/Retrofit Shops, MECC |  | 0% | Labor Hours | TE |  |  | 115 | 77 | 0% | 2023-11-14 | 2023-11-21 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -976 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  | 8 | [10 empty] | 0 | 616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 616 | 0% | 0 | 670.7091 | 670.7091 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 976 |  |  |  | 976 |  | 670.7091 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.6 | 2023/24 On-Ice Activities | 1.2.8.6 2023/24 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 2d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.6.7.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.6.1 | 0 | 670.7091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.6.7.6.1 | C |  | PSL | Shops: Final Upgrade/Retrofit Shops, OML, TOW, SEW |  | 0% | Labor Hours | TE |  |  | 115 | 77 | 0% | 2023-11-14 | 2023-11-21 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -1953 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  | 16 | [10 empty] | 0 | 1232 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1232 | 0% | 0 | 1341.4182 | 1341.4182 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 1953 |  |  |  | 1953 |  | 1341.4182 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.6 | 2023/24 On-Ice Activities | 1.2.8.6 2023/24 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 2d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.6.7.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.6.1 | 0 | 1341.4182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.6.7.7.1 | C |  | PSL | MSHR: Install Drill Hose on Reel |  | 0% | Labor Hours | TE |  |  | 115 | 77 | 0% | 2024-01-05 | 2024-01-11 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -3905 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  |  | 128 | [8 empty] | 0 | 0 | 0 | 9856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9856 | 0% | 0 | 10731.3455 | 10731.3455 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 3905 |  |  |  | 3905 |  | 10731.3455 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.6 | 2023/24 On-Ice Activities | 1.2.8.6 2023/24 On-Ice Activities | cell-link@smartsheet.com | 2021-11-30 21:59 |  | 4d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.6.7.7.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.7.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.7.1 | 0 | 0 | 0 | 10731.3455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.7.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.7.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.7.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.7.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.7.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.6.7.7.2 | C |  | PSL | MSHR: Final Upgrades & Testing |  | 0% | Labor Hours | EN |  |  | 81 | 115 | 0% | 2023-12-10 | 2023-12-14 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -13753 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  | 48 | [9 empty] | 0 | 0 | 5520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5520 | 0% | 0 | 6010.2503 | 6010.2503 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 13753 |  |  |  | 13753 |  | 6010.2503 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.6 | 2023/24 On-Ice Activities | 1.2.8.6 2023/24 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 4d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.6.7.7.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.7.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.7.2 | 0 | 0 | 6010.2503 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.7.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.7.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.7.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.7.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.7.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.6.7.7.3 | C |  | PSL | MSHR: Install Blankets, |  | 0% | Labor Hours | TE |  |  |  | 77 | 0% | 2024-01-12 | 2024-01-16 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  |  | 54 | [8 empty] | 0 | 0 | 0 | 4158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4158 | 0% | 0 | 4527.2864 | 4527.2864 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | [9 empty] | 4527.2864 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.6 | 2023/24 On-Ice Activities | 1.2.8.6 2023/24 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 4d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.6.7.7.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.7.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.7.3 | 0 | 0 | 0 | 4527.2864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.7.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.7.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.7.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.7.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.7.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.6.7.7.3 | C |  | PSL | MSHR: Install Blankets, Connect to Power, Heating Control and Test |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2024-01-12 | 2024-01-16 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -7810 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  |  | 32 | [8 empty] | 0 | 0 | 0 | 3680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3680 | 0% | 0 | 4006.8336 | 4006.8336 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 7810 |  |  |  | 7810 |  | 4006.8336 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.6 | 2023/24 On-Ice Activities | 1.2.8.6 2023/24 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 4d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.6.7.7.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.7.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.7.3 | 0 | 0 | 0 | 4006.8336 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.7.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.7.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.7.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.7.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.7.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.6.7.8.1 | C |  | PSL | Winches/Reels: Final Integration & Testing |  | 0% | Labor Hours | TE |  |  | 115 | 77 | 0% | 2023-12-15 | 2024-01-01 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -7810 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  | 48 | [9 empty] | 0 | 0 | 3696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3696 | 0% | 0 | 4024.2546 | 4024.2546 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 7810 |  |  |  | 7810 |  | 4024.2546 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.6 | 2023/24 On-Ice Activities | 1.2.8.6 2023/24 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 8d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.6.7.8.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.8.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.8.1 | 0 | 0 | 4024.2546 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.8.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.8.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.8.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.8.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.8.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.6.7.8.1 | C |  | PSL | Winches/Reels: Final Integration & Testing |  | 0% | Labor Hours | EN |  |  |  | 115 | 0% | 2023-12-15 | 2024-01-01 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  | 96 | [9 empty] | 0 | 0 | 11040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11040 | 0% | 0 | 12020.5007 | 12020.5007 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | [9 empty] | 12020.5007 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.6 | 2023/24 On-Ice Activities | 1.2.8.6 2023/24 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 8d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.6.7.8.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.8.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.8.1 | 0 | 0 | 12020.5007 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.8.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.8.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.8.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.8.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.8.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.6.7.8.1 | C |  | PSL | Winches/Reels: Final Integration & Testing |  | 0% | Labor Hours | EN |  |  |  | 115 | 0% | 2023-12-15 | 2024-01-01 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  | 48 | [9 empty] | 0 | 0 | 5520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5520 | 0% | 0 | 6010.2503 | 6010.2503 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | [9 empty] | 6010.2503 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.6 | 2023/24 On-Ice Activities | 1.2.8.6 2023/24 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 8d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.6.7.8.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.8.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.8.1 | 0 | 0 | 6010.2503 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.8.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.8.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.8.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.8.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.8.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.6.7.9.1 | C |  | PSL | Fuel Storage/Delivery: Commission Fuel Tower |  | 0% | Labor Hours | TE |  |  | 81 | 77 | 0% | 2023-11-25 | 2023-11-29 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -27507 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  | 32 | 96 | [9 empty] | 0 | 2464 | 7392 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9856 | 0% | 0 | 10731.3455 | 10731.3455 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 27507 |  |  |  | 27507 |  | 10731.3455 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.6 | 2023/24 On-Ice Activities | 1.2.8.6 2023/24 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 8d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.6.7.9.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.9.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.9.1 | 0 | 2682.8364 | 8048.5091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.9.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.9.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.9.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.9.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.9.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.6.7.10.1 | C |  | PSL | TOS/Tower Equipment - Retrofit & Testing |  | 0% | Labor Hours | TE |  |  | 115 | 77 | 0% | 2023-12-31 | 2024-01-12 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -15621 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  |  | 128 | [8 empty] | 0 | 0 | 0 | 9856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9856 | 0% | 0 | 10731.3455 | 10731.3455 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 15621 |  |  |  | 15621 |  | 10731.3455 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.6 | 2023/24 On-Ice Activities | 1.2.8.6 2023/24 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 8d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.6.7.10.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.10.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.10.1 | 0 | 0 | 0 | 10731.3455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.10.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.10.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.10.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.10.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.10.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.6.7.11.1 | C |  | PSL | Computing/Control: System Integration, Verification, Test at NPX |  | 0% | Labor Hours | TE |  |  | 115 | 77 | 0% | 2023-11-29 | 2024-01-23 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -2929 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  | 250 | 350 | 360 | [8 empty] | 0 | 19250 | 26950 | 27720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73920 | 0% | 0 | 80485.0915 | 80485.0915 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 2929 |  |  |  | 2929 |  | 80485.0915 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.6 | 2023/24 On-Ice Activities | 1.2.8.6 2023/24 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 4d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.6.7.11.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.11.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.11.1 | 0 | 20959.6592 | 29343.5229 | 30181.9093 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.11.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.11.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.11.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.11.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.11.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.6.7.11.2 | C |  | PSL | Computing/Control: Testing and Reprogramming Motor Drives |  | 0% | Labor Hours | TE |  |  | 81 | 77 | 0% | 2023-11-29 | 2023-12-26 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -10315 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  | 160 | 160 | [9 empty] | 0 | 12320 | 12320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24640 | 0% | 0 | 26828.3638 | 26828.3638 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 10315 |  |  |  | 10315 |  | 26828.3638 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.6 | 2023/24 On-Ice Activities | 1.2.8.6 2023/24 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 4d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.6.7.11.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.11.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.11.2 | 0 | 13414.1819 | 13414.1819 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.11.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.11.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.11.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.11.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.11.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.6.7.11.3 | C |  | PSL | Computing/Controls: Install Retrofit Kits |  | 0% | Labor Hours | TE |  |  |  | 77 | 0% | 2023-11-22 | 2024-01-23 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  | 48 | 60 | 40 | [8 empty] | 0 | 3696 | 4620 | 3080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11396 | 0% | 0 | 12408.1183 | 12408.1183 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | [9 empty] | 12408.1183 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.6 | 2023/24 On-Ice Activities | 1.2.8.6 2023/24 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 9d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.6.7.11.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.11.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.11.3 | 0 | 4024.2546 | 5030.3182 | 3353.5455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.11.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.11.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.11.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.11.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.11.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.6.7.11.4 | C |  | PSL | Computing/Controls: Misc. Controls Tasking (TE) |  | 0% | Labor Hours | TE |  |  |  | 77 | 0% | 2023-12-01 | 2024-01-23 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  | 48 | 60 | 36 | [8 empty] | 0 | 3696 | 4620 | 2772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11088 | 0% | 0 | 12072.7637 | 12072.7637 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | [9 empty] | 12072.7637 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.6 | 2023/24 On-Ice Activities | 1.2.8.6 2023/24 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.6.7.11.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.11.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.11.4 | 0 | 4024.2546 | 5030.3182 | 3018.1909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.11.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.11.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.11.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.11.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.11.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.6.7.11.4 | C |  | PSL | Computing/Controls: Misc. Controls Tasking (EE) |  | 0% | Labor Hours | EN |  |  |  | 115 | 0% | 2023-12-01 | 2024-01-23 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  | 8 | 25 | 8 | [8 empty] | 0 | 920 | 2875 | 920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4715 | 0% | 0 | 5133.7555 | 5133.7555 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | [9 empty] | 5133.7555 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.6 | 2023/24 On-Ice Activities | 1.2.8.6 2023/24 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 16d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.6.7.11.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.11.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.11.4 | 0 | 1001.7084 | 3130.3387 | 1001.7084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.11.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.11.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.11.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.11.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.11.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.6.7.11.5 | C |  | PSL | Computing/Controls: Conduit wiring |  | 0% | Labor Hours | TE |  |  |  | 77 | 0% | 2023-11-22 | 2024-01-23 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  | 72 | 48 | 48 | [8 empty] | 0 | 5544 | 3696 | 3696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12936 | 0% | 0 | 14084.891 | 14084.891 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | [9 empty] | 14084.891 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.6 | 2023/24 On-Ice Activities | 1.2.8.6 2023/24 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 16d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.6.7.11.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.11.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.11.5 | 0 | 6036.3819 | 4024.2546 | 4024.2546 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.11.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.11.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.11.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.11.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.11.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.6.7.12.1 | C |  | PSL | ARA Drill: Integrate HPU-2 & Commission |  | 0% | Labor Hours | TE |  |  | 115 | 77 | 0% | 2023-11-24 | 2023-12-07 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -5858 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  | 48 | [10 empty] | 0 | 3696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3696 | 0% | 0 | 4024.2546 | 4024.2546 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 5858 |  |  |  | 5858 |  | 4024.2546 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.6 | 2023/24 On-Ice Activities | 1.2.8.6 2023/24 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 4d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.6.7.12.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.12.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.12.1 | 0 | 4024.2546 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.12.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.12.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.12.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.12.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.12.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.6.7.12.1 | C |  | PSL | ARA Drill: Integrate HPU-2 & Commission |  | 0% | Labor Hours | EN |  |  |  | 115 | 0% | 2023-11-24 | 2023-12-07 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  | 48 | [10 empty] | 0 | 5520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5520 | 0% | 0 | 6010.2503 | 6010.2503 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | [9 empty] | 6010.2503 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.6 | 2023/24 On-Ice Activities | 1.2.8.6 2023/24 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 4d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.6.7.12.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.12.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.12.1 | 0 | 6010.2503 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.12.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.12.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.12.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.12.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.12.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.6.7.12.1 | C |  | PSL | ARA Drill: Integrate HPU-2 & Commission |  | 0% | Labor Hours | EN |  |  |  | 115 | 0% | 2023-11-24 | 2023-12-07 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  | 48 | [10 empty] | 0 | 5520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5520 | 0% | 0 | 6010.2503 | 6010.2503 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | [9 empty] | 6010.2503 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.6 | 2023/24 On-Ice Activities | 1.2.8.6 2023/24 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 4d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.6.7.12.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.12.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.12.1 | 0 | 6010.2503 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.12.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.12.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.12.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.12.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.12.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.6.7.12.2 | C |  | PSL | ARA Drill: Decommission & Store ARA Drill |  | 0% | Labor Hours | TE |  |  | 115 | 77 | 0% | 2024-01-24 | 2024-01-30 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -2929 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  |  | 32 | [8 empty] | 0 | 0 | 0 | 2464 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2464 | 0% | 0 | 2682.8364 | 2682.8364 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 2929 |  |  |  | 2929 |  | 2682.8364 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.6 | 2023/24 On-Ice Activities | 1.2.8.6 2023/24 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 2d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.6.7.12.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.12.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.12.2 | 0 | 0 | 0 | 2682.8364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.12.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.12.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.12.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.12.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.7.12.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.6.8.1 | C |  | PSL | Sensor Handling Facility: Assemble Skis and Deck, Erect Walls, Construct Walls, Construct Roof |  | 0% | Labor Hours | EN |  |  | 81 | 115 | 0% | 2023-12-10 | 2023-12-14 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -10315 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  | 168 | [9 empty] | 0 | 0 | 19320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19320 | 0% | 0 | 21035.8762 | 21035.8762 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 10315 |  |  |  | 10315 |  | 21035.8762 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.6 | 2023/24 On-Ice Activities | 1.2.8.6 2023/24 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 2d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.6.8.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.8.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.8.1 | 0 | 0 | 21035.8762 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.8.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.8.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.8.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.8.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.8.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.6.8.2 | C |  | PSL | Sensor Handling Facility: Final Assembly with ASC-provided Crane |  | 0% | Labor Hours | TE |  |  | 115 | 77 | 0% | 2023-12-18 | 2023-12-20 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -5858 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  | 24 | [9 empty] | 0 | 0 | 1848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1848 | 0% | 0 | 2012.1273 | 2012.1273 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 5858 |  |  |  | 5858 |  | 2012.1273 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.6 | 2023/24 On-Ice Activities | 1.2.8.6 2023/24 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 2d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.6.8.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.8.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.8.2 | 0 | 0 | 2012.1273 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.8.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.8.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.8.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.8.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.8.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.6.9.1 | C |  | PSL | Condensate Bulb: Drill and Pump |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2023-12-07 | 2023-12-11 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -1953 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  | 240 | [9 empty] | 0 | 0 | 27600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27600 | 0% | 0 | 30051.2517 | 30051.2517 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 1953 |  |  |  | 1953 |  | 30051.2517 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.6 | 2023/24 On-Ice Activities | 1.2.8.6 2023/24 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 2d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.6.9.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.9.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.9.1 | 0 | 0 | 30051.2517 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.9.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.9.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.9.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.9.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.9.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.6.10.1 | C |  | PSL | Rod Well: Develop & Maintain (Using ARA Drill) |  | 0% | Labor Hours | EN |  |  | 81 | 115 | 0% | 2023-12-11 | 2024-01-16 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -2751 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  | 250 | 150 | [8 empty] | 0 | 0 | 28750 | 17250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46000 | 0% | 0 | 50085.4195 | 50085.4195 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 2751 |  |  |  | 2751 |  | 50085.4195 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.6 | 2023/24 On-Ice Activities | 1.2.8.6 2023/24 On-Ice Activities | cell-link@smartsheet.com | 2021-11-30 21:59 |  | 2d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.6.10.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.10.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.10.1 | 0 | 0 | 31303.3872 | 18782.0323 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.10.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.10.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.10.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.10.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.10.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.6.11.1 | C |  | PSL | IFD: Integration and Commissioning |  | 0% | Labor Hours | TE |  |  | 115 | 77 | 0% | 2023-12-08 | 2023-12-15 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -1953 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  | 32 | [9 empty] | 0 | 0 | 2464 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2464 | 0% | 0 | 2682.8364 | 2682.8364 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 1953 |  |  |  | 1953 |  | 2682.8364 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.6 | 2023/24 On-Ice Activities | 1.2.8.6 2023/24 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 6d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.6.11.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.11.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.11.1 | 0 | 0 | 2682.8364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.11.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.11.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.11.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.11.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.11.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.6.11.2 | C |  | PSL | IFD: Drill 8 Firn Holes |  | 0% | Labor Hours | EN |  |  | 81 | 115 | 0% | 2023-12-15 | 2024-01-18 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -2751 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  | 48 | 48 | [8 empty] | 0 | 0 | 5520 | 5520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11040 | 0% | 0 | 12020.5007 | 12020.5007 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 2751 |  |  |  | 2751 |  | 12020.5007 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.6 | 2023/24 On-Ice Activities | 1.2.8.6 2023/24 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 6d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.6.11.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.11.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.11.2 | 0 | 0 | 6010.2503 | 6010.2503 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.11.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.11.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.11.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.11.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.11.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.6.11.4 | C |  | PSL | IFD: Winterize & Store |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2024-01-18 | 2024-01-25 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -1953 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  |  | 48 | [8 empty] | 0 | 0 | 0 | 5520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5520 | 0% | 0 | 6010.2503 | 6010.2503 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 1953 |  |  |  | 1953 |  | 6010.2503 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.6 | 2023/24 On-Ice Activities | 1.2.8.6 2023/24 On-Ice Activities | cell-link@smartsheet.com | 2021-11-30 21:59 |  | 14d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.6.11.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.11.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.11.4 | 0 | 0 | 0 | 6010.2503 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.11.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.11.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.11.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.11.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.11.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.6.12.1 | C |  | PSL | Wet Test: Readiness Review, Safety Refresher, Emergency & Safety Systems Tested |  | 0% | Labor Hours | EN |  |  | 81 | 115 | 0% | 2024-01-04 | 2024-01-09 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -9627 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  |  | 80 | [8 empty] | 0 | 0 | 0 | 9200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9200 | 0% | 0 | 10017.0839 | 10017.0839 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 9627 |  |  |  | 9627 |  | 10017.0839 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.6 | 2023/24 On-Ice Activities | 1.2.8.6 2023/24 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 14d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.6.12.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.12.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.12.1 | 0 | 0 | 0 | 10017.0839 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.12.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.12.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.12.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.12.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.12.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.6.12.1 | C |  | PSL | Wet Test: Readiness Review, Safety Refresher, Emergency & Safety Systems Tested |  | 0% | Labor Hours | EN |  |  |  | 115 | 0% | 2024-01-04 | 2024-01-09 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  |  | 32 | [8 empty] | 0 | 0 | 0 | 3680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3680 | 0% | 0 | 4006.8336 | 4006.8336 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | [9 empty] | 4006.8336 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.6 | 2023/24 On-Ice Activities | 1.2.8.6 2023/24 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 14d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.6.12.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.12.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.12.1 | 0 | 0 | 0 | 4006.8336 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.12.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.12.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.12.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.12.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.12.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.6.12.2 | C |  | PSL | Wet Test: Fire Boilers, Circulate Water or Glycol |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2024-01-10 | 2024-01-18 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -13668 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  |  | 32 | [8 empty] | 0 | 0 | 0 | 3680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3680 | 0% | 0 | 4006.8336 | 4006.8336 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 13668 |  |  |  | 13668 |  | 4006.8336 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.6 | 2023/24 On-Ice Activities | 1.2.8.6 2023/24 On-Ice Activities | cell-link@smartsheet.com | 2021-11-30 21:59 |  | 14d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.6.12.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.12.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.12.2 | 0 | 0 | 0 | 4006.8336 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.12.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.12.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.12.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.12.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.12.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.6.12.3 | C |  | PSL | Wet Test: Perform Systems Tests (Wet Test & Comm.) |  | 0% | Labor Hours | TE |  |  | 81 | 77 | 0% | 2024-01-17 | 2024-01-22 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -1375 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  |  | 672 | [8 empty] | 0 | 0 | 0 | 51744 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51744 | 0% | 0 | 56339.564 | 56339.564 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 1375 |  |  |  | 1375 |  | 56339.564 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.6 | 2023/24 On-Ice Activities | 1.2.8.6 2023/24 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 3d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.6.12.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.12.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.12.3 | 0 | 0 | 0 | 56339.564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.12.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.12.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.12.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.12.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.12.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.6.12.4 | C |  | PSL | Wet Test: Blow Out Systems (need ASC compressor) |  | 0% | Labor Hours | TE |  |  | 115 | 77 | 0% | 2024-01-23 | 2024-01-26 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -1953 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  |  | 180 | [8 empty] | 0 | 0 | 0 | 13860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13860 | 0% | 0 | 15090.9547 | 15090.9547 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 1953 |  |  |  | 1953 |  | 15090.9547 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.6 | 2023/24 On-Ice Activities | 1.2.8.6 2023/24 On-Ice Activities | cell-link@smartsheet.com | 2021-11-30 21:59 |  | 3d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.6.12.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.12.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.12.4 | 0 | 0 | 0 | 15090.9547 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.12.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.12.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.12.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.12.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.12.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.6.13.1 | C |  | PSL | Close-out: Document, Photograph Equip & Upgrade Work, Further Req's |  | 0% | Labor Hours | EN |  |  | 81 | 115 | 0% | 2024-01-20 | 2024-01-22 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -1375 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  |  | 44 | [8 empty] | 0 | 0 | 0 | 5060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5060 | 0% | 0 | 5509.3961 | 5509.3961 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 1375 |  |  |  | 1375 |  | 5509.3961 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.6 | 2023/24 On-Ice Activities | 1.2.8.6 2023/24 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 3d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.6.13.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.13.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.13.1 | 0 | 0 | 0 | 5509.3961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.13.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.13.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.13.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.13.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.13.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.6.13.2 | C |  | PSL | Close-out: Remove DNF, Computer Equip, Drives, Capacitors, Etc |  | 0% | Labor Hours | TE |  |  | 115 | 77 | 0% | 2024-01-22 | 2024-01-25 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -1953 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  |  | 144 | [8 empty] | 0 | 0 | 0 | 11088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11088 | 0% | 0 | 12072.7637 | 12072.7637 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 1953 |  |  |  | 1953 |  | 12072.7637 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.6 | 2023/24 On-Ice Activities | 1.2.8.6 2023/24 On-Ice Activities | cell-link@smartsheet.com | 2021-11-30 21:59 |  | 2d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.6.13.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.13.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.13.2 | 0 | 0 | 0 | 12072.7637 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.13.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.13.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.13.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.13.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.13.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.6.13.3 | C |  | PSL | Close-out: Winterize/Close/Store all EHWD Equipment |  | 0% | Labor Hours | EN |  |  | 81 | 115 | 0% | 2024-01-25 | 2024-01-30 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -2751 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  |  | 96 | [8 empty] | 0 | 0 | 0 | 11040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11040 | 0% | 0 | 12020.5007 | 12020.5007 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 2751 |  |  |  | 2751 |  | 12020.5007 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.6 | 2023/24 On-Ice Activities | 1.2.8.6 2023/24 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 2d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.6.13.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.13.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.13.3 | 0 | 0 | 0 | 12020.5007 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.13.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.13.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.13.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.13.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.13.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.6.13.4 | C |  | PSL | Close-out: Prepare Retrograde for Shipment |  | 0% | Labor Hours | TE |  |  | 115 | 77 | 0% | 2024-01-22 | 2024-01-30 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -3905 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  |  | 32 | [8 empty] | 0 | 0 | 0 | 2464 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2464 | 0% | 0 | 2682.8364 | 2682.8364 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 3905 |  |  |  | 3905 |  | 2682.8364 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.6 | 2023/24 On-Ice Activities | 1.2.8.6 2023/24 On-Ice Activities | cell-link@smartsheet.com | 2021-11-30 21:59 |  | 2d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.6.13.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.13.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.13.4 | 0 | 0 | 0 | 2682.8364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.13.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.13.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.13.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.13.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.13.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.6.13.5.1 | C |  | PSL | Winterize: Remove & Retro/Store All DNF |  | 0% | Labor Hours | TE |  |  | 115 | 77 | 0% | 2024-01-20 | 2024-01-30 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -1953 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  |  | 48 | [8 empty] | 0 | 0 | 0 | 3696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3696 | 0% | 0 | 4024.2546 | 4024.2546 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 1953 |  |  |  | 1953 |  | 4024.2546 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.6 | 2023/24 On-Ice Activities | 1.2.8.6 2023/24 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 2d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.6.13.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.13.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.13.5.1 | 0 | 0 | 0 | 4024.2546 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.13.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.13.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.13.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.13.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.13.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.6.13.5.2 | C |  | PSL | Winterize: Winterize SES & TOS, Disconnect all Cables, Hoses, Connections |  | 0% | Labor Hours | TE |  |  | 81 | 77 | 0% | 2024-01-24 | 2024-01-31 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -1375 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  |  | 144 | [8 empty] | 0 | 0 | 0 | 11088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11088 | 0% | 0 | 12072.7637 | 12072.7637 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 1375 |  |  |  | 1375 |  | 12072.7637 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.6 | 2023/24 On-Ice Activities | 1.2.8.6 2023/24 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 2d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.6.13.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.13.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.13.5.2 | 0 | 0 | 0 | 12072.7637 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.13.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.13.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.13.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.13.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.13.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.6.13.5.3 | C |  | PSL | Winterize: All EHWD Equipment Winterized |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2024-02-01 | 2024-02-01 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -3905 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 3905 |  |  |  | 3905 |  | 0 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.6 | 2023/24 On-Ice Activities | 1.2.8.6 2023/24 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 4d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.6.13.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.13.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.13.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.13.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.13.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.13.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.13.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.13.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.6.14.1 | C |  | PSL | MCM Logistics Rep (driller) |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2023-10-25 | 2023-11-17 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -7810 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  | 144 | [10 empty] | 0 | 16560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16560 | 0% | 0 | 18030.751 | 18030.751 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 7810 |  |  |  | 7810 |  | 18030.751 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.6 | 2023/24 On-Ice Activities | 1.2.8.6 2023/24 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 4d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.6.14.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.14.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.14.1 | 0 | 18030.751 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.14.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.14.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.14.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.14.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.14.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.6.15 | C |  | PSL | END NPX 2023/24 Season |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2024-02-07 | 2024-02-07 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -976 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 976 |  |  |  | 976 |  | 0 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.6 | 2023/24 On-Ice Activities | 1.2.8.6 2023/24 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 3d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.6.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.6.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.7.1 | C |  | PSL | START NPX 2024/25 Season - Team Arrives 28 [Drilling/Installation] |  | 0% | Labor Hours | TE |  |  | 81 | 77 | 0% | 2024-11-09 | 2024-11-09 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -2751 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 2751 |  |  |  | 2751 |  | 0 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.7 | 2024/25 On-Ice Activities | 1.2.8.7 2024/25 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 3d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.7.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.7.2 | C |  | PSL | Deployment Travel & PQ Costs (24/25) (Driller_PSL_Manager) |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2024-06-01 | 2025-02-27 |  |  |  | 1 (Drill Manager), 5 days deployment travel 3 days redeployment | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -3905 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  | 40 |  | 24 | 96 | [7 empty] | 0 | 4600 | 0 | 2760 | 11040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18400 | 0% | 0 | 20464.9024 |  | 0 |  | 3905 |  |  |  | 3905 |  | 20464.9024 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.7 | 2024/25 On-Ice Activities | 1.2.8.7 2024/25 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 3d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.7.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.2 | 0 | 5116.2256 | 0 | 3069.7354 | 12278.9414 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.7.2 | C |  | PSL | Deployment Travel & PQ Costs (24/25) (Driller_PSL_Direct_Hire) |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2024-06-01 | 2025-02-27 |  |  |  | 20 (PSL Direct Hire), 5 days deployment travel 3 days redeployment | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -3905 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  | 800 |  | 480 | [8 empty] | 0 | 92000 | 0 | 55200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 147200 | 0% | 0 | 163719.2192 |  | 0 |  | 3905 |  |  |  | 3905 |  | 163719.2192 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.7 | 2024/25 On-Ice Activities | 1.2.8.7 2024/25 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 3d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.7.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.2 | 0 | 102324.512 | 0 | 61394.7072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.7.2 | C |  | PSL | Deployment Travel & PQ Costs (24/25) (Engineer_PSL) |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2024-06-01 | 2025-02-27 |  |  |  | 8 (PSL Engineers), 5 days deployment travel 3 days redeployment | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -3905 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  | 320 |  | 192 | [8 empty] | 0 | 36800 | 0 | 22080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58880 | 0% | 0 | 65487.6877 |  | 0 |  | 3905 |  |  |  | 3905 |  | 65487.6877 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.7 | 2024/25 On-Ice Activities | 1.2.8.7 2024/25 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 3d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.7.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.2 | 0 | 40929.8048 | 0 | 24557.8829 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.7.2 | C |  | PSL | Deployment Travel & PQ Costs (24/25) Team |  |  | M & S | EN |  |  | 115 | 1 | 0% | 2024-06-01 | 2025-02-27 |  |  |  | 32 - PQ's @ $950/each (anticipated cost) - 2 Alternates and 2 PSL Rotator | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | -3905 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [8 empty] | 15200 | 15200 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15200 | 15200 | 0 | 0 | 30400 | 53% | 16112 | 46512 | 46512 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 |  | 3905 |  |  |  | 3905 |  | 46512 | M & S | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.7 | 2024/25 On-Ice Activities | 1.2.8.7 2024/25 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 3d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.7.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23256 | 23256 | 0 | 0 | 1.2.8.7.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.7.2 | C |  | PSL | Deployment Travel & PQ Costs (24/25) Team |  |  | Travel | EN |  |  | 115 | 1 | 0% | 2024-06-01 | 2025-02-27 |  |  |  | 30 - Deploy travel costs 2 PSL rotator | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | -3905 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [10 empty] | 48000 | 48000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48000 | 48000 | 96000 | 53% | 50880 | 146880 | 146880 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 |  | 3905 |  |  |  | 3905 |  | 146880 | Travel | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.7 | 2024/25 On-Ice Activities | 1.2.8.7 2024/25 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 3d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.7.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73440 | 73440 | 1.2.8.7.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.7.5.1 | C |  | PSL | SES: Make Ready all Drill Modules (DCC, PHS, MHPs, TOS 1&2, WTs, Handling Facility) |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2024-11-15 | 2024-11-27 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -4882 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  | 244 | [10 empty] | 0 | 28060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28060 | 0% | 0 | 31208.9762 |  | 0 |  | 4882 |  |  |  | 4882 |  | 31208.9762 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.7 | 2024/25 On-Ice Activities | 1.2.8.7 2024/25 On-Ice Activities | cell-link@smartsheet.com | 2021-11-30 21:59 |  | 14d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.7.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.5.1 | 0 | 31208.9762 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.7.5.2 | C |  | PSL | SES: Furnace Checkout & Fire Up (All modules) |  | 0% | Labor Hours | TE |  |  | 81 | 77 | 0% | 2024-11-15 | 2024-11-20 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -3438 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  | 32 | [10 empty] | 0 | 2464 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2464 | 0% | 0 | 2740.5174 |  | 0 |  | 3438 |  |  |  | 3438 |  | 2740.5174 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.7 | 2024/25 On-Ice Activities | 1.2.8.7 2024/25 On-Ice Activities | cell-link@smartsheet.com | 2021-11-30 21:59 |  | 14d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.7.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.5.2 | 0 | 2740.5174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.7.5.3 | C |  | PSL | SES: Perform Emergency Incident Drill & Safety Training |  | 0% | Labor Hours | EN |  |  | 1 | 115 | 0% | 2024-12-08 | 2024-12-10 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -21420 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  | 672 | [9 empty] | 0 | 0 | 77280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77280 | 0% | 0 | 85952.5901 |  | 0 |  |  |  | 21420 |  | 21420 |  | 85952.5901 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.7 | 2024/25 On-Ice Activities | 1.2.8.7 2024/25 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 182d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.7.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.5.3 | 0 | 0 | 85952.5901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.7.5.4 | C |  | PSL | SES: Make ARA Drill Ready for Service |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2024-11-28 | 2024-12-04 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -5975 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  | 40 | [9 empty] | 0 | 0 | 4600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4600 | 0% | 0 | 5116.2256 |  | 0 |  |  |  | 5975 |  | 5975 |  | 5116.2256 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.7 | 2024/25 On-Ice Activities | 1.2.8.7 2024/25 On-Ice Activities | cell-link@smartsheet.com | 2021-11-30 21:59 |  | 103d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.7.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.5.4 | 0 | 0 | 5116.2256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.7.5.4 | C |  | PSL | SES: Make ARA Drill Ready for Service |  | 0% | Labor Hours | TE |  |  |  | 77 | 0% | 2024-11-28 | 2024-12-04 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  | 40 | [9 empty] | 0 | 0 | 3080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3080 | 0% | 0 | 3425.6467 | [9 empty] | 3425.6467 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.7 | 2024/25 On-Ice Activities | 1.2.8.7 2024/25 On-Ice Activities | cell-link@smartsheet.com | 2021-11-30 21:59 |  | 103d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.7.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.5.4 | 0 | 0 | 3425.6467 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.7.5.5 | C |  | PSL | SES: Re-Establish RodWell |  | 0% | Labor Hours | EN |  |  | 81 | 115 | 0% | 2024-12-04 | 2025-01-16 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -42085 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  | 176 | 96 | [8 empty] | 0 | 0 | 20240 | 11040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31280 | 0% | 0 | 34790.3341 |  | 0 |  |  |  | 42085 |  | 42085 |  | 34790.3341 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.7 | 2024/25 On-Ice Activities | 1.2.8.7 2024/25 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 103d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.7.5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.5.5 | 0 | 0 | 22511.3926 | 12278.9414 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.7.5.6 | C |  | PSL | SES: SES and Equipment Maintenance |  | 0% | Labor Hours | TE |  |  | 115 | 77 | 0% | 2024-11-15 | 2025-02-03 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -23900 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  | 60 | 124 | 124 | [8 empty] | 0 | 4620 | 9548 | 9548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23716 | 0% | 0 | 26377.4796 |  | 0 |  |  |  | 23900 |  | 23900 |  | 26377.4796 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.7 | 2024/25 On-Ice Activities | 1.2.8.7 2024/25 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 103d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.7.5.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.5.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.5.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.5.6 | 0 | 5138.4701 | 10619.5048 | 10619.5048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.5.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.5.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.5.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.5.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.7.5.7 | C |  | PSL | SES: Ready for Drilling - (On Ice Final Readiness Assessment) |  | 0% | Labor Hours | EN |  |  | 1 | 115 | 0% | 2024-12-12 | 2024-12-12 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -43605 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  |  |  | 43605 |  | 43605 |  | 0 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.7 | 2024/25 On-Ice Activities | 1.2.8.7 2024/25 On-Ice Activities | cell-link@smartsheet.com | 2021-11-30 21:59 |  | 103d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.7.5.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.5.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.5.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.5.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.5.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.5.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.5.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.5.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.7.5.8 | C |  | PSL | SES: Dig-out |  | 0% | Labor Hours | EN |  |  | 1 | 115 | 0% | 2024-11-14 | 2024-11-18 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -59620 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  | 96 | [10 empty] | 0 | 11040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11040 | 0% | 0 | 12278.9414 |  | 0 |  |  |  | 59620 |  | 59620 |  | 12278.9414 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.7 | 2024/25 On-Ice Activities | 1.2.8.7 2024/25 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 103d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.7.5.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.5.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.5.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.5.8 | 0 | 12278.9414 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.5.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.5.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.5.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.5.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.7.6.1 | C |  | PSL | Generator/PDM: Recommission |  | 0% | Labor Hours | TE |  |  | 81 | 77 | 0% | 2024-11-18 | 2024-11-20 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -21042 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  | 96 | [10 empty] | 0 | 7392 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7392 | 0% | 0 | 8221.5521 |  | 0 |  |  |  | 21042 |  | 21042 |  | 8221.5521 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.7 | 2024/25 On-Ice Activities | 1.2.8.7 2024/25 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 14d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.7.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.6.1 | 0 | 8221.5521 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.7.6.2 | C |  | PSL | Generator/PDM: Generators Ready |  | 0% | Labor Hours | TE |  |  | 115 | 77 | 0% | 2024-11-20 | 2024-11-21 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -1992 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  |  |  | 1992 |  | 1992 |  | 0 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.7 | 2024/25 On-Ice Activities | 1.2.8.7 2024/25 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 2d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.7.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.7.6.3 | C |  | PSL | Generator/PDM: Change from Temp Power to Generators (Stand Alone) |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2024-11-20 | 2024-11-22 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -9958 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  | 8 | [10 empty] | 0 | 920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 920 | 0% | 0 | 1023.2451 |  | 0 |  |  |  | 9958 |  | 9958 |  | 1023.2451 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.7 | 2024/25 On-Ice Activities | 1.2.8.7 2024/25 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 10d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.7.6.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.6.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.6.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.6.3 | 0 | 1023.2451 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.6.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.6.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.6.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.6.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.7.7.1 | C |  | PSL | TOS1/Tower1: Hole Excavation, Trench & Install Cable Anchor (Hole 1) |  | 0% | Labor Hours | EN |  |  | 81 | 115 | 0% | 2024-12-06 | 2024-12-09 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -70142 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  | 16 | [9 empty] | 0 | 0 | 1840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1840 | 0% | 0 | 2046.4902 |  | 0 |  |  |  | 70142 |  | 70142 |  | 2046.4902 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.7 | 2024/25 On-Ice Activities | 1.2.8.7 2024/25 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 10d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.7.7.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.7.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.7.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.7.1 | 0 | 0 | 2046.4902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.7.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.7.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.7.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.7.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.7.7.2 | C |  | PSL | TOS1/Tower1: Position & Level TOS1/Tower1 at Hole 1 |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2024-11-25 | 2024-11-25 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -39834 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  | 16 | [10 empty] | 0 | 1840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1840 | 0% | 0 | 2046.4902 |  | 0 |  |  |  | 39834 |  | 39834 |  | 2046.4902 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.7 | 2024/25 On-Ice Activities | 1.2.8.7 2024/25 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 10d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.7.7.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.7.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.7.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.7.2 | 0 | 2046.4902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.7.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.7.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.7.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.7.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.7.7.3 | C |  | PSL | TOS1/Tower1: Position Sensor Handling Structure |  | 0% | Labor Hours | TE |  |  | 81 | 77 | 0% | 2024-11-26 | 2024-11-27 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -2806 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  | 8 | [10 empty] | 0 | 616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 616 | 0% | 0 | 685.1293 |  | 0 |  |  |  | 2806 |  | 2806 |  | 685.1293 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.7 | 2024/25 On-Ice Activities | 1.2.8.7 2024/25 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 3d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.7.7.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.7.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.7.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.7.3 | 0 | 685.1293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.7.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.7.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.7.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.7.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.7.7.4 | C |  | PSL | TOS1/Tower1: Hose & Cable Delivery & Layout SES-TOS |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2024-12-02 | 2024-12-04 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -1992 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  | 96 | [9 empty] | 0 | 0 | 11040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11040 | 0% | 0 | 12278.9414 |  | 0 |  |  |  | 1992 |  | 1992 |  | 12278.9414 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.7 | 2024/25 On-Ice Activities | 1.2.8.7 2024/25 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 3d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.7.7.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.7.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.7.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.7.4 | 0 | 0 | 12278.9414 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.7.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.7.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.7.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.7.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.7.7.5 | C |  | PSL | TOS1/Tower1: Trench & Install Reel Anchors (Hole 1) |  | 0% | Labor Hours | TE |  |  | 81 | 77 | 0% | 2024-12-05 | 2024-12-09 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -7014 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  | 8 | [9 empty] | 0 | 0 | 616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 616 | 0% | 0 | 685.1293 |  | 0 |  |  |  | 7014 |  | 7014 |  | 685.1293 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.7 | 2024/25 On-Ice Activities | 1.2.8.7 2024/25 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 5d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.7.7.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.7.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.7.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.7.5 | 0 | 0 | 685.1293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.7.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.7.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.7.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.7.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.7.7.6 | C |  | PSL | TOS1/Tower1: Position Hose & Cable Reels (Hole 1) |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2024-12-06 | 2024-12-09 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -9958 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  | 8 | [9 empty] | 0 | 0 | 920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 920 | 0% | 0 | 1023.2451 |  | 0 |  |  |  | 9958 |  | 9958 |  | 1023.2451 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.7 | 2024/25 On-Ice Activities | 1.2.8.7 2024/25 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 5d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.7.7.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.7.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.7.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.7.6 | 0 | 0 | 1023.2451 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.7.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.7.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.7.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.7.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.7.7.7 | C |  | PSL | TOS1/Tower1: Make TOS1 Operational, Deliver fuel, fire furnace |  | 0% | Labor Hours | TE |  |  | 115 | 77 | 0% | 2024-12-06 | 2024-12-09 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -4979 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  | 16 | [9 empty] | 0 | 0 | 1232 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1232 | 0% | 0 | 1370.2587 |  | 0 |  |  |  | 4979 |  | 4979 |  | 1370.2587 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.7 | 2024/25 On-Ice Activities | 1.2.8.7 2024/25 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 5d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.7.7.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.7.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.7.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.7.7 | 0 | 0 | 1370.2587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.7.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.7.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.7.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.7.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.7.7.8 | C |  | PSL | TOS1/Tower1: TOS1 Network/Comms Install |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2024-12-06 | 2024-12-09 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -996 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  | 6 | [9 empty] | 0 | 0 | 690 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 690 | 0% | 0 | 767.4338 |  | 0 |  |  |  | 996 |  | 996 |  | 767.4338 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.7 | 2024/25 On-Ice Activities | 1.2.8.7 2024/25 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 2d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.7.7.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.7.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.7.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.7.8 | 0 | 0 | 767.4338 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.7.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.7.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.7.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.7.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.7.7.9 | C |  | PSL | TOS1/Tower1: Connect Hose Loop, Circulate Water |  | 0% | Labor Hours | TE |  |  | 81 | 77 | 0% | 2024-12-06 | 2024-12-09 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -8417 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  | 48 | [9 empty] | 0 | 0 | 3696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3696 | 0% | 0 | 4110.776 |  | 0 |  |  |  | 8417 |  | 8417 |  | 4110.776 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.7 | 2024/25 On-Ice Activities | 1.2.8.7 2024/25 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 2d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.7.7.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.7.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.7.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.7.9 | 0 | 0 | 4110.776 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.7.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.7.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.7.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.7.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.7.7.10 | C |  | PSL | TOS1/Tower1: Prepare SFC-DOM Cable (Mount on TU20, test slip ring) |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2024-12-06 | 2024-12-09 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -3983 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  | 16 | [9 empty] | 0 | 0 | 1840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1840 | 0% | 0 | 2046.4902 |  | 0 |  |  |  | 3983 |  | 3983 |  | 2046.4902 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.7 | 2024/25 On-Ice Activities | 1.2.8.7 2024/25 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 2d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.7.7.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.7.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.7.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.7.10 | 0 | 0 | 2046.4902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.7.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.7.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.7.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.7.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.7.7.11 | C |  | PSL | TOS1/Tower1: Pull Drill Heads from ICL, Final Testing in TOS |  | 0% | Labor Hours | TE |  |  | 115 | 77 | 0% | 2024-12-09 | 2024-12-12 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -996 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  | 16 | [9 empty] | 0 | 0 | 1232 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1232 | 0% | 0 | 1370.2587 |  | 0 |  |  |  | 996 |  | 996 |  | 1370.2587 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.7 | 2024/25 On-Ice Activities | 1.2.8.7 2024/25 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 2d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.7.7.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.7.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.7.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.7.11 | 0 | 0 | 1370.2587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.7.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.7.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.7.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.7.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.7.7.12 | C |  | PSL | TOS1/Tower1: Site Ready for Drilling |  | 0% | Labor Hours | EN |  |  | 81 | 115 | 0% | 2024-12-13 | 2024-12-16 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -1403 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  |  |  | 1403 |  | 1403 |  | 0 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.7 | 2024/25 On-Ice Activities | 1.2.8.7 2024/25 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 2d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.7.7.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.7.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.7.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.7.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.7.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.7.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.7.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.7.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.7.8.1 | C |  | PSL | TOS2/Tower2: Position & Level TOS2/Tower2 at Hole 2 |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2024-11-26 | 2024-12-02 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -1992 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  | 16 | [10 empty] | 0 | 1840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1840 | 0% | 0 | 2046.4902 |  | 0 |  |  |  | 1992 |  | 1992 |  | 2046.4902 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.7 | 2024/25 On-Ice Activities | 1.2.8.7 2024/25 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 2d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.7.8.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.8.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.8.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.8.1 | 0 | 2046.4902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.8.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.8.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.8.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.8.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.7.8.2 | C |  | PSL | TOS2/Tower2: Cable Layout SES to TOS2 |  | 0% | Labor Hours | TE |  |  | 81 | 77 | 0% | 2024-12-02 | 2024-12-06 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -701 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  | 16 | [9 empty] | 0 | 0 | 1232 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1232 | 0% | 0 | 1370.2587 |  | 0 |  |  |  | 701 |  | 701 |  | 1370.2587 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.7 | 2024/25 On-Ice Activities | 1.2.8.7 2024/25 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 2d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.7.8.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.8.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.8.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.8.2 | 0 | 0 | 1370.2587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.8.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.8.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.8.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.8.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.7.8.3 | C |  | PSL | TOS2/Tower2:Make TOS2 Operational, Deliver fuel, fire furnace |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2024-12-09 | 2024-12-11 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -2988 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  | 16 | [9 empty] | 0 | 0 | 1840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1840 | 0% | 0 | 2046.4902 |  | 0 |  |  |  | 2988 |  | 2988 |  | 2046.4902 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.7 | 2024/25 On-Ice Activities | 1.2.8.7 2024/25 On-Ice Activities | cell-link@smartsheet.com | 2021-11-30 22:10 |  | 4d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.7.8.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.8.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.8.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.8.3 | 0 | 0 | 2046.4902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.8.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.8.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.8.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.8.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.7.8.4 | C |  | PSL | TOS2/Tower2: TOS2 Network/Comms Install |  | 0% | Labor Hours | EN |  |  | 81 | 115 | 0% | 2024-12-09 | 2024-12-12 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -2104 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  | 6 | [9 empty] | 0 | 0 | 690 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 690 | 0% | 0 | 767.4338 |  | 0 |  |  |  | 2104 |  | 2104 |  | 767.4338 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.7 | 2024/25 On-Ice Activities | 1.2.8.7 2024/25 On-Ice Activities | cell-link@smartsheet.com | 2021-11-30 22:10 |  | 4d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.7.8.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.8.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.8.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.8.4 | 0 | 0 | 767.4338 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.8.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.8.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.8.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.8.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.7.8.5 | C |  | PSL | TOS2/Tower2: TOS2/Tower2 in Position & Heated |  | 0% | Labor Hours | TE |  |  | 115 | 77 | 0% | 2024-12-13 | 2024-12-16 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -2988 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  |  |  | 2988 |  | 2988 |  | 0 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.7 | 2024/25 On-Ice Activities | 1.2.8.7 2024/25 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 4d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.7.8.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.8.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.8.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.8.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.8.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.8.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.8.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.8.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.7.9.1 | C |  | PSL | Wet Test: Training (Direct Hire Drillers -15) |  | 0% | Labor Hours | TE |  |  | 115 | 77 | 0% | 2024-11-20 | 2024-12-16 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -996 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  | 1200 | [9 empty] | 0 | 0 | 92400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92400 | 0% | 0 | 102769.4012 |  | 0 |  |  |  | 996 |  | 996 |  | 102769.4012 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.7 | 2024/25 On-Ice Activities | 1.2.8.7 2024/25 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 4d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.7.9.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.9.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.9.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.9.1 | 0 | 0 | 102769.4012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.9.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.9.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.9.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.9.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.7.9.1 | C |  | PSL | Wet Test: Training (Engineer/Drillers - 3) |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2024-11-20 | 2024-12-16 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -996 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  | 240 | [9 empty] | 0 | 0 | 27600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27600 | 0% | 0 | 30697.3536 |  | 0 |  |  |  | 996 |  | 996 |  | 30697.3536 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.7 | 2024/25 On-Ice Activities | 1.2.8.7 2024/25 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 4d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.7.9.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.9.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.9.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.9.1 | 0 | 0 | 30697.3536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.9.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.9.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.9.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.9.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.7.9.1 | C |  | PSL | Wet Test: Readiness Review/Safety Refresher |  | 0% | Labor Hours | TE |  |  | 115 | 77 | 0% | 2024-11-20 | 2024-12-16 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -2988 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  | 224 | [10 empty] | 0 | 17248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17248 | 0% | 0 | 19183.6216 |  | 0 |  |  |  | 2988 |  | 2988 |  | 19183.6216 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.7 | 2024/25 On-Ice Activities | 1.2.8.7 2024/25 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 4d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.7.9.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.9.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.9.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.9.1 | 0 | 19183.6216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.9.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.9.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.9.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.9.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.7.9.2 | C |  | PSL | Wet Test: Emergency & Safety Systems Tested |  | 0% | Labor Hours | EN |  |  | 81 | 115 | 0% | 2024-11-20 | 2024-11-25 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -4208 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  | 192 | [10 empty] | 0 | 22080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22080 | 0% | 0 | 24557.8829 |  | 0 |  |  |  | 4208 |  | 4208 |  | 24557.8829 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.7 | 2024/25 On-Ice Activities | 1.2.8.7 2024/25 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 4d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.7.9.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.9.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.9.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.9.2 | 0 | 24557.8829 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.9.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.9.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.9.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.9.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.7.9.3 | C |  | PSL | Wet Test: Fire Boilers, Circulate Water |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2024-11-26 | 2025-01-08 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -996 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  | 160 | [10 empty] | 0 | 18400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18400 | 0% | 0 | 20464.9024 |  | 0 |  |  |  | 996 |  | 996 |  | 20464.9024 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.7 | 2024/25 On-Ice Activities | 1.2.8.7 2024/25 On-Ice Activities | cell-link@smartsheet.com | 2021-11-30 22:10 |  | 2d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.7.9.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.9.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.9.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.9.3 | 0 | 20464.9024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.9.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.9.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.9.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.9.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.7.9.4 | C |  | PSL | Wet Test: Perform Complete Systems Testing (Wet Test & Comm.) |  | 0% | Labor Hours | TE |  |  | 115 | 77 | 0% | 2024-12-04 | 2024-12-11 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -996 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  | 800 | [9 empty] | 0 | 0 | 61600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61600 | 0% | 0 | 68512.9341 |  | 0 |  |  |  | 996 |  | 996 |  | 68512.9341 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.7 | 2024/25 On-Ice Activities | 1.2.8.7 2024/25 On-Ice Activities | cell-link@smartsheet.com | 2021-11-30 22:10 |  | 2d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.7.9.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.9.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.9.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.9.4 | 0 | 0 | 68512.9341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.9.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.9.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.9.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.9.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.7.10.1 | C |  | PSL | Installation: DRILL HOLE # 1 |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2024-12-13 | 2024-12-16 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -1992 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  | 522 | [9 empty] | 0 | 0 | 60030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60030 | 0% | 0 | 66766.7441 |  | 0 |  |  |  | 1992 |  | 1992 |  | 66766.7441 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.7 | 2024/25 On-Ice Activities | 1.2.8.7 2024/25 On-Ice Activities | cell-link@smartsheet.com | 2021-12-02 15:02 |  | 3d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.7.10.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.1 | 0 | 0 | 66766.7441 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.7.10.2 | C |  | PSL | Installation: Deployment - String 1 |  | 0% | Labor Hours | TE |  |  | 115 | 77 | 0% | 2024-12-16 | 2024-12-18 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -1992 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  | 72 | [9 empty] | 0 | 0 | 5544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5544 | 0% | 0 | 6166.1641 |  | 0 |  |  |  | 1992 |  | 1992 |  | 6166.1641 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.7 | 2024/25 On-Ice Activities | 1.2.8.7 2024/25 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 4d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.7.10.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.2 | 0 | 0 | 6166.1641 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.7.10.3 | C |  | PSL | Installation: String # 1 Deployed & Complete |  | 0% | Labor Hours | EN |  |  | 81 | 115 | 0% | 2024-12-19 | 2024-12-20 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -1403 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  |  |  | 1403 |  | 1403 |  | 0 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.7 | 2024/25 On-Ice Activities | 1.2.8.7 2024/25 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 4d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.7.10.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.7.10.4 | C |  | PSL | Installation: Closeout & Relocate Tower & TOS to Hole 3 |  | 0% | Labor Hours | TE |  |  | 115 | 77 | 0% | 2024-12-16 | 2024-12-18 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -1992 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  | 32 | [9 empty] | 0 | 0 | 2464 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2464 | 0% | 0 | 2740.5174 |  | 0 |  |  |  | 1992 |  | 1992 |  | 2740.5174 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.7 | 2024/25 On-Ice Activities | 1.2.8.7 2024/25 On-Ice Activities | cell-link@smartsheet.com | 2021-11-30 22:10 |  | 2d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.7.10.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.4 | 0 | 0 | 2740.5174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.7.10.5 | C |  | PSL | Installation: Trench & Install Reel Anchors (Hole 2) |  | 0% | Labor Hours | TE |  |  | 81 | 77 | 0% | 2024-12-19 | 2024-12-23 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -1403 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  | 16 | [9 empty] | 0 | 0 | 1232 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1232 | 0% | 0 | 1370.2587 |  | 0 |  |  |  | 1403 |  | 1403 |  | 1370.2587 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.7 | 2024/25 On-Ice Activities | 1.2.8.7 2024/25 On-Ice Activities | cell-link@smartsheet.com | 2021-11-30 22:10 |  | 2d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.7.10.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.5 | 0 | 0 | 1370.2587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.7.10.6 | C |  | PSL | Installation: Relocate Hose, Cable Reels, Sensor Handling Structure (at end of installation) |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2024-12-17 | 2024-12-19 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -5975 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  | 28 | [9 empty] | 0 | 0 | 3220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3220 | 0% | 0 | 3581.3579 |  | 0 |  |  |  | 5975 |  | 5975 |  | 3581.3579 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.7 | 2024/25 On-Ice Activities | 1.2.8.7 2024/25 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 5d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.7.10.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.6 | 0 | 0 | 3581.3579 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.7.10.7 | C |  | PSL | Installation: Prepare SFC-DOM Cable (Mount on TU20, test slip ring) Prep for String 3 |  | 0% | Labor Hours | EN |  |  | 81 | 115 | 0% | 2024-12-19 | 2024-12-20 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -8417 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  | 8 | [9 empty] | 0 | 0 | 920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 920 | 0% | 0 | 1023.2451 |  | 0 |  |  |  | 8417 |  | 8417 |  | 1023.2451 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.7 | 2024/25 On-Ice Activities | 1.2.8.7 2024/25 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 5d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.7.10.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.7 | 0 | 0 | 1023.2451 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.7.10.8 | C |  | PSL | Installation: Operational Debrief |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2024-12-20 | 2024-12-20 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -5975 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  | 112 | [9 empty] | 0 | 0 | 12880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12880 | 0% | 0 | 14325.4317 |  | 0 |  |  |  | 5975 |  | 5975 |  | 14325.4317 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.7 | 2024/25 On-Ice Activities | 1.2.8.7 2024/25 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 5d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.7.10.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.8 | 0 | 0 | 14325.4317 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.7.10.9 | C |  | PSL | Installation: DRILL HOLE # 2 |  | 0% | Labor Hours | TE |  |  | 1 | 77 | 0% | 2024-12-20 | 2024-12-23 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -91433 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  | 522 | [9 empty] | 0 | 0 | 40194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40194 | 0% | 0 | 44704.6895 |  | 0 |  |  |  | 91433 |  | 91433 |  | 44704.6895 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.7 | 2024/25 On-Ice Activities | 1.2.8.7 2024/25 On-Ice Activities | cell-link@smartsheet.com | 2021-11-30 22:10 |  | 5d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.7.10.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.9 | 0 | 0 | 44704.6895 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.7.10.10 | C |  | PSL | Installation: Deployment - String 2 |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2024-12-20 | 2024-12-24 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -996 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  | 72 | [9 empty] | 0 | 0 | 8280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8280 | 0% | 0 | 9209.2061 |  | 0 |  |  |  | 996 |  | 996 |  | 9209.2061 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.7 | 2024/25 On-Ice Activities | 1.2.8.7 2024/25 On-Ice Activities | cell-link@smartsheet.com | 2021-11-30 22:10 |  | 2d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.7.10.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.10 | 0 | 0 | 9209.2061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.7.10.11 | C |  | PSL | Installation: String # 2 Deployed & Complete |  | 0% | Labor Hours | EN |  |  | 81 | 115 | 0% | 2024-12-24 | 2024-12-25 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -701 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  |  |  | 701 |  | 701 |  | 0 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.7 | 2024/25 On-Ice Activities | 1.2.8.7 2024/25 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 2d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.7.10.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.7.10.12 | C |  | PSL | Installation: Closeout & Relocate Tower & TOS to Hole 4 |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2024-12-25 | 2024-12-25 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -996 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  | 32 | [9 empty] | 0 | 0 | 3680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3680 | 0% | 0 | 4092.9805 |  | 0 |  |  |  | 996 |  | 996 |  | 4092.9805 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.7 | 2024/25 On-Ice Activities | 1.2.8.7 2024/25 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 2d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.7.10.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.12 | 0 | 0 | 4092.9805 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.7.10.13 | C |  | PSL | Installation: Trench & Install Reel Anchors (Hole 3) |  | 0% | Labor Hours | EN |  |  | 81 | 115 | 0% | 2024-12-23 | 2024-12-23 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -1403 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  | 16 | [9 empty] | 0 | 0 | 1840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1840 | 0% | 0 | 2046.4902 |  | 0 |  |  |  | 1403 |  | 1403 |  | 2046.4902 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.7 | 2024/25 On-Ice Activities | 1.2.8.7 2024/25 On-Ice Activities | cell-link@smartsheet.com | 2021-11-30 22:10 |  | 2d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.7.10.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.13 | 0 | 0 | 2046.4902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.7.10.14 | C |  | PSL | Installation: Relocate Hose, Cable Reels, Sensor Handling Structure (at end of installation) |  | 0% | Labor Hours | TE |  |  | 115 | 77 | 0% | 2024-12-23 | 2024-12-23 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -1992 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  | 28 | [9 empty] | 0 | 0 | 2156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2156 | 0% | 0 | 2397.9527 |  | 0 |  |  |  | 1992 |  | 1992 |  | 2397.9527 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.7 | 2024/25 On-Ice Activities | 1.2.8.7 2024/25 On-Ice Activities | cell-link@smartsheet.com | 2021-11-30 22:10 |  | 3d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.7.10.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.14 | 0 | 0 | 2397.9527 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.7.10.15 | C |  | PSL | Installation: Prepare SFC-DOM Cable (Mount on TU20, test slip ring) - Prep for String 4 |  | 0% | Labor Hours | EN |  |  | 81 | 115 | 0% | 2024-12-25 | 2024-12-25 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -2806 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  | 8 | [9 empty] | 0 | 0 | 920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 920 | 0% | 0 | 1023.2451 |  | 0 |  |  |  | 2806 |  | 2806 |  | 1023.2451 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.7 | 2024/25 On-Ice Activities | 1.2.8.7 2024/25 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 3d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.7.10.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.15 | 0 | 0 | 1023.2451 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.7.10.16 | C |  | PSL | Installation: DRILL HOLE # 3 |  | 0% | Labor Hours | TE |  |  | 115 | 77 | 0% | 2024-12-26 | 2024-12-27 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -1992 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  | 522 | [9 empty] | 0 | 0 | 40194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40194 | 0% | 0 | 44704.6895 |  | 0 |  |  |  | 1992 |  | 1992 |  | 44704.6895 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.7 | 2024/25 On-Ice Activities | 1.2.8.7 2024/25 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 3d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.7.10.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.16 | 0 | 0 | 44704.6895 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.7.10.17 | C |  | PSL | Installation: Deployment - String 3 |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2024-12-27 | 2024-12-30 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -996 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  | 72 | [9 empty] | 0 | 0 | 8280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8280 | 0% | 0 | 9209.2061 |  | 0 |  |  |  | 996 |  | 996 |  | 9209.2061 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.7 | 2024/25 On-Ice Activities | 1.2.8.7 2024/25 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 3d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.7.10.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.17 | 0 | 0 | 9209.2061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.7.10.18 | C |  | PSL | Installation: String # 3 Deployed & Complete |  | 0% | Labor Hours | TE |  |  | 81 | 77 | 0% | 2024-12-30 | 2024-12-30 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -701 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  |  |  | 701 |  | 701 |  | 0 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.7 | 2024/25 On-Ice Activities | 1.2.8.7 2024/25 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 3d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.7.10.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.7.10.19 | C |  | PSL | Installation: Closeout & Relocate Tower & TOS for Hole 5 |  | 0% | Labor Hours | EN |  |  | 81 | 115 | 0% | 2024-12-31 | 2025-01-01 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -2104 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  |  | 32 | [8 empty] | 0 | 0 | 0 | 3680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3680 | 0% | 0 | 4092.9805 |  | 0 |  |  |  | 2104 |  | 2104 |  | 4092.9805 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.7 | 2024/25 On-Ice Activities | 1.2.8.7 2024/25 On-Ice Activities | cell-link@smartsheet.com | 2021-11-30 22:10 |  | 3d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.7.10.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.19 | 0 | 0 | 0 | 4092.9805 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.7.10.20 | C |  | PSL | Installation: Trench & Install Reel Anchors (Hole 4) |  | 0% | Labor Hours | TE |  |  | 115 | 77 | 0% | 2024-12-30 | 2024-12-30 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -2988 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  | 16 | [9 empty] | 0 | 0 | 1232 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1232 | 0% | 0 | 1370.2587 |  | 0 |  |  |  | 2988 |  | 2988 |  | 1370.2587 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.7 | 2024/25 On-Ice Activities | 1.2.8.7 2024/25 On-Ice Activities | cell-link@smartsheet.com | 2021-11-30 22:14 |  | 3d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.7.10.20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.20 | 0 | 0 | 1370.2587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.7.10.21 | C |  | PSL | Installation: Relocate Hose, Cable Reels, Sensor Handling Structure (at end of installation) |  | 0% | Labor Hours | EN |  |  | 81 | 115 | 0% | 2024-12-30 | 2024-12-30 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -7014 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  | 28 | [9 empty] | 0 | 0 | 3220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3220 | 0% | 0 | 3581.3579 |  | 0 |  |  |  | 7014 |  | 7014 |  | 3581.3579 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.7 | 2024/25 On-Ice Activities | 1.2.8.7 2024/25 On-Ice Activities | cell-link@smartsheet.com | 2021-11-30 22:14 |  | 5d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.7.10.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.21 | 0 | 0 | 3581.3579 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.7.10.22 | C |  | PSL | Installation: Hole Excavation, Trench & Install Cable Anchor (Hole 4) |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2024-12-30 | 2024-12-31 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -4979 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  | 16 | [9 empty] | 0 | 0 | 1840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1840 | 0% | 0 | 2046.4902 |  | 0 |  |  |  | 4979 |  | 4979 |  | 2046.4902 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.7 | 2024/25 On-Ice Activities | 1.2.8.7 2024/25 On-Ice Activities | cell-link@smartsheet.com | 2021-11-30 22:14 |  | 5d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.7.10.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.22 | 0 | 0 | 2046.4902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.7.10.23 | C |  | PSL | Installation: Prepare SFC-Sensor Cable (Mount on TU20, test slip ring) - Prep for String 5 |  | 0% | Labor Hours | TE |  |  | 115 | 77 | 0% | 2025-01-01 | 2025-01-01 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -996 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  |  | 8 | [8 empty] | 0 | 0 | 0 | 616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 616 | 0% | 0 | 685.1293 |  | 0 |  |  |  | 996 |  | 996 |  | 685.1293 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.7 | 2024/25 On-Ice Activities | 1.2.8.7 2024/25 On-Ice Activities | cell-link@smartsheet.com | 2021-11-30 22:14 |  | 2d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.7.10.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.23 | 0 | 0 | 0 | 685.1293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.7.10.24 | C |  | PSL | Installation: DRILL HOLE # 4 |  | 0% | Labor Hours | EN |  |  | 81 | 115 | 0% | 2025-01-02 | 2025-01-03 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -2806 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  |  | 522 | [8 empty] | 0 | 0 | 0 | 60030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60030 | 0% | 0 | 66766.7441 |  | 0 |  |  |  | 2806 |  | 2806 |  | 66766.7441 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.7 | 2024/25 On-Ice Activities | 1.2.8.7 2024/25 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 2d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.7.10.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.24 | 0 | 0 | 0 | 66766.7441 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.7.10.25 | C |  | PSL | Installation: Deployment |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2025-01-03 | 2025-01-03 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -1992 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  |  | 72 | [8 empty] | 0 | 0 | 0 | 8280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8280 | 0% | 0 | 9209.2061 |  | 0 |  |  |  | 1992 |  | 1992 |  | 9209.2061 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.7 | 2024/25 On-Ice Activities | 1.2.8.7 2024/25 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 2d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.7.10.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.25 | 0 | 0 | 0 | 9209.2061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.7.10.26 | C |  | PSL | Installation: String # 4 Deployed & Complete |  | 0% | Labor Hours | TE |  |  | 81 | 77 | 0% | 2025-01-03 | 2025-01-03 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -701 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  |  |  | 701 |  | 701 |  | 0 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.7 | 2024/25 On-Ice Activities | 1.2.8.7 2024/25 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 2d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.7.10.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.7.10.27 | C |  | PSL | Installation: Closeout & Relocate Tower & TOS for Hole 6 |  | 0% | Labor Hours | TE |  |  | 115 | 77 | 0% | 2025-01-03 | 2025-01-03 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -996 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  |  | 32 | [8 empty] | 0 | 0 | 0 | 2464 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2464 | 0% | 0 | 2740.5174 |  | 0 |  |  |  | 996 |  | 996 |  | 2740.5174 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.7 | 2024/25 On-Ice Activities | 1.2.8.7 2024/25 On-Ice Activities | cell-link@smartsheet.com | 2021-11-30 22:14 |  | 2d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.7.10.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.27 | 0 | 0 | 0 | 2740.5174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.7.10.28 | C |  | PSL | Installation: Trench & Install Reel Anchors (Hole 5) |  | 0% | Labor Hours | EN |  |  | 81 | 115 | 0% | 2025-01-03 | 2025-01-03 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -1403 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  |  | 16 | [8 empty] | 0 | 0 | 0 | 1840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1840 | 0% | 0 | 2046.4902 |  | 0 |  |  |  | 1403 |  | 1403 |  | 2046.4902 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.7 | 2024/25 On-Ice Activities | 1.2.8.7 2024/25 On-Ice Activities | cell-link@smartsheet.com | 2021-11-30 22:14 |  | 2d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.7.10.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.28 | 0 | 0 | 0 | 2046.4902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.7.10.29 | C |  | PSL | Installation: Relocate Hose, Cable Reels, Sensor Handling Structure (at end of installation) |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2025-01-03 | 2025-01-03 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -1992 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  |  | 28 | [8 empty] | 0 | 0 | 0 | 3220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3220 | 0% | 0 | 3581.3579 |  | 0 |  |  |  | 1992 |  | 1992 |  | 3581.3579 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.7 | 2024/25 On-Ice Activities | 1.2.8.7 2024/25 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 2d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.7.10.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.29 | 0 | 0 | 0 | 3581.3579 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.7.10.30 | C |  | PSL | Installation: Hole Excavation, Trench & Install Cable Anchor (Hole 5) |  | 0% | Labor Hours | TE |  |  | 81 | 77 | 0% | 2025-01-03 | 2025-01-03 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -701 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  |  | 16 | [8 empty] | 0 | 0 | 0 | 1232 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1232 | 0% | 0 | 1370.2587 |  | 0 |  |  |  | 701 |  | 701 |  | 1370.2587 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.7 | 2024/25 On-Ice Activities | 1.2.8.7 2024/25 On-Ice Activities | cell-link@smartsheet.com | 2021-11-30 22:14 |  | 3d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.7.10.30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.30 | 0 | 0 | 0 | 1370.2587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.7.10.31 | C |  | PSL | Installation: Prepare SFC-Sensor Cable (Mount on TU20, test slip ring) - Prep for String 6 |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2025-01-03 | 2025-01-03 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -996 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  |  | 8 | [8 empty] | 0 | 0 | 0 | 920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 920 | 0% | 0 | 1023.2451 |  | 0 |  |  |  | 996 |  | 996 |  | 1023.2451 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.7 | 2024/25 On-Ice Activities | 1.2.8.7 2024/25 On-Ice Activities | cell-link@smartsheet.com | 2021-11-30 22:14 |  | 3d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.7.10.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.31 | 0 | 0 | 0 | 1023.2451 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.7.10.32 | C |  | PSL | Installation: DRILL HOLE # 5 |  | 0% | Labor Hours | EN |  |  | 81 | 115 | 0% | 2025-01-03 | 2025-01-06 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -1403 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  |  | 522 | [8 empty] | 0 | 0 | 0 | 60030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60030 | 0% | 0 | 66766.7441 |  | 0 |  |  |  | 1403 |  | 1403 |  | 66766.7441 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.7 | 2024/25 On-Ice Activities | 1.2.8.7 2024/25 On-Ice Activities | cell-link@smartsheet.com | 2021-11-30 22:21 |  | 3d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.7.10.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.32 | 0 | 0 | 0 | 66766.7441 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.7.10.33 | C |  | PSL | Installation: Deployment - String 5 |  | 0% | Labor Hours | TE |  |  | 115 | 77 | 0% | 2025-01-06 | 2025-01-07 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -1992 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  |  | 72 | [8 empty] | 0 | 0 | 0 | 5544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5544 | 0% | 0 | 6166.1641 |  | 0 |  |  |  | 1992 |  | 1992 |  | 6166.1641 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.7 | 2024/25 On-Ice Activities | 1.2.8.7 2024/25 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 3d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.7.10.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.33 | 0 | 0 | 0 | 6166.1641 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.7.10.34 | C |  | PSL | Installation: String # 5 Deployed & Complete |  | 0% | Labor Hours | EN |  |  | 81 | 115 | 0% | 2025-01-07 | 2025-01-07 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -2806 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  |  |  | 2806 |  | 2806 |  | 0 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.7 | 2024/25 On-Ice Activities | 1.2.8.7 2024/25 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 6d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.7.10.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.7.10.35 | C |  | PSL | Installation: Closeout & Relocate Tower & TOS for Hole 7 |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2025-01-08 | 2025-01-08 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -1992 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  |  | 32 | [8 empty] | 0 | 0 | 0 | 3680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3680 | 0% | 0 | 4092.9805 |  | 0 |  |  |  | 1992 |  | 1992 |  | 4092.9805 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.7 | 2024/25 On-Ice Activities | 1.2.8.7 2024/25 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 6d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.7.10.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.35 | 0 | 0 | 0 | 4092.9805 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.7.10.36 | C |  | PSL | Installation: Trench & Install Reel Anchors (Hole 6) |  | 0% | Labor Hours | TE |  |  | 81 | 77 | 0% | 2025-01-08 | 2025-01-08 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -2806 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  |  | 16 | [8 empty] | 0 | 0 | 0 | 1232 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1232 | 0% | 0 | 1370.2587 |  | 0 |  |  |  | 2806 |  | 2806 |  | 1370.2587 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.7 | 2024/25 On-Ice Activities | 1.2.8.7 2024/25 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 5d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.7.10.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.36 | 0 | 0 | 0 | 1370.2587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.7.10.37 | C |  | PSL | Installation: Relocate Hose, Cable Reels, Sensor Handling Structure (at end of installation) |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2025-01-08 | 2025-01-08 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -996 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  |  | 28 | [8 empty] | 0 | 0 | 0 | 3220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3220 | 0% | 0 | 3581.3579 |  | 0 |  |  |  | 996 |  | 996 |  | 3581.3579 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.7 | 2024/25 On-Ice Activities | 1.2.8.7 2024/25 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 5d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.7.10.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.37 | 0 | 0 | 0 | 3581.3579 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.7.10.38 | C |  | PSL | Installation: Hole Excavation, Trench & Install Cable Anchor (Hole 6) |  | 0% | Labor Hours | TE |  |  | 115 | 77 | 0% | 2025-01-08 | 2025-01-08 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -1992 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  |  | 16 | [8 empty] | 0 | 0 | 0 | 1232 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1232 | 0% | 0 | 1370.2587 |  | 0 |  |  |  | 1992 |  | 1992 |  | 1370.2587 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.7 | 2024/25 On-Ice Activities | 1.2.8.7 2024/25 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 5d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.7.10.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.38 | 0 | 0 | 0 | 1370.2587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.7.10.39 | C |  | PSL | Installation: Prepare SFC-Sensor Cable (Mount on TU20, test slip ring) - Prep for String 7 |  | 0% | Labor Hours | EN |  |  | 81 | 115 | 0% | 2025-01-08 | 2025-01-08 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -701 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  |  | 8 | [8 empty] | 0 | 0 | 0 | 920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 920 | 0% | 0 | 1023.2451 |  | 0 |  |  |  | 701 |  | 701 |  | 1023.2451 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.7 | 2024/25 On-Ice Activities | 1.2.8.7 2024/25 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 3d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.7.10.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.39 | 0 | 0 | 0 | 1023.2451 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.7.10.40 | C |  | PSL | Installation: DRILL HOLE # 6 |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2025-01-09 | 2025-01-10 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -996 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  |  | 522 | [8 empty] | 0 | 0 | 0 | 60030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60030 | 0% | 0 | 66766.7441 |  | 0 |  |  |  | 996 |  | 996 |  | 66766.7441 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.7 | 2024/25 On-Ice Activities | 1.2.8.7 2024/25 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 3d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.7.10.40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.40 | 0 | 0 | 0 | 66766.7441 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.7.10.41 | C |  | PSL | Installation: Driller Support for Dust Logging Activities |  | 0% | Labor Hours | TE |  |  | 81 | 77 | 0% | 2025-01-10 | 2025-01-10 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -1403 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  |  | 16 | [8 empty] | 0 | 0 | 0 | 1232 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1232 | 0% | 0 | 1370.2587 |  | 0 |  |  |  | 1403 |  | 1403 |  | 1370.2587 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.7 | 2024/25 On-Ice Activities | 1.2.8.7 2024/25 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 4d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.7.10.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.41 | 0 | 0 | 0 | 1370.2587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.7.10.42 | C |  | PSL | Installation: Deployment - String 6 |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2025-01-10 | 2025-01-13 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -1992 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  |  | 72 | [8 empty] | 0 | 0 | 0 | 8280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8280 | 0% | 0 | 9209.2061 |  | 0 |  |  |  | 1992 |  | 1992 |  | 9209.2061 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.7 | 2024/25 On-Ice Activities | 1.2.8.7 2024/25 On-Ice Activities | cell-link@smartsheet.com | 2021-11-30 22:21 |  | 4d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.7.10.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.42 | 0 | 0 | 0 | 9209.2061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.7.10.43 | C |  | PSL | Installation: String # 6 Deployed & Complete |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2025-01-13 | 2025-01-13 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -2988 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  |  |  | 2988 |  | 2988 |  | 0 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.7 | 2024/25 On-Ice Activities | 1.2.8.7 2024/25 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 3d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.7.10.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.7.10.44 | C |  | PSL | Installation: Closeout & Relocate Tower & TOS to Storage |  | 0% | Labor Hours | EN |  |  | 81 | 115 | 0% | 2025-01-14 | 2025-01-14 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -21042 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  |  | 32 | [8 empty] | 0 | 0 | 0 | 3680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3680 | 0% | 0 | 4092.9805 |  | 0 |  |  |  | 21042 |  | 21042 |  | 4092.9805 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.7 | 2024/25 On-Ice Activities | 1.2.8.7 2024/25 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 3d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.7.10.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.44 | 0 | 0 | 0 | 4092.9805 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.7.10.45 | C |  | PSL | Installation: Trench & Install Reel Anchors (Hole 7) |  | 0% | Labor Hours | TE |  |  | 115 | 77 | 0% | 2025-01-15 | 2025-01-15 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -11950 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  |  | 16 | [8 empty] | 0 | 0 | 0 | 1232 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1232 | 0% | 0 | 1370.2587 |  | 0 |  |  |  | 11950 |  | 11950 |  | 1370.2587 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.7 | 2024/25 On-Ice Activities | 1.2.8.7 2024/25 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 3d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.7.10.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.45 | 0 | 0 | 0 | 1370.2587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.7.10.46 | C |  | PSL | Installation: Relocate Hose, Cable Reels, Sensor Handling Structure (at end of installation) |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2025-01-15 | 2025-01-15 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -1992 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  |  | 28 | [8 empty] | 0 | 0 | 0 | 3220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3220 | 0% | 0 | 3581.3579 |  | 0 |  |  |  | 1992 |  | 1992 |  | 3581.3579 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.7 | 2024/25 On-Ice Activities | 1.2.8.7 2024/25 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 2d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.7.10.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.46 | 0 | 0 | 0 | 3581.3579 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.7.10.47 | C |  | PSL | Installation: Hole Excavation, Trench & Install Cable Anchor (Hole 7) |  | 0% | Labor Hours | EN |  |  | 81 | 115 | 0% | 2025-01-15 | 2025-01-15 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -2806 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  |  | 16 | [8 empty] | 0 | 0 | 0 | 1840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1840 | 0% | 0 | 2046.4902 |  | 0 |  |  |  | 2806 |  | 2806 |  | 2046.4902 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.7 | 2024/25 On-Ice Activities | 1.2.8.7 2024/25 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 2d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.7.10.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.47 | 0 | 0 | 0 | 2046.4902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.7.10.48 | C |  | PSL | Installation: DRILL HOLE # 7 |  | 0% | Labor Hours | TE |  |  | 115 | 77 | 0% | 2025-01-16 | 2025-01-17 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -996 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  |  | 522 | [8 empty] | 0 | 0 | 0 | 40194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40194 | 0% | 0 | 44704.6895 |  | 0 |  |  |  | 996 |  | 996 |  | 44704.6895 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.7 | 2024/25 On-Ice Activities | 1.2.8.7 2024/25 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 2d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.7.10.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.48 | 0 | 0 | 0 | 44704.6895 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.7.10.49 | C |  | PSL | Installation: Deployment - String 7 |  | 0% | Labor Hours | EN |  |  | 81 | 115 | 0% | 2025-01-17 | 2025-01-20 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -1403 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  |  | 72 | [8 empty] | 0 | 0 | 0 | 8280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8280 | 0% | 0 | 9209.2061 |  | 0 |  |  |  | 1403 |  | 1403 |  | 9209.2061 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.7 | 2024/25 On-Ice Activities | 1.2.8.7 2024/25 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 2d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.7.10.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.49 | 0 | 0 | 0 | 9209.2061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.7.10.50 | C |  | PSL | Installation: String # 7 Deployed & Complete |  | 0% | Labor Hours | TE |  |  | 115 | 77 | 0% | 2025-01-20 | 2025-01-20 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -1992 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  |  |  | 1992 |  | 1992 |  | 0 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.7 | 2024/25 On-Ice Activities | 1.2.8.7 2024/25 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 2d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.7.10.50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.7.10.51 | C |  | PSL | Installation: Closeout & Relocate Tower & TOS to Storage Change duration 7 days |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2025-01-20 | 2025-01-20 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -1992 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  |  | 32 | [8 empty] | 0 | 0 | 0 | 3680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3680 | 0% | 0 | 4092.9805 |  | 0 |  |  |  | 1992 |  | 1992 |  | 4092.9805 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.7 | 2024/25 On-Ice Activities | 1.2.8.7 2024/25 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 2d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.7.10.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.51 | 0 | 0 | 0 | 4092.9805 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.7.10.52 | C |  | PSL | Installation: Drilling & Installation Complete |  | 0% | Labor Hours | TE |  |  | 115 | 77 | 0% | 2025-01-21 | 2025-01-21 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -996 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  |  |  | 996 |  | 996 |  | 0 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.7 | 2024/25 On-Ice Activities | 1.2.8.7 2024/25 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 2d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.7.10.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.10.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.7.11.1 | C |  | PSL | Decommission and Store: Remove & Retro/Store All DNF |  | 0% | Labor Hours | TE |  |  | 115 | 77 | 0% | 2025-01-10 | 2025-01-23 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -2988 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  |  | 375 | [8 empty] | 0 | 0 | 0 | 28875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28875 | 0% | 0 | 32115.4379 |  | 0 |  |  |  | 2988 |  | 2988 |  | 32115.4379 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.7 | 2024/25 On-Ice Activities | 1.2.8.7 2024/25 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 4d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.7.11.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.11.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.11.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.11.1 | 0 | 0 | 0 | 32115.4379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.11.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.11.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.11.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.11.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.7.11.2 | C |  | PSL | Decommission and Store:Decommission SES & TOS, Disconnect all cables hoses, connections |  | 0% | Labor Hours | EN |  |  | 81 | 115 | 0% | 2025-01-13 | 2025-01-20 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -21042 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  |  | 485 | [8 empty] | 0 | 0 | 0 | 55775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55775 | 0% | 0 | 62034.2354 |  | 0 |  |  |  | 21042 |  | 21042 |  | 62034.2354 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.7 | 2024/25 On-Ice Activities | 1.2.8.7 2024/25 On-Ice Activities | cell-link@smartsheet.com | 2021-11-30 22:21 |  | 4d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.7.11.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.11.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.11.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.11.2 | 0 | 0 | 0 | 62034.2354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.11.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.11.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.11.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.11.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.7.11.3 | C |  | PSL | Decommission and Store: Winterize all EHWD equipment |  | 0% | Labor Hours | TE |  |  | 115 | 77 | 0% | 2025-01-20 | 2025-01-31 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -11950 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  |  | 585 | [8 empty] | 0 | 0 | 0 | 45045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45045 | 0% | 0 | 50100.0831 |  | 0 |  |  |  | 11950 |  | 11950 |  | 50100.0831 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.7 | 2024/25 On-Ice Activities | 1.2.8.7 2024/25 On-Ice Activities | cell-link@smartsheet.com | 2021-11-30 22:21 |  | 4d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.7.11.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.11.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.11.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.11.3 | 0 | 0 | 0 | 50100.0831 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.11.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.11.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.11.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.11.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.7.11.4 | C |  | PSL | Decommission and Store: Remove Drill Hose from MSHR, Respool & Ship to ZCM |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2025-01-12 | 2025-01-16 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -1992 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  |  | 217 | [8 empty] | 0 | 0 | 0 | 24955 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24955 | 0% | 0 | 27755.5239 |  | 0 |  |  |  | 1992 |  | 1992 |  | 27755.5239 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.7 | 2024/25 On-Ice Activities | 1.2.8.7 2024/25 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 2d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.7.11.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.11.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.11.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.11.4 | 0 | 0 | 0 | 27755.5239 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.11.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.11.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.11.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.11.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.7.11.5 | C |  | PSL | Decommission and Store: Shipment of Drill Hose to ZCM |  | 0% | Labor Hours | TE |  |  | 81 | 77 | 0% | 2025-01-17 | 2025-01-17 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -2806 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  |  | 40 | [8 empty] | 0 | 0 | 0 | 3080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3080 | 0% | 0 | 3425.6467 |  | 0 |  |  |  | 2806 |  | 2806 |  | 3425.6467 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.7 | 2024/25 On-Ice Activities | 1.2.8.7 2024/25 On-Ice Activities | cell-link@smartsheet.com | 2021-11-30 22:21 |  | 2d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.7.11.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.11.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.11.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.11.5 | 0 | 0 | 0 | 3425.6467 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.11.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.11.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.11.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.11.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.7.11.6 | C |  | PSL | Decommission and Store: Inventory & Photograph EHWD, Document Repairs needed |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2025-01-23 | 2025-01-27 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -1992 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  |  | 325 | [8 empty] | 0 | 0 | 0 | 37375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37375 | 0% | 0 | 41569.333 |  | 0 |  |  |  | 1992 |  | 1992 |  | 41569.333 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.7 | 2024/25 On-Ice Activities | 1.2.8.7 2024/25 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 3d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.7.11.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.11.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.11.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.11.6 | 0 | 0 | 0 | 41569.333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.11.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.11.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.11.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.11.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.7.11.7 | C |  | PSL | Decommission and Store: UNL Equipment - Deliver to Cargo for Retro or Redistribution |  | 0% | Labor Hours | TE |  |  | 81 | 77 | 0% | 2025-01-27 | 2025-01-29 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -2806 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  |  | 80 | [8 empty] | 0 | 0 | 0 | 6160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6160 | 0% | 0 | 6851.2934 |  | 0 |  |  |  | 2806 |  | 2806 |  | 6851.2934 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.7 | 2024/25 On-Ice Activities | 1.2.8.7 2024/25 On-Ice Activities | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 3d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.7.11.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.11.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.11.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.11.7 | 0 | 0 | 0 | 6851.2934 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.11.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.11.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.11.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.11.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.7.11.8 | C |  | PSL | Decommission and Store: Crate and Deliver EHWD Equipment to Cargo for Retrograde or Redistribution |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2025-01-23 | 2025-01-29 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -996 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  |  | 225 | [8 empty] | 0 | 0 | 0 | 25875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25875 | 0% | 0 | 28778.769 |  | 0 |  |  |  | 996 |  | 996 |  | 28778.769 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.7 | 2024/25 On-Ice Activities | 1.2.8.7 2024/25 On-Ice Activities | cell-link@smartsheet.com | 2021-11-30 22:21 |  | 2d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.7.11.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.11.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.11.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.11.8 | 0 | 0 | 0 | 28778.769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.11.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.11.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.11.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.11.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.8.7.11.9 | C |  | PSL | Decommission and Store: Cargo Retro (23/24) |  | 0% | Labor Hours | EN |  |  | 81 | 115 | 0% | 2025-01-17 | 2025-02-11 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -1403 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  |  |  | 1403 |  | 1403 |  | 0 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.8 | Drill Field Seasons | 1.2.8 Drill Field Seasons | 1.2.8.7 | 2024/25 On-Ice Activities | 1.2.8.7 2024/25 On-Ice Activities | cell-link@smartsheet.com | 2021-11-30 22:21 |  | 2d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.8.7.11.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.11.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.11.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.11.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.11.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.11.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.11.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8.7.11.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.9.2.1 | C |  | UW | String: Plan & Coordinate Installation (2020-2021) | Tosi | 0% | Labor Hours | SS |  |  | 81 | 38 | 35% | 2020-10-01 | 2021-09-28 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 9719 | 0 | [5 empty] | 9719 |  | 0 | Labor - LoE | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.9 | String/Cable Installation | 1.2.9 String/Cable Installation | 1.2.9.2 | String/Cable Installation 2020-21 | 1.2.9.2 String/Cable Installation 2020-21 | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 71d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.9.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.9.2.3 | C |  | UW | String: Procure Installation Hardware Samples |  | 0% | Labor Hours | SS |  |  | 115 | 55 | 35% | 2021-09-28 | 2021-09-28 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 37922.58 | [5 empty] | 42228 |  | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.9 | String/Cable Installation | 1.2.9 String/Cable Installation | 1.2.9.2 | String/Cable Installation 2020-21 | 1.2.9.2 String/Cable Installation 2020-21 | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 314d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.9.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.9.2.3 | C |  | UW | String: Procure Installation Hardware Samples |  |  | CapEx | SS |  |  | 115 | 1 | 0% | 2021-09-28 | 2021-09-28 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 0 | CapEx | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.9 | String/Cable Installation | 1.2.9 String/Cable Installation | 1.2.9.2 | String/Cable Installation 2020-21 | 1.2.9.2 String/Cable Installation 2020-21 | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 314d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.9.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.9.2.4 | C |  | UW | String: Installation Procedures Document Drafted |  | 0% | Labor Hours | SS |  |  |  | 55 | 35% | 2021-05-01 | 2021-07-30 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.9 | String/Cable Installation | 1.2.9 String/Cable Installation | 1.2.9.2 | String/Cable Installation 2020-21 | 1.2.9.2 String/Cable Installation 2020-21 | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.9.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.9.2.4 | C |  | PSL | String: Design Sensor Handling Structure (Attached to TOS) |  | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2021-05-01 | 2021-07-30 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | 39886 |  |  |  |  | 43073 |  | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.9 | String/Cable Installation | 1.2.9 String/Cable Installation | 1.2.9.2 | String/Cable Installation 2020-21 | 1.2.9.2 String/Cable Installation 2020-21 | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 313d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.9.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.9.3.1 | C |  | UW | String: Plan & Coordinate Installation (2021-2022) | Tosi | 46.15% | Labor Hours | SS |  | VQ |  | 38 | 35% | 2021-10-01 | 2022-09-30 |  |  |  |  | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 4104 | 4104 | 4104 | 4104 | 4104 | 4104 | 4104 | 4104 | 4104 | 4104 | 4104 | 4104 | 49248 | 53% | 26101.44 | 78624.2962 | 78624.2962 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 78624.2962 | Labor - LoE | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.9 | String/Cable Installation | 1.2.9 String/Cable Installation | 1.2.9.3 | String/Cable Installation 2021-22 | 1.2.9.3 String/Cable Installation 2021-22 | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.9.3.1 | 6552.0247 | 6552.0247 | 6552.0247 | 6552.0247 | 6552.0247 | 6552.0247 | 6552.0247 | 6552.0247 | 6552.0247 | 6552.0247 | 6552.0247 | 6552.0247 | 1.2.9.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.3.1 | 3172.1252 | 3172.1252 | 3172.1252 | 3172.1252 | 3172.1252 | 3172.1252 | 3172.1252 | 3172.1252 | 3172.1252 | 3172.1252 | 3172.1252 | 3172.1252 | 38065.5029 | 1.2.9.3.1 | 1110.2438 | 1110.2438 | 1110.2438 | 1110.2438 | 1110.2438 | 1110.2438 | 1110.2438 | 1110.2438 | 1110.2438 | 1110.2438 | 1110.2438 | 1110.2438 | 13322.926 | 1.2.9.3.1 | 2269.6556 | 2269.6556 | 2269.6556 | 2269.6556 | 2269.6556 | 2269.6556 | 2269.6556 | 2269.6556 | 2269.6556 | 2269.6556 | 2269.6556 | 2269.6556 | 27235.8673 | 78624.2962 | 1.2.9.3.1 | 78624.2962 | 78624.2962 | 6552.0247 | 13104.0494 | 19656.074 | 26208.0987 | 32760.1234 | 39312.1481 | 45864.1728 | 52416.1975 | 58968.2221 | 65520.2468 | 72072.2715 | 78624.2962 | 6552.0247 | 13104.0494 | 19656.074 | 26208.0987 | 32760.1234 | 39312.1481 | 45864.1728 | 52416.1975 | 58968.2221 | 65520.2468 | 72072.2715 | 78624.2962
| 1.2 | 1.2.9.3.2 | C |  | PSL | String: Sensor Handling Process Defined |  | 1.333% | Labor Hours | EN |  | VQ |  | 115 | 0% | 2021-11-15 | 2021-11-15 | [7 empty] | 8 | 8 | 8 | [6 empty] | 0 | 0 | 0 | 920 | 920 | 920 | 0 | 0 | 0 | 0 | 0 | 0 | 2760 | 0% | 0 | 2879.9558 | 2879.9558 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | [9 empty] | 2879.9558 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.9 | String/Cable Installation | 1.2.9 String/Cable Installation | 1.2.9.3 | String/Cable Installation 2021-22 | 1.2.9.3 String/Cable Installation 2021-22 | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.9.3.2 | 0 | 0 | 0 | 959.9853 | 959.9853 | 959.9853 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.3.2 | 0 | 0 | 0 | 959.9853 | 959.9853 | 959.9853 | 0 | 0 | 0 | 0 | 0 | 0 | 2879.9558 | 1.2.9.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2879.9558 | 1.2.9.3.2 | 2879.9558 | 2879.9558 | 0 | 0 | 0 | 959.9853 | 1919.9705 | 2879.9558 | 2879.9558 | 2879.9558 | 2879.9558 | 2879.9558 | 2879.9558 | 2879.9558 | 0 | 0 | 0 | 959.9853 | 1919.9705 | 2879.9558 | 2879.9558 | 2879.9558 | 2879.9558 | 2879.9558 | 2879.9558 | 2879.9558
| 1.2 | 1.2.9.3.3 | C |  | PSL | String: Procure & Fabricate Sensor Handling Structure |  | 11.11% | Labor Hours | TE |  | VQ |  | 77 | 0% | 2021-11-16 | 2022-07-18 | [7 empty] | 40 | 40 | 40 | 40 | 20 | 20 |  |  |  | 0 | 0 | 0 | 3080 | 3080 | 3080 | 3080 | 1540 | 1540 | 0 | 0 | 0 | 15400 | 0% | 0 | 16069.3186 | 16069.3186 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | [9 empty] | 16069.3186 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.9 | String/Cable Installation | 1.2.9 String/Cable Installation | 1.2.9.3 | String/Cable Installation 2021-22 | 1.2.9.3 String/Cable Installation 2021-22 | cell-link@smartsheet.com | 2021-11-30 22:32 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.9.3.3 | 0 | 0 | 0 | 3213.8637 | 3213.8637 | 3213.8637 | 3213.8637 | 1606.9319 | 1606.9319 | 0 | 0 | 0 | 1.2.9.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.3.3 | 0 | 0 | 0 | 3213.8637 | 3213.8637 | 3213.8637 | 3213.8637 | 1606.9319 | 1606.9319 | 0 | 0 | 0 | 16069.3186 | 1.2.9.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16069.3186 | 1.2.9.3.3 | 16069.3186 | 96815.245 | 0 | 0 | 0 | 3213.8637 | 6427.7275 | 9641.5912 | 12855.4549 | 14462.3868 | 16069.3186 | 16069.3186 | 16069.3186 | 16069.3186 | 0 | 38959.9853 | 55959.9853 | 81079.8343 | 84293.698 | 88467.547 | 91681.4107 | 94248.3279 | 96815.245 | 96815.245 | 96815.245 | 96815.245
| 1.2 | 1.2.9.3.3 | C |  | PSL | String: Procure & Fabricate Sensor Handling Structure |  | 2.222% | Labor Hours | EN |  | VQ |  | 115 | 0% | 2021-11-16 | 2022-07-18 | [5 empty] | 8 |  | 8 |  | 8 |  | 8 | 8 |  |  |  | 0 | 920 | 0 | 920 | 0 | 920 | 0 | 920 | 920 | 0 | 0 | 0 | 4600 | 0% | 0 | 4799.9263 | 4799.9263 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | [9 empty] | 4799.9263 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.9 | String/Cable Installation | 1.2.9 String/Cable Installation | 1.2.9.3 | String/Cable Installation 2021-22 | 1.2.9.3 String/Cable Installation 2021-22 | cell-link@smartsheet.com | 2021-11-30 22:32 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.9.3.3 | 0 | 959.9853 | 0 | 959.9853 | 0 | 959.9853 | 0 | 959.9853 | 959.9853 | 0 | 0 | 0 | 1.2.9.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.3.3 | 0 | 959.9853 | 0 | 959.9853 | 0 | 959.9853 | 0 | 959.9853 | 959.9853 | 0 | 0 | 0 | 4799.9263 | 1.2.9.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4799.9263 | 1.2.9.3.3 | 4799.9263 | 80745.9263 | 0 | 959.9853 | 959.9853 | 1919.9705 | 1919.9705 | 2879.9558 | 2879.9558 | 3839.9411 | 4799.9263 | 4799.9263 | 4799.9263 | 4799.9263 | 0 | 38959.9853 | 55959.9853 | 77865.9705 | 77865.9705 | 78825.9558 | 78825.9558 | 79785.9411 | 80745.9263 | 80745.9263 | 80745.9263 | 80745.9263
| 1.2 | 1.2.9.3.3 | C |  | PSL | String: Procure & Fabricate Sensor Handling Structure |  |  | CapEx |  |  | VQ |  | 1 | 0% | 2021-11-16 | 2022-07-18 |  |  |  | Cost includes building materials, crane fork, a dolly and a lift table, conveyor belt. Truck crane estimated 20k. |  | 38000 | 17000 | 20946 | [8 empty] | 0 | 38000 | 17000 | 20946 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75946 | 53% | 0 | 75946 | 75946 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 75946 | CapEx | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.9 | String/Cable Installation | 1.2.9 String/Cable Installation | 1.2.9.3 | String/Cable Installation 2021-22 | 1.2.9.3 String/Cable Installation 2021-22 | cell-link@smartsheet.com | 2021-11-30 22:32 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.9.3.3 | 0 | 38000 | 17000 | 20946 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.3.3 | 0 | 38000 | 17000 | 20946 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75946 | 1.2.9.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75946 | 1.2.9.3.3 | 75946 | 75946 | 0 | 38000 | 55000 | 75946 | 75946 | 75946 | 75946 | 75946 | 75946 | 75946 | 75946 | 75946 | 0 | 38000 | 55000 | 75946 | 75946 | 75946 | 75946 | 75946 | 75946 | 75946 | 75946 | 75946
| 1.2 | 1.2.9.3.4 | C |  | PSL | String: Installation Procedure Draft and Test - PSL Support for Deployment Tower Ops |  | 0.8889% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2022-04-01 | 2022-08-31 | [10 empty] | 2 | 4 | 4 | 4 | 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 230 | 460 | 460 | 460 | 230 | 0 | 1840 | 0% | 0 | 1919.9705 | 1919.9705 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 9285.2211 | [5 empty] | 9384 |  | 1919.9705 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.9 | String/Cable Installation | 1.2.9 String/Cable Installation | 1.2.9.3 | String/Cable Installation 2021-22 | 1.2.9.3 String/Cable Installation 2021-22 | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 95d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.9.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 239.9963 | 479.9926 | 479.9926 | 479.9926 | 239.9963 | 0 | 1.2.9.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 239.9963 | 479.9926 | 479.9926 | 479.9926 | 239.9963 | 0 | 1919.9705 | 1.2.9.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1919.9705 | 1.2.9.3.4 | 1919.9705 | 1919.9705 | 0 | 0 | 0 | 0 | 0 | 0 | 239.9963 | 719.989 | 1199.9816 | 1679.9742 | 1919.9705 | 1919.9705 | 0 | 0 | 0 | 0 | 0 | 0 | 239.9963 | 719.989 | 1199.9816 | 1679.9742 | 1919.9705 | 1919.9705
| 1.2 | 1.2.9.3.5 | C |  | UW | String: Procedures for Installation Document Complete |  | 0% | Labor Hours | SC |  |  | 81 | 45 | 35% | 2022-08-15 | 2022-08-15 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 13219 | [5 empty] | 13219 |  | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.9 | String/Cable Installation | 1.2.9 String/Cable Installation | 1.2.9.3 | String/Cable Installation 2021-22 | 1.2.9.3 String/Cable Installation 2021-22 | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 95d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.9.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.9.3.6 | C |  | PSL | String: Procedure and Hardware Review |  | 0.8889% | Labor Hours | EN |  |  | 81 | 115 | 0% | 2022-09-15 | 2022-09-15 | [15 empty] | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1840 | 1840 | 0% | 0 | 1919.9705 | 1919.9705 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 13219 | [5 empty] | 13219 |  | 1919.9705 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.9 | String/Cable Installation | 1.2.9 String/Cable Installation | 1.2.9.3 | String/Cable Installation 2021-22 | 1.2.9.3 String/Cable Installation 2021-22 | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 95d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.9.3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1919.9705 | 1.2.9.3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1919.9705 | 1919.9705 | 1.2.9.3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1919.9705 | 1.2.9.3.6 | 1919.9705 | 1919.9705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1919.9705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1919.9705
| 1.2 | 1.2.9.3.7 | C |  | PSL | String: Hole Lifetime and Diameter Evaluation Complete |  | 1.667% | Labor Hours | EN |  | VQ | 1 | 115 | 0% | 2022-05-01 | 2022-07-29 | [11 empty] | 10 | 10 | 10 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1150 | 1150 | 1150 | 0 | 0 | 3450 | 0% | 0 | 3599.9448 | 3599.9448 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 42369 | [5 empty] | 42369 |  | 3599.9448 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.9 | String/Cable Installation | 1.2.9 String/Cable Installation | 1.2.9.3 | String/Cable Installation 2021-22 | 1.2.9.3 String/Cable Installation 2021-22 | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 95d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.9.3.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1199.9816 | 1199.9816 | 1199.9816 | 0 | 0 | 1.2.9.3.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.3.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.3.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.3.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1199.9816 | 1199.9816 | 1199.9816 | 0 | 0 | 3599.9448 | 1.2.9.3.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.3.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3599.9448 | 1.2.9.3.7 | 3599.9448 | 3599.9448 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1199.9816 | 2399.9632 | 3599.9448 | 3599.9448 | 3599.9448 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1199.9816 | 2399.9632 | 3599.9448 | 3599.9448 | 3599.9448
| 1.2 | 1.2.9.3.8 | C |  | PSL | String: Deployment Connectivity Monitor Design, Procurement and System Integration |  | 4.444% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2022-06-02 | 2024-05-01 | [12 empty] | 40 | 40 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4600 | 4600 | 0 | 0 | 9200 | 0% | 0 | 9599.8527 | 9599.8527 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | 4786 |  |  |  |  | 4786 |  | 9599.8527 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.9 | String/Cable Installation | 1.2.9 String/Cable Installation | 1.2.9.3 | String/Cable Installation 2021-22 | 1.2.9.3 String/Cable Installation 2021-22 | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 11d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.9.3.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4799.9263 | 4799.9263 | 0 | 0 | 1.2.9.3.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.3.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.3.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.3.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4799.9263 | 4799.9263 | 0 | 0 | 9599.8527 | 1.2.9.3.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.3.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9599.8527 | 1.2.9.3.8 | 9599.8527 | 29599.8527 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4799.9263 | 9599.8527 | 9599.8527 | 9599.8527 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14799.9263 | 29599.8527 | 29599.8527 | 29599.8527
| 1.2 | 1.2.9.3.8 | C |  | UW | String: Deployment Connectivity Monitor Design, Procurement and System Integration |  |  | CapEx | EN |  |  |  | 1 | 0% | 2022-06-02 | 2024-05-01 |  |  |  | 20k for slip ring module for DOM connectivity, 4 k for hand held devices | [8 empty] | 10000 | 10000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 10000 | 0 | 0 | 20000 | 53% | 0 | 20000 | 20000 |  |  | 4000 | [9 empty] | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 53% | 0 | 4000 | 4000 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 24000 | CapEx | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.9 | String/Cable Installation | 1.2.9 String/Cable Installation | 1.2.9.3 | String/Cable Installation 2021-22 | 1.2.9.3 String/Cable Installation 2021-22 | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 11d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.9.3.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 10000 | 0 | 0 | 1.2.9.3.8 | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.3.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.3.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.3.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 10000 | 0 | 0 | 20000 | 1.2.9.3.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.3.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 1.2.9.3.8 | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 20000 | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 20000 | 20000 | 20000
| 1.2 | 1.2.9.3.10 | C |  | PSL | String: Define Pressure Sensor Requirements |  | 0.1111% | Labor Hours | EN |  |  |  | 115 | 0% | 2021-10-01 | 2022-02-04 |  | TRUE | [5 empty] | 2 | [8 empty] | 0 | 0 | 0 | 230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 230 | 0% | 0 | 239.9963 | 239.9963 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | [7 empty] | 239.9963 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.9 | String/Cable Installation | 1.2.9 String/Cable Installation | 1.2.9.3 | String/Cable Installation 2021-22 | 1.2.9.3 String/Cable Installation 2021-22 | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 24d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.9.3.10 | 0 | 0 | 0 | 239.9963 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.3.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.3.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.3.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.3.10 | 0 | 0 | 0 | 239.9963 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 239.9963 | 1.2.9.3.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.3.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 239.9963 | 1.2.9.3.10 | 239.9963 | 239.9963 | 0 | 0 | 0 | 239.9963 | 239.9963 | 239.9963 | 239.9963 | 239.9963 | 239.9963 | 239.9963 | 239.9963 | 239.9963 | 0 | 0 | 0 | 239.9963 | 239.9963 | 239.9963 | 239.9963 | 239.9963 | 239.9963 | 239.9963 | 239.9963 | 239.9963
| 1.2 | 1.2.9.3.11 | C |  | UW | String: Finalize Sensor Handling Process & Procure Handling Equipment |  | 0.3846% | Labor Hours | SS |  |  | 115 | 55 | 35% | 2022-06-02 | 2022-09-01 | [12 empty] | 4 |  | 4 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 297 | 0 | 297 | 0 | 594 | 53% | 314.82 | 948.3194 | -65528.6806 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 |  | 66477 |  |  |  | 65901 |  | 948.3194 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.9 | String/Cable Installation | 1.2.9 String/Cable Installation | 1.2.9.3 | String/Cable Installation 2021-22 | 1.2.9.3 String/Cable Installation 2021-22 | cell-link@smartsheet.com | 2021-11-30 22:32 |  | 313d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.9.3.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 474.1597 | 0 | 474.1597 | 0 | 1.2.9.3.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.3.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.3.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.3.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 229.5617 | 0 | 229.5617 | 0 | 459.1234 | 1.2.9.3.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80.3466 | 0 | 80.3466 | 0 | 160.6932 | 1.2.9.3.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 164.2514 | 0 | 164.2514 | 0 | 328.5028 | 948.3194 | 1.2.9.3.11 | 948.3194 | 948.3194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 474.1597 | 474.1597 | 948.3194 | 948.3194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 474.1597 | 474.1597 | 948.3194 | 948.3194
| 1.2 | 1.2.9.3.11 | C |  | UW | String: Finalize Sensor Handling Process & Procure Handling Equipment |  |  | CapEx | SS |  |  | 115 | 1 | 0% | 2022-06-02 | 2022-09-01 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 0 | CapEx | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.9 | String/Cable Installation | 1.2.9 String/Cable Installation | 1.2.9.3 | String/Cable Installation 2021-22 | 1.2.9.3 String/Cable Installation 2021-22 | cell-link@smartsheet.com | 2021-11-30 22:32 |  | 313d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.9.3.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.3.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.3.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.3.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.3.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.3.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.3.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.3.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.9.3.12 | C |  | PSL | String: Crate, Prepare & Ship Sensor Handling Structure |  | 1.333% | Labor Hours | TE |  |  |  | 77 | 0% | 2022-09-02 | 2022-10-03 | [15 empty] | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1848 | 1848 | 0% | 0 | 1928.3182 | 1928.3182 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | [7 empty] | 1928.3182 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.9 | String/Cable Installation | 1.2.9 String/Cable Installation | 1.2.9.3 | String/Cable Installation 2021-22 | 1.2.9.3 String/Cable Installation 2021-22 | cell-link@smartsheet.com | 2021-11-30 22:32 |  | 2d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.9.3.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1928.3182 | 1.2.9.3.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.3.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.3.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.3.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1928.3182 | 1928.3182 | 1.2.9.3.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.3.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1928.3182 | 1.2.9.3.12 | 1928.3182 | 7283.3182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1928.3182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7283.3182
| 1.2 | 1.2.9.3.12 | C |  | PSL | String: Crate, Prepare & Ship Sensor Handling Structure |  |  | M & S | TE |  |  |  | 1 | 0% | 2022-09-02 | 2022-10-03 | [15 empty] | 3500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3500 | 3500 | 53% | 1855 | 5355 | 5355 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 5355 | M & S | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.9 | String/Cable Installation | 1.2.9 String/Cable Installation | 1.2.9.3 | String/Cable Installation 2021-22 | 1.2.9.3 String/Cable Installation 2021-22 | cell-link@smartsheet.com | 2021-11-30 22:32 |  | 2d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.9.3.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5355 | 1.2.9.3.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.3.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.3.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.3.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3500 | 3500 | 1.2.9.3.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.3.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1855 | 1855 | 5355 | 1.2.9.3.12 | 5355 | 5355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5355
| 1.2 | 1.2.9.3.13 | C |  | UW | String: Procure Installation Hardware Samples |  | 0% | Labor Hours | SS |  |  |  | 55 | 35% | 2021-11-04 | 2022-02-04 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.9 | String/Cable Installation | 1.2.9 String/Cable Installation | 1.2.9.3 | String/Cable Installation 2021-22 | 1.2.9.3 String/Cable Installation 2021-22 | cell-link@smartsheet.com | 2021-11-30 22:32 |  | 314d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.9.3.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.3.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.3.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.3.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.3.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.3.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.3.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.3.13 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000
| 1.2 | 1.2.9.3.13 | C |  | UW | String: Procure Installation Hardware Samples |  |  | CapEx | SS |  |  |  | 1 | 0% | 2021-11-04 | 2022-02-04 | [6 empty] | 1000 | 1000 | [8 empty] | 0 | 0 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 53% | 0 | 2000 | 2000 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 2000 | CapEx | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.9 | String/Cable Installation | 1.2.9 String/Cable Installation | 1.2.9.3 | String/Cable Installation 2021-22 | 1.2.9.3 String/Cable Installation 2021-22 | cell-link@smartsheet.com | 2021-11-30 22:32 |  | 314d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.9.3.13 | 0 | 0 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.3.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.3.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.3.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.3.13 | 0 | 0 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 1.2.9.3.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.3.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 1.2.9.3.13 | 2000 | 2000 | 0 | 0 | 1000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 0 | 0 | 1000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000
| 1.2 | 1.2.9.4.1 | C |  | UW | String: Plan & Coordinate Installation (2022-2023) | Tosi | 0% | Labor Hours | SS |  |  |  | 38 | 35% | 2022-10-03 | 2023-10-02 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | -2592 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 4104 | 4104 | 4104 | 4104 | 4104 | 4104 | 4104 | 4104 | 4104 | 4104 | 4104 | 4104 | 49248 | 53% | 26101.44 | 80314.7186 | 80314.7186 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 |  | 2592 | [5 empty] | 80314.7186 | Labor - LoE | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.9 | String/Cable Installation | 1.2.9 String/Cable Installation | 1.2.9.4 | String/Cable Installation 2022-23 | 1.2.9.4 String/Cable Installation 2022-23 | cell-link@smartsheet.com | 2021-11-30 22:32 |  | 2d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.9.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.4.1 | 6692.8932 | 6692.8932 | 6692.8932 | 6692.8932 | 6692.8932 | 6692.8932 | 6692.8932 | 6692.8932 | 6692.8932 | 6692.8932 | 6692.8932 | 6692.8932 | 1.2.9.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.9.4.2 | C |  | UW | String: Installation Review |  | 0% | Labor Hours | SE |  |  |  | 55 | 35% | 2023-07-31 | 2023-08-07 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 | [7 empty] | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.9 | String/Cable Installation | 1.2.9 String/Cable Installation | 1.2.9.4 | String/Cable Installation 2022-23 | 1.2.9.4 String/Cable Installation 2022-23 | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 2d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.9.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.9.4.3 | C |  | UW | String: Procure Installation Kit Samples |  | 0% | Labor Hours | SE |  |  |  | 55 | 35% | 2023-07-31 | 2023-07-31 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 | [7 empty] | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.9 | String/Cable Installation | 1.2.9 String/Cable Installation | 1.2.9.4 | String/Cable Installation 2022-23 | 1.2.9.4 String/Cable Installation 2022-23 | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 3d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.9.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.9.4.4 | C |  | UW | String: South Pole Acceptance Testing (SPAT) Process & Support Requirements Defined |  | 0% | Labor Hours | SE |  |  |  | 55 | 35% | 2023-09-22 | 2023-09-22 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 | [7 empty] | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.9 | String/Cable Installation | 1.2.9 String/Cable Installation | 1.2.9.4 | String/Cable Installation 2022-23 | 1.2.9.4 String/Cable Installation 2022-23 | cell-link@smartsheet.com | 2021-11-30 22:32 |  | 3d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.9.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.9.4.5 | C |  | UW | String: Procure Installation Kits and Weights |  |  | CapEx | SE |  |  | 1 | 1 | 0% | 2023-06-01 | 2023-06-29 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | -2929 | [8 empty] | 125000 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125000 | 0 | 0 | 0 | 125000 | 53% | 0 | 125000 | 125000 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 |  | 2929 |  |  |  | 2929 |  | 125000 | CapEx | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.9 | String/Cable Installation | 1.2.9 String/Cable Installation | 1.2.9.4 | String/Cable Installation 2022-23 | 1.2.9.4 String/Cable Installation 2022-23 | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 3d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.9.4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125000 | 0 | 0 | 0 | 1.2.9.4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.9.4.6 | C |  | PSL | String: Procure Laser Rangers ($1k) & Pressure Sensors ($90k - 7 plus spares) |  |  | CapEx | SE |  |  | 81 | 1 | 0% | 2022-05-01 | 2023-09-21 | [11 empty] | 12000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 | 0 | 0 | 0 | 0 | 12000 | 53% | 0 | 12000 | 9937 | [7 empty] | 79000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79000 | 0 | 0 | 0 | 0 | 79000 | 53% | 0 | 79000 | 79000 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 |  | 2063 |  |  |  | 2063 |  | 91000 | CapEx | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.9 | String/Cable Installation | 1.2.9 String/Cable Installation | 1.2.9.4 | String/Cable Installation 2022-23 | 1.2.9.4 String/Cable Installation 2022-23 | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 3d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.9.4.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 | 0 | 0 | 0 | 0 | 1.2.9.4.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79000 | 0 | 0 | 0 | 0 | 1.2.9.4.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.4.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.4.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 | 0 | 0 | 0 | 0 | 12000 | 1.2.9.4.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.4.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 | 1.2.9.4.6 | 12000 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 | 12000 | 12000 | 12000 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 | 12000 | 12000 | 12000 | 12000
| 1.2 | 1.2.9.4.7 | C |  | UW | String: Deployment Connectivity Monitor Fabrication Complete |  | 0% | Labor Hours | SC |  |  |  | 45 | 35% | 2023-07-31 | 2023-07-31 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 | [7 empty] | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.9 | String/Cable Installation | 1.2.9 String/Cable Installation | 1.2.9.4 | String/Cable Installation 2022-23 | 1.2.9.4 String/Cable Installation 2022-23 | cell-link@smartsheet.com | 2021-11-30 22:32 |  | 3d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.9.4.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.4.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.4.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.4.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.4.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.4.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.4.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.4.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.9.4.8 | C |  | UW | String: Hole Lifetime Drill Model Development Refinement |  | 0% | Labor Hours | SC |  |  |  | 45 | 35% | 2022-10-03 | 2022-11-01 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 | [7 empty] | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.9 | String/Cable Installation | 1.2.9 String/Cable Installation | 1.2.9.4 | String/Cable Installation 2022-23 | 1.2.9.4 String/Cable Installation 2022-23 | cell-link@smartsheet.com | 2021-11-30 22:32 |  | 3d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.9.4.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.4.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.4.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.4.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.4.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.4.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.4.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.4.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.9.4.9 | C |  | PSL | String: Prepare Installation Hardware for Shipping |  | 0% | Labor Hours | TE |  |  |  | 77 | 0% | 2023-05-01 | 2023-05-30 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -3880 | [7 empty] | 10 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 770 | 0 | 0 | 0 | 0 | 770 | 0% | 0 | 820.7405 | 820.7405 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 3880 | [5 empty] | 820.7405 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.9 | String/Cable Installation | 1.2.9 String/Cable Installation | 1.2.9.4 | String/Cable Installation 2022-23 | 1.2.9.4 String/Cable Installation 2022-23 | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 3d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.9.4.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.4.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 820.7405 | 0 | 0 | 0 | 0 | 1.2.9.4.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.4.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.4.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.4.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.4.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.4.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.9.4.10 | C |  | UW | String: Ship Installation Kits and Weights |  |  | M & S | TE |  |  |  | 1 | 0% | 2023-05-31 | 2023-06-29 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | -3880 | [8 empty] | 6500 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6500 | 0 | 0 | 0 | 6500 | 53% | 3445 | 9945 | 9945 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 |  | 3880 | [5 empty] | 9945 | M & S | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.9 | String/Cable Installation | 1.2.9 String/Cable Installation | 1.2.9.4 | String/Cable Installation 2022-23 | 1.2.9.4 String/Cable Installation 2022-23 | cell-link@smartsheet.com | 2021-11-30 22:32 |  | 3d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.9.4.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.4.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9945 | 0 | 0 | 0 | 1.2.9.4.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.4.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.4.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.4.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.4.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.4.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.9.4.11 | C |  | UW | String: Modify Tower/Bridge & ICL for Cable Routing (ASC) |  | 0% | Labor Hours | SC |  |  |  | 45 | 35% | 2022-10-03 | 2022-11-01 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 | [7 empty] | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.9 | String/Cable Installation | 1.2.9 String/Cable Installation | 1.2.9.4 | String/Cable Installation 2022-23 | 1.2.9.4 String/Cable Installation 2022-23 | cell-link@smartsheet.com | 2021-11-30 22:32 |  | 3d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.9.4.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.4.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.4.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.4.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.4.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.4.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.4.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.4.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.9.4.12 | C |  | PSL | String: Sensor Sleds Construction |  | 0% | Labor Hours | SC |  |  |  |  | 0% | 2022-11-16 | 2023-01-17 |  |  |  | ASC | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | [7 empty] | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.9 | String/Cable Installation | 1.2.9 String/Cable Installation | 1.2.9.4 | String/Cable Installation 2022-23 | 1.2.9.4 String/Cable Installation 2022-23 | cell-link@smartsheet.com | 2021-11-30 22:32 |  | 3d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.9.4.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.4.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.4.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.4.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.4.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.4.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.4.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.4.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.9.4.13 | C |  | UW | String: Logbook Requirements Defined and Design Completed |  | 0.7692% | Labor Hours | EN |  |  | 81 | 40 | 35% | 2023-07-27 | 2023-09-21 | [14 empty] | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 432 | 432 | 864 | 53% | 457.92 | 1379.3736 | 1379.3736 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 | 3371 |  |  |  |  | 3371 |  | 1379.3736 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.9 | String/Cable Installation | 1.2.9 String/Cable Installation | 1.2.9.4 | String/Cable Installation 2022-23 | 1.2.9.4 String/Cable Installation 2022-23 | cell-link@smartsheet.com | 2021-11-30 22:32 |  | 11d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.9.4.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 689.6868 | 689.6868 | 1.2.9.4.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.4.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.4.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.4.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 333.9079 | 333.9079 | 667.8158 | 1.2.9.4.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 116.8678 | 116.8678 | 233.7355 | 1.2.9.4.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 238.9111 | 238.9111 | 477.8222 | 1379.3736 | 1.2.9.4.13 | 1379.3736 | 1379.3736 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 689.6868 | 1379.3736 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 689.6868 | 1379.3736
| 1.2 | 1.2.9.5.1 | C |  | UW | String: Plan & Coordinate Installation (2023-2024) | Tosi | 0% | Labor Hours | SS |  |  | 115 | 38 | 35% | 2023-10-03 | 2024-10-01 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | -66477 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 4104 | 4104 | 4104 | 4104 | 4104 | 4104 | 4104 | 4104 | 4104 | 4104 | 4104 | 4104 | 49248 | 53% | 26101.44 | 82041.485 | 82041.485 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 |  |  |  | 66477 |  | 112032 |  | 82041.485 | Labor - LoE | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.9 | String/Cable Installation | 1.2.9 String/Cable Installation | 1.2.9.5 | String/Cable Installation 2023-24 | 1.2.9.5 String/Cable Installation 2023-24 | cell-link@smartsheet.com | 2021-11-30 22:32 |  | 233d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.9.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.5.1 | 6836.7904 | 6836.7904 | 6836.7904 | 6836.7904 | 6836.7904 | 6836.7904 | 6836.7904 | 6836.7904 | 6836.7904 | 6836.7904 | 6836.7904 | 6836.7904 | 1.2.9.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.9.5.2 | C |  | UW | String: Off-Ice Installation Training |  | 0% | Labor Hours | SC |  |  |  | 45 | 35% | 2024-08-08 | 2024-08-12 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 | [7 empty] | 0 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.9 | String/Cable Installation | 1.2.9 String/Cable Installation | 1.2.9.5 | String/Cable Installation 2023-24 | 1.2.9.5 String/Cable Installation 2023-24 | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 3d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.9.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.9.5.3 | C |  | UW | String: South Pole Acceptance Testing (SPAT) Support Equipment Shipped |  | 0% | Labor Hours | SC |  |  |  | 45 | 35% | 2023-10-03 | 2023-11-01 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | 8 | [11 empty] | 486 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 486 | 53% | 257.58 | 809.6199 | 809.6199 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 | [7 empty] | 809.6199 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.9 | String/Cable Installation | 1.2.9 String/Cable Installation | 1.2.9.5 | String/Cable Installation 2023-24 | 1.2.9.5 String/Cable Installation 2023-24 | cell-link@smartsheet.com | 2021-11-30 22:32 |  | 2d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.9.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.5.3 | 809.6199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.9.5.4 | C |  | PSL | String: Ship Laser Rangers, Pressure Sensors & Deployment Monitor |  | 0% | Labor Hours | TE |  |  |  | 77 | 0% | 2023-10-03 | 2023-10-17 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 24 | [11 empty] | 1848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1848 | 0% | 0 | 2012.1273 | 2012.1273 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | [7 empty] | 2012.1273 | Labor - Task | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.9 | String/Cable Installation | 1.2.9 String/Cable Installation | 1.2.9.5 | String/Cable Installation 2023-24 | 1.2.9.5 String/Cable Installation 2023-24 | cell-link@smartsheet.com | 2021-11-30 22:32 |  | 24d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.9.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.5.4 | 2012.1273 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.9.5.4 | C |  | PSL | String: Ship Laser Rangers, Pressure Sensors & Deployment Monitor |  |  | M & S | TE |  |  |  | 1 | 0% | 2023-10-03 | 2023-10-17 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | 3500 | [11 empty] | 3500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3500 | 53% | 1855 | 5355 | 5355 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 5355 | M & S | Off Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.9 | String/Cable Installation | 1.2.9 String/Cable Installation | 1.2.9.5 | String/Cable Installation 2023-24 | 1.2.9.5 String/Cable Installation 2023-24 | cell-link@smartsheet.com | 2021-11-30 22:32 |  | 24d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.9.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.5.4 | 5355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.9.5.5 | C |  | UW | String: On-ice Sensor Handling Training |  | 0% | Labor Hours | SS |  |  |  | 55 | 35% | 2024-11-15 | 2024-11-29 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | -3880 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 |  |  |  | 3880 |  |  |  | 0 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.9 | String/Cable Installation | 1.2.9 String/Cable Installation | 1.2.9.5 | String/Cable Installation 2023-24 | 1.2.9.5 String/Cable Installation 2023-24 | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 24d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.9.5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.9.5.5 | C |  | PSL | String: On-ice Sensor Handling Training |  | 0% | Labor Hours | TE |  |  |  | 77 | 0% | 2024-11-15 | 2024-11-29 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | [9 empty] | 0 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.9 | String/Cable Installation | 1.2.9 String/Cable Installation | 1.2.9.5 | String/Cable Installation 2023-24 | 1.2.9.5 String/Cable Installation 2023-24 | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 24d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.9.5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.9.5.6.3 | C |  | PSL | String: Prep/Uncrate Cable Spools; Load onto TU20 (ASC & UW) |  | 0% | Labor Hours | TE |  |  |  | 77 | 0% | 2023-12-04 | 2023-12-06 |  |  |  | PSL & ASC | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  | 24 | [9 empty] | 0 | 0 | 1848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1848 | 0% | 0 | 2012.1273 | 2012.1273 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | [7 empty] | 2012.1273 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.9 | String/Cable Installation | 1.2.9 String/Cable Installation | 1.2.9.5 | String/Cable Installation 2023-24 | 1.2.9.5 String/Cable Installation 2023-24 | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 3d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.9.5.6.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.5.6.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.5.6.3 | 0 | 0 | 2012.1273 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.5.6.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.5.6.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.5.6.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.5.6.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.5.6.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.9.5.6.4 | C |  | PSL | String: Install 7 Surface Cables into ICL Tower, Across Bridge, into ICL (ASC & UW) |  | 0% | Labor Hours | SC |  |  |  |  | 0% | 2023-12-06 | 2023-12-08 |  |  |  | 1.4 & ASC | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  | 16 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | [7 empty] | 0 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.9 | String/Cable Installation | 1.2.9 String/Cable Installation | 1.2.9.5 | String/Cable Installation 2023-24 | 1.2.9.5 String/Cable Installation 2023-24 | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 2d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.9.5.6.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.5.6.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.5.6.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.5.6.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.5.6.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.5.6.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.5.6.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.5.6.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.9.5.6.5 | C |  | UW | String: Prep Cables & Attach to Grounding System in ICL (ASC & UW) |  | 0% | Labor Hours | SE |  |  |  | 55 | 35% | 2023-12-07 | 2023-12-11 |  |  |  | 1.4 & ASC | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 |  |  | 8 | [9 empty] | 0 | 0 | 594 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 594 | 53% | 314.82 | 989.5355 | 989.5355 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 | [7 empty] | 989.5355 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.9 | String/Cable Installation | 1.2.9 String/Cable Installation | 1.2.9.5 | String/Cable Installation 2023-24 | 1.2.9.5 String/Cable Installation 2023-24 | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 24d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.9.5.6.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.5.6.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.5.6.5 | 0 | 0 | 989.5355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.5.6.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.5.6.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.5.6.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.5.6.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.5.6.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.9.5.6.6 | C |  | UW | String: Connect Surface Cables into ICL Patch Panels (UW) |  | 0% | Labor Hours | SE |  |  |  | 55 | 35% | 2023-12-07 | 2023-12-11 |  |  |  | 1.4 Task | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | -3880 |  |  | 8 | [9 empty] | 0 | 0 | 594 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 594 | 53% | 314.82 | 989.5355 | 989.5355 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 |  |  |  | 3880 |  |  |  | 989.5355 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.9 | String/Cable Installation | 1.2.9 String/Cable Installation | 1.2.9.5 | String/Cable Installation 2023-24 | 1.2.9.5 String/Cable Installation 2023-24 | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 24d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.9.5.6.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.5.6.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.5.6.6 | 0 | 0 | 989.5355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.5.6.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.5.6.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.5.6.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.5.6.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.5.6.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.9.5.6.9 | C |  | PSL | String: Unspool & Lay Surface Cables from Tower to SJB Pits (ASC, UW & MSU) |  | 0% | Labor Hours | SC |  |  |  |  | 0% | 2023-12-13 | 2023-12-14 |  |  |  | ASC | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  | 32 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | [7 empty] | 0 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.9 | String/Cable Installation | 1.2.9 String/Cable Installation | 1.2.9.5 | String/Cable Installation 2023-24 | 1.2.9.5 String/Cable Installation 2023-24 | cell-link@smartsheet.com | 2021-11-30 22:32 |  | 3d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.9.5.6.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.5.6.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.5.6.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.5.6.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.5.6.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.5.6.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.5.6.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.5.6.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.9.5.6.10 | C |  | PSL | String: Install SJB's in Pits (2); Connect cables (ASC & UW) |  | 0% | Labor Hours | SC |  |  |  |  | 0% | 2023-12-15 | 2023-12-18 |  |  |  | ASC | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  | 8 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | [7 empty] | 0 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.9 | String/Cable Installation | 1.2.9 String/Cable Installation | 1.2.9.5 | String/Cable Installation 2023-24 | 1.2.9.5 String/Cable Installation 2023-24 | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 2d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.9.5.6.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.5.6.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.5.6.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.5.6.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.5.6.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.5.6.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.5.6.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.5.6.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.9.6.1 | C |  | UW | String: Plan & Coordinate Installation (2024-25) | Tosi | 0% | Labor Hours | SS |  |  |  | 38 | 35% | 2024-10-02 | 2025-05-27 |  |  |  | ASC | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 |  |  |  |  | 4104 | 4104 | 4104 | 4104 | 4104 | 4104 | 4104 | 4104 | 0 | 0 | 0 | 0 | 32832 | 53% | 17400.96 | 55870.2513 |  | 0 | [7 empty] | 55870.2513 | Labor - LoE | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.9 | String/Cable Installation | 1.2.9 String/Cable Installation | 1.2.9.6 | String/Cable Installation 2024-25 | 1.2.9.6 String/Cable Installation 2024-25 | cell-link@smartsheet.com | 2021-11-30 22:32 |  | 24d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.9.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.1 | 6983.7814 | 6983.7814 | 6983.7814 | 6983.7814 | 6983.7814 | 6983.7814 | 6983.7814 | 6983.7814 | 0 | 0 | 0 | 0 | 1.2.9.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.9.6.2 | C |  | UW | String: On Ice Readiness Review for 1st Hole Drill / Deployment |  | 0% | Labor Hours | SC |  |  |  | 45 | 35% | 2024-12-02 | 2024-12-02 |  |  |  | ASC Activity | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 | [7 empty] | 0 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.9 | String/Cable Installation | 1.2.9 String/Cable Installation | 1.2.9.6 | String/Cable Installation 2024-25 | 1.2.9.6 String/Cable Installation 2024-25 | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 24d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.9.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.9.6.2 | C |  | PSL | String: On Ice Readiness Review for 1st Hole Drill / Deployment |  | 0% | Labor Hours | SC |  |  |  | 0 | 0% | 2024-12-02 | 2024-12-02 |  |  |  | ASC Activity | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  | 16 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | [9 empty] | 0 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.9 | String/Cable Installation | 1.2.9 String/Cable Installation | 1.2.9.6 | String/Cable Installation 2024-25 | 1.2.9.6 String/Cable Installation 2024-25 | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 24d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.9.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.9.6.3 | C |  | PSL | String: Erect Sensor Testing Tent - (ASC) |  | 0% | Labor Hours | TE |  |  |  | 77 | 0% | 2024-12-01 | 2024-12-03 |  |  |  | ASC | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | [7 empty] | 0 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.9 | String/Cable Installation | 1.2.9 String/Cable Installation | 1.2.9.6 | String/Cable Installation 2024-25 | 1.2.9.6 String/Cable Installation 2024-25 | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 2d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.9.6.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.9.6.4.1 | C |  | PSL | String: Excavate Surface Junction Box (SJB #1) Vaults (hole side) (ASC) |  | 0% | Labor Hours | SC |  |  |  | 0 | 0% | 2024-11-26 | 2024-11-28 |  |  |  | ASC Activity | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | [7 empty] | 0 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.9 | String/Cable Installation | 1.2.9 String/Cable Installation | 1.2.9.6 | String/Cable Installation 2024-25 | 1.2.9.6 String/Cable Installation 2024-25 | cell-link@smartsheet.com | 2021-11-30 22:32 |  | 2d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.9.6.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.9.6.4.2 | C |  | PSL | String: Remove SJB #1 Vault Lid & Walls (ASC) |  | 0% | Labor Hours | SC |  |  |  |  | 0% | 2024-11-29 | 2024-12-03 |  |  |  | UW Activity - Cable personnel (1.4) | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  | 8 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | [7 empty] | 0 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.9 | String/Cable Installation | 1.2.9 String/Cable Installation | 1.2.9.6 | String/Cable Installation 2024-25 | 1.2.9.6 String/Cable Installation 2024-25 | cell-link@smartsheet.com | 2021-11-30 22:32 |  | 24d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.9.6.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.9.6.4.3 | C |  | PSL | String: Trench from Holes to SJB #2 Pits, 3 times (ASC) |  | 0% | Labor Hours | TE |  |  |  | 77 | 0% | 2024-12-04 | 2024-12-06 |  |  |  | ASC Activity | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | [7 empty] | 0 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.9 | String/Cable Installation | 1.2.9 String/Cable Installation | 1.2.9.6 | String/Cable Installation 2024-25 | 1.2.9.6 String/Cable Installation 2024-25 | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 24d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.9.6.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.9.6.4.4 | C |  | PSL | String: Spool Slack Cable in Pit/Trench, 3 times (UW & MSU) |  | 0% | Labor Hours | TE |  |  |  | 77 | 0% | 2024-12-09 | 2024-12-11 |  |  |  | ASC Activity | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  | 16 | [9 empty] | 0 | 0 | 1232 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1232 | 0% | 0 | 1370.2587 |  | 0 | [7 empty] | 1370.2587 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.9 | String/Cable Installation | 1.2.9 String/Cable Installation | 1.2.9.6 | String/Cable Installation 2024-25 | 1.2.9.6 String/Cable Installation 2024-25 | cell-link@smartsheet.com | 2021-11-30 22:32 |  | 2d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.9.6.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.4.4 | 0 | 0 | 1370.2587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.9.6.4.5 | C |  | PSL | String: Connect Cables to SJB #1 x 3 (UW) |  | 0% | Labor Hours | SE |  |  |  | 0 | 0% | 2024-12-11 | 2024-12-13 |  |  |  | ASC Activity | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  | 112 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | [7 empty] | 0 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.9 | String/Cable Installation | 1.2.9 String/Cable Installation | 1.2.9.6 | String/Cable Installation 2024-25 | 1.2.9.6 String/Cable Installation 2024-25 | cell-link@smartsheet.com | 2021-11-30 22:32 |  | 2d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.9.6.4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.9.6.4.6 | C |  | UW | String: Survey & Backfill Cable Trenches, 3 times (ASC & UW) |  | 0% | Labor Hours | SC |  |  |  | 45 | 35% | 2024-12-10 | 2024-12-12 |  |  |  | UW Activity - Cable personnel (1.4) | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 |  |  | 48 | [9 empty] | 0 | 0 | 2916 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2916 | 53% | 1545.48 | 4962.1605 |  | 0 | [7 empty] | 4962.1605 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.9 | String/Cable Installation | 1.2.9 String/Cable Installation | 1.2.9.6 | String/Cable Installation 2024-25 | 1.2.9.6 String/Cable Installation 2024-25 | cell-link@smartsheet.com | 2021-11-30 22:32 |  | 24d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.9.6.4.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.4.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.4.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.4.6 | 0 | 0 | 4962.1605 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.4.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.4.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.4.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.4.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.9.6.4.7 | C |  | UW | String: Excavate Surface Junction Box (SJB #2) Vaults (hole side) (ASC & UW) |  | 0% | Labor Hours | SC |  |  |  | 45 | 35% | 2024-12-12 | 2024-12-16 |  |  |  | ASC Activity | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 |  |  | 8 | [9 empty] | 0 | 0 | 486 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 486 | 53% | 257.58 | 827.0267 |  | 0 | [7 empty] | 827.0267 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.9 | String/Cable Installation | 1.2.9 String/Cable Installation | 1.2.9.6 | String/Cable Installation 2024-25 | 1.2.9.6 String/Cable Installation 2024-25 | cell-link@smartsheet.com | 2021-11-30 22:32 |  | 24d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.9.6.4.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.4.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.4.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.4.7 | 0 | 0 | 827.0267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.4.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.4.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.4.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.4.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.9.6.4.8 | C |  | UW | String: Remove SJB #2 Vault Lid & Walls (ASC) |  | 0% | Labor Hours | SC |  |  |  | 45 | 35% | 2024-12-12 | 2024-12-13 |  |  |  | ASC Activity | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 |  |  | 16 | [9 empty] | 0 | 0 | 972 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 972 | 53% | 515.16 | 1654.0535 |  | 0 | [7 empty] | 1654.0535 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.9 | String/Cable Installation | 1.2.9 String/Cable Installation | 1.2.9.6 | String/Cable Installation 2024-25 | 1.2.9.6 String/Cable Installation 2024-25 | cell-link@smartsheet.com | 2021-11-30 22:32 |  | 2d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.9.6.4.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.4.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.4.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.4.8 | 0 | 0 | 1654.0535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.4.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.4.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.4.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.4.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.9.6.4.9 | C |  | PSL | String: Trench from Holes to SJB #2 Pit, 4 times (ASC) |  | 0% | Labor Hours | SC |  |  |  |  | 0% | 2024-12-13 | 2024-12-16 |  |  |  | ASC Activity | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | [7 empty] | 0 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.9 | String/Cable Installation | 1.2.9 String/Cable Installation | 1.2.9.6 | String/Cable Installation 2024-25 | 1.2.9.6 String/Cable Installation 2024-25 | cell-link@smartsheet.com | 2021-11-30 22:32 |  | 2d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.9.6.4.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.4.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.4.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.4.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.4.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.4.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.4.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.4.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.9.6.4.10 | C |  | PSL | String: Spool Slack Cable in Pit/Trench, 4 times (UW & MSU) |  | 0% | Labor Hours | TE |  |  |  | 77 | 0% | 2024-12-13 | 2024-12-16 |  |  |  | UW Activity - Cable personnel (1.4) | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  | 16 | [9 empty] | 0 | 0 | 1232 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1232 | 0% | 0 | 1370.2587 |  | 0 | [7 empty] | 1370.2587 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.9 | String/Cable Installation | 1.2.9 String/Cable Installation | 1.2.9.6 | String/Cable Installation 2024-25 | 1.2.9.6 String/Cable Installation 2024-25 | cell-link@smartsheet.com | 2021-11-30 22:32 |  | 24d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.9.6.4.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.4.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.4.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.4.10 | 0 | 0 | 1370.2587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.4.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.4.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.4.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.4.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.9.6.4.11 | C |  | PSL | String: Connect Cables to SJB #2 x 4 (UW & MSU) |  | 0% | Labor Hours | SC |  |  |  |  | 0% | 2024-12-16 | 2024-12-18 |  |  |  | ASC Activity | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  | 8 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | [7 empty] | 0 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.9 | String/Cable Installation | 1.2.9 String/Cable Installation | 1.2.9.6 | String/Cable Installation 2024-25 | 1.2.9.6 String/Cable Installation 2024-25 | cell-link@smartsheet.com | 2021-11-30 22:32 |  | 24d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.9.6.4.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.4.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.4.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.4.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.4.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.4.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.4.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.4.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | 1.2.9.6.4.12 | C |  | PSL | String: Survey & Backfill Cable Trenches, 4 times (ASC & UW) |  | 0% | Labor Hours | SC |  |  |  |  | 0% | 2024-12-18 | 2024-12-20 |  |  |  | ASC Activity | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  |  | 8 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | [7 empty] | 0 | Labor - Task | On Ice | 1.2 | Implementation | 1.2 Implementation | 1.2.9 | String/Cable Installation | 1.2.9 String/Cable Installation | 1.2.9.6 | String/Cable Installation 2024-25 | 1.2.9.6 String/Cable Installation 2024-25 | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 2d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.2.9.6.4.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.4.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.4.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.4.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.4.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.4.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.4.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9.6.4.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 | 1.3.1 | P |  | UW | mDOM Preliminary Design Review | Wendt | 0% | Labor Hours | SS |  |  | 55 | 54 | 35% | 2018-10-01 | 2023-09-01 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 4477 | 0 | [5 empty] | 4477 |  | 0 | Labor - Task | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.3.1 | mDOM | 1.3.1 mDOM | 1.3.1 | mDOM | 1.3.1 mDOM | cell-link@smartsheet.com | 2021-12-02 19:49 |  | 1235d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 | 1.3.1 | P |  | PSU | mDOM Preliminary Design Review |  |  | Travel |  |  |  | 1 | 1 | 0% | 2018-10-01 | 2023-09-01 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 4608 | 0 | [5 empty] | 4608 |  | 0 | Travel | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.3.1 | mDOM | 1.3.1 mDOM | 1.3.1 | mDOM | 1.3.1 mDOM | cell-link@smartsheet.com | 2021-12-02 19:49 |  | 1235d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 | 1.3.1 | P |  | UW | mDOM Preliminary Design Review |  |  | Travel |  |  |  | 1 | 1 | 0% | 2018-10-01 | 2023-09-01 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 4896 | 0 | [5 empty] | 4896 |  | 0 | Travel | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.3.1 | mDOM | 1.3.1 mDOM | 1.3.1 | mDOM | 1.3.1 mDOM | cell-link@smartsheet.com | 2021-12-02 19:49 |  | 1235d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TRUE | 1.3 | 1.3.1.1.3 | C |  | UW | Test firmware for wavedeform on the FPGA | N.N. | 0% | Labor Hours | GR |  |  | 1 | 30 | 19.9% | 2020-01-02 | 2021-09-30 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 0 | Labor - Task | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.3.1 | mDOM | 1.3.1 mDOM | 1.3.1.1 | mDOM DAQ Electronics | 1.3.1.1 mDOM DAQ Electronics | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.3.1.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.1.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.1.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.1.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.1.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.1.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.1.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.1.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TRUE | 1.3 | 1.3.1.1.2.2.4 | C |  | UW | mDOM Mainboard HALT | N.N. | 1.923% | Labor Hours | EN |  |  |  | 40 | 35% | 2021-03-08 | 2021-03-19 |  |  |  |  | 40 | [11 empty] | 2160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2160 | 53% | 1144.8 | 3448.434 | 3448.434 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 3448.434 | Labor - Task | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.3.1 | mDOM | 1.3.1 mDOM | 1.3.1.1 | mDOM DAQ Electronics | 1.3.1.1 mDOM DAQ Electronics | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.3.1.1.2.2.4 | 3448.434 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.1.1.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.1.1.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.1.1.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.1.1.2.2.4 | 1669.5396 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1669.5396 | 1.3.1.1.2.2.4 | 584.3389 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 584.3389 | 1.3.1.1.2.2.4 | 1194.5556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1194.5556 | 3448.434 | 1.3.1.1.2.2.4 | 3448.434 | 5284.434 | 3448.434 | 3448.434 | 3448.434 | 3448.434 | 3448.434 | 3448.434 | 3448.434 | 3448.434 | 3448.434 | 3448.434 | 3448.434 | 3448.434 | 5284.434 | 5284.434 | 5284.434 | 5284.434 | 5284.434 | 5284.434 | 5284.434 | 5284.434 | 5284.434 | 5284.434 | 5284.434 | 5284.434
TRUE | 1.3 | 1.3.1.1.2.2.4 | C |  | UW | mDOM Mainboard HALT |  |  | M & S |  |  |  |  | 1 | 0% | 2021-03-08 | 2021-03-19 |  |  |  |  | 1200 | [11 empty] | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 53% | 636 | 1836 | 1836 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 1836 | M & S | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.3.1 | mDOM | 1.3.1 mDOM | 1.3.1.1 | mDOM DAQ Electronics | 1.3.1.1 mDOM DAQ Electronics | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.3.1.1.2.2.4 | 1836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.1.1.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.1.1.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.1.1.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.1.1.2.2.4 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 1.3.1.1.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.1.1.2.2.4 | 636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 636 | 1836 | 1.3.1.1.2.2.4 | 1836 | 1836 | 1836 | 1836 | 1836 | 1836 | 1836 | 1836 | 1836 | 1836 | 1836 | 1836 | 1836 | 1836 | 1836 | 1836 | 1836 | 1836 | 1836 | 1836 | 1836 | 1836 | 1836 | 1836 | 1836 | 1836
| 1.3 | 1.3.1.3.1 | C |  | UW | Preliminary design phase | Wendt | 0% | Labor Hours | SS |  |  | 55 | 54 | 35% | 2018-10-01 | 2019-03-15 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 17907 | 0 | [5 empty] | 17907 |  | 0 | Labor - Task | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.3.1 | mDOM | 1.3.1 mDOM | 1.3.1.3 | mDOM High Voltage Subsystem | 1.3.1.3 mDOM High Voltage Subsystem | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 143d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.3.1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 | 1.3.1.3.1 | C |  | UW | Preliminary design phase | van Eijk | 0% | Labor Hours | PO |  |  | 30 | 30 | 18.9% | 2018-10-01 | 2019-03-15 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 9768 | 0 | [5 empty] | 9768 |  | 0 | Labor - Task | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.3.1 | mDOM | 1.3.1 mDOM | 1.3.1.3 | mDOM High Voltage Subsystem | 1.3.1.3 mDOM High Voltage Subsystem | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 143d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.3.1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 | 1.3.1.3.1 | C |  | UW | Preliminary design phase |  |  | M & S |  |  |  | 1 | 1 | 0% | 2018-10-01 | 2019-03-15 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 2754 | 0 | [5 empty] | 2754 |  | 0 | M & S | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.3.1 | mDOM | 1.3.1 mDOM | 1.3.1.3 | mDOM High Voltage Subsystem | 1.3.1.3 mDOM High Voltage Subsystem | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 143d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.3.1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 | 1.3.1.3.1 | C |  | UW | Foreign trips to coordinate interfaces and test prototypes in integrated mDOM |  |  | Travel |  |  |  | 1 | 1 | 0% | 2018-10-01 | 2019-03-15 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 9792 | 0 | [5 empty] | 9792 |  | 0 | Travel | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.3.1 | mDOM | 1.3.1 mDOM | 1.3.1.3 | mDOM High Voltage Subsystem | 1.3.1.3 mDOM High Voltage Subsystem | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 143d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.3.1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 | 1.3.1.3.2 | C |  | UW | Final design phase (Ch. Wendt) | Wendt | 0% | Labor Hours | SS |  |  | 55 | 54 | 35% | 2019-02-18 | 2019-12-06 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 13430 | 16524 | [5 empty] | 31696 |  | 0 | Labor - Task | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.3.1 | mDOM | 1.3.1 mDOM | 1.3.1.3 | mDOM High Voltage Subsystem | 1.3.1.3 mDOM High Voltage Subsystem | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 251d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.3.1.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.1.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.1.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.1.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.1.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.1.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.1.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.1.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 | 1.3.1.3.2 | C |  | UW | Final design phase | van Eijk | 0% | Labor Hours | PO |  |  | 30 | 30 | 18.9% | 2019-02-18 | 2019-12-06 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 7326 | 0 | [5 empty] | 17289 |  | 0 | Labor - Task | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.3.1 | mDOM | 1.3.1 mDOM | 1.3.1.3 | mDOM High Voltage Subsystem | 1.3.1.3 mDOM High Voltage Subsystem | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 251d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.3.1.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.1.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.1.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.1.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.1.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.1.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.1.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.1.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 | 1.3.1.3.2 | C |  | UW | Final design phase |  |  | M & S |  |  |  | 1 | 1 | 0% | 2019-02-18 | 2019-12-06 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 1836 | 3978 | [5 empty] | 5814 |  | 0 | M & S | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.3.1 | mDOM | 1.3.1 mDOM | 1.3.1.3 | mDOM High Voltage Subsystem | 1.3.1.3 mDOM High Voltage Subsystem | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 251d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.3.1.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.1.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.1.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.1.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.1.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.1.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.1.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.1.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 | 1.3.1.3.2 | C |  | UW | Foreign trips to integrate and test HV susbsytem in mDOM and participate in design verification |  |  | Travel |  |  |  | 1 | 1 | 0% | 2019-02-18 | 2019-12-06 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 5355 | [5 empty] | 9988 |  | 0 | Travel | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.3.1 | mDOM | 1.3.1 mDOM | 1.3.1.3 | mDOM High Voltage Subsystem | 1.3.1.3 mDOM High Voltage Subsystem | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 251d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.3.1.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.1.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.1.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.1.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.1.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.1.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.1.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.1.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 | 1.3.1.8.8 | C |  | UW | mDOM Final Design Review (Ch. Wendt) | Wendt | 1.923% | Labor Hours | SS |  |  | 55 | 54 | 35% | 2021-05-05 | 2021-05-05 | [5 empty] | 40 | [10 empty] | 0 | 2916 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2916 | 53% | 1545.48 | 4655.386 | 4655.386 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 4131 | [5 empty] | 4566 |  | 4655.386 | Labor - Task | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.3.1 | mDOM | 1.3.1 mDOM | 1.3.1.8 | Integrated mDOM | 1.3.1.8 Integrated mDOM | cell-link@smartsheet.com | 2021-12-01 20:41 |  | 1235d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.3.1.8.8 | 0 | 4655.386 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.1.8.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.1.8.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.1.8.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.1.8.8 | 0 | 2253.8785 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2253.8785 | 1.3.1.8.8 | 0 | 788.8575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 788.8575 | 1.3.1.8.8 | 0 | 1612.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1612.65 | 4655.386 | 1.3.1.8.8 | 4655.386 | 4655.386 | 0 | 4655.386 | 4655.386 | 4655.386 | 4655.386 | 4655.386 | 4655.386 | 4655.386 | 4655.386 | 4655.386 | 4655.386 | 4655.386 | 0 | 4655.386 | 4655.386 | 4655.386 | 4655.386 | 4655.386 | 4655.386 | 4655.386 | 4655.386 | 4655.386 | 4655.386 | 4655.386
| 1.3 | 1.3.2.7.6 | C |  | UW | D-Egg Final Design Review (P. Sandstrom) | Sandstrom | 0% | Labor Hours | SE |  |  |  | 53 | 35% | 2019-11-25 | 2019-11-25 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 4131 | [7 empty] | 0 | Labor - Task | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.3.2 | D-Egg | 1.3.2 D-Egg | 1.3.2.7 | Integrated D-Egg | 1.3.2.7 Integrated D-Egg | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.3.2.7.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.2.7.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.2.7.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.2.7.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.2.7.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.2.7.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.2.7.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.2.7.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 | 1.3.2.7.6 | C |  | PSU | D-Egg Final Design Review |  |  | Travel | SE |  |  |  | 1 | 0% | 2019-11-25 | 2019-11-25 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 |  | 5531.75 | [7 empty] | 0 | Travel | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.3.2 | D-Egg | 1.3.2 D-Egg | 1.3.2.7 | Integrated D-Egg | 1.3.2.7 Integrated D-Egg | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.3.2.7.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.2.7.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.2.7.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.2.7.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.2.7.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.2.7.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.2.7.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.2.7.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 | 1.3.2.7.6 | C |  | UW | D-Egg Final Design Review |  |  | Travel | SE |  |  |  | 1 | 0% | 2019-11-25 | 2019-11-25 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 5355 | [7 empty] | 0 | Travel | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.3.2 | D-Egg | 1.3.2 D-Egg | 1.3.2.7 | Integrated D-Egg | 1.3.2.7 Integrated D-Egg | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.3.2.7.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.2.7.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.2.7.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.2.7.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.2.7.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.2.7.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.2.7.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.2.7.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 | 1.3.3.1.1.1 | C |  | UW | Update schematics |  |  | M & S |  |  |  | 1 | 1 | 0% | 2019-04-01 | 2019-05-03 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 4590 | 0 | [5 empty] | 4590 |  | 0 | M & S | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.3.3 | PDOM | 1.3.3 PDOM | 1.3.3.1 | PDOM DAQ Electronics | 1.3.3.1 PDOM DAQ Electronics | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 29d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.3.3.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 | 1.3.3.1.1.2 | C |  | UW | Layout |  |  | M & S |  |  |  | 1 | 1 | 0% | 2019-05-06 | 2019-06-14 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 6120 | 0 | [5 empty] | 6120 |  | 0 | M & S | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.3.3 | PDOM | 1.3.3 PDOM | 1.3.3.1 | PDOM DAQ Electronics | 1.3.3.1 PDOM DAQ Electronics | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 35d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.3.3.1.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.1.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.1.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.1.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.1.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.1.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.1.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.1.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 | 1.3.3.1.1.3 | C |  | UW | PDOM Rev2 Mainboard production (Qty. 10) |  |  | M & S |  |  |  | 1 | 1 | 0% | 2019-06-17 | 2019-07-26 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 22950 | 0 | [5 empty] | 22950 |  | 0 | M & S | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.3.3 | PDOM | 1.3.3 PDOM | 1.3.3.1 | PDOM DAQ Electronics | 1.3.3.1 PDOM DAQ Electronics | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 35d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.3.3.1.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.1.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.1.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.1.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.1.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.1.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.1.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.1.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 | 1.3.3.1.1.5 | C |  | UW | Testing |  |  | M & S |  |  |  | 1 | 1 | 0% | 2019-07-29 | 2019-11-08 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 1530 | 0 | [5 empty] | 1530 |  | 0 | M & S | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.3.3 | PDOM | 1.3.3 PDOM | 1.3.3.1 | PDOM DAQ Electronics | 1.3.3.1 PDOM DAQ Electronics | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 89d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.3.3.1.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.1.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.1.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.1.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.1.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.1.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.1.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.1.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 | 1.3.3.1.1.5 | C |  | UW | Foreign trip to Chiba to support setting up testing infrastructure for common D-Egg PDOM Mainboard |  |  | Travel |  |  |  | 1 | 1 | 0% | 2019-07-29 | 2019-11-08 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 4896 | 0 | [5 empty] | 4896 |  | 0 | Travel | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.3.3 | PDOM | 1.3.3 PDOM | 1.3.3.1 | PDOM DAQ Electronics | 1.3.3.1 PDOM DAQ Electronics | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 89d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.3.3.1.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.1.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.1.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.1.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.1.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.1.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.1.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.1.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 | 1.3.3.1.2.1 | C |  | UW | Update schematics |  |  | M & S |  |  |  | 1 | 1 | 0% | 2020-05-01 | 2020-05-28 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 306 | [5 empty] | 306 |  | 0 | M & S | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.3.3 | PDOM | 1.3.3 PDOM | 1.3.3.1 | PDOM DAQ Electronics | 1.3.3.1 PDOM DAQ Electronics | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 23d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.3.3.1.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.1.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.1.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.1.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.1.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.1.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.1.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.1.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 | 1.3.3.1.2.2 | C |  | UW | Layout |  |  | M & S |  |  |  | 1 | 1 | 0% | 2020-05-29 | 2020-07-09 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 6120 | [5 empty] | 6120 |  | 0 | M & S | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.3.3 | PDOM | 1.3.3 PDOM | 1.3.3.1 | PDOM DAQ Electronics | 1.3.3.1 PDOM DAQ Electronics | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 35d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.3.3.1.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.1.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.1.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.1.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.1.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.1.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.1.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.1.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 | 1.3.3.1.2.4 | C |  | UW | 10 Rev3 PDOM Mainboards |  |  | M & S |  |  | EE | 1 | 1 | 0% | 2021-11-12 | 2021-12-23 | [5 empty] | 13000 | [10 empty] | 0 | 13000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13000 | 53% | 6890 | 19890 | 19890 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 15600 | [5 empty] | 15600 |  | 19890 | M & S | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.3.3 | PDOM | 1.3.3 PDOM | 1.3.3.1 | PDOM DAQ Electronics | 1.3.3.1 PDOM DAQ Electronics | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 35d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.3.3.1.2.4 | 0 | 19890 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.1.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.1.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.1.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.1.2.4 | 0 | 13000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13000 | 1.3.3.1.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.1.2.4 | 0 | 6890 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6890 | 19890 | 1.3.3.1.2.4 | 19890 | 35119.434 | 0 | 19890 | 19890 | 19890 | 19890 | 19890 | 19890 | 19890 | 19890 | 19890 | 19890 | 19890 | 0 | 31559.217 | 35119.434 | 35119.434 | 35119.434 | 35119.434 | 35119.434 | 35119.434 | 35119.434 | 35119.434 | 35119.434 | 35119.434
TRUE | 1.3 | 1.3.3.1.2.4 | C |  | UW | 10 PDOM Calibration Boards |  |  | M & S |  |  | EE |  | 1 | 0% | 2021-11-12 | 2021-12-23 | [5 empty] | 6500 | [10 empty] | 0 | 6500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6500 | 53% | 3445 | 9945 | 9945 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 9945 | M & S | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.3.3 | PDOM | 1.3.3 PDOM | 1.3.3.1 | PDOM DAQ Electronics | 1.3.3.1 PDOM DAQ Electronics | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.3.3.1.2.4 | 0 | 9945 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.1.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.1.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.1.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.1.2.4 | 0 | 6500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6500 | 1.3.3.1.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.1.2.4 | 0 | 3445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3445 | 9945 | 1.3.3.1.2.4 | 9945 | 15229.434 | 0 | 9945 | 9945 | 9945 | 9945 | 9945 | 9945 | 9945 | 9945 | 9945 | 9945 | 9945 | 0 | 11669.217 | 15229.434 | 15229.434 | 15229.434 | 15229.434 | 15229.434 | 15229.434 | 15229.434 | 15229.434 | 15229.434 | 15229.434
| 1.3 | 1.3.3.1.2.4 | C |  | UW | PDOM Mainboard HALT | N.N. | 1.923% | Labor Hours | EN |  |  |  | 40 | 35% | 2021-11-12 | 2021-12-23 | [5 empty] | 20 | 20 | [9 empty] | 0 | 1080 | 1080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2160 | 53% | 1144.8 | 3448.434 | 3448.434 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 3448.434 | Labor - Task | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.3.3 | PDOM | 1.3.3 PDOM | 1.3.3.1 | PDOM DAQ Electronics | 1.3.3.1 PDOM DAQ Electronics | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.3.3.1.2.4 | 0 | 1724.217 | 1724.217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.1.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.1.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.1.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.1.2.4 | 0 | 834.7698 | 834.7698 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1669.5396 | 1.3.3.1.2.4 | 0 | 292.1694 | 292.1694 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 584.3389 | 1.3.3.1.2.4 | 0 | 597.2778 | 597.2778 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1194.5556 | 3448.434 | 1.3.3.1.2.4 | 3448.434 | 5284.434 | 0 | 1724.217 | 3448.434 | 3448.434 | 3448.434 | 3448.434 | 3448.434 | 3448.434 | 3448.434 | 3448.434 | 3448.434 | 3448.434 | 0 | 1724.217 | 5284.434 | 5284.434 | 5284.434 | 5284.434 | 5284.434 | 5284.434 | 5284.434 | 5284.434 | 5284.434 | 5284.434
| 1.3 | 1.3.3.1.2.4 | C |  | UW | PDOM Mainboard HALT |  |  | M & S |  |  |  | 1 | 1 | 0% | 2021-11-12 | 2021-12-23 |  | TRUE |  |  |  |  | 1200 | [9 empty] | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 53% | 636 | 1836 | 1836 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 1530 | [5 empty] | 1530 |  | 1836 | M & S | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.3.3 | PDOM | 1.3.3 PDOM | 1.3.3.1 | PDOM DAQ Electronics | 1.3.3.1 PDOM DAQ Electronics | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 35d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.3.3.1.2.4 | 0 | 0 | 1836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.1.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.1.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.1.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.1.2.4 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 1.3.3.1.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.1.2.4 | 0 | 0 | 636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 636 | 1836 | 1.3.3.1.2.4 | 1836 | 1836 | 0 | 0 | 1836 | 1836 | 1836 | 1836 | 1836 | 1836 | 1836 | 1836 | 1836 | 1836 | 0 | 0 | 1836 | 1836 | 1836 | 1836 | 1836 | 1836 | 1836 | 1836 | 1836 | 1836
| 1.3 | 1.3.3.1.2.5 | C |  | UW | Domestic trip to PCA manufacturer |  |  | Travel |  |  |  | 1 | 1 | 0% | 2022-07-18 | 2022-08-26 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 2754 | [5 empty] | 2809 |  | 0 | Travel | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.3.3 | PDOM | 1.3.3 PDOM | 1.3.3.1 | PDOM DAQ Electronics | 1.3.3.1 PDOM DAQ Electronics | cell-link@smartsheet.com | 2021-11-30 23:01 |  | 35d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.3.3.1.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.1.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.1.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.1.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.1.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.1.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.1.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.1.2.5 | 0 | 48750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48750 | 48750
| 1.3 | 1.3.3.1.2.5 | C |  | UW | 25 Rev3 PDOM Mainboards |  |  | CapEx |  |  | EE | 1 | 1 | 0% | 2022-07-18 | 2022-08-26 |  | TRUE | [12 empty] | 32500 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32500 | 0 | 32500 | 53% | 0 | 32500 | 32500 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 | 26000 |  |  |  |  | 108000 |  | 32500 | CapEx | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.3.3 | PDOM | 1.3.3 PDOM | 1.3.3.1 | PDOM DAQ Electronics | 1.3.3.1 PDOM DAQ Electronics | cell-link@smartsheet.com | 2021-11-30 23:01 |  | 35d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.3.3.1.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32500 | 0 | 1.3.3.1.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.1.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.1.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.1.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32500 | 0 | 32500 | 1.3.3.1.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.1.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32500 | 1.3.3.1.2.5 | 32500 | 48750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32500 | 32500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48750 | 48750
TRUE | 1.3 | 1.3.3.1.2.5 | C |  | UW | 25 PDOM Calibration Boards |  |  | CapEx |  |  | EE |  | 1 | 0% | 2022-07-18 | 2022-08-26 | [14 empty] | 16250 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16250 | 0 | 16250 | 53% | 0 | 16250 | 16250 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 16250 | CapEx | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.3.3 | PDOM | 1.3.3 PDOM | 1.3.3.1 | PDOM DAQ Electronics | 1.3.3.1 PDOM DAQ Electronics | cell-link@smartsheet.com | 2021-11-30 23:01 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.3.3.1.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16250 | 0 | 1.3.3.1.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.1.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.1.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.1.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16250 | 0 | 16250 | 1.3.3.1.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.1.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16250 | 1.3.3.1.2.5 | 16250 | 16250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16250 | 16250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16250 | 16250
| 1.3 | 1.3.3.2.1 | C |  | UW | PDOM HV System Preliminary Design |  |  | M & S |  |  |  | 1 | 1 | 0% | 2019-05-01 | 2019-10-15 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 6885 | 0 | [5 empty] | 6885 |  | 0 | M & S | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.3.3 | PDOM | 1.3.3 PDOM | 1.3.3.2 | PDOM High Voltage Subsystem | 1.3.3.2 PDOM High Voltage Subsystem | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 144d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.3.3.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 | 1.3.3.2.1 | C |  | UW | Two domestic trips to HV generator manufacturers |  |  | Travel |  |  |  | 1 | 1 | 0% | 2019-05-01 | 2019-10-15 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 5508 | 0 | [5 empty] | 5508 |  | 0 | Travel | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.3.3 | PDOM | 1.3.3 PDOM | 1.3.3.2 | PDOM High Voltage Subsystem | 1.3.3.2 PDOM High Voltage Subsystem | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 144d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.3.3.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 | 1.3.3.2.2.1 | C |  | UW | Update schematics |  |  | M & S |  |  |  | 1 | 1 | 0% | 2021-06-01 | 2021-06-28 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 765 | [5 empty] | 765 |  | 0 | M & S | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.3.3 | PDOM | 1.3.3 PDOM | 1.3.3.2 | PDOM High Voltage Subsystem | 1.3.3.2 PDOM High Voltage Subsystem | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 24d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.3.3.2.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.2.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.2.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.2.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.2.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.2.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.2.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.2.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 | 1.3.3.2.2.2 | C |  | UW | Layout |  |  | M & S |  |  |  | 1 | 1 | 0% | 2022-01-15 | 2022-02-10 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 3060 | [5 empty] | 3060 |  | 0 | M & S | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.3.3 | PDOM | 1.3.3 PDOM | 1.3.3.2 | PDOM High Voltage Subsystem | 1.3.3.2 PDOM High Voltage Subsystem | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 24d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.3.3.2.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.2.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.2.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.2.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.2.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.2.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.2.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.2.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 | 1.3.3.2.2.3 | C |  | UW | PDOM HV System production (Qty. 15) |  |  | M & S |  |  |  | 1 | 1 | 0% | 2022-02-11 | 2022-03-24 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 765 | [5 empty] | 765 |  | 0 | M & S | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.3.3 | PDOM | 1.3.3 PDOM | 1.3.3.2 | PDOM High Voltage Subsystem | 1.3.3.2 PDOM High Voltage Subsystem | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 36d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.3.3.2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.2.2.3 | 0 | 5355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5355 | 5355 | 5355 | 5355 | 5355 | 5355 | 5355
| 1.3 | 1.3.3.2.2.3 | C |  | UW | Domestic trip to PCA manufacturer |  |  | Travel |  |  |  | 1 | 1 | 0% | 2022-02-11 | 2022-03-24 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 2754 | [5 empty] | 2809 |  | 0 | Travel | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.3.3 | PDOM | 1.3.3 PDOM | 1.3.3.2 | PDOM High Voltage Subsystem | 1.3.3.2 PDOM High Voltage Subsystem | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 36d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.3.3.2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.2.2.3 | 0 | 5355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5355 | 5355 | 5355 | 5355 | 5355 | 5355 | 5355
| 1.3 | 1.3.3.2.2.3 | C |  | UW | 10 PDOM HV subsystems (HV supply PCA) |  |  | M & S |  |  | EE | 1 | 1 | 0% | 2022-02-11 | 2022-03-24 | [9 empty] | 3500 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 3500 | 0 | 0 | 0 | 0 | 0 | 0 | 3500 | 53% | 1855 | 5355 | 5355 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 4800 | [5 empty] | 4800 |  | 5355 | M & S | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.3.3 | PDOM | 1.3.3 PDOM | 1.3.3.2 | PDOM High Voltage Subsystem | 1.3.3.2 PDOM High Voltage Subsystem | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 36d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.3.3.2.2.3 | 0 | 0 | 0 | 0 | 0 | 5355 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.2.2.3 | 0 | 0 | 0 | 0 | 0 | 3500 | 0 | 0 | 0 | 0 | 0 | 0 | 3500 | 1.3.3.2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.2.2.3 | 0 | 0 | 0 | 0 | 0 | 1855 | 0 | 0 | 0 | 0 | 0 | 0 | 1855 | 5355 | 1.3.3.2.2.3 | 5355 | 5355 | 0 | 0 | 0 | 0 | 0 | 5355 | 5355 | 5355 | 5355 | 5355 | 5355 | 5355 | 0 | 0 | 0 | 0 | 0 | 5355 | 5355 | 5355 | 5355 | 5355 | 5355 | 5355
| 1.3 | 1.3.3.2.2.4 | C |  | UW | Testing | Resource 1 | 0% | Labor Hours | PO |  |  | 30 | 30 | 18.9% | 2022-03-25 | 2022-04-21 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 6549.012 | [5 empty] | 7472 |  | 0 | Labor - Task | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.3.3 | PDOM | 1.3.3 PDOM | 1.3.3.2 | PDOM High Voltage Subsystem | 1.3.3.2 PDOM High Voltage Subsystem | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 24d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.3.3.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 | 1.3.3.2.2.4 | C |  | UW | Testing |  |  | M & S |  |  |  | 1 | 1 | 0% | 2022-03-25 | 2022-04-21 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 3060 | [5 empty] | 3060 |  | 0 | M & S | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.3.3 | PDOM | 1.3.3 PDOM | 1.3.3.2 | PDOM High Voltage Subsystem | 1.3.3.2 PDOM High Voltage Subsystem | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 24d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.3.3.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 | 1.3.3.2.2.5 | C |  | UW | PDOM HV system production (Qty. 25) |  |  | M & S |  |  |  | 1 | 1 | 0% | 2022-07-18 | 2022-08-26 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 | 765 |  |  |  |  | 765 |  | 0 | M & S | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.3.3 | PDOM | 1.3.3 PDOM | 1.3.3.2 | PDOM High Voltage Subsystem | 1.3.3.2 PDOM High Voltage Subsystem | cell-link@smartsheet.com | 2021-11-30 23:01 |  | 35d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.3.3.2.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.2.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.2.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.2.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.2.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.2.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.2.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.2.2.5 | 0 | 8750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8750 | 8750
| 1.3 | 1.3.3.2.2.5 | C |  | UW | 25 PDOM HV subsystems (HV supply PCA) |  |  | CapEx |  |  | EE | 1 | 1 | 0% | 2022-07-18 | 2022-08-26 |  | TRUE | [12 empty] | 8750 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8750 | 0 | 8750 | 53% | 0 | 8750 | 8750 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 | 8000 |  |  |  |  | 8000 |  | 8750 | CapEx | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.3.3 | PDOM | 1.3.3 PDOM | 1.3.3.2 | PDOM High Voltage Subsystem | 1.3.3.2 PDOM High Voltage Subsystem | cell-link@smartsheet.com | 2021-11-30 23:01 |  | 35d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.3.3.2.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8750 | 0 | 1.3.3.2.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.2.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.2.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.2.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8750 | 0 | 8750 | 1.3.3.2.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.2.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8750 | 1.3.3.2.2.5 | 8750 | 8750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8750 | 8750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8750 | 8750
| 1.3 | 1.3.3.4 | P |  | UW | 35 Penetrator Cable Assemblies and attachment hardware |  |  | CapEx |  |  | EE | 1 | 1 | 0% | 2022-02-07 | 2024-09-09 |  | TRUE | [7 empty] | 16100 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 16100 | 0 | 0 | 0 | 0 | 0 | 0 | 16100 | 53% | 0 | 16100 | 16100 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 16100 | 16100 | [5 empty] | 16100 |  | 16100 | CapEx | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.3.3 | PDOM | 1.3.3 PDOM | 1.3.3.4 | IceCube DOM Refurbishment | 1.3.3.4 IceCube DOM Refurbishment | cell-link@smartsheet.com | 2021-11-30 23:06 |  | 856d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.3.3.4 | 0 | 0 | 0 | 0 | 0 | 16100 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4 | 0 | 0 | 0 | 0 | 0 | 16100 | 0 | 0 | 0 | 0 | 0 | 0 | 16100 | 1.3.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16100 | 1.3.3.4 | 16100 | 16100 | 0 | 0 | 0 | 0 | 0 | 16100 | 16100 | 16100 | 16100 | 16100 | 16100 | 16100 | 0 | 0 | 0 | 0 | 0 | 16100 | 16100 | 16100 | 16100 | 16100 | 16100 | 16100
| 1.3 | 1.3.3.4.1 | C |  | UW | Miscellaneous parts ($ 300 per refurbished PDOM) |  |  | CapEx |  |  | HD | 1 | 1 | 0% | 2022-04-25 | 2022-05-20 |  | TRUE | [9 empty] | 3000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 3000 | 53% | 0 | 3000 | 3000 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 | 3600 |  |  |  |  | 10500 |  | 3000 | CapEx | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.3.3 | PDOM | 1.3.3 PDOM | 1.3.3.4 | IceCube DOM Refurbishment | 1.3.3.4 IceCube DOM Refurbishment | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 856d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.3.3.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 1.3.3.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 3000 | 1.3.3.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 1.3.3.4.1 | 3000 | 14171.5912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 3000 | 3000 | 3000 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14171.5912 | 14171.5912 | 14171.5912 | 14171.5912 | 14171.5912
| 1.3 | 1.3.3.4.1 | C |  | UW | Refurbish 10 IceCube DOMs | N.N. | 0% | Labor Hours | EN |  |  | 40 | 40 | 35% | 2022-04-25 | 2022-05-20 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 | 8302 |  |  |  |  | 8302 |  | 0 | Labor - Task | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.3.3 | PDOM | 1.3.3 PDOM | 1.3.3.4 | IceCube DOM Refurbishment | 1.3.3.4 IceCube DOM Refurbishment | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 23d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.3.3.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.1 | 0 | 11171.5912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11171.5912 | 11171.5912 | 11171.5912 | 11171.5912 | 11171.5912
| 1.3 | 1.3.3.4.1 | C |  | PSL | Refurbish 10 IceCube DOMs | N.N. | 6.667% | Labor Hours | TE |  |  | 81 | 77 | 0% | 2022-04-25 | 2022-05-20 |  | TRUE | [9 empty] | 120 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9240 | 0 | 0 | 0 | 0 | 9240 | 0% | 0 | 9641.5912 | 9641.5912 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | 8262 |  |  |  |  | 8262 |  | 9641.5912 | Labor - Task | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.3.3 | PDOM | 1.3.3 PDOM | 1.3.3.4 | IceCube DOM Refurbishment | 1.3.3.4 IceCube DOM Refurbishment | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 23d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.3.3.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9641.5912 | 0 | 0 | 0 | 0 | 1.3.3.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9641.5912 | 0 | 0 | 0 | 0 | 9641.5912 | 1.3.3.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9641.5912 | 1.3.3.4.1 | 9641.5912 | 11171.5912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9641.5912 | 9641.5912 | 9641.5912 | 9641.5912 | 9641.5912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11171.5912 | 11171.5912 | 11171.5912 | 11171.5912 | 11171.5912
| 1.3 | 1.3.3.4.1 | C |  | UW | Refurbish 10 IceCube DOMs |  |  | M & S |  |  |  | 1 | 1 | 0% | 2022-04-25 | 2022-05-20 |  | TRUE | [9 empty] | 1000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 1000 | 53% | 530 | 1530 | 1530 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 | 1530 |  |  |  |  | 1530 |  | 1530 | M & S | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.3.3 | PDOM | 1.3.3 PDOM | 1.3.3.4 | IceCube DOM Refurbishment | 1.3.3.4 IceCube DOM Refurbishment | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 23d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.3.3.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1530 | 0 | 0 | 0 | 0 | 1.3.3.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 1000 | 1.3.3.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 530 | 0 | 0 | 0 | 0 | 530 | 1530 | 1.3.3.4.1 | 1530 | 1530 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1530 | 1530 | 1530 | 1530 | 1530 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1530 | 1530 | 1530 | 1530 | 1530
| 1.3 | 1.3.3.4.2 | C |  | UW | Design Verification Test | N.N. | 0% | Labor Hours | EN |  |  | 40 | 40 | 35% | 2022-05-23 | 2022-07-15 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 | 3321 |  |  |  |  | 3321 |  | 0 | Labor - Task | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.3.3 | PDOM | 1.3.3 PDOM | 1.3.3.4 | IceCube DOM Refurbishment | 1.3.3.4 IceCube DOM Refurbishment | cell-link@smartsheet.com | 2021-11-30 23:01 |  | 47d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.3.3.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.2 | 0 | 27550.4649 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27550.4649 | 27550.4649 | 27550.4649 | 27550.4649
| 1.3 | 1.3.3.4.2 | C |  | UW | Design Verification Test | N.N. | 5.769% | Labor Hours | SC |  |  | 45 | 45 | 35% | 2022-05-23 | 2022-07-15 |  | TRUE | [10 empty] | 120 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7290 | 0 | 0 | 0 | 7290 | 53% | 3863.7 | 11638.4649 | 11638.4649 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 | 3736 |  |  |  |  | 3736 |  | 11638.4649 | Labor - Task | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.3.3 | PDOM | 1.3.3 PDOM | 1.3.3.4 | IceCube DOM Refurbishment | 1.3.3.4 IceCube DOM Refurbishment | cell-link@smartsheet.com | 2021-11-30 23:01 |  | 47d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.3.3.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11638.4649 | 0 | 0 | 0 | 1.3.3.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5634.6961 | 0 | 0 | 0 | 5634.6961 | 1.3.3.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1972.1437 | 0 | 0 | 0 | 1972.1437 | 1.3.3.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4031.6251 | 0 | 0 | 0 | 4031.6251 | 11638.4649 | 1.3.3.4.2 | 11638.4649 | 27550.4649 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11638.4649 | 11638.4649 | 11638.4649 | 11638.4649 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27550.4649 | 27550.4649 | 27550.4649 | 27550.4649
| 1.3 | 1.3.3.4.2 | C |  | UW | Design Verification Test |  |  | M & S |  |  |  | 1 | 1 | 0% | 2022-05-23 | 2022-07-15 |  | TRUE | [10 empty] | 5000 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 5000 | 53% | 2650 | 7650 | 7650 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 | 7650 |  |  |  |  | 7650 |  | 7650 | M & S | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.3.3 | PDOM | 1.3.3 PDOM | 1.3.3.4 | IceCube DOM Refurbishment | 1.3.3.4 IceCube DOM Refurbishment | cell-link@smartsheet.com | 2021-11-30 23:01 |  | 47d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.3.3.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7650 | 0 | 0 | 0 | 1.3.3.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 5000 | 1.3.3.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2650 | 0 | 0 | 0 | 2650 | 7650 | 1.3.3.4.2 | 7650 | 15912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7650 | 7650 | 7650 | 7650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15912 | 15912 | 15912 | 15912
| 1.3 | 1.3.3.4.2 | C |  | UW | Three domestic trips to test facilities for pressure, vibration, and shock |  |  | Travel |  |  |  | 1 | 1 | 0% | 2022-05-23 | 2022-07-15 |  | TRUE | [10 empty] | 5400 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5400 | 0 | 0 | 0 | 5400 | 53% | 2862 | 8262 | 8262 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 | 8427 |  |  |  |  | 8427 |  | 8262 | Travel | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.3.3 | PDOM | 1.3.3 PDOM | 1.3.3.4 | IceCube DOM Refurbishment | 1.3.3.4 IceCube DOM Refurbishment | cell-link@smartsheet.com | 2021-11-30 23:01 |  | 47d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.3.3.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8262 | 0 | 0 | 0 | 1.3.3.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5400 | 0 | 0 | 0 | 5400 | 1.3.3.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2862 | 0 | 0 | 0 | 2862 | 8262 | 1.3.3.4.2 | 8262 | 8262 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8262 | 8262 | 8262 | 8262 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8262 | 8262 | 8262 | 8262
| 1.3 | 1.3.3.4.3 | C |  | UW | Ship DVT modules to NTS | N.N. | 0% | Labor Hours | AD |  |  | 35 | 35 | 35% | 2022-07-18 | 2022-07-29 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 | 145 |  |  |  |  | 145 |  | 0 | Labor - Task | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.3.3 | PDOM | 1.3.3 PDOM | 1.3.3.4 | IceCube DOM Refurbishment | 1.3.3.4 IceCube DOM Refurbishment | cell-link@smartsheet.com | 2021-11-30 23:01 |  | 11d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.3.3.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.3 | 0 | 1530 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1530 | 1530 | 1530
| 1.3 | 1.3.3.4.3 | C |  | UW | Ship DVT modules to NTS |  |  | M & S |  |  |  | 1 | 1 | 0% | 2022-07-18 | 2022-07-29 |  | TRUE | [11 empty] | 1000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 1000 | 53% | 530 | 1530 | 1530 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 | 1530 |  |  |  |  | 1530 |  | 1530 | M & S | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.3.3 | PDOM | 1.3.3 PDOM | 1.3.3.4 | IceCube DOM Refurbishment | 1.3.3.4 IceCube DOM Refurbishment | cell-link@smartsheet.com | 2021-11-30 23:01 |  | 11d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.3.3.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1530 | 0 | 0 | 1.3.3.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 1000 | 1.3.3.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 530 | 0 | 0 | 530 | 1530 | 1.3.3.4.3 | 1530 | 1530 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1530 | 1530 | 1530 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1530 | 1530 | 1530
| 1.3 | 1.3.3.4.3 | C |  | UW | Domestic trip to NTS to set up and comission test modules |  |  | Travel |  |  |  | 1 | 1 | 0% | 2022-07-18 | 2022-07-29 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 | 2809 |  |  |  |  | 2809 |  | 0 | Travel | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.3.3 | PDOM | 1.3.3 PDOM | 1.3.3.4 | IceCube DOM Refurbishment | 1.3.3.4 IceCube DOM Refurbishment | cell-link@smartsheet.com | 2021-11-30 23:01 |  | 11d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.3.3.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 | 1.3.3.4.4.1 | C |  | UW | Set up refurbishment Facility | Resource 2 | 0% | Labor Hours | EN |  |  | 40 | 40 | 35% | 2022-02-07 | 2022-04-29 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 13219.2 | [5 empty] | 13284 |  | 0 | Labor - Task | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.3.3 | PDOM | 1.3.3 PDOM | 1.3.3.4 | IceCube DOM Refurbishment | 1.3.3.4 IceCube DOM Refurbishment | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 72d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.3.3.4.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 | 1.3.3.4.4.1 | C |  | PSL | Set up refurbishment Facility | Resource 3 | 0% | Labor Hours | TE |  |  | 81 | 77 | 0% | 2022-02-07 | 2022-04-29 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 24640 | [5 empty] | 26438 |  | 0 | Labor - Task | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.3.3 | PDOM | 1.3.3 PDOM | 1.3.3.4 | IceCube DOM Refurbishment | 1.3.3.4 IceCube DOM Refurbishment | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 72d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.3.3.4.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 | 1.3.3.4.4.1 | C |  | UW | Set up refurbishment Facility |  |  | M & S |  |  |  | 1 | 1 | 0% | 2022-02-07 | 2022-04-29 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 30600 | [5 empty] | 30600 |  | 0 | M & S | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.3.3 | PDOM | 1.3.3 PDOM | 1.3.3.4 | IceCube DOM Refurbishment | 1.3.3.4 IceCube DOM Refurbishment | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 72d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.3.3.4.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 | 1.3.3.4.5.1 | C |  | UW | Refurbishment Batch #1 (Qty. 20) | N.N. | 0% | Labor Hours | EN |  |  | 40 | 40 | 35% | 2022-08-29 | 2022-09-23 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 | 830 |  |  |  |  | 830 |  | 0 | Labor - Task | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.3.3 | PDOM | 1.3.3 PDOM | 1.3.3.4 | IceCube DOM Refurbishment | 1.3.3.4 IceCube DOM Refurbishment | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 11d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.3.3.4.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.5.1 | 0 | 28343.1824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28343.1824
| 1.3 | 1.3.3.4.5.1 | C |  | PSL | Refurbishment Batch #1 (Qty. 20) | N.N. | 13.33% | Labor Hours | TE |  |  | 81 | 77 | 0% | 2022-08-29 | 2022-09-23 |  | TRUE | [13 empty] | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18480 | 18480 | 0% | 0 | 19283.1824 | 19283.1824 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | 8262 |  |  |  |  | 8262 |  | 19283.1824 | Labor - Task | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.3.3 | PDOM | 1.3.3 PDOM | 1.3.3.4 | IceCube DOM Refurbishment | 1.3.3.4 IceCube DOM Refurbishment | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 11d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.3.3.4.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19283.1824 | 1.3.3.4.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19283.1824 | 19283.1824 | 1.3.3.4.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19283.1824 | 1.3.3.4.5.1 | 19283.1824 | 28343.1824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19283.1824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28343.1824
| 1.3 | 1.3.3.4.5.1 | C |  | UW | Refurbishment Batch #1 (Qty. 20) |  |  | M & S |  |  |  | 1 | 1 | 0% | 2022-08-29 | 2022-09-23 |  | TRUE | [13 empty] | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 2000 | 53% | 1060 | 3060 | 3060 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 | 306 |  |  |  |  | 306 |  | 3060 | M & S | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.3.3 | PDOM | 1.3.3 PDOM | 1.3.3.4 | IceCube DOM Refurbishment | 1.3.3.4 IceCube DOM Refurbishment | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 11d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.3.3.4.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3060 | 1.3.3.4.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 2000 | 1.3.3.4.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1060 | 1060 | 3060 | 1.3.3.4.5.1 | 3060 | 9060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9060
| 1.3 | 1.3.3.4.5.1 | C |  | UW | Miscellaneous parts ($ 300 per refurbished PDOM) |  |  | CapEx |  |  | HD |  | 1 | 0% | 2022-08-29 | 2022-09-23 |  | TRUE | [13 empty] | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 6000 | 53% | 0 | 6000 | 6000 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 | 6900 | [6 empty] | 6000 | CapEx | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.3.3 | PDOM | 1.3.3 PDOM | 1.3.3.4 | IceCube DOM Refurbishment | 1.3.3.4 IceCube DOM Refurbishment | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.3.3.4.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 1.3.3.4.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 6000 | 1.3.3.4.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 1.3.3.4.5.1 | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000
| 1.3 | 1.3.3.4.5.2 | C |  | UW | FAT Batch #1 | N.N. | 1.442% | Labor Hours | SC |  |  | 45 | 45 | 35% | 2022-09-26 | 2022-11-04 |  | TRUE | [13 empty] | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1822.5 | 1822.5 | 53% | 965.925 | 2909.6162 | 2909.6162 | 80 | 20 | [10 empty] | 4860 | 1215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6075 | 53% | 3219.75 | 9907.2432 | 9907.2432 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 | 3049 |  |  |  |  | 4543 |  | 12816.8595 | Labor - Task | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.3.3 | PDOM | 1.3.3 PDOM | 1.3.3.4 | IceCube DOM Refurbishment | 1.3.3.4 IceCube DOM Refurbishment | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 17d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.3.3.4.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2909.6162 | 1.3.3.4.5.2 | 7925.7946 | 1981.4486 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1408.674 | 1408.674 | 1.3.3.4.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 493.0359 | 493.0359 | 1.3.3.4.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1007.9063 | 1007.9063 | 2909.6162 | 1.3.3.4.5.2 | 2909.6162 | 2909.6162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2909.6162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2909.6162
| 1.3 | 1.3.3.4.5.2 | C |  | UW | FAT Batch #1 |  |  | M & S |  |  |  | 1 | 1 | 0% | 2022-09-26 | 2022-11-04 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | 4000 | [11 empty] | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 53% | 2120 | 6120 | 6120 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 | 612 |  |  |  |  | 918 |  | 6120 | M & S | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.3.3 | PDOM | 1.3.3 PDOM | 1.3.3.4 | IceCube DOM Refurbishment | 1.3.3.4 IceCube DOM Refurbishment | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 17d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.3.3.4.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.5.2 | 6120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 | 1.3.3.4.5.3 | C |  | PSL | Packing Batch #1 | N.N. | 0% | Labor Hours | TE |  |  | 81 | 77 | 0% | 2022-11-07 | 2022-11-11 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  | 40 | [10 empty] | 0 | 3080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3080 | 0% | 0 | 3282.9618 | 3282.9618 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | 843 |  |  |  |  | 843 |  | 3282.9618 | Labor - Task | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.3.3 | PDOM | 1.3.3 PDOM | 1.3.3.4 | IceCube DOM Refurbishment | 1.3.3.4 IceCube DOM Refurbishment | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 5d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.3.3.4.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.5.3 | 0 | 3282.9618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 | 1.3.3.4.5.3 | C |  | UW | Packing Batch #1 |  |  | M & S |  |  |  | 1 | 1 | 0% | 2022-11-07 | 2022-11-11 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 |  | 1000 | [10 empty] | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 53% | 530 | 1530 | 1530 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 | [5 empty] | 459 |  | 1530 | M & S | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.3.3 | PDOM | 1.3.3 PDOM | 1.3.3.4 | IceCube DOM Refurbishment | 1.3.3.4 IceCube DOM Refurbishment | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 5d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.3.3.4.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.5.3 | 0 | 1530 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 | 1.3.3.4.6 | C |  | UW | Ship to Pt. Hueneme | N.N. | 0% | Labor Hours | AD |  |  | 35 | 35 | 35% | 2023-08-01 | 2023-08-28 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 | 222 |  |  |  |  | 222 |  | 0 | Labor - Task | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.3.3 | PDOM | 1.3.3 PDOM | 1.3.3.4 | IceCube DOM Refurbishment | 1.3.3.4 IceCube DOM Refurbishment | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 48d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.3.3.4.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 | 1.3.3.4.6 | C |  | UW | Ship to Pt. Hueneme |  |  | M & S |  |  |  | 1 | 1 | 0% | 2023-08-01 | 2023-08-28 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [10 empty] | 1000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 1000 | 53% | 530 | 1530 | 1530 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 | 1530 |  |  |  |  | 1530 |  | 1530 | M & S | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.3.3 | PDOM | 1.3.3 PDOM | 1.3.3.4 | IceCube DOM Refurbishment | 1.3.3.4 IceCube DOM Refurbishment | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 48d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.3.3.4.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1530 | 0 | 1.3.3.4.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 | 1.3.3.4.7 | C |  | UW | Ship to Pt. Hueneme |  |  | M & S |  |  |  |  | 1 | 0% | 2024-08-13 | 2024-09-09 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [10 empty] | 1000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 1000 | 53% | 530 | 1530 | 1530 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 1530 | M & S | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.3.3 | PDOM | 1.3.3 PDOM | 1.3.3.4 | IceCube DOM Refurbishment | 1.3.3.4 IceCube DOM Refurbishment | cell-link@smartsheet.com | 2021-11-30 23:06 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.3.3.4.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1530 | 0 | 1.3.3.4.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.4.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 | 1.3.3.3 | C |  | UW | PDOM Final Design Review (P. Sandstrom) | Sandstrom | 0% | Labor Hours | SE |  |  | 55 | 53 | 35% | 2022-07-15 | 2022-07-15 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 | 4048 |  |  |  |  | 4566 |  | 0 | Labor - Task | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.3.3 | PDOM | 1.3.3 PDOM | 1.3.3.3 | PDOM Final Design Review | 1.3.3.3 PDOM Final Design Review | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1235d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.3.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 | 1.3.3.3 | C |  | PSU | PDOM Final Design Review |  |  | Travel |  |  |  | 1 | 1 | 0% | 2022-07-15 | 2022-07-15 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 |  | 0 | [5 empty] | 2644 |  | 0 | Travel | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.3.3 | PDOM | 1.3.3 PDOM | 1.3.3.3 | PDOM Final Design Review | 1.3.3.3 PDOM Final Design Review | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1235d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.3.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 | 1.3.3.3 | C |  | UW | PDOM Final Design Review |  |  | Travel |  |  |  | 1 | 1 | 0% | 2022-07-15 | 2022-07-15 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 | [5 empty] | 2809 |  | 0 | Travel | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.3.3 | PDOM | 1.3.3 PDOM | 1.3.3.3 | PDOM Final Design Review | 1.3.3.3 PDOM Final Design Review | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1235d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.3.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TRUE | 1.3 | 1.3.4.2 | P |  | UW | ICM Firmware development | Meures | 0% | Labor Hours | EN |  |  |  | 40 | 35% | 2020-11-30 | 2021-01-15 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 0 | Labor - Task | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.3.4 | Ice Comms Module | 1.3.4 Ice Comms Module | 1.3.4.2 | ICM Firmware | 1.3.4.2 ICM Firmware | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.3.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TRUE | 1.3 | 1.3.4.2 | P |  | UW | ICM Firmware development | N.N. | 0% | Labor Hours | EN |  |  |  | 40 | 35% | 2020-11-30 | 2021-01-15 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 0 | Labor - Task | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.3.4 | Ice Comms Module | 1.3.4 Ice Comms Module | 1.3.4.2 | ICM Firmware | 1.3.4.2 ICM Firmware | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.3.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 | 1.3.5 | P |  | UW | FOM development | Resource 4 | 0% | Labor Hours | PO |  |  |  | 30 | 18.9% | 2019-01-01 | 2022-01-03 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 26196.048 | [7 empty] | 0 | Labor - Task | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.3.5 | Special Devices | 1.3.5 Special Devices | 1.3.5 | Special Devices | 1.3.5 Special Devices | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 | 1.3.5 | P |  | UW | LOM development (Ch. Wendt) | Wendt | 0% | Labor Hours | SS |  |  |  | 54 | 35% | 2019-01-01 | 2022-01-03 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 21811.68 | [7 empty] | 0 | Labor - Task | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.3.5 | Special Devices | 1.3.5 Special Devices | 1.3.5 | Special Devices | 1.3.5 Special Devices | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 | 1.3.5 | P |  | UW | FOM/LOM materials |  |  | M & S |  |  |  |  | 1 | 0% | 2019-01-01 | 2022-01-03 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 15300 | [7 empty] | 0 | M & S | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.3.5 | Special Devices | 1.3.5 Special Devices | 1.3.5 | Special Devices | 1.3.5 Special Devices | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 | 1.3.5.2 | C |  | UA | R&D module mission review | Resource 6 | 0% | Labor Hours | SC |  |  | 45 | 45 | 32% | 2020-05-04 | 2020-05-04 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49% | 0 | 0 |  | 3540.24 | 3708 |  |  |  |  | 3708 |  | 0 | Labor - Task | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.3.5 | Special Devices | 1.3.5 Special Devices | 1.3.5.2 | R&D module mission review | 1.3.5.2 R&D module mission review | cell-link@smartsheet.com | 2021-11-30 23:07 |  | 1d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.3.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 | 1.3.5.2 | C |  | UMD | R&D module mission review | Resource 7 | 0% | Labor Hours | SC |  |  | 45 | 45 | 29% | 2020-05-04 | 2020-05-04 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54.5% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54.5% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54.5% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54.5% | 0 | 0 |  | 3587.49 | 3615 |  |  |  |  | 3615 |  | 0 | Labor - Task | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.3.5 | Special Devices | 1.3.5 Special Devices | 1.3.5.2 | R&D module mission review | 1.3.5.2 R&D module mission review | cell-link@smartsheet.com | 2021-11-30 23:07 |  | 1d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.3.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 | 1.3.5.2 | C |  | UW | R&D module mission review | Resource 8 | 0% | Labor Hours | SE |  |  | 55 | 55 | 35% | 2020-05-04 | 2020-05-04 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 4544.1 | 4658 |  |  |  |  | 4658 |  | 0 | Labor - Task | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.3.5 | Special Devices | 1.3.5 Special Devices | 1.3.5.2 | R&D module mission review | 1.3.5.2 R&D module mission review | cell-link@smartsheet.com | 2021-11-30 23:07 |  | 1d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.3.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 | 1.3.5.2 | C |  | PSL | R&D module mission review | Resource 9 | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2020-05-04 | 2020-05-04 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 4600 | 4786 |  |  |  |  | 4786 |  | 0 | Labor - Task | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.3.5 | Special Devices | 1.3.5 Special Devices | 1.3.5.2 | R&D module mission review | 1.3.5.2 R&D module mission review | cell-link@smartsheet.com | 2021-11-30 23:07 |  | 1d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.3.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 | 1.3.5.2 | C |  | MSU | R&D module mission review | Resource 10 | 0% | Labor Hours | SC |  |  | 45 | 45 | 32% | 2020-05-04 | 2020-05-04 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 |  | 3682.8 | 3832 |  |  |  |  | 3832 |  | 0 | Labor - Task | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.3.5 | Special Devices | 1.3.5 Special Devices | 1.3.5.2 | R&D module mission review | 1.3.5.2 R&D module mission review | cell-link@smartsheet.com | 2021-11-30 23:07 |  | 1d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.3.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 | 1.3.5.2 | C |  | UA | R&D module mission review |  |  | Travel |  |  |  | 1 | 1 | 0% | 2020-05-04 | 2020-05-04 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49% | 0 | 0 |  | 0 | 2809 |  |  |  |  | 2809 |  | 0 | Travel | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.3.5 | Special Devices | 1.3.5 Special Devices | 1.3.5.2 | R&D module mission review | 1.3.5.2 R&D module mission review | cell-link@smartsheet.com | 2021-11-30 23:07 |  | 1d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.3.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 | 1.3.5.2 | C |  | UMD | R&D module mission review |  |  | Travel |  |  |  | 1 | 1 | 0% | 2020-05-04 | 2020-05-04 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54.5% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54.5% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54.5% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54.5% | 0 | 0 |  | 0 | 2781 |  |  |  |  | 2781 |  | 0 | Travel | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.3.5 | Special Devices | 1.3.5 Special Devices | 1.3.5.2 | R&D module mission review | 1.3.5.2 R&D module mission review | cell-link@smartsheet.com | 2021-11-30 23:07 |  | 1d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.3.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 | 1.3.5.2 | C |  | UW | R&D module mission review |  |  | Travel |  |  |  | 1 | 1 | 0% | 2020-05-04 | 2020-05-04 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 | 2865 |  |  |  |  | 2865 |  | 0 | Travel | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.3.5 | Special Devices | 1.3.5 Special Devices | 1.3.5.2 | R&D module mission review | 1.3.5.2 R&D module mission review | cell-link@smartsheet.com | 2021-11-30 23:07 |  | 1d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.3.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 | 1.3.5.2 | C |  | PSL | R&D module mission review |  |  | Travel |  |  |  | 1 | 1 | 0% | 2020-05-04 | 2020-05-04 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 | 2865 |  |  |  |  | 2865 |  | 0 | Travel | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.3.5 | Special Devices | 1.3.5 Special Devices | 1.3.5.2 | R&D module mission review | 1.3.5.2 R&D module mission review | cell-link@smartsheet.com | 2021-11-30 23:07 |  | 1d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.3.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 | 1.3.5.2 | C |  | MSU | R&D module mission review |  |  | Travel |  |  |  | 1 | 1 | 0% | 2020-05-04 | 2020-05-04 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 |  | 0 | 2903 |  |  |  |  | 2903 |  | 0 | Travel | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.3.5 | Special Devices | 1.3.5 Special Devices | 1.3.5.2 | R&D module mission review | 1.3.5.2 R&D module mission review | cell-link@smartsheet.com | 2021-11-30 23:07 |  | 1d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.3.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 | 1.3.5.4 | C |  | UA | R&D modules deployment readiness review | N.N. | 0% | Labor Hours | SC |  |  | 45 | 45 | 32% | 2022-01-03 | 2022-01-03 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49% | 0 | 0 | -3782 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49% | 0 | 0 |  | 0 |  | 3782 |  |  |  | 3782 |  | 0 | Labor - Task | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.3.5 | Special Devices | 1.3.5 Special Devices | 1.3.5.4 | R&D modules deployment readiness review | 1.3.5.4 R&D modules deployment readiness review | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.3.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 | 1.3.5.4 | C |  | UMD | R&D modules deployment readiness review | N.N. | 0% | Labor Hours | SC |  |  | 45 | 45 | 29% | 2022-01-03 | 2022-01-03 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54.5% | 0 | 0 | -3688 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54.5% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54.5% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54.5% | 0 | 0 |  | 0 |  | 3688 |  |  |  | 3688 |  | 0 | Labor - Task | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.3.5 | Special Devices | 1.3.5 Special Devices | 1.3.5.4 | R&D modules deployment readiness review | 1.3.5.4 R&D modules deployment readiness review | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.3.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 | 1.3.5.4 | C |  | UW | R&D modules deployment readiness review | N.N. | 0% | Labor Hours | SE |  |  | 55 | 55 | 35% | 2022-01-03 | 2022-01-03 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | -4751 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 |  | 4751 |  |  |  | 4751 |  | 0 | Labor - Task | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.3.5 | Special Devices | 1.3.5 Special Devices | 1.3.5.4 | R&D modules deployment readiness review | 1.3.5.4 R&D modules deployment readiness review | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.3.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 | 1.3.5.4 | C |  | PSL | R&D modules deployment readiness review | N.N. | 0% | Labor Hours | EN |  |  | 115 | 115 | 0% | 2022-01-03 | 2022-01-03 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | -4882 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 4882 |  |  |  | 4882 |  | 0 | Labor - Task | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.3.5 | Special Devices | 1.3.5 Special Devices | 1.3.5.4 | R&D modules deployment readiness review | 1.3.5.4 R&D modules deployment readiness review | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.3.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 | 1.3.5.4 | C |  | MSU | R&D modules deployment readiness review | N.N. | 0% | Labor Hours | SC |  |  | 45 | 45 | 32% | 2022-01-03 | 2022-01-03 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | -3908 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 |  | 0 |  | 3908 |  |  |  | 3908 |  | 0 | Labor - Task | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.3.5 | Special Devices | 1.3.5 Special Devices | 1.3.5.4 | R&D modules deployment readiness review | 1.3.5.4 R&D modules deployment readiness review | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.3.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 | 1.3.5.4 | C |  | UA | R&D modules deployment readiness review |  |  | Travel |  |  |  | 1 | 1 | 0% | 2022-01-03 | 2022-01-03 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49% | 0 | 0 | -2865 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49% | 0 | 0 |  | 0 |  | 2865 |  |  |  | 2865 |  | 0 | Travel | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.3.5 | Special Devices | 1.3.5 Special Devices | 1.3.5.4 | R&D modules deployment readiness review | 1.3.5.4 R&D modules deployment readiness review | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.3.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 | 1.3.5.4 | C |  | UMD | R&D modules deployment readiness review |  |  | Travel |  |  |  | 1 | 1 | 0% | 2022-01-03 | 2022-01-03 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54.5% | 0 | 0 | -2837 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54.5% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54.5% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54.5% | 0 | 0 |  | 0 |  | 2837 |  |  |  | 2837 |  | 0 | Travel | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.3.5 | Special Devices | 1.3.5 Special Devices | 1.3.5.4 | R&D modules deployment readiness review | 1.3.5.4 R&D modules deployment readiness review | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.3.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 | 1.3.5.4 | C |  | UW | R&D modules deployment readiness review |  |  | Travel |  |  |  | 1 | 1 | 0% | 2022-01-03 | 2022-01-03 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | -2923 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 |  | 2923 |  |  |  | 2923 |  | 0 | Travel | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.3.5 | Special Devices | 1.3.5 Special Devices | 1.3.5.4 | R&D modules deployment readiness review | 1.3.5.4 R&D modules deployment readiness review | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.3.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 | 1.3.5.4 | C |  | PSL | R&D modules deployment readiness review |  |  | Travel |  |  |  | 1 | 1 | 0% | 2022-01-03 | 2022-01-03 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | -2923 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 |  | 2923 |  |  |  | 2923 |  | 0 | Travel | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.3.5 | Special Devices | 1.3.5 Special Devices | 1.3.5.4 | R&D modules deployment readiness review | 1.3.5.4 R&D modules deployment readiness review | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.3.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 | 1.3.5.4 | C |  | MSU | R&D modules deployment readiness review |  |  | Travel |  |  |  | 1 | 1 | 0% | 2022-01-03 | 2022-01-03 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | -2961 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 |  | 0 |  | 2961 |  |  |  | 2961 |  | 0 | Travel | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.3.5 | Special Devices | 1.3.5 Special Devices | 1.3.5.4 | R&D modules deployment readiness review | 1.3.5.4 R&D modules deployment readiness review | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.3.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | 1.4 | P |  | MSU | CPT Management - Ty DeYoung | DeYoung | 11.54% | Labor Hours | KE |  |  | 100 | 81 | 8% | 2018-11-14 | 2025-10-01 |  | TRUE | [9 empty] | 40 | 80 | 80 | 40 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3499.2 | 6998.4 | 6998.4 | 3499.2 | 0 | 20995.2 | 55% | 11547.36 | 33956.9329 | 11071.7579 | [7 empty] | 40 | 80 | 80 | 40 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3499.2 | 6998.4 | 6998.4 | 3499.2 | 0 | 20995.2 | 55% | 11547.36 | 34687.0069 | 34687.0069 | [7 empty] | 40 | 80 | 80 | 40 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3499.2 | 6998.4 | 6998.4 | 3499.2 | 0 | 20995.2 | 55% | 11547.36 | 35432.7776 | 35432.7776 | [7 empty] | 40 | 80 | 80 | 40 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3499.2 | 6998.4 | 6998.4 | 3499.2 | 0 | 20995.2 | 55% | 11547.36 | 36194.5823 | 10416 | 21585.2256 | 22327 | 22885.175 |  | 0 |  | 54205 |  | 140271.2997 | Labor - LoE | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4 | CPT management | 1.4 CPT management | 1.4 | CPT | 1.4 CPT | cell-link@smartsheet.com | 2021-12-01 14:33 |  | 1431d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5659.4888 | 11318.9776 | 11318.9776 | 5659.4888 | 0 | 1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5781.1678 | 11562.3356 | 11562.3356 | 5781.1678 | 0 | 1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5905.4629 | 11810.9259 | 11810.9259 | 5905.4629 | 0 | 1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6032.4304 | 12064.8608 | 12064.8608 | 6032.4304 | 0 | 1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3380.8177 | 6761.6354 | 6761.6354 | 3380.8177 | 0 | 20284.9061 | 1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 270.4654 | 540.9308 | 540.9308 | 270.4654 | 0 | 1622.7925 | 1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2008.2057 | 4016.4114 | 4016.4114 | 2008.2057 | 0 | 12049.2342 | 33956.9329 | 1.4 | 33956.9329 | 40311.9329 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5659.4888 | 16978.4664 | 28297.4441 | 33956.9329 | 33956.9329 | 2983.75 | 2983.75 | 2983.75 | 3177.5 | 3177.5 | 3177.5 | 6161.25 | 11820.7388 | 23139.7164 | 34652.4441 | 40311.9329 | 40311.9329
| 1.4 | 1.4 | P |  | MSU | Miscellaneous Supplies |  |  | M & S |  |  |  | 1 | 1 | 0% | 2018-11-14 | 2025-10-01 |  | TRUE |  |  | 125 |  |  | 125 |  |  | 125 |  |  | 125 |  |  | 125 | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 500 | 55% | 275 | 775 | 0 | 125 |  |  | 125 |  |  | 125 |  |  | 125 |  |  | 125 | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 500 | 55% | 275 | 775 | 0 | 125 |  |  | 125 |  |  | 125 |  |  | 125 |  |  | 125 | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 500 | 55% | 275 | 775 | 775 | 125 |  |  | 125 |  |  | 125 |  |  | 125 |  |  | 125 | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 500 | 55% | 275 | 775 | 775 | 775 | 775 | 775 |  | 775 |  | 3875 |  | 3100 | M & S | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4 | CPT management | 1.4 CPT management | 1.4 | CPT | 1.4 CPT | cell-link@smartsheet.com | 2021-12-01 14:33 |  | 1431d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4 | 193.75 | 0 | 0 | 193.75 | 0 | 0 | 193.75 | 0 | 0 | 193.75 | 0 | 0 | 1.4 | 193.75 | 0 | 0 | 193.75 | 0 | 0 | 193.75 | 0 | 0 | 193.75 | 0 | 0 | 1.4 | 193.75 | 0 | 0 | 193.75 | 0 | 0 | 193.75 | 0 | 0 | 193.75 | 0 | 0 | 1.4 | 193.75 | 0 | 0 | 193.75 | 0 | 0 | 193.75 | 0 | 0 | 193.75 | 0 | 0 | 1.4 | 125 | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 500 | 1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4 | 68.75 | 0 | 0 | 68.75 | 0 | 0 | 68.75 | 0 | 0 | 68.75 | 0 | 0 | 275 | 775 | 1.4 | 775 | 6355 | 193.75 | 193.75 | 193.75 | 387.5 | 387.5 | 387.5 | 581.25 | 581.25 | 581.25 | 775 | 775 | 775 | 2983.75 | 2983.75 | 2983.75 | 3177.5 | 3177.5 | 3177.5 | 6161.25 | 6161.25 | 6161.25 | 6355 | 6355 | 6355
| 1.4 | 1.4 | P |  | MSU | Reviews and Project Planning Meetings | DeYoung |  | Travel |  |  |  | 1 | 1 | 0% | 2018-11-14 | 2025-10-01 |  | TRUE |  |  | 1800 | [5 empty] | 1800 | [5 empty] | 1800 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 3600 | 55% | 1980 | 5580 | 0 | 1800 | [5 empty] | 1800 | [5 empty] | 1800 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 3600 | 55% | 1980 | 5580 | 2790 | 1800 | [5 empty] | 1800 | [5 empty] | 1800 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 3600 | 55% | 1980 | 5580 | 5580 | 1800 | [5 empty] | 1800 | [5 empty] | 1800 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 3600 | 55% | 1980 | 5580 | 5580 | 5580 | 5580 | 5580 |  | 2790 |  | 20155 |  | 22320 | Travel | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4 | CPT management | 1.4 CPT management | 1.4 | CPT | 1.4 CPT | cell-link@smartsheet.com | 2021-12-01 14:33 |  | 1431d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4 | 2790 | 0 | 0 | 0 | 0 | 0 | 2790 | 0 | 0 | 0 | 0 | 0 | 1.4 | 2790 | 0 | 0 | 0 | 0 | 0 | 2790 | 0 | 0 | 0 | 0 | 0 | 1.4 | 2790 | 0 | 0 | 0 | 0 | 0 | 2790 | 0 | 0 | 0 | 0 | 0 | 1.4 | 2790 | 0 | 0 | 0 | 0 | 0 | 2790 | 0 | 0 | 0 | 0 | 0 | 1.4 | 1800 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 3600 | 1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4 | 990 | 0 | 0 | 0 | 0 | 0 | 990 | 0 | 0 | 0 | 0 | 0 | 1980 | 5580 | 1.4 | 5580 | 5580 | 2790 | 2790 | 2790 | 2790 | 2790 | 2790 | 5580 | 5580 | 5580 | 5580 | 5580 | 5580 | 2790 | 2790 | 2790 | 2790 | 2790 | 2790 | 5580 | 5580 | 5580 | 5580 | 5580 | 5580
| 1.4 | 1.4.1.1 | P |  | MSU | Miscellaneous supplies |  |  | M & S |  |  |  |  | 1 | 0% | 2018-11-14 | 2023-05-09 |  |  |  |  | 125 |  |  | 125 |  |  | 125 |  |  | 125 |  |  | 125 | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 500 | 55% | 275 | 775 | 775 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | [9 empty] | 775 | M & S | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.1 | Main Cable Assembly | 1.4.1.1 Main Cable Assembly | cell-link@smartsheet.com | 2021-11-30 23:14 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.1 | 193.75 | 0 | 0 | 193.75 | 0 | 0 | 193.75 | 0 | 0 | 193.75 | 0 | 0 | 1.4.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1 | 125 | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 500 | 1.4.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1 | 68.75 | 0 | 0 | 68.75 | 0 | 0 | 68.75 | 0 | 0 | 68.75 | 0 | 0 | 275 | 775 | 1.4.1.1 | 775 | 775 | 193.75 | 193.75 | 193.75 | 387.5 | 387.5 | 387.5 | 581.25 | 581.25 | 581.25 | 775 | 775 | 775 | 193.75 | 193.75 | 193.75 | 387.5 | 387.5 | 387.5 | 581.25 | 581.25 | 581.25 | 775 | 775 | 775
| 1.4 | 1.4.1.1.1.1.3 | C |  | MSU | Sample quads for evaluation |  |  | CapEx |  |  | HD |  | 1 | 0% | 2021-01-01 | 2021-10-29 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 |  | 10075 | [7 empty] | 0 | CapEx | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.1 | Main Cable Assembly | 1.4.1.1 Main Cable Assembly | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 915d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.1.1.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | 1.4.1.1.1.1.3 | C |  | MSU | Procurement of sample quads | Ferguson | 0% | Labor Hours | EN |  |  |  | 60 | 0% | 2021-01-01 | 2021-10-29 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | [9 empty] | 0 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.1 | Main Cable Assembly | 1.4.1.1 Main Cable Assembly | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.1.1.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | 1.4.1.1.1.1.4 | C |  | MSU | Evaluation of sample quads | Ferguson | 1.923% | Labor Hours | EN |  |  | 1 | 60 | 0% | 2021-03-01 | 2022-03-01 | [7 empty] | 20 | 20 | [7 empty] | 0 | 0 | 0 | 1200 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2400 | 55% | 1320 | 3881.6796 | 3106.6796 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | -775 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 775 | 775 | 775 | 775 |  | 775 |  | 3875 |  | 3881.6796 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.1 | Main Cable Assembly | 1.4.1.1 Main Cable Assembly | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 695d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.1.1.1.4 | 0 | 0 | 0 | 1940.8398 | 1940.8398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.1.4 | 0 | 0 | 0 | 1252.1547 | 1252.1547 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2504.3094 | 1.4.1.1.1.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.1.4 | 0 | 0 | 0 | 688.6851 | 688.6851 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1377.3702 | 3881.6796 | 1.4.1.1.1.1.4 | 3881.6796 | 3881.6796 | 0 | 0 | 0 | 1940.8398 | 3881.6796 | 3881.6796 | 3881.6796 | 3881.6796 | 3881.6796 | 3881.6796 | 3881.6796 | 3881.6796 | 0 | 0 | 0 | 1940.8398 | 3881.6796 | 3881.6796 | 3881.6796 | 3881.6796 | 3881.6796 | 3881.6796 | 3881.6796 | 3881.6796
| 1.4 | 1.4.1.1.1.2.1 | C |  | MSU | Main cable final design | Ferguson, Ng | 5.769% | Labor Hours | EN |  |  | 1 | 60 | 0% | 2021-01-01 | 2022-06-01 |  | TRUE |  |  |  |  | 20 | 20 | 20 | 20 | 20 | 20 |  |  |  |  | 0 | 0 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 0 | 0 | 0 | 0 | 7200 | 55% | 3960 | 11645.0387 | 11645.0387 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 30690 | 5580 | [5 empty] | 30690 |  | 11645.0387 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.1 | Main Cable Assembly | 1.4.1.1 Main Cable Assembly | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 695d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.1.1.2.1 | 0 | 0 | 1940.8398 | 1940.8398 | 1940.8398 | 1940.8398 | 1940.8398 | 1940.8398 | 0 | 0 | 0 | 0 | 1.4.1.1.1.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.2.1 | 0 | 0 | 1252.1547 | 1252.1547 | 1252.1547 | 1252.1547 | 1252.1547 | 1252.1547 | 0 | 0 | 0 | 0 | 7512.9282 | 1.4.1.1.1.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.2.1 | 0 | 0 | 688.6851 | 688.6851 | 688.6851 | 688.6851 | 688.6851 | 688.6851 | 0 | 0 | 0 | 0 | 4132.1105 | 11645.0387 | 1.4.1.1.1.2.1 | 11645.0387 | 11645.0387 | 0 | 0 | 1940.8398 | 3881.6796 | 5822.5194 | 7763.3591 | 9704.1989 | 11645.0387 | 11645.0387 | 11645.0387 | 11645.0387 | 11645.0387 | 0 | 0 | 1940.8398 | 3881.6796 | 5822.5194 | 7763.3591 | 9704.1989 | 11645.0387 | 11645.0387 | 11645.0387 | 11645.0387 | 11645.0387
| 1.4 | 1.4.1.1.1.2.2 | C |  | MSU | Prototype main cable production | Ng | 1.923% | Labor Hours | EN |  |  | 1 | 60 | 0% | 2021-04-01 | 2022-03-01 |  |  |  |  | 10 | 10 | 10 | 10 | [8 empty] | 600 | 600 | 600 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2400 | 55% | 1320 | 3881.6796 | 3881.6796 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 8370 | 8370 | 8370 |  |  |  |  | 16907 |  | 3881.6796 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.1 | Main Cable Assembly | 1.4.1.1 Main Cable Assembly | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 695d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.1.1.2.2 | 970.4199 | 970.4199 | 970.4199 | 970.4199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.2.2 | 626.0774 | 626.0774 | 626.0774 | 626.0774 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2504.3094 | 1.4.1.1.1.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.2.2 | 344.3425 | 344.3425 | 344.3425 | 344.3425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1377.3702 | 3881.6796 | 1.4.1.1.1.2.2 | 3881.6796 | 3881.6796 | 970.4199 | 1940.8398 | 2911.2597 | 3881.6796 | 3881.6796 | 3881.6796 | 3881.6796 | 3881.6796 | 3881.6796 | 3881.6796 | 3881.6796 | 3881.6796 | 970.4199 | 1940.8398 | 2911.2597 | 3881.6796 | 3881.6796 | 3881.6796 | 3881.6796 | 3881.6796 | 3881.6796 | 3881.6796 | 3881.6796 | 3881.6796
| 1.4 | 1.4.1.1.1.2.2 | C |  | MSU | Prototype main cable production |  |  | CapEx |  |  | HD |  | 1 | 0% | 2021-04-01 | 2022-03-01 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | [9 empty] | 0 | CapEx | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.1 | Main Cable Assembly | 1.4.1.1 Main Cable Assembly | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.1.1.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | 1.4.1.1.1.2.3 | C |  | MSU | Prototype main cable testing | Ferguson, Ng | 5.769% | Labor Hours | EN |  |  | 1 | 60 | 0% | 2022-03-02 | 2022-03-29 |  | TRUE | [7 empty] | 120 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 7200 | 0 | 0 | 0 | 0 | 0 | 0 | 7200 | 55% | 3960 | 11645.0387 | 11645.0387 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 16000 | 12000 | [5 empty] | 16000 |  | 11645.0387 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.1 | Main Cable Assembly | 1.4.1.1 Main Cable Assembly | cell-link@smartsheet.com | 2021-11-30 23:09 |  | 695d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.1.1.2.3 | 0 | 0 | 0 | 0 | 0 | 11645.0387 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.2.3 | 0 | 0 | 0 | 0 | 0 | 7512.9282 | 0 | 0 | 0 | 0 | 0 | 0 | 7512.9282 | 1.4.1.1.1.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.2.3 | 0 | 0 | 0 | 0 | 0 | 4132.1105 | 0 | 0 | 0 | 0 | 0 | 0 | 4132.1105 | 11645.0387 | 1.4.1.1.1.2.3 | 11645.0387 | 22340.0387 | 0 | 0 | 0 | 0 | 0 | 11645.0387 | 11645.0387 | 11645.0387 | 11645.0387 | 11645.0387 | 11645.0387 | 11645.0387 | 0 | 0 | 0 | 0 | 0 | 22340.0387 | 22340.0387 | 22340.0387 | 22340.0387 | 22340.0387 | 22340.0387 | 22340.0387
| 1.4 | 1.4.1.1.1.2.3 | C |  | MSU | Prototype main cable testing |  |  | M & S |  |  | EE |  | 1 | 0% | 2022-03-02 | 2022-03-29 | [9 empty] | 1500 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 55% | 825 | 2325 | 2325 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | [9 empty] | 2325 | M & S | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.1 | Main Cable Assembly | 1.4.1.1 Main Cable Assembly | cell-link@smartsheet.com | 2021-11-30 23:09 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.1.1.2.3 | 0 | 0 | 0 | 0 | 0 | 2325 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.2.3 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 1.4.1.1.1.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.2.3 | 0 | 0 | 0 | 0 | 0 | 825 | 0 | 0 | 0 | 0 | 0 | 0 | 825 | 2325 | 1.4.1.1.1.2.3 | 2325 | 10695 | 0 | 0 | 0 | 0 | 0 | 2325 | 2325 | 2325 | 2325 | 2325 | 2325 | 2325 | 0 | 0 | 0 | 0 | 0 | 10695 | 10695 | 10695 | 10695 | 10695 | 10695 | 10695
| 1.4 | 1.4.1.1.1.2.3 | C |  | MSU | Prototype main cable testing |  |  | Travel |  |  |  |  | 1 | 0% | 2022-03-02 | 2022-03-29 | [9 empty] | 5400 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 5400 | 0 | 0 | 0 | 0 | 0 | 0 | 5400 | 55% | 2970 | 8370 | 8370 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | [9 empty] | 8370 | Travel | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.1 | Main Cable Assembly | 1.4.1.1 Main Cable Assembly | cell-link@smartsheet.com | 2021-11-30 23:09 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.1.1.2.3 | 0 | 0 | 0 | 0 | 0 | 8370 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.2.3 | 0 | 0 | 0 | 0 | 0 | 5400 | 0 | 0 | 0 | 0 | 0 | 0 | 5400 | 1.4.1.1.1.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.2.3 | 0 | 0 | 0 | 0 | 0 | 2970 | 0 | 0 | 0 | 0 | 0 | 0 | 2970 | 8370 | 1.4.1.1.1.2.3 | 8370 | 8370 | 0 | 0 | 0 | 0 | 0 | 8370 | 8370 | 8370 | 8370 | 8370 | 8370 | 8370 | 0 | 0 | 0 | 0 | 0 | 8370 | 8370 | 8370 | 8370 | 8370 | 8370 | 8370
| 1.4 | 1.4.1.1.1.2.4 | C |  | MSU | Final design review | Ferguson, Ng | 3.846% | Labor Hours | EN |  |  |  | 60 | 0% | 2022-03-30 | 2022-04-12 |  | TRUE | [8 empty] | 80 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 4800 | 0 | 0 | 0 | 0 | 0 | 4800 | 55% | 2640 | 7763.3591 | 7763.3591 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 |  | 21700 | [7 empty] | 7763.3591 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.1 | Main Cable Assembly | 1.4.1.1 Main Cable Assembly | cell-link@smartsheet.com | 2021-11-30 23:09 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.1.1.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 7763.3591 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 5008.6188 | 0 | 0 | 0 | 0 | 0 | 5008.6188 | 1.4.1.1.1.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 2754.7403 | 0 | 0 | 0 | 0 | 0 | 2754.7403 | 7763.3591 | 1.4.1.1.1.2.4 | 7763.3591 | 7763.3591 | 0 | 0 | 0 | 0 | 0 | 0 | 7763.3591 | 7763.3591 | 7763.3591 | 7763.3591 | 7763.3591 | 7763.3591 | 0 | 0 | 0 | 0 | 0 | 0 | 7763.3591 | 7763.3591 | 7763.3591 | 7763.3591 | 7763.3591 | 7763.3591
| 1.4 | 1.4.1.1.1.2.5 | C |  | MSU | Prototype main cable shipping to breakout installation facility | Ng | 1.923% | Labor Hours | EN |  |  |  | 60 | 0% | 2022-03-30 | 2022-05-03 |  | TRUE | [8 empty] | 40 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 2400 | 0 | 0 | 0 | 0 | 0 | 2400 | 55% | 1320 | 3881.6796 | 3881.6796 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 |  | 9300 | [7 empty] | 3881.6796 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.1 | Main Cable Assembly | 1.4.1.1 Main Cable Assembly | cell-link@smartsheet.com | 2021-11-30 23:09 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.1.1.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 3881.6796 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 2504.3094 | 0 | 0 | 0 | 0 | 0 | 2504.3094 | 1.4.1.1.1.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 1377.3702 | 0 | 0 | 0 | 0 | 0 | 1377.3702 | 3881.6796 | 1.4.1.1.1.2.5 | 3881.6796 | 11631.6796 | 0 | 0 | 0 | 0 | 0 | 0 | 3881.6796 | 3881.6796 | 3881.6796 | 3881.6796 | 3881.6796 | 3881.6796 | 0 | 0 | 0 | 0 | 0 | 0 | 3881.6796 | 11631.6796 | 11631.6796 | 11631.6796 | 11631.6796 | 11631.6796
| 1.4 | 1.4.1.1.1.2.5 | C |  | MSU | Prototype main cable shipping to breakout installation facility |  |  | M & S |  |  | EE |  | 1 | 0% | 2022-03-30 | 2022-05-03 | [11 empty] | 5000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 5000 | 55% | 2750 | 7750 | 7750 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | [9 empty] | 7750 | M & S | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.1 | Main Cable Assembly | 1.4.1.1 Main Cable Assembly | cell-link@smartsheet.com | 2021-11-30 23:09 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.1.1.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7750 | 0 | 0 | 0 | 0 | 1.4.1.1.1.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 5000 | 1.4.1.1.1.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2750 | 0 | 0 | 0 | 0 | 2750 | 7750 | 1.4.1.1.1.2.5 | 7750 | 7750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7750 | 7750 | 7750 | 7750 | 7750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7750 | 7750 | 7750 | 7750 | 7750
| 1.4 | 1.4.1.1.1.3.1 | C |  | MSU | Procurement | Ferguson | 1.923% | Labor Hours | EN |  |  |  | 60 | 0% | 2021-01-05 | 2022-05-03 |  | TRUE | [8 empty] | 40 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 2400 | 0 | 0 | 0 | 0 | 0 | 2400 | 55% | 1320 | 3881.6796 | 3881.6796 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 |  | 5580 | [7 empty] | 3881.6796 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.1 | Main Cable Assembly | 1.4.1.1 Main Cable Assembly | cell-link@smartsheet.com | 2021-11-30 23:14 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.1.1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 3881.6796 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 2504.3094 | 0 | 0 | 0 | 0 | 0 | 2504.3094 | 1.4.1.1.1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 1377.3702 | 0 | 0 | 0 | 0 | 0 | 1377.3702 | 3881.6796 | 1.4.1.1.1.3.1 | 3881.6796 | 3881.6796 | 0 | 0 | 0 | 0 | 0 | 0 | 3881.6796 | 3881.6796 | 3881.6796 | 3881.6796 | 3881.6796 | 3881.6796 | 0 | 0 | 0 | 0 | 0 | 0 | 3881.6796 | 3881.6796 | 3881.6796 | 3881.6796 | 3881.6796 | 3881.6796
| 1.4 | 1.4.1.1.1.3.2.1 | C |  | MSU | Fabrication | Ferguson, Ng | 6.731% | Labor Hours | EN |  |  |  | 60 | 0% | 2022-05-04 | 2022-07-26 | [11 empty] | 60 | 40 | 40 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3600 | 2400 | 2400 | 0 | 0 | 8400 | 55% | 4620 | 13585.8785 | 13585.8785 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 |  | 0 | 5400 | [6 empty] | 13585.8785 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.1 | Main Cable Assembly | 1.4.1.1 Main Cable Assembly | cell-link@smartsheet.com | 2021-11-30 23:14 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.1.1.3.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5822.5194 | 3881.6796 | 3881.6796 | 0 | 0 | 1.4.1.1.1.3.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.3.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.3.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.3.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3756.4641 | 2504.3094 | 2504.3094 | 0 | 0 | 8765.0829 | 1.4.1.1.1.3.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.3.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2066.0553 | 1377.3702 | 1377.3702 | 0 | 0 | 4820.7956 | 13585.8785 | 1.4.1.1.1.3.2.1 | 13585.8785 | 13585.8785 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5822.5194 | 9704.1989 | 13585.8785 | 13585.8785 | 13585.8785 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5822.5194 | 9704.1989 | 13585.8785 | 13585.8785 | 13585.8785
| 1.4 | 1.4.1.1.1.3.2.2 | C |  | MSU | Electrical verification testing | Ferguson | 2.885% | Labor Hours | EN |  |  | 50 | 60 | 0% | 2022-07-27 | 2022-08-02 | [13 empty] | 60 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3600 | 0 | 0 | 3600 | 55% | 1980 | 5822.5194 | 5822.5194 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 4092 | 0 | [5 empty] | 4092 |  | 5822.5194 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.1 | Main Cable Assembly | 1.4.1.1 Main Cable Assembly | cell-link@smartsheet.com | 2021-11-30 23:14 |  | 2d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.1.1.3.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5822.5194 | 0 | 0 | 1.4.1.1.1.3.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.3.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.3.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.3.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3756.4641 | 0 | 0 | 3756.4641 | 1.4.1.1.1.3.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.3.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2066.0553 | 0 | 0 | 2066.0553 | 5822.5194 | 1.4.1.1.1.3.2.2 | 5822.5194 | 14192.5194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5822.5194 | 5822.5194 | 5822.5194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14192.5194 | 14192.5194 | 14192.5194
| 1.4 | 1.4.1.1.1.3.2.2 | C |  | MSU | Electrical verification testing |  |  | Travel |  |  |  |  | 1 | 0% | 2022-07-27 | 2022-08-02 | [13 empty] | 5400 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5400 | 0 | 0 | 5400 | 55% | 2970 | 8370 | 8370 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | [9 empty] | 8370 | Travel | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.1 | Main Cable Assembly | 1.4.1.1 Main Cable Assembly | cell-link@smartsheet.com | 2021-11-30 23:14 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.1.1.3.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8370 | 0 | 0 | 1.4.1.1.1.3.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.3.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.3.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.3.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5400 | 0 | 0 | 5400 | 1.4.1.1.1.3.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.3.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2970 | 0 | 0 | 2970 | 8370 | 1.4.1.1.1.3.2.2 | 8370 | 8370 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8370 | 8370 | 8370 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8370 | 8370 | 8370
| 1.4 | 1.4.1.1.1.3.2.4 | C |  | MSU | First article shipping to breakout installation facility | Ferguson | 0.9615% | Labor Hours | EN |  |  | 50 | 60 | 0% | 2022-08-03 | 2022-09-06 | [14 empty] | 20 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 0 | 1200 | 55% | 660 | 1940.8398 | 1940.8398 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 7161 | 9486 | [5 empty] | 7161 |  | 1940.8398 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.1 | Main Cable Assembly | 1.4.1.1 Main Cable Assembly | cell-link@smartsheet.com | 2021-11-30 23:14 |  | 103d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.1.1.3.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1940.8398 | 0 | 1.4.1.1.1.3.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.3.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.3.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.3.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1252.1547 | 0 | 1252.1547 | 1.4.1.1.1.3.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.3.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 688.6851 | 0 | 688.6851 | 1940.8398 | 1.4.1.1.1.3.2.4 | 1940.8398 | 1940.8398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1940.8398 | 1940.8398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1940.8398 | 1940.8398
| 1.4 | 1.4.1.1.1.3.3 | C |  | MSU | Production readiness review | Ferguson, Ng | 5.769% | Labor Hours | EN |  |  | 50 | 60 | 0% | 2022-08-03 | 2022-08-16 | [14 empty] | 120 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7200 | 0 | 7200 | 55% | 3960 | 11645.0387 | 11645.0387 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 5115 | 22134 | [5 empty] | 5115 |  | 11645.0387 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.1 | Main Cable Assembly | 1.4.1.1 Main Cable Assembly | cell-link@smartsheet.com | 2021-11-30 23:14 |  | 105d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.1.1.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11645.0387 | 0 | 1.4.1.1.1.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7512.9282 | 0 | 7512.9282 | 1.4.1.1.1.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4132.1105 | 0 | 4132.1105 | 11645.0387 | 1.4.1.1.1.3.3 | 11645.0387 | 11645.0387 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11645.0387 | 11645.0387 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11645.0387 | 11645.0387
| 1.4 | 1.4.1.1.1.3.4 | C |  | MSU | Production of final six main cables | Ferguson, Ng | 1.923% | Labor Hours | EN |  |  |  | 60 | 0% | 2022-08-17 | 2022-11-22 | [14 empty] | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 1200 | 2400 | 55% | 1320 | 3881.6796 | 3881.6796 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 |  | 11067 | [7 empty] | 3881.6796 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.1 | Main Cable Assembly | 1.4.1.1 Main Cable Assembly | cell-link@smartsheet.com | 2021-11-30 23:14 |  | 12d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.1.1.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1940.8398 | 1940.8398 | 1.4.1.1.1.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1252.1547 | 1252.1547 | 2504.3094 | 1.4.1.1.1.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 688.6851 | 688.6851 | 1377.3702 | 3881.6796 | 1.4.1.1.1.3.4 | 3881.6796 | 3881.6796 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1940.8398 | 3881.6796 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1940.8398 | 3881.6796
| 1.4 | 1.4.1.1.1.3.5 | C |  | MSU | Main Cable Production Complete |  | 0% | Labor Hours | EN |  |  | 50 | 60 | 0% | 2022-11-23 | 2022-11-23 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 4092 | 12648 | [5 empty] | 12440 |  | 0 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.1 | Main Cable Assembly | 1.4.1.1 Main Cable Assembly | cell-link@smartsheet.com | 2021-11-30 23:14 |  | 12d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.1.1.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | 1.4.1.1.1.3.6 | C |  | MSU | Production cable shipping to breakout installation facility | Ferguson | 0% | Labor Hours | EN |  |  | 50 | 60 | 0% | 2022-11-23 | 2022-12-27 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 4092 | 18972 | [5 empty] | 4092 |  | 0 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.1 | Main Cable Assembly | 1.4.1.1 Main Cable Assembly | cell-link@smartsheet.com | 2021-11-30 23:14 |  | 18d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.1.1.3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1.3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | 1.4.1.1.2.1.1 | C |  | MSU | Breakout preliminary design | Ferguson, Ng | 7.692% | Labor Hours | EN |  |  | 100 | 60 | 0% | 2021-01-01 | 2022-04-15 | [7 empty] | 20 | 20 | 40 | 80 | [5 empty] | 0 | 0 | 0 | 1200 | 1200 | 2400 | 4800 | 0 | 0 | 0 | 0 | 0 | 9600 | 55% | 5280 | 15526.7183 | -7358.4567 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 10416 | 21585.2256 | 22327 | 22885.175 |  | 0 |  | 54205 |  | 15526.7183 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.1 | Main Cable Assembly | 1.4.1.1 Main Cable Assembly | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1431d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.1.2.1.1 | 0 | 0 | 0 | 1940.8398 | 1940.8398 | 3881.6796 | 7763.3591 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.2.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.2.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.2.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.2.1.1 | 0 | 0 | 0 | 1252.1547 | 1252.1547 | 2504.3094 | 5008.6188 | 0 | 0 | 0 | 0 | 0 | 10017.2376 | 1.4.1.1.2.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.2.1.1 | 0 | 0 | 0 | 688.6851 | 688.6851 | 1377.3702 | 2754.7403 | 0 | 0 | 0 | 0 | 0 | 5509.4807 | 15526.7183 | 1.4.1.1.2.1.1 | 15526.7183 | 15526.7183 | 0 | 0 | 0 | 1940.8398 | 3881.6796 | 7763.3591 | 15526.7183 | 15526.7183 | 15526.7183 | 15526.7183 | 15526.7183 | 15526.7183 | 0 | 0 | 0 | 1940.8398 | 3881.6796 | 7763.3591 | 15526.7183 | 15526.7183 | 15526.7183 | 15526.7183 | 15526.7183 | 15526.7183
| 1.4 | 1.4.1.1.2.1.2 | C |  | MSU | Breakout preliminary design review | Ferguson, Ng | 2.885% | Labor Hours | EN |  |  | 1 | 60 | 0% | 2022-04-18 | 2022-04-29 | [10 empty] | 60 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 3600 | 0 | 0 | 0 | 0 | 0 | 3600 | 55% | 1980 | 5822.5194 | 5047.5194 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | -775 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 775 | 775 | 775 | 775 |  | 775 |  | 3875 |  | 5822.5194 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.1 | Main Cable Assembly | 1.4.1.1 Main Cable Assembly | cell-link@smartsheet.com | 2021-11-30 23:09 |  | 1431d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.1.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 5822.5194 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 3756.4641 | 0 | 0 | 0 | 0 | 0 | 3756.4641 | 1.4.1.1.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 2066.0553 | 0 | 0 | 0 | 0 | 0 | 2066.0553 | 5822.5194 | 1.4.1.1.2.1.2 | 5822.5194 | 5822.5194 | 0 | 0 | 0 | 0 | 0 | 0 | 5822.5194 | 5822.5194 | 5822.5194 | 5822.5194 | 5822.5194 | 5822.5194 | 0 | 0 | 0 | 0 | 0 | 0 | 5822.5194 | 5822.5194 | 5822.5194 | 5822.5194 | 5822.5194 | 5822.5194
| 1.4 | 1.4.1.1.2.2.1 | C |  | MSU | Breakout final design | Ferguson, Ng | 8.654% | Labor Hours | EN |  |  | 1 | 60 | 0% | 2022-05-02 | 2022-07-08 | [11 empty] | 60 | 80 | 40 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3600 | 4800 | 2400 | 0 | 0 | 10800 | 55% | 5940 | 17467.5581 | 11887.5581 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | -2790 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 5580 | 5580 | 5580 | 5580 |  | 2790 |  | 20155 |  | 17467.5581 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.1 | Main Cable Assembly | 1.4.1.1 Main Cable Assembly | cell-link@smartsheet.com | 2021-12-02 19:33 |  | 1431d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.1.2.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5822.5194 | 7763.3591 | 3881.6796 | 0 | 0 | 1.4.1.1.2.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.2.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.2.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.2.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3756.4641 | 5008.6188 | 2504.3094 | 0 | 0 | 11269.3923 | 1.4.1.1.2.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.2.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2066.0553 | 2754.7403 | 1377.3702 | 0 | 0 | 6198.1658 | 17467.5581 | 1.4.1.1.2.2.1 | 17467.5581 | 17467.5581 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5822.5194 | 13585.8785 | 17467.5581 | 17467.5581 | 17467.5581 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5822.5194 | 13585.8785 | 17467.5581 | 17467.5581 | 17467.5581
| 1.4 | 1.4.1.1.2.2.2 | C |  | MSU | Breakout prototype production | Ferguson, Ng | 1.923% | Labor Hours | EN |  |  |  | 60 | 0% | 2022-09-02 | 2022-09-29 |  | TRUE | [13 empty] | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2400 | 2400 | 55% | 1320 | 3881.6796 | 3881.6796 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 |  | 10075 | [7 empty] | 3881.6796 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.1 | Main Cable Assembly | 1.4.1.1 Main Cable Assembly | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 915d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.1.2.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3881.6796 | 1.4.1.1.2.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.2.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.2.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.2.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2504.3094 | 2504.3094 | 1.4.1.1.2.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.2.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1377.3702 | 1377.3702 | 3881.6796 | 1.4.1.1.2.2.2 | 3881.6796 | 3881.6796 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3881.6796 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3881.6796
| 1.4 | 1.4.1.1.2.2.3 | C |  | MSU | Breakout prototype testing | Ferguson, Ng | 0% | Labor Hours | EN |  |  | 1 | 60 | 0% | 2022-09-30 | 2022-10-27 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | -775 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | -775 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 775 | 775 | 775 | 775 |  | 775 |  | 3875 |  | 0 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.1 | Main Cable Assembly | 1.4.1.1 Main Cable Assembly | cell-link@smartsheet.com | 2021-11-30 23:09 |  | 695d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.1.2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | 1.4.1.1.2.2.3 | C |  | MSU | Breakout prototype testing |  |  | Travel |  |  |  |  | 1 | 0% | 2022-09-30 | 2022-10-27 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | [9 empty] | 0 | Travel | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.1 | Main Cable Assembly | 1.4.1.1 Main Cable Assembly | cell-link@smartsheet.com | 2021-11-30 23:09 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.1.2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | 1.4.1.1.2.2.4 | C |  | MSU | Breakout final design review | Ferguson, Ng | 0% | Labor Hours | EN |  |  | 1 | 60 | 0% | 2022-10-28 | 2022-11-10 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 30690 | 5580 | [5 empty] | 30690 |  | 0 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.1 | Main Cable Assembly | 1.4.1.1 Main Cable Assembly | cell-link@smartsheet.com | 2021-11-30 23:09 |  | 695d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.1.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | 1.4.1.1.2.2.4 | C |  | MSU | Breakout final design review |  |  | Travel |  |  |  |  | 1 | 0% | 2022-10-28 | 2022-11-10 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | [9 empty] | 0 | Travel | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.1 | Main Cable Assembly | 1.4.1.1 Main Cable Assembly | cell-link@smartsheet.com | 2021-11-30 23:09 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.1.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | 1.4.1.1.3.2 | C |  | MSU | MCA production |  |  | Travel |  |  |  |  | 1 | 0% | 2022-12-28 | 2023-03-21 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | [9 empty] | 0 | Travel | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.1 | Main Cable Assembly | 1.4.1.1 Main Cable Assembly | cell-link@smartsheet.com | 2021-11-30 23:14 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.1.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | 1.4.1.1.3.2 | C |  | MSU | MCA production | Ferguson, Ng | 0% | Labor Hours | EN |  |  | 1 | 60 | 0% | 2022-12-28 | 2023-03-21 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 16000 | 12000 | [5 empty] | 16000 |  | 0 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.1 | Main Cable Assembly | 1.4.1.1 Main Cable Assembly | cell-link@smartsheet.com | 2021-11-30 23:14 |  | 695d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.1.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | 1.4.1.1.3.3 | C |  | MSU | Pre-ship review | Ferguson, Ng | 0% | Labor Hours | EN |  |  |  | 60 | 0% | 2023-03-22 | 2023-04-04 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 |  | 21700 | [7 empty] | 0 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.1 | Main Cable Assembly | 1.4.1.1 Main Cable Assembly | cell-link@smartsheet.com | 2021-11-30 23:14 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.1.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | 1.4.1.1.3.4 | C |  | MSU | Main Cable Assembly shipping to PTH | Ferguson | 0% | Labor Hours | EN |  |  |  | 60 | 0% | 2023-04-05 | 2023-05-09 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 |  | 9300 | [7 empty] | 0 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.1 | Main Cable Assembly | 1.4.1.1 Main Cable Assembly | cell-link@smartsheet.com | 2021-11-30 23:14 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.1.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | 1.4.1.2 | P |  | MSU | Miscellaneous supplies |  |  | M & S |  |  |  |  | 1 | 0% | 2021-11-01 | 2024-12-01 | [7 empty] | 125 |  |  | 125 |  |  | 125 |  |  | 0 | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 375 | 55% | 206.25 | 581.25 | 581.25 | 125 |  |  | 125 |  |  | 125 |  |  | 125 |  |  | 125 | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 500 | 55% | 275 | 775 | 775 | 125 |  |  | 125 |  |  | 125 | [5 empty] | 125 | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 0 | 0 | 0 | 375 | 55% | 206.25 | 581.25 | 581.25 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | [9 empty] | 1937.5 | M & S | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.2 | Breakout Cable Assemblies | 1.4.1.2 Breakout Cable Assemblies | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.2 | 0 | 0 | 0 | 193.75 | 0 | 0 | 193.75 | 0 | 0 | 193.75 | 0 | 0 | 1.4.1.2 | 193.75 | 0 | 0 | 193.75 | 0 | 0 | 193.75 | 0 | 0 | 193.75 | 0 | 0 | 1.4.1.2 | 193.75 | 0 | 0 | 193.75 | 0 | 0 | 193.75 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2 | 0 | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 375 | 1.4.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2 | 0 | 0 | 0 | 68.75 | 0 | 0 | 68.75 | 0 | 0 | 68.75 | 0 | 0 | 206.25 | 581.25 | 1.4.1.2 | 581.25 | 581.25 | 0 | 0 | 0 | 193.75 | 193.75 | 193.75 | 387.5 | 387.5 | 387.5 | 581.25 | 581.25 | 581.25 | 0 | 0 | 0 | 193.75 | 193.75 | 193.75 | 387.5 | 387.5 | 387.5 | 581.25 | 581.25 | 581.25
| 1.4 | 1.4.1.2.1.1 | C |  | MSU | BCA preliminary design | Ferguson, Ng | 17.31% | Labor Hours | EN |  |  |  | 60 | 0% | 2021-11-01 | 2022-04-29 |  | TRUE |  |  |  | 160 | 40 | 80 | 80 | [7 empty] | 0 | 9600 | 2400 | 4800 | 4800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21600 | 55% | 11880 | 34935.1161 | 34935.1161 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 |  | 5580 | [7 empty] | 34935.1161 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.2 | Breakout Cable Assemblies | 1.4.1.2 Breakout Cable Assemblies | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.2.1.1 | 0 | 15526.7183 | 3881.6796 | 7763.3591 | 7763.3591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.1.1 | 0 | 10017.2376 | 2504.3094 | 5008.6188 | 5008.6188 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22538.7846 | 1.4.1.2.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.1.1 | 0 | 5509.4807 | 1377.3702 | 2754.7403 | 2754.7403 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12396.3315 | 34935.1161 | 1.4.1.2.1.1 | 34935.1161 | 34935.1161 | 0 | 15526.7183 | 19408.3979 | 27171.757 | 34935.1161 | 34935.1161 | 34935.1161 | 34935.1161 | 34935.1161 | 34935.1161 | 34935.1161 | 34935.1161 | 0 | 15526.7183 | 19408.3979 | 27171.757 | 34935.1161 | 34935.1161 | 34935.1161 | 34935.1161 | 34935.1161 | 34935.1161 | 34935.1161 | 34935.1161
| 1.4 | 1.4.1.2.1.2 | C |  | MSU | BCA preliminary design review | Ferguson, Ng | 5.769% | Labor Hours | EN |  |  |  | 60 | 0% | 2022-03-01 | 2022-03-07 | [9 empty] | 120 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 7200 | 0 | 0 | 0 | 0 | 0 | 0 | 7200 | 55% | 3960 | 11645.0387 | 11645.0387 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 |  | 0 | 5400 | [6 empty] | 11645.0387 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.2 | Breakout Cable Assemblies | 1.4.1.2 Breakout Cable Assemblies | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.2.1.2 | 0 | 0 | 0 | 0 | 0 | 11645.0387 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.1.2 | 0 | 0 | 0 | 0 | 0 | 7512.9282 | 0 | 0 | 0 | 0 | 0 | 0 | 7512.9282 | 1.4.1.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.1.2 | 0 | 0 | 0 | 0 | 0 | 4132.1105 | 0 | 0 | 0 | 0 | 0 | 0 | 4132.1105 | 11645.0387 | 1.4.1.2.1.2 | 11645.0387 | 17225.0387 | 0 | 0 | 0 | 0 | 0 | 11645.0387 | 11645.0387 | 11645.0387 | 11645.0387 | 11645.0387 | 11645.0387 | 11645.0387 | 0 | 0 | 0 | 0 | 0 | 17225.0387 | 17225.0387 | 17225.0387 | 17225.0387 | 17225.0387 | 17225.0387 | 17225.0387
| 1.4 | 1.4.1.2.1.2 | C |  | MSU | BCA preliminary design review |  |  | Travel |  |  |  |  | 1 | 0% | 2022-03-01 | 2022-03-07 | [9 empty] | 3600 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 3600 | 0 | 0 | 0 | 0 | 0 | 0 | 3600 | 55% | 1980 | 5580 | 5580 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | [9 empty] | 5580 | Travel | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.2 | Breakout Cable Assemblies | 1.4.1.2 Breakout Cable Assemblies | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.2.1.2 | 0 | 0 | 0 | 0 | 0 | 5580 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.1.2 | 0 | 0 | 0 | 0 | 0 | 3600 | 0 | 0 | 0 | 0 | 0 | 0 | 3600 | 1.4.1.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.1.2 | 0 | 0 | 0 | 0 | 0 | 1980 | 0 | 0 | 0 | 0 | 0 | 0 | 1980 | 5580 | 1.4.1.2.1.2 | 5580 | 5580 | 0 | 0 | 0 | 0 | 0 | 5580 | 5580 | 5580 | 5580 | 5580 | 5580 | 5580 | 0 | 0 | 0 | 0 | 0 | 5580 | 5580 | 5580 | 5580 | 5580 | 5580 | 5580
| 1.4 | 1.4.1.2.1.3 | C |  | MSU | Prototype procurement | Ferguson | 3.365% | Labor Hours | EN |  |  | 50 | 60 | 0% | 2022-03-08 | 2022-04-04 | [9 empty] | 60 | 10 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 3600 | 600 | 0 | 0 | 0 | 0 | 0 | 4200 | 55% | 2310 | 6792.9392 | 6792.9392 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 4092 | 0 | [5 empty] | 4092 |  | 6792.9392 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.2 | Breakout Cable Assemblies | 1.4.1.2 Breakout Cable Assemblies | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 2d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.2.1.3 | 0 | 0 | 0 | 0 | 0 | 5822.5194 | 970.4199 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.1.3 | 0 | 0 | 0 | 0 | 0 | 3756.4641 | 626.0774 | 0 | 0 | 0 | 0 | 0 | 4382.5414 | 1.4.1.2.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.1.3 | 0 | 0 | 0 | 0 | 0 | 2066.0553 | 344.3425 | 0 | 0 | 0 | 0 | 0 | 2410.3978 | 6792.9392 | 1.4.1.2.1.3 | 6792.9392 | 6792.9392 | 0 | 0 | 0 | 0 | 0 | 5822.5194 | 6792.9392 | 6792.9392 | 6792.9392 | 6792.9392 | 6792.9392 | 6792.9392 | 0 | 0 | 0 | 0 | 0 | 5822.5194 | 6792.9392 | 6792.9392 | 6792.9392 | 6792.9392 | 6792.9392 | 6792.9392
| 1.4 | 1.4.1.2.1.4 | C |  | MSU | BCA prototype production | Ferguson, Ng | 4.327% | Labor Hours | EN |  |  | 50 | 60 | 0% | 2022-04-05 | 2022-07-25 | [10 empty] | 10 | 20 | 20 | 40 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 600 | 1200 | 1200 | 2400 | 0 | 0 | 5400 | 55% | 2970 | 8733.779 | 8733.779 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 10230 | 4743 | [5 empty] | 10230 |  | 8733.779 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.2 | Breakout Cable Assemblies | 1.4.1.2 Breakout Cable Assemblies | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 109d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.2.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 970.4199 | 1940.8398 | 1940.8398 | 3881.6796 | 0 | 0 | 1.4.1.2.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 626.0774 | 1252.1547 | 1252.1547 | 2504.3094 | 0 | 0 | 5634.6961 | 1.4.1.2.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 344.3425 | 688.6851 | 688.6851 | 1377.3702 | 0 | 0 | 3099.0829 | 8733.779 | 1.4.1.2.1.4 | 8733.779 | 28733.779 | 0 | 0 | 0 | 0 | 0 | 0 | 970.4199 | 2911.2597 | 4852.0995 | 8733.779 | 8733.779 | 8733.779 | 0 | 0 | 0 | 0 | 0 | 0 | 970.4199 | 2911.2597 | 4852.0995 | 28733.779 | 28733.779 | 28733.779
| 1.4 | 1.4.1.2.1.4 | C |  | MSU | BCA prototypes |  |  | CapEx |  |  | EE |  | 1 | 0% | 2022-04-05 | 2022-07-25 | [13 empty] | 20000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 20000 | 55% | 0 | 20000 | 20000 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | [9 empty] | 20000 | CapEx | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.2 | Breakout Cable Assemblies | 1.4.1.2 Breakout Cable Assemblies | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.2.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 1.4.1.2.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 20000 | 1.4.1.2.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 1.4.1.2.1.4 | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000 | 20000
| 1.4 | 1.4.1.2.1.5 | C |  | MSU | BCA prototype evaluation | Ferguson, Ng | 5.769% | Labor Hours | EN |  |  | 50 | 60 | 0% | 2022-07-26 | 2022-08-08 | [13 empty] | 60 | 60 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3600 | 3600 | 0 | 7200 | 55% | 3960 | 11645.0387 | 11645.0387 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 7161 | 9486 | [5 empty] | 7161 |  | 11645.0387 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.2 | Breakout Cable Assemblies | 1.4.1.2 Breakout Cable Assemblies | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 103d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.2.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5822.5194 | 5822.5194 | 0 | 1.4.1.2.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3756.4641 | 3756.4641 | 0 | 7512.9282 | 1.4.1.2.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2066.0553 | 2066.0553 | 0 | 4132.1105 | 11645.0387 | 1.4.1.2.1.5 | 11645.0387 | 17225.0387 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5822.5194 | 11645.0387 | 11645.0387 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5822.5194 | 17225.0387 | 17225.0387
| 1.4 | 1.4.1.2.1.5 | C |  | MSU | BCA prototype evaluation |  |  | Travel |  |  |  |  | 1 | 0% | 2022-07-26 | 2022-08-08 | [14 empty] | 3600 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3600 | 0 | 3600 | 55% | 1980 | 5580 | 5580 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | [9 empty] | 5580 | Travel | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.2 | Breakout Cable Assemblies | 1.4.1.2 Breakout Cable Assemblies | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.2.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5580 | 0 | 1.4.1.2.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3600 | 0 | 3600 | 1.4.1.2.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1980 | 0 | 1980 | 5580 | 1.4.1.2.1.5 | 5580 | 5580 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5580 | 5580 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5580 | 5580
| 1.4 | 1.4.1.2.2.1 | C |  | MSU | BCA final design | Ferguson, Ng | 4.808% | Labor Hours | EN |  |  | 50 | 60 | 0% | 2022-08-09 | 2022-09-05 | [14 empty] | 80 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4800 | 1200 | 6000 | 55% | 3300 | 9704.1989 | 9704.1989 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 5115 | 22134 | [5 empty] | 5115 |  | 9704.1989 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.2 | Breakout Cable Assemblies | 1.4.1.2 Breakout Cable Assemblies | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 105d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.2.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7763.3591 | 1940.8398 | 1.4.1.2.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5008.6188 | 1252.1547 | 6260.7735 | 1.4.1.2.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2754.7403 | 688.6851 | 3443.4254 | 9704.1989 | 1.4.1.2.2.1 | 9704.1989 | 9704.1989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7763.3591 | 9704.1989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7763.3591 | 9704.1989
| 1.4 | 1.4.1.2.2.2 | C |  | MSU | Final BCA prototype production | Ferguson, Ng | 1.923% | Labor Hours | EN |  |  |  | 60 | 0% | 2022-09-06 | 2022-11-28 | [15 empty] | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2400 | 2400 | 55% | 1320 | 3881.6796 | 3881.6796 | 40 | 40 | [10 empty] | 2400 | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4800 | 55% | 2640 | 7930.2714 | 7930.2714 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 |  | 11067 | [7 empty] | 11811.9509 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.2 | Breakout Cable Assemblies | 1.4.1.2 Breakout Cable Assemblies | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 12d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.2.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3881.6796 | 1.4.1.2.2.2 | 3965.1357 | 3965.1357 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2504.3094 | 2504.3094 | 1.4.1.2.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1377.3702 | 1377.3702 | 3881.6796 | 1.4.1.2.2.2 | 3881.6796 | 3881.6796 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3881.6796 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3881.6796
| 1.4 | 1.4.1.2.2.2 | C |  | MSU | Final BCA prototypes |  |  | CapEx |  |  | EE |  | 1 | 0% | 2022-09-06 | 2022-11-28 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 |  | 15000 | [10 empty] | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 55% | 0 | 15000 | 15000 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | [9 empty] | 15000 | CapEx | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.2 | Breakout Cable Assemblies | 1.4.1.2 Breakout Cable Assemblies | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.2.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.2.2 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | 1.4.1.2.2.3 | C |  | MSU | Final BCA prototype testing | Ferguson, Ng | 0% | Labor Hours | EN |  |  | 50 | 60 | 0% | 2022-11-29 | 2022-12-12 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 |  |  | 80 | [9 empty] | 0 | 0 | 4800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4800 | 55% | 2640 | 7930.2714 | 7930.2714 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 4092 | 12648 | [5 empty] | 12440 |  | 7930.2714 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.2 | Breakout Cable Assemblies | 1.4.1.2 Breakout Cable Assemblies | cell-link@smartsheet.com | 2021-11-30 23:14 |  | 12d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.2.3 | 0 | 0 | 7930.2714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | 1.4.1.2.2.3 | C |  | MSU | Final BCA prototype testing |  |  | Travel |  |  |  |  | 1 | 0% | 2022-11-29 | 2022-12-12 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 |  |  | 5400 | [9 empty] | 0 | 0 | 5400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5400 | 55% | 2970 | 8370 | 8370 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | [9 empty] | 8370 | Travel | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.2 | Breakout Cable Assemblies | 1.4.1.2 Breakout Cable Assemblies | cell-link@smartsheet.com | 2021-11-30 23:14 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.2.3 | 0 | 0 | 8370 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | 1.4.1.2.2.4 | C |  | MSU | BCA final design review | Ferguson, Ng | 0% | Labor Hours | EN |  |  | 50 | 60 | 0% | 2023-01-10 | 2023-01-16 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 |  |  |  | 160 | [8 empty] | 0 | 0 | 0 | 9600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9600 | 55% | 5280 | 15860.5427 | 15860.5427 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 4092 | 18972 | [5 empty] | 4092 |  | 15860.5427 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.2 | Breakout Cable Assemblies | 1.4.1.2 Breakout Cable Assemblies | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 18d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.2.4 | 0 | 0 | 0 | 15860.5427 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | 1.4.1.2.2.4 | C |  | MSU | BCA final design review |  |  | Travel |  |  |  |  | 1 | 0% | 2023-01-10 | 2023-01-16 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 |  |  |  | 5400 | [8 empty] | 0 | 0 | 0 | 5400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5400 | 55% | 2970 | 8370 | 8370 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | [9 empty] | 8370 | Travel | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.2 | Breakout Cable Assemblies | 1.4.1.2 Breakout Cable Assemblies | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.2.4 | 0 | 0 | 0 | 8370 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | 1.4.1.2.3.1 | C |  | MSU | BCA manufacturing - first two strings | Ferguson, Ng | 0% | Labor Hours | EN |  |  | 100 | 60 | 0% | 2023-01-31 | 2023-02-27 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | -22885.175 |  |  |  |  | 120 | [7 empty] | 0 | 0 | 0 | 0 | 7200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7200 | 55% | 3960 | 11895.407 | 11895.407 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 10416 | 21585.2256 | 22327 | 22885.175 |  | 0 |  | 54205 |  | 11895.407 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.2 | Breakout Cable Assemblies | 1.4.1.2 Breakout Cable Assemblies | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1431d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.2.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.3.1 | 0 | 0 | 0 | 0 | 11895.407 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | 1.4.1.2.3.1 | C |  | MSU | BCA manufacturing - first two strings |  |  | Travel |  |  |  |  | 1 | 0% | 2023-01-31 | 2023-02-27 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 |  |  |  |  | 3600 | [7 empty] | 0 | 0 | 0 | 0 | 3600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3600 | 55% | 1980 | 5580 | 5580 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | [9 empty] | 5580 | Travel | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.2 | Breakout Cable Assemblies | 1.4.1.2 Breakout Cable Assemblies | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.2.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.3.1 | 0 | 0 | 0 | 0 | 5580 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | 1.4.1.2.3.1 | C |  | MSU | BCA connectors - first two strings, MCA side |  |  | CapEx |  |  | HD |  | 1 | 0% | 2023-01-31 | 2023-02-27 |  |  |  | PCA side connectors already purchased | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 |  |  |  |  | 7300 | [7 empty] | 0 | 0 | 0 | 0 | 7300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7300 | 55% | 0 | 7300 | 7300 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | [9 empty] | 7300 | CapEx | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.2 | Breakout Cable Assemblies | 1.4.1.2 Breakout Cable Assemblies | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.2.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.3.1 | 0 | 0 | 0 | 0 | 7300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | 1.4.1.2.3.1 | C |  | MSU | BCA cable - first two strings |  |  | CapEx |  |  | HD |  | 1 | 0% | 2023-01-31 | 2023-02-27 |  |  |  | 525 m of cable per string, $15/m based on SB 45027 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 |  |  |  |  | 15750 | [7 empty] | 0 | 0 | 0 | 0 | 15750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15750 | 55% | 0 | 15750 | 15750 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | [9 empty] | 15750 | CapEx | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.2 | Breakout Cable Assemblies | 1.4.1.2 Breakout Cable Assemblies | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.2.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.3.1 | 0 | 0 | 0 | 0 | 15750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | 1.4.1.2.3.1 | C |  | MSU | BCA fabrication costs - first two strings |  |  | CapEx |  |  | HD |  | 1 | 0% | 2023-01-31 | 2023-02-27 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 |  |  |  |  | 20000 | [7 empty] | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 55% | 0 | 20000 | 20000 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | [9 empty] | 20000 | CapEx | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.2 | Breakout Cable Assemblies | 1.4.1.2 Breakout Cable Assemblies | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.2.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.3.1 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | 1.4.1.2.3.2 | C |  | MSU | BCA pre-ship review | Ferguson, Ng | 0% | Labor Hours | EN |  |  | 1 | 60 | 0% | 2023-02-28 | 2023-03-13 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | -775 | [5 empty] | 80 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 4800 | 0 | 0 | 0 | 0 | 0 | 0 | 4800 | 55% | 2640 | 7930.2714 | 7155.2714 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 775 | 775 | 775 | 775 |  | 775 |  | 3875 |  | 7930.2714 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.2 | Breakout Cable Assemblies | 1.4.1.2 Breakout Cable Assemblies | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1431d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.2.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.3.2 | 0 | 0 | 0 | 0 | 0 | 7930.2714 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | 1.4.1.2.3.3 | C |  | MSU | Shipping to PTH | Ferguson, Ng | 0% | Labor Hours | EN |  |  | 1 | 60 | 0% | 2023-03-14 | 2023-03-27 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | -5580 | [5 empty] | 40 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 2400 | 55% | 1320 | 3965.1357 | 1175.1357 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 5580 | 5580 | 5580 | 5580 |  | 2790 |  | 20155 |  | 3965.1357 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.2 | Breakout Cable Assemblies | 1.4.1.2 Breakout Cable Assemblies | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1431d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.2.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.3.3 | 0 | 0 | 0 | 0 | 0 | 3965.1357 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | 1.4.1.2.3.3 | C |  | MSU | Shipping costs to PTH |  |  | M & S |  |  |  |  | 1 | 0% | 2023-03-14 | 2023-03-27 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [5 empty] | 1000 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 55% | 550 | 1550 | 1550 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | [9 empty] | 1550 | M & S | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.2 | Breakout Cable Assemblies | 1.4.1.2 Breakout Cable Assemblies | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.2.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.3.3 | 0 | 0 | 0 | 0 | 0 | 1550 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | 1.4.1.2.4.1 | C |  | MSU | BCA manufacturing | Ferguson, Ng | 0% | Labor Hours | EN |  |  |  | 60 | 0% | 2023-02-28 | 2023-05-22 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [5 empty] | 40 | 40 | 40 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2400 | 2400 | 2400 | 0 | 0 | 0 | 0 | 7200 | 55% | 3960 | 11895.407 | 11895.407 | 20 | 20 | 20 | 20 | 20 | 20 | [6 empty] | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 7200 | 55% | 3960 | 12151.1583 | 12151.1583 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 |  | 10075 | [7 empty] | 24046.5653 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.2 | Breakout Cable Assemblies | 1.4.1.2 Breakout Cable Assemblies | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 915d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.2.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.4.1 | 0 | 0 | 0 | 0 | 0 | 3965.1357 | 3965.1357 | 3965.1357 | 0 | 0 | 0 | 0 | 1.4.1.2.4.1 | 2025.193 | 2025.193 | 2025.193 | 2025.193 | 2025.193 | 2025.193 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | 1.4.1.2.4.1 | C |  | MSU | BCA manufacturing |  |  | Travel |  |  |  |  | 1 | 0% | 2023-02-28 | 2023-05-22 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [6 empty] | 3600 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 3600 | 0 | 0 | 0 | 0 | 0 | 3600 | 55% | 1980 | 5580 | 5580 |  |  | 3600 | [9 empty] | 0 | 0 | 3600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3600 | 55% | 1980 | 5580 | 5580 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | [9 empty] | 11160 | Travel | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.2 | Breakout Cable Assemblies | 1.4.1.2 Breakout Cable Assemblies | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.2.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 5580 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.4.1 | 0 | 0 | 5580 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | 1.4.1.2.4.1 | C |  | MSU | BCA connectors - last five strings, MCA side |  |  | CapEx |  |  | HD |  | 1 | 0% | 2023-02-28 | 2023-05-22 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [7 empty] | 18250 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18250 | 0 | 0 | 0 | 0 | 18250 | 55% | 0 | 18250 | 18250 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | [9 empty] | 18250 | CapEx | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.2 | Breakout Cable Assemblies | 1.4.1.2 Breakout Cable Assemblies | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.2.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18250 | 0 | 0 | 0 | 0 | 1.4.1.2.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | 1.4.1.2.4.1 | C |  | MSU | BCA cable - last five strings |  |  | CapEx |  |  | HD |  | 1 | 0% | 2023-02-28 | 2023-05-22 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [7 empty] | 39375 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39375 | 0 | 0 | 0 | 0 | 39375 | 55% | 0 | 39375 | 39375 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | [9 empty] | 39375 | CapEx | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.2 | Breakout Cable Assemblies | 1.4.1.2 Breakout Cable Assemblies | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.2.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39375 | 0 | 0 | 0 | 0 | 1.4.1.2.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | 1.4.1.2.4.1 | C |  | MSU | BCA fabrication costs - last five strings |  |  | CapEx |  |  | HD |  | 1 | 0% | 2023-02-28 | 2023-05-22 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [7 empty] | 50000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 50000 | 55% | 0 | 50000 | 50000 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | [9 empty] | 50000 | CapEx | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.2 | Breakout Cable Assemblies | 1.4.1.2 Breakout Cable Assemblies | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.2.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 1.4.1.2.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | 1.4.1.2.4.2 | C |  | MSU | Shipping to PTH | Ferguson, Ng | 0% | Labor Hours | EN |  |  | 1 | 60 | 0% | 2023-05-23 | 2023-06-05 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | -775 | [7 empty] | 20 | 10 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 600 | 0 | 0 | 0 | 1800 | 55% | 990 | 2973.8518 | 2198.8518 | [5 empty] | 40 | 20 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 2400 | 1200 | 0 | 0 | 0 | 0 | 0 | 3600 | 55% | 1980 | 6075.5791 | 6075.5791 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 775 | 775 | 775 | 775 |  | 775 |  | 3875 |  | 9049.4309 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.2 | Breakout Cable Assemblies | 1.4.1.2 Breakout Cable Assemblies | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 695d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.2.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1982.5678 | 991.2839 | 0 | 0 | 0 | 1.4.1.2.4.2 | 0 | 0 | 0 | 0 | 0 | 4050.3861 | 2025.193 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | 1.4.1.2.4.2 | C |  | MSU | Shipping costs to PTH |  |  | M & S |  |  |  |  | 1 | 0% | 2023-05-23 | 2023-06-05 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [8 empty] | 2500 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 0 | 0 | 0 | 2500 | 55% | 1375 | 3875 | 3875 | [5 empty] | 1500 | 1500 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 1500 | 1500 | 0 | 0 | 0 | 0 | 0 | 3000 | 55% | 1650 | 4650 | 4650 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | [9 empty] | 8525 | M & S | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.2 | Breakout Cable Assemblies | 1.4.1.2 Breakout Cable Assemblies | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.2.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3875 | 0 | 0 | 0 | 1.4.1.2.4.2 | 0 | 0 | 0 | 0 | 0 | 2325 | 2325 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.2.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | 1.4.1.3 | P |  | MSU | Miscellaneous supplies |  |  | M & S |  |  |  |  | 1 | 0% | 2021-01-01 | 2022-06-07 |  |  |  |  | 125 |  |  | 125 |  |  | 125 | [5 empty] | 125 | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 0 | 0 | 0 | 375 | 55% | 206.25 | 581.25 | 581.25 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | [9 empty] | 581.25 | M & S | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.3 | Penetrator Cable Assembly | 1.4.1.3 Penetrator Cable Assembly | cell-link@smartsheet.com | 2021-12-01 14:13 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.3 | 193.75 | 0 | 0 | 193.75 | 0 | 0 | 193.75 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3 | 125 | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 0 | 0 | 0 | 375 | 1.4.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3 | 68.75 | 0 | 0 | 68.75 | 0 | 0 | 68.75 | 0 | 0 | 0 | 0 | 0 | 206.25 | 581.25 | 1.4.1.3 | 581.25 | 581.25 | 193.75 | 193.75 | 193.75 | 387.5 | 387.5 | 387.5 | 581.25 | 581.25 | 581.25 | 581.25 | 581.25 | 581.25 | 193.75 | 193.75 | 193.75 | 387.5 | 387.5 | 387.5 | 581.25 | 581.25 | 581.25 | 581.25 | 581.25 | 581.25
| 1.4 | 1.4.1.3.1.1 | C |  | MSU | v1 PCA fabrication | Ferguson, Ng | 0% | Labor Hours | EN |  |  | 1 | 60 | 0% | 2021-01-01 | 2021-03-01 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 30690 | 5580 | [5 empty] | 30690 |  | 0 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.3 | Penetrator Cable Assembly | 1.4.1.3 Penetrator Cable Assembly | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 695d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.3.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | 1.4.1.3.1.2 | C |  | MSU | v1 PCA shipping to DOM production facilities | Ng | 2.692% | Labor Hours | EN |  |  | 1 | 60 | 0% | 2021-01-01 | 2022-04-29 |  |  |  |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | [5 empty] | 480 | 480 | 480 | 480 | 480 | 480 | 480 | 0 | 0 | 0 | 0 | 0 | 3360 | 55% | 1848 | 5434.3514 | 5434.3514 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 8370 | 8370 | 8370 |  |  |  |  | 16907 |  | 5434.3514 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.3 | Penetrator Cable Assembly | 1.4.1.3 Penetrator Cable Assembly | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 695d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.3.1.2 | 776.3359 | 776.3359 | 776.3359 | 776.3359 | 776.3359 | 776.3359 | 776.3359 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.1.2 | 500.8619 | 500.8619 | 500.8619 | 500.8619 | 500.8619 | 500.8619 | 500.8619 | 0 | 0 | 0 | 0 | 0 | 3506.0332 | 1.4.1.3.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.1.2 | 275.474 | 275.474 | 275.474 | 275.474 | 275.474 | 275.474 | 275.474 | 0 | 0 | 0 | 0 | 0 | 1928.3182 | 5434.3514 | 1.4.1.3.1.2 | 5434.3514 | 5434.3514 | 776.3359 | 1552.6718 | 2329.0077 | 3105.3437 | 3881.6796 | 4658.0155 | 5434.3514 | 5434.3514 | 5434.3514 | 5434.3514 | 5434.3514 | 5434.3514 | 776.3359 | 1552.6718 | 2329.0077 | 3105.3437 | 3881.6796 | 4658.0155 | 5434.3514 | 5434.3514 | 5434.3514 | 5434.3514 | 5434.3514 | 5434.3514
TRUE | 1.4 | 1.4.1.3.1.3 | C |  | MSU | v1 PCA restesting | Ferguson | 1.923% | Labor Hours | EN |  |  |  | 60 | 0% | 2021-10-01 | 2022-03-31 |  |  |  |  | 40 | [11 empty] | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2400 | 55% | 1320 | 3881.6796 | 3881.6796 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | [9 empty] | 3881.6796 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.3 | Penetrator Cable Assembly | 1.4.1.3 Penetrator Cable Assembly | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.3.1.3 | 3881.6796 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.1.3 | 2504.3094 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2504.3094 | 1.4.1.3.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.1.3 | 1377.3702 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1377.3702 | 3881.6796 | 1.4.1.3.1.3 | 3881.6796 | 7138.5899 | 3881.6796 | 3881.6796 | 3881.6796 | 3881.6796 | 3881.6796 | 3881.6796 | 3881.6796 | 3881.6796 | 3881.6796 | 3881.6796 | 3881.6796 | 3881.6796 | 6583.5097 | 6583.5097 | 6583.5097 | 6583.5097 | 6861.0498 | 7138.5899 | 7138.5899 | 7138.5899 | 7138.5899 | 7138.5899 | 7138.5899 | 7138.5899
TRUE | 1.4 | 1.4.1.3.1.3 | C |  | MSU | v1 PCA restesting | Markel | 1.923% | Labor Hours | UG |  |  |  | 13 | 32% | 2021-10-01 | 2022-03-31 |  |  |  |  | 20 |  |  |  | 10 | 10 | [6 empty] | 343.2 | 0 | 0 | 0 | 171.6 | 171.6 | 0 | 0 | 0 | 0 | 0 | 0 | 686.4 | 55% | 377.52 | 1110.1604 | 1110.1604 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | [9 empty] | 1110.1604 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.3 | Penetrator Cable Assembly | 1.4.1.3 Penetrator Cable Assembly | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.3.1.3 | 555.0802 | 0 | 0 | 0 | 277.5401 | 277.5401 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.1.3 | 271.3002 | 0 | 0 | 0 | 135.6501 | 135.6501 | 0 | 0 | 0 | 0 | 0 | 0 | 542.6004 | 1.4.1.3.1.3 | 86.8161 | 0 | 0 | 0 | 43.408 | 43.408 | 0 | 0 | 0 | 0 | 0 | 0 | 173.6321 | 1.4.1.3.1.3 | 196.9639 | 0 | 0 | 0 | 98.482 | 98.482 | 0 | 0 | 0 | 0 | 0 | 0 | 393.9279 | 1110.1604 | 1.4.1.3.1.3 | 1110.1604 | 3256.9104 | 555.0802 | 555.0802 | 555.0802 | 555.0802 | 832.6203 | 1110.1604 | 1110.1604 | 1110.1604 | 1110.1604 | 1110.1604 | 1110.1604 | 1110.1604 | 2701.8302 | 2701.8302 | 2701.8302 | 2701.8302 | 2979.3703 | 3256.9104 | 3256.9104 | 3256.9104 | 3256.9104 | 3256.9104 | 3256.9104 | 3256.9104
TRUE | 1.4 | 1.4.1.3.1.3 | C |  | MSU | v1 PCA restesting |  |  | M & S |  |  | CP |  | 1 | 0% | 2021-10-01 | 2022-03-31 |  |  |  |  | 1385 | [11 empty] | 1385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1385 | 55% | 761.75 | 2146.75 | 2146.75 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | [9 empty] | 2146.75 | M & S | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.3 | Penetrator Cable Assembly | 1.4.1.3 Penetrator Cable Assembly | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.3.1.3 | 2146.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.1.3 | 1385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1385 | 1.4.1.3.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.1.3 | 761.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 761.75 | 2146.75 | 1.4.1.3.1.3 | 2146.75 | 2146.75 | 2146.75 | 2146.75 | 2146.75 | 2146.75 | 2146.75 | 2146.75 | 2146.75 | 2146.75 | 2146.75 | 2146.75 | 2146.75 | 2146.75 | 2146.75 | 2146.75 | 2146.75 | 2146.75 | 2146.75 | 2146.75 | 2146.75 | 2146.75 | 2146.75 | 2146.75 | 2146.75 | 2146.75
| 1.4 | 1.4.1.3.1.2 | C |  | MSU | Shipping costs for v1 PCAs |  |  | M & S |  |  | HD |  | 1 | 0% | 2021-01-01 | 2022-04-29 |  |  |  |  | 300 | [5 empty] | 300 | [5 empty] | 300 | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 600 | 55% | 330 | 930 | 930 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | [9 empty] | 930 | M & S | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.3 | Penetrator Cable Assembly | 1.4.1.3 Penetrator Cable Assembly | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.3.1.2 | 465 | 0 | 0 | 0 | 0 | 0 | 465 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.1.2 | 300 | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 600 | 1.4.1.3.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.1.2 | 165 | 0 | 0 | 0 | 0 | 0 | 165 | 0 | 0 | 0 | 0 | 0 | 330 | 930 | 1.4.1.3.1.2 | 930 | 930 | 465 | 465 | 465 | 465 | 465 | 465 | 930 | 930 | 930 | 930 | 930 | 930 | 465 | 465 | 465 | 465 | 465 | 465 | 930 | 930 | 930 | 930 | 930 | 930
| 1.4 | 1.4.1.3.3.1 | C |  | MSU | PCA mating cable design | Ferguson, Ng | 0% | Labor Hours | EN |  |  | 1 | 60 | 0% | 2021-01-01 | 2021-01-29 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 16000 | 12000 | [5 empty] | 16000 |  | 0 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.3 | Penetrator Cable Assembly | 1.4.1.3 Penetrator Cable Assembly | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 695d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.3.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | 1.4.1.3.3.2 | C |  | MSU | PCA mating cable prototyping | Ferguson, Ng | 0% | Labor Hours | EN |  |  |  | 60 | 0% | 2021-01-01 | 2021-02-15 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 |  | 21700 | [7 empty] | 0 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.3 | Penetrator Cable Assembly | 1.4.1.3 Penetrator Cable Assembly | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.3.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | 1.4.1.3.3.2 | C |  | MSU | Mating cable prototype materials |  |  | M & S |  |  |  |  | 1 | 0% | 2021-01-01 | 2021-02-15 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | [9 empty] | 0 | M & S | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.3 | Penetrator Cable Assembly | 1.4.1.3 Penetrator Cable Assembly | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.3.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | 1.4.1.3.3.3 | C |  | MSU | PCA mating cable materials procurement | Ng | 0% | Labor Hours | EN |  |  |  | 60 | 0% | 2021-02-16 | 2021-03-01 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 |  | 9300 | [7 empty] | 0 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.3 | Penetrator Cable Assembly | 1.4.1.3 Penetrator Cable Assembly | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.3.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | 1.4.1.3.3.4 | C |  | MSU | PCA mating cable materials shipping | Ng | 0% | Labor Hours | EN |  |  |  | 60 | 0% | 2021-03-02 | 2021-03-15 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 |  | 5580 | [7 empty] | 0 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.3 | Penetrator Cable Assembly | 1.4.1.3 Penetrator Cable Assembly | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.3.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | 1.4.1.3.2.1 | C |  | MSU | v2 PCA design revisions | Ng | 0% | Labor Hours | EN |  |  |  | 60 | 0% | 2021-01-01 | 2021-03-31 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 |  | 0 | 5400 | [6 empty] | 0 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.3 | Penetrator Cable Assembly | 1.4.1.3 Penetrator Cable Assembly | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.3.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | 1.4.1.3.2.2 | C |  | MSU | v2 PCA fabrication | Ng | 1.154% | Labor Hours | EN |  |  | 50 | 60 | 0% | 2021-04-01 | 2021-12-31 |  |  |  |  | 8 | 8 | 8 | [9 empty] | 480 | 480 | 480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | 55% | 792 | 2329.0077 | 2329.0077 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 4092 | 0 | [5 empty] | 4092 |  | 2329.0077 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.3 | Penetrator Cable Assembly | 1.4.1.3 Penetrator Cable Assembly | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 2d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.3.2.2 | 776.3359 | 776.3359 | 776.3359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.2.2 | 500.8619 | 500.8619 | 500.8619 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1502.5856 | 1.4.1.3.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.2.2 | 275.474 | 275.474 | 275.474 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 826.4221 | 2329.0077 | 1.4.1.3.2.2 | 2329.0077 | 2329.0077 | 776.3359 | 1552.6718 | 2329.0077 | 2329.0077 | 2329.0077 | 2329.0077 | 2329.0077 | 2329.0077 | 2329.0077 | 2329.0077 | 2329.0077 | 2329.0077 | 776.3359 | 1552.6718 | 2329.0077 | 2329.0077 | 2329.0077 | 2329.0077 | 2329.0077 | 2329.0077 | 2329.0077 | 2329.0077 | 2329.0077 | 2329.0077
| 1.4 | 1.4.1.3.2.3 | C |  | MSU | v2 PCA shipping to DOM production facilities | Ng | 1.538% | Labor Hours | EN |  |  | 50 | 60 | 0% | 2021-04-01 | 2022-01-31 |  |  |  |  | 8 | 8 | 8 | 8 | [8 empty] | 480 | 480 | 480 | 480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1920 | 55% | 1056 | 3105.3437 | 3105.3437 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 10230 | 4743 | [5 empty] | 10230 |  | 3105.3437 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.3 | Penetrator Cable Assembly | 1.4.1.3 Penetrator Cable Assembly | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 109d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.3.2.3 | 776.3359 | 776.3359 | 776.3359 | 776.3359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.2.3 | 500.8619 | 500.8619 | 500.8619 | 500.8619 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2003.4475 | 1.4.1.3.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.2.3 | 275.474 | 275.474 | 275.474 | 275.474 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1101.8961 | 3105.3437 | 1.4.1.3.2.3 | 3105.3437 | 3570.3437 | 776.3359 | 1552.6718 | 2329.0077 | 3105.3437 | 3105.3437 | 3105.3437 | 3105.3437 | 3105.3437 | 3105.3437 | 3105.3437 | 3105.3437 | 3105.3437 | 1241.3359 | 2017.6718 | 2794.0077 | 3570.3437 | 3570.3437 | 3570.3437 | 3570.3437 | 3570.3437 | 3570.3437 | 3570.3437 | 3570.3437 | 3570.3437
| 1.4 | 1.4.1.3.2.3 | C |  | MSU | v2 PCA shipping (prototypes and units for project-supported devices) |  |  | M & S |  |  |  |  | 1 | 0% | 2021-04-01 | 2022-01-31 |  |  |  |  | 300 | [11 empty] | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 55% | 165 | 465 | 465 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | [9 empty] | 465 | M & S | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.3 | Penetrator Cable Assembly | 1.4.1.3 Penetrator Cable Assembly | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.3.2.3 | 465 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.2.3 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 1.4.1.3.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.2.3 | 165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165 | 465 | 1.4.1.3.2.3 | 465 | 465 | 465 | 465 | 465 | 465 | 465 | 465 | 465 | 465 | 465 | 465 | 465 | 465 | 465 | 465 | 465 | 465 | 465 | 465 | 465 | 465 | 465 | 465 | 465 | 465
TRUE | 1.4 | 1.4.1.3.4.1 | C |  | MSU | SPAT cable design (do not renumber me!) | Ferguson | 2.404% | Labor Hours | EN |  |  |  | 60 | 0% | 2021-09-15 | 2022-02-01 |  |  |  |  | 10 | 10 | 10 | 20 | [8 empty] | 600 | 600 | 600 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 55% | 1650 | 4852.0995 | 4852.0995 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | [9 empty] | 4852.0995 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.3 | Penetrator Cable Assembly | 1.4.1.3 Penetrator Cable Assembly | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.3.4.1 | 970.4199 | 970.4199 | 970.4199 | 1940.8398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.4.1 | 626.0774 | 626.0774 | 626.0774 | 1252.1547 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3130.3868 | 1.4.1.3.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.4.1 | 344.3425 | 344.3425 | 344.3425 | 688.6851 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1721.7127 | 4852.0995 | 1.4.1.3.4.1 | 4852.0995 | 4852.0995 | 970.4199 | 1940.8398 | 2911.2597 | 4852.0995 | 4852.0995 | 4852.0995 | 4852.0995 | 4852.0995 | 4852.0995 | 4852.0995 | 4852.0995 | 4852.0995 | 970.4199 | 1940.8398 | 2911.2597 | 4852.0995 | 4852.0995 | 4852.0995 | 4852.0995 | 4852.0995 | 4852.0995 | 4852.0995 | 4852.0995 | 4852.0995
TRUE | 1.4 | 1.4.1.3.4.2 | C |  | MSU | SPAT cable materials procurement | Ferguson | 0.3846% | Labor Hours | EN |  |  |  | 60 | 0% | 2022-02-02 | 2022-05-10 | [8 empty] | 8 | [7 empty] | 0 | 0 | 0 | 0 | 480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 480 | 55% | 264 | 776.3359 | 776.3359 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | [9 empty] | 776.3359 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.3 | Penetrator Cable Assembly | 1.4.1.3 Penetrator Cable Assembly | cell-link@smartsheet.com | 2021-12-01 14:13 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.3.4.2 | 0 | 0 | 0 | 0 | 776.3359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.4.2 | 0 | 0 | 0 | 0 | 500.8619 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500.8619 | 1.4.1.3.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.4.2 | 0 | 0 | 0 | 0 | 275.474 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 275.474 | 776.3359 | 1.4.1.3.4.2 | 776.3359 | 2264.3359 | 0 | 0 | 0 | 0 | 776.3359 | 776.3359 | 776.3359 | 776.3359 | 776.3359 | 776.3359 | 776.3359 | 776.3359 | 0 | 0 | 0 | 0 | 776.3359 | 776.3359 | 776.3359 | 2264.3359 | 2264.3359 | 2264.3359 | 2264.3359 | 2264.3359
TRUE | 1.4 | 1.4.1.3.4.2 | C |  | MSU | SPAT cable materials |  |  | M & S |  |  | CP |  | 1 | 0% | 2022-02-02 | 2022-05-10 | [11 empty] | 960 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 960 | 0 | 0 | 0 | 0 | 960 | 55% | 528 | 1488 | 1488 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | [9 empty] | 1488 | M & S | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.3 | Penetrator Cable Assembly | 1.4.1.3 Penetrator Cable Assembly | cell-link@smartsheet.com | 2021-12-01 14:13 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.3.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1488 | 0 | 0 | 0 | 0 | 1.4.1.3.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 960 | 0 | 0 | 0 | 0 | 960 | 1.4.1.3.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 528 | 0 | 0 | 0 | 0 | 528 | 1488 | 1.4.1.3.4.2 | 1488 | 1488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1488 | 1488 | 1488 | 1488 | 1488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1488 | 1488 | 1488 | 1488 | 1488
TRUE | 1.4 | 1.4.1.3.4.3 | C |  | MSU | SPAT cable production | Ferguson | 1.442% | Labor Hours | EN |  |  |  | 60 | 0% | 2022-05-11 | 2022-05-24 | [11 empty] | 30 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 1800 | 55% | 990 | 2911.2597 | 2911.2597 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | [9 empty] | 2911.2597 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.3 | Penetrator Cable Assembly | 1.4.1.3 Penetrator Cable Assembly | cell-link@smartsheet.com | 2021-12-01 14:13 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.3.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2911.2597 | 0 | 0 | 0 | 0 | 1.4.1.3.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1878.2321 | 0 | 0 | 0 | 0 | 1878.2321 | 1.4.1.3.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1033.0276 | 0 | 0 | 0 | 0 | 1033.0276 | 2911.2597 | 1.4.1.3.4.3 | 2911.2597 | 2911.2597 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2911.2597 | 2911.2597 | 2911.2597 | 2911.2597 | 2911.2597 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2911.2597 | 2911.2597 | 2911.2597 | 2911.2597 | 2911.2597
TRUE | 1.4 | 1.4.1.3.4.4 | C |  | MSU | SPAT cable shipping | Ferguson | 0.3846% | Labor Hours | EN |  |  |  | 60 | 0% | 2022-05-25 | 2022-06-07 | [11 empty] | 8 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 480 | 0 | 0 | 0 | 0 | 480 | 55% | 264 | 776.3359 | 776.3359 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | [9 empty] | 776.3359 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.3 | Penetrator Cable Assembly | 1.4.1.3 Penetrator Cable Assembly | cell-link@smartsheet.com | 2021-12-01 14:13 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.3.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 776.3359 | 0 | 0 | 0 | 0 | 1.4.1.3.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500.8619 | 0 | 0 | 0 | 0 | 500.8619 | 1.4.1.3.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 275.474 | 0 | 0 | 0 | 0 | 275.474 | 776.3359 | 1.4.1.3.4.4 | 776.3359 | 776.3359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 776.3359 | 776.3359 | 776.3359 | 776.3359 | 776.3359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 776.3359 | 776.3359 | 776.3359 | 776.3359 | 776.3359
| 1.4 | 1.4.1.4 | P |  | MSU | Miscellaneous supplies |  |  | M & S |  |  |  |  | 1 | 0% | 2021-01-01 | 2022-11-24 |  |  |  |  | 125 |  |  | 125 |  |  | 125 |  |  | 125 |  |  | 125 | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 500 | 55% | 275 | 775 | 775 | 125 |  |  | 125 | [8 empty] | 125 | 0 | 0 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 55% | 137.5 | 387.5 | 387.5 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | [9 empty] | 1162.5 | M & S | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.4 | String Hardware | 1.4.1.4 String Hardware | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.4 | 193.75 | 0 | 0 | 193.75 | 0 | 0 | 193.75 | 0 | 0 | 193.75 | 0 | 0 | 1.4.1.4 | 193.75 | 0 | 0 | 193.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.4 | 125 | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 500 | 1.4.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.4 | 68.75 | 0 | 0 | 68.75 | 0 | 0 | 68.75 | 0 | 0 | 68.75 | 0 | 0 | 275 | 775 | 1.4.1.4 | 775 | 775 | 193.75 | 193.75 | 193.75 | 387.5 | 387.5 | 387.5 | 581.25 | 581.25 | 581.25 | 775 | 775 | 775 | 193.75 | 193.75 | 193.75 | 387.5 | 387.5 | 387.5 | 581.25 | 581.25 | 581.25 | 775 | 775 | 775
| 1.4 | 1.4.1.4.1.1 | C |  | MSU | Final design | Ng | 1.923% | Labor Hours | EN |  |  | 50 | 60 | 0% | 2021-01-01 | 2022-04-01 |  |  |  |  | 40 | [11 empty] | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2400 | 55% | 1320 | 3881.6796 | 3881.6796 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 7161 | 9486 | [5 empty] | 7161 |  | 3881.6796 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.4 | String Hardware | 1.4.1.4 String Hardware | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 103d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.4.1.1 | 3881.6796 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.4.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.4.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.4.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.4.1.1 | 2504.3094 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2504.3094 | 1.4.1.4.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.4.1.1 | 1377.3702 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1377.3702 | 3881.6796 | 1.4.1.4.1.1 | 3881.6796 | 3881.6796 | 3881.6796 | 3881.6796 | 3881.6796 | 3881.6796 | 3881.6796 | 3881.6796 | 3881.6796 | 3881.6796 | 3881.6796 | 3881.6796 | 3881.6796 | 3881.6796 | 3881.6796 | 3881.6796 | 3881.6796 | 3881.6796 | 3881.6796 | 3881.6796 | 3881.6796 | 3881.6796 | 3881.6796 | 3881.6796 | 3881.6796 | 3881.6796
| 1.4 | 1.4.1.4.1.2 | C |  | MSU | Support rope prototype procurement | Ng | 0.3846% | Labor Hours | EN |  |  | 50 | 60 | 0% | 2021-07-08 | 2021-10-29 |  |  |  |  | 8 | [11 empty] | 480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 480 | 55% | 264 | 776.3359 | 776.3359 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 5115 | 22134 | [5 empty] | 5115 |  | 776.3359 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.4 | String Hardware | 1.4.1.4 String Hardware | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 105d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.4.1.2 | 776.3359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.4.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.4.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.4.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.4.1.2 | 500.8619 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500.8619 | 1.4.1.4.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.4.1.2 | 275.474 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 275.474 | 776.3359 | 1.4.1.4.1.2 | 776.3359 | 776.3359 | 776.3359 | 776.3359 | 776.3359 | 776.3359 | 776.3359 | 776.3359 | 776.3359 | 776.3359 | 776.3359 | 776.3359 | 776.3359 | 776.3359 | 776.3359 | 776.3359 | 776.3359 | 776.3359 | 776.3359 | 776.3359 | 776.3359 | 776.3359 | 776.3359 | 776.3359 | 776.3359 | 776.3359
| 1.4 | 1.4.1.4.1.2 | C |  | MSU | Support rope prototypes |  |  | M & S |  |  | EE |  | 1 | 0% | 2021-07-08 | 2021-10-29 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | [9 empty] | 0 | M & S | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.4 | String Hardware | 1.4.1.4 String Hardware | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.4.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.4.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.4.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.4.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.4.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.4.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.4.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.4.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | 1.4.1.4.1.3 | C |  | MSU | Support rope prototype testing | Ng | 3.846% | Labor Hours | EN |  |  |  | 60 | 0% | 2021-11-01 | 2021-12-10 | [5 empty] | 40 | 40 | [9 empty] | 0 | 2400 | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4800 | 55% | 2640 | 7763.3591 | 7763.3591 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 |  | 11067 | [7 empty] | 7763.3591 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.4 | String Hardware | 1.4.1.4 String Hardware | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 12d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.4.1.3 | 0 | 3881.6796 | 3881.6796 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.4.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.4.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.4.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.4.1.3 | 0 | 2504.3094 | 2504.3094 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5008.6188 | 1.4.1.4.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.4.1.3 | 0 | 1377.3702 | 1377.3702 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2754.7403 | 7763.3591 | 1.4.1.4.1.3 | 7763.3591 | 7763.3591 | 0 | 3881.6796 | 7763.3591 | 7763.3591 | 7763.3591 | 7763.3591 | 7763.3591 | 7763.3591 | 7763.3591 | 7763.3591 | 7763.3591 | 7763.3591 | 0 | 3881.6796 | 7763.3591 | 7763.3591 | 7763.3591 | 7763.3591 | 7763.3591 | 7763.3591 | 7763.3591 | 7763.3591 | 7763.3591 | 7763.3591
TRUE | 1.4 | 1.4.1.4.1.4 | C |  | MSU | Cable knot testing | Ng | 3.846% | Labor Hours | EN |  |  |  | 60 | 0% | 2021-09-01 | 2021-11-23 |  |  |  |  | 40 | 40 | [10 empty] | 2400 | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4800 | 55% | 2640 | 7763.3591 | 7763.3591 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | [9 empty] | 7763.3591 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.4 | String Hardware | 1.4.1.4 String Hardware | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.4.1.4 | 3881.6796 | 3881.6796 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.4.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.4.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.4.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.4.1.4 | 2504.3094 | 2504.3094 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5008.6188 | 1.4.1.4.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.4.1.4 | 1377.3702 | 1377.3702 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2754.7403 | 7763.3591 | 1.4.1.4.1.4 | 7763.3591 | 7763.3591 | 3881.6796 | 7763.3591 | 7763.3591 | 7763.3591 | 7763.3591 | 7763.3591 | 7763.3591 | 7763.3591 | 7763.3591 | 7763.3591 | 7763.3591 | 7763.3591 | 3881.6796 | 7763.3591 | 7763.3591 | 7763.3591 | 7763.3591 | 7763.3591 | 7763.3591 | 7763.3591 | 7763.3591 | 7763.3591 | 7763.3591 | 7763.3591
| 1.4 | 1.4.1.4.1.5 | C |  | MSU | String hardware final design review | Ng | 3.846% | Labor Hours | EN |  |  | 50 | 60 | 0% | 2022-03-07 | 2022-04-01 | [9 empty] | 80 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 4800 | 0 | 0 | 0 | 0 | 0 | 0 | 4800 | 55% | 2640 | 7763.3591 | 7763.3591 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 4092 | 12648 | [5 empty] | 12440 |  | 7763.3591 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.4 | String Hardware | 1.4.1.4 String Hardware | cell-link@smartsheet.com | 2021-12-01 14:13 |  | 12d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.4.1.5 | 0 | 0 | 0 | 0 | 0 | 7763.3591 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.4.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.4.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.4.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.4.1.5 | 0 | 0 | 0 | 0 | 0 | 5008.6188 | 0 | 0 | 0 | 0 | 0 | 0 | 5008.6188 | 1.4.1.4.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.4.1.5 | 0 | 0 | 0 | 0 | 0 | 2754.7403 | 0 | 0 | 0 | 0 | 0 | 0 | 2754.7403 | 7763.3591 | 1.4.1.4.1.5 | 7763.3591 | 10553.3591 | 0 | 0 | 0 | 0 | 0 | 7763.3591 | 7763.3591 | 7763.3591 | 7763.3591 | 7763.3591 | 7763.3591 | 7763.3591 | 0 | 0 | 0 | 0 | 0 | 10553.3591 | 10553.3591 | 10553.3591 | 10553.3591 | 10553.3591 | 10553.3591 | 10553.3591
| 1.4 | 1.4.1.4.1.5 | C |  | MSU | String hardware final design review |  |  | Travel |  |  |  |  | 1 | 0% | 2022-03-07 | 2022-04-01 | [9 empty] | 1800 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 55% | 990 | 2790 | 2790 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | [9 empty] | 2790 | Travel | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.4 | String Hardware | 1.4.1.4 String Hardware | cell-link@smartsheet.com | 2021-12-01 14:13 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.4.1.5 | 0 | 0 | 0 | 0 | 0 | 2790 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.4.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.4.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.4.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.4.1.5 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 1.4.1.4.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.4.1.5 | 0 | 0 | 0 | 0 | 0 | 990 | 0 | 0 | 0 | 0 | 0 | 0 | 990 | 2790 | 1.4.1.4.1.5 | 2790 | 2790 | 0 | 0 | 0 | 0 | 0 | 2790 | 2790 | 2790 | 2790 | 2790 | 2790 | 2790 | 0 | 0 | 0 | 0 | 0 | 2790 | 2790 | 2790 | 2790 | 2790 | 2790 | 2790
| 1.4 | 1.4.1.4.1.6 | C |  | MSU | String hardware procurement | Ng | 3.846% | Labor Hours | EN |  |  | 100 | 60 | 0% | 2022-07-01 | 2022-07-14 | [13 empty] | 80 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4800 | 0 | 0 | 4800 | 55% | 2640 | 7763.3591 | -15121.8159 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 10416 | 21585.2256 | 22327 | 22885.175 |  | 0 |  | 54205 |  | 7763.3591 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.4 | String Hardware | 1.4.1.4 String Hardware | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1431d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.4.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7763.3591 | 0 | 0 | 1.4.1.4.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.4.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.4.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.4.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5008.6188 | 0 | 0 | 5008.6188 | 1.4.1.4.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.4.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2754.7403 | 0 | 0 | 2754.7403 | 7763.3591 | 1.4.1.4.1.6 | 7763.3591 | 165763.3591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7763.3591 | 7763.3591 | 7763.3591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165763.3591 | 165763.3591 | 165763.3591
| 1.4 | 1.4.1.4.1.6 | C |  | MSU | Cable grips |  |  | CapEx |  |  | CP |  | 1 | 0% | 2022-07-01 | 2022-07-14 | [13 empty] | 126000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 126000 | 0 | 0 | 126000 | 55% | 0 | 126000 | 126000 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | [9 empty] | 126000 | CapEx | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.4 | String Hardware | 1.4.1.4 String Hardware | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.4.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 126000 | 0 | 0 | 1.4.1.4.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.4.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.4.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.4.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 126000 | 0 | 0 | 126000 | 1.4.1.4.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.4.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 126000 | 1.4.1.4.1.6 | 126000 | 158000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 126000 | 126000 | 126000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158000 | 158000 | 158000
| 1.4 | 1.4.1.4.1.6 | C |  | MSU | Extension ropes for long strings |  |  | CapEx |  |  | CP |  | 1 | 0% | 2022-07-01 | 2022-07-14 | [13 empty] | 32000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32000 | 0 | 0 | 32000 | 55% | 0 | 32000 | 32000 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | [9 empty] | 32000 | CapEx | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.4 | String Hardware | 1.4.1.4 String Hardware | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.4.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32000 | 0 | 0 | 1.4.1.4.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.4.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.4.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.4.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32000 | 0 | 0 | 32000 | 1.4.1.4.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.4.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32000 | 1.4.1.4.1.6 | 32000 | 32000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32000 | 32000 | 32000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32000 | 32000 | 32000
| 1.4 | 1.4.1.4.1.7 | C |  | MSU | String hardware shipping to MCA production facility | Ng | 2.308% | Labor Hours | EN |  |  | 1 | 60 | 0% | 2022-08-12 | 2022-11-03 | [14 empty] | 40 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2400 | 480 | 2880 | 55% | 1584 | 4658.0155 | 3883.0155 | 8 | 8 | [10 empty] | 480 | 480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 960 | 55% | 528 | 1586.0543 | 811.0543 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 775 | 775 | 775 | 775 |  | 775 |  | 3875 |  | 6244.0698 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.4 | String Hardware | 1.4.1.4 String Hardware | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1431d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.4.1.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3881.6796 | 776.3359 | 1.4.1.4.1.7 | 793.0271 | 793.0271 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.4.1.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.4.1.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.4.1.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2504.3094 | 500.8619 | 3005.1713 | 1.4.1.4.1.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.4.1.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1377.3702 | 275.474 | 1652.8442 | 4658.0155 | 1.4.1.4.1.7 | 4658.0155 | 4658.0155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3881.6796 | 4658.0155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3881.6796 | 4658.0155
| 1.4 | 1.4.1.5 | P |  | MSU | Miscellaneous supplies |  |  | M & S |  |  |  |  | 1 | 0% | 2021-01-01 | 2023-04-24 | [10 empty] | 125 |  |  | 125 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 250 | 55% | 137.5 | 387.5 | 387.5 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | [9 empty] | 387.5 | M & S | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.5 | Cable emulators | 1.4.1.5 Cable emulators | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 193.75 | 0 | 0 | 193.75 | 0 | 0 | 1.4.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 250 | 1.4.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 68.75 | 0 | 0 | 68.75 | 0 | 0 | 137.5 | 387.5 | 1.4.1.5 | 387.5 | 387.5 | 0 | 0 | 0 | 0 | 0 | 0 | 193.75 | 193.75 | 193.75 | 387.5 | 387.5 | 387.5 | 0 | 0 | 0 | 0 | 0 | 0 | 193.75 | 193.75 | 193.75 | 387.5 | 387.5 | 387.5
| 1.4 | 1.4.1.5.1 | C |  | MSU | Determine cable emulator requirements | Ferguson | 0% | Labor Hours | EN |  |  | 1 | 60 | 0% | 2021-01-01 | 2021-01-29 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | -5580 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | -2790 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 5580 | 5580 | 5580 | 5580 |  | 2790 |  | 20155 |  | 0 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.5 | Cable emulators | 1.4.1.5 Cable emulators | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1431d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | 1.4.1.5.2 | C |  | MSU | Cable emulator box design | Ferguson | 7.692% | Labor Hours | EN |  |  |  | 60 | 0% | 2022-04-05 | 2022-05-02 |  | TRUE | [8 empty] | 160 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 9600 | 0 | 0 | 0 | 0 | 0 | 9600 | 55% | 5280 | 15526.7183 | 15526.7183 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 |  | 10075 | [7 empty] | 15526.7183 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.5 | Cable emulators | 1.4.1.5 Cable emulators | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 915d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 15526.7183 | 0 | 0 | 0 | 0 | 0 | 1.4.1.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 10017.2376 | 0 | 0 | 0 | 0 | 0 | 10017.2376 | 1.4.1.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 5509.4807 | 0 | 0 | 0 | 0 | 0 | 5509.4807 | 15526.7183 | 1.4.1.5.2 | 15526.7183 | 15526.7183 | 0 | 0 | 0 | 0 | 0 | 0 | 15526.7183 | 15526.7183 | 15526.7183 | 15526.7183 | 15526.7183 | 15526.7183 | 0 | 0 | 0 | 0 | 0 | 0 | 15526.7183 | 15526.7183 | 15526.7183 | 15526.7183 | 15526.7183 | 15526.7183
| 1.4 | 1.4.1.5.3 | C |  | MSU | Cable emulator PCB layout | Ferguson | 11.54% | Labor Hours | EN |  |  | 1 | 60 | 0% | 2022-05-03 | 2022-06-20 | [11 empty] | 160 | 80 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9600 | 4800 | 0 | 0 | 0 | 14400 | 55% | 7920 | 23290.0774 | 22515.0774 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | -775 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 775 | 775 | 775 | 775 |  | 775 |  | 3875 |  | 23290.0774 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.5 | Cable emulators | 1.4.1.5 Cable emulators | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 695d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15526.7183 | 7763.3591 | 0 | 0 | 0 | 1.4.1.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10017.2376 | 5008.6188 | 0 | 0 | 0 | 15025.8564 | 1.4.1.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5509.4807 | 2754.7403 | 0 | 0 | 0 | 8264.221 | 23290.0774 | 1.4.1.5.3 | 23290.0774 | 23290.0774 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15526.7183 | 23290.0774 | 23290.0774 | 23290.0774 | 23290.0774 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15526.7183 | 23290.0774 | 23290.0774 | 23290.0774 | 23290.0774
| 1.4 | 1.4.1.5.4 | C |  | MSU | Cable emulator PCB procurement | Ferguson | 4.327% | Labor Hours | EN |  |  | 1 | 60 | 0% | 2022-06-21 | 2022-07-04 |  | TRUE | [10 empty] | 80 | 10 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4800 | 600 | 0 | 0 | 5400 | 55% | 2970 | 8733.779 | 8733.779 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 30690 | 5580 | [5 empty] | 30690 |  | 8733.779 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.5 | Cable emulators | 1.4.1.5 Cable emulators | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 695d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7763.3591 | 970.4199 | 0 | 0 | 1.4.1.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5008.6188 | 626.0774 | 0 | 0 | 5634.6961 | 1.4.1.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2754.7403 | 344.3425 | 0 | 0 | 3099.0829 | 8733.779 | 1.4.1.5.4 | 8733.779 | 9663.779 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7763.3591 | 8733.779 | 8733.779 | 8733.779 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7763.3591 | 9663.779 | 9663.779 | 9663.779
| 1.4 | 1.4.1.5.4 | C |  | MSU | Cable emulator PCBs |  |  | M & S |  |  | EE |  | 1 | 0% | 2022-06-21 | 2022-07-04 |  |  |  | assuming 20 boxes | [9 empty] | 600 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600 | 0 | 0 | 600 | 55% | 330 | 930 | 930 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | [9 empty] | 930 | M & S | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.5 | Cable emulators | 1.4.1.5 Cable emulators | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 930 | 0 | 0 | 1.4.1.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600 | 0 | 0 | 600 | 1.4.1.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 330 | 0 | 0 | 330 | 930 | 1.4.1.5.4 | 930 | 930 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 930 | 930 | 930 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 930 | 930 | 930
| 1.4 | 1.4.1.5.5 | C |  | MSU | Procurement of prototype materials | Ferguson | 2.692% | Labor Hours | EN |  |  | 1 | 60 | 0% | 2022-07-05 | 2022-10-24 | [13 empty] | 40 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2400 | 480 | 480 | 3360 | 55% | 1848 | 5434.3514 | 5434.3514 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 8370 | 8370 | 8370 |  |  |  |  | 16907 |  | 5434.3514 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.5 | Cable emulators | 1.4.1.5 Cable emulators | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 695d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3881.6796 | 776.3359 | 776.3359 | 1.4.1.5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2504.3094 | 500.8619 | 500.8619 | 3506.0332 | 1.4.1.5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1377.3702 | 275.474 | 275.474 | 1928.3182 | 5434.3514 | 1.4.1.5.5 | 5434.3514 | 5589.3514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3881.6796 | 4658.0155 | 5434.3514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3881.6796 | 4658.0155 | 5589.3514
| 1.4 | 1.4.1.5.5 | C |  | MSU | Cable emulator prototype materials |  |  | M & S |  |  | EE |  | 1 | 0% | 2022-07-05 | 2022-10-24 | [15 empty] | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 55% | 55 | 155 | 155 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | [9 empty] | 155 | M & S | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.5 | Cable emulators | 1.4.1.5 Cable emulators | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 155 | 1.4.1.5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 1.4.1.5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 55 | 155 | 1.4.1.5.5 | 155 | 155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 155
| 1.4 | 1.4.1.5.6 | C |  | MSU | Prototype assembly | Ferguson | 0% | Labor Hours | EN |  |  | 1 | 60 | 0% | 2022-10-25 | 2022-10-31 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 16000 | 12000 | [5 empty] | 16000 |  | 0 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.5 | Cable emulators | 1.4.1.5 Cable emulators | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 695d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.5.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.5.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.5.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.5.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.5.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.5.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.5.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.5.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | 1.4.1.5.7 | C |  | MSU | Cable emulator testing | Ferguson | 0% | Labor Hours | EN |  |  |  | 60 | 0% | 2022-11-01 | 2022-11-07 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 |  | 21700 | [7 empty] | 0 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.5 | Cable emulators | 1.4.1.5 Cable emulators | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.5.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.5.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.5.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.5.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.5.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.5.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.5.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.5.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | 1.4.1.5.8 | C |  | MSU | Cable emulator final design review | Ferguson | 0% | Labor Hours | EN |  |  |  | 60 | 0% | 2022-11-08 | 2022-11-21 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 |  | 9300 | [7 empty] | 0 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.5 | Cable emulators | 1.4.1.5 Cable emulators | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.5.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.5.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.5.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.5.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.5.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.5.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.5.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.5.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | 1.4.1.5.9 | C |  | MSU | Procurement of materials for cable emulator production | Ferguson | 0% | Labor Hours | EN |  |  |  | 60 | 0% | 2022-11-22 | 2023-03-13 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 |  | 5580 | [7 empty] | 0 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.5 | Cable emulators | 1.4.1.5 Cable emulators | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.5.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.5.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.5.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.5.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.5.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.5.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.5.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.5.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | 1.4.1.5.9 | C |  | MSU | Cable emulator materials |  |  | M & S |  |  | EE |  | 1 | 0% | 2022-11-22 | 2023-03-13 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | [9 empty] | 0 | M & S | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.5 | Cable emulators | 1.4.1.5 Cable emulators | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.5.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.5.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.5.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.5.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.5.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.5.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.5.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.5.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | 1.4.1.5.10 | C |  | MSU | Cable emulator assembly | Ferguson | 0% | Labor Hours | EN |  |  |  | 60 | 0% | 2023-03-14 | 2023-04-10 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 |  | 0 | 5400 | [6 empty] | 0 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.5 | Cable emulators | 1.4.1.5 Cable emulators | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.5.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.5.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.5.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.5.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.5.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.5.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.5.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.5.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | 1.4.1.5.11 | C |  | MSU | Cable emulator shipping | Ferguson | 0% | Labor Hours | EN |  |  | 50 | 60 | 0% | 2023-04-11 | 2023-04-24 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 4092 | 0 | [5 empty] | 4092 |  | 0 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.5 | Cable emulators | 1.4.1.5 Cable emulators | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 2d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.5.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.5.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.5.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.5.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.5.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.5.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.5.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.5.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | 1.4.1.5.11 | C |  | MSU | Cable emulator shipping costs |  |  | M & S |  |  |  |  | 1 | 0% | 2023-04-11 | 2023-04-24 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | [9 empty] | 0 | M & S | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.1 | Downhole Cables | 1.4.1 Downhole Cables | 1.4.1.5 | Cable emulators | 1.4.1.5 Cable emulators | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.1.5.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.5.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.5.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.5.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.5.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.5.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.5.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1.5.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | 1.4.2.1 | P |  | MSU | Miscellaneous supplies |  |  | M & S |  |  |  |  | 1 | 0% | 2020-12-01 | 2023-12-01 | [6 empty] | 125 |  |  | 125 |  |  | 125 |  |  | 125 | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 125 | 500 | 55% | 275 | 775 | 775 |  |  | 125 | [9 empty] | 0 | 0 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125 | 55% | 68.75 | 193.75 | 193.75 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | [9 empty] | 968.75 | M & S | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.2 | Surface Cables | 1.4.2 Surface Cables | 1.4.2.1 | Surface Cable Assemblies | 1.4.2.1 Surface Cable Assemblies | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.2.1 | 0 | 0 | 193.75 | 0 | 0 | 193.75 | 0 | 0 | 193.75 | 0 | 0 | 193.75 | 1.4.2.1 | 0 | 0 | 193.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1 | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 125 | 500 | 1.4.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1 | 0 | 0 | 68.75 | 0 | 0 | 68.75 | 0 | 0 | 68.75 | 0 | 0 | 68.75 | 275 | 775 | 1.4.2.1 | 775 | 775 | 0 | 0 | 193.75 | 193.75 | 193.75 | 387.5 | 387.5 | 387.5 | 581.25 | 581.25 | 581.25 | 775 | 0 | 0 | 193.75 | 193.75 | 193.75 | 387.5 | 387.5 | 387.5 | 581.25 | 581.25 | 581.25 | 775
| 1.4 | 1.4.2.1.1 | C |  | MSU | Final design | Ferguson, Ng | 0% | Labor Hours | EN |  |  | 100 | 60 | 0% | 2020-12-01 | 2021-01-29 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | -22885.175 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 10416 | 21585.2256 | 22327 | 22885.175 |  | 0 |  | 54205 |  | 0 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.2 | Surface Cables | 1.4.2 Surface Cables | 1.4.2.1 | Surface Cable Assemblies | 1.4.2.1 Surface Cable Assemblies | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1431d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.2.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | 1.4.2.1.1 | C |  | UW | Final design | Kelley | 0% | Labor Hours | SC |  |  |  | 52 | 35% | 2020-12-01 | 2021-01-29 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 0 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.2 | Surface Cables | 1.4.2 Surface Cables | 1.4.2.1 | Surface Cable Assemblies | 1.4.2.1 Surface Cable Assemblies | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.2.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | 1.4.2.1.2 | C |  | MSU | Final design review | Ferguson, Ng | 0% | Labor Hours | EN |  |  | 1 | 60 | 0% | 2021-02-01 | 2021-02-02 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | -775 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | -775 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 775 | 775 | 775 | 775 |  | 775 |  | 3875 |  | 0 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.2 | Surface Cables | 1.4.2 Surface Cables | 1.4.2.1 | Surface Cable Assemblies | 1.4.2.1 Surface Cable Assemblies | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1431d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | 1.4.2.1.2 | C |  | UW | Final design review | Kelley | 0% | Labor Hours | SC |  |  |  | 52 | 35% | 2021-02-01 | 2021-02-02 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 0 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.2 | Surface Cables | 1.4.2 Surface Cables | 1.4.2.1 | Surface Cable Assemblies | 1.4.2.1 Surface Cable Assemblies | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | 1.4.2.1.3 | C |  | MSU | Procurement | Ferguson | 0% | Labor Hours | EN |  |  | 1 | 60 | 0% | 2021-02-03 | 2021-03-30 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | -5580 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | -2790 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 5580 | 5580 | 5580 | 5580 |  | 2790 |  | 20155 |  | 0 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.2 | Surface Cables | 1.4.2 Surface Cables | 1.4.2.1 | Surface Cable Assemblies | 1.4.2.1 Surface Cable Assemblies | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1431d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.2.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | 1.4.2.1.4 | C |  | MSU | Cable production | Ferguson | 0% | Labor Hours | EN |  |  |  | 60 | 0% | 2021-03-31 | 2021-06-22 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 |  | 10075 | [7 empty] | 0 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.2 | Surface Cables | 1.4.2 Surface Cables | 1.4.2.1 | Surface Cable Assemblies | 1.4.2.1 Surface Cable Assemblies | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 915d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.2.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | 1.4.2.1.4 | C |  | MSU | Surface cables |  |  | CapEx |  |  | HD |  | 1 | 0% | 2021-03-31 | 2021-06-22 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | [9 empty] | 0 | CapEx | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.2 | Surface Cables | 1.4.2 Surface Cables | 1.4.2.1 | Surface Cable Assemblies | 1.4.2.1 Surface Cable Assemblies | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.2.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | 1.4.2.1.5 | C |  | MSU | Shipping to connectorization facility | Ferguson | 0% | Labor Hours | EN |  |  | 1 | 60 | 0% | 2021-06-23 | 2021-08-31 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | -775 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | -775 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 775 | 775 | 775 | 775 |  | 775 |  | 3875 |  | 0 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.2 | Surface Cables | 1.4.2 Surface Cables | 1.4.2.1 | Surface Cable Assemblies | 1.4.2.1 Surface Cable Assemblies | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 695d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.2.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | 1.4.2.1.5 | C |  | MSU | Shipping costs |  |  | CapEx |  |  | EE |  | 1 | 0% | 2021-06-23 | 2021-08-31 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | [9 empty] | 0 | CapEx | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.2 | Surface Cables | 1.4.2 Surface Cables | 1.4.2.1 | Surface Cable Assemblies | 1.4.2.1 Surface Cable Assemblies | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.2.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | 1.4.2.1.6 | C |  | MSU | Connectorization | Shooltz | 7.692% | Labor Hours | TE |  |  | 1 | 71 | 0% | 2021-09-01 | 2021-10-15 |  | TRUE |  |  | 160 | [11 empty] | 11360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11360 | 55% | 6248 | 18373.2833 | 18373.2833 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 30690 | 5580 | [5 empty] | 30690 |  | 18373.2833 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.2 | Surface Cables | 1.4.2 Surface Cables | 1.4.2.1 | Surface Cable Assemblies | 1.4.2.1 Surface Cable Assemblies | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 695d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.2.1.6 | 18373.2833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.6 | 11853.7312 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11853.7312 | 1.4.2.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.6 | 6519.5521 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6519.5521 | 18373.2833 | 1.4.2.1.6 | 18373.2833 | 55979.3833 | 18373.2833 | 18373.2833 | 18373.2833 | 18373.2833 | 18373.2833 | 18373.2833 | 18373.2833 | 18373.2833 | 18373.2833 | 18373.2833 | 18373.2833 | 18373.2833 | 55979.3833 | 55979.3833 | 55979.3833 | 55979.3833 | 55979.3833 | 55979.3833 | 55979.3833 | 55979.3833 | 55979.3833 | 55979.3833 | 55979.3833 | 55979.3833
TRUE | 1.4 | 1.4.2.1.6 | C |  | MSU | Surface cable assembly connectors |  |  | M & S |  |  | CP |  | 1 | 0% | 2021-09-01 | 2021-10-15 |  |  |  |  | 19623 | [11 empty] | 19623 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19623 | 55% | 10792.65 | 30415.65 | 30415.65 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | [9 empty] | 30415.65 | M & S | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.2 | Surface Cables | 1.4.2 Surface Cables | 1.4.2.1 | Surface Cable Assemblies | 1.4.2.1 Surface Cable Assemblies | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.2.1.6 | 30415.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.6 | 19623 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19623 | 1.4.2.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.6 | 10792.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10792.65 | 30415.65 | 1.4.2.1.6 | 30415.65 | 37606.1 | 30415.65 | 30415.65 | 30415.65 | 30415.65 | 30415.65 | 30415.65 | 30415.65 | 30415.65 | 30415.65 | 30415.65 | 30415.65 | 30415.65 | 37606.1 | 37606.1 | 37606.1 | 37606.1 | 37606.1 | 37606.1 | 37606.1 | 37606.1 | 37606.1 | 37606.1 | 37606.1 | 37606.1
TRUE | 1.4 | 1.4.2.1.6 | C |  | MSU | Surface cable assembly test equipment |  |  | M & S |  |  | CP |  | 1 | 0% | 2021-09-01 | 2021-10-15 |  |  |  |  | 1679 | [11 empty] | 1679 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1679 | 55% | 923.45 | 2602.45 | 2602.45 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | [9 empty] | 2602.45 | M & S | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.2 | Surface Cables | 1.4.2 Surface Cables | 1.4.2.1 | Surface Cable Assemblies | 1.4.2.1 Surface Cable Assemblies | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.2.1.6 | 2602.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.6 | 1679 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1679 | 1.4.2.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.6 | 923.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 923.45 | 2602.45 | 1.4.2.1.6 | 2602.45 | 7190.45 | 2602.45 | 2602.45 | 2602.45 | 2602.45 | 2602.45 | 2602.45 | 2602.45 | 2602.45 | 2602.45 | 2602.45 | 2602.45 | 2602.45 | 7190.45 | 7190.45 | 7190.45 | 7190.45 | 7190.45 | 7190.45 | 7190.45 | 7190.45 | 7190.45 | 7190.45 | 7190.45 | 7190.45
TRUE | 1.4 | 1.4.2.1.6 | C |  | MSU | Surface cable assembly zipper tubes |  |  | M & S |  |  | CP |  | 1 | 0% | 2021-09-01 | 2021-10-15 |  |  |  |  | 2960 | [11 empty] | 2960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2960 | 55% | 1628 | 4588 | 4588 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | [9 empty] | 4588 | M & S | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.2 | Surface Cables | 1.4.2 Surface Cables | 1.4.2.1 | Surface Cable Assemblies | 1.4.2.1 Surface Cable Assemblies | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.2.1.6 | 4588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.6 | 2960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2960 | 1.4.2.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.6 | 1628 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1628 | 4588 | 1.4.2.1.6 | 4588 | 4588 | 4588 | 4588 | 4588 | 4588 | 4588 | 4588 | 4588 | 4588 | 4588 | 4588 | 4588 | 4588 | 4588 | 4588 | 4588 | 4588 | 4588 | 4588 | 4588 | 4588 | 4588 | 4588 | 4588 | 4588
| 1.4 | 1.4.2.1.7 | C |  | MSU | Pre-ship review | Ferguson, Ng | 0.9615% | Labor Hours | EN |  |  | 1 | 60 | 0% | 2021-10-18 | 2021-11-03 |  |  |  |  | 20 | [11 empty] | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 55% | 660 | 1940.8398 | 1940.8398 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 8370 | 8370 | 8370 |  |  |  |  | 16907 |  | 1940.8398 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.2 | Surface Cables | 1.4.2 Surface Cables | 1.4.2.1 | Surface Cable Assemblies | 1.4.2.1 Surface Cable Assemblies | cell-link@smartsheet.com | 2021-12-01 14:15 |  | 695d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.2.1.7 | 1940.8398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.7 | 1252.1547 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1252.1547 | 1.4.2.1.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.7 | 688.6851 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 688.6851 | 1940.8398 | 1.4.2.1.7 | 1940.8398 | 3061.5808 | 1940.8398 | 1940.8398 | 1940.8398 | 1940.8398 | 1940.8398 | 1940.8398 | 1940.8398 | 1940.8398 | 1940.8398 | 1940.8398 | 1940.8398 | 1940.8398 | 3061.5808 | 3061.5808 | 3061.5808 | 3061.5808 | 3061.5808 | 3061.5808 | 3061.5808 | 3061.5808 | 3061.5808 | 3061.5808 | 3061.5808 | 3061.5808
| 1.4 | 1.4.2.1.7 | C |  | UW | Pre-ship review | Kelley | 0.4808% | Labor Hours | SC |  |  |  | 52 | 35% | 2021-10-18 | 2021-11-03 |  |  |  |  | 10 | [11 empty] | 702 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 702 | 53% | 372.06 | 1120.7411 | 1120.7411 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 1120.7411 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.2 | Surface Cables | 1.4.2 Surface Cables | 1.4.2.1 | Surface Cable Assemblies | 1.4.2.1 Surface Cable Assemblies | cell-link@smartsheet.com | 2021-12-01 14:15 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.2.1.7 | 1120.7411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.7 | 542.6004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 542.6004 | 1.4.2.1.7 | 189.9101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 189.9101 | 1.4.2.1.7 | 388.2306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 388.2306 | 1120.7411 | 1.4.2.1.7 | 1120.7411 | 1120.7411 | 1120.7411 | 1120.7411 | 1120.7411 | 1120.7411 | 1120.7411 | 1120.7411 | 1120.7411 | 1120.7411 | 1120.7411 | 1120.7411 | 1120.7411 | 1120.7411 | 1120.7411 | 1120.7411 | 1120.7411 | 1120.7411 | 1120.7411 | 1120.7411 | 1120.7411 | 1120.7411 | 1120.7411 | 1120.7411 | 1120.7411 | 1120.7411
| 1.4 | 1.4.2.1.8 | C |  | MSU | Shipping to PTH | Ng | 0.4808% | Labor Hours | EN |  |  | 1 | 60 | 0% | 2021-11-04 | 2021-12-01 |  | TRUE |  |  |  | 10 | [10 empty] | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600 | 55% | 330 | 970.4199 | 970.4199 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 16000 | 12000 | [5 empty] | 16000 |  | 970.4199 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.2 | Surface Cables | 1.4.2 Surface Cables | 1.4.2.1 | Surface Cable Assemblies | 1.4.2.1 Surface Cable Assemblies | cell-link@smartsheet.com | 2021-12-01 14:15 |  | 695d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.2.1.8 | 0 | 970.4199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.8 | 0 | 626.0774 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 626.0774 | 1.4.2.1.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.8 | 0 | 344.3425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 344.3425 | 970.4199 | 1.4.2.1.8 | 970.4199 | 5970.4199 | 0 | 970.4199 | 970.4199 | 970.4199 | 970.4199 | 970.4199 | 970.4199 | 970.4199 | 970.4199 | 970.4199 | 970.4199 | 970.4199 | 0 | 5970.4199 | 5970.4199 | 5970.4199 | 5970.4199 | 5970.4199 | 5970.4199 | 5970.4199 | 5970.4199 | 5970.4199 | 5970.4199 | 5970.4199
| 1.4 | 1.4.2.1.8 | C |  | UW | Shipping to PTH | Kelley | 0% | Labor Hours | SC |  |  |  | 52 | 35% | 2021-11-04 | 2021-12-01 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 0 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.2 | Surface Cables | 1.4.2 Surface Cables | 1.4.2.1 | Surface Cable Assemblies | 1.4.2.1 Surface Cable Assemblies | cell-link@smartsheet.com | 2021-12-01 14:15 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.2.1.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.8 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000
| 1.4 | 1.4.2.1.8 | C |  | UW | Shipping costs |  |  | CapEx |  |  | HD |  | 1 | 0% | 2021-11-04 | 2021-12-01 | [5 empty] | 5000 | [10 empty] | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 53% | 0 | 5000 | 5000 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 5000 | CapEx | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.2 | Surface Cables | 1.4.2 Surface Cables | 1.4.2.1 | Surface Cable Assemblies | 1.4.2.1 Surface Cable Assemblies | cell-link@smartsheet.com | 2021-12-01 14:15 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.2.1.8 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.8 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 1.4.2.1.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.1.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 1.4.2.1.8 | 5000 | 5000 | 0 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 0 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000
| 1.4 | 1.4.2.2 | P |  | UW | Miscellaneous supplies |  |  | M & S |  |  |  |  | 1 | 0% | 2022-02-01 | 2023-12-01 | [8 empty] | 125 |  |  | 125 |  |  | 125 |  | 0 | 0 | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 375 | 53% | 198.75 | 573.75 | 573.75 |  | 125 | [10 empty] | 0 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125 | 53% | 66.25 | 191.25 | 191.25 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 765 | M & S | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.2 | Surface Cables | 1.4.2 Surface Cables | 1.4.2.2 | Surface Junction Boxes | 1.4.2.2 Surface Junction Boxes | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.2.2 | 0 | 0 | 0 | 0 | 191.25 | 0 | 0 | 191.25 | 0 | 0 | 191.25 | 0 | 1.4.2.2 | 0 | 191.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.2 | 0 | 0 | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 375 | 1.4.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.2 | 0 | 0 | 0 | 0 | 66.25 | 0 | 0 | 66.25 | 0 | 0 | 66.25 | 0 | 198.75 | 573.75 | 1.4.2.2 | 573.75 | 573.75 | 0 | 0 | 0 | 0 | 191.25 | 191.25 | 191.25 | 382.5 | 382.5 | 382.5 | 573.75 | 573.75 | 0 | 0 | 0 | 0 | 191.25 | 191.25 | 191.25 | 382.5 | 382.5 | 382.5 | 573.75 | 573.75
| 1.4 | 1.4.2.2.1 | C |  | MSU | Final design | Ferguson, Ng | 2.885% | Labor Hours | EN |  |  |  | 60 | 0% | 2022-02-01 | 2022-06-20 |  | TRUE | [6 empty] | 10 | 10 | 10 | 10 | 20 |  |  |  | 0 | 0 | 0 | 0 | 600 | 600 | 600 | 600 | 1200 | 0 | 0 | 0 | 3600 | 55% | 1980 | 5822.5194 | 5822.5194 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 |  | 5580 | [7 empty] | 5822.5194 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.2 | Surface Cables | 1.4.2 Surface Cables | 1.4.2.2 | Surface Junction Boxes | 1.4.2.2 Surface Junction Boxes | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.2.2.1 | 0 | 0 | 0 | 0 | 970.4199 | 970.4199 | 970.4199 | 970.4199 | 1940.8398 | 0 | 0 | 0 | 1.4.2.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.2.1 | 0 | 0 | 0 | 0 | 626.0774 | 626.0774 | 626.0774 | 626.0774 | 1252.1547 | 0 | 0 | 0 | 3756.4641 | 1.4.2.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.2.1 | 0 | 0 | 0 | 0 | 344.3425 | 344.3425 | 344.3425 | 344.3425 | 688.6851 | 0 | 0 | 0 | 2066.0553 | 5822.5194 | 1.4.2.2.1 | 5822.5194 | 9184.7425 | 0 | 0 | 0 | 0 | 970.4199 | 1940.8398 | 2911.2597 | 3881.6796 | 5822.5194 | 5822.5194 | 5822.5194 | 5822.5194 | 0 | 0 | 0 | 0 | 1530.7904 | 3061.5808 | 4592.3713 | 6123.1617 | 9184.7425 | 9184.7425 | 9184.7425 | 9184.7425
| 1.4 | 1.4.2.2.1 | C |  | UW | Final design | Kelley | 1.442% | Labor Hours | SC |  |  |  | 52 | 35% | 2022-02-01 | 2022-06-20 | [8 empty] | 5 | 5 | 5 | 5 | 10 |  |  |  | 0 | 0 | 0 | 0 | 351 | 351 | 351 | 351 | 702 | 0 | 0 | 0 | 2106 | 53% | 1116.18 | 3362.2232 | 3362.2232 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 3362.2232 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.2 | Surface Cables | 1.4.2 Surface Cables | 1.4.2.2 | Surface Junction Boxes | 1.4.2.2 Surface Junction Boxes | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.2.2.1 | 0 | 0 | 0 | 0 | 560.3705 | 560.3705 | 560.3705 | 560.3705 | 1120.7411 | 0 | 0 | 0 | 1.4.2.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.2.1 | 0 | 0 | 0 | 0 | 271.3002 | 271.3002 | 271.3002 | 271.3002 | 542.6004 | 0 | 0 | 0 | 1627.8011 | 1.4.2.2.1 | 0 | 0 | 0 | 0 | 94.9551 | 94.9551 | 94.9551 | 94.9551 | 189.9101 | 0 | 0 | 0 | 569.7304 | 1.4.2.2.1 | 0 | 0 | 0 | 0 | 194.1153 | 194.1153 | 194.1153 | 194.1153 | 388.2306 | 0 | 0 | 0 | 1164.6917 | 3362.2232 | 1.4.2.2.1 | 3362.2232 | 3362.2232 | 0 | 0 | 0 | 0 | 560.3705 | 1120.7411 | 1681.1116 | 2241.4821 | 3362.2232 | 3362.2232 | 3362.2232 | 3362.2232 | 0 | 0 | 0 | 0 | 560.3705 | 1120.7411 | 1681.1116 | 2241.4821 | 3362.2232 | 3362.2232 | 3362.2232 | 3362.2232
| 1.4 | 1.4.2.2.2 | C |  | MSU | Final design review | Ferguson, Ng | 2.308% | Labor Hours | EN |  |  |  | 60 | 0% | 2022-06-21 | 2022-06-21 | [12 empty] | 48 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2880 | 0 | 0 | 0 | 2880 | 55% | 1584 | 4658.0155 | 4658.0155 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 |  | 0 | 5400 | [6 empty] | 4658.0155 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.2 | Surface Cables | 1.4.2 Surface Cables | 1.4.2.2 | Surface Junction Boxes | 1.4.2.2 Surface Junction Boxes | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.2.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4658.0155 | 0 | 0 | 0 | 1.4.2.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3005.1713 | 0 | 0 | 0 | 3005.1713 | 1.4.2.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1652.8442 | 0 | 0 | 0 | 1652.8442 | 4658.0155 | 1.4.2.2.2 | 4658.0155 | 7347.794 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4658.0155 | 4658.0155 | 4658.0155 | 4658.0155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7347.794 | 7347.794 | 7347.794 | 7347.794
| 1.4 | 1.4.2.2.2 | C |  | UW | Final design review | Kelley | 1.154% | Labor Hours | SC |  |  |  | 52 | 35% | 2022-06-21 | 2022-06-21 | [12 empty] | 24 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1684.8 | 0 | 0 | 0 | 1684.8 | 53% | 892.944 | 2689.7786 | 2689.7786 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 2689.7786 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.2 | Surface Cables | 1.4.2 Surface Cables | 1.4.2.2 | Surface Junction Boxes | 1.4.2.2 Surface Junction Boxes | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.2.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2689.7786 | 0 | 0 | 0 | 1.4.2.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1302.2409 | 0 | 0 | 0 | 1302.2409 | 1.4.2.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 455.7843 | 0 | 0 | 0 | 455.7843 | 1.4.2.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 931.7534 | 0 | 0 | 0 | 931.7534 | 2689.7786 | 1.4.2.2.2 | 2689.7786 | 2689.7786 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2689.7786 | 2689.7786 | 2689.7786 | 2689.7786 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2689.7786 | 2689.7786 | 2689.7786 | 2689.7786
| 1.4 | 1.4.2.2.3 | C |  | MSU | Procurement | Ng | 2.404% | Labor Hours | EN |  |  |  | 60 | 0% | 2022-06-22 | 2022-10-11 | [12 empty] | 20 | 20 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 1200 | 300 | 300 | 3000 | 55% | 1650 | 4852.0995 | 4852.0995 | 10 | [11 empty] | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600 | 55% | 330 | 991.2839 | 991.2839 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | [9 empty] | 5843.3834 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.2 | Surface Cables | 1.4.2 Surface Cables | 1.4.2.2 | Surface Junction Boxes | 1.4.2.2 Surface Junction Boxes | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1940.8398 | 1940.8398 | 485.2099 | 485.2099 | 1.4.2.2.3 | 991.2839 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1252.1547 | 1252.1547 | 313.0387 | 313.0387 | 3130.3868 | 1.4.2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 688.6851 | 688.6851 | 172.1713 | 172.1713 | 1721.7127 | 4852.0995 | 1.4.2.2.3 | 4852.0995 | 4852.0995 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1940.8398 | 3881.6796 | 4366.8895 | 4852.0995 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1940.8398 | 3881.6796 | 4366.8895 | 4852.0995
| 1.4 | 1.4.2.2.4 | C |  | MSU | Fabrication | Ng | 0% | Labor Hours | EN |  |  |  | 60 | 0% | 2022-10-12 | 2022-12-06 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | 10 | 5 | 5 | [9 empty] | 600 | 300 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 55% | 660 | 1982.5678 | 1982.5678 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | [9 empty] | 1982.5678 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.2 | Surface Cables | 1.4.2 Surface Cables | 1.4.2.2 | Surface Junction Boxes | 1.4.2.2 Surface Junction Boxes | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.2.4 | 991.2839 | 495.642 | 495.642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | 1.4.2.2.4 | C |  | MSU | SJBs |  |  | CapEx |  |  | EE |  | 1 | 0% | 2022-10-12 | 2022-12-06 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 |  |  | 14000 | [9 empty] | 0 | 0 | 14000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14000 | 55% | 0 | 14000 | 14000 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | [9 empty] | 14000 | CapEx | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.2 | Surface Cables | 1.4.2 Surface Cables | 1.4.2.2 | Surface Junction Boxes | 1.4.2.2 Surface Junction Boxes | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.2.4 | 0 | 0 | 14000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | 1.4.2.2.5 | C |  | MSU | Pre-ship review | Ferguson, Ng | 0% | Labor Hours | EN |  |  |  | 60 | 0% | 2022-12-07 | 2022-12-27 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 |  |  | 20 | [9 empty] | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 55% | 660 | 1982.5678 | 1982.5678 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | [9 empty] | 1982.5678 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.2 | Surface Cables | 1.4.2 Surface Cables | 1.4.2.2 | Surface Junction Boxes | 1.4.2.2 Surface Junction Boxes | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.2.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.2.5 | 0 | 0 | 1982.5678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | 1.4.2.2.5 | C |  | UW | Pre-ship review | Kelley | 0% | Labor Hours | SC |  |  |  | 52 | 35% | 2022-12-07 | 2022-12-27 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 |  |  | 10 | [9 empty] | 0 | 0 | 702 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 702 | 53% | 372.06 | 1144.837 | 1144.837 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 1144.837 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.2 | Surface Cables | 1.4.2 Surface Cables | 1.4.2.2 | Surface Junction Boxes | 1.4.2.2 Surface Junction Boxes | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.2.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.2.5 | 0 | 0 | 1144.837 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | 1.4.2.2.6 | C |  | MSU | Shipping to PTH | Ng | 0% | Labor Hours | EN |  |  | 50 | 60 | 0% | 2022-12-28 | 2023-02-21 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 4092 | 0 | [5 empty] | 4092 |  | 0 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.2 | Surface Cables | 1.4.2 Surface Cables | 1.4.2.2 | Surface Junction Boxes | 1.4.2.2 Surface Junction Boxes | cell-link@smartsheet.com | 2021-12-01 14:15 |  | 2d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.2.2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | 1.4.2.2.6 | C |  | MSU | Shipping costs to PTH |  |  | M & S |  |  | EE |  | 1 | 0% | 2022-12-28 | 2023-02-21 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | [9 empty] | 0 | M & S | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.2 | Surface Cables | 1.4.2 Surface Cables | 1.4.2.2 | Surface Junction Boxes | 1.4.2.2 Surface Junction Boxes | cell-link@smartsheet.com | 2021-12-01 14:15 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.2.2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | 1.4.2.3 | P |  | UW | Miscellaneous supplies |  |  | M & S |  |  |  |  | 1 | 0% | 2021-01-01 | 2024-02-15 |  |  |  |  | 125 |  |  | 125 |  |  | 125 |  |  | 125 |  |  | 125 | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 500 | 53% | 265 | 765 | 765 | 125 |  |  | 125 |  |  | 125 |  |  | 125 |  |  | 125 | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 500 | 53% | 265 | 765 | 765 | 125 |  |  | 125 | [8 empty] | 125 | 0 | 0 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 53% | 132.5 | 382.5 | 382.5 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 1912.5 | M & S | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.2 | Surface Cables | 1.4.2 Surface Cables | 1.4.2.3 | ICL Upgrade | 1.4.2.3 ICL Upgrade | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.2.3 | 191.25 | 0 | 0 | 191.25 | 0 | 0 | 191.25 | 0 | 0 | 191.25 | 0 | 0 | 1.4.2.3 | 191.25 | 0 | 0 | 191.25 | 0 | 0 | 191.25 | 0 | 0 | 191.25 | 0 | 0 | 1.4.2.3 | 191.25 | 0 | 0 | 191.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.3 | 125 | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 500 | 1.4.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.3 | 66.25 | 0 | 0 | 66.25 | 0 | 0 | 66.25 | 0 | 0 | 66.25 | 0 | 0 | 265 | 765 | 1.4.2.3 | 765 | 765 | 191.25 | 191.25 | 191.25 | 382.5 | 382.5 | 382.5 | 573.75 | 573.75 | 573.75 | 765 | 765 | 765 | 191.25 | 191.25 | 191.25 | 382.5 | 382.5 | 382.5 | 573.75 | 573.75 | 573.75 | 765 | 765 | 765
| 1.4 | 1.4.2.3.1 | C |  | UW | ASC liaison | Kelley | 5.769% | Labor Hours | SC | TRUE |  | 50 | 52 | 35% | 2021-01-01 | 2024-02-15 |  |  |  |  | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 702 | 702 | 702 | 702 | 702 | 702 | 702 | 702 | 702 | 702 | 702 | 702 | 8424 | 53% | 4464.72 | 13448.8928 | 13448.8928 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 702 | 702 | 702 | 702 | 702 | 702 | 702 | 702 | 702 | 702 | 702 | 702 | 8424 | 53% | 4464.72 | 13738.044 | 13738.044 | 10 | 10 | 10 | 10 | 10 | [7 empty] | 702 | 702 | 702 | 702 | 702 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3510 | 53% | 1860.3 | 5847.255 | 5847.255 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 4092 | 18972 | [5 empty] | 4092 |  | 33034.1917 | Labor - Task | On Ice | 1.4 | CPT | 1.4 CPT | 1.4.2 | Surface Cables | 1.4.2 Surface Cables | 1.4.2.3 | ICL Upgrade | 1.4.2.3 ICL Upgrade | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 18d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.2.3.1 | 1120.7411 | 1120.7411 | 1120.7411 | 1120.7411 | 1120.7411 | 1120.7411 | 1120.7411 | 1120.7411 | 1120.7411 | 1120.7411 | 1120.7411 | 1120.7411 | 1.4.2.3.1 | 1144.837 | 1144.837 | 1144.837 | 1144.837 | 1144.837 | 1144.837 | 1144.837 | 1144.837 | 1144.837 | 1144.837 | 1144.837 | 1144.837 | 1.4.2.3.1 | 1169.451 | 1169.451 | 1169.451 | 1169.451 | 1169.451 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.3.1 | 542.6004 | 542.6004 | 542.6004 | 542.6004 | 542.6004 | 542.6004 | 542.6004 | 542.6004 | 542.6004 | 542.6004 | 542.6004 | 542.6004 | 6511.2044 | 1.4.2.3.1 | 189.9101 | 189.9101 | 189.9101 | 189.9101 | 189.9101 | 189.9101 | 189.9101 | 189.9101 | 189.9101 | 189.9101 | 189.9101 | 189.9101 | 2278.9216 | 1.4.2.3.1 | 388.2306 | 388.2306 | 388.2306 | 388.2306 | 388.2306 | 388.2306 | 388.2306 | 388.2306 | 388.2306 | 388.2306 | 388.2306 | 388.2306 | 4658.7668 | 13448.8928 | 1.4.2.3.1 | 13448.8928 | 13448.8928 | 1120.7411 | 2241.4821 | 3362.2232 | 4482.9643 | 5603.7053 | 6724.4464 | 7845.1874 | 8965.9285 | 10086.6696 | 11207.4106 | 12328.1517 | 13448.8928 | 1120.7411 | 2241.4821 | 3362.2232 | 4482.9643 | 5603.7053 | 6724.4464 | 7845.1874 | 8965.9285 | 10086.6696 | 11207.4106 | 12328.1517 | 13448.8928
| 1.4 | 1.4.2.3.2.1 | C |  | UW | Final design | Kelley | 1.923% | Labor Hours | SC | TRUE |  | 100 | 52 | 35% | 2022-04-01 | 2022-04-28 | [10 empty] | 40 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 2808 | 0 | 0 | 0 | 0 | 0 | 2808 | 53% | 1488.24 | 4482.9643 | -18402.2107 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 10416 | 21585.2256 | 22327 | 22885.175 |  | 0 |  | 54205 |  | 4482.9643 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.2 | Surface Cables | 1.4.2 Surface Cables | 1.4.2.3 | ICL Upgrade | 1.4.2.3 ICL Upgrade | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1431d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.2.3.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 4482.9643 | 0 | 0 | 0 | 0 | 0 | 1.4.2.3.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.3.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.3.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.3.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 2170.4015 | 0 | 0 | 0 | 0 | 0 | 2170.4015 | 1.4.2.3.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 759.6405 | 0 | 0 | 0 | 0 | 0 | 759.6405 | 1.4.2.3.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 1552.9223 | 0 | 0 | 0 | 0 | 0 | 1552.9223 | 4482.9643 | 1.4.2.3.2.1 | 4482.9643 | 4482.9643 | 0 | 0 | 0 | 0 | 0 | 0 | 4482.9643 | 4482.9643 | 4482.9643 | 4482.9643 | 4482.9643 | 4482.9643 | 0 | 0 | 0 | 0 | 0 | 0 | 4482.9643 | 4482.9643 | 4482.9643 | 4482.9643 | 4482.9643 | 4482.9643
| 1.4 | 1.4.2.3.2.2 | C |  | UW | Procurement | Kelley | 1.154% | Labor Hours | SC | TRUE |  | 1 | 52 | 35% | 2022-04-29 | 2022-08-18 | [11 empty] | 24 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1684.8 | 0 | 0 | 0 | 0 | 1684.8 | 53% | 892.944 | 2689.7786 | 1914.7786 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | -775 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 775 | 775 | 775 | 775 |  | 775 |  | 3875 |  | 2689.7786 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.2 | Surface Cables | 1.4.2 Surface Cables | 1.4.2.3 | ICL Upgrade | 1.4.2.3 ICL Upgrade | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1431d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.2.3.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2689.7786 | 0 | 0 | 0 | 0 | 1.4.2.3.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.3.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.3.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.3.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1302.2409 | 0 | 0 | 0 | 0 | 1302.2409 | 1.4.2.3.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 455.7843 | 0 | 0 | 0 | 0 | 455.7843 | 1.4.2.3.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 931.7534 | 0 | 0 | 0 | 0 | 931.7534 | 2689.7786 | 1.4.2.3.2.2 | 2689.7786 | 4219.7786 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2689.7786 | 2689.7786 | 2689.7786 | 2689.7786 | 2689.7786 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2689.7786 | 2689.7786 | 2689.7786 | 4219.7786 | 4219.7786
| 1.4 | 1.4.2.3.2.2 | C |  | UW | Patch panels |  |  | M & S |  | TRUE |  |  | 1 | 0% | 2022-04-29 | 2022-08-18 | [14 empty] | 1000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 1000 | 53% | 530 | 1530 | 1530 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 1530 | M & S | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.2 | Surface Cables | 1.4.2 Surface Cables | 1.4.2.3 | ICL Upgrade | 1.4.2.3 ICL Upgrade | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.2.3.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1530 | 0 | 1.4.2.3.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.3.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.3.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.3.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 1000 | 1.4.2.3.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.3.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 530 | 0 | 530 | 1530 | 1.4.2.3.2.2 | 1530 | 1530 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1530 | 1530 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1530 | 1530
| 1.4 | 1.4.2.3.2.3 | C |  | UW | Fabrication | Kelley | 1.923% | Labor Hours | SC | TRUE |  | 1 | 52 | 35% | 2022-08-19 | 2022-09-29 | [14 empty] | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1404 | 1404 | 2808 | 53% | 1488.24 | 4482.9643 | -1097.0357 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | -2790 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 5580 | 5580 | 5580 | 5580 |  | 2790 |  | 20155 |  | 4482.9643 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.2 | Surface Cables | 1.4.2 Surface Cables | 1.4.2.3 | ICL Upgrade | 1.4.2.3 ICL Upgrade | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1431d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.2.3.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2241.4821 | 2241.4821 | 1.4.2.3.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.3.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.3.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.3.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1085.2007 | 1085.2007 | 2170.4015 | 1.4.2.3.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 379.8203 | 379.8203 | 759.6405 | 1.4.2.3.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 776.4611 | 776.4611 | 1552.9223 | 4482.9643 | 1.4.2.3.2.3 | 4482.9643 | 4482.9643 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2241.4821 | 4482.9643 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2241.4821 | 4482.9643
| 1.4 | 1.4.2.3.2.4 | C |  | UW | Pre-ship review | Kelley | 0% | Labor Hours | SC | TRUE |  |  | 52 | 35% | 2022-09-30 | 2022-10-13 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | 24 | [11 empty] | 1684.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1684.8 | 53% | 892.944 | 2747.6088 | 2747.6088 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 10075 | [7 empty] | 2747.6088 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.2 | Surface Cables | 1.4.2 Surface Cables | 1.4.2.3 | ICL Upgrade | 1.4.2.3 ICL Upgrade | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 915d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.2.3.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.3.2.4 | 2747.6088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.3.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.3.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.3.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.3.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.3.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.3.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | 1.4.2.3.2.5 | C |  | UW | Shipping to PTH (NB: small) | Kelley | 0% | Labor Hours | SC | TRUE |  | 1 | 52 | 35% | 2022-10-14 | 2022-10-27 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | -775 | 24 | [11 empty] | 1684.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1684.8 | 53% | 892.944 | 2747.6088 | 1972.6088 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 775 | 775 | 775 | 775 |  | 775 |  | 3875 |  | 2747.6088 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.2 | Surface Cables | 1.4.2 Surface Cables | 1.4.2.3 | ICL Upgrade | 1.4.2.3 ICL Upgrade | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 695d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.2.3.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.3.2.5 | 2747.6088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.3.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.3.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.3.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.3.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.3.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.3.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | 1.4.2.3.2.5 | C |  | UW | Shipping costs |  |  | M & S |  | TRUE |  |  | 1 | 0% | 2022-10-14 | 2022-10-27 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | 1000 | [11 empty] | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 53% | 530 | 1530 | 1530 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 1530 | M & S | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.2 | Surface Cables | 1.4.2 Surface Cables | 1.4.2.3 | ICL Upgrade | 1.4.2.3 ICL Upgrade | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.2.3.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.3.2.5 | 1530 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.3.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.3.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.3.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.3.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.3.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.3.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | 1.4.2.3.2.8 | C |  | UW | Installation in ICL | Kelley | 0% | Labor Hours | SC | TRUE |  | 1 | 52 | 35% | 2023-12-15 | 2023-12-15 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 |  |  | 8 | [9 empty] | 0 | 0 | 561.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 561.6 | 53% | 297.648 | 935.5608 | 935.5608 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 16000 | 12000 | [5 empty] | 16000 |  | 935.5608 | Labor - Task | On Ice | 1.4 | CPT | 1.4 CPT | 1.4.2 | Surface Cables | 1.4.2 Surface Cables | 1.4.2.3 | ICL Upgrade | 1.4.2.3 ICL Upgrade | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 695d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.2.3.2.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.3.2.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.3.2.8 | 0 | 0 | 935.5608 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.3.2.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.3.2.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.3.2.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.3.2.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.3.2.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | 1.4.2.3.3.1 | C |  | UW | Final design | Kelley | 0.9615% | Labor Hours | SC | TRUE |  |  | 52 | 35% | 2022-03-01 | 2022-04-11 |  | TRUE | [7 empty] | 10 | 10 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 702 | 702 | 0 | 0 | 0 | 0 | 0 | 1404 | 53% | 744.12 | 2241.4821 | 2241.4821 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 21700 | [7 empty] | 2241.4821 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.2 | Surface Cables | 1.4.2 Surface Cables | 1.4.2.3 | ICL Upgrade | 1.4.2.3 ICL Upgrade | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.2.3.3.1 | 0 | 0 | 0 | 0 | 0 | 1120.7411 | 1120.7411 | 0 | 0 | 0 | 0 | 0 | 1.4.2.3.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.3.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.3.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.3.3.1 | 0 | 0 | 0 | 0 | 0 | 542.6004 | 542.6004 | 0 | 0 | 0 | 0 | 0 | 1085.2007 | 1.4.2.3.3.1 | 0 | 0 | 0 | 0 | 0 | 189.9101 | 189.9101 | 0 | 0 | 0 | 0 | 0 | 379.8203 | 1.4.2.3.3.1 | 0 | 0 | 0 | 0 | 0 | 388.2306 | 388.2306 | 0 | 0 | 0 | 0 | 0 | 776.4611 | 2241.4821 | 1.4.2.3.3.1 | 2241.4821 | 2241.4821 | 0 | 0 | 0 | 0 | 0 | 1120.7411 | 2241.4821 | 2241.4821 | 2241.4821 | 2241.4821 | 2241.4821 | 2241.4821 | 0 | 0 | 0 | 0 | 0 | 1120.7411 | 2241.4821 | 2241.4821 | 2241.4821 | 2241.4821 | 2241.4821 | 2241.4821
| 1.4 | 1.4.2.3.3.2 | C |  | UW | Prototype production and evaluation | Kelley | 2.692% | Labor Hours | SC | TRUE |  |  | 52 | 35% | 2022-04-12 | 2022-06-06 |  | TRUE | [8 empty] | 24 | 24 | 8 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1684.8 | 1684.8 | 561.6 | 0 | 0 | 0 | 3931.2 | 53% | 2083.536 | 6276.15 | 6276.15 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 9300 | [7 empty] | 6276.15 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.2 | Surface Cables | 1.4.2 Surface Cables | 1.4.2.3 | ICL Upgrade | 1.4.2.3 ICL Upgrade | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.2.3.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 2689.7786 | 2689.7786 | 896.5929 | 0 | 0 | 0 | 1.4.2.3.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.3.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.3.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.3.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 1302.2409 | 1302.2409 | 434.0803 | 0 | 0 | 0 | 3038.5621 | 1.4.2.3.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 455.7843 | 455.7843 | 151.9281 | 0 | 0 | 0 | 1063.4967 | 1.4.2.3.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 931.7534 | 931.7534 | 310.5845 | 0 | 0 | 0 | 2174.0912 | 6276.15 | 1.4.2.3.3.2 | 6276.15 | 9948.15 | 0 | 0 | 0 | 0 | 0 | 0 | 2689.7786 | 5379.5571 | 6276.15 | 6276.15 | 6276.15 | 6276.15 | 0 | 0 | 0 | 0 | 0 | 0 | 6361.7786 | 9051.5571 | 9948.15 | 9948.15 | 9948.15 | 9948.15
| 1.4 | 1.4.2.3.3.2 | C |  | UW | Patch cable prototypes |  |  | M & S |  | TRUE | CP |  | 1 | 0% | 2022-04-12 | 2022-06-06 | [10 empty] | 2400 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 2400 | 0 | 0 | 0 | 0 | 0 | 2400 | 53% | 1272 | 3672 | 3672 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 3672 | M & S | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.2 | Surface Cables | 1.4.2 Surface Cables | 1.4.2.3 | ICL Upgrade | 1.4.2.3 ICL Upgrade | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.2.3.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 3672 | 0 | 0 | 0 | 0 | 0 | 1.4.2.3.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.3.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.3.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.3.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 2400 | 0 | 0 | 0 | 0 | 0 | 2400 | 1.4.2.3.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.3.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 1272 | 0 | 0 | 0 | 0 | 0 | 1272 | 3672 | 1.4.2.3.3.2 | 3672 | 3672 | 0 | 0 | 0 | 0 | 0 | 0 | 3672 | 3672 | 3672 | 3672 | 3672 | 3672 | 0 | 0 | 0 | 0 | 0 | 0 | 3672 | 3672 | 3672 | 3672 | 3672 | 3672
| 1.4 | 1.4.2.3.3.3 | C |  | UW | Final design review | Kelley | 1.154% | Labor Hours | SC | TRUE |  |  | 52 | 35% | 2022-06-07 | 2022-06-07 |  | TRUE | [10 empty] | 24 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1684.8 | 0 | 0 | 0 | 1684.8 | 53% | 892.944 | 2689.7786 | 2689.7786 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 5580 | [7 empty] | 2689.7786 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.2 | Surface Cables | 1.4.2 Surface Cables | 1.4.2.3 | ICL Upgrade | 1.4.2.3 ICL Upgrade | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.2.3.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2689.7786 | 0 | 0 | 0 | 1.4.2.3.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.3.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.3.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.3.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1302.2409 | 0 | 0 | 0 | 1302.2409 | 1.4.2.3.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 455.7843 | 0 | 0 | 0 | 455.7843 | 1.4.2.3.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 931.7534 | 0 | 0 | 0 | 931.7534 | 2689.7786 | 1.4.2.3.3.3 | 2689.7786 | 2689.7786 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2689.7786 | 2689.7786 | 2689.7786 | 2689.7786 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2689.7786 | 2689.7786 | 2689.7786 | 2689.7786
| 1.4 | 1.4.2.3.3.4 | C |  | UW | Procurement | Kelley | 0.9615% | Labor Hours | SC | TRUE |  |  | 52 | 35% | 2022-06-08 | 2022-09-27 | [12 empty] | 10 | 10 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 702 | 702 | 0 | 0 | 1404 | 53% | 744.12 | 2241.4821 | 2241.4821 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 | 5400 | [6 empty] | 2241.4821 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.2 | Surface Cables | 1.4.2 Surface Cables | 1.4.2.3 | ICL Upgrade | 1.4.2.3 ICL Upgrade | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.2.3.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1120.7411 | 1120.7411 | 0 | 0 | 1.4.2.3.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.3.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.3.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.3.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 542.6004 | 542.6004 | 0 | 0 | 1085.2007 | 1.4.2.3.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 189.9101 | 189.9101 | 0 | 0 | 379.8203 | 1.4.2.3.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 388.2306 | 388.2306 | 0 | 0 | 776.4611 | 2241.4821 | 1.4.2.3.3.4 | 2241.4821 | 33269.8821 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1120.7411 | 2241.4821 | 2241.4821 | 2241.4821 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1120.7411 | 2241.4821 | 33269.8821 | 33269.8821
| 1.4 | 1.4.2.3.3.4 | C |  | UW | Patch cables |  |  | M & S |  | TRUE |  |  | 1 | 0% | 2022-06-08 | 2022-09-27 |  |  |  | surface cables to FHs, 169+20 NTS | [10 empty] | 20280 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20280 | 0 | 20280 | 53% | 10748.4 | 31028.4 | 31028.4 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 31028.4 | M & S | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.2 | Surface Cables | 1.4.2 Surface Cables | 1.4.2.3 | ICL Upgrade | 1.4.2.3 ICL Upgrade | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.2.3.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31028.4 | 0 | 1.4.2.3.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.3.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.3.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.3.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20280 | 0 | 20280 | 1.4.2.3.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.3.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10748.4 | 0 | 10748.4 | 31028.4 | 1.4.2.3.3.4 | 31028.4 | 31028.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31028.4 | 31028.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31028.4 | 31028.4
| 1.4 | 1.4.2.3.3.5 | C |  | UW | Production | Kelley | 1.923% | Labor Hours | SC | TRUE |  | 50 | 52 | 35% | 2022-09-28 | 2022-11-22 | [15 empty] | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2808 | 2808 | 53% | 1488.24 | 4482.9643 | 4482.9643 | 10 | 10 | [10 empty] | 702 | 702 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1404 | 53% | 744.12 | 2289.674 | 2289.674 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 4092 | 0 | [5 empty] | 4092 |  | 6772.6383 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.2 | Surface Cables | 1.4.2 Surface Cables | 1.4.2.3 | ICL Upgrade | 1.4.2.3 ICL Upgrade | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 2d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.2.3.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4482.9643 | 1.4.2.3.3.5 | 1144.837 | 1144.837 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.3.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.3.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.3.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2170.4015 | 2170.4015 | 1.4.2.3.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 759.6405 | 759.6405 | 1.4.2.3.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1552.9223 | 1552.9223 | 4482.9643 | 1.4.2.3.3.5 | 4482.9643 | 4482.9643 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4482.9643 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4482.9643
| 1.4 | 1.4.2.3.3.6 | C |  | UW | Pre-ship review | Kelley | 0% | Labor Hours | SC | TRUE |  | 50 | 52 | 35% | 2022-11-23 | 2022-11-29 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 |  | 16 | [10 empty] | 0 | 1123.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1123.2 | 53% | 595.296 | 1831.7392 | 1831.7392 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 10230 | 4743 | [5 empty] | 10230 |  | 1831.7392 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.2 | Surface Cables | 1.4.2 Surface Cables | 1.4.2.3 | ICL Upgrade | 1.4.2.3 ICL Upgrade | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 109d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.2.3.3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.3.3.6 | 0 | 1831.7392 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.3.3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.3.3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.3.3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.3.3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.3.3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.3.3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | 1.4.2.3.3.7 | C |  | UW | Shipping to PTH | Kelley | 0% | Labor Hours | SC | TRUE |  | 50 | 52 | 35% | 2022-11-30 | 2022-12-06 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 |  |  | 16 | [9 empty] | 0 | 0 | 1123.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1123.2 | 53% | 595.296 | 1831.7392 | 1831.7392 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 7161 | 9486 | [5 empty] | 7161 |  | 1831.7392 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.2 | Surface Cables | 1.4.2 Surface Cables | 1.4.2.3 | ICL Upgrade | 1.4.2.3 ICL Upgrade | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 103d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.2.3.3.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.3.3.7 | 0 | 0 | 1831.7392 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.3.3.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.3.3.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.3.3.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.3.3.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.3.3.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.3.3.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | 1.4.2.3.3.7 | C |  | UW | Patch cable shipping costs |  |  | M & S |  | TRUE |  |  | 1 | 0% | 2022-11-30 | 2022-12-06 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 |  |  | 1200 | [9 empty] | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 53% | 636 | 1836 | 1836 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 1836 | M & S | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.2 | Surface Cables | 1.4.2 Surface Cables | 1.4.2.3 | ICL Upgrade | 1.4.2.3 ICL Upgrade | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.2.3.3.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.3.3.7 | 0 | 0 | 1836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.3.3.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.3.3.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.3.3.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.3.3.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.3.3.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.3.3.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | 1.4.2.3.3.10 | C |  | UW | Installation in ICL | Kelley | 0% | Labor Hours | SC | TRUE |  | 50 | 52 | 35% | 2024-01-01 | 2024-01-05 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 |  |  |  | 40 | [8 empty] | 0 | 0 | 0 | 2808 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2808 | 53% | 1488.24 | 4677.804 | 4677.804 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 4092 | 12648 | [5 empty] | 12440 |  | 4677.804 | Labor - Task | On Ice | 1.4 | CPT | 1.4 CPT | 1.4.2 | Surface Cables | 1.4.2 Surface Cables | 1.4.2.3 | ICL Upgrade | 1.4.2.3 ICL Upgrade | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 12d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.2.3.3.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.3.3.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.3.3.10 | 0 | 0 | 0 | 4677.804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.3.3.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.3.3.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.3.3.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.3.3.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2.3.3.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | 1.4.3.1.1.3 | C |  | MSU | FieldHub rev1 testing and installation at NTS | Halliday | 1.923% | Labor Hours | PO |  |  | 1 | 26 | 23% | 2022-05-16 | 2022-06-30 | [7 empty] | 16 | 8 | 8 | 8 | [5 empty] | 0 | 0 | 0 | 511.68 | 255.84 | 255.84 | 255.84 | 0 | 0 | 0 | 0 | 0 | 1279.2 | 55% | 703.56 | 2068.9352 | 1293.9352 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | -775 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 775 | 775 | 775 | 775 |  | 775 |  | 3875 |  | 2068.9352 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.3 | FieldHub | 1.4.3 FieldHub | 1.4.3.1 | FieldHub Electronics | 1.4.3.1 FieldHub Electronics | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1431d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.3.1.1.3 | 0 | 0 | 0 | 827.5741 | 413.787 | 413.787 | 413.787 | 0 | 0 | 0 | 0 | 0 | 1.4.3.1.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.3.1.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.3.1.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.3.1.1.3 | 0 | 0 | 0 | 434.0803 | 217.0401 | 217.0401 | 217.0401 | 0 | 0 | 0 | 0 | 0 | 1085.2007 | 1.4.3.1.1.3 | 0 | 0 | 0 | 99.8385 | 49.9192 | 49.9192 | 49.9192 | 0 | 0 | 0 | 0 | 0 | 249.5962 | 1.4.3.1.1.3 | 0 | 0 | 0 | 293.6553 | 146.8277 | 146.8277 | 146.8277 | 0 | 0 | 0 | 0 | 0 | 734.1383 | 2068.9352 | 1.4.3.1.1.3 | 2068.9352 | 2068.9352 | 0 | 0 | 0 | 827.5741 | 1241.3611 | 1655.1482 | 2068.9352 | 2068.9352 | 2068.9352 | 2068.9352 | 2068.9352 | 2068.9352 | 0 | 0 | 0 | 827.5741 | 1241.3611 | 1655.1482 | 2068.9352 | 2068.9352 | 2068.9352 | 2068.9352 | 2068.9352 | 2068.9352
| 1.4 | 1.4.3.1.1.6 | C |  | MSU | FieldHub rev2 testing and installation at NTS | Halliday | 0% | Labor Hours | PO |  |  | 1 | 26 | 23% | 2022-11-01 | 2022-11-30 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | -775 | 24 | 24 | [10 empty] | 767.52 | 767.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1535.04 | 55% | 844.272 | 2536.1008 | 1761.1008 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 775 | 775 | 775 | 775 |  | 775 |  | 3875 |  | 2536.1008 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.3 | FieldHub | 1.4.3 FieldHub | 1.4.3.1 | FieldHub Electronics | 1.4.3.1 FieldHub Electronics | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 695d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.3.1.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.3.1.1.6 | 1268.0504 | 1268.0504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.3.1.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.3.1.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.3.1.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.3.1.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.3.1.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.3.1.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | 1.4.3.1.1.7 | C |  | UW | FieldHub prototype installed in ICL (hand carry) |  | 0% | Labor Hours | SC | TRUE |  | 1 | 45 | 35% | 2022-12-01 | 2023-01-31 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 30690 | 5580 | [5 empty] | 30690 |  | 0 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.3 | FieldHub | 1.4.3 FieldHub | 1.4.3.1 | FieldHub Electronics | 1.4.3.1 FieldHub Electronics | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 695d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.3.1.1.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.3.1.1.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.3.1.1.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.3.1.1.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.3.1.1.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.3.1.1.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.3.1.1.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.3.1.1.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | 1.4.3.1.2.8 | C |  | UW | Installation and commissioning in ICL |  | 0% | Labor Hours | SC |  |  |  | 45 | 35% | 2023-11-01 | 2024-01-31 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 |  |  | 40 | 40 | [8 empty] | 0 | 0 | 2430 | 2430 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4860 | 53% | 2575.8 | 8270.2675 |  | 11067 | [7 empty] | 8270.2675 | Labor - Task | On Ice | 1.4 | CPT | 1.4 CPT | 1.4.3 | FieldHub | 1.4.3 FieldHub | 1.4.3.1 | FieldHub Electronics | 1.4.3.1 FieldHub Electronics | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 12d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.3.1.2.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.3.1.2.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.3.1.2.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.3.1.2.8 | 0 | 0 | 4135.1337 | 4135.1337 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.3.1.2.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.3.1.2.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.3.1.2.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.3.1.2.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | 1.4.4.1 | P |  | UW | Miscellaneous supplies |  |  | M & S |  |  |  |  | 1 | 0% | 2021-02-01 | 2023-12-21 | [5 empty] | 125 |  |  | 125 |  |  | 125 |  |  | 125 |  | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 500 | 53% | 265 | 765 | 765 |  | 125 | [10 empty] | 0 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125 | 53% | 66.25 | 191.25 | 191.25 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 956.25 | M & S | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.4 | CPT Central Infrastructure | 1.4.4 CPT Central Infrastructure | 1.4.4.1 | Communications and Timing Systems | 1.4.4.1 Communications and Timing Systems | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.4.1 | 0 | 191.25 | 0 | 0 | 191.25 | 0 | 0 | 191.25 | 0 | 0 | 191.25 | 0 | 1.4.4.1 | 0 | 191.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 500 | 1.4.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1 | 0 | 66.25 | 0 | 0 | 66.25 | 0 | 0 | 66.25 | 0 | 0 | 66.25 | 0 | 265 | 765 | 1.4.4.1 | 765 | 765 | 0 | 191.25 | 191.25 | 191.25 | 382.5 | 382.5 | 382.5 | 573.75 | 573.75 | 573.75 | 765 | 765 | 0 | 191.25 | 191.25 | 191.25 | 382.5 | 382.5 | 382.5 | 573.75 | 573.75 | 573.75 | 765 | 765
| 1.4 | 1.4.4.1.1.1 | C |  | UW | Procurement | Kelley | 1.154% | Labor Hours | SC |  |  | 50 | 52 | 35% | 2021-02-01 | 2022-07-29 | [7 empty] | 8 | 8 | 8 | [6 empty] | 0 | 0 | 0 | 561.6 | 561.6 | 561.6 | 0 | 0 | 0 | 0 | 0 | 0 | 1684.8 | 53% | 892.944 | 2689.7786 | 2689.7786 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 4092 | 18972 | [5 empty] | 4092 |  | 2689.7786 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.4 | CPT Central Infrastructure | 1.4.4 CPT Central Infrastructure | 1.4.4.1 | Communications and Timing Systems | 1.4.4.1 Communications and Timing Systems | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 18d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.4.1.1.1 | 0 | 0 | 0 | 896.5929 | 896.5929 | 896.5929 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.1.1 | 0 | 0 | 0 | 434.0803 | 434.0803 | 434.0803 | 0 | 0 | 0 | 0 | 0 | 0 | 1302.2409 | 1.4.4.1.1.1 | 0 | 0 | 0 | 151.9281 | 151.9281 | 151.9281 | 0 | 0 | 0 | 0 | 0 | 0 | 455.7843 | 1.4.4.1.1.1 | 0 | 0 | 0 | 310.5845 | 310.5845 | 310.5845 | 0 | 0 | 0 | 0 | 0 | 0 | 931.7534 | 2689.7786 | 1.4.4.1.1.1 | 2689.7786 | 37989.7786 | 0 | 0 | 0 | 896.5929 | 1793.1857 | 2689.7786 | 2689.7786 | 2689.7786 | 2689.7786 | 2689.7786 | 2689.7786 | 2689.7786 | 0 | 0 | 0 | 896.5929 | 1793.1857 | 2689.7786 | 2889.7786 | 2889.7786 | 2889.7786 | 37989.7786 | 37989.7786 | 37989.7786
| 1.4 | 1.4.4.1.1.1 | C |  | UW | Fiber patch cables for NTS (10) |  |  | CapEx |  |  | CP |  | 1 | 0% | 2021-02-01 | 2022-07-29 | [10 empty] | 200 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 200 | 53% | 0 | 200 | 200 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 200 | CapEx | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.4 | CPT Central Infrastructure | 1.4.4 CPT Central Infrastructure | 1.4.4.1 | Communications and Timing Systems | 1.4.4.1 Communications and Timing Systems | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.4.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 200 | 1.4.4.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 1.4.4.1.1.1 | 200 | 35300 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 200 | 200 | 200 | 200 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 200 | 200 | 35300 | 35300 | 35300
| 1.4 | 1.4.4.1.1.1 | C |  | UW | White Rabbit OEM nodes for NTS and SPTS (10 total, 6 to be purchased) |  |  | CapEx |  |  | CP |  | 1 | 0% | 2021-02-01 | 2022-07-29 |  |  |  | 4 already purchased by NvE, 6 more planned | [9 empty] | 12000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 | 0 | 0 | 12000 | 53% | 0 | 12000 | 12000 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 12000 | CapEx | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.4 | CPT Central Infrastructure | 1.4.4 CPT Central Infrastructure | 1.4.4.1 | Communications and Timing Systems | 1.4.4.1 Communications and Timing Systems | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.4.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 | 0 | 0 | 1.4.4.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 | 0 | 0 | 12000 | 1.4.4.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 | 1.4.4.1.1.1 | 12000 | 35100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 | 12000 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35100 | 35100 | 35100
| 1.4 | 1.4.4.1.1.1 | C |  | UW | White rabbit switches for ICL (2 total, 1 to be purchased) |  |  | CapEx |  | TRUE | CP |  | 1 | 0% | 2021-02-01 | 2022-07-29 |  |  |  | cost for 1 unit; one already purchased by NvE | [9 empty] | 3100 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3100 | 0 | 0 | 3100 | 53% | 0 | 3100 | 3100 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 3100 | CapEx | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.4 | CPT Central Infrastructure | 1.4.4 CPT Central Infrastructure | 1.4.4.1 | Communications and Timing Systems | 1.4.4.1 Communications and Timing Systems | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.4.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3100 | 0 | 0 | 1.4.4.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3100 | 0 | 0 | 3100 | 1.4.4.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3100 | 1.4.4.1.1.1 | 3100 | 23100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3100 | 3100 | 3100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23100 | 23100 | 23100
| 1.4 | 1.4.4.1.1.1 | C |  | UW | White Rabbit OEM nodes for ICL (10) |  |  | CapEx |  |  | CP |  | 1 | 0% | 2021-02-01 | 2022-07-29 | [13 empty] | 20000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 20000 | 53% | 0 | 20000 | 20000 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 20000 | CapEx | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.4 | CPT Central Infrastructure | 1.4.4 CPT Central Infrastructure | 1.4.4.1 | Communications and Timing Systems | 1.4.4.1 Communications and Timing Systems | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.4.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 1.4.4.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 20000 | 1.4.4.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 1.4.4.1.1.1 | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000 | 20000
| 1.4 | 1.4.4.1.1.3 | C |  | UW | Shipping to PTH | Kelley | 0% | Labor Hours | SC |  |  | 1 | 52 | 35% | 2022-09-26 | 2022-09-30 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | -775 | [11 empty] | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1123.2 | 1123.2 | 53% | 595.296 | 1831.7392 | 1056.7392 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 775 | 775 | 775 | 775 |  | 775 |  | 3875 |  | 1831.7392 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.4 | CPT Central Infrastructure | 1.4.4 CPT Central Infrastructure | 1.4.4.1 | Communications and Timing Systems | 1.4.4.1 Communications and Timing Systems | cell-link@smartsheet.com | 2021-12-01 14:26 |  | 1431d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.4.1.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1831.7392 | 1.4.4.1.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | 1.4.4.1.1.3 | C |  | UW | Shipping costs |  |  | M & S |  |  |  |  | 1 | 0% | 2022-09-26 | 2022-09-30 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [11 empty] | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 500 | 53% | 265 | 765 | 765 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 765 | M & S | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.4 | CPT Central Infrastructure | 1.4.4 CPT Central Infrastructure | 1.4.4.1 | Communications and Timing Systems | 1.4.4.1 Communications and Timing Systems | cell-link@smartsheet.com | 2021-12-01 14:26 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.4.1.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 765 | 1.4.4.1.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | 1.4.4.1.1.5 | C |  | UW | Installation in ICL | Kelley | 0% | Labor Hours | SC | TRUE |  |  | 52 | 35% | 2023-09-01 | 2023-09-14 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 |  |  | 15 | [9 empty] | 0 | 0 | 1053 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1053 | 53% | 558.09 | 1754.1765 | 1754.1765 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 10075 | [7 empty] | 1754.1765 | Labor - Task | On Ice | 1.4 | CPT | 1.4 CPT | 1.4.4 | CPT Central Infrastructure | 1.4.4 CPT Central Infrastructure | 1.4.4.1 | Communications and Timing Systems | 1.4.4.1 Communications and Timing Systems | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 915d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.4.1.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.1.5 | 0 | 0 | 1754.1765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | 1.4.4.1.2.1 | C |  | UW | Final design | Kelley | 0% | Labor Hours | SC |  |  | 1 | 52 | 35% | 2023-03-01 | 2023-03-28 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [5 empty] | 140 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 9828 | 0 | 0 | 0 | 0 | 0 | 0 | 9828 | 53% | 5208.84 | 16027.718 | 16027.718 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 30690 | 5580 | [5 empty] | 30690 |  | 16027.718 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.4 | CPT Central Infrastructure | 1.4.4 CPT Central Infrastructure | 1.4.4.1 | Communications and Timing Systems | 1.4.4.1 Communications and Timing Systems | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 695d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.4.1.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.2.1 | 0 | 0 | 0 | 0 | 0 | 16027.718 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | 1.4.4.1.2.2 | C |  | UW | Prototype production | Kelley | 0% | Labor Hours | SC |  |  | 1 | 52 | 35% | 2023-03-29 | 2023-04-25 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [5 empty] | 20 | 60 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 1404 | 4212 | 0 | 0 | 0 | 0 | 0 | 5616 | 53% | 2976.48 | 9158.696 | 9158.696 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 8370 | 8370 | 8370 |  |  |  |  | 16907 |  | 9158.696 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.4 | CPT Central Infrastructure | 1.4.4 CPT Central Infrastructure | 1.4.4.1 | Communications and Timing Systems | 1.4.4.1 Communications and Timing Systems | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 695d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.4.1.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.2.2 | 0 | 0 | 0 | 0 | 0 | 2289.674 | 6869.022 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | 1.4.4.1.2.2 | C |  | UW | Timing monitoring prototype |  |  | CapEx |  |  | HD |  | 1 | 0% | 2023-03-29 | 2023-04-25 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [5 empty] | 3000 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 53% | 0 | 3000 | 3000 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 3000 | CapEx | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.4 | CPT Central Infrastructure | 1.4.4 CPT Central Infrastructure | 1.4.4.1 | Communications and Timing Systems | 1.4.4.1 Communications and Timing Systems | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.4.1.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.2.2 | 0 | 0 | 0 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | 1.4.4.1.2.3 | C |  | UW | Installation and testing at NTS/SPTS | Kelley | 0% | Labor Hours | SC |  |  | 1 | 52 | 35% | 2023-04-26 | 2023-06-20 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [6 empty] | 20 | 20 | 20 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1404 | 1404 | 1404 | 0 | 0 | 0 | 4212 | 53% | 2232.36 | 6869.022 | 6869.022 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 16000 | 12000 | [5 empty] | 16000 |  | 6869.022 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.4 | CPT Central Infrastructure | 1.4.4 CPT Central Infrastructure | 1.4.4.1 | Communications and Timing Systems | 1.4.4.1 Communications and Timing Systems | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 695d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.4.1.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 2289.674 | 2289.674 | 2289.674 | 0 | 0 | 0 | 1.4.4.1.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | 1.4.4.1.2.3 | C |  | UW | Installation and testing at NTS/SPTS |  |  | Travel |  |  |  |  | 1 | 0% | 2023-04-26 | 2023-06-20 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [8 empty] | 1800 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 1800 | 53% | 954 | 2754 | 2754 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 2754 | Travel | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.4 | CPT Central Infrastructure | 1.4.4 CPT Central Infrastructure | 1.4.4.1 | Communications and Timing Systems | 1.4.4.1 Communications and Timing Systems | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.4.1.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2754 | 0 | 0 | 0 | 1.4.4.1.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | 1.4.4.1.2.4 | C |  | UW | Production of ICL system | Kelley | 0% | Labor Hours | SC |  |  |  | 52 | 35% | 2023-06-21 | 2023-07-18 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [8 empty] | 40 | 40 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2808 | 2808 | 0 | 0 | 5616 | 53% | 2976.48 | 9158.696 | 9158.696 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 21700 | [7 empty] | 9158.696 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.4 | CPT Central Infrastructure | 1.4.4 CPT Central Infrastructure | 1.4.4.1 | Communications and Timing Systems | 1.4.4.1 Communications and Timing Systems | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.4.1.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4579.348 | 4579.348 | 0 | 0 | 1.4.4.1.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | 1.4.4.1.2.4 | C |  | UW | Timing monitoring system for ICL |  |  | CapEx |  |  | HD |  | 1 | 0% | 2023-06-21 | 2023-07-18 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [8 empty] | 3000 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 0 | 0 | 0 | 3000 | 53% | 0 | 3000 | 3000 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 3000 | CapEx | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.4 | CPT Central Infrastructure | 1.4.4 CPT Central Infrastructure | 1.4.4.1 | Communications and Timing Systems | 1.4.4.1 Communications and Timing Systems | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.4.1.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 0 | 0 | 0 | 1.4.4.1.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | 1.4.4.1.2.6 | C |  | UW | Shipping to CHC | Kelley | 0% | Labor Hours | SC |  |  |  | 52 | 35% | 2023-08-15 | 2023-09-11 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [11 empty] | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1684.8 | 1684.8 | 53% | 892.944 | 2747.6088 | 2747.6088 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 5580 | [7 empty] | 2747.6088 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.4 | CPT Central Infrastructure | 1.4.4 CPT Central Infrastructure | 1.4.4.1 | Communications and Timing Systems | 1.4.4.1 Communications and Timing Systems | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.4.1.2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2747.6088 | 1.4.4.1.2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | 1.4.4.1.2.6 | C |  | UW | Shipping costs |  |  | M & S |  |  |  |  | 1 | 0% | 2023-08-15 | 2023-09-11 |  |  |  | assumes joint shipment with 1.4.4.1.1 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 0 | M & S | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.4 | CPT Central Infrastructure | 1.4.4 CPT Central Infrastructure | 1.4.4.1 | Communications and Timing Systems | 1.4.4.1 Communications and Timing Systems | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.4.1.2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | 1.4.4.1.2.8 | C |  | UW | Installation in ICL | Kelley | 0% | Labor Hours | SC | TRUE |  | 50 | 52 | 35% | 2023-12-15 | 2023-12-21 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 |  |  | 15 | [9 empty] | 0 | 0 | 1053 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1053 | 53% | 558.09 | 1754.1765 | 1754.1765 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 4092 | 0 | [5 empty] | 4092 |  | 1754.1765 | Labor - Task | On Ice | 1.4 | CPT | 1.4 CPT | 1.4.4 | CPT Central Infrastructure | 1.4.4 CPT Central Infrastructure | 1.4.4.1 | Communications and Timing Systems | 1.4.4.1 Communications and Timing Systems | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 2d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.4.1.2.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.2.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.2.8 | 0 | 0 | 1754.1765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.2.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.2.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.2.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.2.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.2.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | 1.4.4.1.2.8 | C |  | UW | Deployment to Pole for installation in ICL | Kelley |  | Travel |  | TRUE |  |  | 1 | 0% | 2023-12-15 | 2023-12-21 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 |  | 1200 | [10 empty] | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 53% | 636 | 1836 | 1836 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 1836 | Travel | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.4 | CPT Central Infrastructure | 1.4.4 CPT Central Infrastructure | 1.4.4.1 | Communications and Timing Systems | 1.4.4.1 Communications and Timing Systems | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.4.1.2.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.2.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.2.8 | 0 | 1836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.2.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.2.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.2.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.2.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.1.2.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | 1.4.4.2.1.1 | C |  | UW | Final design | Kelley | 2.885% | Labor Hours | SC |  |  |  | 52 | 35% | 2021-03-01 | 2022-06-17 | [8 empty] | 30 | 30 | [6 empty] | 0 | 0 | 0 | 0 | 2106 | 2106 | 0 | 0 | 0 | 0 | 0 | 0 | 4212 | 53% | 2232.36 | 6724.4464 | 6724.4464 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 11067 | [7 empty] | 6724.4464 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.4 | CPT Central Infrastructure | 1.4.4 CPT Central Infrastructure | 1.4.4.2 | Power systems | 1.4.4.2 Power systems | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 12d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.4.2.1.1 | 0 | 0 | 0 | 0 | 3362.2232 | 3362.2232 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.1.1 | 0 | 0 | 0 | 0 | 1627.8011 | 1627.8011 | 0 | 0 | 0 | 0 | 0 | 0 | 3255.6022 | 1.4.4.2.1.1 | 0 | 0 | 0 | 0 | 569.7304 | 569.7304 | 0 | 0 | 0 | 0 | 0 | 0 | 1139.4608 | 1.4.4.2.1.1 | 0 | 0 | 0 | 0 | 1164.6917 | 1164.6917 | 0 | 0 | 0 | 0 | 0 | 0 | 2329.3834 | 6724.4464 | 1.4.4.2.1.1 | 6724.4464 | 6724.4464 | 0 | 0 | 0 | 0 | 3362.2232 | 6724.4464 | 6724.4464 | 6724.4464 | 6724.4464 | 6724.4464 | 6724.4464 | 6724.4464 | 0 | 0 | 0 | 0 | 3362.2232 | 6724.4464 | 6724.4464 | 6724.4464 | 6724.4464 | 6724.4464 | 6724.4464 | 6724.4464
| 1.4 | 1.4.4.2.1.2 | C |  | UW | Sample procurement and evaluation | Kelley | 2.885% | Labor Hours | SC |  |  | 50 | 52 | 35% | 2022-03-28 | 2022-06-17 | [9 empty] | 20 | 40 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 1404 | 2808 | 0 | 0 | 0 | 0 | 0 | 4212 | 53% | 2232.36 | 6724.4464 | 6724.4464 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 4092 | 12648 | [5 empty] | 12440 |  | 6724.4464 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.4 | CPT Central Infrastructure | 1.4.4 CPT Central Infrastructure | 1.4.4.2 | Power systems | 1.4.4.2 Power systems | cell-link@smartsheet.com | 2021-12-01 14:26 |  | 12d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.4.2.1.2 | 0 | 0 | 0 | 0 | 0 | 2241.4821 | 4482.9643 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.1.2 | 0 | 0 | 0 | 0 | 0 | 1085.2007 | 2170.4015 | 0 | 0 | 0 | 0 | 0 | 3255.6022 | 1.4.4.2.1.2 | 0 | 0 | 0 | 0 | 0 | 379.8203 | 759.6405 | 0 | 0 | 0 | 0 | 0 | 1139.4608 | 1.4.4.2.1.2 | 0 | 0 | 0 | 0 | 0 | 776.4611 | 1552.9223 | 0 | 0 | 0 | 0 | 0 | 2329.3834 | 6724.4464 | 1.4.4.2.1.2 | 6724.4464 | 9484.4464 | 0 | 0 | 0 | 0 | 0 | 2241.4821 | 6724.4464 | 6724.4464 | 6724.4464 | 6724.4464 | 6724.4464 | 6724.4464 | 0 | 0 | 0 | 0 | 0 | 2241.4821 | 6724.4464 | 6724.4464 | 9484.4464 | 9484.4464 | 9484.4464 | 9484.4464
| 1.4 | 1.4.4.2.1.2 | C |  | UW | DC power supply chassis (1) |  |  | CapEx |  |  | CP |  | 1 | 0% | 2022-03-28 | 2022-06-17 | [12 empty] | 560 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 560 | 0 | 0 | 0 | 560 | 53% | 0 | 560 | 560 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 560 | CapEx | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.4 | CPT Central Infrastructure | 1.4.4 CPT Central Infrastructure | 1.4.4.2 | Power systems | 1.4.4.2 Power systems | cell-link@smartsheet.com | 2021-12-01 14:26 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.4.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 560 | 0 | 0 | 0 | 1.4.4.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 560 | 0 | 0 | 0 | 560 | 1.4.4.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 560 | 1.4.4.2.1.2 | 560 | 2760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 560 | 560 | 560 | 560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2760 | 2760 | 2760 | 2760
| 1.4 | 1.4.4.2.1.2 | C |  | UW | 48V DC power supply modules (5) |  |  | CapEx |  |  | CP |  | 1 | 0% | 2022-03-28 | 2022-06-17 | [12 empty] | 2200 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2200 | 0 | 0 | 0 | 2200 | 53% | 0 | 2200 | 2200 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 2200 | CapEx | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.4 | CPT Central Infrastructure | 1.4.4 CPT Central Infrastructure | 1.4.4.2 | Power systems | 1.4.4.2 Power systems | cell-link@smartsheet.com | 2021-12-01 14:26 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.4.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2200 | 0 | 0 | 0 | 1.4.4.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2200 | 0 | 0 | 0 | 2200 | 1.4.4.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2200 | 1.4.4.2.1.2 | 2200 | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2200 | 2200 | 2200 | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2200 | 2200 | 2200 | 2200
| 1.4 | 1.4.4.2.1.3 | C |  | UW | Final design review | Kelley | 1.923% | Labor Hours | SC |  |  | 50 | 52 | 35% | 2022-06-20 | 2022-06-24 | [12 empty] | 40 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2808 | 0 | 0 | 0 | 2808 | 53% | 1488.24 | 4482.9643 | 4482.9643 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 4092 | 18972 | [5 empty] | 4092 |  | 4482.9643 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.4 | CPT Central Infrastructure | 1.4.4 CPT Central Infrastructure | 1.4.4.2 | Power systems | 1.4.4.2 Power systems | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 18d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.4.2.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4482.9643 | 0 | 0 | 0 | 1.4.4.2.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2170.4015 | 0 | 0 | 0 | 2170.4015 | 1.4.4.2.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 759.6405 | 0 | 0 | 0 | 759.6405 | 1.4.4.2.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1552.9223 | 0 | 0 | 0 | 1552.9223 | 4482.9643 | 1.4.4.2.1.3 | 4482.9643 | 4482.9643 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4482.9643 | 4482.9643 | 4482.9643 | 4482.9643 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4482.9643 | 4482.9643 | 4482.9643 | 4482.9643
| 1.4 | 1.4.4.2.1.4 | C |  | UW | Procurement | Kelley | 1.538% | Labor Hours | SC |  |  | 100 | 52 | 35% | 2022-06-27 | 2022-09-16 | [13 empty] | 16 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1123.2 | 561.6 | 561.6 | 2246.4 | 53% | 1190.592 | 3586.3714 | -19298.8036 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 10416 | 21585.2256 | 22327 | 22885.175 |  | 0 |  | 54205 |  | 3586.3714 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.4 | CPT Central Infrastructure | 1.4.4 CPT Central Infrastructure | 1.4.4.2 | Power systems | 1.4.4.2 Power systems | cell-link@smartsheet.com | 2021-12-01 14:26 |  | 1431d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.4.2.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1793.1857 | 896.5929 | 896.5929 | 1.4.4.2.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 868.1606 | 434.0803 | 434.0803 | 1736.3212 | 1.4.4.2.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 303.8562 | 151.9281 | 151.9281 | 607.7124 | 1.4.4.2.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 621.1689 | 310.5845 | 310.5845 | 1242.3378 | 3586.3714 | 1.4.4.2.1.4 | 3586.3714 | 20146.3714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1793.1857 | 2689.7786 | 3586.3714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1793.1857 | 10969.7786 | 20146.3714
| 1.4 | 1.4.4.2.1.4 | C |  | UW | DC power supply chassis for NTS + SPTS (3) |  |  | CapEx |  |  | CP |  | 1 | 0% | 2022-06-27 | 2022-09-16 | [14 empty] | 1680 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1680 | 0 | 1680 | 53% | 0 | 1680 | 1680 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 1680 | CapEx | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.4 | CPT Central Infrastructure | 1.4.4 CPT Central Infrastructure | 1.4.4.2 | Power systems | 1.4.4.2 Power systems | cell-link@smartsheet.com | 2021-12-01 14:26 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.4.2.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1680 | 0 | 1.4.4.2.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1680 | 0 | 1680 | 1.4.4.2.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1680 | 1.4.4.2.1.4 | 1680 | 16560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1680 | 1680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8280 | 16560
| 1.4 | 1.4.4.2.1.4 | C |  | UW | 48V DC power supply modules for NTS + SPTS (15) |  |  | CapEx |  |  | CP |  | 1 | 0% | 2022-06-27 | 2022-09-16 | [14 empty] | 6600 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6600 | 0 | 6600 | 53% | 0 | 6600 | 6600 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 6600 | CapEx | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.4 | CPT Central Infrastructure | 1.4.4 CPT Central Infrastructure | 1.4.4.2 | Power systems | 1.4.4.2 Power systems | cell-link@smartsheet.com | 2021-12-01 14:26 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.4.2.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6600 | 0 | 1.4.4.2.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6600 | 0 | 6600 | 1.4.4.2.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6600 | 1.4.4.2.1.4 | 6600 | 14880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6600 | 6600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6600 | 14880
| 1.4 | 1.4.4.2.1.4 | C |  | UW | DC power supply chassis for ICL (3) |  |  | CapEx |  |  | CP |  | 1 | 0% | 2022-06-27 | 2022-09-16 | [15 empty] | 1680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1680 | 1680 | 53% | 0 | 1680 | 1680 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 1680 | CapEx | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.4 | CPT Central Infrastructure | 1.4.4 CPT Central Infrastructure | 1.4.4.2 | Power systems | 1.4.4.2 Power systems | cell-link@smartsheet.com | 2021-12-01 14:26 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.4.2.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1680 | 1.4.4.2.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1680 | 1680 | 1.4.4.2.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1680 | 1.4.4.2.1.4 | 1680 | 8280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8280
| 1.4 | 1.4.4.2.1.4 | C |  | UW | 48V DC power supply modules for ICL (15) |  |  | CapEx |  |  | CP |  | 1 | 0% | 2022-06-27 | 2022-09-16 | [15 empty] | 6600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6600 | 6600 | 53% | 0 | 6600 | 6600 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 6600 | CapEx | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.4 | CPT Central Infrastructure | 1.4.4 CPT Central Infrastructure | 1.4.4.2 | Power systems | 1.4.4.2 Power systems | cell-link@smartsheet.com | 2021-12-01 14:26 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.4.2.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6600 | 1.4.4.2.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6600 | 6600 | 1.4.4.2.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6600 | 1.4.4.2.1.4 | 6600 | 6600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6600
| 1.4 | 1.4.4.2.1.5 | C |  | UW | Installation and testing at NTS | Kelley | 0.7212% | Labor Hours | SC |  |  | 1 | 52 | 35% | 2022-09-23 | 2022-10-20 | [15 empty] | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1053 | 1053 | 53% | 558.09 | 1681.1116 | 906.1116 | 10 | [11 empty] | 702 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 702 | 53% | 372.06 | 1144.837 | 369.837 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 775 | 775 | 775 | 775 |  | 775 |  | 3875 |  | 2825.9486 | Labor - Task | On Ice | 1.4 | CPT | 1.4 CPT | 1.4.4 | CPT Central Infrastructure | 1.4.4 CPT Central Infrastructure | 1.4.4.2 | Power systems | 1.4.4.2 Power systems | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1431d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.4.2.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1681.1116 | 1.4.4.2.1.5 | 1144.837 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 813.9006 | 813.9006 | 1.4.4.2.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 284.8652 | 284.8652 | 1.4.4.2.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 582.3458 | 582.3458 | 1681.1116 | 1.4.4.2.1.5 | 1681.1116 | 1681.1116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1681.1116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1681.1116
| 1.4 | 1.4.4.2.2.1 | C |  | UW | Final design | Kelley | 5.288% | Labor Hours | SC |  |  | 1 | 52 | 35% | 2021-05-01 | 2022-06-17 | [9 empty] | 80 | 30 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 5616 | 2106 | 0 | 0 | 0 | 0 | 0 | 7722 | 53% | 4092.66 | 12328.1517 | 6748.1517 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | -2790 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 5580 | 5580 | 5580 | 5580 |  | 2790 |  | 20155 |  | 12328.1517 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.4 | CPT Central Infrastructure | 1.4.4 CPT Central Infrastructure | 1.4.4.2 | Power systems | 1.4.4.2 Power systems | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1431d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.4.2.2.1 | 0 | 0 | 0 | 0 | 0 | 8965.9285 | 3362.2232 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.2.1 | 0 | 0 | 0 | 0 | 0 | 4340.803 | 1627.8011 | 0 | 0 | 0 | 0 | 0 | 5968.6041 | 1.4.4.2.2.1 | 0 | 0 | 0 | 0 | 0 | 1519.281 | 569.7304 | 0 | 0 | 0 | 0 | 0 | 2089.0114 | 1.4.4.2.2.1 | 0 | 0 | 0 | 0 | 0 | 3105.8445 | 1164.6917 | 0 | 0 | 0 | 0 | 0 | 4270.5362 | 12328.1517 | 1.4.4.2.2.1 | 12328.1517 | 30327.8755 | 0 | 0 | 0 | 0 | 0 | 8965.9285 | 12328.1517 | 12328.1517 | 12328.1517 | 12328.1517 | 12328.1517 | 12328.1517 | 0 | 0 | 0 | 0 | 0 | 20965.7444 | 30327.8755 | 30327.8755 | 30327.8755 | 30327.8755 | 30327.8755 | 30327.8755
| 1.4 | 1.4.4.2.2.1 | C |  | PSL | Final design |  | 8.333% | Labor Hours | EN |  |  |  | 115 | 0% | 2021-05-01 | 2022-06-17 | [9 empty] | 100 | 50 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 11500 | 5750 | 0 | 0 | 0 | 0 | 0 | 17250 | 0% | 0 | 17999.7238 | 17999.7238 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | [9 empty] | 17999.7238 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.4 | CPT Central Infrastructure | 1.4.4 CPT Central Infrastructure | 1.4.4.2 | Power systems | 1.4.4.2 Power systems | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.4.2.2.1 | 0 | 0 | 0 | 0 | 0 | 11999.8159 | 5999.9079 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.2.1 | 0 | 0 | 0 | 0 | 0 | 11999.8159 | 5999.9079 | 0 | 0 | 0 | 0 | 0 | 17999.7238 | 1.4.4.2.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17999.7238 | 1.4.4.2.2.1 | 17999.7238 | 17999.7238 | 0 | 0 | 0 | 0 | 0 | 11999.8159 | 17999.7238 | 17999.7238 | 17999.7238 | 17999.7238 | 17999.7238 | 17999.7238 | 0 | 0 | 0 | 0 | 0 | 11999.8159 | 17999.7238 | 17999.7238 | 17999.7238 | 17999.7238 | 17999.7238 | 17999.7238
| 1.4 | 1.4.4.2.2.2 | C |  | UW | Prototype production and evaluation | Kelley | 3.846% | Labor Hours | SC |  |  |  | 52 | 35% | 2022-04-25 | 2022-06-17 |  | TRUE | [8 empty] | 20 | 40 | 20 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1404 | 2808 | 1404 | 0 | 0 | 0 | 5616 | 53% | 2976.48 | 8965.9285 | 8965.9285 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 10075 | [7 empty] | 8965.9285 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.4 | CPT Central Infrastructure | 1.4.4 CPT Central Infrastructure | 1.4.4.2 | Power systems | 1.4.4.2 Power systems | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 915d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.4.2.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 2241.4821 | 4482.9643 | 2241.4821 | 0 | 0 | 0 | 1.4.4.2.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 1085.2007 | 2170.4015 | 1085.2007 | 0 | 0 | 0 | 4340.803 | 1.4.4.2.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 379.8203 | 759.6405 | 379.8203 | 0 | 0 | 0 | 1519.281 | 1.4.4.2.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 776.4611 | 1552.9223 | 776.4611 | 0 | 0 | 0 | 3105.8445 | 8965.9285 | 1.4.4.2.2.2 | 8965.9285 | 10840.9285 | 0 | 0 | 0 | 0 | 0 | 0 | 2241.4821 | 6724.4464 | 8965.9285 | 8965.9285 | 8965.9285 | 8965.9285 | 0 | 0 | 0 | 0 | 0 | 0 | 2241.4821 | 6724.4464 | 10840.9285 | 10840.9285 | 10840.9285 | 10840.9285
| 1.4 | 1.4.4.2.2.2 | C |  | UW | Custom power fanout prototype |  |  | CapEx |  |  | EE |  | 1 | 0% | 2022-04-25 | 2022-06-17 | [12 empty] | 1500 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 1500 | 53% | 0 | 1500 | 1500 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 1500 | CapEx | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.4 | CPT Central Infrastructure | 1.4.4 CPT Central Infrastructure | 1.4.4.2 | Power systems | 1.4.4.2 Power systems | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.4.2.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 1.4.4.2.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 1500 | 1.4.4.2.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 1.4.4.2.2.2 | 1500 | 1875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 1500 | 1500 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1875 | 1875 | 1875 | 1875
| 1.4 | 1.4.4.2.2.2 | C |  | UW | Power fanout cables (5) |  |  | CapEx |  |  | EE |  | 1 | 0% | 2022-04-25 | 2022-06-17 | [12 empty] | 375 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 375 | 0 | 0 | 0 | 375 | 53% | 0 | 375 | 375 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 375 | CapEx | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.4 | CPT Central Infrastructure | 1.4.4 CPT Central Infrastructure | 1.4.4.2 | Power systems | 1.4.4.2 Power systems | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.4.2.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 375 | 0 | 0 | 0 | 1.4.4.2.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 375 | 0 | 0 | 0 | 375 | 1.4.4.2.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 375 | 1.4.4.2.2.2 | 375 | 375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 375 | 375 | 375 | 375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 375 | 375 | 375 | 375
| 1.4 | 1.4.4.2.2.3 | C |  | UW | Final design review | Kelley | 1.923% | Labor Hours | SC |  |  | 1 | 52 | 35% | 2022-06-20 | 2022-06-24 | [12 empty] | 40 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2808 | 0 | 0 | 0 | 2808 | 53% | 1488.24 | 4482.9643 | 3707.9643 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | -775 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 775 | 775 | 775 | 775 |  | 775 |  | 3875 |  | 4482.9643 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.4 | CPT Central Infrastructure | 1.4.4 CPT Central Infrastructure | 1.4.4.2 | Power systems | 1.4.4.2 Power systems | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 695d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.4.2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4482.9643 | 0 | 0 | 0 | 1.4.4.2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2170.4015 | 0 | 0 | 0 | 2170.4015 | 1.4.4.2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 759.6405 | 0 | 0 | 0 | 759.6405 | 1.4.4.2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1552.9223 | 0 | 0 | 0 | 1552.9223 | 4482.9643 | 1.4.4.2.2.3 | 4482.9643 | 4482.9643 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4482.9643 | 4482.9643 | 4482.9643 | 4482.9643 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4482.9643 | 4482.9643 | 4482.9643 | 4482.9643
| 1.4 | 1.4.4.2.2.4 | C |  | UW | Production | Kelley | 2.885% | Labor Hours | SC |  |  | 1 | 52 | 35% | 2022-06-27 | 2022-09-02 |  | TRUE | [10 empty] | 40 | 20 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2808 | 1404 | 0 | 0 | 4212 | 53% | 2232.36 | 6724.4464 | 6724.4464 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 30690 | 5580 | [5 empty] | 30690 |  | 6724.4464 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.4 | CPT Central Infrastructure | 1.4.4 CPT Central Infrastructure | 1.4.4.2 | Power systems | 1.4.4.2 Power systems | cell-link@smartsheet.com | 2021-12-01 14:26 |  | 695d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.4.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4482.9643 | 2241.4821 | 0 | 0 | 1.4.4.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2170.4015 | 1085.2007 | 0 | 0 | 3255.6022 | 1.4.4.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 759.6405 | 379.8203 | 0 | 0 | 1139.4608 | 1.4.4.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1552.9223 | 776.4611 | 0 | 0 | 2329.3834 | 6724.4464 | 1.4.4.2.2.4 | 6724.4464 | 12349.4464 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4482.9643 | 6724.4464 | 6724.4464 | 6724.4464 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4482.9643 | 6724.4464 | 8599.4464 | 12349.4464
| 1.4 | 1.4.4.2.2.4 | C |  | UW | Custom power fanout unit for NTS |  |  | CapEx |  |  | EE |  | 1 | 0% | 2022-06-27 | 2022-09-02 | [14 empty] | 1500 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 1500 | 53% | 0 | 1500 | 1500 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 1500 | CapEx | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.4 | CPT Central Infrastructure | 1.4.4 CPT Central Infrastructure | 1.4.4.2 | Power systems | 1.4.4.2 Power systems | cell-link@smartsheet.com | 2021-12-01 14:26 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.4.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 1.4.4.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 1500 | 1.4.4.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 1.4.4.2.2.4 | 1500 | 5625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1875 | 5625
| 1.4 | 1.4.4.2.2.4 | C |  | UW | Power fanout cables for NTS (5) |  |  | CapEx |  |  | EE |  | 1 | 0% | 2022-06-27 | 2022-09-02 | [14 empty] | 375 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 375 | 0 | 375 | 53% | 0 | 375 | 375 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 375 | CapEx | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.4 | CPT Central Infrastructure | 1.4.4 CPT Central Infrastructure | 1.4.4.2 | Power systems | 1.4.4.2 Power systems | cell-link@smartsheet.com | 2021-12-01 14:26 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.4.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 375 | 0 | 1.4.4.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 375 | 0 | 375 | 1.4.4.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 375 | 1.4.4.2.2.4 | 375 | 4125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 375 | 375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 375 | 4125
| 1.4 | 1.4.4.2.2.4 | C |  | UW | Custom power fanout units for ICL (2) |  |  | CapEx |  |  | EE |  | 1 | 0% | 2022-06-27 | 2022-09-02 | [15 empty] | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 3000 | 53% | 0 | 3000 | 3000 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 3000 | CapEx | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.4 | CPT Central Infrastructure | 1.4.4 CPT Central Infrastructure | 1.4.4.2 | Power systems | 1.4.4.2 Power systems | cell-link@smartsheet.com | 2021-12-01 14:26 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.4.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 1.4.4.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 3000 | 1.4.4.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 1.4.4.2.2.4 | 3000 | 3750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3750
| 1.4 | 1.4.4.2.2.4 | C |  | UW | Power fanout cables for ICL (10) |  |  | CapEx |  |  | EE |  | 1 | 0% | 2022-06-27 | 2022-09-02 | [15 empty] | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 750 | 53% | 0 | 750 | 750 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 750 | CapEx | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.4 | CPT Central Infrastructure | 1.4.4 CPT Central Infrastructure | 1.4.4.2 | Power systems | 1.4.4.2 Power systems | cell-link@smartsheet.com | 2021-12-01 14:26 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.4.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 1.4.4.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 750 | 1.4.4.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 1.4.4.2.2.4 | 750 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750
| 1.4 | 1.4.4.2.2.5 | C |  | UW | Installation and testing at NTS | Kelley | 0.7212% | Labor Hours | SC |  |  | 1 | 52 | 35% | 2022-09-23 | 2022-10-20 | [15 empty] | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1053 | 1053 | 53% | 558.09 | 1681.1116 | 1681.1116 | 10 | [11 empty] | 702 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 702 | 53% | 372.06 | 1144.837 | 1144.837 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 8370 | 8370 | 8370 |  |  |  |  | 16907 |  | 2825.9486 | Labor - Task | On Ice | 1.4 | CPT | 1.4 CPT | 1.4.4 | CPT Central Infrastructure | 1.4.4 CPT Central Infrastructure | 1.4.4.2 | Power systems | 1.4.4.2 Power systems | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 695d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.4.2.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1681.1116 | 1.4.4.2.2.5 | 1144.837 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 813.9006 | 813.9006 | 1.4.4.2.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 284.8652 | 284.8652 | 1.4.4.2.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 582.3458 | 582.3458 | 1681.1116 | 1.4.4.2.2.5 | 1681.1116 | 1681.1116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1681.1116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1681.1116
| 1.4 | 1.4.4.2.3.1 | C |  | UW | Final design | Kelley | 5.769% | Labor Hours | SC |  |  | 1 | 52 | 35% | 2021-05-15 | 2022-06-17 |  | TRUE | [5 empty] | 40 | 40 | 40 | [6 empty] | 0 | 0 | 0 | 2808 | 2808 | 2808 | 0 | 0 | 0 | 0 | 0 | 0 | 8424 | 53% | 4464.72 | 13448.8928 | 13448.8928 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 16000 | 12000 | [5 empty] | 16000 |  | 13448.8928 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.4 | CPT Central Infrastructure | 1.4.4 CPT Central Infrastructure | 1.4.4.2 | Power systems | 1.4.4.2 Power systems | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 695d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.4.2.3.1 | 0 | 0 | 0 | 4482.9643 | 4482.9643 | 4482.9643 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.3.1 | 0 | 0 | 0 | 2170.4015 | 2170.4015 | 2170.4015 | 0 | 0 | 0 | 0 | 0 | 0 | 6511.2044 | 1.4.4.2.3.1 | 0 | 0 | 0 | 759.6405 | 759.6405 | 759.6405 | 0 | 0 | 0 | 0 | 0 | 0 | 2278.9216 | 1.4.4.2.3.1 | 0 | 0 | 0 | 1552.9223 | 1552.9223 | 1552.9223 | 0 | 0 | 0 | 0 | 0 | 0 | 4658.7668 | 13448.8928 | 1.4.4.2.3.1 | 13448.8928 | 13448.8928 | 0 | 0 | 0 | 4482.9643 | 8965.9285 | 13448.8928 | 13448.8928 | 13448.8928 | 13448.8928 | 13448.8928 | 13448.8928 | 13448.8928 | 0 | 0 | 0 | 4482.9643 | 8965.9285 | 13448.8928 | 13448.8928 | 13448.8928 | 13448.8928 | 13448.8928 | 13448.8928 | 13448.8928
| 1.4 | 1.4.4.2.3.2 | C |  | UW | Prototype production and evaluation | Kelley | 1.442% | Labor Hours | SC |  |  |  | 52 | 35% | 2022-03-28 | 2022-06-17 |  | TRUE | [7 empty] | 10 | 10 | 10 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 702 | 702 | 702 | 0 | 0 | 0 | 0 | 2106 | 53% | 1116.18 | 3362.2232 | 3362.2232 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 21700 | [7 empty] | 3362.2232 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.4 | CPT Central Infrastructure | 1.4.4 CPT Central Infrastructure | 1.4.4.2 | Power systems | 1.4.4.2 Power systems | cell-link@smartsheet.com | 2021-12-01 14:27 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.4.2.3.2 | 0 | 0 | 0 | 0 | 0 | 1120.7411 | 1120.7411 | 1120.7411 | 0 | 0 | 0 | 0 | 1.4.4.2.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.3.2 | 0 | 0 | 0 | 0 | 0 | 542.6004 | 542.6004 | 542.6004 | 0 | 0 | 0 | 0 | 1627.8011 | 1.4.4.2.3.2 | 0 | 0 | 0 | 0 | 0 | 189.9101 | 189.9101 | 189.9101 | 0 | 0 | 0 | 0 | 569.7304 | 1.4.4.2.3.2 | 0 | 0 | 0 | 0 | 0 | 388.2306 | 388.2306 | 388.2306 | 0 | 0 | 0 | 0 | 1164.6917 | 3362.2232 | 1.4.4.2.3.2 | 3362.2232 | 4112.2232 | 0 | 0 | 0 | 0 | 0 | 1120.7411 | 2241.4821 | 3362.2232 | 3362.2232 | 3362.2232 | 3362.2232 | 3362.2232 | 0 | 0 | 0 | 0 | 0 | 1870.7411 | 2991.4821 | 4112.2232 | 4112.2232 | 4112.2232 | 4112.2232 | 4112.2232
| 1.4 | 1.4.4.2.3.2 | C |  | UW | Power control unit prototype |  |  | CapEx |  |  | EE |  | 1 | 0% | 2022-03-28 | 2022-06-17 | [9 empty] | 750 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 53% | 0 | 750 | 750 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 750 | CapEx | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.4 | CPT Central Infrastructure | 1.4.4 CPT Central Infrastructure | 1.4.4.2 | Power systems | 1.4.4.2 Power systems | cell-link@smartsheet.com | 2021-12-01 14:27 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.4.2.3.2 | 0 | 0 | 0 | 0 | 0 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.3.2 | 0 | 0 | 0 | 0 | 0 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 1.4.4.2.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 1.4.4.2.3.2 | 750 | 750 | 0 | 0 | 0 | 0 | 0 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 0 | 0 | 0 | 0 | 0 | 750 | 750 | 750 | 750 | 750 | 750 | 750
| 1.4 | 1.4.4.2.3.3 | C |  | UW | Final design review | Kelley | 0.9615% | Labor Hours | SC |  |  |  | 52 | 35% | 2022-06-20 | 2022-06-24 |  | TRUE | [10 empty] | 20 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1404 | 0 | 0 | 0 | 1404 | 53% | 744.12 | 2241.4821 | 2241.4821 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 9300 | [7 empty] | 2241.4821 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.4 | CPT Central Infrastructure | 1.4.4 CPT Central Infrastructure | 1.4.4.2 | Power systems | 1.4.4.2 Power systems | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.4.2.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2241.4821 | 0 | 0 | 0 | 1.4.4.2.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1085.2007 | 0 | 0 | 0 | 1085.2007 | 1.4.4.2.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 379.8203 | 0 | 0 | 0 | 379.8203 | 1.4.4.2.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 776.4611 | 0 | 0 | 0 | 776.4611 | 2241.4821 | 1.4.4.2.3.3 | 2241.4821 | 2241.4821 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2241.4821 | 2241.4821 | 2241.4821 | 2241.4821 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2241.4821 | 2241.4821 | 2241.4821 | 2241.4821
| 1.4 | 1.4.4.2.3.4 | C |  | UW | Production | Kelley | 5.769% | Labor Hours | SC |  |  |  | 52 | 35% | 2022-06-27 | 2022-09-02 |  | TRUE | [10 empty] | 40 | 40 | 40 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2808 | 2808 | 2808 | 0 | 8424 | 53% | 4464.72 | 13448.8928 | 13448.8928 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 5580 | [7 empty] | 13448.8928 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.4 | CPT Central Infrastructure | 1.4.4 CPT Central Infrastructure | 1.4.4.2 | Power systems | 1.4.4.2 Power systems | cell-link@smartsheet.com | 2021-12-01 14:27 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.4.2.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4482.9643 | 4482.9643 | 4482.9643 | 0 | 1.4.4.2.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2170.4015 | 2170.4015 | 2170.4015 | 0 | 6511.2044 | 1.4.4.2.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 759.6405 | 759.6405 | 759.6405 | 0 | 2278.9216 | 1.4.4.2.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1552.9223 | 1552.9223 | 1552.9223 | 0 | 4658.7668 | 13448.8928 | 1.4.4.2.3.4 | 13448.8928 | 15698.8928 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4482.9643 | 8965.9285 | 13448.8928 | 13448.8928 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4482.9643 | 8965.9285 | 15698.8928 | 15698.8928
| 1.4 | 1.4.4.2.3.4 | C |  | UW | Power control unit for NTS |  |  | CapEx |  |  | EE |  | 1 | 0% | 2022-06-27 | 2022-09-02 | [14 empty] | 750 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 0 | 750 | 53% | 0 | 750 | 750 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 750 | CapEx | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.4 | CPT Central Infrastructure | 1.4.4 CPT Central Infrastructure | 1.4.4.2 | Power systems | 1.4.4.2 Power systems | cell-link@smartsheet.com | 2021-12-01 14:27 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.4.2.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 0 | 1.4.4.2.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 0 | 750 | 1.4.4.2.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 1.4.4.2.3.4 | 750 | 2250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2250 | 2250
| 1.4 | 1.4.4.2.3.4 | C |  | UW | Power control units for ICL (2) |  |  | CapEx |  |  | EE |  | 1 | 0% | 2022-06-27 | 2022-09-02 | [14 empty] | 1500 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 1500 | 53% | 0 | 1500 | 1500 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 1500 | CapEx | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.4 | CPT Central Infrastructure | 1.4.4 CPT Central Infrastructure | 1.4.4.2 | Power systems | 1.4.4.2 Power systems | cell-link@smartsheet.com | 2021-12-01 14:27 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.4.2.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 1.4.4.2.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 1500 | 1.4.4.2.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 1.4.4.2.3.4 | 1500 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 1500
| 1.4 | 1.4.4.2.3.5 | C |  | UW | Installation and testing at NTS | Kelley | 0.4808% | Labor Hours | SC |  |  |  | 52 | 35% | 2022-09-23 | 2022-10-20 | [15 empty] | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 702 | 702 | 53% | 372.06 | 1120.7411 | 1120.7411 | 32 |  |  | 10 | [8 empty] | 2246.4 | 0 | 0 | 702 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2948.4 | 53% | 1562.652 | 4808.3154 | 4808.3154 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 | 5400 | [6 empty] | 5929.0565 | Labor - Task | On Ice | 1.4 | CPT | 1.4 CPT | 1.4.4 | CPT Central Infrastructure | 1.4.4 CPT Central Infrastructure | 1.4.4.2 | Power systems | 1.4.4.2 Power systems | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.4.2.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1120.7411 | 1.4.4.2.3.5 | 3663.4784 | 0 | 0 | 1144.837 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 542.6004 | 542.6004 | 1.4.4.2.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 189.9101 | 189.9101 | 1.4.4.2.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 388.2306 | 388.2306 | 1120.7411 | 1.4.4.2.3.5 | 1120.7411 | 1120.7411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1120.7411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1120.7411
| 1.4 | 1.4.4.2.3.5 | C |  | UW | Installation and testing at NTS |  |  | Travel |  |  |  |  | 1 | 0% | 2022-09-23 | 2022-10-20 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | 1800 |  |  | 1800 | [8 empty] | 1800 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3600 | 53% | 1908 | 5508 | 5508 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 5508 | Travel | On Ice | 1.4 | CPT | 1.4 CPT | 1.4.4 | CPT Central Infrastructure | 1.4.4 CPT Central Infrastructure | 1.4.4.2 | Power systems | 1.4.4.2 Power systems | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.4.2.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.3.5 | 2754 | 0 | 0 | 2754 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | 1.4.4.2.4.1 | C |  | UW | Pre-ship review | Kelley | 0% | Labor Hours | SC |  |  | 50 | 52 | 35% | 2022-12-01 | 2022-12-28 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 |  |  | 24 |  | 24 | [7 empty] | 0 | 0 | 1684.8 | 0 | 1684.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3369.6 | 53% | 1785.888 | 5495.2176 | 5495.2176 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 4092 | 0 | [5 empty] | 4092 |  | 5495.2176 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.4 | CPT Central Infrastructure | 1.4.4 CPT Central Infrastructure | 1.4.4.2 | Power systems | 1.4.4.2 Power systems | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 2d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.4.2.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.4.1 | 0 | 0 | 2747.6088 | 0 | 2747.6088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | 1.4.4.2.4.2 | C |  | UW | Shipping to PTH (ComAir? RDD 9/15/23) | Kelley | 0% | Labor Hours | SC |  |  | 50 | 52 | 35% | 2022-12-29 | 2023-01-11 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [5 empty] | 24 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 1684.8 | 0 | 0 | 0 | 0 | 0 | 0 | 1684.8 | 53% | 892.944 | 2747.6088 | 2747.6088 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 10230 | 4743 | [5 empty] | 10230 |  | 2747.6088 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.4 | CPT Central Infrastructure | 1.4.4 CPT Central Infrastructure | 1.4.4.2 | Power systems | 1.4.4.2 Power systems | cell-link@smartsheet.com | 2021-12-01 14:33 |  | 109d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.4.2.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.4.2 | 0 | 0 | 0 | 0 | 0 | 2747.6088 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | 1.4.4.2.4.2 | C |  | UW | Shipping costs |  |  | M & S |  |  |  |  | 1 | 0% | 2022-12-29 | 2023-01-11 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [5 empty] | 500 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 53% | 265 | 765 | 765 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 765 | M & S | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.4 | CPT Central Infrastructure | 1.4.4 CPT Central Infrastructure | 1.4.4.2 | Power systems | 1.4.4.2 Power systems | cell-link@smartsheet.com | 2021-12-01 14:33 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.4.2.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.4.2 | 0 | 0 | 0 | 0 | 0 | 765 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | 1.4.4.2.4.4 | C |  | UW | Installation in ICL | Kelley | 0% | Labor Hours | SC |  |  | 50 | 52 | 35% | 2023-12-01 | 2023-12-14 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 |  |  | 50 | [9 empty] | 0 | 0 | 3510 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3510 | 53% | 1860.3 | 5847.255 | 5847.255 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 5115 | 22134 | [5 empty] | 5115 |  | 5847.255 | Labor - Task | On Ice | 1.4 | CPT | 1.4 CPT | 1.4.4 | CPT Central Infrastructure | 1.4.4 CPT Central Infrastructure | 1.4.4.2 | Power systems | 1.4.4.2 Power systems | cell-link@smartsheet.com | 2021-12-01 14:33 |  | 105d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.4.2.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.4.4 | 0 | 0 | 5847.255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4.2.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | 1.4.5.2 | P |  | MSU | Miscellaneous supplies |  |  | M & S |  |  |  |  | 1 | 0% | 2022-03-15 | 2022-05-27 | [9 empty] | 125 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 125 | 55% | 68.75 | 193.75 | 193.75 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | [9 empty] | 193.75 | M & S | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.5 | Northern Test System | 1.4.5 Northern Test System | 1.4.5.2 | NTS Cables | 1.4.5.2 NTS Cables | cell-link@smartsheet.com | 2021-12-01 14:33 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.5.2 | 0 | 0 | 0 | 0 | 0 | 193.75 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.5.2 | 0 | 0 | 0 | 0 | 0 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 125 | 1.4.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.5.2 | 0 | 0 | 0 | 0 | 0 | 68.75 | 0 | 0 | 0 | 0 | 0 | 0 | 68.75 | 193.75 | 1.4.5.2 | 193.75 | 193.75 | 0 | 0 | 0 | 0 | 0 | 193.75 | 193.75 | 193.75 | 193.75 | 193.75 | 193.75 | 193.75 | 0 | 0 | 0 | 0 | 0 | 193.75 | 193.75 | 193.75 | 193.75 | 193.75 | 193.75 | 193.75
| 1.4 | 1.4.5.2.1 | C |  | MSU | Facility construction | Ng, Ferguson | 4.808% | Labor Hours | EN |  |  |  | 60 | 0% | 2022-03-15 | 2022-04-29 | [9 empty] | 40 | 60 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 2400 | 3600 | 0 | 0 | 0 | 0 | 0 | 6000 | 55% | 3300 | 9704.1989 | 9704.1989 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 |  | 11067 | [7 empty] | 9704.1989 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.5 | Northern Test System | 1.4.5 Northern Test System | 1.4.5.2 | NTS Cables | 1.4.5.2 NTS Cables | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 12d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.5.2.1 | 0 | 0 | 0 | 0 | 0 | 3881.6796 | 5822.5194 | 0 | 0 | 0 | 0 | 0 | 1.4.5.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.5.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.5.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.5.2.1 | 0 | 0 | 0 | 0 | 0 | 2504.3094 | 3756.4641 | 0 | 0 | 0 | 0 | 0 | 6260.7735 | 1.4.5.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.5.2.1 | 0 | 0 | 0 | 0 | 0 | 1377.3702 | 2066.0553 | 0 | 0 | 0 | 0 | 0 | 3443.4254 | 9704.1989 | 1.4.5.2.1 | 9704.1989 | 15911.0046 | 0 | 0 | 0 | 0 | 0 | 3881.6796 | 9704.1989 | 9704.1989 | 9704.1989 | 9704.1989 | 9704.1989 | 9704.1989 | 0 | 0 | 0 | 0 | 0 | 5950.6148 | 15911.0046 | 15911.0046 | 15911.0046 | 15911.0046 | 15911.0046 | 15911.0046
TRUE | 1.4 | 1.4.5.2.1 | C |  | MSU | Facility construction | Halliday | 5.769% | Labor Hours | PO |  |  |  | 26 | 23% | 2022-03-15 | 2022-04-29 | [9 empty] | 40 | 80 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 1279.2 | 2558.4 | 0 | 0 | 0 | 0 | 0 | 3837.6 | 55% | 2110.68 | 6206.8056 | 6206.8056 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | [9 empty] | 6206.8056 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.5 | Northern Test System | 1.4.5 Northern Test System | 1.4.5.2 |  | 1.4.5.2 | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.5.2.1 | 0 | 0 | 0 | 0 | 0 | 2068.9352 | 4137.8704 | 0 | 0 | 0 | 0 | 0 | 1.4.5.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.5.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.5.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.5.2.1 | 0 | 0 | 0 | 0 | 0 | 1085.2007 | 2170.4015 | 0 | 0 | 0 | 0 | 0 | 3255.6022 | 1.4.5.2.1 | 0 | 0 | 0 | 0 | 0 | 249.5962 | 499.1923 | 0 | 0 | 0 | 0 | 0 | 748.7885 | 1.4.5.2.1 | 0 | 0 | 0 | 0 | 0 | 734.1383 | 1468.2766 | 0 | 0 | 0 | 0 | 0 | 2202.4149 | 6206.8056 | 1.4.5.2.1 | 6206.8056 | 6206.8056 | 0 | 0 | 0 | 0 | 0 | 2068.9352 | 6206.8056 | 6206.8056 | 6206.8056 | 6206.8056 | 6206.8056 | 6206.8056 | 0 | 0 | 0 | 0 | 0 | 2068.9352 | 6206.8056 | 6206.8056 | 6206.8056 | 6206.8056 | 6206.8056 | 6206.8056
| 1.4 | 1.4.5.2.1 | C |  | MSU | Support structures for NTS quads |  |  | M & S |  |  |  |  | 1 | 0% | 2022-03-15 | 2022-04-29 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | [9 empty] | 0 | M & S | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.5 | Northern Test System | 1.4.5 Northern Test System | 1.4.5.2 | NTS Cables | 1.4.5.2 NTS Cables | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.5.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.5.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.5.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.5.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.5.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.5.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.5.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.5.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | 1.4.5.2.2 | C |  | MSU | Installation of NTS quads | Halliday | 1.923% | Labor Hours | PO |  |  | 50 | 26 | 23% | 2022-05-02 | 2022-05-27 | [11 empty] | 40 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1279.2 | 0 | 0 | 0 | 0 | 1279.2 | 55% | 703.56 | 2068.9352 | 2068.9352 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 4092 | 12648 | [5 empty] | 12440 |  | 2068.9352 | Labor - Task | On Ice | 1.4 | CPT | 1.4 CPT | 1.4.5 | Northern Test System | 1.4.5 Northern Test System | 1.4.5.2 | NTS Cables | 1.4.5.2 NTS Cables | cell-link@smartsheet.com | 2021-12-01 14:33 |  | 12d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.5.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2068.9352 | 0 | 0 | 0 | 0 | 1.4.5.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.5.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.5.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.5.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1085.2007 | 0 | 0 | 0 | 0 | 1085.2007 | 1.4.5.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 249.5962 | 0 | 0 | 0 | 0 | 249.5962 | 1.4.5.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 734.1383 | 0 | 0 | 0 | 0 | 734.1383 | 2068.9352 | 1.4.5.2.2 | 2068.9352 | 2068.9352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2068.9352 | 2068.9352 | 2068.9352 | 2068.9352 | 2068.9352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2068.9352 | 2068.9352 | 2068.9352 | 2068.9352 | 2068.9352
| 1.4 | 1.4.5.3 | P |  | MSU | Miscellaneous supplies |  |  | M & S |  |  |  |  | 1 | 0% | 2021-01-01 | 2021-10-29 |  |  |  |  | 125 | [11 empty] | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125 | 55% | 68.75 | 193.75 | 193.75 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | [9 empty] | 193.75 | M & S | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.5 | Northern Test System | 1.4.5 Northern Test System | 1.4.5.3 | NTS dark boxes | 1.4.5.3 NTS dark boxes | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.5.3 | 193.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.5.3 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125 | 1.4.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.5.3 | 68.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68.75 | 193.75 | 1.4.5.3 | 193.75 | 193.75 | 193.75 | 193.75 | 193.75 | 193.75 | 193.75 | 193.75 | 193.75 | 193.75 | 193.75 | 193.75 | 193.75 | 193.75 | 193.75 | 193.75 | 193.75 | 193.75 | 193.75 | 193.75 | 193.75 | 193.75 | 193.75 | 193.75 | 193.75 | 193.75
| 1.4 | 1.4.5.3.1 | C |  | MSU | Order materials | Halliday | 0% | Labor Hours | PO |  |  | 50 | 26 | 23% | 2021-01-01 | 2021-01-29 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 4092 | 18972 | [5 empty] | 4092 |  | 0 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.5 | Northern Test System | 1.4.5 Northern Test System | 1.4.5.3 | NTS dark boxes | 1.4.5.3 NTS dark boxes | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 18d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.5.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.5.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.5.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.5.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.5.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.5.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.5.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.5.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | 1.4.5.3.1 | C |  | MSU | Construction materials for dark barrels |  |  | M & S |  |  |  |  | 1 | 0% | 2021-01-01 | 2021-01-29 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | [9 empty] | 0 | M & S | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.5 | Northern Test System | 1.4.5 Northern Test System | 1.4.5.3 | NTS dark boxes | 1.4.5.3 NTS dark boxes | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.5.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.5.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.5.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.5.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.5.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.5.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.5.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.5.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | 1.4.5.3.2 | C |  | MSU | Construction | Halliday | 1.923% | Labor Hours | PO |  |  | 100 | 26 | 23% | 2021-02-01 | 2021-10-29 |  |  |  |  | 40 | [11 empty] | 1279.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1279.2 | 55% | 703.56 | 2068.9352 | -20816.2398 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 10416 | 21585.2256 | 22327 | 22885.175 |  | 0 |  | 54205 |  | 2068.9352 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.5 | Northern Test System | 1.4.5 Northern Test System | 1.4.5.3 | NTS dark boxes | 1.4.5.3 NTS dark boxes | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1431d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.5.3.2 | 2068.9352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.5.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.5.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.5.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.5.3.2 | 1085.2007 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1085.2007 | 1.4.5.3.2 | 249.5962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 249.5962 | 1.4.5.3.2 | 734.1383 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 734.1383 | 2068.9352 | 1.4.5.3.2 | 2068.9352 | 3179.0956 | 2068.9352 | 2068.9352 | 2068.9352 | 2068.9352 | 2068.9352 | 2068.9352 | 2068.9352 | 2068.9352 | 2068.9352 | 2068.9352 | 2068.9352 | 2068.9352 | 3179.0956 | 3179.0956 | 3179.0956 | 3179.0956 | 3179.0956 | 3179.0956 | 3179.0956 | 3179.0956 | 3179.0956 | 3179.0956 | 3179.0956 | 3179.0956
TRUE | 1.4 | 1.4.5.3.2 | C |  | MSU | Construction | Markel | 1.923% | Labor Hours | UG |  |  |  | 13 | 32% | 2021-02-01 | 2021-10-29 |  |  |  |  | 40 | [11 empty] | 686.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 686.4 | 55% | 377.52 | 1110.1604 | 1110.1604 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | [9 empty] | 1110.1604 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.5 | Northern Test System | 1.4.5 Northern Test System | 1.4.5.3 | NTS dark boxes | 1.4.5.3 NTS dark boxes | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.5.3.2 | 1110.1604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.5.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.5.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.5.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.5.3.2 | 542.6004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 542.6004 | 1.4.5.3.2 | 173.6321 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 173.6321 | 1.4.5.3.2 | 393.9279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 393.9279 | 1110.1604 | 1.4.5.3.2 | 1110.1604 | 1110.1604 | 1110.1604 | 1110.1604 | 1110.1604 | 1110.1604 | 1110.1604 | 1110.1604 | 1110.1604 | 1110.1604 | 1110.1604 | 1110.1604 | 1110.1604 | 1110.1604 | 1110.1604 | 1110.1604 | 1110.1604 | 1110.1604 | 1110.1604 | 1110.1604 | 1110.1604 | 1110.1604 | 1110.1604 | 1110.1604 | 1110.1604 | 1110.1604
| 1.4 | 1.4.5.4.1 | C |  | MSU | Commissioning | Halliday | 0% | Labor Hours | PO |  |  | 1 | 26 | 23% | 2021-01-01 | 2021-05-31 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | -5580 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | -2790 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 5580 | 5580 | 5580 | 5580 |  | 2790 |  | 20155 |  | 0 | Labor - Task | On Ice | 1.4 | CPT | 1.4 CPT | 1.4.5 | Northern Test System | 1.4.5 Northern Test System | 1.4.5.4 | NTS Operations | 1.4.5.4 NTS Operations | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1431d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.5.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.5.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.5.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.5.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.5.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.5.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.5.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.5.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | 1.4.5.4.1 | C |  | MSU | Commissioning | Ng | 0% | Labor Hours | EN |  |  |  | 60 | 0% | 2021-01-01 | 2021-05-31 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0 | 0 | [9 empty] | 0 | Labor - Task | On Ice | 1.4 | CPT | 1.4 CPT | 1.4.5 | Northern Test System | 1.4.5 Northern Test System | 1.4.5.4 | NTS Operations | 1.4.5.4 NTS Operations | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.5.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.5.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.5.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.5.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.5.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.5.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.5.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.5.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | 1.4.5.4.3 | C |  | MSU | NTS Operations | Ng | 23.08% | Labor Hours | EN | TRUE |  | 1 | 60 | 0% | 2021-06-02 | 2025-10-01 |  |  |  |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400 | 28800 | 55% | 15840 | 46580.1548 | 45805.1548 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400 | 28800 | 55% | 15840 | 47581.6282 | 46806.6282 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400 | 28800 | 55% | 15840 | 48604.6332 | 48604.6332 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400 | 28800 | 55% | 15840 | 49649.6328 | 775 | 775 | 775 | 775 |  | 775 |  | 3875 |  | 192416.049 | Labor - Task | Off Ice | 1.4 | CPT | 1.4 CPT | 1.4.5 | Northern Test System | 1.4.5 Northern Test System | 1.4.5.4 | NTS Operations | 1.4.5.4 NTS Operations | cell-link@smartsheet.com | 2021-12-01 14:33 |  | 695d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.4.5.4.3 | 3881.6796 | 3881.6796 | 3881.6796 | 3881.6796 | 3881.6796 | 3881.6796 | 3881.6796 | 3881.6796 | 3881.6796 | 3881.6796 | 3881.6796 | 3881.6796 | 1.4.5.4.3 | 3965.1357 | 3965.1357 | 3965.1357 | 3965.1357 | 3965.1357 | 3965.1357 | 3965.1357 | 3965.1357 | 3965.1357 | 3965.1357 | 3965.1357 | 3965.1357 | 1.4.5.4.3 | 4050.3861 | 4050.3861 | 4050.3861 | 4050.3861 | 4050.3861 | 4050.3861 | 4050.3861 | 4050.3861 | 4050.3861 | 4050.3861 | 4050.3861 | 4050.3861 | 1.4.5.4.3 | 4137.4694 | 4137.4694 | 4137.4694 | 4137.4694 | 4137.4694 | 4137.4694 | 4137.4694 | 4137.4694 | 4137.4694 | 4137.4694 | 4137.4694 | 4137.4694 | 1.4.5.4.3 | 2504.3094 | 2504.3094 | 2504.3094 | 2504.3094 | 2504.3094 | 2504.3094 | 2504.3094 | 2504.3094 | 2504.3094 | 2504.3094 | 2504.3094 | 2504.3094 | 30051.7128 | 1.4.5.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.5.4.3 | 1377.3702 | 1377.3702 | 1377.3702 | 1377.3702 | 1377.3702 | 1377.3702 | 1377.3702 | 1377.3702 | 1377.3702 | 1377.3702 | 1377.3702 | 1377.3702 | 16528.442 | 46580.1548 | 1.4.5.4.3 | 46580.1548 | 46580.1548 | 3881.6796 | 7763.3591 | 11645.0387 | 15526.7183 | 19408.3979 | 23290.0774 | 27171.757 | 31053.4366 | 34935.1161 | 38816.7957 | 42698.4753 | 46580.1548 | 3881.6796 | 7763.3591 | 11645.0387 | 15526.7183 | 19408.3979 | 23290.0774 | 27171.757 | 31053.4366 | 34935.1161 | 38816.7957 | 42698.4753 | 46580.1548
| 1.5 | 1.5.3.1.1 | C |  | UA | Simulation Studies |  | 0% | Labor Hours | PO |  |  | 30 | 30 | 17.38% | 2018-10-01 | 2023-09-18 |  | TRUE |  | zeroed postdoc, needed later years when we have schedule approved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49% | 0 | 0 | -31830 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 3063.618 | 3063.618 | 3063.618 | 3063.618 | 3063.618 | 3063.618 | 3063.618 | 3063.618 | 3063.618 | 3063.618 | 3063.618 | 3063.618 | 36763.416 | 49% | 18014.0738 | 58387.145 | 50270.145 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 3063.618 | 3063.618 | 3063.618 | 3063.618 | 3063.618 | 3063.618 | 3063.618 | 3063.618 | 3063.618 | 3063.618 | 3063.618 | 3063.618 | 36763.416 | 49% | 18014.0738 | 59642.4686 | 59642.4686 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 3063.618 | 3063.618 | 3063.618 | 3063.618 | 3063.618 | 3063.618 | 3063.618 | 3063.618 | 3063.618 | 3063.618 | 3063.618 | 3063.618 | 36763.416 | 49% | 18014.0738 | 60924.7817 |  | 0 |  | 31830 |  | 8117 |  | 39947 |  | 178954.3954 | Labor - Task | Off Ice | 1.5 | Characterization and Calibration System | 1.5 Characterization and Calibration System | 1.5.3 | Array Calibration | 1.5.3 Array Calibration | 1.5.3.1 | Calibration Benchmarks | 1.5.3.1 Calibration Benchmarks | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 389d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.5.3.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5.3.1.1 | 4865.5954 | 4865.5954 | 4865.5954 | 4865.5954 | 4865.5954 | 4865.5954 | 4865.5954 | 4865.5954 | 4865.5954 | 4865.5954 | 4865.5954 | 4865.5954 | 1.5.3.1.1 | 4970.2057 | 4970.2057 | 4970.2057 | 4970.2057 | 4970.2057 | 4970.2057 | 4970.2057 | 4970.2057 | 4970.2057 | 4970.2057 | 4970.2057 | 4970.2057 | 1.5.3.1.1 | 5077.0651 | 5077.0651 | 5077.0651 | 5077.0651 | 5077.0651 | 5077.0651 | 5077.0651 | 5077.0651 | 5077.0651 | 5077.0651 | 5077.0651 | 5077.0651 | 1.5.3.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5.3.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5.3.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5.3.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5 | 1.5.3.2.4 | C |  | UA | Create Database Structure for Timing Calibration Data |  | 0% | Labor Hours | PO |  |  | 30 | 30 | 17.38% | 2022-10-04 | 2023-12-29 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49% | 0 | 0 | -31830 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49% | 0 | 0 | -8117 | 47.7 | 47.7 | 47.7 | 47.7 | 47.7 | 47.7 | 47.7 | 47.7 | 47.7 | 47.7 | 47.7 | 47.7 | 1679.7078 | 1679.7078 | 1679.7078 | 1679.7078 | 1679.7078 | 1679.7078 | 1679.7078 | 1679.7078 | 1679.7078 | 1679.7078 | 1679.7078 | 1679.7078 | 20156.4936 | 49% | 9876.6819 | 32700.5259 | 32700.5259 | 47.7 | 47.7 | 47.7 | [9 empty] | 1679.7078 | 1679.7078 | 1679.7078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5039.1234 | 49% | 2469.1705 | 8350.8968 |  | 0 |  | 31830 |  | 8117 |  | 39947 |  | 41051.4227 | Labor - Task | Off Ice | 1.5 | Characterization and Calibration System | 1.5 Characterization and Calibration System | 1.5.3 | Array Calibration | 1.5.3 Array Calibration | 1.5.3.2 | Timing Calibration | 1.5.3.2 Timing Calibration | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 389d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.5.3.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5.3.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5.3.2.4 | 2725.0438 | 2725.0438 | 2725.0438 | 2725.0438 | 2725.0438 | 2725.0438 | 2725.0438 | 2725.0438 | 2725.0438 | 2725.0438 | 2725.0438 | 2725.0438 | 1.5.3.2.4 | 2783.6323 | 2783.6323 | 2783.6323 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5.3.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5.3.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5.3.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5.3.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5 | 1.5.3.2.4 | C |  | UW | Create Database Structure for Timing Calibration Data |  | 0% | Labor Hours | EN | TRUE |  | 40 | 40 | 35% | 2022-10-04 | 2023-12-29 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | -6910 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 |  | 6910 |  |  |  | 6910 |  | 0 | Labor - Task | Off Ice | 1.5 | Characterization and Calibration System | 1.5 Characterization and Calibration System | 1.5.3 | Array Calibration | 1.5.3 Array Calibration | 1.5.3.2 | Timing Calibration | 1.5.3.2 Timing Calibration | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 389d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.5.3.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5.3.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5.3.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5.3.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5.3.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5.3.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5.3.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5.3.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5 | 1.5.3.2.5 | C |  | UA | Analyze Timing Calibration Data from Deployed Modules |  | 0% | Labor Hours | PO |  |  | 30 | 30 | 17.38% | 2024-01-01 | 2024-09-26 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49% | 0 | 0 | -24350 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49% | 0 | 0 | 0 |  |  |  | 47.7 | 47.7 | 47.7 | 47.7 | 47.7 | 47.7 | 47.7 | 47.7 | 47.7 | 0 | 0 | 0 | 1679.7078 | 1679.7078 | 1679.7078 | 1679.7078 | 1679.7078 | 1679.7078 | 1679.7078 | 1679.7078 | 1679.7078 | 15117.3702 | 49% | 7407.5114 | 25052.6904 |  | 0 |  |  |  | 24350 |  | 24350 |  | 25052.6904 | Labor - Task | Off Ice | 1.5 | Characterization and Calibration System | 1.5 Characterization and Calibration System | 1.5.3 | Array Calibration | 1.5.3 Array Calibration | 1.5.3.2 | Timing Calibration | 1.5.3.2 Timing Calibration | cell-link@smartsheet.com | 2021-12-01 19:41 |  | 233d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.5.3.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5.3.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5.3.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5.3.2.5 | 0 | 0 | 0 | 2783.6323 | 2783.6323 | 2783.6323 | 2783.6323 | 2783.6323 | 2783.6323 | 2783.6323 | 2783.6323 | 2783.6323 | 1.5.3.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5.3.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5.3.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5.3.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5 | 1.5.3.3.2 | C |  | UA | Create Database Structure for Geometry Calibration Data |  | 0% | Labor Hours | PO |  |  | 30 | 30 | 17.38% | 2022-10-03 | 2023-12-28 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49% | 0 | 0 | -31830 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49% | 0 | 0 | -8117 | 47.7 | 47.7 | 47.7 | 47.7 | 47.7 | 47.7 | 47.7 | 47.7 | 47.7 | 47.7 | 47.7 | 47.7 | 1679.7078 | 1679.7078 | 1679.7078 | 1679.7078 | 1679.7078 | 1679.7078 | 1679.7078 | 1679.7078 | 1679.7078 | 1679.7078 | 1679.7078 | 1679.7078 | 20156.4936 | 49% | 9876.6819 | 32700.5259 | 32700.5259 | 47.7 | 47.7 | 47.7 | [9 empty] | 1679.7078 | 1679.7078 | 1679.7078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5039.1234 | 49% | 2469.1705 | 8350.8968 |  | 0 |  | 31830 |  | 8117 |  | 39947 |  | 41051.4227 | Labor - Task | Off Ice | 1.5 | Characterization and Calibration System | 1.5 Characterization and Calibration System | 1.5.3 | Array Calibration | 1.5.3 Array Calibration | 1.5.3.3 | Geometry Calibration | 1.5.3.3 Geometry Calibration | cell-link@smartsheet.com | 2021-12-01 19:41 |  | 389d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.5.3.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5.3.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5.3.3.2 | 2725.0438 | 2725.0438 | 2725.0438 | 2725.0438 | 2725.0438 | 2725.0438 | 2725.0438 | 2725.0438 | 2725.0438 | 2725.0438 | 2725.0438 | 2725.0438 | 1.5.3.3.2 | 2783.6323 | 2783.6323 | 2783.6323 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5.3.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5.3.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5.3.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5.3.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5 | 1.5.3.3.2 | C |  | UW | Create Database Structure for Geometry Calibration Data |  | 0% | Labor Hours | EN | TRUE |  | 40 | 40 | 35% | 2022-10-03 | 2023-12-28 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | -6910 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 |  | 6910 |  |  |  | 6910 |  | 0 | Labor - Task | Off Ice | 1.5 | Characterization and Calibration System | 1.5 Characterization and Calibration System | 1.5.3 | Array Calibration | 1.5.3 Array Calibration | 1.5.3.3 | Geometry Calibration | 1.5.3.3 Geometry Calibration | cell-link@smartsheet.com | 2021-12-01 19:41 |  | 389d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.5.3.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5.3.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5.3.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5.3.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5.3.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5.3.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5.3.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5.3.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5 | 1.5.3.3.3 | C |  | UA | Analyze Geometry Calibration Data from Deployed Modules |  | 0% | Labor Hours | PO |  |  | 30 | 30 | 17.38% | 2023-12-29 | 2024-09-25 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49% | 0 | 0 | -24350 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49% | 0 | 0 | 0 |  |  |  | 47.7 | 47.7 | 47.7 | 47.7 | 47.7 | 47.7 | 47.7 | 47.7 | 47.7 | 0 | 0 | 0 | 1679.7078 | 1679.7078 | 1679.7078 | 1679.7078 | 1679.7078 | 1679.7078 | 1679.7078 | 1679.7078 | 1679.7078 | 15117.3702 | 49% | 7407.5114 | 25052.6904 |  | 0 |  |  |  | 24350 |  | 24350 |  | 25052.6904 | Labor - Task | Off Ice | 1.5 | Characterization and Calibration System | 1.5 Characterization and Calibration System | 1.5.3 | Array Calibration | 1.5.3 Array Calibration | 1.5.3.3 | Geometry Calibration | 1.5.3.3 Geometry Calibration | cell-link@smartsheet.com | 2021-12-01 19:41 |  | 233d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.5.3.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5.3.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5.3.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5.3.3.3 | 0 | 0 | 0 | 2783.6323 | 2783.6323 | 2783.6323 | 2783.6323 | 2783.6323 | 2783.6323 | 2783.6323 | 2783.6323 | 2783.6323 | 1.5.3.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5.3.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5.3.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5.3.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5 | 1.5.3.4.2 | C |  | UA | Software Development |  | 0% | Labor Hours | PO |  |  | 30 | 30 | 17.38% | 2022-10-03 | 2024-01-01 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49% | 0 | 0 | -31830 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49% | 0 | 0 | -8117 | 47.7 | 47.7 | 47.7 | 47.7 | 47.7 | 47.7 | 47.7 | 47.7 | 47.7 | 47.7 | 47.7 | 47.7 | 1679.7078 | 1679.7078 | 1679.7078 | 1679.7078 | 1679.7078 | 1679.7078 | 1679.7078 | 1679.7078 | 1679.7078 | 1679.7078 | 1679.7078 | 1679.7078 | 20156.4936 | 49% | 9876.6819 | 32700.5259 | 32700.5259 | 47.7 | 47.7 | 47.7 | [9 empty] | 1679.7078 | 1679.7078 | 1679.7078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5039.1234 | 49% | 2469.1705 | 8350.8968 |  | 0 |  | 31830 |  | 8117 |  | 39947 |  | 41051.4227 | Labor - Task | Off Ice | 1.5 | Characterization and Calibration System | 1.5 Characterization and Calibration System | 1.5.3 | Array Calibration | 1.5.3 Array Calibration | 1.5.3.4 | Ice Properties Calibration | 1.5.3.4 Ice Properties Calibration | cell-link@smartsheet.com | 2021-12-01 19:41 |  | 391d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.5.3.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5.3.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5.3.4.2 | 2725.0438 | 2725.0438 | 2725.0438 | 2725.0438 | 2725.0438 | 2725.0438 | 2725.0438 | 2725.0438 | 2725.0438 | 2725.0438 | 2725.0438 | 2725.0438 | 1.5.3.4.2 | 2783.6323 | 2783.6323 | 2783.6323 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5.3.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5.3.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5.3.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5.3.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5 | 1.5.3.4.2 | C |  | UA | Software Development |  | 0% | Labor Hours | PO |  |  | 30 | 30 | 17.38% | 2022-10-03 | 2024-01-01 |  |  |  | zeroed postdoc, needed later years when we have schedule approved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49% | 0 | 0 | -31830 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 3063.618 | 3063.618 | 3063.618 | 3063.618 | 3063.618 | 3063.618 | 3063.618 | 3063.618 | 3063.618 | 3063.618 | 3063.618 | 3063.618 | 36763.416 | 49% | 18014.0738 | 58387.145 | 50270.145 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 3063.618 | 3063.618 | 3063.618 | 3063.618 | 3063.618 | 3063.618 | 3063.618 | 3063.618 | 3063.618 | 3063.618 | 3063.618 | 3063.618 | 36763.416 | 49% | 18014.0738 | 59642.4686 | 59642.4686 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 3063.618 | 3063.618 | 3063.618 | 3063.618 | 3063.618 | 3063.618 | 3063.618 | 3063.618 | 3063.618 | 3063.618 | 3063.618 | 3063.618 | 36763.416 | 49% | 18014.0738 | 60924.7817 |  | 0 |  | 31830 |  | 8117 |  | 39947 |  | 178954.3954 | Labor - Task | Off Ice | 1.5 | Characterization and Calibration System | 1.5 Characterization and Calibration System | 1.5.3 | Array Calibration | 1.5.3 Array Calibration | 1.5.3.4 | Ice Properties Calibration | 1.5.3.4 Ice Properties Calibration | cell-link@smartsheet.com | 2021-12-01 19:41 |  | 391d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.5.3.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5.3.4.2 | 4865.5954 | 4865.5954 | 4865.5954 | 4865.5954 | 4865.5954 | 4865.5954 | 4865.5954 | 4865.5954 | 4865.5954 | 4865.5954 | 4865.5954 | 4865.5954 | 1.5.3.4.2 | 4970.2057 | 4970.2057 | 4970.2057 | 4970.2057 | 4970.2057 | 4970.2057 | 4970.2057 | 4970.2057 | 4970.2057 | 4970.2057 | 4970.2057 | 4970.2057 | 1.5.3.4.2 | 5077.0651 | 5077.0651 | 5077.0651 | 5077.0651 | 5077.0651 | 5077.0651 | 5077.0651 | 5077.0651 | 5077.0651 | 5077.0651 | 5077.0651 | 5077.0651 | 1.5.3.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5.3.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5.3.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5.3.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5 | 1.5.3.4.3 | C |  | UA | Execution |  | 0% | Labor Hours | PO |  |  | 30 | 30 | 17.38% | 2024-01-02 | 2024-09-26 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49% | 0 | 0 | -24350 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49% | 0 | 0 | 0 |  |  |  | 47.7 | 47.7 | 47.7 | 47.7 | 47.7 | 47.7 | 47.7 | 47.7 | 47.7 | 0 | 0 | 0 | 1679.7078 | 1679.7078 | 1679.7078 | 1679.7078 | 1679.7078 | 1679.7078 | 1679.7078 | 1679.7078 | 1679.7078 | 15117.3702 | 49% | 7407.5114 | 25052.6904 |  | 0 |  |  |  | 24350 |  | 24350 |  | 25052.6904 | Labor - Task | Off Ice | 1.5 | Characterization and Calibration System | 1.5 Characterization and Calibration System | 1.5.3 | Array Calibration | 1.5.3 Array Calibration | 1.5.3.4 | Ice Properties Calibration | 1.5.3.4 Ice Properties Calibration | cell-link@smartsheet.com | 2021-12-01 19:41 |  | 231d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.5.3.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5.3.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5.3.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5.3.4.3 | 0 | 0 | 0 | 2783.6323 | 2783.6323 | 2783.6323 | 2783.6323 | 2783.6323 | 2783.6323 | 2783.6323 | 2783.6323 | 2783.6323 | 1.5.3.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5.3.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5.3.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5.3.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TRUE | 1.5 | 1.5.3.5.1 | C |  | UW | Dust logger shipping UCB to UW/PSL |  |  | CapEx |  |  | HD | 1 | 1 | 0% | 2022-06-01 | 2022-08-31 | [10 empty] | 1000 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 1000 | 53% | 0 | 1000 | 1000 | [6 empty] | 1000 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 1000 | 53% | 0 | 1000 | 1000 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 2000 | CapEx | Off Ice | 1.5 | Characterization and Calibration System | 1.5 Characterization and Calibration System | 1.5.3 | Array Calibration | 1.5.3 Array Calibration | 1.5.3.5 | Pre-deployment Hole Measurement | 1.5.3.5 Pre-deployment Hole Measurement | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.5.3.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 1.5.3.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 1.5.3.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5.3.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5.3.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 1000 | 1.5.3.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5.3.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 1.5.3.5.1 | 1000 | 26858.5081 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 1000 | 26858.5081 | 26858.5081 | 26858.5081 | 26858.5081
TRUE | 1.5 | 1.5.3.5.1 | C |  | UW | PSL Engineering support for summer 2022 testing |  | 2.308% | Labor Hours | EN |  |  |  | 40 | 35% | 2022-06-01 | 2022-08-31 | [12 empty] | 48 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2592 | 0 | 0 | 0 | 2592 | 53% | 1373.76 | 4138.1209 | 4138.1209 | [8 empty] | 48 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2592 | 0 | 0 | 0 | 2592 | 53% | 1373.76 | 4227.0905 | 4227.0905 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 8365.2113 | Labor - Task | Off Ice | 1.5 | Characterization and Calibration System | 1.5 Characterization and Calibration System | 1.5.3 | Array Calibration | 1.5.3 Array Calibration | 1.5.3.5 | Pre-deployment Hole Measurement | 1.5.3.5 Pre-deployment Hole Measurement | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.5.3.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4138.1209 | 0 | 0 | 0 | 1.5.3.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4227.0905 | 0 | 0 | 0 | 1.5.3.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5.3.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5.3.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2003.4475 | 0 | 0 | 0 | 2003.4475 | 1.5.3.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 701.2066 | 0 | 0 | 0 | 701.2066 | 1.5.3.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1433.4667 | 0 | 0 | 0 | 1433.4667 | 4138.1209 | 1.5.3.5.1 | 4138.1209 | 25858.5081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4138.1209 | 4138.1209 | 4138.1209 | 4138.1209 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25858.5081 | 25858.5081 | 25858.5081 | 25858.5081
TRUE | 1.5 | 1.5.3.5.1 | C |  | UW | Research Scientist to test dust logger |  | 7.692% | Labor Hours | SS |  |  |  | 55 | 35% | 2022-06-01 | 2022-08-31 | [12 empty] | 160 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11880 | 0 | 0 | 0 | 11880 | 53% | 6296.4 | 18966.3872 | 18966.3872 | [8 empty] | 160 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11880 | 0 | 0 | 0 | 11880 | 53% | 6296.4 | 19374.1646 | 19374.1646 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 38340.5518 | Labor - Task | Off Ice | 1.5 | Characterization and Calibration System | 1.5 Characterization and Calibration System | 1.5.3 | Array Calibration | 1.5.3 Array Calibration | 1.5.3.5 | Pre-deployment Hole Measurement | 1.5.3.5 Pre-deployment Hole Measurement | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.5.3.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18966.3872 | 0 | 0 | 0 | 1.5.3.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19374.1646 | 0 | 0 | 0 | 1.5.3.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5.3.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5.3.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9182.4678 | 0 | 0 | 0 | 9182.4678 | 1.5.3.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3213.8637 | 0 | 0 | 0 | 3213.8637 | 1.5.3.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6570.0557 | 0 | 0 | 0 | 6570.0557 | 18966.3872 | 1.5.3.5.1 | 18966.3872 | 21720.3872 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18966.3872 | 18966.3872 | 18966.3872 | 18966.3872 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21720.3872 | 21720.3872 | 21720.3872 | 21720.3872
TRUE | 1.5 | 1.5.3.5.1 | C |  | UW | Travel to test dust logger |  |  | Travel |  |  |  | 1 | 1 | 0% | 2022-06-01 | 2022-08-31 | [12 empty] | 1800 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 1800 | 53% | 954 | 2754 | 2754 | [8 empty] | 1800 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 1800 | 53% | 954 | 2754 | 2754 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 5508 | Travel | Off Ice | 1.5 | Characterization and Calibration System | 1.5 Characterization and Calibration System | 1.5.3 | Array Calibration | 1.5.3 Array Calibration | 1.5.3.5 | Pre-deployment Hole Measurement | 1.5.3.5 Pre-deployment Hole Measurement | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.5.3.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2754 | 0 | 0 | 0 | 1.5.3.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2754 | 0 | 0 | 0 | 1.5.3.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5.3.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5.3.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 1800 | 1.5.3.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5.3.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 954 | 0 | 0 | 0 | 954 | 2754 | 1.5.3.5.1 | 2754 | 2754 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2754 | 2754 | 2754 | 2754 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2754 | 2754 | 2754 | 2754
TRUE | 1.5 | 1.5.3.5.2 | C |  | UW | Shipping of logger and winch to PTH |  |  | CapEx |  |  | VQ | 1 | 1 | 0% | 2023-09-01 | 2023-09-01 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | -17621 | [11 empty] | 14000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14000 | 14000 | 53% | 0 | 14000 | 14000 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 |  |  |  | 17621 |  | 62375 |  | 14000 | CapEx | Off Ice | 1.5 | Characterization and Calibration System | 1.5 Characterization and Calibration System | 1.5.3 | Array Calibration | 1.5.3 Array Calibration | 1.5.3.5 | Pre-deployment Hole Measurement | 1.5.3.5 Pre-deployment Hole Measurement | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.5.3.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5.3.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5.3.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14000 | 1.5.3.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5.3.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5.3.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5.3.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5.3.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5 | 1.5.4.1 | C |  | UA | Calibration Management | Williams | 3.846% | Labor Hours | KE |  |  | 100 | 73 | 32% | 2019-01-11 | 2024-09-27 |  | TRUE | [11 empty] | 80 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7708.8 | 0 | 0 | 7708.8 | 49% | 3777.312 | 11985.3243 | 714.3243 | [9 empty] | 80 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7708.8 | 0 | 0 | 7708.8 | 49% | 3777.312 | 12243.0087 | 619.0087 | [9 empty] | 80 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7708.8 | 0 | 0 | 7708.8 | 49% | 3777.312 | 12506.2334 | 12506.2334 | [9 empty] | 80 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7708.8 | 0 | 0 | 7708.8 | 49% | 3777.312 | 12775.1174 | 10424 | 10833.1344 | 11050 | 11271 |  | 11624 |  | 55202 |  | 49509.6839 | Labor - LoE | Off Ice | 1.5 | Characterization and Calibration System | 1.5 Characterization and Calibration System | 1.5.4 | Calibration Management and Organization | 1.5.4 Calibration Management and Organization | 1.5.4.1 | Calibration management | 1.5.4.1 Calibration management | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1446d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.5.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11985.3243 | 0 | 0 | 1.5.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12243.0087 | 0 | 0 | 1.5.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12506.2334 | 0 | 0 | 1.5.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12775.1174 | 0 | 0 | 1.5.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6093.8195 | 0 | 0 | 6093.8195 | 1.5.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1950.0223 | 0 | 0 | 1950.0223 | 1.5.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3941.4825 | 0 | 0 | 3941.4825 | 11985.3243 | 1.5.4.1 | 11985.3243 | 16455.3243 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11985.3243 | 11985.3243 | 11985.3243 | 372.5 | 745 | 1117.5 | 1490 | 1862.5 | 2235 | 2607.5 | 2980 | 3352.5 | 15710.3243 | 16082.8243 | 16455.3243
| 1.5 | 1.5.4.1 | C |  | UA | Miscellaneous supplies for calibration and outreach activities |  |  | M & S |  |  |  | 1 | 1 | 0% | 2019-01-11 | 2024-09-27 |  | TRUE |  |  | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 3000 | 49% | 1470 | 4470 | 0 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 3000 | 49% | 1470 | 4470 | 0 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 3000 | 49% | 1470 | 4470 | 4470 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 3000 | 49% | 1470 | 4470 | 4470 | 4470 | 4470 | 4470 |  | 4470 |  | 22350 |  | 17880 | M & S | Off Ice | 1.5 | Characterization and Calibration System | 1.5 Characterization and Calibration System | 1.5.4 | Calibration Management and Organization | 1.5.4 Calibration Management and Organization | 1.5.4.1 | Calibration management | 1.5.4.1 Calibration management | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1446d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.5.4.1 | 372.5 | 372.5 | 372.5 | 372.5 | 372.5 | 372.5 | 372.5 | 372.5 | 372.5 | 372.5 | 372.5 | 372.5 | 1.5.4.1 | 372.5 | 372.5 | 372.5 | 372.5 | 372.5 | 372.5 | 372.5 | 372.5 | 372.5 | 372.5 | 372.5 | 372.5 | 1.5.4.1 | 372.5 | 372.5 | 372.5 | 372.5 | 372.5 | 372.5 | 372.5 | 372.5 | 372.5 | 372.5 | 372.5 | 372.5 | 1.5.4.1 | 372.5 | 372.5 | 372.5 | 372.5 | 372.5 | 372.5 | 372.5 | 372.5 | 372.5 | 372.5 | 372.5 | 372.5 | 1.5.4.1 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 3000 | 1.5.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5.4.1 | 122.5 | 122.5 | 122.5 | 122.5 | 122.5 | 122.5 | 122.5 | 122.5 | 122.5 | 122.5 | 122.5 | 122.5 | 1470 | 4470 | 1.5.4.1 | 4470 | 4470 | 372.5 | 745 | 1117.5 | 1490 | 1862.5 | 2235 | 2607.5 | 2980 | 3352.5 | 3725 | 4097.5 | 4470 | 372.5 | 745 | 1117.5 | 1490 | 1862.5 | 2235 | 2607.5 | 2980 | 3352.5 | 3725 | 4097.5 | 4470
| 1.5 | 1.5.4.2 | C |  | UA | Travel to reviews and working meetings |  |  | Travel |  |  |  | 1 | 1 | 0% | 2019-01-11 | 2024-09-27 |  | TRUE | [6 empty] | 1800 |  |  | 3200 |  | 1800 | 3200 |  | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 3200 | 0 | 1800 | 3200 | 0 | 10000 | 49% | 4900 | 14900 | 694 |  |  |  |  | 1800 |  |  | 3200 |  | 1800 | 3200 |  | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 3200 | 0 | 1800 | 3200 | 0 | 10000 | 49% | 4900 | 14900 | -2017 |  |  |  |  | 1800 |  |  | 3200 |  | 1800 | 3200 |  | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 3200 | 0 | 1800 | 3200 | 0 | 10000 | 49% | 4900 | 14900 | 14900 |  |  |  |  | 1800 |  |  | 3200 |  | 1800 | 3200 |  | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 3200 | 0 | 1800 | 3200 | 0 | 10000 | 49% | 4900 | 14900 | 18846 | 11219.7 | 14642 | 14206 |  | 16917 |  | 75836 |  | 59600 | Travel | Off Ice | 1.5 | Characterization and Calibration System | 1.5 Characterization and Calibration System | 1.5.4 | Calibration Management and Organization | 1.5.4 Calibration Management and Organization | 1.5.4.2 | Travel | 1.5.4.2 Travel | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1446d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.5.4.2 | 0 | 0 | 0 | 0 | 2682 | 0 | 0 | 4768 | 0 | 2682 | 4768 | 0 | 1.5.4.2 | 0 | 0 | 0 | 0 | 2682 | 0 | 0 | 4768 | 0 | 2682 | 4768 | 0 | 1.5.4.2 | 0 | 0 | 0 | 0 | 2682 | 0 | 0 | 4768 | 0 | 2682 | 4768 | 0 | 1.5.4.2 | 0 | 0 | 0 | 0 | 2682 | 0 | 0 | 4768 | 0 | 2682 | 4768 | 0 | 1.5.4.2 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 3200 | 0 | 1800 | 3200 | 0 | 10000 | 1.5.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5.4.2 | 0 | 0 | 0 | 0 | 882 | 0 | 0 | 1568 | 0 | 882 | 1568 | 0 | 4900 | 14900 | 1.5.4.2 | 14900 | 14900 | 0 | 0 | 0 | 0 | 2682 | 2682 | 2682 | 7450 | 7450 | 10132 | 14900 | 14900 | 0 | 0 | 0 | 0 | 2682 | 2682 | 2682 | 7450 | 7450 | 10132 | 14900 | 14900
| 1.6 | 1.6.0 | C |  | UMD | L2 Task management - Erik Blaufuss | Blaufuss | 24.81% | Labor Hours | SS |  |  | 55 | 68 | 29% | 2020-10-01 | 2024-06-28 |  | TRUE |  | 25% effort for management - EKB | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 3771.96 | 3771.96 | 3771.96 | 3771.96 | 3771.96 | 3771.96 | 3771.96 | 3771.96 | 3771.96 | 3771.96 | 3771.96 | 3771.96 | 45263.52 | 54.5% | 24668.6184 | 72971.5465 | 18886.5465 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 3771.96 | 3771.96 | 3771.96 | 3771.96 | 3771.96 | 3771.96 | 3771.96 | 3771.96 | 3771.96 | 3771.96 | 3771.96 | 3771.96 | 45263.52 | 54.5% | 24668.6184 | 74540.4347 | 19374.4347 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 3771.96 | 3771.96 | 3771.96 | 3771.96 | 3771.96 | 3771.96 | 3771.96 | 3771.96 | 3771.96 | 3771.96 | 3771.96 | 3771.96 | 45263.52 | 54.5% | 24668.6184 | 76143.0541 | 76143.0541 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 43 |  |  |  | 3771.96 | 3771.96 | 3771.96 | 3771.96 | 3771.96 | 3771.96 | 3771.96 | 3771.96 | 3771.96 | 0 | 0 | 0 | 33947.64 | 54.5% | 18501.4638 | 58335.0973 | 25483 | 68903.7246 | 53024 | 54085 |  | 55166 |  | 239742 |  | 281990.1326 | Labor - LoE | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.0 | L2 Task Management | 1.6.0 L2 Task Management | 1.6.0 | Data Systems Integration Management | 1.6.0 Data Systems Integration Management | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1460d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.0 | 6080.9622 | 6080.9622 | 6080.9622 | 6080.9622 | 6080.9622 | 6080.9622 | 6080.9622 | 6080.9622 | 6080.9622 | 6080.9622 | 6080.9622 | 6080.9622 | 1.6.0 | 6211.7029 | 6211.7029 | 6211.7029 | 6211.7029 | 6211.7029 | 6211.7029 | 6211.7029 | 6211.7029 | 6211.7029 | 6211.7029 | 6211.7029 | 6211.7029 | 1.6.0 | 6345.2545 | 6345.2545 | 6345.2545 | 6345.2545 | 6345.2545 | 6345.2545 | 6345.2545 | 6345.2545 | 6345.2545 | 6345.2545 | 6345.2545 | 6345.2545 | 1.6.0 | 6481.6775 | 6481.6775 | 6481.6775 | 6481.6775 | 6481.6775 | 6481.6775 | 6481.6775 | 6481.6775 | 6481.6775 | 0 | 0 | 0 | 1.6.0 | 3051.0836 | 3051.0836 | 3051.0836 | 3051.0836 | 3051.0836 | 3051.0836 | 3051.0836 | 3051.0836 | 3051.0836 | 3051.0836 | 3051.0836 | 3051.0836 | 36613.0034 | 1.6.0 | 884.8142 | 884.8142 | 884.8142 | 884.8142 | 884.8142 | 884.8142 | 884.8142 | 884.8142 | 884.8142 | 884.8142 | 884.8142 | 884.8142 | 10617.771 | 1.6.0 | 2145.0643 | 2145.0643 | 2145.0643 | 2145.0643 | 2145.0643 | 2145.0643 | 2145.0643 | 2145.0643 | 2145.0643 | 2145.0643 | 2145.0643 | 2145.0643 | 25740.7721 | 72971.5465 | 1.6.0 | 72971.5465 | 84068.5465 | 6080.9622 | 12161.9244 | 18242.8866 | 24323.8488 | 30404.811 | 36485.7732 | 42566.7354 | 48647.6977 | 54728.6599 | 60809.6221 | 66890.5843 | 72971.5465 | 6080.9622 | 12161.9244 | 18242.8866 | 24323.8488 | 30404.811 | 36485.7732 | 50882.7354 | 56963.6977 | 63044.6599 | 69125.6221 | 75206.5843 | 84068.5465
| 1.6 | 1.6.0 | C |  | UMD | Travel to annual project reviews |  |  | Travel |  |  |  | 1 | 1 | 0% | 2020-10-01 | 2024-06-28 |  | TRUE | [8 empty] | 1800 |  |  |  |  | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 1800 | 3600 | 54.5% | 1962 | 5562 | -111 | [6 empty] | 1800 |  |  |  |  | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 1800 | 3600 | 54.5% | 1962 | 5562 | 2669 | [6 empty] | 1800 |  |  |  |  | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 1800 | 3600 | 54.5% | 1962 | 5562 | 5562 | [6 empty] | 1800 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 1800 | 54.5% | 981 | 2781 | 5346 | 5562 | 5562 | 5673 |  | 2893 |  | 24927 |  | 19467 | Travel | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.0 | L2 Task Management | 1.6.0 L2 Task Management | 1.6.0 | Data Systems Integration Management | 1.6.0 Data Systems Integration Management | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1460d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.0 | 0 | 0 | 0 | 0 | 0 | 0 | 2781 | 0 | 0 | 0 | 0 | 2781 | 1.6.0 | 0 | 0 | 0 | 0 | 0 | 0 | 2781 | 0 | 0 | 0 | 0 | 2781 | 1.6.0 | 0 | 0 | 0 | 0 | 0 | 0 | 2781 | 0 | 0 | 0 | 0 | 2781 | 1.6.0 | 0 | 0 | 0 | 0 | 0 | 0 | 2781 | 0 | 0 | 0 | 0 | 0 | 1.6.0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 1800 | 3600 | 1.6.0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.0 | 0 | 0 | 0 | 0 | 0 | 0 | 981 | 0 | 0 | 0 | 0 | 981 | 1962 | 5562 | 1.6.0 | 5562 | 11097 | 0 | 0 | 0 | 0 | 0 | 0 | 2781 | 2781 | 2781 | 2781 | 2781 | 5562 | 0 | 0 | 0 | 0 | 0 | 0 | 8316 | 8316 | 8316 | 8316 | 8316 | 11097
| 1.6 | 1.6.0 | C |  | UMD | Travel to project planning workshops and meetings |  |  | Travel |  |  |  | 1 | 1 | 0% | 2020-10-01 | 2024-06-28 |  | TRUE | [8 empty] | 1800 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 1800 | 54.5% | 981 | 2781 | -2892 | [6 empty] | 1800 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 1800 | 54.5% | 981 | 2781 | 2781 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54.5% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54.5% | 0 | 0 | 2673 | 5562 | 5562 | 5673 |  |  |  | 19361 |  | 5562 | Travel | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.0 | L2 Task Management | 1.6.0 L2 Task Management | 1.6.0 | Data Systems Integration Management | 1.6.0 Data Systems Integration Management | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1460d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.0 | 0 | 0 | 0 | 0 | 0 | 0 | 2781 | 0 | 0 | 0 | 0 | 0 | 1.6.0 | 0 | 0 | 0 | 0 | 0 | 0 | 2781 | 0 | 0 | 0 | 0 | 0 | 1.6.0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 1800 | 1.6.0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.0 | 0 | 0 | 0 | 0 | 0 | 0 | 981 | 0 | 0 | 0 | 0 | 0 | 981 | 2781 | 1.6.0 | 2781 | 5535 | 0 | 0 | 0 | 0 | 0 | 0 | 2781 | 2781 | 2781 | 2781 | 2781 | 2781 | 0 | 0 | 0 | 0 | 0 | 0 | 5535 | 5535 | 5535 | 5535 | 5535 | 5535
| 1.6 | 1.6.0 | C |  | UW | Travel to project planning workshops and meetings |  |  | Travel |  |  |  | 1 | 1 | 0% | 2020-10-01 | 2024-06-28 |  | TRUE | [8 empty] | 1800 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 1800 | 53% | 954 | 2754 | -169 | [6 empty] | 1800 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 1800 | 53% | 954 | 2754 | 2754 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 |  |  |  | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 0 | 0 | 0 | 90 | 53% | 47.7 | 137.7 |  | 0 | 2865 | 2923 |  |  |  | 8597 |  | 5645.7 | Travel | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.0 | L2 Task Management | 1.6.0 L2 Task Management | 1.6.0 | Data Systems Integration Management | 1.6.0 Data Systems Integration Management | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1460d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.0 | 0 | 0 | 0 | 0 | 0 | 0 | 2754 | 0 | 0 | 0 | 0 | 0 | 1.6.0 | 0 | 0 | 0 | 0 | 0 | 0 | 2754 | 0 | 0 | 0 | 0 | 0 | 1.6.0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.0 | 15.3 | 15.3 | 15.3 | 15.3 | 15.3 | 15.3 | 15.3 | 15.3 | 15.3 | 0 | 0 | 0 | 1.6.0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 1800 | 1.6.0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.0 | 0 | 0 | 0 | 0 | 0 | 0 | 954 | 0 | 0 | 0 | 0 | 0 | 954 | 2754 | 1.6.0 | 2754 | 2754 | 0 | 0 | 0 | 0 | 0 | 0 | 2754 | 2754 | 2754 | 2754 | 2754 | 2754 | 0 | 0 | 0 | 0 | 0 | 0 | 2754 | 2754 | 2754 | 2754 | 2754 | 2754
| 1.6 | 1.6.1.0 | C |  | UW | L3 Task management - Jim Braun | Braun | 5.769% | Labor Hours | SC |  |  | 45 | 41 | 35% | 2020-10-01 | 2024-06-28 |  | TRUE |  |  | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 553.5 | 553.5 | 553.5 | 553.5 | 553.5 | 553.5 | 553.5 | 553.5 | 553.5 | 553.5 | 553.5 | 553.5 | 6642 | 53% | 3520.26 | 10603.9347 | -1057.0653 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 553.5 | 553.5 | 553.5 | 553.5 | 553.5 | 553.5 | 553.5 | 553.5 | 553.5 | 553.5 | 553.5 | 553.5 | 6642 | 53% | 3520.26 | 10831.9193 | -1062.0807 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 553.5 | 553.5 | 553.5 | 553.5 | 553.5 | 553.5 | 553.5 | 553.5 | 553.5 | 553.5 | 553.5 | 553.5 | 6642 | 53% | 3520.26 | 11064.8055 | 11064.8055 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 5494 | 10038.33 | 11432 | 11661 |  | 11894 |  | 51690 |  | 32500.6595 | Labor - LoE | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.1 | Online Systems Software | 1.6.1 Online Systems Software | 1.6.1.0 | Online System Software Management | 1.6.1.0 Online System Software Management | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1460d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.0 | 883.6612 | 883.6612 | 883.6612 | 883.6612 | 883.6612 | 883.6612 | 883.6612 | 883.6612 | 883.6612 | 883.6612 | 883.6612 | 883.6612 | 1.6.1.0 | 902.6599 | 902.6599 | 902.6599 | 902.6599 | 902.6599 | 902.6599 | 902.6599 | 902.6599 | 902.6599 | 902.6599 | 902.6599 | 902.6599 | 1.6.1.0 | 922.0671 | 922.0671 | 922.0671 | 922.0671 | 922.0671 | 922.0671 | 922.0671 | 922.0671 | 922.0671 | 922.0671 | 922.0671 | 922.0671 | 1.6.1.0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.0 | 427.8195 | 427.8195 | 427.8195 | 427.8195 | 427.8195 | 427.8195 | 427.8195 | 427.8195 | 427.8195 | 427.8195 | 427.8195 | 427.8195 | 5133.8343 | 1.6.1.0 | 149.7368 | 149.7368 | 149.7368 | 149.7368 | 149.7368 | 149.7368 | 149.7368 | 149.7368 | 149.7368 | 149.7368 | 149.7368 | 149.7368 | 1796.842 | 1.6.1.0 | 306.1049 | 306.1049 | 306.1049 | 306.1049 | 306.1049 | 306.1049 | 306.1049 | 306.1049 | 306.1049 | 306.1049 | 306.1049 | 306.1049 | 3673.2584 | 10603.9347 | 1.6.1.0 | 10603.9347 | 10603.9347 | 883.6612 | 1767.3224 | 2650.9837 | 3534.6449 | 4418.3061 | 5301.9673 | 6185.6286 | 7069.2898 | 7952.951 | 8836.6122 | 9720.2735 | 10603.9347 | 883.6612 | 1767.3224 | 2650.9837 | 3534.6449 | 4418.3061 | 5301.9673 | 6185.6286 | 7069.2898 | 7952.951 | 8836.6122 | 9720.2735 | 10603.9347
| 1.6 | 1.6.1.1 | P |  | UW | Miscellaneous supplies |  |  | M & S |  | TRUE |  | 1 | 1 | 0% | 2018-11-01 | 2024-03-15 | [10 empty] | 500 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 500 | 53% | 265 | 765 | 0 | [6 empty] | 500 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 500 | 53% | 265 | 765 | 0 | [6 empty] | 400 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 400 | 53% | 212 | 612 | 612 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 765 | 765 | 765 | 765 |  | 765 |  | 3825 |  | 2142 | M & S | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.1 | Online Systems Software | 1.6.1 Online Systems Software | 1.6.1.1 | DAQ Software | 1.6.1.1 DAQ Software | cell-link@smartsheet.com | 2021-12-01 19:52 |  | 1460d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 765 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 765 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 612 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 500 | 1.6.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 265 | 0 | 0 | 0 | 0 | 0 | 265 | 765 | 1.6.1.1 | 765 | 6808.5 | 0 | 0 | 0 | 0 | 0 | 0 | 765 | 765 | 765 | 765 | 765 | 765 | 0 | 0 | 0 | 0 | 0 | 1453.5 | 4972.5 | 4972.5 | 4972.5 | 4972.5 | 4972.5 | 6808.5
| 1.6 | 1.6.1.1 | P |  | UW | PQ process |  |  | M & S |  |  |  | 1 | 1 | 0% | 2018-11-01 | 2024-03-15 |  | TRUE | [7 empty] | 950 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 950 | 0 | 0 | 0 | 0 | 0 | 0 | 950 | 53% | 503.5 | 1453.5 | -0.5 | [5 empty] | 950 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 950 | 0 | 0 | 0 | 0 | 0 | 0 | 950 | 53% | 503.5 | 1453.5 | 1453.5 | [5 empty] | 950 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 950 | 0 | 0 | 0 | 0 | 0 | 0 | 950 | 53% | 503.5 | 1453.5 | 1453.5 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 |  | 1454 |  |  |  | 1454 |  | 4360.5 | M & S | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.1 | Online Systems Software | 1.6.1 Online Systems Software | 1.6.1.1 | DAQ Software | 1.6.1.1 DAQ Software | cell-link@smartsheet.com | 2021-12-01 19:52 |  | 1460d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.1 | 0 | 0 | 0 | 0 | 0 | 1453.5 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1 | 0 | 0 | 0 | 0 | 0 | 1453.5 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1 | 0 | 0 | 0 | 0 | 0 | 1453.5 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1 | 0 | 0 | 0 | 0 | 0 | 950 | 0 | 0 | 0 | 0 | 0 | 0 | 950 | 1.6.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1 | 0 | 0 | 0 | 0 | 0 | 503.5 | 0 | 0 | 0 | 0 | 0 | 0 | 503.5 | 1453.5 | 1.6.1.1 | 1453.5 | 6043.5 | 0 | 0 | 0 | 0 | 0 | 1453.5 | 1453.5 | 1453.5 | 1453.5 | 1453.5 | 1453.5 | 1453.5 | 0 | 0 | 0 | 0 | 0 | 1453.5 | 4207.5 | 4207.5 | 4207.5 | 4207.5 | 4207.5 | 6043.5
| 1.6 | 1.6.1.1 | P |  | UW | Travel to internal development workshops |  |  | Travel |  |  |  | 1 | 1 | 0% | 2018-11-01 | 2024-03-15 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 2754 | 2754 | [5 empty] | 5563 |  | 0 | Travel | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.1 | Online Systems Software | 1.6.1 Online Systems Software | 1.6.1.1 | DAQ Software | 1.6.1.1 DAQ Software | cell-link@smartsheet.com | 2021-12-01 19:52 |  | 1460d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1 | 0 | 4590 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2754 | 2754 | 2754 | 2754 | 2754 | 4590
| 1.6 | 1.6.1.1 | P |  | UW | Travel to NTS for new OM integration work |  |  | Travel |  |  |  | 1 | 1 | 0% | 2018-11-01 | 2024-03-15 |  | TRUE | [8 empty] | 1800 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 1800 | 53% | 954 | 2754 | 2754 | [6 empty] | 1800 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 1800 | 53% | 954 | 2754 | 2754 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 2754 | 0 | [5 empty] | 2754 |  | 5508 | Travel | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.1 | Online Systems Software | 1.6.1 Online Systems Software | 1.6.1.1 | DAQ Software | 1.6.1.1 DAQ Software | cell-link@smartsheet.com | 2021-12-01 19:52 |  | 1460d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 2754 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 2754 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 1800 | 1.6.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 954 | 0 | 0 | 0 | 0 | 0 | 954 | 2754 | 1.6.1.1 | 2754 | 4590 | 0 | 0 | 0 | 0 | 0 | 0 | 2754 | 2754 | 2754 | 2754 | 2754 | 2754 | 0 | 0 | 0 | 0 | 0 | 0 | 2754 | 2754 | 2754 | 2754 | 2754 | 4590
| 1.6 | 1.6.1.1 | P |  | UW | Travel to NTS for new calibration device integration work |  |  | Travel |  |  |  | 1 | 1 | 0% | 2018-11-01 | 2024-03-15 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [6 empty] | 1800 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 1800 | 53% | 954 | 2754 | 2754 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 | 2865 |  |  |  |  | 2865 |  | 2754 | Travel | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.1 | Online Systems Software | 1.6.1 Online Systems Software | 1.6.1.1 | DAQ Software | 1.6.1.1 DAQ Software | cell-link@smartsheet.com | 2021-12-01 19:52 |  | 1460d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 2754 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1 | 0 | 1836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1836
| 1.6 | 1.6.1.1 | P |  | UW | Deployment to Pole |  |  | Travel |  | TRUE |  | 1 | 1 | 0% | 2018-11-01 | 2024-03-15 | [15 empty] | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 1200 | 53% | 636 | 1836 | 1836 | [11 empty] | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 1200 | 53% | 636 | 1836 | -151 | [11 empty] | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 1200 | 53% | 636 | 1836 | 1836 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 |  |  |  | 1987 |  | 1987 |  | 5508 | Travel | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.1 | Online Systems Software | 1.6.1 Online Systems Software | 1.6.1.1 | DAQ Software | 1.6.1.1 DAQ Software | cell-link@smartsheet.com | 2021-12-01 19:52 |  | 1460d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1836 | 1.6.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1836 | 1.6.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1836 | 1.6.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 1200 | 1.6.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 636 | 636 | 1836 | 1.6.1.1 | 1836 | 1836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1836
| 1.6 | 1.6.1.1.1.1 | C |  | UW | DAQ-OM Interface Design |  | 0% | Labor Hours | EN | TRUE |  | 40 | 40 | 35% | 2018-11-01 | 2019-05-23 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 18721 | 0 | [5 empty] | 18721 |  | 0 | Labor - Task | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.1 | Online Systems Software | 1.6.1 Online Systems Software | 1.6.1.1 | DAQ Software | 1.6.1.1 DAQ Software | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 175d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.6 | 1.6.1.1.1.3 | C |  | UW | Testing minimal DAQ software tools developed for DVT testing |  | 0% | Labor Hours | EN | TRUE |  | 40 | 40 | 35% | 2019-05-27 | 2019-09-26 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 22791 | 4957.2 | [5 empty] | 26112 |  | 0 | Labor - Task | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.1 | Online Systems Software | 1.6.1 Online Systems Software | 1.6.1.1 | DAQ Software | 1.6.1.1 DAQ Software | cell-link@smartsheet.com | 2021-12-01 20:21 |  | 102d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.1.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.6 | 1.6.1.1.1.4.1 | C |  | UW | Define DAQ interface to FieldHub |  | 0% | Labor Hours | EN | TRUE |  |  | 40 | 35% | 2019-08-15 | 2019-11-01 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 9914.4 | [7 empty] | 0 | Labor - Task | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.1 | Online Systems Software | 1.6.1 Online Systems Software | 1.6.1.1 | DAQ Software | 1.6.1.1 DAQ Software | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.1.1.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1.1.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1.1.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1.1.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1.1.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1.1.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1.1.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1.1.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.6 | 1.6.1.1.1.5 | C |  | UW | Testing DAQ software implementation and testing for FATs |  | 0% | Labor Hours | EN | TRUE |  | 40 | 40 | 35% | 2019-11-04 | 2020-05-04 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 33048 | [5 empty] | 33210 |  | 0 | Labor - Task | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.1 | Online Systems Software | 1.6.1 Online Systems Software | 1.6.1.1 | DAQ Software | 1.6.1.1 DAQ Software | cell-link@smartsheet.com | 2021-12-01 19:41 |  | 66d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.1.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.6 | 1.6.1.1.1.7 | C |  | UW | Extend DAQ testing software for all OM types (mDOM, pDOM) |  | 0% | Labor Hours | EN | TRUE |  |  | 40 | 35% | 2020-05-06 | 2021-03-22 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 23133.6 | [7 empty] | 0 | Labor - Task | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.1 | Online Systems Software | 1.6.1 Online Systems Software | 1.6.1.1 | DAQ Software | 1.6.1.1 DAQ Software | cell-link@smartsheet.com | 2021-12-01 19:41 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.1.1.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1.1.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1.1.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1.1.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1.1.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1.1.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1.1.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1.1.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.6 | 1.6.1.1.1.8 | C |  | UW | Support DAQ installation for all sensor testing |  | 0% | Labor Hours | EN | TRUE |  | 40 | 40 | 35% | 2020-10-01 | 2022-06-30 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | -4319 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | -4405 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 8262 | 8468 | 4319 |  | 4405 |  | 33797 |  | 0 | Labor - Task | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.1 | Online Systems Software | 1.6.1 Online Systems Software | 1.6.1.1 | DAQ Software | 1.6.1.1 DAQ Software | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1161d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.1.1.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1.1.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1.1.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1.1.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1.1.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1.1.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1.1.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1.1.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.6 | 1.6.1.1.1.9 | C |  | UW | Capture Upgrade high-level DAQ requirements |  | 4.808% | Labor Hours | EN | TRUE |  |  | 40 | 35% | 2022-06-01 | 2022-08-31 | [12 empty] | 30 | 40 | 30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1620 | 2160 | 1620 | 0 | 5400 | 53% | 2862 | 8621.0851 | 5621.0851 | [8 empty] | 30 | 40 | 30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1620 | 2160 | 1620 | 0 | 5400 | 53% | 2862 | 8806.4384 | 8806.4384 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 | 6000 | 3000 | [5 empty] | 17427.5235 | Labor - Task | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.1 | Online Systems Software | 1.6.1 Online Systems Software | 1.6.1.1 | DAQ Software | 1.6.1.1 DAQ Software | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.1.1.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2586.3255 | 3448.434 | 2586.3255 | 0 | 1.6.1.1.1.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2641.9315 | 3522.5754 | 2641.9315 | 0 | 1.6.1.1.1.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1.1.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1.1.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1252.1547 | 1669.5396 | 1252.1547 | 0 | 4173.849 | 1.6.1.1.1.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 438.2541 | 584.3389 | 438.2541 | 0 | 1460.8472 | 1.6.1.1.1.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 895.9167 | 1194.5556 | 895.9167 | 0 | 2986.389 | 8621.0851 | 1.6.1.1.1.9 | 8621.0851 | 8621.0851 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2586.3255 | 6034.7596 | 8621.0851 | 8621.0851 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2586.3255 | 6034.7596 | 8621.0851 | 8621.0851
| 1.6 | 1.6.1.1.1.11 | C |  | UW | DAQ software implementation and testing for Production Systems |  | 0.9615% | Labor Hours | EN | TRUE |  | 40 | 40 | 35% | 2022-09-02 | 2023-11-24 | [15 empty] | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1080 | 1080 | 53% | 572.4 | 1724.217 | -50102.783 | [11 empty] | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1080 | 1080 | 53% | 572.4 | 1761.2877 | -19383.7123 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 2160 | 2160 | 2160 | 2160 | 2160 | 2160 | 2160 | 2160 | 2160 | 2160 | 2160 | 2160 | 25920 | 53% | 13737.6 | 43179.729 | 43179.729 | 40 | 40 | 20 | [9 empty] | 2160 | 2160 | 1080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5400 | 53% | 2862 | 9189.1861 |  | 0 |  | 51827 |  | 21145 |  | 72972 |  | 55854.4197 | Labor - Task | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.1 | Online Systems Software | 1.6.1 Online Systems Software | 1.6.1.1 | DAQ Software | 1.6.1.1 DAQ Software | cell-link@smartsheet.com | 2021-12-01 19:52 |  | 385d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.1.1.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1724.217 | 1.6.1.1.1.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1761.2877 | 1.6.1.1.1.11 | 3598.3107 | 3598.3107 | 3598.3107 | 3598.3107 | 3598.3107 | 3598.3107 | 3598.3107 | 3598.3107 | 3598.3107 | 3598.3107 | 3598.3107 | 3598.3107 | 1.6.1.1.1.11 | 3675.6744 | 3675.6744 | 1837.8372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1.1.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 834.7698 | 834.7698 | 1.6.1.1.1.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 292.1694 | 292.1694 | 1.6.1.1.1.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 597.2778 | 597.2778 | 1724.217 | 1.6.1.1.1.11 | 1724.217 | 1724.217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1724.217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1724.217
| 1.6 | 1.6.1.1.1.13 | C |  | UW | DAQ software deployment at SPS |  | 0% | Labor Hours | EN | TRUE |  |  | 40 | 35% | 2023-12-12 | 2024-01-08 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 |  |  |  | 80 | 60 | [7 empty] | 0 | 0 | 0 | 4320 | 3240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7560 | 53% | 4006.8 | 12864.8605 | [9 empty] | 12864.8605 | Labor - Task | On Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.1 | Online Systems Software | 1.6.1 Online Systems Software | 1.6.1.1 | DAQ Software | 1.6.1.1 DAQ Software | cell-link@smartsheet.com | 2021-12-01 19:52 |  | 385d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.1.1.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1.1.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1.1.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1.1.13 | 0 | 0 | 0 | 7351.3489 | 5513.5116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1.1.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1.1.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1.1.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1.1.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.6 | 1.6.1.1.2.1 | C |  | UW | DAQ-Calibraton device Interface Design |  | 0% | Labor Hours | EN | TRUE |  | 40 | 40 | 35% | 2020-11-01 | 2021-04-15 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 6512 | 16524 | [5 empty] | 6512 |  | 0 | Labor - Task | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.1 | Online Systems Software | 1.6.1 Online Systems Software | 1.6.1.1 | DAQ Software | 1.6.1.1 DAQ Software | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 51d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.1.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.6 | 1.6.1.1.2.3 | C |  | UW | DAQ-Calibration software software implementation and testing for NTS |  | 0% | Labor Hours | EN | TRUE |  | 40 | 40 | 35% | 2021-05-31 | 2022-03-15 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 | 40649 |  |  |  |  | 40649 |  | 0 | Labor - Task | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.1 | Online Systems Software | 1.6.1 Online Systems Software | 1.6.1.1 | DAQ Software | 1.6.1.1 DAQ Software | cell-link@smartsheet.com | 2021-12-01 20:21 |  | 299d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.1.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.6 | 1.6.1.1.2.5 | C |  | UW | Support DAQ installation for NTS calibration testing |  | 5.769% | Labor Hours | EN | TRUE |  | 40 | 40 | 35% | 2021-09-15 | 2024-03-01 |  |  |  |  | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 6480 | 53% | 3434.4 | 10345.3021 | 1707.3021 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 6480 | 53% | 3434.4 | 10567.7261 | 6162.7261 | 10 | 10 | 10 | 10 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 540 | 540 | 540 | 540 | 270 | 270 | 270 | 270 | 270 | 270 | 270 | 270 | 4320 | 53% | 2289.6 | 7196.6215 | 7196.6215 | 5 | 5 | 5 | 5 | 5 | [7 empty] | 270 | 270 | 270 | 270 | 270 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1350 | 53% | 715.5 | 2297.2965 |  | 0 |  | 8638 |  | 4405 |  | 13043 |  | 30406.9463 | Labor - Task | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.1 | Online Systems Software | 1.6.1 Online Systems Software | 1.6.1.1 | DAQ Software | 1.6.1.1 DAQ Software | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 563d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.1.2.5 | 862.1085 | 862.1085 | 862.1085 | 862.1085 | 862.1085 | 862.1085 | 862.1085 | 862.1085 | 862.1085 | 862.1085 | 862.1085 | 862.1085 | 1.6.1.1.2.5 | 880.6438 | 880.6438 | 880.6438 | 880.6438 | 880.6438 | 880.6438 | 880.6438 | 880.6438 | 880.6438 | 880.6438 | 880.6438 | 880.6438 | 1.6.1.1.2.5 | 899.5777 | 899.5777 | 899.5777 | 899.5777 | 449.7888 | 449.7888 | 449.7888 | 449.7888 | 449.7888 | 449.7888 | 449.7888 | 449.7888 | 1.6.1.1.2.5 | 459.4593 | 459.4593 | 459.4593 | 459.4593 | 459.4593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1.2.5 | 417.3849 | 417.3849 | 417.3849 | 417.3849 | 417.3849 | 417.3849 | 417.3849 | 417.3849 | 417.3849 | 417.3849 | 417.3849 | 417.3849 | 5008.6188 | 1.6.1.1.2.5 | 146.0847 | 146.0847 | 146.0847 | 146.0847 | 146.0847 | 146.0847 | 146.0847 | 146.0847 | 146.0847 | 146.0847 | 146.0847 | 146.0847 | 1753.0166 | 1.6.1.1.2.5 | 298.6389 | 298.6389 | 298.6389 | 298.6389 | 298.6389 | 298.6389 | 298.6389 | 298.6389 | 298.6389 | 298.6389 | 298.6389 | 298.6389 | 3583.6668 | 10345.3021 | 1.6.1.1.2.5 | 10345.3021 | 10345.3021 | 862.1085 | 1724.217 | 2586.3255 | 3448.434 | 4310.5426 | 5172.6511 | 6034.7596 | 6896.8681 | 7758.9766 | 8621.0851 | 9483.1936 | 10345.3021 | 862.1085 | 1724.217 | 2586.3255 | 3448.434 | 4310.5426 | 5172.6511 | 6034.7596 | 6896.8681 | 7758.9766 | 8621.0851 | 9483.1936 | 10345.3021
| 1.6 | 1.6.1.1.2.6 | C |  | UW | DAQ-Calibration device software implementation and testing for Production Systems |  | 0% | Labor Hours | EN | TRUE |  | 40 | 40 | 35% | 2023-02-01 | 2024-02-15 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | -34551 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | -22026 |  |  |  |  | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 0 | 0 | 0 | 0 | 1080 | 1080 | 1080 | 1080 | 1080 | 1080 | 1080 | 1080 | 8640 | 53% | 4579.2 | 14393.243 | 14393.243 | 20 | 20 | 20 | 20 | 20 | [7 empty] | 1080 | 1080 | 1080 | 1080 | 1080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5400 | 53% | 2862 | 9189.1861 |  | 0 |  | 34551 |  | 22026 |  | 56578 |  | 23582.4291 | Labor - Task | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.1 | Online Systems Software | 1.6.1 Online Systems Software | 1.6.1.1 | DAQ Software | 1.6.1.1 DAQ Software | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 326d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.1.2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1.2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1.2.6 | 0 | 0 | 0 | 0 | 1799.1554 | 1799.1554 | 1799.1554 | 1799.1554 | 1799.1554 | 1799.1554 | 1799.1554 | 1799.1554 | 1.6.1.1.2.6 | 1837.8372 | 1837.8372 | 1837.8372 | 1837.8372 | 1837.8372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1.2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1.2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1.2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1.2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.6 | 1.6.1.1.2.8 | C |  | UW | DAQ for calibration devices software deployment at SPS |  | 0% | Labor Hours | EN | TRUE |  | 40 | 40 | 35% | 2024-02-19 | 2024-03-15 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | -7048 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 |  |  |  |  | 20 | 80 | [6 empty] | 0 | 0 | 0 | 0 | 1080 | 4320 | 0 | 0 | 0 | 0 | 0 | 0 | 5400 | 53% | 2862 | 9189.1861 |  | 0 |  |  |  | 7048 |  | 7048 |  | 9189.1861 | Labor - Task | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.1 | Online Systems Software | 1.6.1 Online Systems Software | 1.6.1.1 | DAQ Software | 1.6.1.1 DAQ Software | cell-link@smartsheet.com | 2021-12-01 19:52 |  | 24d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.1.2.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1.2.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1.2.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1.2.8 | 0 | 0 | 0 | 0 | 1837.8372 | 7351.3489 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1.2.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1.2.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1.2.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.1.2.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.6 | 1.6.1.2 | P |  | UW | Miscellaneous supplies |  |  | M & S |  | TRUE |  | 1 | 1 | 0% | 2018-06-01 | 2024-03-14 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | -765 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | -765 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 765 | 765 | 765 | 765 |  | 765 |  | 3825 |  | 0 | M & S | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.1 | Online Systems Software | 1.6.1 Online Systems Software | 1.6.1.2 | Experiment Control | 1.6.1.2 Experiment Control | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1460d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.6 | 1.6.1.2 | P |  | UW | PQ process |  |  | M & S |  | TRUE |  | 1 | 1 | 0% | 2018-06-01 | 2024-03-14 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | -1454 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 |  | 1454 |  |  |  | 1454 |  | 0 | M & S | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.1 | Online Systems Software | 1.6.1 Online Systems Software | 1.6.1.2 | Experiment Control | 1.6.1.2 Experiment Control | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1460d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.6 | 1.6.1.2 | P |  | UW | Travel to NTS for new OM integration work |  |  | Travel |  | TRUE |  | 1 | 1 | 0% | 2018-06-01 | 2024-03-14 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 2754 | 2754 | [5 empty] | 2754 |  | 0 | Travel | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.1 | Online Systems Software | 1.6.1 Online Systems Software | 1.6.1.2 | Experiment Control | 1.6.1.2 Experiment Control | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1460d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.6 | 1.6.1.2 | P |  | UW | Travel to NTS for new calibration device integration work |  |  | Travel |  | TRUE |  | 1 | 1 | 0% | 2018-06-01 | 2024-03-14 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 | 2865 |  |  |  |  | 2865 |  | 0 | Travel | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.1 | Online Systems Software | 1.6.1 Online Systems Software | 1.6.1.2 | Experiment Control | 1.6.1.2 Experiment Control | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1460d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.6 | 1.6.1.2 | P |  | UW | Deployment to pole |  |  | Travel |  | TRUE |  | 1 | 1 | 0% | 2018-06-01 | 2024-03-14 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | -1987 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 |  |  |  | 1987 |  | 1987 |  | 0 | Travel | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.1 | Online Systems Software | 1.6.1 Online Systems Software | 1.6.1.2 | Experiment Control | 1.6.1.2 Experiment Control | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1460d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.6 | 1.6.1.2.1.1 | C |  | UW | Interface Design to OM (ExpControl, Config, Calib) |  | 0% | Labor Hours | EN | TRUE |  | 40 | 40 | 35% | 2018-06-01 | 2019-11-01 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 22791 | 6609.6 | [5 empty] | 22791 |  | 0 | Labor - Task | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.1 | Online Systems Software | 1.6.1 Online Systems Software | 1.6.1.2 | Experiment Control | 1.6.1.2 Experiment Control | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 197d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.2.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.2.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.2.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.2.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.2.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.2.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.2.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.2.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.6 | 1.6.1.2.1.3 | C |  | UW | ExpControl - OM software Implementation and testing for NTS |  | 0% | Labor Hours | EN | TRUE |  | 40 | 40 | 35% | 2019-06-19 | 2019-10-21 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 19535 | 6609.6 | [5 empty] | 26177 |  | 0 | Labor - Task | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.1 | Online Systems Software | 1.6.1 Online Systems Software | 1.6.1.2 | Experiment Control | 1.6.1.2 Experiment Control | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 102d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.2.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.2.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.2.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.2.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.2.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.2.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.2.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.2.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.6 | 1.6.1.2.1.5 | C |  | UW | Testing ExpControl software implementation and testing for FATs |  | 0% | Labor Hours | EN | TRUE |  | 40 | 40 | 35% | 2019-10-23 | 2020-04-22 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 19828.8 | [5 empty] | 18265 |  | 0 | Labor - Task | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.1 | Online Systems Software | 1.6.1 Online Systems Software | 1.6.1.2 | Experiment Control | 1.6.1.2 Experiment Control | cell-link@smartsheet.com | 2021-12-01 20:21 |  | 66d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.2.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.2.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.2.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.2.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.2.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.2.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.2.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.2.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.6 | 1.6.1.2.1.7 | C |  | UW | Extend testing ExpControl software to all OM types (mDOM, pDOM) |  | 0% | Labor Hours | EN | TRUE |  |  | 40 | 35% | 2020-04-24 | 2021-03-10 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 12393 | [7 empty] | 0 | Labor - Task | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.1 | Online Systems Software | 1.6.1 Online Systems Software | 1.6.1.2 | Experiment Control | 1.6.1.2 Experiment Control | cell-link@smartsheet.com | 2021-12-01 20:21 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.2.1.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.2.1.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.2.1.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.2.1.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.2.1.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.2.1.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.2.1.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.2.1.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.6 | 1.6.1.2.1.8 | C |  | UW | Support ExpControl installation for NTS sensor testing |  | 5.769% | Labor Hours | EN | TRUE |  | 40 | 40 | 35% | 2020-10-01 | 2022-06-30 |  |  |  |  | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 6480 | 53% | 3434.4 | 10345.3021 | 6026.3021 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 6480 | 53% | 3434.4 | 10567.7261 | 6162.7261 | 10 | 10 | 10 | 10 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 540 | 540 | 540 | 540 | 270 | 270 | 270 | 270 | 270 | 270 | 270 | 270 | 4320 | 53% | 2289.6 | 7196.6215 | 7196.6215 | 5 | 5 | 5 | 5 | [8 empty] | 270 | 270 | 270 | 270 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1080 | 53% | 572.4 | 1837.8372 |  | 1652.4 | 8468 | 4319 |  | 4405 |  | 33797 |  | 29947.487 | Labor - Task | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.1 | Online Systems Software | 1.6.1 Online Systems Software | 1.6.1.2 | Experiment Control | 1.6.1.2 Experiment Control | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1161d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.2.1.8 | 862.1085 | 862.1085 | 862.1085 | 862.1085 | 862.1085 | 862.1085 | 862.1085 | 862.1085 | 862.1085 | 862.1085 | 862.1085 | 862.1085 | 1.6.1.2.1.8 | 880.6438 | 880.6438 | 880.6438 | 880.6438 | 880.6438 | 880.6438 | 880.6438 | 880.6438 | 880.6438 | 880.6438 | 880.6438 | 880.6438 | 1.6.1.2.1.8 | 899.5777 | 899.5777 | 899.5777 | 899.5777 | 449.7888 | 449.7888 | 449.7888 | 449.7888 | 449.7888 | 449.7888 | 449.7888 | 449.7888 | 1.6.1.2.1.8 | 459.4593 | 459.4593 | 459.4593 | 459.4593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.2.1.8 | 417.3849 | 417.3849 | 417.3849 | 417.3849 | 417.3849 | 417.3849 | 417.3849 | 417.3849 | 417.3849 | 417.3849 | 417.3849 | 417.3849 | 5008.6188 | 1.6.1.2.1.8 | 146.0847 | 146.0847 | 146.0847 | 146.0847 | 146.0847 | 146.0847 | 146.0847 | 146.0847 | 146.0847 | 146.0847 | 146.0847 | 146.0847 | 1753.0166 | 1.6.1.2.1.8 | 298.6389 | 298.6389 | 298.6389 | 298.6389 | 298.6389 | 298.6389 | 298.6389 | 298.6389 | 298.6389 | 298.6389 | 298.6389 | 298.6389 | 3583.6668 | 10345.3021 | 1.6.1.2.1.8 | 10345.3021 | 10345.3021 | 862.1085 | 1724.217 | 2586.3255 | 3448.434 | 4310.5426 | 5172.6511 | 6034.7596 | 6896.8681 | 7758.9766 | 8621.0851 | 9483.1936 | 10345.3021 | 862.1085 | 1724.217 | 2586.3255 | 3448.434 | 4310.5426 | 5172.6511 | 6034.7596 | 6896.8681 | 7758.9766 | 8621.0851 | 9483.1936 | 10345.3021
| 1.6 | 1.6.1.2.1.9 | C |  | UW | Capture requirements for Expont - Upgrade OM |  | 4.808% | Labor Hours | EN | TRUE |  |  | 40 | 35% | 2022-06-01 | 2022-08-31 | [12 empty] | 30 | 40 | 30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1620 | 2160 | 1620 | 0 | 5400 | 53% | 2862 | 8621.0851 | 5621.0851 | [8 empty] | 30 | 40 | 30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1620 | 2160 | 1620 | 0 | 5400 | 53% | 2862 | 8806.4384 | 8806.4384 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 | 6000 | 3000 | [5 empty] | 17427.5235 | Labor - Task | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.1 | Online Systems Software | 1.6.1 Online Systems Software | 1.6.1.2 | Experiment Control | 1.6.1.2 Experiment Control | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.2.1.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2586.3255 | 3448.434 | 2586.3255 | 0 | 1.6.1.2.1.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2641.9315 | 3522.5754 | 2641.9315 | 0 | 1.6.1.2.1.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.2.1.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.2.1.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1252.1547 | 1669.5396 | 1252.1547 | 0 | 4173.849 | 1.6.1.2.1.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 438.2541 | 584.3389 | 438.2541 | 0 | 1460.8472 | 1.6.1.2.1.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 895.9167 | 1194.5556 | 895.9167 | 0 | 2986.389 | 8621.0851 | 1.6.1.2.1.9 | 8621.0851 | 8621.0851 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2586.3255 | 6034.7596 | 8621.0851 | 8621.0851 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2586.3255 | 6034.7596 | 8621.0851 | 8621.0851
| 1.6 | 1.6.1.2.1.11 | C |  | UW | ExpControl-OM software Implementation and testing for Production System |  | 0.9615% | Labor Hours | EN | TRUE |  | 40 | 40 | 35% | 2022-09-16 | 2023-12-08 | [15 empty] | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1080 | 1080 | 53% | 572.4 | 1724.217 | -32826.783 | [11 empty] | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1080 | 1080 | 53% | 572.4 | 1761.2877 | -7049.7123 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 2160 | 2160 | 2160 | 2160 | 2160 | 2160 | 2160 | 2160 | 2160 | 2160 | 2160 | 2160 | 25920 | 53% | 13737.6 | 43179.729 | 43179.729 | 20 | 20 | 20 | [9 empty] | 1080 | 1080 | 1080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3240 | 53% | 1717.2 | 5513.5116 |  | 0 |  | 34551 |  | 8811 |  | 43362 |  | 52178.7453 | Labor - Task | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.1 | Online Systems Software | 1.6.1 Online Systems Software | 1.6.1.2 | Experiment Control | 1.6.1.2 Experiment Control | cell-link@smartsheet.com | 2021-12-01 19:52 |  | 387d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.2.1.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1724.217 | 1.6.1.2.1.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1761.2877 | 1.6.1.2.1.11 | 3598.3107 | 3598.3107 | 3598.3107 | 3598.3107 | 3598.3107 | 3598.3107 | 3598.3107 | 3598.3107 | 3598.3107 | 3598.3107 | 3598.3107 | 3598.3107 | 1.6.1.2.1.11 | 1837.8372 | 1837.8372 | 1837.8372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.2.1.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 834.7698 | 834.7698 | 1.6.1.2.1.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 292.1694 | 292.1694 | 1.6.1.2.1.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 597.2778 | 597.2778 | 1724.217 | 1.6.1.2.1.11 | 1724.217 | 1724.217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1724.217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1724.217
| 1.6 | 1.6.1.2.1.13 | C |  | UW | ExpControl deployment at SPS |  | 0% | Labor Hours | EN | TRUE |  | 40 | 40 | 35% | 2024-01-15 | 2024-02-09 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | -7048 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 |  |  |  | 80 | 60 | [7 empty] | 0 | 0 | 0 | 4320 | 3240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7560 | 53% | 4006.8 | 12864.8605 |  | 0 |  |  |  | 7048 |  | 7048 |  | 12864.8605 | Labor - Task | On Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.1 | Online Systems Software | 1.6.1 Online Systems Software | 1.6.1.2 | Experiment Control | 1.6.1.2 Experiment Control | cell-link@smartsheet.com | 2021-12-01 19:52 |  | 24d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.2.1.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.2.1.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.2.1.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.2.1.13 | 0 | 0 | 0 | 7351.3489 | 5513.5116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.2.1.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.2.1.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.2.1.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.2.1.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.6 | 1.6.1.2.2.1 | C |  | UW | Interface Design to Calibration Devices (ExpControl, Config, Calib) |  | 0% | Labor Hours | EN | TRUE |  | 40 | 40 | 35% | 2021-06-27 | 2021-12-09 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 9768 | 13219.2 | [5 empty] | 9768 |  | 0 | Labor - Task | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.1 | Online Systems Software | 1.6.1 Online Systems Software | 1.6.1.2 | Experiment Control | 1.6.1.2 Experiment Control | cell-link@smartsheet.com | 2021-12-01 19:52 |  | 51d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.2.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.2.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.2.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.2.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.2.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.2.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.2.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.2.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.6 | 1.6.1.2.2.3 | C |  | UW | ExpControl - Calibration devices software Implementation and testing for NTS |  | 0% | Labor Hours | EN | TRUE |  | 40 | 40 | 35% | 2021-12-13 | 2022-09-12 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | -6910 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 | 33874 | 6910 |  |  |  | 40784 |  | 0 | Labor - Task | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.1 | Online Systems Software | 1.6.1 Online Systems Software | 1.6.1.2 | Experiment Control | 1.6.1.2 Experiment Control | cell-link@smartsheet.com | 2021-12-01 19:52 |  | 419d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.6 | 1.6.1.2.2.5 | C |  | UW | Support ExpControl installation for NTS calibration sensor testing |  | 5.769% | Labor Hours | EN | TRUE |  | 40 | 40 | 35% | 2022-09-14 | 2024-02-14 |  |  |  |  | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 6480 | 53% | 3434.4 | 10345.3021 | 1707.3021 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 6480 | 53% | 3434.4 | 10567.7261 | 6162.7261 | 10 | 10 | 10 | 10 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 540 | 540 | 540 | 540 | 270 | 270 | 270 | 270 | 270 | 270 | 270 | 270 | 4320 | 53% | 2289.6 | 7196.6215 | 7196.6215 | 5 | 5 | 5 | 5 | 5 | [7 empty] | 270 | 270 | 270 | 270 | 270 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1350 | 53% | 715.5 | 2297.2965 |  | 0 |  | 8638 |  | 4405 |  | 13043 |  | 30406.9463 | Labor - Task | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.1 | Online Systems Software | 1.6.1 Online Systems Software | 1.6.1.2 | Experiment Control | 1.6.1.2 Experiment Control | cell-link@smartsheet.com | 2021-12-01 19:52 |  | 442d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.2.2.5 | 862.1085 | 862.1085 | 862.1085 | 862.1085 | 862.1085 | 862.1085 | 862.1085 | 862.1085 | 862.1085 | 862.1085 | 862.1085 | 862.1085 | 1.6.1.2.2.5 | 880.6438 | 880.6438 | 880.6438 | 880.6438 | 880.6438 | 880.6438 | 880.6438 | 880.6438 | 880.6438 | 880.6438 | 880.6438 | 880.6438 | 1.6.1.2.2.5 | 899.5777 | 899.5777 | 899.5777 | 899.5777 | 449.7888 | 449.7888 | 449.7888 | 449.7888 | 449.7888 | 449.7888 | 449.7888 | 449.7888 | 1.6.1.2.2.5 | 459.4593 | 459.4593 | 459.4593 | 459.4593 | 459.4593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.2.2.5 | 417.3849 | 417.3849 | 417.3849 | 417.3849 | 417.3849 | 417.3849 | 417.3849 | 417.3849 | 417.3849 | 417.3849 | 417.3849 | 417.3849 | 5008.6188 | 1.6.1.2.2.5 | 146.0847 | 146.0847 | 146.0847 | 146.0847 | 146.0847 | 146.0847 | 146.0847 | 146.0847 | 146.0847 | 146.0847 | 146.0847 | 146.0847 | 1753.0166 | 1.6.1.2.2.5 | 298.6389 | 298.6389 | 298.6389 | 298.6389 | 298.6389 | 298.6389 | 298.6389 | 298.6389 | 298.6389 | 298.6389 | 298.6389 | 298.6389 | 3583.6668 | 10345.3021 | 1.6.1.2.2.5 | 10345.3021 | 10345.3021 | 862.1085 | 1724.217 | 2586.3255 | 3448.434 | 4310.5426 | 5172.6511 | 6034.7596 | 6896.8681 | 7758.9766 | 8621.0851 | 9483.1936 | 10345.3021 | 862.1085 | 1724.217 | 2586.3255 | 3448.434 | 4310.5426 | 5172.6511 | 6034.7596 | 6896.8681 | 7758.9766 | 8621.0851 | 9483.1936 | 10345.3021
| 1.6 | 1.6.1.2.2.6 | C |  | UW | ExpControl-Calibration devices software Implementation and testing for Production System |  | 0% | Labor Hours | EN | TRUE |  | 40 | 40 | 35% | 2023-01-31 | 2024-02-14 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | -17276 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | -35242 |  |  |  |  | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 0 | 0 | 0 | 0 | 1080 | 1080 | 1080 | 1080 | 1080 | 1080 | 1080 | 1080 | 8640 | 53% | 4579.2 | 14393.243 | 14393.243 | 20 | 20 | 20 | 20 | 20 | [7 empty] | 1080 | 1080 | 1080 | 1080 | 1080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5400 | 53% | 2862 | 9189.1861 |  | 0 |  | 17276 |  | 35242 |  | 52518 |  | 23582.4291 | Labor - Task | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.1 | Online Systems Software | 1.6.1 Online Systems Software | 1.6.1.2 | Experiment Control | 1.6.1.2 Experiment Control | cell-link@smartsheet.com | 2021-12-01 19:52 |  | 325d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.2.2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.2.2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.2.2.6 | 0 | 0 | 0 | 0 | 1799.1554 | 1799.1554 | 1799.1554 | 1799.1554 | 1799.1554 | 1799.1554 | 1799.1554 | 1799.1554 | 1.6.1.2.2.6 | 1837.8372 | 1837.8372 | 1837.8372 | 1837.8372 | 1837.8372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.2.2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.2.2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.2.2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.2.2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.6 | 1.6.1.2.2.8 | C |  | UW | ExpControl deployment at SPS |  | 0% | Labor Hours | EN | TRUE |  | 40 | 40 | 35% | 2024-02-16 | 2024-03-14 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | -7048 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 |  |  |  |  | 20 | 80 | [6 empty] | 0 | 0 | 0 | 0 | 1080 | 4320 | 0 | 0 | 0 | 0 | 0 | 0 | 5400 | 53% | 2862 | 9189.1861 |  | 0 |  |  |  | 7048 |  | 7048 |  | 9189.1861 | Labor - Task | On Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.1 | Online Systems Software | 1.6.1 Online Systems Software | 1.6.1.2 | Experiment Control | 1.6.1.2 Experiment Control | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 24d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.2.2.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.2.2.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.2.2.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.2.2.8 | 0 | 0 | 0 | 0 | 1837.8372 | 7351.3489 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.2.2.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.2.2.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.2.2.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.2.2.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.6 | 1.6.1.3 | P |  | UMD | Online Filtering Software Contrator - MARK AS CONSULTING SVC |  |  | M & S |  | TRUE |  | 1 | 1 | 0% | 2021-12-07 | 2024-03-27 | [6 empty] | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 0 | 0 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 10000 | 54.5% | 5450 | 15450 | 600 |  |  | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 0 | 0 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 10000 | 54.5% | 5450 | 15450 | 600 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 12000 | 54.5% | 6540 | 18540 | 18540 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | [6 empty] | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 54.5% | 3270 | 9270 |  | 0 | 7425 | 14850 |  | 14850 |  | 37125 |  | 58710 | M & S | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.1 | Online Systems Software | 1.6.1 Online Systems Software | 1.6.1.3 | Online Filtering | 1.6.1.3 Online Filtering | cell-link@smartsheet.com | 2021-12-01 19:52 |  | 776d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.3 | 0 | 0 | 1545 | 1545 | 1545 | 1545 | 1545 | 1545 | 1545 | 1545 | 1545 | 1545 | 1.6.1.3 | 0 | 0 | 1545 | 1545 | 1545 | 1545 | 1545 | 1545 | 1545 | 1545 | 1545 | 1545 | 1.6.1.3 | 1545 | 1545 | 1545 | 1545 | 1545 | 1545 | 1545 | 1545 | 1545 | 1545 | 1545 | 1545 | 1.6.1.3 | 1545 | 1545 | 1545 | 1545 | 1545 | 1545 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.3 | 0 | 0 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 10000 | 1.6.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.3 | 0 | 0 | 545 | 545 | 545 | 545 | 545 | 545 | 545 | 545 | 545 | 545 | 5450 | 15450 | 1.6.1.3 | 15450 | 15450 | 0 | 0 | 1545 | 3090 | 4635 | 6180 | 7725 | 9270 | 10815 | 12360 | 13905 | 15450 | 0 | 0 | 1545 | 3090 | 4635 | 6180 | 7725 | 9270 | 10815 | 12360 | 13905 | 15450
| 1.6 | 1.6.1.3.1 | C |  | UMD | Specify Online Filter Req'mts (New sensors / Calib Devices) |  | 5.769% | Labor Hours | EN | TRUE |  | 50 | 50 | 35% | 2021-12-07 | 2022-05-30 | [6 empty] | 20 | 20 | 20 | 20 | 20 | 20 |  |  |  |  | 0 | 0 | 1350 | 1350 | 1350 | 1350 | 1350 | 1350 | 0 | 0 | 0 | 0 | 8100 | 54.5% | 4414.5 | 13058.4083 | 13058.4083 |  |  | 20 | 20 | 20 | 20 | 20 | 20 |  |  |  |  | 0 | 0 | 1350 | 1350 | 1350 | 1350 | 1350 | 1350 | 0 | 0 | 0 | 0 | 8100 | 54.5% | 4414.5 | 13339.1641 | 13339.1641 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54.5% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54.5% | 0 | 0 |  | 0 | 8034 |  |  |  |  | 8034 |  | 26397.5724 | Labor - Task | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.1 | Online Systems Software | 1.6.1 Online Systems Software | 1.6.1.3 | Online Filtering | 1.6.1.3 Online Filtering | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 150d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.3.1 | 0 | 0 | 2176.4014 | 2176.4014 | 2176.4014 | 2176.4014 | 2176.4014 | 2176.4014 | 0 | 0 | 0 | 0 | 1.6.1.3.1 | 0 | 0 | 2223.194 | 2223.194 | 2223.194 | 2223.194 | 2223.194 | 2223.194 | 0 | 0 | 0 | 0 | 1.6.1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.3.1 | 0 | 0 | 1043.4623 | 1043.4623 | 1043.4623 | 1043.4623 | 1043.4623 | 1043.4623 | 0 | 0 | 0 | 0 | 6260.7735 | 1.6.1.3.1 | 0 | 0 | 365.2118 | 365.2118 | 365.2118 | 365.2118 | 365.2118 | 365.2118 | 0 | 0 | 0 | 0 | 2191.2707 | 1.6.1.3.1 | 0 | 0 | 767.7274 | 767.7274 | 767.7274 | 767.7274 | 767.7274 | 767.7274 | 0 | 0 | 0 | 0 | 4606.3641 | 13058.4083 | 1.6.1.3.1 | 13058.4083 | 13058.4083 | 0 | 0 | 2176.4014 | 4352.8028 | 6529.2042 | 8705.6056 | 10882.0069 | 13058.4083 | 13058.4083 | 13058.4083 | 13058.4083 | 13058.4083 | 0 | 0 | 2176.4014 | 4352.8028 | 6529.2042 | 8705.6056 | 10882.0069 | 13058.4083 | 13058.4083 | 13058.4083 | 13058.4083 | 13058.4083
| 1.6 | 1.6.1.3.2 | C |  | UMD | Design Filter Sys for unified DAQ readout of ALL sensors& Calib Devices |  | 2.885% | Labor Hours | EN | TRUE |  | 50 | 50 | 35% | 2022-05-31 | 2022-08-30 | [12 empty] | 20 | 20 | 20 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1350 | 1350 | 1350 | 0 | 4050 | 54.5% | 2207.25 | 6529.2042 | 6529.2042 | [8 empty] | 20 | 20 | 20 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1350 | 1350 | 1350 | 0 | 4050 | 54.5% | 2207.25 | 6669.5821 | 6669.5821 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54.5% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54.5% | 0 | 0 |  | 0 | 8034 |  |  |  |  | 8034 |  | 13198.7862 | Labor - Task | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.1 | Online Systems Software | 1.6.1 Online Systems Software | 1.6.1.3 | Online Filtering | 1.6.1.3 Online Filtering | cell-link@smartsheet.com | 2021-12-01 19:52 |  | 150d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2176.4014 | 2176.4014 | 2176.4014 | 0 | 1.6.1.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2223.194 | 2223.194 | 2223.194 | 0 | 1.6.1.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1043.4623 | 1043.4623 | 1043.4623 | 0 | 3130.3868 | 1.6.1.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 365.2118 | 365.2118 | 365.2118 | 0 | 1095.6354 | 1.6.1.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 767.7274 | 767.7274 | 767.7274 | 0 | 2303.1821 | 6529.2042 | 1.6.1.3.2 | 6529.2042 | 6529.2042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2176.4014 | 4352.8028 | 6529.2042 | 6529.2042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2176.4014 | 4352.8028 | 6529.2042 | 6529.2042
| 1.6 | 1.6.1.3.4 | C |  | UMD | Implement and testing of filtering SW for prod. systems |  | 0.4808% | Labor Hours | EN | TRUE |  | 50 | 50 | 35% | 2022-09-01 | 2024-01-18 | [15 empty] | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 675 | 675 | 54.5% | 367.875 | 1088.2007 | -3008.7993 | [11 empty] | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 675 | 675 | 54.5% | 367.875 | 1111.597 | -3067.403 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 1350 | 1350 | 1350 | 1350 | 1350 | 1350 | 1350 | 1350 | 1350 | 1350 | 1350 | 1350 | 16200 | 54.5% | 8829 | 27251.9123 | 27251.9123 | 20 | 20 | 20 | 20 | 20 | [7 empty] | 1350 | 1350 | 1350 | 1350 | 1350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6750 | 54.5% | 3678.75 | 11599.0952 |  | 0 |  | 4097 |  | 4179 |  | 8277 |  | 41050.8051 | Labor - Task | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.1 | Online Systems Software | 1.6.1 Online Systems Software | 1.6.1.3 | Online Filtering | 1.6.1.3 Online Filtering | cell-link@smartsheet.com | 2021-12-01 19:52 |  | 359d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1088.2007 | 1.6.1.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1111.597 | 1.6.1.3.4 | 2270.9927 | 2270.9927 | 2270.9927 | 2270.9927 | 2270.9927 | 2270.9927 | 2270.9927 | 2270.9927 | 2270.9927 | 2270.9927 | 2270.9927 | 2270.9927 | 1.6.1.3.4 | 2319.819 | 2319.819 | 2319.819 | 2319.819 | 2319.819 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 521.7311 | 521.7311 | 1.6.1.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 182.6059 | 182.6059 | 1.6.1.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 383.8637 | 383.8637 | 1088.2007 | 1.6.1.3.4 | 1088.2007 | 1088.2007 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1088.2007 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1088.2007
| 1.6 | 1.6.1.3.6 | C |  | UMD | New Online Filter Sys Deployment at SPS |  | 0% | Labor Hours | EN | TRUE |  | 50 | 50 | 35% | 2024-02-29 | 2024-03-27 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54.5% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54.5% | 0 | 0 | -4179 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54.5% | 0 | 0 | 0 | [5 empty] | 80 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 5400 | 0 | 0 | 0 | 0 | 0 | 0 | 5400 | 54.5% | 2943 | 9279.2761 |  | 0 |  |  |  | 4179 |  | 4179 |  | 9279.2761 | Labor - Task | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.1 | Online Systems Software | 1.6.1 Online Systems Software | 1.6.1.3 | Online Filtering | 1.6.1.3 Online Filtering | cell-link@smartsheet.com | 2021-12-01 19:52 |  | 104d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.3.6 | 0 | 0 | 0 | 0 | 0 | 9279.2761 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.6 | 1.6.1.4 | P |  | UW | Miscellaneous supplies |  |  | M & S |  |  |  | 1 | 1 | 0% | 2018-12-06 | 2024-05-31 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | -765 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | -765 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 765 | 765 | 765 | 765 |  | 765 |  | 3825 |  | 0 | M & S | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.1 | Online Systems Software | 1.6.1 Online Systems Software | 1.6.1.4 | OM Software | 1.6.1.4 OM Software | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1122d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4 | 0 | 2754 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2754 | 2754 | 2754 | 2754
| 1.6 | 1.6.1.4 | P |  | UW | Micro controller development setup |  |  | M & S |  |  |  | 1 | 1 | 0% | 2018-12-06 | 2024-05-31 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 1530 | 0 | [5 empty] | 1530 |  | 0 | M & S | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.1 | Online Systems Software | 1.6.1 Online Systems Software | 1.6.1.4 | OM Software | 1.6.1.4 OM Software | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1122d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4 | 0 | 2754 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2754 | 2754 | 2754 | 2754
| 1.6 | 1.6.1.4 | P |  | UW | PQ Process |  |  | M & S |  |  |  | 1 | 1 | 0% | 2018-12-06 | 2024-05-31 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | -1454 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 |  | 1454 |  |  |  | 1454 |  | 0 | M & S | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.1 | Online Systems Software | 1.6.1 Online Systems Software | 1.6.1.4 | OM Software | 1.6.1.4 OM Software | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1122d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4 | 0 | 2754 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2754 | 2754 | 2754 | 2754
| 1.6 | 1.6.1.4 | P |  | UW | Travel to internal project workshops |  |  | Travel |  |  |  | 1 | 1 | 0% | 2018-12-06 | 2024-05-31 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 2754 | 0 | [5 empty] | 5563 |  | 0 | Travel | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.1 | Online Systems Software | 1.6.1 Online Systems Software | 1.6.1.4 | OM Software | 1.6.1.4 OM Software | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1122d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4 | 0 | 2754 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2754 | 2754 | 2754 | 2754
| 1.6 | 1.6.1.4 | P |  | UW | Travel to NTS for OM integration work |  |  | Travel |  |  |  | 1 | 1 | 0% | 2018-12-06 | 2024-05-31 |  | TRUE | [10 empty] | 1800 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 1800 | 53% | 954 | 2754 | 2754 | [8 empty] | 1800 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 1800 | 53% | 954 | 2754 | 2754 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 2754 | 2754 | [5 empty] | 5563 |  | 5508 | Travel | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.1 | Online Systems Software | 1.6.1 Online Systems Software | 1.6.1.4 | OM Software | 1.6.1.4 OM Software | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1122d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2754 | 0 | 0 | 0 | 1.6.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2754 | 0 | 0 | 0 | 1.6.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 1800 | 1.6.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 954 | 0 | 0 | 0 | 954 | 2754 | 1.6.1.4 | 2754 | 2754 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2754 | 2754 | 2754 | 2754 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2754 | 2754 | 2754 | 2754
| 1.6 | 1.6.1.4 | P |  | UW | Deployment to pole |  |  | Travel |  |  |  | 1 | 1 | 0% | 2018-12-06 | 2024-05-31 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | -1987 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 |  |  |  | 1987 |  | 1987 |  | 0 | Travel | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.1 | Online Systems Software | 1.6.1 Online Systems Software | 1.6.1.4 | OM Software | 1.6.1.4 OM Software | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1122d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.6 | 1.6.1.4.1 | C |  | UW | Develop OM hardware-software high-level design |  | 0% | Labor Hours | EN |  |  | 40 | 40 | 35% | 2018-12-06 | 2019-01-15 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 5942 | 0 | [5 empty] | 5942 |  | 0 | Labor - Task | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.1 | Online Systems Software | 1.6.1 Online Systems Software | 1.6.1.4 | OM Software | 1.6.1.4 OM Software | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 35d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.6 | 1.6.1.4.2 | C |  | UW | Develop OM software development environment allowing cross-compilation on all OM types |  | 0% | Labor Hours | EN |  |  | 40 | 40 | 35% | 2019-01-16 | 2019-04-12 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 13023 | 0 | [5 empty] | 13023 |  | 0 | Labor - Task | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.1 | Online Systems Software | 1.6.1 Online Systems Software | 1.6.1.4 | OM Software | 1.6.1.4 OM Software | cell-link@smartsheet.com | 2021-12-01 20:21 |  | 76d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.6 | 1.6.1.4.3.1 | C |  | UW | Capture design requirements for OM testing app for FAT testing |  | 0% | Labor Hours | EN |  |  | 40 | 40 | 35% | 2019-01-16 | 2019-03-04 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 4640 | 0 | [5 empty] | 4640 |  | 0 | Labor - Task | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.1 | Online Systems Software | 1.6.1 Online Systems Software | 1.6.1.4 | OM Software | 1.6.1.4 OM Software | cell-link@smartsheet.com | 2021-12-01 20:21 |  | 40d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.4.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.6 | 1.6.1.4.3.2 | P |  | UW | Software design and prototyping of OM testing app |  | 0% | Labor Hours | EN |  |  | 40 | 40 | 35% | 2019-03-04 | 2019-07-09 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 13023 | 0 | [5 empty] | 13023 |  | 0 | Labor - Task | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.1 | Online Systems Software | 1.6.1 Online Systems Software | 1.6.1.4 | OM Software | 1.6.1.4 OM Software | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 52d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.4.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.6 | 1.6.1.4.3.2.1 | C |  | UW | Specify and implement interfaces from MCU to In-OM devices - Jeff Weber | Weber | 0% | Labor Hours | SE |  |  |  | 51 | 35% | 2019-03-04 | 2019-07-09 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 3284.145 | [7 empty] | 0 | Labor - Task | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.1 | Online Systems Software | 1.6.1 Online Systems Software | 1.6.1.4 | OM Software | 1.6.1.4 OM Software | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.4.3.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.3.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.3.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.3.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.3.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.3.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.3.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.3.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.6 | 1.6.1.4.3.2.2 | C |  | UW | Specify and implement interface to from MCU to ICM - Jeff Weber | Weber | 0% | Labor Hours | SE |  |  |  | 51 | 35% | 2019-03-04 | 2019-05-22 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 3284.145 | [7 empty] | 0 | Labor - Task | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.1 | Online Systems Software | 1.6.1 Online Systems Software | 1.6.1.4 | OM Software | 1.6.1.4 OM Software | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.4.3.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.3.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.3.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.3.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.3.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.3.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.3.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.3.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.6 | 1.6.1.4.3.3 | C |  | UW | Develop and test OM testing app for DV testing - Jeff Weber | Weber | 0% | Labor Hours | SE |  |  | 40 | 51 | 35% | 2019-05-01 | 2019-10-21 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 40698 | 10947.15 | [5 empty] | 40698 |  | 0 | Labor - Task | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.1 | Online Systems Software | 1.6.1 Online Systems Software | 1.6.1.4 | OM Software | 1.6.1.4 OM Software | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 132d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.4.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.6 | 1.6.1.4.3.4.1 | C |  | UW | Capture design requirements for FAT testing OM software - Jeff Weber | Weber | 0% | Labor Hours | SE |  |  |  | 51 | 35% | 2019-10-23 | 2020-01-22 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 8757.72 | [7 empty] | 0 | Labor - Task | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.1 | Online Systems Software | 1.6.1 Online Systems Software | 1.6.1.4 | OM Software | 1.6.1.4 OM Software | cell-link@smartsheet.com | 2021-12-01 19:52 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.4.3.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.3.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.3.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.3.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.3.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.3.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.3.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.3.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.6 | 1.6.1.4.3.5 | C |  | UW | Develop and test OM testing app for FAT testing - Jeff Weber | Weber | 0% | Labor Hours | SE |  |  | 40 | 51 | 35% | 2020-01-23 | 2020-06-25 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 79366.8375 | [5 empty] | 24907 |  | 0 | Labor - Task | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.1 | Online Systems Software | 1.6.1 Online Systems Software | 1.6.1.4 | OM Software | 1.6.1.4 OM Software | cell-link@smartsheet.com | 2021-12-01 19:52 |  | 78d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.4.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.6 | 1.6.1.4.3.7 | C |  | UW | Extend OM testing app for mDOM, pDOM devices |  | 0% | Labor Hours | SE | TRUE |  |  | 55 | 35% | 2020-06-29 | 2020-11-27 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 0 | Labor - Task | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.1 | Online Systems Software | 1.6.1 Online Systems Software | 1.6.1.4 | OM Software | 1.6.1.4 OM Software | cell-link@smartsheet.com | 2021-12-01 20:15 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.4.3.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.3.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.3.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.3.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.3.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.3.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.3.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.3.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.6 | 1.6.1.4.3.8 | C |  | UW | Support OM testing app thru FAT testing cycles |  | 32.69% | Labor Hours | SE |  |  |  | 55 | 35% | 2020-11-30 | 2022-05-19 |  | TRUE |  |  | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 |  |  |  |  | 6311.25 | 6311.25 | 6311.25 | 6311.25 | 6311.25 | 6311.25 | 6311.25 | 6311.25 | 0 | 0 | 0 | 0 | 50490 | 53% | 26759.7 | 80607.1458 | 80607.1458 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 |  |  |  |  | 5197.5 | 5197.5 | 5197.5 | 5197.5 | 5197.5 | 5197.5 | 5197.5 | 5197.5 | 0 | 0 | 0 | 0 | 41580 | 53% | 22037.4 | 67809.576 | 67809.576 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 148416.7218 | Labor - Task | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.1 | Online Systems Software | 1.6.1 Online Systems Software | 1.6.1.4 | OM Software | 1.6.1.4 OM Software | cell-link@smartsheet.com | 2021-12-01 20:15 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.4.3.8 | 10075.8932 | 10075.8932 | 10075.8932 | 10075.8932 | 10075.8932 | 10075.8932 | 10075.8932 | 10075.8932 | 0 | 0 | 0 | 0 | 1.6.1.4.3.8 | 8476.197 | 8476.197 | 8476.197 | 8476.197 | 8476.197 | 8476.197 | 8476.197 | 8476.197 | 0 | 0 | 0 | 0 | 1.6.1.4.3.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.3.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.3.8 | 4878.186 | 4878.186 | 4878.186 | 4878.186 | 4878.186 | 4878.186 | 4878.186 | 4878.186 | 0 | 0 | 0 | 0 | 39025.4881 | 1.6.1.4.3.8 | 1707.3651 | 1707.3651 | 1707.3651 | 1707.3651 | 1707.3651 | 1707.3651 | 1707.3651 | 1707.3651 | 0 | 0 | 0 | 0 | 13658.9209 | 1.6.1.4.3.8 | 3490.3421 | 3490.3421 | 3490.3421 | 3490.3421 | 3490.3421 | 3490.3421 | 3490.3421 | 3490.3421 | 0 | 0 | 0 | 0 | 27922.7368 | 80607.1458 | 1.6.1.4.3.8 | 80607.1458 | 80607.1458 | 10075.8932 | 20151.7864 | 30227.6797 | 40303.5729 | 50379.4661 | 60455.3593 | 70531.2526 | 80607.1458 | 80607.1458 | 80607.1458 | 80607.1458 | 80607.1458 | 10075.8932 | 20151.7864 | 30227.6797 | 40303.5729 | 50379.4661 | 60455.3593 | 70531.2526 | 80607.1458 | 80607.1458 | 80607.1458 | 80607.1458 | 80607.1458
| 1.6 | 1.6.1.4.3.9 | C |  | UW | Develop SPAT testing software |  | 4.087% | Labor Hours | SE |  |  |  | 55 | 35% | 2022-08-31 | 2022-10-31 |  | TRUE | [13 empty] | 85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6311.25 | 6311.25 | 53% | 3344.9625 | 10075.8932 | 10075.8932 | [11 empty] | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5197.5 | 5197.5 | 53% | 2754.675 | 8476.197 | 8476.197 | 35 | 35 | [10 empty] | 2598.75 | 2598.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5197.5 | 53% | 2754.675 | 8658.4352 | 8658.4352 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 27210.5255 | Labor - Task | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.1 | Online Systems Software | 1.6.1 Online Systems Software | 1.6.1.4 | OM Software | 1.6.1.4 OM Software | cell-link@smartsheet.com | 2021-12-01 20:15 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.4.3.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10075.8932 | 1.6.1.4.3.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8476.197 | 1.6.1.4.3.9 | 4329.2176 | 4329.2176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.3.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.3.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4878.186 | 4878.186 | 1.6.1.4.3.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1707.3651 | 1707.3651 | 1.6.1.4.3.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3490.3421 | 3490.3421 | 10075.8932 | 1.6.1.4.3.9 | 10075.8932 | 10075.8932 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10075.8932 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10075.8932
| 1.6 | 1.6.1.4.4.1 | C |  | UW | Capture design requirements for OM calibration collection app - Jeff Weber | Weber | 0% | Labor Hours | SE | TRUE |  | 40 | 51 | 35% | 2020-02-03 | 2020-03-13 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 13683.9375 | [5 empty] | 10378 |  | 0 | Labor - Task | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.1 | Online Systems Software | 1.6.1 Online Systems Software | 1.6.1.4 | OM Software | 1.6.1.4 OM Software | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 35d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.4.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.6 | 1.6.1.4.4.2 | C |  | UW | Software design and prototyping of OM data calibration app - Jeff Weber | Weber | 0% | Labor Hours | SE | TRUE |  | 40 | 51 | 35% | 2020-03-16 | 2020-05-01 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 16420.725 | [5 empty] | 13284 |  | 0 | Labor - Task | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.1 | Online Systems Software | 1.6.1 Online Systems Software | 1.6.1.4 | OM Software | 1.6.1.4 OM Software | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 41d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.4.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.6 | 1.6.1.4.4.3 | C |  | UW | Develop and test OM data calibration app - Jeff Weber | Weber | 0% | Labor Hours | SE |  |  | 40 | 51 | 35% | 2020-05-04 | 2021-01-01 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 87577.2 | 21171 |  |  |  |  | 80948 |  | 0 | Labor - Task | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.1 | Online Systems Software | 1.6.1 Online Systems Software | 1.6.1.4 | OM Software | 1.6.1.4 OM Software | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 209d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.4.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.6 | 1.6.1.4.5.1 | C |  | UW | xDOMapp design development |  | 0% | Labor Hours | SE |  |  |  | 55 | 35% | 2020-12-01 | 2021-10-15 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 0 | Labor - Task | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.1 | Online Systems Software | 1.6.1 Online Systems Software | 1.6.1.4 | OM Software | 1.6.1.4 OM Software | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.4.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.6 | 1.6.1.4.5.3 | C |  | UW | Prototype xDOMapp development and testing at NTS |  | 0% | Labor Hours | SE |  |  | 40 | 55 | 35% | 2021-11-01 | 2022-01-14 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 | 10586 |  |  |  |  | 10586 |  | 0 | Labor - Task | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.1 | Online Systems Software | 1.6.1 Online Systems Software | 1.6.1.4 | OM Software | 1.6.1.4 OM Software | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 38d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.4.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.6 | 1.6.1.4.5.4 | C |  | UW | Software design and prototyping of OM data collection app |  | 12.26% | Labor Hours | SE |  |  | 40 | 55 | 35% | 2022-06-15 | 2022-08-31 |  | TRUE | [10 empty] | 85 | 85 | 85 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6311.25 | 6311.25 | 6311.25 | 0 | 18933.75 | 53% | 10034.8875 | 30227.6797 | 30227.6797 | [8 empty] | 70 | 70 | 70 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5197.5 | 5197.5 | 5197.5 | 0 | 15592.5 | 53% | 8264.025 | 25428.591 | 25428.591 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 | 13550 |  |  |  |  | 13550 |  | 55656.2707 | Labor - Task | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.1 | Online Systems Software | 1.6.1 Online Systems Software | 1.6.1.4 | OM Software | 1.6.1.4 OM Software | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 38d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.4.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10075.8932 | 10075.8932 | 10075.8932 | 0 | 1.6.1.4.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8476.197 | 8476.197 | 8476.197 | 0 | 1.6.1.4.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4878.186 | 4878.186 | 4878.186 | 0 | 14634.5581 | 1.6.1.4.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1707.3651 | 1707.3651 | 1707.3651 | 0 | 5122.0953 | 1.6.1.4.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3490.3421 | 3490.3421 | 3490.3421 | 0 | 10471.0263 | 30227.6797 | 1.6.1.4.5.4 | 30227.6797 | 30227.6797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10075.8932 | 20151.7864 | 30227.6797 | 30227.6797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10075.8932 | 20151.7864 | 30227.6797 | 30227.6797
| 1.6 | 1.6.1.4.5.6 | C |  | UW | Develop and test OM data collection app |  | 1.923% | Labor Hours | SE | TRUE |  | 40 | 55 | 35% | 2022-09-14 | 2023-06-19 | [15 empty] | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2970 | 2970 | 53% | 1574.1 | 4741.5968 | -81636.4032 | [11 empty] | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2970 | 2970 | 53% | 1574.1 | 4843.5411 | 4843.5411 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 |  |  |  | 2970 | 2970 | 2970 | 2970 | 2970 | 2970 | 2970 | 2970 | 2970 | 0 | 0 | 0 | 26730 | 53% | 14166.9 | 44529.0955 | 44529.0955 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 |  | 86378 |  |  |  | 86378 |  | 54114.2334 | Labor - Task | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.1 | Online Systems Software | 1.6.1 Online Systems Software | 1.6.1.4 | OM Software | 1.6.1.4 OM Software | cell-link@smartsheet.com | 2021-12-01 20:00 |  | 239d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.4.5.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4741.5968 | 1.6.1.4.5.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4843.5411 | 1.6.1.4.5.6 | 4947.6773 | 4947.6773 | 4947.6773 | 4947.6773 | 4947.6773 | 4947.6773 | 4947.6773 | 4947.6773 | 4947.6773 | 0 | 0 | 0 | 1.6.1.4.5.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.5.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2295.617 | 2295.617 | 1.6.1.4.5.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 803.4659 | 803.4659 | 1.6.1.4.5.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1642.5139 | 1642.5139 | 4741.5968 | 1.6.1.4.5.6 | 4741.5968 | 4741.5968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4741.5968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4741.5968
| 1.6 | 1.6.1.4.5.8 | C |  | UW | Support xDOMapp through SPAT testing and deployment |  | 0% | Labor Hours | SE |  |  |  | 55 | 35% | 2022-12-01 | 2024-05-31 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 |  |  | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 0 | 0 | 2598.75 | 2598.75 | 2598.75 | 2598.75 | 2598.75 | 2598.75 | 2598.75 | 2598.75 | 2598.75 | 2598.75 | 25987.5 | 53% | 13773.375 | 43292.1762 | 43292.1762 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 |  |  |  |  | 2227.5 | 2227.5 | 2227.5 | 2227.5 | 2227.5 | 2227.5 | 2227.5 | 2227.5 | 0 | 0 | 0 | 0 | 17820 | 53% | 9444.6 | 30324.314 | [9 empty] | 73616.4902 | Labor - Task | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.1 | Online Systems Software | 1.6.1 Online Systems Software | 1.6.1.4 | OM Software | 1.6.1.4 OM Software | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.4.5.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.5.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.5.8 | 0 | 0 | 4329.2176 | 4329.2176 | 4329.2176 | 4329.2176 | 4329.2176 | 4329.2176 | 4329.2176 | 4329.2176 | 4329.2176 | 4329.2176 | 1.6.1.4.5.8 | 3790.5393 | 3790.5393 | 3790.5393 | 3790.5393 | 3790.5393 | 3790.5393 | 3790.5393 | 3790.5393 | 0 | 0 | 0 | 0 | 1.6.1.4.5.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.5.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.5.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.5.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.6 | 1.6.1.4.6.1 | C |  | UW | Develop and test MMB software package on prototype MMB |  | 0% | Labor Hours | SE | TRUE |  |  | 55 | 35% | 2021-06-01 | 2021-10-29 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 0 | Labor - Task | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.1 | Online Systems Software | 1.6.1 Online Systems Software | 1.6.1.4 | OM Software | 1.6.1.4 OM Software | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.4.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.6 | 1.6.1.4.6.3 | C |  | UW | Complete MMB software support package for calibration devices |  | 0% | Labor Hours | SE | TRUE |  |  | 55 | 35% | 2022-05-13 | 2022-09-13 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 0 | Labor - Task | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.1 | Online Systems Software | 1.6.1 Online Systems Software | 1.6.1.4 | OM Software | 1.6.1.4 OM Software | cell-link@smartsheet.com | 2021-12-01 20:15 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.4.6.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.6.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.6.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.6.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.6.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.6.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.6.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.6.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.6 | 1.6.1.4.6.5 | C |  | UW | Support MMB-xDOMapp software for calibration devices |  | 11.54% | Labor Hours | SE | TRUE |  |  | 55 | 35% | 2022-09-29 | 2024-02-14 |  |  |  |  | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 1485 | 1485 | 1485 | 1485 | 1485 | 1485 | 1485 | 1485 | 1485 | 1485 | 1485 | 1485 | 17820 | 53% | 9444.6 | 28449.5809 | 28449.5809 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 1485 | 1485 | 1485 | 1485 | 1485 | 1485 | 1485 | 1485 | 1485 | 1485 | 1485 | 1485 | 17820 | 53% | 9444.6 | 29061.2468 | 29061.2468 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 742.5 | 742.5 | 742.5 | 742.5 | 742.5 | 742.5 | 742.5 | 742.5 | 742.5 | 742.5 | 742.5 | 742.5 | 8910 | 53% | 4722.3 | 14843.0318 | 14843.0318 | 10 | 10 | 10 | 10 | 10 | 10 | [6 empty] | 742.5 | 742.5 | 742.5 | 742.5 | 742.5 | 742.5 | 0 | 0 | 0 | 0 | 0 | 0 | 4455 | 53% | 2361.15 | 7581.0785 | [9 empty] | 79934.938 | Labor - Task | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.1 | Online Systems Software | 1.6.1 Online Systems Software | 1.6.1.4 | OM Software | 1.6.1.4 OM Software | cell-link@smartsheet.com | 2021-12-01 20:00 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.4.6.5 | 2370.7984 | 2370.7984 | 2370.7984 | 2370.7984 | 2370.7984 | 2370.7984 | 2370.7984 | 2370.7984 | 2370.7984 | 2370.7984 | 2370.7984 | 2370.7984 | 1.6.1.4.6.5 | 2421.7706 | 2421.7706 | 2421.7706 | 2421.7706 | 2421.7706 | 2421.7706 | 2421.7706 | 2421.7706 | 2421.7706 | 2421.7706 | 2421.7706 | 2421.7706 | 1.6.1.4.6.5 | 1236.9193 | 1236.9193 | 1236.9193 | 1236.9193 | 1236.9193 | 1236.9193 | 1236.9193 | 1236.9193 | 1236.9193 | 1236.9193 | 1236.9193 | 1236.9193 | 1.6.1.4.6.5 | 1263.5131 | 1263.5131 | 1263.5131 | 1263.5131 | 1263.5131 | 1263.5131 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.4.6.5 | 1147.8085 | 1147.8085 | 1147.8085 | 1147.8085 | 1147.8085 | 1147.8085 | 1147.8085 | 1147.8085 | 1147.8085 | 1147.8085 | 1147.8085 | 1147.8085 | 13773.7017 | 1.6.1.4.6.5 | 401.733 | 401.733 | 401.733 | 401.733 | 401.733 | 401.733 | 401.733 | 401.733 | 401.733 | 401.733 | 401.733 | 401.733 | 4820.7956 | 1.6.1.4.6.5 | 821.257 | 821.257 | 821.257 | 821.257 | 821.257 | 821.257 | 821.257 | 821.257 | 821.257 | 821.257 | 821.257 | 821.257 | 9855.0836 | 28449.5809 | 1.6.1.4.6.5 | 28449.5809 | 28449.5809 | 2370.7984 | 4741.5968 | 7112.3952 | 9483.1936 | 11853.992 | 14224.7904 | 16595.5888 | 18966.3872 | 21337.1856 | 23707.9841 | 26078.7825 | 28449.5809 | 2370.7984 | 4741.5968 | 7112.3952 | 9483.1936 | 11853.992 | 14224.7904 | 16595.5888 | 18966.3872 | 21337.1856 | 23707.9841 | 26078.7825 | 28449.5809
| 1.6 | 1.6.1.5.1 | C |  | UW | maintenance of mini-FieldHub server software for FAT |  | 3.606% | Labor Hours | SC | TRUE |  |  | 45 | 35% | 2021-01-01 | 2021-12-31 |  |  |  |  | 25 | 25 | 25 | [9 empty] | 1518.75 | 1518.75 | 1518.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4556.25 | 53% | 2414.8125 | 7274.0406 | 7274.0406 | 25 | 25 | 25 | [9 empty] | 1518.75 | 1518.75 | 1518.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4556.25 | 53% | 2414.8125 | 7430.4324 | 7430.4324 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 14704.473 | Labor - Task | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.1 | Online Systems Software | 1.6.1 Online Systems Software | 1.6.1.5 | FieldHub Software | 1.6.1.5 FieldHub Software | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.5.1 | 2424.6802 | 2424.6802 | 2424.6802 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.5.1 | 2476.8108 | 2476.8108 | 2476.8108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.5.1 | 1173.895 | 1173.895 | 1173.895 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3521.6851 | 1.6.1.5.1 | 410.8633 | 410.8633 | 410.8633 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1232.5898 | 1.6.1.5.1 | 839.9219 | 839.9219 | 839.9219 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2519.7657 | 7274.0406 | 1.6.1.5.1 | 7274.0406 | 7274.0406 | 2424.6802 | 4849.3604 | 7274.0406 | 7274.0406 | 7274.0406 | 7274.0406 | 7274.0406 | 7274.0406 | 7274.0406 | 7274.0406 | 7274.0406 | 7274.0406 | 2424.6802 | 4849.3604 | 7274.0406 | 7274.0406 | 7274.0406 | 7274.0406 | 7274.0406 | 7274.0406 | 7274.0406 | 7274.0406 | 7274.0406 | 7274.0406
| 1.6 | 1.6.1.5.2 | C |  | UW | development and testing of FieldHub SBC OS and toolchain |  | 0% | Labor Hours | SC | TRUE |  |  | 45 | 35% | 2021-06-01 | 2021-07-30 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 0 | Labor - Task | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.1 | Online Systems Software | 1.6.1 Online Systems Software | 1.6.1.5 | FieldHub Software | 1.6.1.5 FieldHub Software | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.6 | 1.6.1.5.3 | C |  | UW | modification of FieldHub server software to support full FieldHub functionality |  | 15.38% | Labor Hours | SC | TRUE |  |  | 45 | 35% | 2022-01-14 | 2022-04-29 | [7 empty] | 80 | 80 | 80 | 80 | [5 empty] | 0 | 0 | 0 | 4860 | 4860 | 4860 | 4860 | 0 | 0 | 0 | 0 | 0 | 19440 | 53% | 10303.2 | 31035.9064 | 31035.9064 |  |  |  | 80 | 80 | 80 | 80 | [5 empty] | 0 | 0 | 0 | 4860 | 4860 | 4860 | 4860 | 0 | 0 | 0 | 0 | 0 | 19440 | 53% | 10303.2 | 31703.1784 | 31703.1784 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 62739.0848 | Labor - Task | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.1 | Online Systems Software | 1.6.1 Online Systems Software | 1.6.1.5 | FieldHub Software | 1.6.1.5 FieldHub Software | cell-link@smartsheet.com | 2021-12-01 20:00 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.5.3 | 0 | 0 | 0 | 7758.9766 | 7758.9766 | 7758.9766 | 7758.9766 | 0 | 0 | 0 | 0 | 0 | 1.6.1.5.3 | 0 | 0 | 0 | 7925.7946 | 7925.7946 | 7925.7946 | 7925.7946 | 0 | 0 | 0 | 0 | 0 | 1.6.1.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.5.3 | 0 | 0 | 0 | 3756.4641 | 3756.4641 | 3756.4641 | 3756.4641 | 0 | 0 | 0 | 0 | 0 | 15025.8564 | 1.6.1.5.3 | 0 | 0 | 0 | 1314.7624 | 1314.7624 | 1314.7624 | 1314.7624 | 0 | 0 | 0 | 0 | 0 | 5259.0497 | 1.6.1.5.3 | 0 | 0 | 0 | 2687.7501 | 2687.7501 | 2687.7501 | 2687.7501 | 0 | 0 | 0 | 0 | 0 | 10751.0003 | 31035.9064 | 1.6.1.5.3 | 31035.9064 | 31035.9064 | 0 | 0 | 0 | 7758.9766 | 15517.9532 | 23276.9298 | 31035.9064 | 31035.9064 | 31035.9064 | 31035.9064 | 31035.9064 | 31035.9064 | 0 | 0 | 0 | 7758.9766 | 15517.9532 | 23276.9298 | 31035.9064 | 31035.9064 | 31035.9064 | 31035.9064 | 31035.9064 | 31035.9064
| 1.6 | 1.6.1.5.5 | C |  | UW | development of FieldHub monitoring software (IceCube Live interface) |  | 0% | Labor Hours | SC | TRUE |  |  | 45 | 35% | 2022-09-29 | 2022-11-28 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | 50 | 50 | [10 empty] | 3037.5 | 3037.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6075 | 53% | 3219.75 | 10120.249 | 10120.249 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 10120.249 | Labor - Task | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.1 | Online Systems Software | 1.6.1 Online Systems Software | 1.6.1.5 | FieldHub Software | 1.6.1.5 FieldHub Software | cell-link@smartsheet.com | 2021-12-01 20:15 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.5.5 | 5060.1245 | 5060.1245 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.6 | 1.6.1.5.6 | C |  | UW | development of FieldHub / pDAQ StringHub interface layer |  | 0% | Labor Hours | SC | TRUE |  |  | 45 | 35% | 2022-11-14 | 2023-05-11 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 |  | 80 | 80 | 80 | 80 | 80 | 80 | [5 empty] | 0 | 4860 | 4860 | 4860 | 4860 | 4860 | 4860 | 0 | 0 | 0 | 0 | 0 | 29160 | 53% | 15454.8 | 48577.1951 | 48577.1951 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | [9 empty] | 48577.1951 | Labor - Task | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.1 | Online Systems Software | 1.6.1 Online Systems Software | 1.6.1.5 | FieldHub Software | 1.6.1.5 FieldHub Software | cell-link@smartsheet.com | 2021-12-01 20:15 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.5.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.5.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.5.6 | 0 | 8096.1992 | 8096.1992 | 8096.1992 | 8096.1992 | 8096.1992 | 8096.1992 | 0 | 0 | 0 | 0 | 0 | 1.6.1.5.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.5.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.5.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.5.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.5.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 | 1.6.1.6 | P |  | PSU | mDOM Final Design Review (T. Anderson) | Anderson | 1.923% | Labor Hours | SE |  |  | 55 | 55 | 40% | 2018-12-17 | 2022-07-18 | [5 empty] | 40 | [10 empty] | 0 | 3080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3080 | 58.05% | 1787.94 | 5079.5116 | 5079.5116 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 |  | 3398.7072 | [5 empty] | 4524 |  | 5079.5116 | Labor - Task | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.6.1 | mDOM | 1.6.1 mDOM | 1.6.1.6 | Integrated mDOM | 1.6.1.6 Integrated mDOM | cell-link@smartsheet.com | 2021-12-01 20:00 |  | 1235d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.6 | 0 | 5079.5116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6 | 0 | 2295.617 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2295.617 | 1.6.1.6 | 0 | 918.2468 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 918.2468 | 1.6.1.6 | 0 | 1865.6479 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1865.6479 | 5079.5116 | 1.6.1.6 | 5079.5116 | 5079.5116 | 0 | 5079.5116 | 5079.5116 | 5079.5116 | 5079.5116 | 5079.5116 | 5079.5116 | 5079.5116 | 5079.5116 | 5079.5116 | 5079.5116 | 5079.5116 | 0 | 5079.5116 | 5079.5116 | 5079.5116 | 5079.5116 | 5079.5116 | 5079.5116 | 5079.5116 | 5079.5116 | 5079.5116 | 5079.5116 | 5079.5116
| 1.6 | 1.6.1.6 | P |  | PSU | mDOM Preliminary Design Review | Anderson | 0% | Labor Hours | SE |  |  | 55 | 55 | 40% | 2018-12-17 | 2022-07-18 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 4435 | 0 | [5 empty] | 4435 |  | 0 | Labor - Task | Off Ice | 1.6 | Sensors | 1.6 Sensors | 1.6.1 | mDOM | 1.6.1 mDOM | 1.6.1.6 | mDOM | 1.6.1.6 mDOM | cell-link@smartsheet.com | 2021-12-01 20:00 |  | 1235d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 | 1.6.1.6.1.1.1 | C |  | PSU | Build 4 ch. analog-front end (AFE) demonstrator board | Anderson | 0% | Labor Hours | SE |  |  | 55 | 55 | 40% | 2018-12-17 | 2019-02-22 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 17741 | 0 | [5 empty] | 17741 |  | 0 | Labor - Task | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.6.1 | mDOM | 1.6.1 mDOM | 1.6.1.6 | mDOM DAQ Electronics | 1.6.1.6 mDOM DAQ Electronics | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 59d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.6.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 | 1.6.1.6.1.1.1 | C |  | PSU | Build 4 ch. analog-front end (AFE) demonstrator board |  |  | M & S |  |  |  | 1 | 1 | 0% | 2018-12-17 | 2019-02-22 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 7481 | 0 | [5 empty] | 7481 |  | 0 | M & S | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.6.1 | mDOM | 1.6.1 mDOM | 1.6.1.6 | mDOM DAQ Electronics | 1.6.1.6 mDOM DAQ Electronics | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 59d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.6.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 | 1.6.1.6.1.1.1 | C |  | PSU | Foreign trip to coordinate firmware design and interfaces |  |  | Travel |  |  |  | 1 | 1 | 0% | 2018-12-17 | 2019-02-22 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 4608 | 0 | [5 empty] | 4608 |  | 0 | Travel | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.6.1 | mDOM | 1.6.1 mDOM | 1.6.1.6 | mDOM DAQ Electronics | 1.6.1.6 mDOM DAQ Electronics | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 59d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.6.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 | 1.6.1.6.1.1.2 | C |  | PSU | Characterization of AFE performance | Anderson | 0% | Labor Hours | SE |  |  | 55 | 55 | 40% | 2019-02-25 | 2019-03-22 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 13306 | 0 | [5 empty] | 13306 |  | 0 | Labor - Task | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.6.1 | mDOM | 1.6.1 mDOM | 1.6.1.6 | mDOM DAQ Electronics | 1.6.1.6 mDOM DAQ Electronics | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 23d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.6.1.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.1.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.1.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.1.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.1.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.1.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.1.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.1.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 | 1.6.1.6.1.1.2 | C |  | PSU | Characterization of AFE performance |  | 0% | Labor Hours | PO |  |  | 30 | 30 | 40% | 2019-02-25 | 2019-03-22 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 7258 | 0 | [5 empty] | 7258 |  | 0 | Labor - Task | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.6.1 | mDOM | 1.6.1 mDOM | 1.6.1.6 | mDOM DAQ Electronics | 1.6.1.6 mDOM DAQ Electronics | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 23d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.6.1.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.1.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.1.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.1.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.1.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.1.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.1.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.1.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 | 1.6.1.6.1.1.2 | C |  | PSU | Characterization of AFE performance |  |  | M & S |  |  |  | 1 | 1 | 0% | 2019-02-25 | 2019-03-22 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 7998 | 0 | [5 empty] | 7998 |  | 0 | M & S | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.6.1 | mDOM | 1.6.1 mDOM | 1.6.1.6 | mDOM DAQ Electronics | 1.6.1.6 mDOM DAQ Electronics | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 23d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.6.1.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.1.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.1.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.1.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.1.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.1.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.1.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.1.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 | 1.6.1.6.1.1.2 | C |  | PSU | Foreign trips to participate in testing and characterization |  |  | Travel |  |  |  | 1 | 1 | 0% | 2019-02-25 | 2019-03-22 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 9216 | 0 | [5 empty] | 9216 |  | 0 | Travel | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.6.1 | mDOM | 1.6.1 mDOM | 1.6.1.6 | mDOM DAQ Electronics | 1.6.1.6 mDOM DAQ Electronics | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 23d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.6.1.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.1.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.1.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.1.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.1.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.1.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.1.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.1.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 | 1.6.1.6.1.2 | C |  | PSU | Firmware development | Anderson | 0% | Labor Hours | SE |  |  | 55 | 55 | 40% | 2020-01-02 | 2021-09-30 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 62093 | 23790.9504 | [5 empty] | 62093 |  | 0 | Labor - Task | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.6.1 | mDOM | 1.6.1 mDOM | 1.6.1.6 | mDOM DAQ Electronics | 1.6.1.6 mDOM DAQ Electronics | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 119d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TRUE | 1.3 | 1.6.1.6.1.2 | C |  | PSU | Firmware development | Fienberg | 0% | Labor Hours | PO |  |  |  | 30 | 40% | 2020-01-02 | 2021-09-30 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | [9 empty] | 0 | Labor - Task | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.6.1 | mDOM | 1.6.1 mDOM | 1.6.1.6 | mDOM DAQ Electronics | 1.6.1.6 mDOM DAQ Electronics | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TRUE | 1.3 | 1.6.1.6.1.2 | C |  | PSU | Work-from-home kit for firmware development (Anderson) |  |  | M & S |  |  | CP | 1 | 1 | 0% | 2020-01-02 | 2021-09-30 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | [9 empty] | 0 | M & S | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.6.1 | mDOM | 1.6.1 mDOM | 1.6.1.6 | mDOM DAQ Electronics | 1.6.1.6 mDOM DAQ Electronics | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TRUE | 1.3 | 1.6.1.6.1.2 | C |  | PSU | Work-from-home kit for firmware development (Fienberg) |  |  | M & S |  |  | CP |  | 1 | 0% | 2020-01-02 | 2021-09-30 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | [9 empty] | 0 | M & S | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.6.1 | mDOM | 1.6.1 mDOM | 1.6.1.6 | mDOM DAQ Electronics | 1.6.1.6 mDOM DAQ Electronics | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 | 1.6.1.6.1.3 | C |  | PSU | Pulsed Laser Test Stand for Design verification |  |  | M & S |  |  | CP | 1 | 1 | 0% | 2021-06-07 | 2021-07-02 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 1440 | 790.25 | [5 empty] | 2160 |  | 0 | M & S | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.6.1 | mDOM | 1.6.1 mDOM | 1.6.1.6 | mDOM DAQ Electronics | 1.6.1.6 mDOM DAQ Electronics | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 71d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.6.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TRUE | 1.6 | 1.6.1.6.1.5 | C |  | PSU | Firmware Support for preparation of mDOM FAT | Anderson | 0.7692% | Labor Hours | SE |  |  |  | 55 | 40% | 2021-07-26 | 2021-09-03 |  | TRUE | TRUE |  |  |  | 8 | 8 | [8 empty] | 0 | 0 | 616 | 616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1232 | 58.05% | 715.176 | 2031.8047 | 2031.8047 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | [9 empty] | 2031.8047 | Labor - Task | Off Ice | 1.6 | Sensors | 1.6 Sensors | 1.6.1 | mDOM | 1.6.1 mDOM | 1.6.1.6 | mDOM Production Facilities | 1.6.1.6 mDOM Production Facilities | marek.rogal@icecube.wisc.edu | 2021-11-09 09:23 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.6.1.5 | 0 | 0 | 1015.9023 | 1015.9023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.1.5 | 0 | 0 | 459.1234 | 459.1234 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 918.2468 | 1.6.1.6.1.5 | 0 | 0 | 183.6494 | 183.6494 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 367.2987 | 1.6.1.6.1.5 | 0 | 0 | 373.1296 | 373.1296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 746.2592 | 2031.8047 | 1.6.1.6.1.5 | 2031.8047 | 6464.833 | 0 | 0 | 1015.9023 | 2031.8047 | 2031.8047 | 2031.8047 | 2031.8047 | 2031.8047 | 2031.8047 | 2031.8047 | 2031.8047 | 2031.8047 | 0 | 0 | 3232.4165 | 6464.833 | 6464.833 | 6464.833 | 6464.833 | 6464.833 | 6464.833 | 6464.833 | 6464.833 | 6464.833
TRUE | 1.6 | 1.6.1.6.1.5 | C |  | PSU | Firmware Support for preparation of mDOM FAT | Fienberg | 3.077% | Labor Hours | PO |  |  |  | 30 | 40% | 2021-07-26 | 2021-09-03 |  | TRUE | TRUE |  |  |  | 32 | 32 | [8 empty] | 0 | 0 | 1344 | 1344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2688 | 58.05% | 1560.384 | 4433.0283 | 4433.0283 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | [9 empty] | 4433.0283 | Labor - Task | Off Ice | 1.6 | Sensors | 1.6 Sensors | 1.6.1 | mDOM | 1.6.1 mDOM | 1.6.1.6 | mDOM Production Facilities | 1.6.1.6 mDOM Production Facilities | marek.rogal@icecube.wisc.edu | 2021-11-09 09:23 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.6.1.5 | 0 | 0 | 2216.5142 | 2216.5142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.1.5 | 0 | 0 | 1001.7238 | 1001.7238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2003.4475 | 1.6.1.6.1.5 | 0 | 0 | 400.6895 | 400.6895 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 801.379 | 1.6.1.6.1.5 | 0 | 0 | 814.1009 | 814.1009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1628.2018 | 4433.0283 | 1.6.1.6.1.5 | 4433.0283 | 4433.0283 | 0 | 0 | 2216.5142 | 4433.0283 | 4433.0283 | 4433.0283 | 4433.0283 | 4433.0283 | 4433.0283 | 4433.0283 | 4433.0283 | 4433.0283 | 0 | 0 | 2216.5142 | 4433.0283 | 4433.0283 | 4433.0283 | 4433.0283 | 4433.0283 | 4433.0283 | 4433.0283 | 4433.0283 | 4433.0283
| 1.3 | 1.6.1.6.2.1 | C |  | PSU | Firmware development | Anderson | 0% | Labor Hours | SE |  |  |  | 55 | 40% | 2019-05-01 | 2021-03-31 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 |  | 10196.1216 | [7 empty] | 0 | Labor - Task | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.6.1 | D-Egg | 1.6.1 D-Egg | 1.6.1.6 | D-Egg DAQ Electronics | 1.6.1.6 D-Egg DAQ Electronics | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.6.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TRUE | 1.3 | 1.6.1.6.2.1 | C |  | PSU | Firmware development | Fienberg | 0% | Labor Hours | PO |  |  |  | 30 | 40% | 2019-05-01 | 2021-03-31 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | [9 empty] | 0 | Labor - Task | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.6.1 | D-Egg | 1.6.1 D-Egg | 1.6.1.6 | D-Egg DAQ Electronics | 1.6.1.6 D-Egg DAQ Electronics | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.6.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 | 1.6.1.6.2.2 | C |  | PSU | Design Verification (T. Anderson) | Anderson | 0% | Labor Hours | SE |  |  |  | 55 | 40% | 2019-12-19 | 2020-02-26 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 |  | 10196.1216 | [7 empty] | 0 | Labor - Task | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.6.1 | D-Egg | 1.6.1 D-Egg | 1.6.1.6 | D-Egg DAQ Electronics | 1.6.1.6 D-Egg DAQ Electronics | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.6.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 | 1.6.1.6.2.2 | C |  | PSU | Design Verification | Fienberg | 0% | Labor Hours | PO |  |  |  | 30 | 40% | 2019-12-19 | 2020-02-26 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 |  | 13276.2 | [7 empty] | 0 | Labor - Task | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.6.1 | D-Egg | 1.6.1 D-Egg | 1.6.1.6 | D-Egg DAQ Electronics | 1.6.1.6 D-Egg DAQ Electronics | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.6.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 | 1.6.1.6.3.1 | C |  | PSU | Integrated D-Egg Design Verification Test (T. Anderson) | Anderson | 0% | Labor Hours | SE |  |  |  | 55 | 40% | 2019-11-11 | 2020-01-03 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 |  | 12490.249 | [7 empty] | 0 | Labor - Task | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.6.1 | D-Egg | 1.6.1 D-Egg | 1.6.1.6 | Integrated D-Egg | 1.6.1.6 Integrated D-Egg | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.6.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 | 1.6.1.6.3.1 | C |  | PSU | Integrated D-Egg Design Verification Test | Fienberg | 0% | Labor Hours | PO |  |  |  | 30 | 40% | 2019-11-11 | 2020-01-03 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 |  | 13276.2 | [7 empty] | 0 | Labor - Task | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.6.1 | D-Egg | 1.6.1 D-Egg | 1.6.1.6 | Integrated D-Egg | 1.6.1.6 Integrated D-Egg | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.6.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 | 1.6.1.6.3.1 | C |  | PSU | Foreign trip to participate in DVT activities in Chiba |  |  | Travel |  |  |  |  | 1 | 0% | 2019-11-11 | 2020-01-03 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 |  | 0 | [7 empty] | 0 | Travel | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.6.1 | D-Egg | 1.6.1 D-Egg | 1.6.1.6 | Integrated D-Egg | 1.6.1.6 Integrated D-Egg | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.6.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 | 1.6.1.6.3.2 | C |  | PSU | D-Egg Final Design Review (T. Anderson) | Anderson | 0% | Labor Hours | SE |  |  |  | 55 | 40% | 2019-11-25 | 2019-11-25 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 |  | 3398.7072 | [7 empty] | 0 | Labor - Task | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.6.1 | D-Egg | 1.6.1 D-Egg | 1.6.1.6 | Integrated D-Egg | 1.6.1.6 Integrated D-Egg | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.6.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 | 1.6.1.6.4.1 | C |  | PSU | Firmware |  | 0% | Labor Hours | SE |  |  | 55 | 55 | 40% | 2019-03-01 | 2019-07-18 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 39917 | 0 | [5 empty] | 39917 |  | 0 | Labor - Task | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.6.1 | PDOM | 1.6.1 PDOM | 1.6.1.6 | PDOM DAQ Electronics | 1.6.1.6 PDOM DAQ Electronics | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 120d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.6.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 | 1.6.1.6.4.1 | C |  | PSU | Domestic trips to coordinate firmware / hardware development |  |  | Travel |  |  |  | 1 | 1 | 0% | 2019-03-01 | 2019-07-18 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 10368 | 0 | [5 empty] | 10368 |  | 0 | Travel | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.6.1 | PDOM | 1.6.1 PDOM | 1.6.1.6 | PDOM DAQ Electronics | 1.6.1.6 PDOM DAQ Electronics | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 120d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.6.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 | 1.6.1.6.4.2 | C |  | PSU | Testing (T. Anderson) | Anderson | 0% | Labor Hours | SE |  |  | 55 | 55 | 40% | 2019-07-19 | 2019-10-31 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 13306 | 4503.287 | [5 empty] | 22353 |  | 0 | Labor - Task | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.6.1 | PDOM | 1.6.1 PDOM | 1.6.1.6 | PDOM DAQ Electronics | 1.6.1.6 PDOM DAQ Electronics | cell-link@smartsheet.com | 2021-12-01 20:00 |  | 89d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.6.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 | 1.6.1.6.4.2 | C |  | PSU | Testing | Fienberg | 0% | Labor Hours | PO |  |  | 30 | 30 | 40% | 2019-07-19 | 2019-10-31 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 4838 | 4425.4 | [5 empty] | 12241 |  | 0 | Labor - Task | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.6.1 | PDOM | 1.6.1 PDOM | 1.6.1.6 | PDOM DAQ Electronics | 1.6.1.6 PDOM DAQ Electronics | cell-link@smartsheet.com | 2021-12-01 20:00 |  | 89d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.6.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 | 1.6.1.6.4.2 | C |  | PSU | Testing |  |  | M & S |  |  |  | 1 | 1 | 0% | 2019-07-19 | 2019-10-31 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 32134 | 5722.9905 | [5 empty] | 37348 |  | 0 | M & S | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.6.1 | PDOM | 1.6.1 PDOM | 1.6.1.6 | PDOM DAQ Electronics | 1.6.1.6 PDOM DAQ Electronics | cell-link@smartsheet.com | 2021-12-01 20:00 |  | 89d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.6.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 | 1.6.1.6.4.2 | C |  | PSU | Foreign trip to Chiba to support setting up testing infrastructure for common D-Egg PDOM Mainboard |  |  | Travel |  |  |  | 1 | 1 | 0% | 2019-07-19 | 2019-10-31 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 4608 | 0 | [5 empty] | 4608 |  | 0 | Travel | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.6.1 | PDOM | 1.6.1 PDOM | 1.6.1.6 | PDOM DAQ Electronics | 1.6.1.6 PDOM DAQ Electronics | cell-link@smartsheet.com | 2021-12-01 20:00 |  | 89d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.6.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.6 | 1.6.1.6.4.4 | C |  | PSU | Testing (T. Anderson) | Anderson | 0% | Labor Hours | SE |  |  | 55 | 55 | 40% | 2021-10-01 | 2022-07-15 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 |  | 6797.4144 | [5 empty] | 9048 |  | 0 | Labor - Task | Off Ice | 1.6 | Sensors | 1.6 Sensors | 1.6.1 | PDOM | 1.6.1 PDOM | 1.6.1.6 | PDOM DAQ Electronics | 1.6.1.6 PDOM DAQ Electronics | marek.rogal@icecube.wisc.edu | 2021-11-09 09:23 |  | 35d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.6.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.6 | 1.6.1.6.4.4 | C |  | PSU | Testing | Fienberg | 0% | Labor Hours | PO |  |  | 30 | 30 | 40% | 2021-10-01 | 2022-07-15 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 |  | 4425.4 | [5 empty] | 4935 |  | 0 | Labor - Task | Off Ice | 1.6 | Sensors | 1.6 Sensors | 1.6.1 | PDOM | 1.6.1 PDOM | 1.6.1.6 | PDOM DAQ Electronics | 1.6.1.6 PDOM DAQ Electronics | marek.rogal@icecube.wisc.edu | 2021-11-09 09:23 |  | 35d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.6.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 | 1.6.1.6.4.4 | C |  | PSU | Testing |  |  | M & S |  |  | EE | 1 | 1 | 0% | 2021-10-01 | 2022-07-15 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 |  | 1580.5 | [5 empty] | 1440 |  | 0 | M & S | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.6.1 | PDOM | 1.6.1 PDOM | 1.6.1.6 | PDOM DAQ Electronics | 1.6.1.6 PDOM DAQ Electronics | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 35d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.6.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TRUE | 1.6 | 1.6.1.6.4.3 | C |  | PSU | Adapt D-Egg Firmware to PDOM Mainboard and verify design | Anderson | 3.846% | Labor Hours | SE |  |  |  | 55 | 40% | 2021-11-12 | 2021-12-23 |  | TRUE | TRUE |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 |  |  | 616 | 616 | 616 | 616 | 616 | 616 | 616 | 616 | 616 | 616 | 0 | 0 | 6160 | 58.05% | 3575.88 | 10159.0233 | 10159.0233 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | [9 empty] | 10159.0233 | Labor - Task | Off Ice | 1.6 | Sensors | 1.6 Sensors | 1.6.1 | PDOM | 1.6.1 PDOM | 1.6.1.6 | PDOM DAQ Electronics | 1.6.1.6 PDOM DAQ Electronics | marek.rogal@icecube.wisc.edu | 2021-11-09 09:23 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.6.4.3 | 1015.9023 | 1015.9023 | 1015.9023 | 1015.9023 | 1015.9023 | 1015.9023 | 1015.9023 | 1015.9023 | 1015.9023 | 1015.9023 | 0 | 0 | 1.6.1.6.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.4.3 | 459.1234 | 459.1234 | 459.1234 | 459.1234 | 459.1234 | 459.1234 | 459.1234 | 459.1234 | 459.1234 | 459.1234 | 0 | 0 | 4591.2339 | 1.6.1.6.4.3 | 183.6494 | 183.6494 | 183.6494 | 183.6494 | 183.6494 | 183.6494 | 183.6494 | 183.6494 | 183.6494 | 183.6494 | 0 | 0 | 1836.4936 | 1.6.1.6.4.3 | 373.1296 | 373.1296 | 373.1296 | 373.1296 | 373.1296 | 373.1296 | 373.1296 | 373.1296 | 373.1296 | 373.1296 | 0 | 0 | 3731.2958 | 10159.0233 | 1.6.1.6.4.3 | 10159.0233 | 32324.1649 | 1015.9023 | 2031.8047 | 3047.707 | 4063.6093 | 5079.5116 | 6095.414 | 7111.3163 | 8127.2186 | 9143.1209 | 10159.0233 | 10159.0233 | 10159.0233 | 3232.4165 | 6464.833 | 9697.2495 | 12929.666 | 16162.0824 | 19394.4989 | 22626.9154 | 25859.3319 | 29091.7484 | 32324.1649 | 32324.1649 | 32324.1649
TRUE | 1.6 | 1.6.1.6.4.3 | C |  | PSU | Adapt D-Egg Firmware to PDOM Mainboard and verify design | Fienberg | 15.38% | Labor Hours | PO |  |  |  | 30 | 40% | 2021-11-12 | 2021-12-23 |  | TRUE | TRUE |  | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 |  |  | 1344 | 1344 | 1344 | 1344 | 1344 | 1344 | 1344 | 1344 | 1344 | 1344 | 0 | 0 | 13440 | 58.05% | 7801.92 | 22165.1416 | 22165.1416 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | [9 empty] | 22165.1416 | Labor - Task | Off Ice | 1.6 | Sensors | 1.6 Sensors | 1.6.1 | PDOM | 1.6.1 PDOM | 1.6.1.6 | PDOM DAQ Electronics | 1.6.1.6 PDOM DAQ Electronics | marek.rogal@icecube.wisc.edu | 2021-11-09 09:23 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.6.4.3 | 2216.5142 | 2216.5142 | 2216.5142 | 2216.5142 | 2216.5142 | 2216.5142 | 2216.5142 | 2216.5142 | 2216.5142 | 2216.5142 | 0 | 0 | 1.6.1.6.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.4.3 | 1001.7238 | 1001.7238 | 1001.7238 | 1001.7238 | 1001.7238 | 1001.7238 | 1001.7238 | 1001.7238 | 1001.7238 | 1001.7238 | 0 | 0 | 10017.2376 | 1.6.1.6.4.3 | 400.6895 | 400.6895 | 400.6895 | 400.6895 | 400.6895 | 400.6895 | 400.6895 | 400.6895 | 400.6895 | 400.6895 | 0 | 0 | 4006.895 | 1.6.1.6.4.3 | 814.1009 | 814.1009 | 814.1009 | 814.1009 | 814.1009 | 814.1009 | 814.1009 | 814.1009 | 814.1009 | 814.1009 | 0 | 0 | 8141.009 | 22165.1416 | 1.6.1.6.4.3 | 22165.1416 | 22165.1416 | 2216.5142 | 4433.0283 | 6649.5425 | 8866.0567 | 11082.5708 | 13299.085 | 15515.5991 | 17732.1133 | 19948.6275 | 22165.1416 | 22165.1416 | 22165.1416 | 2216.5142 | 4433.0283 | 6649.5425 | 8866.0567 | 11082.5708 | 13299.085 | 15515.5991 | 17732.1133 | 19948.6275 | 22165.1416 | 22165.1416 | 22165.1416
| 1.6 | 1.6.1.6.4.5 | C |  | PSU | PDOM Final Design Review (T. Anderson) | Anderson | 0% | Labor Hours | SE |  |  | 55 | 55 | 40% | 2022-07-18 | 2022-07-18 |  | TRUE | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 |  | 0 | 3399 |  |  |  |  | 4524 |  | 0 | Labor - Task | Off Ice | 1.6 | Sensors | 1.6 Sensors | 1.6.1 | PDOM | 1.6.1 PDOM | 1.6.1.6 | PDOM Final Design Review | 1.6.1.6 PDOM Final Design Review | cell-link@smartsheet.com | 2021-12-01 20:00 |  | 1235d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.6.4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 | 1.6.1.6.5.1 | C |  | PSU | R&D module mission review | Resource 5 | 0% | Labor Hours | SE |  |  | 55 | 55 | 40% | 2020-05-01 | 2020-05-01 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 |  | 4867.94 | 4614 |  |  |  |  | 4614 |  | 0 | Labor - Task | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.6.1 | Special Devices | 1.6.1 Special Devices | 1.6.1.6 | R&D module mission review | 1.6.1.6 R&D module mission review | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.6.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 | 1.6.1.6.5.1 | C |  | PSU | R&D module mission review |  |  | Travel |  |  |  | 1 | 1 | 0% | 2020-05-01 | 2020-05-01 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 |  | 0 | 2697 |  |  |  |  | 2697 |  | 0 | Travel | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.6.1 | Special Devices | 1.6.1 Special Devices | 1.6.1.6 | R&D module mission review | 1.6.1.6 R&D module mission review | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.6.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 | 1.6.1.6.5.2 | C |  | PSU | R&D modules deployment readiness review | N.N. | 0% | Labor Hours | SE |  |  | 55 | 55 | 40% | 2022-01-03 | 2022-01-03 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | -4707 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 |  | 0 |  | 4707 |  |  |  | 4707 |  | 0 | Labor - Task | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.6.1 | Special Devices | 1.6.1 Special Devices | 1.6.1.6 | R&D modules deployment readiness review | 1.6.1.6 R&D modules deployment readiness review | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.6.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 | 1.6.1.6.5.2 | C |  | PSU | R&D modules deployment readiness review |  |  | Travel |  |  |  | 1 | 1 | 0% | 2022-01-03 | 2022-01-03 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | -2751 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.05% | 0 | 0 |  | 0 |  | 2751 |  |  |  | 2751 |  | 0 | Travel | Off Ice | 1.3 | Sensors | 1.3 Sensors | 1.6.1 | Special Devices | 1.6.1 Special Devices | 1.6.1.6 | R&D modules deployment readiness review | 1.6.1.6 R&D modules deployment readiness review | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.1.6.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1.6.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.6 | 1.6.2.0 | C |  | UMD | L3 Task management - Alex Olivas | Olivas | 5.769% | Labor Hours | SC | TRUE |  | 45 | 45 | 29% | 2020-10-01 | 2024-06-28 |  |  |  |  | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 580.5 | 580.5 | 580.5 | 580.5 | 580.5 | 580.5 | 580.5 | 580.5 | 580.5 | 580.5 | 580.5 | 580.5 | 6966 | 54.5% | 3796.47 | 11230.2312 | 167.2312 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 580.5 | 580.5 | 580.5 | 580.5 | 580.5 | 580.5 | 580.5 | 580.5 | 580.5 | 580.5 | 580.5 | 580.5 | 6966 | 54.5% | 3796.47 | 11471.6811 | 187.6811 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 580.5 | 580.5 | 580.5 | 580.5 | 580.5 | 580.5 | 580.5 | 580.5 | 580.5 | 580.5 | 580.5 | 580.5 | 6966 | 54.5% | 3796.47 | 11718.3223 | 11718.3223 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 |  |  |  | 580.5 | 580.5 | 580.5 | 580.5 | 580.5 | 580.5 | 580.5 | 580.5 | 580.5 | 0 | 0 | 0 | 5224.5 | 54.5% | 2847.3525 | 8977.6997 | 5212 | 22768.6032 | 10846 | 11063 |  | 11284 |  | 49038 |  | 43397.9342 | Labor - LoE | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.2 | Offline Systems | 1.6.2 Offline Systems | 1.6.2.0 | Offline Systems Management | 1.6.2.0 Offline Systems Management | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1408d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.2.0 | 935.8526 | 935.8526 | 935.8526 | 935.8526 | 935.8526 | 935.8526 | 935.8526 | 935.8526 | 935.8526 | 935.8526 | 935.8526 | 935.8526 | 1.6.2.0 | 955.9734 | 955.9734 | 955.9734 | 955.9734 | 955.9734 | 955.9734 | 955.9734 | 955.9734 | 955.9734 | 955.9734 | 955.9734 | 955.9734 | 1.6.2.0 | 976.5269 | 976.5269 | 976.5269 | 976.5269 | 976.5269 | 976.5269 | 976.5269 | 976.5269 | 976.5269 | 976.5269 | 976.5269 | 976.5269 | 1.6.2.0 | 997.5222 | 997.5222 | 997.5222 | 997.5222 | 997.5222 | 997.5222 | 997.5222 | 997.5222 | 997.5222 | 0 | 0 | 0 | 1.6.2.0 | 469.558 | 469.558 | 469.558 | 469.558 | 469.558 | 469.558 | 469.558 | 469.558 | 469.558 | 469.558 | 469.558 | 469.558 | 5634.6961 | 1.6.2.0 | 136.1718 | 136.1718 | 136.1718 | 136.1718 | 136.1718 | 136.1718 | 136.1718 | 136.1718 | 136.1718 | 136.1718 | 136.1718 | 136.1718 | 1634.0619 | 1.6.2.0 | 330.1228 | 330.1228 | 330.1228 | 330.1228 | 330.1228 | 330.1228 | 330.1228 | 330.1228 | 330.1228 | 330.1228 | 330.1228 | 330.1228 | 3961.4731 | 11230.2312 | 1.6.2.0 | 11230.2312 | 11230.2312 | 935.8526 | 1871.7052 | 2807.5578 | 3743.4104 | 4679.263 | 5615.1156 | 6550.9682 | 7486.8208 | 8422.6734 | 9358.526 | 10294.3786 | 11230.2312 | 935.8526 | 1871.7052 | 2807.5578 | 3743.4104 | 4679.263 | 5615.1156 | 6550.9682 | 7486.8208 | 8422.6734 | 9358.526 | 10294.3786 | 11230.2312
| 1.6 | 1.6.2.1 | P |  | UMD | Travel for internal workshop discussions |  |  | Travel |  | TRUE |  | 1 | 1 | 0% | 2019-12-24 | 2023-05-01 | [13 empty] | 1800 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 1800 | 54.5% | 981 | 2781 | 2781 | [9 empty] | 1800 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 1800 | 54.5% | 981 | 2781 | 2781 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54.5% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54.5% | 0 | 0 |  | 2781 | [5 empty] | 2726 |  | 5562 | Travel | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.2 | Offline Systems | 1.6.2 Offline Systems | 1.6.2.1 | Core Software | 1.6.2.1 Core Software | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 163d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2781 | 0 | 0 | 1.6.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2781 | 0 | 0 | 1.6.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 1800 | 1.6.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 981 | 0 | 0 | 981 | 2781 | 1.6.2.1 | 2781 | 2781 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2781 | 2781 | 2781 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2781 | 2781 | 2781
| 1.6 | 1.6.2.1.1 | C |  | UMD | Capture Required changes to IceTray software packages |  | 0% | Labor Hours | SS | TRUE |  | 45 | 55 | 29% | 2019-12-24 | 2020-01-27 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54.5% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54.5% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54.5% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54.5% | 0 | 0 |  | 4384.71 | [5 empty] | 3544 |  | 0 | Labor - Task | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.2 | Offline Systems | 1.6.2 Offline Systems | 1.6.2.1 | Core Software | 1.6.2.1 Core Software | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 30d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.2.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.2.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.2.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.2.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.2.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.2.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.2.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.2.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.6 | 1.6.2.1.2 | C |  | UMD | Design updates to IceTray (support new optical sensor Data/Config/Calib Info) |  | 0% | Labor Hours | SS | TRUE |  | 45 | 55 | 29% | 2020-01-28 | 2020-03-02 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54.5% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54.5% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54.5% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54.5% | 0 | 0 |  | 4384.71 | [5 empty] | 3544 |  | 0 | Labor - Task | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.2 | Offline Systems | 1.6.2 Offline Systems | 1.6.2.1 | Core Software | 1.6.2.1 Core Software | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 30d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.6 | 1.6.2.1.3 | C |  | UMD | Develop and test Updates to IceTray (support new optical sensor Data/Config/Calib Info) |  | 0% | Labor Hours | SS | TRUE |  | 45 | 55 | 29% | 2020-03-03 | 2021-10-29 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54.5% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54.5% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54.5% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54.5% | 0 | 0 |  | 15346.485 | [5 empty] | 14178 |  | 0 | Labor - Task | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.2 | Offline Systems | 1.6.2 Offline Systems | 1.6.2.1 | Core Software | 1.6.2.1 Core Software | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 102d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.2.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.2.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.2.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.2.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.2.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.2.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.2.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.2.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.6 | 1.6.2.1.5 | C |  | UMD | Extend Core Software to include support for new hardware readouts |  | 0% | Labor Hours | SS | TRUE |  |  | 55 | 29% | 2023-03-01 | 2023-04-28 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54.5% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54.5% | 0 | 0 | 0 | [5 empty] | 80 | 80 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 5676 | 5676 | 0 | 0 | 0 | 0 | 0 | 11352 | 54.5% | 6186.84 | 19096.5252 | 19096.5252 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54.5% | 0 | 0 | [9 empty] | 19096.5252 | Labor - Task | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.2 | Offline Systems | 1.6.2 Offline Systems | 1.6.2.1 | Core Software | 1.6.2.1 Core Software | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  |  | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.2.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.2.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.2.1.5 | 0 | 0 | 0 | 0 | 0 | 9548.2626 | 9548.2626 | 0 | 0 | 0 | 0 | 0 | 1.6.2.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.2.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.2.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.2.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.2.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.6 | 1.6.2.3 | P |  | UMD | Cloud computing services |  |  | M & S |  | TRUE |  | 1 | 1 | 0% | 2019-01-01 | 2024-06-27 | [10 empty] | 2400 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 2400 | 0 | 0 | 0 | 0 | 0 | 2400 | 54.5% | 1308 | 3708 | -5 | [6 empty] | 2400 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 2400 | 0 | 0 | 0 | 0 | 0 | 2400 | 54.5% | 1308 | 3708 | -3717 | [6 empty] | 2400 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 2400 | 0 | 0 | 0 | 0 | 0 | 2400 | 54.5% | 1308 | 3708 | 3708 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54.5% | 0 | 0 | 3713 | 3708 | 3713 | 3713 |  | 7425 |  | 22275 |  | 11124 | M & S | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.2 | Offline Systems | 1.6.2 Offline Systems | 1.6.2.3 | Tools and Infrastructure | 1.6.2.3 Tools and Infrastructure | cell-link@smartsheet.com | 2021-12-01 20:00 |  | 1408d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 3708 | 0 | 0 | 0 | 0 | 0 | 1.6.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 3708 | 0 | 0 | 0 | 0 | 0 | 1.6.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 3708 | 0 | 0 | 0 | 0 | 0 | 1.6.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 2400 | 0 | 0 | 0 | 0 | 0 | 2400 | 1.6.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 1308 | 0 | 0 | 0 | 0 | 0 | 1308 | 3708 | 1.6.2.3 | 3708 | 3708 | 0 | 0 | 0 | 0 | 0 | 0 | 3708 | 3708 | 3708 | 3708 | 3708 | 3708 | 0 | 0 | 0 | 0 | 0 | 0 | 3708 | 3708 | 3708 | 3708 | 3708 | 3708
| 1.6 | 1.6.2.3.1 | C |  | UMD | Evaluate readiness of Current IceCube SW Development Infrastructure to Support IceCube Upgrade SW Activities& TimeScales |  | 0% | Labor Hours | EN | TRUE |  | 50 | 50 | 35% | 2019-01-01 | 2019-03-29 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54.5% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54.5% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54.5% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54.5% | 0 | 0 | 15927 | 0 | [5 empty] | 15927 |  | 0 | Labor - Task | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.2 | Offline Systems | 1.6.2 Offline Systems | 1.6.2.3 | Tools and Infrastructure | 1.6.2.3 Tools and Infrastructure | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 76d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.2.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.2.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.2.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.2.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.2.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.2.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.2.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.2.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.6 | 1.6.2.3.2 | C |  | UMD | Upgrade IceCube SW Development Infrastructure to support Upgrade activities |  | 0% | Labor Hours | EN | TRUE |  | 50 | 50 | 35% | 2019-04-01 | 2019-07-30 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54.5% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54.5% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54.5% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54.5% | 0 | 0 | 23166 | 0 | [5 empty] | 23166 |  | 0 | Labor - Task | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.2 | Offline Systems | 1.6.2 Offline Systems | 1.6.2.3 | Tools and Infrastructure | 1.6.2.3 Tools and Infrastructure | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 104d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.2.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.2.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.2.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.2.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.2.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.2.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.2.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.2.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.6 | 1.6.2.3.3 | C |  | UMD | Support Upgrade SW Development environment and infrastructure |  | 5.769% | Labor Hours | EN | TRUE |  | 50 | 50 | 35% | 2019-07-31 | 2024-06-27 |  |  |  |  | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 675 | 675 | 675 | 675 | 675 | 675 | 675 | 675 | 675 | 675 | 675 | 675 | 8100 | 54.5% | 4414.5 | 13058.4083 | -7428.5917 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 675 | 675 | 675 | 675 | 675 | 675 | 675 | 675 | 675 | 675 | 675 | 675 | 8100 | 54.5% | 4414.5 | 13339.1641 | -7556.8359 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 675 | 675 | 675 | 675 | 675 | 675 | 675 | 675 | 675 | 675 | 675 | 675 | 8100 | 54.5% | 4414.5 | 13625.9561 | 13625.9561 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 |  |  |  | 675 | 675 | 675 | 675 | 675 | 675 | 675 | 675 | 675 | 0 | 0 | 0 | 6075 | 54.5% | 3310.875 | 10439.1856 | 3861 | 25029 | 20085 | 20487 |  | 20896 |  | 85020 |  | 50462.7142 | Labor - Task | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.2 | Offline Systems | 1.6.2 Offline Systems | 1.6.2.3 | Tools and Infrastructure | 1.6.2.3 Tools and Infrastructure | cell-link@smartsheet.com | 2021-12-01 20:00 |  | 1226d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.2.3.3 | 1088.2007 | 1088.2007 | 1088.2007 | 1088.2007 | 1088.2007 | 1088.2007 | 1088.2007 | 1088.2007 | 1088.2007 | 1088.2007 | 1088.2007 | 1088.2007 | 1.6.2.3.3 | 1111.597 | 1111.597 | 1111.597 | 1111.597 | 1111.597 | 1111.597 | 1111.597 | 1111.597 | 1111.597 | 1111.597 | 1111.597 | 1111.597 | 1.6.2.3.3 | 1135.4963 | 1135.4963 | 1135.4963 | 1135.4963 | 1135.4963 | 1135.4963 | 1135.4963 | 1135.4963 | 1135.4963 | 1135.4963 | 1135.4963 | 1135.4963 | 1.6.2.3.3 | 1159.9095 | 1159.9095 | 1159.9095 | 1159.9095 | 1159.9095 | 1159.9095 | 1159.9095 | 1159.9095 | 1159.9095 | 0 | 0 | 0 | 1.6.2.3.3 | 521.7311 | 521.7311 | 521.7311 | 521.7311 | 521.7311 | 521.7311 | 521.7311 | 521.7311 | 521.7311 | 521.7311 | 521.7311 | 521.7311 | 6260.7735 | 1.6.2.3.3 | 182.6059 | 182.6059 | 182.6059 | 182.6059 | 182.6059 | 182.6059 | 182.6059 | 182.6059 | 182.6059 | 182.6059 | 182.6059 | 182.6059 | 2191.2707 | 1.6.2.3.3 | 383.8637 | 383.8637 | 383.8637 | 383.8637 | 383.8637 | 383.8637 | 383.8637 | 383.8637 | 383.8637 | 383.8637 | 383.8637 | 383.8637 | 4606.3641 | 13058.4083 | 1.6.2.3.3 | 13058.4083 | 13058.4083 | 1088.2007 | 2176.4014 | 3264.6021 | 4352.8028 | 5441.0035 | 6529.2042 | 7617.4049 | 8705.6056 | 9793.8062 | 10882.0069 | 11970.2076 | 13058.4083 | 1088.2007 | 2176.4014 | 3264.6021 | 4352.8028 | 5441.0035 | 6529.2042 | 7617.4049 | 8705.6056 | 9793.8062 | 10882.0069 | 11970.2076 | 13058.4083
| 1.6 | 1.6.4.0 | C |  | UW | L3 Task management - Ralf Auer | Auer | 5.769% | Labor Hours | EN |  |  | 40 | 47 | 35% | 2020-10-01 | 2024-06-28 |  | TRUE |  |  | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 634.5 | 634.5 | 634.5 | 634.5 | 634.5 | 634.5 | 634.5 | 634.5 | 634.5 | 634.5 | 634.5 | 634.5 | 7614 | 53% | 4035.42 | 12155.73 | 1790.73 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 634.5 | 634.5 | 634.5 | 634.5 | 634.5 | 634.5 | 634.5 | 634.5 | 634.5 | 634.5 | 634.5 | 634.5 | 7614 | 53% | 4035.42 | 12417.0782 | 1844.0782 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 634.5 | 634.5 | 634.5 | 634.5 | 634.5 | 634.5 | 634.5 | 634.5 | 634.5 | 634.5 | 634.5 | 634.5 | 7614 | 53% | 4035.42 | 12684.0454 | 12684.0454 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 |  |  |  | 634.5 | 634.5 | 634.5 | 634.5 | 634.5 | 634.5 | 634.5 | 634.5 | 634.5 | 0 | 0 | 0 | 5710.5 | 53% | 3026.565 | 9717.5643 | 4884 | 8922.96 | 10162 | 10365 |  | 10573 |  | 45947 |  | 46974.4179 | Labor - LoE | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.4 | Computing Infrastructure | 1.6.4 Computing Infrastructure | 1.6.4.0 | Computing Infrastructure Management | 1.6.4.0 Computing Infrastructure Management | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1460d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.4.0 | 1012.9775 | 1012.9775 | 1012.9775 | 1012.9775 | 1012.9775 | 1012.9775 | 1012.9775 | 1012.9775 | 1012.9775 | 1012.9775 | 1012.9775 | 1012.9775 | 1.6.4.0 | 1034.7565 | 1034.7565 | 1034.7565 | 1034.7565 | 1034.7565 | 1034.7565 | 1034.7565 | 1034.7565 | 1034.7565 | 1034.7565 | 1034.7565 | 1034.7565 | 1.6.4.0 | 1057.0038 | 1057.0038 | 1057.0038 | 1057.0038 | 1057.0038 | 1057.0038 | 1057.0038 | 1057.0038 | 1057.0038 | 1057.0038 | 1057.0038 | 1057.0038 | 1.6.4.0 | 1079.7294 | 1079.7294 | 1079.7294 | 1079.7294 | 1079.7294 | 1079.7294 | 1079.7294 | 1079.7294 | 1079.7294 | 0 | 0 | 0 | 1.6.4.0 | 490.4273 | 490.4273 | 490.4273 | 490.4273 | 490.4273 | 490.4273 | 490.4273 | 490.4273 | 490.4273 | 490.4273 | 490.4273 | 490.4273 | 5885.1271 | 1.6.4.0 | 171.6495 | 171.6495 | 171.6495 | 171.6495 | 171.6495 | 171.6495 | 171.6495 | 171.6495 | 171.6495 | 171.6495 | 171.6495 | 171.6495 | 2059.7945 | 1.6.4.0 | 350.9007 | 350.9007 | 350.9007 | 350.9007 | 350.9007 | 350.9007 | 350.9007 | 350.9007 | 350.9007 | 350.9007 | 350.9007 | 350.9007 | 4210.8084 | 12155.73 | 1.6.4.0 | 12155.73 | 12155.73 | 1012.9775 | 2025.955 | 3038.9325 | 4051.91 | 5064.8875 | 6077.865 | 7090.8425 | 8103.82 | 9116.7975 | 10129.775 | 11142.7525 | 12155.73 | 1012.9775 | 2025.955 | 3038.9325 | 4051.91 | 5064.8875 | 6077.865 | 7090.8425 | 8103.82 | 9116.7975 | 10129.775 | 11142.7525 | 12155.73
| 1.6 | 1.6.4.1 | P |  | UW | Miscellaneous supplies |  |  | M & S |  | TRUE |  | 1 | 1 | 0% | 2019-02-01 | 2024-06-28 | [10 empty] | 500 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 500 | 53% | 265 | 765 | 0 | [6 empty] | 500 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 500 | 53% | 265 | 765 | 0 | [6 empty] | 500 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 500 | 53% | 265 | 765 | 765 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 765 | 765 | 765 | 765 |  | 765 |  | 3825 |  | 2295 | M & S | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.4 | Computing Infrastructure | 1.6.4 Computing Infrastructure | 1.6.4.1 | SPTS/NTS computing needs | 1.6.4.1 SPTS/NTS computing needs | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1381d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 765 | 0 | 0 | 0 | 0 | 0 | 1.6.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 765 | 0 | 0 | 0 | 0 | 0 | 1.6.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 765 | 0 | 0 | 0 | 0 | 0 | 1.6.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 500 | 1.6.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 265 | 0 | 0 | 0 | 0 | 0 | 265 | 765 | 1.6.4.1 | 765 | 765 | 0 | 0 | 0 | 0 | 0 | 0 | 765 | 765 | 765 | 765 | 765 | 765 | 0 | 0 | 0 | 0 | 0 | 0 | 765 | 765 | 765 | 765 | 765 | 765
| 1.6 | 1.6.4.1 | P |  | UW | Trip to MSU to install NTS equipment |  |  | Travel |  |  |  | 1 | 1 | 0% | 2019-02-01 | 2024-06-28 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | -2923 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [6 empty] | 1800 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 1800 | 53% | 954 | 2754 | 2754 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 2754 | 2754 |  | 2923 |  |  |  | 5677 |  | 2754 | Travel | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.4 | Computing Infrastructure | 1.6.4 Computing Infrastructure | 1.6.4.1 | SPTS/NTS computing needs | 1.6.4.1 SPTS/NTS computing needs | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1381d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 2754 | 0 | 0 | 0 | 0 | 0 | 1.6.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.6 | 1.6.4.1 | P |  | UW | Trip to MSU to coordinate NTS setup and planning workshop |  |  | Travel |  |  |  | 1 | 1 | 0% | 2019-02-01 | 2024-06-28 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 2754 | 0 | [5 empty] | 2754 |  | 0 | Travel | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.4 | Computing Infrastructure | 1.6.4 Computing Infrastructure | 1.6.4.1 | SPTS/NTS computing needs | 1.6.4.1 SPTS/NTS computing needs | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1381d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.6 | 1.6.4.1 | P |  | UW | NTS computing system purchase |  |  | CapEx |  |  | EE | 1 | 1 | 0% | 2019-02-01 | 2024-06-28 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [5 empty] | 2500 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 53% | 0 | 2500 | 2500 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 41500 | 0 | [5 empty] | 41500 |  | 2500 | CapEx | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.4 | Computing Infrastructure | 1.6.4 Computing Infrastructure | 1.6.4.1 | SPTS/NTS computing needs | 1.6.4.1 SPTS/NTS computing needs | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1381d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.1 | 0 | 0 | 0 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.6 | 1.6.4.1 | P |  | UW | SPTS computing system additions |  |  | CapEx |  |  | EE | 1 | 1 | 0% | 2019-02-01 | 2024-06-28 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 10000 | [5 empty] | 10000 |  | 0 | CapEx | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.4 | Computing Infrastructure | 1.6.4 Computing Infrastructure | 1.6.4.1 | SPTS/NTS computing needs | 1.6.4.1 SPTS/NTS computing needs | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1381d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.6 | 1.6.4.1.1.1 | C |  | UW | Specify Requirements/Design NTS Computing Sys |  | 0% | Labor Hours | EN |  |  | 40 | 40 | 35% | 2019-02-01 | 2019-02-28 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 6512 | 0 | [5 empty] | 6512 |  | 0 | Labor - Task | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.4 | Computing Infrastructure | 1.6.4 Computing Infrastructure | 1.6.4.1 | SPTS/NTS computing needs | 1.6.4.1 SPTS/NTS computing needs | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 24d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.4.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.6 | 1.6.4.1.1.2 | C |  | UW | Procure NTS Computing Hardware |  | 0% | Labor Hours | EN |  |  | 40 | 40 | 35% | 2019-03-01 | 2019-03-29 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 6512 | 0 | [5 empty] | 6512 |  | 0 | Labor - Task | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.4 | Computing Infrastructure | 1.6.4 Computing Infrastructure | 1.6.4.1 | SPTS/NTS computing needs | 1.6.4.1 SPTS/NTS computing needs | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 25d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.4.1.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.1.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.1.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.1.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.1.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.1.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.1.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.1.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.6 | 1.6.4.1.1.3 | C |  | UW | Buildout NTS Computing System |  | 0% | Labor Hours | EN |  |  | 40 | 40 | 35% | 2019-04-01 | 2019-05-31 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 9768 | 0 | [5 empty] | 9768 |  | 0 | Labor - Task | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.4 | Computing Infrastructure | 1.6.4 Computing Infrastructure | 1.6.4.1 | SPTS/NTS computing needs | 1.6.4.1 SPTS/NTS computing needs | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 53d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.4.1.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.1.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.1.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.1.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.1.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.1.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.1.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.1.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.6 | 1.6.4.1.1.5 | C |  | UW | Refresh NTS HW to match SPS/IDF |  | 0% | Labor Hours | EN | TRUE |  | 40 | 40 | 35% | 2023-04-01 | 2023-04-28 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | -6910 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [6 empty] | 40 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 2160 | 0 | 0 | 0 | 0 | 0 | 2160 | 53% | 1144.8 | 3598.3107 | 3598.3107 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 |  | 6910 |  |  |  | 6910 |  | 3598.3107 | Labor - Task | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.4 | Computing Infrastructure | 1.6.4 Computing Infrastructure | 1.6.4.1 | SPTS/NTS computing needs | 1.6.4.1 SPTS/NTS computing needs | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 25d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.4.1.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.1.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.1.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 3598.3107 | 0 | 0 | 0 | 0 | 0 | 1.6.4.1.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.1.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.1.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.1.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.1.1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.6 | 1.6.4.1.1.6 | C |  | UW | Support NTS System |  | 5.769% | Labor Hours | EN | TRUE |  | 40 | 40 | 35% | 2019-09-15 | 2024-06-28 |  |  |  |  | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 6480 | 53% | 3434.4 | 10345.3021 | 1707.3021 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 6480 | 53% | 3434.4 | 10567.7261 | 1756.7261 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 6480 | 53% | 3434.4 | 10794.9322 | 10794.9322 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 |  |  |  | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 0 | 0 | 0 | 4860 | 53% | 2575.8 | 8270.2675 | 6512 | 9914.4 | 8468 | 8638 |  | 8811 |  | 40731 |  | 39978.228 | Labor - Task | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.4 | Computing Infrastructure | 1.6.4 Computing Infrastructure | 1.6.4.1 | SPTS/NTS computing needs | 1.6.4.1 SPTS/NTS computing needs | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 1277d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.4.1.1.6 | 862.1085 | 862.1085 | 862.1085 | 862.1085 | 862.1085 | 862.1085 | 862.1085 | 862.1085 | 862.1085 | 862.1085 | 862.1085 | 862.1085 | 1.6.4.1.1.6 | 880.6438 | 880.6438 | 880.6438 | 880.6438 | 880.6438 | 880.6438 | 880.6438 | 880.6438 | 880.6438 | 880.6438 | 880.6438 | 880.6438 | 1.6.4.1.1.6 | 899.5777 | 899.5777 | 899.5777 | 899.5777 | 899.5777 | 899.5777 | 899.5777 | 899.5777 | 899.5777 | 899.5777 | 899.5777 | 899.5777 | 1.6.4.1.1.6 | 918.9186 | 918.9186 | 918.9186 | 918.9186 | 918.9186 | 918.9186 | 918.9186 | 918.9186 | 918.9186 | 0 | 0 | 0 | 1.6.4.1.1.6 | 417.3849 | 417.3849 | 417.3849 | 417.3849 | 417.3849 | 417.3849 | 417.3849 | 417.3849 | 417.3849 | 417.3849 | 417.3849 | 417.3849 | 5008.6188 | 1.6.4.1.1.6 | 146.0847 | 146.0847 | 146.0847 | 146.0847 | 146.0847 | 146.0847 | 146.0847 | 146.0847 | 146.0847 | 146.0847 | 146.0847 | 146.0847 | 1753.0166 | 1.6.4.1.1.6 | 298.6389 | 298.6389 | 298.6389 | 298.6389 | 298.6389 | 298.6389 | 298.6389 | 298.6389 | 298.6389 | 298.6389 | 298.6389 | 298.6389 | 3583.6668 | 10345.3021 | 1.6.4.1.1.6 | 10345.3021 | 10345.3021 | 862.1085 | 1724.217 | 2586.3255 | 3448.434 | 4310.5426 | 5172.6511 | 6034.7596 | 6896.8681 | 7758.9766 | 8621.0851 | 9483.1936 | 10345.3021 | 862.1085 | 1724.217 | 2586.3255 | 3448.434 | 4310.5426 | 5172.6511 | 6034.7596 | 6896.8681 | 7758.9766 | 8621.0851 | 9483.1936 | 10345.3021
| 1.6 | 1.6.4.1.2.1 | C |  | UW | Design/Specify SPTS Ext req'd to support Upgrade Activities |  | 0% | Labor Hours | EN | TRUE |  | 40 | 40 | 35% | 2020-01-06 | 2021-05-04 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 6609.6 | [5 empty] | 6642 |  | 0 | Labor - Task | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.4 | Computing Infrastructure | 1.6.4 Computing Infrastructure | 1.6.4.1 | SPTS/NTS computing needs | 1.6.4.1 SPTS/NTS computing needs | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 103d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.4.1.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.1.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.1.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.1.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.1.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.1.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.1.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.1.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.6 | 1.6.4.1.2.2 | C |  | UW | Procure Computing Hardware for SPTS Ext |  | 0% | Labor Hours | EN | TRUE |  | 40 | 40 | 35% | 2021-05-05 | 2021-08-04 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 6609.6 | [5 empty] | 6642 |  | 0 | Labor - Task | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.4 | Computing Infrastructure | 1.6.4 Computing Infrastructure | 1.6.4.1 | SPTS/NTS computing needs | 1.6.4.1 SPTS/NTS computing needs | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 79d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.4.1.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.1.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.1.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.1.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.1.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.1.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.1.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.1.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.6 | 1.6.4.1.2.3 | C |  | UW | Buildout SPTS Computing System for Ext(s) |  | 0% | Labor Hours | EN | TRUE |  | 40 | 40 | 35% | 2021-08-05 | 2021-10-01 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 9914.4 | [5 empty] | 9963 |  | 0 | Labor - Task | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.4 | Computing Infrastructure | 1.6.4 Computing Infrastructure | 1.6.4.1 | SPTS/NTS computing needs | 1.6.4.1 SPTS/NTS computing needs | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 50d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.4.1.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.1.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.1.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.1.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.1.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.1.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.1.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.1.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.6 | 1.6.4.2 | P |  | UW | Miscellaneous supplies |  |  | M & S |  |  |  | 1 | 1 | 0% | 2019-05-01 | 2024-01-17 |  | TRUE | [8 empty] | 500 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 500 | 53% | 265 | 765 | 0 | [6 empty] | 500 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 500 | 53% | 265 | 765 | 0 | [6 empty] | 500 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 500 | 53% | 265 | 765 | 765 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 765 | 765 | 765 | 765 |  | 765 |  | 3825 |  | 2295 | M & S | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.4 | Computing Infrastructure | 1.6.4 Computing Infrastructure | 1.6.4.2 | SPS computing needs | 1.6.4.2 SPS computing needs | cell-link@smartsheet.com | 2021-12-01 20:00 |  | 1163d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 765 | 0 | 0 | 0 | 0 | 0 | 1.6.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 765 | 0 | 0 | 0 | 0 | 0 | 1.6.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 765 | 0 | 0 | 0 | 0 | 0 | 1.6.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 500 | 1.6.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 265 | 0 | 0 | 0 | 0 | 0 | 265 | 765 | 1.6.4.2 | 765 | 2601 | 0 | 0 | 0 | 0 | 0 | 0 | 765 | 765 | 765 | 765 | 765 | 765 | 0 | 0 | 0 | 0 | 0 | 0 | 765 | 765 | 765 | 765 | 765 | 2601
| 1.6 | 1.6.4.2 | P |  | UW | PQ process |  |  | M & S |  |  |  | 1 | 1 | 0% | 2019-05-01 | 2024-01-17 |  |  |  | Ralf/IT person PQ for Upgrade prep work | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | -1454 | [5 empty] | 950 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 950 | 0 | 0 | 0 | 0 | 0 | 0 | 950 | 53% | 503.5 | 1453.5 | 1453.5 | [5 empty] | 950 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 950 | 0 | 0 | 0 | 0 | 0 | 0 | 950 | 53% | 503.5 | 1453.5 | 1453.5 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 | 0 | 1454 |  |  |  | 2907 |  | 2907 | M & S | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.4 | Computing Infrastructure | 1.6.4 Computing Infrastructure | 1.6.4.2 | SPS computing needs | 1.6.4.2 SPS computing needs | cell-link@smartsheet.com | 2021-12-01 20:00 |  | 1163d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.2 | 0 | 0 | 0 | 0 | 0 | 1453.5 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.2 | 0 | 0 | 0 | 0 | 0 | 1453.5 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.2 | 0 | 1836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1836
| 1.6 | 1.6.4.2 | P |  | UW | Deployment to Pole |  |  | Travel |  | TRUE |  | 1 | 1 | 0% | 2019-05-01 | 2024-01-17 |  | TRUE | [13 empty] | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 1200 | 53% | 636 | 1836 | 1836 | [11 empty] | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 1200 | 53% | 636 | 1836 | -151 | [11 empty] | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 1200 | 53% | 636 | 1836 | 1836 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 |  | 0 |  | 1987 |  | 3936 |  | 5508 | Travel | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.4 | Computing Infrastructure | 1.6.4 Computing Infrastructure | 1.6.4.2 | SPS computing needs | 1.6.4.2 SPS computing needs | cell-link@smartsheet.com | 2021-12-01 20:00 |  | 1163d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1836 | 1.6.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1836 | 1.6.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1836 | 1.6.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 1200 | 1.6.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 636 | 636 | 1836 | 1.6.4.2 | 1836 | 1836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1836
| 1.6 | 1.6.4.2 | P |  | UW | SPS computing system additions |  |  | CapEx |  |  | EE | 1 | 1 | 0% | 2019-05-01 | 2024-01-17 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | -10000 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [8 empty] | 10000 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 10000 | 53% | 0 | 10000 | 10000 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 |  | 10000 |  |  |  | 10000 |  | 10000 | CapEx | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.4 | Computing Infrastructure | 1.6.4 Computing Infrastructure | 1.6.4.2 | SPS computing needs | 1.6.4.2 SPS computing needs | cell-link@smartsheet.com | 2021-12-01 20:00 |  | 1163d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 1.6.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.6 | 1.6.4.2.1 | C |  | UW | Specify space and power needs for IDF design process |  | 0% | Labor Hours | EN |  |  | 40 | 40 | 35% | 2019-05-01 | 2019-06-28 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 6512 | 0 | [5 empty] | 6512 |  | 0 | Labor - Task | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.4 | Computing Infrastructure | 1.6.4 Computing Infrastructure | 1.6.4.2 | SPS computing needs | 1.6.4.2 SPS computing needs | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 51d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.4.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.6 | 1.6.4.2.9 | C |  | UW | Design/Specify SPS Computing Sys Extensions for Upgrade |  | 0% | Labor Hours | EN | TRUE |  | 40 | 40 | 35% | 2023-02-01 | 2023-04-03 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | -6910 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 |  |  |  |  | 20 | 20 | 10 | [5 empty] | 0 | 0 | 0 | 0 | 1080 | 1080 | 540 | 0 | 0 | 0 | 0 | 0 | 2700 | 53% | 1431 | 4497.8884 | 4497.8884 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 |  | 6910 |  |  |  | 6910 |  | 4497.8884 | Labor - Task | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.4 | Computing Infrastructure | 1.6.4 Computing Infrastructure | 1.6.4.2 | SPS computing needs | 1.6.4.2 SPS computing needs | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 52d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.4.2.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.2.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.2.9 | 0 | 0 | 0 | 0 | 1799.1554 | 1799.1554 | 899.5777 | 0 | 0 | 0 | 0 | 0 | 1.6.4.2.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.2.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.2.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.2.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.2.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.6 | 1.6.4.2.10 | C |  | UW | Procure Computing Sys for SPSExt |  | 0% | Labor Hours | EN | TRUE |  | 40 | 40 | 35% | 2023-04-04 | 2023-05-02 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | -3455 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [6 empty] | 10 | 20 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 540 | 1080 | 0 | 0 | 0 | 0 | 1620 | 53% | 858.6 | 2698.7331 | 2698.7331 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 |  | 3455 |  |  |  | 3455 |  | 2698.7331 | Labor - Task | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.4 | Computing Infrastructure | 1.6.4 Computing Infrastructure | 1.6.4.2 | SPS computing needs | 1.6.4.2 SPS computing needs | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 25d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.4.2.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.2.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.2.10 | 0 | 0 | 0 | 0 | 0 | 0 | 899.5777 | 1799.1554 | 0 | 0 | 0 | 0 | 1.6.4.2.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.2.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.2.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.2.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.2.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.6 | 1.6.4.2.11 | C |  | UW | Buildout and test SPS systems in North |  | 0% | Labor Hours | EN | TRUE |  | 40 | 40 | 35% | 2023-05-03 | 2023-07-04 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | -10365 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [7 empty] | 20 | 40 | 40 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1080 | 2160 | 2160 | 0 | 0 | 5400 | 53% | 2862 | 8995.7769 | 8995.7769 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 |  | 10365 |  |  |  | 10365 |  | 8995.7769 | Labor - Task | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.4 | Computing Infrastructure | 1.6.4 Computing Infrastructure | 1.6.4.2 | SPS computing needs | 1.6.4.2 SPS computing needs | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 54d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.4.2.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.2.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.2.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1799.1554 | 3598.3107 | 3598.3107 | 0 | 0 | 1.6.4.2.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.2.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.2.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.2.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.2.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.6 | 1.6.4.2.12 | C |  | UW | Ship Computing Sys for SPS Ext to Pole |  | 0% | Labor Hours | EN | TRUE |  | 40 | 40 | 35% | 2023-07-05 | 2023-08-03 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | -3455 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [9 empty] | 20 | 20 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1080 | 1080 | 0 | 2160 | 53% | 1144.8 | 3598.3107 | 3598.3107 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 |  | 3455 |  |  |  | 3455 |  | 3598.3107 | Labor - Task | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.4 | Computing Infrastructure | 1.6.4 Computing Infrastructure | 1.6.4.2 | SPS computing needs | 1.6.4.2 SPS computing needs | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 26d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.4.2.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.2.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.2.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1799.1554 | 1799.1554 | 0 | 1.6.4.2.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.2.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.2.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.2.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.2.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.6 | 1.6.4.2.14 | C |  | UW | Installation at Pole |  | 0% | Labor Hours | EN | TRUE |  | 40 | 40 | 35% | 2023-12-14 | 2024-01-16 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | -17621 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 |  |  | 160 | 160 | [8 empty] | 0 | 0 | 8640 | 8640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17280 | 53% | 9158.4 | 29405.3954 |  | 0 |  |  |  | 17621 |  | 17621 |  | 29405.3954 | Labor - Task | On Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.4 | Computing Infrastructure | 1.6.4 Computing Infrastructure | 1.6.4.2 | SPS computing needs | 1.6.4.2 SPS computing needs | cell-link@smartsheet.com | 2021-12-01 20:00 |  | 28d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.4.2.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.2.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.2.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.2.14 | 0 | 0 | 14702.6977 | 14702.6977 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.2.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.2.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.2.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.2.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.6 | 1.6.4.3.1 | C |  | UW | Support Upgrade Distributed Mass Production |  | 0% | Labor Hours | EN | TRUE |  | 40 | 40 | 35% | 2021-11-03 | 2022-01-25 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 | 10162 |  |  |  |  | 10162 |  | 0 | Labor - Task | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.4 | Computing Infrastructure | 1.6.4 Computing Infrastructure | 1.6.4.3 | Distributed computing needs | 1.6.4.3 Distributed computing needs | cell-link@smartsheet.com | 2021-12-01 20:00 |  | 72d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.4.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.6 | 1.6.4.3.2 | C |  | UW | Support Distributed Mass Production for"As Built" Detector Verification |  | 0% | Labor Hours | EN | TRUE |  | 40 | 40 | 35% | 2021-09-20 | 2021-10-19 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | -17621 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [7 empty] | 35 | 35 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1890 | 1890 | 0 | 0 | 0 | 3780 | 53% | 2003.4 | 6432.4302 |  | 0 |  |  |  | 17621 |  | 17621 |  | 6432.4302 | Labor - Task | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.4 | Computing Infrastructure | 1.6.4 Computing Infrastructure | 1.6.4.3 | Distributed computing needs | 1.6.4.3 Distributed computing needs | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 119d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.4.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3216.2151 | 3216.2151 | 0 | 0 | 0 | 1.6.4.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.6 | 1.6.5.1.1 | C |  | UW | Develop and review OM module commissioning plan |  | 0% | Labor Hours | SC | TRUE |  | 40 | 45 | 35% | 2023-06-01 | 2023-08-01 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [8 empty] | 40 | 20 | 10 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2430 | 1215 | 607.5 | 0 | 4252.5 | 53% | 2253.825 | 7084.1743 | 7084.1743 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 | 10162 |  |  |  |  | 25080 |  | 7084.1743 | Labor - Task | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.5 | Upgrade String Commissioning | 1.6.5 Upgrade String Commissioning | 1.6.5.1 | Upgrade OM module commissioning | 1.6.5.1 Upgrade OM module commissioning | marek.rogal@icecube.wisc.edu | 2021-10-29 11:44 |  | 72d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.5.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.5.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.5.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4048.0996 | 2024.0498 | 1012.0249 | 0 | 1.6.5.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.5.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.5.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.5.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.5.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.6 | 1.6.5.1.3 | C |  | UW | Develop software needed for OM commissioning |  | 0% | Labor Hours | SC | TRUE |  | 40 | 45 | 35% | 2023-08-03 | 2023-10-03 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | -17621 | [10 empty] | 30 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1822.5 | 2430 | 4252.5 | 53% | 2253.825 | 7084.1743 | 7084.1743 | 20 | [11 empty] | 1215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1215 | 53% | 643.95 | 2067.5669 |  | 0 |  |  |  | 17621 |  | 32539 |  | 9151.7411 | Labor - Task | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.5 | Upgrade String Commissioning | 1.6.5 Upgrade String Commissioning | 1.6.5.1 | Upgrade OM module commissioning | 1.6.5.1 Upgrade OM module commissioning | cell-link@smartsheet.com | 2021-12-01 20:00 |  | 119d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.5.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.5.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.5.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3036.0747 | 4048.0996 | 1.6.5.1.3 | 2067.5669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.5.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.5.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.5.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.5.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.6 | 1.6.5.1.4 | C |  | UW | Commission newly deployed OMs following deployment |  | 0% | Labor Hours | SC | TRUE |  | 40 | 45 | 35% | 2024-01-01 | 2024-04-01 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 |  |  |  | 60 | 60 | 60 | 60 | [5 empty] | 0 | 0 | 0 | 3645 | 3645 | 3645 | 3645 | 0 | 0 | 0 | 0 | 0 | 14580 | 53% | 7727.4 | 24810.8024 |  | 0 | 10162 |  |  |  |  | 39998 |  | 24810.8024 | Labor - Task | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.5 | Upgrade String Commissioning | 1.6.5 Upgrade String Commissioning | 1.6.5.1 | Upgrade OM module commissioning | 1.6.5.1 Upgrade OM module commissioning | marek.rogal@icecube.wisc.edu | 2021-10-29 11:07 |  | 72d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.5.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.5.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.5.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.5.1.4 | 0 | 0 | 0 | 6202.7006 | 6202.7006 | 6202.7006 | 6202.7006 | 0 | 0 | 0 | 0 | 0 | 1.6.5.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.5.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.5.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.5.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.6 | 1.6.5.2.1 | C |  | UW | Develop and review calibration device commissioning plan |  | 0% | Labor Hours | SC | TRUE |  | 40 | 45 | 35% | 2023-07-01 | 2023-09-01 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | -17621 | [9 empty] | 20 | 40 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1215 | 2430 | 607.5 | 4252.5 | 53% | 2253.825 | 7084.1743 | 7084.1743 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 |  | 0 |  |  |  | 17621 |  | 47457 |  | 7084.1743 | Labor - Task | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.5 | Upgrade String Commissioning | 1.6.5 Upgrade String Commissioning | 1.6.5.2 | Upgrade calibration device commissioning | 1.6.5.2 Upgrade calibration device commissioning | marek.rogal@icecube.wisc.edu | 2021-10-29 11:07 |  | 119d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.5.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.5.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.5.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024.0498 | 4048.0996 | 1012.0249 | 1.6.5.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.5.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.5.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.5.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.5.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.6 | 1.6.5.2.3 | C |  | UW | Develop software needed for calibration device commissioning |  | 0% | Labor Hours | SC | TRUE |  | 40 | 45 | 35% | 2023-09-05 | 2023-11-03 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [11 empty] | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 607.5 | 607.5 | 53% | 321.975 | 1012.0249 | 1012.0249 | 30 | 20 | [10 empty] | 1822.5 | 1215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3037.5 | 53% | 1609.875 | 5168.9172 |  | 0 | 10162 |  |  |  |  | 54916 |  | 6180.9421 | Labor - Task | Off Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.5 | Upgrade String Commissioning | 1.6.5 Upgrade String Commissioning | 1.6.5.2 | Upgrade calibration device commissioning | 1.6.5.2 Upgrade calibration device commissioning | cell-link@smartsheet.com | 2021-12-01 20:00 |  | 72d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.5.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.5.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.5.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1012.0249 | 1.6.5.2.3 | 3101.3503 | 2067.5669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.5.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.5.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.5.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.5.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.6 | 1.6.5.2.4 | C |  | UW | Commission newly deployed calibration devices following deployment |  | 0% | Labor Hours | SC | TRUE |  | 40 | 45 | 35% | 2024-01-01 | 2024-04-01 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | -17621 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53% | 0 | 0 | 0 |  |  |  | 60 | 60 | 60 | 60 | [5 empty] | 0 | 0 | 0 | 3645 | 3645 | 3645 | 3645 | 0 | 0 | 0 | 0 | 0 | 14580 | 53% | 7727.4 | 24810.8024 |  | 0 |  |  |  | 17621 |  | 62375 |  | 24810.8024 | Labor - Task | On Ice | 1.6 | IceCube Data Systems Integration | 1.6 IceCube Data Systems Integration | 1.6.5 | Upgrade String Commissioning | 1.6.5 Upgrade String Commissioning | 1.6.5.2 | Upgrade calibration device commissioning | 1.6.5.2 Upgrade calibration device commissioning | marek.rogal@icecube.wisc.edu | 2021-10-29 11:07 |  | 119d | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1.1122 | 1.1361 | 1.6.5.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.5.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.5.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.5.2.4 | 0 | 0 | 0 | 6202.7006 | 6202.7006 | 6202.7006 | 6202.7006 | 0 | 0 | 0 | 0 | 0 | 1.6.5.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.5.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.5.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.5.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Percent Complete | [10 empty] | 1 | 0% | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #NO MATCH |  | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #NO MATCH |  | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #NO MATCH |  | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #NO MATCH |  | 0 | [9 empty] | 0 | [11 empty] | marek.rogal@icecube.wisc.edu | 2021-10-29 11:07 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0