## 1.2.4.1
Upgrade Cost Estimate
Name: | 1.2.4.1 Architecture
Parent WBS: | 1.2 Implementation |  | MATERIALS ESTIMATE | [14 empty] | LABOR ESTIMATE | [6 empty] | TOTAL | SCHEDULE INPUT
Description of Scope:
Initials/Date: |  |  | Quantities | [6 empty] | Basis of Estimate (Select One, See Table Below) | [7 empty] | HOURS | [8 empty] | SCHEDULE LOGIC
WBS (if known) | Project Year (0-10) | Description | QTY | Spare | Total | Fabricate or Procure? | Procurement Details Manufacturer, Model, P/N, Vendor | Unit Price | Total Expected Price | C1 LOE Tasks | C2 Advanced | C3 Preliminary | C4 Conceptual | C5 Pre- Conceptual | C6 Rough Estimate | Cost Estimating Technique (See Table Below) | Materials Comments/Notes (procurement lead time, shipping restrictions, etc) | ENGR ($115/hr) | CAD ($81/hr) | SHOP ($77/hr) | STUDENT ($15/hr) | Total Hours | Total Hours Cost | Labor Comments/Schedule Inputs (eg. "March" or "After Microturbine running", etc) |  | Duration (Weeks) | Predecessors | Successors | Milestone | % of total | orig mat'l | orig labor | orig tot | delta | 14720
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0 |  |  |  |  | 0 |  |  | 0 | 0
1.2.4.1.8 | 5 | Coordination with USAP IT (PY5) |  |  | 0 | [6 empty] | x |  |  |  | D |  | 20 |  |  |  | 20 | 2300 | 6 mtgs x 3 engr x 1hr/mtg + 2 hr prep | 2300 |  |  |  |  | 13.5135
1.2.4.1.9 | 5 | CS Drawings & Documentation (PY5) |  |  | 0 | [6 empty] | x |  |  |  | D |  | 32 |  |  |  | 32 | 3680 |  | 3680 |  |  |  |  | 21.6216 |  | 0 | 0 | 3680
1.2.4.1.10 | 6 | CS Drawings & Documentation (PY6) |  |  | 0 | [6 empty] | x |  |  |  | D |  | 32 |  |  |  | 32 | 3680 |  | 3680 |  |  |  |  | 21.6216 |  | 0 | 0 | 3680
1.2.4.1.11 | 7 | CS Drawings & Documentation (PY7) |  |  | 0 | [6 empty] | x |  |  |  | D |  | 32 |  |  |  | 32 | 3680 |  | 3680 |  |  |  |  | 21.6216 |  | 0 | 0 | 3680
1.2.4.1.12 | 8 | CS Drawings & Documentation (PY8) |  |  | 0 | [6 empty] | x |  |  |  | D |  | 32 |  |  |  | 32 | 3680 |  | 3680 |  |  |  |  | 21.6216 |  | 0 | 0 | 3680
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[9 empty] | 0 | Total Expected Materials Cost | [7 empty] | 148 | 0 | 0 | 0 | 148 | 17020 | Total Hours Cost | 17020
Schedule Logic Terms that can be used:
FS = Finish-to-Start
SS = Start-Start
FF = Finish-Finsh
SF = Start-to-Finish

## 1.2.4.2
Upgrade Cost Estimate
Name: | 1.2.4.2 Control System Hardware
Parent WBS: | 1.2 Implementation |  | MATERIALS ESTIMATE | [14 empty] | LABOR ESTIMATE | [6 empty] | TOTAL | SCHEDULE INPUT
Description of Scope:
Initials/Date: |  |  | Quantities | [6 empty] | Basis of Estimate (Select One, See Table Below) | [7 empty] | HOURS | [8 empty] | SCHEDULE LOGIC
WBS (if known) | Project Year (0-10) | Description | QTY | Spare | Total | Fabricate or Procure? | Procurement Details Manufacturer, Model, P/N, Vendor | Unit Price | Total Expected Price | C1 LOE Tasks | C2 Advanced | C3 Preliminary | C4 Conceptual | C5 Pre- Conceptual | C6 Rough Estimate | Cost Estimating Technique (See Table Below) | Materials Comments/Notes (procurement lead time, shipping restrictions, etc) | ENGR ($115/hr) | CAD ($81/hr) | SHOP ($77/hr) | STUDENT ($15/hr) | Total Hours | Total Hours Cost | Labor Comments/Schedule Inputs (eg. "March" or "After Microturbine running", etc) |  | Duration (Weeks) | Predecessors | Successors | Milestone | % of total | orig mat'l | orig labor | orig tot | delta | -34821.61
1.2.4.2.1 | 4 | PLC Motor Controllers and Readouts |  |  | 0 |  |  |  | 0 | [8 empty] | 0 |  |  |  | 0 | 0 |  | 0 |  |  |  |  | 0 | 16500 | 5175 | 21675 | -21675
1.2.4.2.1.1 | 4 | Design, Build and Test New PLC and Network Box for HPP |  |  | 0 |  |  |  | 0 | [12 empty] | 0 | 0 |  | 0 |  |  |  |  | 0
1.2.4.2.1.1.1 | 4 | PLC and Network Box for HPP Design & Build |  |  | 0 |  |  |  | 0 | [12 empty] | 0 | 0 |  | 0 |  |  |  |  | 0
1.2.4.2.1.2 | 4 | Design, Build & Test RWCR Control Box |  |  | 0 |  |  |  | 0 | [8 empty] | 0 |  |  |  | 0 | 0 |  | 0 |  |  |  |  | 0 | 0 | 12075 | 12075 | -12075
[5 empty] | 0 |  |  |  | 0 | [12 empty] | 0 | 0 |  | 0 |  |  |  |  | 0
1.2.4.2.2 |  | Sensors |  |  | 0 |  |  |  | 0 | [12 empty] | 0 | 0 |  | 0 |  |  |  |  | 0
1.2.4.2.2.5 | 5 | Procure System Sensors (PY5) |  |  | 0 |  |  |  | 27776.17 |  | x |  |  |  |  | C | see breakdown below | 32 |  |  |  | 32 | 3680 | procurement | 31456.17 |  |  |  |  | 22.1798 | 25000 | 3680 | 28680 | 2776.17
[5 empty] | 0 |  |  |  | 0 | [12 empty] | 0 | 0 |  | 0 |  |  |  |  | 0
1.2.4.2.5 | 6 | Infrastructure Repair & Upgrade (w/sub-tasks) obsolete |  |  | 0 |  |  |  | 0 |  | x |  |  |  |  | C |  | 0 |  |  |  | 0 | 0 |  | 0 |  |  |  |  | 0 | 0 | 5175 | 5175 | -5175
[5 empty] | 0 |  |  |  | 0 | [12 empty] | 0 | 0 |  | 0 |  |  |  |  | 0
1.2.4.2.11 |  | Computing Equipment - Production |  |  | 0 |  |  |  | 0 | [12 empty] | 0 | 0 |  | 0 |  |  |  |  | 0
1.2.4.2.11.1 | 5 | CS HW Production Ignition Servers (3x: DCC, TOS1, TOS2) |  |  | 0 |  |  |  | 4671.24 |  | x |  |  |  |  | C | see breakdown below | 10 |  |  |  | 10 | 1150 | procurement | 5821.24 |  |  |  |  | 4.1046 | 10000 | 1150 | 11150 | -5328.76
1.2.4.2.11.2 | 5 | CS HW Production Database Server (1x: DCC) |  |  | 0 |  |  |  | 2905.78 |  | x |  |  |  |  | C | see breakdown below | 10 |  |  |  | 10 | 1150 | procurement | 4055.78 |  |  |  |  | 2.8597 | 10000 | 1150 | 11150 | -7094.22
1.2.4.2.11.3 | 5 | CS HW Production Peripherals (3x sets: DCC, TOS1, TOS2) |  |  | 0 |  |  |  | 17520.34 |  | x |  |  |  |  | C | see breakdown below | 16 |  |  |  | 16 | 1840 | procurement | 19360.34 |  |  |  |  | 13.651 | 2720 | 1840 | 4560 | 14800.34
1.2.4.2.11.4 | 5 | CS HW DCC Core Switch & Security Appliance |  |  | 0 |  |  |  | 19803.36 |  | x |  |  |  |  | C | see breakdown below | 8 |  |  |  | 8 | 920 | procurement | 20723.36 |  |  |  |  | 14.6121 | 6000 | 920 | 6920 | 13803.36
1.2.4.2.11.5 | 5 | CS HW Production Main PLC - PLC (redundant), I/O, network, UPS, in a box (3x: DCC, TOS1, TOS2) |  |  | 0 |  |  |  | 29866.5 |  | x |  |  |  |  | C | see breakdown below | 36 |  |  |  | 36 | 4140 | procurement | 34006.5 |  |  |  |  | 23.9781 | 30000 | 4140 | 34140 | -133.5
[9 empty] | 0 | [12 empty] | 0 | 0 |  | 0 |  |  |  |  | 0
1.2.4.2.13 | 6 | CS HW PY6 Resupply |  |  | 0 |  |  |  | 4000 |  |  |  | x |  |  | D | cables, connectors, hardware, etc. - related to core system | 80 |  |  |  | 80 | 9200 | procurement | 13200 |  |  |  |  | 9.3074 | 4000 | 16560 | 20560 | -7360
1.2.4.2.14 | 7 | CS HW PY7 Resupply |  |  | 0 |  |  |  | 4000 |  |  |  | x |  |  | D | cables, connectors, hardware, etc. - related to core system | 80 |  |  |  | 80 | 9200 | procurement | 13200 |  |  |  |  | 9.3074 | 4000 | 16560 | 20560 | -7360
[5 empty] | 0 |  |  |  | 0 | [12 empty] | 0 | 0 |  | 0 |  |  |  |  | 0
[9 empty] | 110543.39 | Total Expected Materials Cost | [7 empty] | 272 | 0 | 0 | 0 | 272 | 31280 | Total Hours Cost | 141823.39
Schedule Logic Terms that can be used:
FS = Finish-to-Start
[8 empty] | 1.2.4.2.11 - Production HW |  | note: spares included |  | TOTAL: | 74767.22 | [13 empty] | SS = Start-Start
[8 empty] | WBS | Item | Qty | $/ea | subtotal | line total | quote | [12 empty] | FF = Finish-Finsh
[8 empty] | 1.2.4.2.11.1 | Ignitions servers | 4 | 1167.81 |  | 4671.24 | link | [12 empty] | SF = Start-to-Finish
[8 empty] | 1.2.4.2.11.2 | dB server | 2 | 1452.89 |  | 2905.78 | link
[8 empty] | 1.2.4.2.11.3 | Peripherals |  |  |  | 17520.34
[9 empty] | DCC UPS | 2 | 4279.22 | 8558.44 |  | link
[9 empty] | TOS UPS | 3 | 2427.3 | 7281.9 |  | link
[9 empty] | Monitors | 8 | 180 | 1440 |  | link
[9 empty] | Keyboards | 8 | 30 | 240 |  | link
[8 empty] | 1.2.4.2.11.4 | Switches & Security |  |  |  | 19803.36
[9 empty] | Stratix Switch (TOS) | 3 | 4723.36 | 14170.08 |  | link
[9 empty] | Core Switch (DCC) | 2 | 1420.65 | 2841.3 |  | link
[9 empty] | Security Appliance | 2 | 1395.99 | 2791.98 |  | link
[8 empty] | 1.2.4.2.11.5 | Core PLC | 3 | 9955.5 |  | 29866.5 | link
[8 empty] | 1.2.4.2.2 - Sensors (PY5 only - PTs and dPTs) |  |  |  | TOTAL: | 27776.17
[9 empty] | Item | Qty | $/ea | subtotal | line total | quote
[9 empty] | System PT outfit - lot | 1 | 19436.47 |  | 19436.47 | link
[9 empty] | flow dP sensors | 5 | 1667.94 |  | 8339.7 | link

## 1.2.4.3
Upgrade Cost Estimate
Name: | 1.2.4.3 Control System Software
Parent WBS: | 1.2 Implementation |  | MATERIALS ESTIMATE | [14 empty] | LABOR ESTIMATE | [6 empty] | TOTAL | SCHEDULE INPUT
Description of Scope:
Initials/Date: |  |  | Quantities | [6 empty] | Basis of Estimate (Select One, See Table Below) | [7 empty] | HOURS | [8 empty] | SCHEDULE LOGIC
WBS (if known) | Project Year (0-10) | Description | QTY | Spare | Total | Fabricate or Procure? | Procurement Details Manufacturer, Model, P/N, Vendor | Unit Price | Total Expected Price | C1 LOE Tasks | C2 Advanced | C3 Preliminary | C4 Conceptual | C5 Pre- Conceptual | C6 Rough Estimate | Cost Estimating Technique (See Table Below) | Materials Comments/Notes (procurement lead time, shipping restrictions, etc) | ENGR ($115/hr) | CAD ($81/hr) | SHOP ($77/hr) | STUDENT ($15/hr) | Total Hours | Total Hours Cost | Labor Comments/Schedule Inputs (eg. "March" or "After Microturbine running", etc) |  | Duration (Weeks) | Predecessors | Successors | Milestone | % of total | orig mat'l | orig labor | orig tot | delta | 11846.62
1.2.4.3.4 | 5 & 6 | PLC & Software Development (w/sub-tasks) | [9 empty] | x |  |  |  | D |  | 120 |  |  |  | 120 | 13800 | expert opinion, hi-level integration task carrying over from PY4. 40hr vendor relations, 80hr PLC/SCADA/dB integration in testBed | 13800 |  |  |  |  | 6.7569 |  | 16790 | 16790 | -2990
1.2.4.3.5 | 5 | Controls Software: SCADA Monitoring Software - Server | [6 empty] | 2296.62 |  | x |  |  |  |  | C | 2x Dell servers for testBed, $1148.31/ea | 20 |  |  |  | 20 | 2300 | expert opinion, procure and receive | 4596.62 |  |  |  |  | 2.2506 | 10000 | 2300 | 12300 | -7703.38
[22 empty] | 0 | 0 |  | 0 |  |  |  |  | 0
1.2.4.3.9 |  | CS SW SES Operator Screen development | [19 empty] | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0 | 0
1.2.4.3.9.1 |  | Develop MHP-MDS UI Screens [x4] | [19 empty] | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0 | 0
1.2.4.3.9.1.1 | 5 | Local-Panel MDS-specific HMI (PY5) | [9 empty] | x |  |  |  | D |  | 20 |  |  |  | 20 | 2300 | expert opinion | 2300 |  |  |  |  | 1.1261 |  | 2300 | 2300 | 0
1.2.4.3.9.1.2 | 6 | Local-Panel MDS-specific HMI (PY6) | [9 empty] | x |  |  |  | D |  | 20 |  |  |  | 20 | 2300 | expert opinion | 2300 |  |  |  |  | 1.1261 |  | 2300 | 2300 | 0
1.2.4.3.9.1.3 | 5 | DCC-based SCADA UI (PY5) | [9 empty] | x |  |  |  | D |  | 80 |  |  |  | 80 | 9200 | expert opinion | 9200 |  |  |  |  | 4.5046 |  | 5750 | 5750 | 3450
1.2.4.3.9.1.4 | 6 | DCC-based SCADA UI (PY6) | [9 empty] | x |  |  |  | D |  | 80 |  |  |  | 80 | 9200 | expert opinion | 9200 |  |  |  |  | 4.5046 |  | 5750 | 5750 | 3450
1.2.4.3.9.2 |  | Develop FuelSystem-MDS UI Screens | [19 empty] | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0 | 0
1.2.4.3.9.2.1 | 5 | Local-Panel MDS-specific HMI (PY5) | [9 empty] | x |  |  |  | D |  | 8 |  |  |  | 8 | 920 | expert opinion | 920 |  |  |  |  | 0.45046 |  | 920 | 920 | 0
1.2.4.3.9.2.2 | 6 | Local-Panel MDS-specific HMI (PY6) | [9 empty] | x |  |  |  | D |  | 8 |  |  |  | 8 | 920 | expert opinion | 920 |  |  |  |  | 0.45046 |  | 920 | 920 | 0
1.2.4.3.9.2.3 | 5 | DCC-based SCADA (PY5) | [9 empty] | x |  |  |  | D |  | 8 |  |  |  | 8 | 920 | expert opinion | 920 |  |  |  |  | 0.45046 |  | 920 | 920 | 0
1.2.4.3.9.2.4 | 6 | DCC-based SCADA (PY6) | [9 empty] | x |  |  |  | D |  | 8 |  |  |  | 8 | 920 | expert opinion | 920 |  |  |  |  | 0.45046 |  | 920 | 920 | 0
1.2.4.3.9.3 |  | Develop GenSets-MDS UI Screens [x3] | [19 empty] | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0 | 0
1.2.4.3.9.3.1 | 5 | Local-Panel MDS-specific HMI (PY5) | [9 empty] | x |  |  |  | D |  | 8 |  |  |  | 8 | 920 | expert opinion | 920 |  |  |  |  | 0.45046 |  | 920 | 920 | 0
1.2.4.3.9.3.2 | 6 | Local-Panel MDS-specific HMI (PY6) | [9 empty] | x |  |  |  | D |  | 8 |  |  |  | 8 | 920 | expert opinion | 920 |  |  |  |  | 0.45046 |  | 920 | 920 | 0
1.2.4.3.9.3.3 | 5 | DCC-based SCADA (PY5) | [9 empty] | x |  |  |  | D |  | 12 |  |  |  | 12 | 1380 | expert opinion | 1380 |  |  |  |  | 0.67569 |  | 1380 | 1380 | 0
1.2.4.3.9.3.4 | 6 | DCC-based SCADA (PY6) | [9 empty] | x |  |  |  | D |  | 12 |  |  |  | 12 | 1380 | expert opinion | 1380 |  |  |  |  | 0.67569 |  | 1380 | 1380 | 0
1.2.4.3.9.4 |  | Develop Rodwell System UI Screens | [19 empty] | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0 | 0
1.2.4.3.9.4.1 placeholder - no resources | 5 | Local-Panel MDS-specific HMI (PY5) | [15 empty] | 0 |  |  |  | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0 | 0
1.2.4.3.9.4.2 placeholder - no resources | 6 | Local-Panel MDS-specific HMI (PY6) | [15 empty] | 0 |  |  |  | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0 | 0
1.2.4.3.9.4.3 | 5 | DCC-based SCADA (PY5) | [9 empty] | x |  |  |  | D |  | 40 |  |  |  | 40 | 4600 | expert opinion | 4600 |  |  |  |  | 2.2523 |  | 3680 | 3680 | 920
1.2.4.3.9.4.4 | 6 | DCC-based SCADA (PY6) | [9 empty] | x |  |  |  | D |  | 40 |  |  |  | 40 | 4600 | expert opinion | 4600 |  |  |  |  | 2.2523 |  | 3680 | 3680 | 920
1.2.4.3.9.5 |  | Develop HPP-MDS UI Screens | [19 empty] | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0 | 0
1.2.4.3.9.5.1 | 5 | Local-Panel MDS-specific HMI (PY5) | [9 empty] | x |  |  |  | D |  | 18 |  |  |  | 18 | 2070 | expert opinion | 2070 |  |  |  |  | 1.0135 |  | 2070 | 2070 | 0
1.2.4.3.9.5.2 | 6 | Local-Panel MDS-specific HMI (PY6) |  |  | 0 | [6 empty] | x |  |  |  | D |  | 18 |  |  |  | 18 | 2070 | expert opinion | 2070 |  |  |  |  | 1.0135 |  | 2070 | 2070 | 0
1.2.4.3.9.5.3 | 5 | DCC-based SCADA (PY5) |  |  | 0 | [6 empty] | x |  |  |  | D |  | 40 |  |  |  | 40 | 4600 | expert opinion | 4600 |  |  |  |  | 2.2523 |  | 4140 | 4140 | 460
1.2.4.3.9.5.4 | 6 | DCC-based SCADA (PY6) |  |  | 0 | [6 empty] | x |  |  |  | D |  | 40 |  |  |  | 40 | 4600 | expert opinion | 4600 |  |  |  |  | 2.2523 |  | 4140 | 4140 | 460
1.2.4.3.9.6 |  | Develop PHS-MDS UI Screens |  |  | 0 | [16 empty] | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0 | 0
1.2.4.3.9.6.1 | 5 | Local-Panel MDS-specific HMI (PY5) |  |  | 0 | [6 empty] | x |  |  |  | D |  | 16 |  |  |  | 16 | 1840 | expert opinion | 1840 |  |  |  |  | 0.90092 |  | 1840 | 1840 | 0
1.2.4.3.9.6.2 | 6 | Local-Panel MDS-specific HMI (PY6) |  |  | 0 | [6 empty] | x |  |  |  | D |  | 16 |  |  |  | 16 | 1840 | expert opinion | 1840 |  |  |  |  | 0.90092 |  | 1840 | 1840 | 0
1.2.4.3.9.6.3 | 5 | DCC-based SCADA (PY5) |  |  | 0 | [6 empty] | x |  |  |  | D |  | 40 |  |  |  | 40 | 4600 | expert opinion | 4600 |  |  |  |  | 2.2523 |  | 3910 | 3910 | 690
1.2.4.3.9.6.4 | 6 | DCC-based SCADA (PY6) |  |  | 0 | [6 empty] | x |  |  |  | D |  | 40 |  |  |  | 40 | 4600 | expert opinion | 4600 |  |  |  |  | 2.2523 |  | 3910 | 3910 | 690
[30 empty] | 0 |  |  | 0 | 0
1.2.4.3.10 |  | CS SW TOS Operator Screen Development |  |  | 0 | [16 empty] | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0 | 0
1.2.4.3.10.1 | 5 | SCADA - DrillHead (PY5) |  |  | 0 | [6 empty] | X |  |  |  | D |  | 8 |  |  |  | 8 | 920 | expert opinion | 920 |  |  |  |  | 0.45046 |  | 920 | 920 | 0
1.2.4.3.10.2 | 6 | SCADA - DrillHead (PY6) |  |  | 0 | [6 empty] | X |  |  |  | D |  | 8 |  |  |  | 8 | 920 | expert opinion | 920 |  |  |  |  | 0.45046 |  | 920 | 920 | 0
1.2.4.3.10.3 | 5 | SCADA - Drill_Settings (PY5) |  |  | 0 | [6 empty] | X |  |  |  | D |  | 8 |  |  |  | 8 | 920 | expert opinion | 920 |  |  |  |  | 0.45046 |  | 920 | 920 | 0
1.2.4.3.10.4 | 6 | SCADA - Drill_Settings (PY6) |  |  | 0 | [6 empty] | X |  |  |  | D |  | 8 |  |  |  | 8 | 920 | expert opinion | 920 |  |  |  |  | 0.45046 |  | 920 | 920 | 0
1.2.4.3.10.5 | 5 | SCADA - Drilling_Drill Control (PY5) |  |  | 0 | [6 empty] | X |  |  |  | D |  | 12 |  |  |  | 12 | 1380 | expert opinion | 1380 |  |  |  |  | 0.67569 |  | 1380 | 1380 | 0
1.2.4.3.10.6 | 6 | SCADA - Drilling_Drill Control (PY6) |  |  | 0 | [6 empty] | X |  |  |  | D |  | 12 |  |  |  | 12 | 1380 | expert opinion | 1380 |  |  |  |  | 0.67569 |  | 1380 | 1380 | 0
1.2.4.3.10.7 | 5 | SCADA - Drilling_Cable Level Wind (PY5) |  |  | 0 | [6 empty] | X |  |  |  | D |  | 12 |  |  |  | 12 | 1380 | expert opinion | 1380 |  |  |  |  | 0.67569 |  | 1380 | 1380 | 0
1.2.4.3.10.8 | 6 | SCADA - Drilling_Cable Level Wind (PY6) |  |  | 0 | [6 empty] | X |  |  |  | D |  | 12 |  |  |  | 12 | 1380 | expert opinion | 1380 |  |  |  |  | 0.67569 |  | 1380 | 1380 | 0
1.2.4.3.10.9 | 5 | SCADA - Drilling_Hose Level Wind (PY5) |  |  | 0 | [6 empty] | X |  |  |  | D |  | 12 |  |  |  | 12 | 1380 | expert opinion | 1380 |  |  |  |  | 0.67569 |  | 1380 | 1380 | 0
1.2.4.3.10.10 | 6 | SCADA - Drilling_Hose Level Wind (PY6) |  |  | 0 | [6 empty] | X |  |  |  | D |  | 12 |  |  |  | 12 | 1380 | expert opinion | 1380 |  |  |  |  | 0.67569 |  | 1380 | 1380 | 0
1.2.4.3.10.11 | 5 | SCADA - Return Water Pump (PY5) |  |  | 0 | [6 empty] | X |  |  |  | D |  | 8 |  |  |  | 8 | 920 | expert opinion | 920 |  |  |  |  | 0.45046 |  | 920 | 920 | 0
1.2.4.3.10.12 | 6 | SCADA - Return Water Pump (PY6) |  |  | 0 | [6 empty] | X |  |  |  | D |  | 8 |  |  |  | 8 | 920 | expert opinion | 920 |  |  |  |  | 0.45046 |  | 920 | 920 | 0
1.2.4.3.10.13 | 5 | SCADA - Deployment - Cable (PY5) |  |  | 0 | [6 empty] | X |  |  |  | D |  | 8 |  |  |  | 8 | 920 | expert opinion | 920 |  |  |  |  | 0.45046 |  | 920 | 920 | 0
1.2.4.3.10.14 | 6 | SCADA - Deployment - Cable (PY6) |  |  | 0 | [6 empty] | X |  |  |  | D |  | 8 |  |  |  | 8 | 920 | expert opinion | 920 |  |  |  |  | 0.45046 |  | 920 | 920 | 0
1.2.4.3.10.15 | 5 | SCADA - Deployment Settings (PY5) |  |  | 0 | [6 empty] | X |  |  |  | D |  | 10 |  |  |  | 10 | 1150 | expert opinion | 1150 |  |  |  |  | 0.56307 |  | 1150 | 1150 | 0
1.2.4.3.10.16 | 6 | SCADA - Deployment Settings (PY6) |  |  | 0 | [6 empty] | X |  |  |  | D |  | 10 |  |  |  | 10 | 1150 | expert opinion | 1150 |  |  |  |  | 0.56307 |  | 1150 | 1150 | 0
[30 empty] | 0 |  |  | 0 | 0
1.2.4.3.11 |  | CS SW dB Design, my SQL |  |  | 0 | [16 empty] | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0 | 0
1.2.4.3.11.1 | 5 | Build DCC dB schema (PY5) |  |  | 0 | [6 empty] | X |  |  |  | D |  | 80 |  |  |  | 80 | 9200 | expert opinion | 9200 |  |  |  |  | 4.5046 |  | 8280 | 8280 | 920
1.2.4.3.11.2 | 6 | Build DCC dB schema (PY6) |  |  | 0 | [6 empty] | X |  |  |  | D |  | 80 |  |  |  | 80 | 9200 | expert opinion | 9200 |  |  |  |  | 4.5046 |  | 8280 | 8280 | 920
1.2.4.3.11.3 | 5 | Build Drill dB schema (PY5) |  |  | 0 | [6 empty] | X |  |  |  | D |  | 40 |  |  |  | 40 | 4600 | expert opinion | 4600 |  |  |  |  | 2.2523 |  | 4140 | 4140 | 460
1.2.4.3.11.4 | 6 | Build Drill dB schema (PY6) |  |  | 0 | [6 empty] | X |  |  |  | D |  | 40 |  |  |  | 40 | 4600 | expert opinion | 4600 |  |  |  |  | 2.2523 |  | 4140 | 4140 | 460
1.2.4.3.11.5 | 5 | Build Deploy dB schema (PY5) |  |  | 0 | [6 empty] | X |  |  |  | D |  | 30 |  |  |  | 30 | 3450 | expert opinion | 3450 |  |  |  |  | 1.6892 |  | 3450 | 3450 | 0
1.2.4.3.11.6 | 6 | Build Deploy dB schema (PY6) |  |  | 0 | [6 empty] | X |  |  |  | D |  | 30 |  |  |  | 30 | 3450 | expert opinion | 3450 |  |  |  |  | 1.6892 |  | 3450 | 3450 | 0
0
1.2.4.3.12 | 6 | CS SW Standup Production Computing Hardware, Configure, Verify before Shipment (3x systems) (PY6) |  |  | 0 | [7 empty] | X |  |  | D |  | 140 |  |  |  | 140 | 16100 | expert opinion, 5mo duration | 16100 |  |  |  |  | 7.883 | 0 | 12420 | 12420 | 3680
1.2.4.3.13 | 7 | CS SW MDS-specific HMI Refinement (PY7) |  |  | 0 | [7 empty] | X |  |  | D |  | 80 |  |  |  | 80 | 9200 | expert opnion, 4mo duration | 9200 |  |  |  |  | 4.5046 | 0 | 8280 | 8280 | 920
1.2.4.3.14 | 7 | CS SW DCC-based SCADA Refinement (PY7) |  |  | 0 | [7 empty] | X |  |  | D |  | 120 |  |  |  | 120 | 13800 | expert opnion, 4mo duration | 13800 |  |  |  |  | 6.7569 | 0 | 12420 | 12420 | 1380
1.2.4.3.15 | 7 | CS SW TOS-based SCADA Refinement (PY7) |  |  | 0 | [7 empty] | X |  |  | D |  | 120 |  |  |  | 120 | 13800 | expert opnion, 4mo duration | 13800 |  |  |  |  | 6.7569 | 0 | 12420 | 12420 | 1380
1.2.4.3.16 | 7 | CS SW dB Refinement (PY7) |  |  | 0 | [7 empty] | X |  |  | D |  | 120 |  |  |  | 120 | 13800 | expert opnion, 4mo duration | 13800 |  |  |  |  | 6.7569 | 0 | 12420 | 12420 | 1380
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0 |  |  |  |  | 0
[9 empty] | 2296.62 | Total Expected Materials Cost | [7 empty] | 1756 | 0 | 0 | 0 | 1756 | 201940 | Total Hours Cost | 204236.62
Schedule Logic Terms that can be used:
FS = Finish-to-Start
SS = Start-Start
FF = Finish-Finsh
SF = Start-to-Finish

## 1.2.4.4
Upgrade Cost Estimate
Name: | 1.2.4.4 Motor Drives
Parent WBS: | 1.2 Implementation |  | MATERIALS ESTIMATE | [14 empty] | LABOR ESTIMATE | [6 empty] | TOTAL | SCHEDULE INPUT
Description of Scope:
Initials/Date: |  |  | Quantities | [6 empty] | Basis of Estimate (Select One, See Table Below) | [7 empty] | HOURS | [8 empty] | SCHEDULE LOGIC
WBS (if known) | Project Year (0-10) | Description | QTY | Spare | Total | Fabricate or Procure? | Procurement Details Manufacturer, Model, P/N, Vendor | Unit Price | Total Expected Price | C1 LOE Tasks | C2 Advanced | C3 Preliminary | C4 Conceptual | C5 Pre- Conceptual | C6 Rough Estimate | Cost Estimating Technique (See Table Below) | Materials Comments/Notes (procurement lead time, shipping restrictions, etc) | ENGR ($115/hr) | CAD ($81/hr) | SHOP ($77/hr) | STUDENT ($15/hr) | Total Hours | Total Hours Cost | Labor Comments/Schedule Inputs (eg. "March" or "After Microturbine running", etc) |  | Duration (Weeks) | Predecessors | Successors | Milestone
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
1.2.4.4.4 |  | Programming and Testing at PSL |  |  | 0 | [6 empty] | x |  |  |  | D |  | 135 |  |  |  | 135 | 15525 | expert opinion. Carryover task from PY4. Final archiving of drives prior to shipments | 15525
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[9 empty] | 0 | Total Expected Materials Cost | [7 empty] | 135 | 0 | 0 | 0 | 135 | 15525 | Total Hours Cost | 15525
Schedule Logic Terms that can be used:
FS = Finish-to-Start
SS = Start-Start
FF = Finish-Finsh
SF = Start-to-Finish

## 1.2.4.5
Upgrade Cost Estimate
Name: | 1.2.4.5 E-Stop System
Parent WBS: | 1.2 Implementation |  | MATERIALS ESTIMATE | [14 empty] | LABOR ESTIMATE | [6 empty] | TOTAL | SCHEDULE INPUT
Description of Scope:
Initials/Date: |  |  | Quantities | [6 empty] | Basis of Estimate (Select One, See Table Below) | [7 empty] | HOURS | [8 empty] | SCHEDULE LOGIC
WBS (if known) | Project Year (0-10) | Description | QTY | Spare | Total | Fabricate or Procure? | Procurement Details Manufacturer, Model, P/N, Vendor | Unit Price | Total Expected Price | C1 LOE Tasks | C2 Advanced | C3 Preliminary | C4 Conceptual | C5 Pre- Conceptual | C6 Rough Estimate | Cost Estimating Technique (See Table Below) | Materials Comments/Notes (procurement lead time, shipping restrictions, etc) | ENGR ($115/hr) | CAD ($81/hr) | SHOP ($77/hr) | STUDENT ($15/hr) | Total Hours | Total Hours Cost | Labor Comments/Schedule Inputs (eg. "March" or "After Microturbine running", etc) |  | Duration (Weeks) | Predecessors | Successors | Milestone
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
1.2.4.5.6 | 6 | E-Stop Resupply (PY6) |  |  | 0 |  |  |  | 5000 |  |  |  | x |  |  | D | Annual resupply: mil connectors, slap switches, cabling, e-stop box components (relays, power supplies, connectors) | 24 |  | 24 |  | 48 | 4608 | expert opinion: identifying, procuring, organizing | 9608
1.2.4.5.7 | 7 | E-Stop Resupply (PY7) |  |  | 0 |  |  |  | 5000 |  |  |  | x |  |  | D | Annual resupply: mil connectors, slap switches, cabling, e-stop box components (relays, power supplies, connectors) | 24 |  | 24 |  | 48 | 4608 | expert opinion: identifying, procuring, organizing | 9608
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[9 empty] | 10000 | Total Expected Materials Cost | [7 empty] | 48 | 0 | 48 | 0 | 96 | 9216 | Total Hours Cost | 19216
Schedule Logic Terms that can be used:
FS = Finish-to-Start
SS = Start-Start
FF = Finish-Finsh
SF = Start-to-Finish

## 1.2.4.6
Upgrade Cost Estimate
Name: | 1.2.4.6 Drill Control Center
Parent WBS: | 1.2 Implementation |  | MATERIALS ESTIMATE | [14 empty] | LABOR ESTIMATE | [6 empty] | TOTAL | SCHEDULE INPUT
Description of Scope:
Initials/Date: |  |  | Quantities | [6 empty] | Basis of Estimate (Select One, See Table Below) | [7 empty] | HOURS | [8 empty] | SCHEDULE LOGIC
WBS (if known) | Project Year (0-10) | Description | QTY | Spare | Total | Fabricate or Procure? | Procurement Details Manufacturer, Model, P/N, Vendor | Unit Price | Total Expected Price | C1 LOE Tasks | C2 Advanced | C3 Preliminary | C4 Conceptual | C5 Pre- Conceptual | C6 Rough Estimate | Cost Estimating Technique (See Table Below) | Materials Comments/Notes (procurement lead time, shipping restrictions, etc) | ENGR ($115/hr) | CAD ($81/hr) | SHOP ($77/hr) | STUDENT ($15/hr) | Total Hours | Total Hours Cost | Labor Comments/Schedule Inputs (eg. "March" or "After Microturbine running", etc) |  | Duration (Weeks) | Predecessors | Successors | Milestone | % of total | orig mat'l | orig labor | orig tot | delta | 3270
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0 |  |  |  |  | 0
1.2.4.6.3 | 5 | Update Workspace (desk, chairs), Procure Printer & Accessories |  |  | 0 |  |  |  | 10770 |  | x |  |  |  |  | C | All-in-One 11x17 printer = $3599.99 Chairs, qty=6 x $1195/ea = $7170 Total = $10770 See following quotes at this link: - 1.2.4_Printer_HP… - 1.2.4 Chair Aeron… | 32 |  |  |  | 32 | 3680 | procuring, receiving, warehousing, packing | 14450 | [5 empty] | 7500 | 3680 | 11180 | 3270
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[9 empty] | 10770 | Total Expected Materials Cost | [7 empty] | 32 | 0 | 0 | 0 | 32 | 3680 | Total Hours Cost | 14450
Schedule Logic Terms that can be used:
FS = Finish-to-Start
SS = Start-Start
FF = Finish-Finsh
SF = Start-to-Finish

## 1.2.4.7
Upgrade Cost Estimate
Name: | 1.2.4.7 Outdoor Cables
Parent WBS: | 1.2 Implementation |  | MATERIALS ESTIMATE | [14 empty] | LABOR ESTIMATE | [6 empty] | TOTAL | SCHEDULE INPUT
Description of Scope:
Initials/Date: |  |  | Quantities | [6 empty] | Basis of Estimate (Select One, See Table Below) | [7 empty] | HOURS | [8 empty] | SCHEDULE LOGIC
WBS (if known) | Project Year (0-10) | Description | QTY | Spare | Total | Fabricate or Procure? | Procurement Details Manufacturer, Model, P/N, Vendor | Unit Price | Total Expected Price | C1 LOE Tasks | C2 Advanced | C3 Preliminary | C4 Conceptual | C5 Pre- Conceptual | C6 Rough Estimate | Cost Estimating Technique (See Table Below) | Materials Comments/Notes (procurement lead time, shipping restrictions, etc) | ENGR ($115/hr) | CAD ($81/hr) | SHOP ($77/hr) | STUDENT ($15/hr) | Total Hours | Total Hours Cost | Labor Comments/Schedule Inputs (eg. "March" or "After Microturbine running", etc) |  | Duration (Weeks) | Predecessors | Successors | Milestone | % of total | orig mat'l | orig labor | orig tot | delta | 1840
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0 |  |  |  |  | 0
1.2.4.7.3 | 5 | Fabricate and Test SES & SES to TOS Cables - Signal |  |  | 0 | [6 empty] | x |  |  |  | D |  | 40 |  |  |  | 40 | 4600 | expert opinion | 4600 | [6 empty] | 2760 | 2760 | 1840
1.2.4.7.4 | 6 | CS Cabling Resupply (PY6) |  |  | 0 |  |  |  | 5000 |  |  |  | x |  |  | D | annual resupply. ethernet cabling, connectors, management | 24 |  |  |  | 24 | 2760 | expert opinion | 7760
1.2.4.7.5 | 7 | CS Cabling Resupply (PY7) |  |  | 0 |  |  |  | 5000 |  |  |  | x |  |  | D | annual resupply. ethernet cabling, connectors, management | 24 |  |  |  | 24 | 2760 | expert opinion | 7760
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0
[9 empty] | 10000 | Total Expected Materials Cost | [7 empty] | 88 | 0 | 0 | 0 | 88 | 10120 | Total Hours Cost | 20120
Schedule Logic Terms that can be used:
FS = Finish-to-Start
SS = Start-Start
FF = Finish-Finsh
SF = Start-to-Finish

## 1.2.4.8
Upgrade Cost Estimate
Name: | 1.2.4.8 Controls Subsystems (PY5-PY8)
Parent WBS: | 1.2 Implementation |  | MATERIALS ESTIMATE | [14 empty] | LABOR ESTIMATE | [6 empty] | TOTAL | SCHEDULE INPUT
Description of Scope:
Initials/Date: |  |  | Quantities | [6 empty] | Basis of Estimate (Select One, See Table Below) | [7 empty] | HOURS | [8 empty] | SCHEDULE LOGIC
WBS (if known) | Project Year (0-10) | Description | QTY | Spare | Total | Fabricate or Procure? | Procurement Details Manufacturer, Model, P/N, Vendor | Unit Price | Total Expected Price | C1 LOE Tasks | C2 Advanced | C3 Preliminary | C4 Conceptual | C5 Pre- Conceptual | C6 Rough Estimate | Cost Estimating Technique (See Table Below) | Materials Comments/Notes (procurement lead time, shipping restrictions, etc) | ENGR ($115/hr) | CAD ($81/hr) | SHOP ($77/hr) | STUDENT ($15/hr) | Total Hours | Total Hours Cost | Labor Comments/Schedule Inputs (eg. "March" or "After Microturbine running", etc) |  | Duration (Weeks) | Predecessors | Successors | Milestone | % of total | orig mat'l | orig labor | orig tot | delta | 6218
1.2.4.8.1 |  | CS MHPs |  |  | 0 | [16 empty] | 0 | 0 |  | 0
1.2.4.8.1.2 |  | CS MHP HW2-3: Heater Controller Temp Displays & Controllers | [19 empty] | 0 | 0 |  | 0 |  |  |  |  | 0 |  |  | 0 | 0
1.2.4.8.1.2.1 | 5 | Procure sample temperature display and digital thermostat, install in test bed heater, test | [6 empty] | 300 |  | x |  |  |  |  | D | 1x SOLO display ($100) and 1x SOLO controller ($111) + custom mounting kit. See "1.2.4 Solo" quotes here | 8 |  |  |  | 8 | 920 | expert opinion | 1220 |  |  |  |  | 0.18928 | 300 | 3680 | 3980 | -2760
1.2.4.8.1.2.2 | 5 | Select and procure temperature display units for heater controls, conversion hardware | [6 empty] | 4500 |  | x |  |  |  |  | C | qty=38 + 4 spares. 42x $100. Plus production mounting kits ~$300. See "Solo display" quote here | 8 |  |  |  | 8 | 920 | expert opinion | 5420 |  |  |  |  | 0.84091 | 2400 | 3680 | 6080 | -660
1.2.4.8.1.2.3 | 5 | Replace temperature display units, remove RTD DGHs, transfer net connections, test | [9 empty] | x |  |  |  | D |  | 24 |  | 100 |  | 124 | 10460 | expert opinion. There are 38 heaters. 100 tech hr/38 ~ 2.5 hr/heater control | 10460 |  |  |  |  | 1.6229 |  | 15228 | 15228 | -4768
1.2.4.8.1.2.4 | 5 | Select and procure digital thermostats for heater controls, conversion hardware | [6 empty] | 4962 |  | x |  |  |  |  | C | qty=38 + 4 spares. 42x $111. Plus production mounting kits ~$300. See "Solo display" quote here | 8 |  |  |  | 8 | 920 | expert opinion | 5882 |  |  |  |  | 0.91259 | 3200 | 3680 | 6880 | -998
1.2.4.8.1.2.5 | 5 | Write thermostat field replacement procedure | [9 empty] | x |  |  |  | D |  | 24 |  |  |  | 24 | 2760 | expert opinion | 2760 |  |  |  |  | 0.42821 |  | 2760 | 2760 | 0
1.2.4.8.1.3 |  | CS MHP HW4-6: Maintain Documentation, Prepare Field Plans | [19 empty] | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0 | 0
1.2.4.8.1.3.1 | 5 | Write rewiring and test instructions for MHP E-stop boxes (fixes switch contact selections made in Gen 1) | [9 empty] | x |  |  |  | D |  | 24 |  |  |  | 24 | 2760 | expert opinion | 2760 |  |  |  |  | 0.42821 |  | 2760 | 2760 | 0
1.2.4.8.1.3.2 | 5 | Write test procedures for dry heater tests | [9 empty] | x |  |  |  | D |  | 32 |  |  |  | 32 | 3680 | expert opinion | 3680 |  |  |  |  | 0.57095 |  | 3680 | 3680 | 0
1.2.4.8.1.3.3 | 5 | Assemble equipment to test flow meters (excitation coil and portable pulse generator) | [6 empty] | 759 |  |  | x |  |  |  | C | pulse generator $359 + hardware for excitation coil and field kit case ~$400. See this link for pulse generator | 24 |  |  |  | 24 | 2760 | expert opinion | 3519 |  |  |  |  | 0.54597 | 800 | 2760 | 3560 | -41
1.2.4.8.1.3.4 | 5 | Write flow meter test procedure and assemble test kit | [9 empty] | x |  |  |  | D |  | 24 |  |  |  | 24 | 2760 | expert opinion | 2760 |  |  |  |  | 0.42821
1.2.4.8.1.5 |  | CS MHP SW: Develop PLC-MHP MDS SW Functionality [Entire MHP system] | [19 empty] | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0 | 0
1.2.4.8.1.5.1 |  | Develop heater-based sensor readout; (heater temp/flow manifold pressures | [9 empty] | x |  |  |  | D |  | 120 |  |  |  | 120 | 13800 | expert opinion | 13800 |  |  |  |  | 2.1411 |  | 12420 | 12420 | 1380
1.2.4.8.1.5.2 |  | Develop environmental sensor readout; (bldg temps, smoke, e-stop) | [9 empty] | x |  |  |  | D |  | 36 |  |  |  | 36 | 4140 | expert opinion | 4140 |  |  |  |  | 0.64232 |  | 4140 | 4140 | 0
1.2.4.8.1.5.3 |  | Develop heater control; (ON/OFF, Thermostat setpoint) | [9 empty] | x |  |  |  | D |  | 40 |  |  |  | 40 | 4600 | expert opinion | 4600 |  |  |  |  | 0.71369 |  | 4140 | 4140 | 460
1.2.4.8.1.5.4 | 4 | Configure network switch | [22 empty] | 0
1.2.4.8.1.5.5 | 4 | Configure RTA gateway to M-DGH interface | [22 empty] | 0
1.2.4.8.1.5.6 | 4 | Configure M-DGHs | [22 empty] | 0
1.2.4.8.1.5.7 |  | Implement interlocks | [9 empty] | x |  |  |  | D |  | 20 |  |  |  | 20 | 2300 | expert opinion | 2300 |  |  |  |  | 0.35684 |  | 2300 | 2300 | 0
1.2.4.8.1.5.8 |  | Document Subsystem | [9 empty] | x |  |  |  | D |  | 20 |  |  |  | 20 | 2300 | expert opinion | 2300 | [5 empty] | 0 | 0 | 0 | 2300
0
1.2.4.8.2 |  | CS PHS & WT2 | [19 empty] | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0 | 0
1.2.4.8.2.1 |  | CS PHS HW1: Motor Drive Config & Install Kits | [19 empty] | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0 | 0
1.2.4.8.2.1.1 | 4 | Procure motor drives (2 transfer pumps)
1.2.4.8.2.1.2 | 4 | Configure VFDs with accessories, connection pigtails, document
1.2.4.8.2.1.3 | 5 | Develop VFD installation strategy & document, procure materials | [9 empty] | x |  |  |  | D |  | 40 |  | 16 |  | 56 | 5832 | expert opinion | 5832 |  |  |  |  | 0.90483 |  | 7442 | 7442 | -1610
1.2.4.8.2.2 |  | CS PHS HW2: Estop Box Re-outfitting
1.2.4.8.2.2.1 | 4 | Select and procure E-stop relays
1.2.4.8.2.2.2 | 4 | Develop and document E-stop box rewiring instructions
1.2.4.8.2.3 |  | CS PHS HW3: Network Box Refurb & Config | [9 empty] | x | [9 empty] | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0 | 0
1.2.4.8.2.3.1 | 4 | Select and procure PHS network switch, mount in protective enclosure
1.2.4.8.2.3.2 | 5 | Select and procure new power supplies for the network box, procure one RS-485 gateway | [6 empty] | 925 |  | x |  |  |  |  | C | Power supplies ~ 2x $100 = $200 Gateway $724.50 Total = $925 see this link for Gateway quote | 16 |  |  |  | 16 | 1840 | expert opinion | 2765 |  |  |  |  | 0.42899 | 1000 | 1840 | 2840 | -75
1.2.4.8.2.3.3 | 5 | Redesign and rebuild PHS network box with new I/O, document as-built configuration | [6 empty] | 3850 |  |  | x |  |  |  | C | remote i/o without PLC, see breakdown below. | 144 |  | 40 |  | 184 | 19640 | expert opinion | 23490 |  |  |  |  | 3.6444 | 3000 | 19332 | 22332 | 1158
1.2.4.8.2.3.4 | 5 | Indicate where approximately 20 sensor and network cables terminate in PHS and document config. plans | [9 empty] | x |  |  |  | D |  | 108 |  |  |  | 108 | 12420 | expert opinion | 12420 |  |  |  |  | 1.9269 |  | 12420 | 12420 | 0
1.2.4.8.2.3.5 | 5 | Configure heater-mounted DGH modules, develop and document DGH installation and test plans | [9 empty] | x |  |  |  | D |  | 24 |  | 16 |  | 40 | 3992 | expert opinion | 3992 |  |  |  |  | 0.61935 |  | 3376 | 3376 | 616
1.2.4.8.2.4 | 5 | CS PHS HW4: New E-stop Slap Switch & Box for Outdoor Location | [6 empty] | 200 |  |  | x |  |  |  | D | est. for slap switch in small enclosure with connectors | 8 |  |  |  | 8 | 920 | expert opinion | 1120 |  |  |  |  | 0.17377 | 200 | 920 | 1120 | 0
1.2.4.8.2.5 | 5 | CS PHS HW5: Develop heater test procedures, configure test tools, document test plans | [9 empty] | x |  |  |  | D |  | 36 |  |  |  | 36 | 4140 | expert opinion | 4140 |  |  |  |  | 0.64232 |  | 4140 | 4140 | 0
1.2.4.8.2.6
1.2.4.8.2.6.1 | 4 | Select and procure new tank level and temperature sensors
1.2.4.8.2.6.2 | 4 | Install one level sensors in the test bed and operate over some period
1.2.4.8.2.6.3 | 4 | Test level sensor tolerance of environmental conditions and system noise
1.2.4.8.2.6.4 | 4 | Design and build cables for tank sensors
1.2.4.8.2.7 |  | CS PHS HW7-8: Maintain Documentation, Prepare Field Plans | [9 empty] | x | [9 empty] | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0 | 0
1.2.4.8.2.7.1 | 5 | Develop and document test plans for all PHS system components | [9 empty] | x |  |  |  | D |  | 36 |  |  |  | 36 | 4140 | expert opinion | 4140 |  |  |  |  | 0.64232 |  | 4140 | 4140 | 0
1.2.4.8.2.7.2 | 5 | Review Gen-1 docs, identify where sensor connections terminated, plan for reconnection and test | [9 empty] | x |  |  |  | D |  | 36 |  |  |  | 36 | 4140 | expert opinion | 4140 |  |  |  |  | 0.64232 |  | 4140 | 4140 | 0
1.2.4.8.2.8 |  | Develop PLC-PHS MDS SW Functionality | [9 empty] | x | [9 empty] | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0 | 0
1.2.4.8.2.8.1 |  | Develop heater-based sensor readout; (heater temp/flow manifold pressures) | [9 empty] | x |  |  |  | D |  | 24 |  |  |  | 24 | 2760 | expert opinion | 2760 |  |  |  |  | 0.42821 |  | 4140 | 4140 | -1380
1.2.4.8.2.8.2 |  | Develop environmental sensor readout; (bldg temps, smoke, e-stop) | [9 empty] | x |  |  |  | D |  | 16 |  |  |  | 16 | 1840 | expert opinion | 1840 |  |  |  |  | 0.28547 |  | 1840 | 1840 | 0
1.2.4.8.2.8.3 |  | Develop water tank sensors readout | [9 empty] | x |  |  |  | D |  | 24 |  |  |  | 24 | 2760 | expert opinion | 2760 |  |  |  |  | 0.42821 |  | 2760 | 2760 | 0
1.2.4.8.2.8.4 |  | Develop heater control; (ON/OFF, Thermostat setpoint) | [9 empty] | x |  |  |  | D |  | 16 |  |  |  | 16 | 1840 | expert opinion | 1840 |  |  |  |  | 0.28547 |  | 1840 | 1840 | 0
1.2.4.8.2.8.5 |  | Develop AB drive/pump control; (variable speed velocity drives) | [9 empty] | x |  |  |  | D |  | 40 |  |  |  | 40 | 4600 | expert opinion | 4600 |  |  |  |  | 0.71369 |  | 4140 | 4140 | 460
1.2.4.8.2.8.6 | 4 | Configure/document network switch
1.2.4.8.2.8.7 | 4 | Configure/document RTA gateway to M-DGH interface
1.2.4.8.2.8.8 | 4 | Configure/document Point I/O Block
1.2.4.8.2.8.9 | 4 | Configure/document M-DGHs (Heater-mounted + all others)
1.2.4.8.2.8.10 |  | Implement interlocks | [9 empty] | x |  |  |  | D |  | 20 |  |  |  | 20 | 2300 | expert opinion | 2300 |  |  |  |  | 0.35684 |  | 2300 | 2300 | 0
1.2.4.8.2.8.11 |  | Document Subsystem | [9 empty] | x |  |  |  | D |  | 40 |  |  |  | 40 | 4600 | expert opinion | 4600 |  |  |  |  | 0.71369 |  | 4140 | 4140 | 460
[30 empty] | 0 |  |  | 0 | 0
1.2.4.8.3 |  | CS TOS & Reels | [19 empty] | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0 | 0
1.2.4.8.3.1 |  | CS TOS HW1: Motor Drive Config & Install Kits | [9 empty] | x | [9 empty] | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0 | 0
1.2.4.8.3.1.1 | 4 | Procure TOS motor drives (16 VFDs) and accessories
1.2.4.8.3.1.2 | 4 | (PY4) Configure VFDs with accessories, connection pigtails, document
1.2.4.8.3.1.3 | 5 | Configure VFDs with accessories, connection pigtails, document | [6 empty] | 5000 |  |  | x |  |  |  | D | est. for AC power and control signal pigtail materials. 16x drives to configure with HW. | 24 |  | 40 |  | 64 | 5840 | expert opninion | 10840 |  |  |  |  | 1.6818 | 2000 | 2456 | 4456 | 6384
1.2.4.8.3.1.4 | 5 | Develop VFD mechanical and electrical installation strategies & document, procure materials | [6 empty] | 2000 |  |  | x |  |  |  | D | est. for hardware needed for VFD installation kits. Use existing mounting locations but adapt for new form factor. Material and hardware. 16x drives to install. | 40 |  | 80 |  | 120 | 10760 | expert opninion | 12760 |  |  |  |  | 1.9797 | 4000 | 9512 | 13512 | -752
1.2.4.8.3.1.5 | 5 | SW configuration and autotuning, make plan - MDCR/LW, DSHR/LW, RWHR, RWCR, Tower Hoist | [9 empty] | x |  |  |  | D |  | 80 |  |  |  | 80 | 9200 | expert opinion | 9200 |  |  |  |  | 1.4274 |  | 8280 | 8280 | 920
1.2.4.8.3.2 |  | CS TOS HW2: Estop | [19 empty] | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0 | 0
1.2.4.8.3.2.1 | 4 | Review Gen 1 documentation against as-built units located at PSL; mark up and update drawings | [9 empty] | x |  |  |  | D | [5 empty] | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0 | 0
1.2.4.8.3.2.2 | 5 | Document changes to E-stop and Reel stop interfaces to motor drives, procure materials, implement | [6 empty] | 4000 |  |  | x |  |  |  | D | connectors and wiring, large panel reconfiguration, interfaces with all drives, i/o, and reels. 2x panels $2000/ea est. | 120 |  | 40 |  | 160 | 16880 | expert opinion | 20880 |  |  |  |  | 3.2395 | 2000 | 15192 | 17192 | 3688
1.2.4.8.3.2.3 | 5 | Test refurbished E-stop panels with reel safety junction boxes, I/O boxes, network boxes, drives | [6 empty] | 250 |  |  | x |  |  |  | D | test equip | 200 |  | 80 |  | 280 | 29160 | expert opinion | 29410 |  |  |  |  | 4.5629 | 2000 | 30844 | 32844 | -3434
1.2.4.8.3.2.4 | 4 | Develop and document E-stop switch re-wiring plans for TOS, procure spare slap switches | [9 empty] | x |  |  |  | D | [5 empty] | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0 | 0
1.2.4.8.3.2.5 | 4 | (PY4) Design new E-stop controllers for TOS, build and test boxes | [9 empty] | x |  |  |  | D | [5 empty] | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0 | 0
1.2.4.8.3.2.6 | 5 | Design new E-stop controllers for TOS, build and test boxes | [6 empty] | 3000 |  |  | x |  |  |  | D | Circuit boards, industrial switches, MS connectors, enclosures. Qty = 2 @ $1500/ea materials. Copy DCC controller design | 120 |  | 80 |  | 200 | 19960 | expert opinion | 22960 |  |  |  |  | 3.5622 | 1000 | 17964 | 18964 | 3996
1.2.4.8.3.3 |  | CS TOS HW3: Network & PLC | [19 empty] | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0 | 0
1.2.4.8.3.3.1 | 5 | Spec and procure new power supplies for TOS network boxes, procure DGH gateway, document changes | [6 empty] | 1650 |  | x |  |  |  |  | C | 2x TOS network boxes. Power supplies ~ 2x $100 = $200, Gateway 2x $725 = $1450, Total = $1650. See this link for Gateway quote | 24 |  |  |  | 24 | 2760 | expert opinion | 4410 |  |  |  |  | 0.68421 | 1000 | 3680 | 4680 | -270
1.2.4.8.3.3.2 | 5 | Document plans for TOS network box upgrades, specify and procure tools and materials | [6 empty] | 400 |  |  | x |  |  |  | D | specialty tools and connection hardware, wiring | 24 |  | 16 |  | 40 | 3992 | expert opinion | 4392 |  |  |  |  | 0.68141 | 400 | 3376 | 3776 | 616
1.2.4.8.3.3.3 | 5 | Spec TOS network switch location, spec cables to drives, I/O boxes, network box, DCC modem, PC, PLC, e-stop controller | [6 empty] | 1000 |  |  | x |  |  |  | D | Industrial Ethernet cables, connectors | 60 |  | 32 |  | 92 | 9364 | expert opinion | 10364 |  |  |  |  | 1.608 | 1000 | 9364 | 10364 | 0
1.2.4.8.3.3.4 | 5 | Design enclosures for TOS PLCs and attached I/O used for payout encoders, load cells; procure parts | [6 empty] | 2000 |  |  | x |  |  |  | D | supplemental to core PLCs in 1.2.4.2. This tasks captures some anticipated additional I/O and connection hardware for motion control system, and packaging the PLCs into the TOS control rooms, wire management, etc. Engr. Est. $1000/TOS x 2 TOSes | 80 |  |  |  | 80 | 9200 | expert opinion | 11200 |  |  |  |  | 1.7377 | 8000 | 16560 | 24560 | -13360
1.2.4.8.3.3.5 | 5 | Construct enclosures for TOS PLCs and attached I/O , test | [6 empty] | 200 |  |  | x |  |  |  | D |  | 60 |  | 72 |  | 132 | 12444 | expert opinion | 12644 |  |  |  |  | 1.9617 | 200 | 13824 | 14024 | -1380
1.2.4.8.3.4 |  | CS TOS HW4: I/O Boxes | [19 empty] | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0 | 0
1.2.4.8.3.4.1 | 4 | Design I/O box upgrades using A-B Point I/O modules, install | [9 empty] | x |  |  |  | D | [5 empty] | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0 | 0
1.2.4.8.3.4.2 | 4 | Test I/O boxes with pendants and motor drives | [9 empty] | x |  |  |  | D | [5 empty] | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0 | 0
1.2.4.8.3.4.3 | 4 | Design and build cables for I/O box connections to motor drives and E-stop box | [9 empty] | x |  |  |  | D | [5 empty] | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0 | 0
1.2.4.8.3.4.4 | 4 | Rebuild two portable I/O boxes, test (used to operate return water cable reel motor drives with pendant) | [9 empty] | x |  |  |  | D | [5 empty] | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0 | 0
1.2.4.8.3.5 |  | CS TOS HW5-6: Maintain Documentation, Develop Field Plans | [19 empty] | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0 | 0
1.2.4.8.3.5.1 | 5 | Develop and document on-ice test plans for E-stop, Reel-Stop, and Fault Detection hardware | [9 empty] | x |  |  |  | D |  | 40 |  |  |  | 40 | 4600 | expert opinion | 4600 |  |  |  |  | 0.71369 |  | 4140 | 4140 | 460
1.2.4.8.3.5.2 | 5 | Develop and document on-ice test plans for integrated hardware | [9 empty] | x |  |  |  | D |  | 120 |  |  |  | 120 | 13800 | expert opinion | 13800 |  |  |  |  | 2.1411 |  | 16560 | 16560 | -2760
1.2.4.8.3.6 |  | CS TOS HW7: Tower Payout Encoders & Load Cells | [19 empty] | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0 | 0
1.2.4.8.3.6.1 | 4 | Review documentation, specify hose and cable payout encoders, specify load cells, procure | [8 empty] | x |  |  |  |  | D | [5 empty] | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0 | 0
1.2.4.8.3.6.2 | 5 | Test load cells and payout encoders with PLC, verify functionality required for payout control; load sharing | [9 empty] | x |  |  |  | D |  | 200 |  |  |  | 200 | 23000 | expert opinion | 23000 |  |  |  |  | 3.5684 |  | 34500 | 34500 | -11500
1.2.4.8.3.7 | 4 | CS TOS HW8: Line Filters for All Drives in TOS2, Identify and Procure | [9 empty] | x |  |  |  | D | [5 empty] | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0 | 0
1.2.4.8.3.8 | 5 | CS TOS HW9: Tower Hoist Reconnect Materials TOS2, Identify and Procure | [6 empty] | 1000 |  |  | x |  |  |  | D | est. power and signal wiring and connectors | 40 |  |  |  | 40 | 4600 | expert opinion | 5600 |  |  |  |  | 0.86883 | 1000 | 3680 | 4680 | 920
1.2.4.8.3.9 | 5 | CS TOS HW10: Review deployment plans and HW, integrate with drill | [9 empty] | x |  |  |  | D |  | 120 |  |  |  | 120 | 13800 | expert opinion | 13800 |  |  |  |  | 2.1411 |  | 12420 | 12420 | 1380
1.2.4.8.3.10 |  | CS TOS Develop PLC Space SW Functionality | [19 empty] | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0 | 0
1.2.4.8.3.10.1 | 5 | Develop general control/monitoring software | [9 empty] | x |  |  |  | D |  | 120 |  |  |  | 120 | 13800 | expert opinion | 13800 |  |  |  |  | 2.1411 |  | 12420 | 12420 | 1380
1.2.4.8.3.10.2 | 5 | Develop reel control software(MCR/LW, DSHR/LW, RWHR, RWCR, Tower Winch) | [9 empty] | x |  |  |  | D |  | 80 |  |  |  | 80 | 9200 | expert opinion | 9200 |  |  |  |  | 1.4274 |  | 8280 | 8280 | 920
1.2.4.8.3.10.3 | 5 | Develop tension-sharing algorithm software (MCR/LW, DSHR/LW) | [9 empty] | x |  |  |  | D |  | 120 |  |  |  | 120 | 13800 | expert opinion | 13800 |  |  |  |  | 2.1411 |  | 12420 | 12420 | 1380
1.2.4.8.3.10.4 | 5 | Develop drillhead data monitoring interface) | [9 empty] | x |  |  |  | D |  | 24 |  |  |  | 24 | 2760 | expert opinion | 2760 |  |  |  |  | 0.42821 |  | 2760 | 2760 | 0
1.2.4.8.3.10.5 | 4 | Configure/document network switch | [9 empty] | x |  |  |  | D | [5 empty] | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0 | 0
1.2.4.8.3.10.6 | 4 | Configure RTA gateway to M-DGH interface | [9 empty] | x |  |  |  | D | [5 empty] | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0 | 0
1.2.4.8.3.10.7 | 4 | Configure M-DGHs | [9 empty] | x |  |  |  | D | [5 empty] | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0 | 0
1.2.4.8.3.10.8 | 5 | Implement interlocks | [9 empty] | x |  |  |  | D |  | 40 |  |  |  | 40 | 4600 | expert opinion | 4600 |  |  |  |  | 0.71369 |  | 4140 | 4140 | 460
1.2.4.8.3.10.9 | 5 | Document Subsystem | [9 empty] | x |  |  |  | D |  | 40 |  |  |  | 40 | 4600 | expert opinion | 4600 |  |  |  |  | 0.71369 |  | 4140 | 4140 | 460
[33 empty] | 0 | 0
1.2.4.8.4 |  | CS Drillheads | [19 empty] | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0 | 0
1.2.4.8.4.1 | 5 | CS HW Drillhead sofware/hardware production version | [6 empty] | 2510 |  | x |  |  |  |  | C | Industrial-grade Raspberry Pi, mounted in drillhead power supply chassis. Redundant (2 per chassis). 1 set in each TOS. Rasp Pi $335/ea x (2*2 + 2 spares) = $2010. Cabling and connectors ~$500. Total = $2510. Click here for RaspPi quote. | 60 |  |  |  | 60 | 6900 | expert opinion | 9410 |  |  |  |  | 1.46 | 4000 | 4140 | 8140 | 1270
1.2.4.8.4.2 |  | Develop Linux SW Functionality | [19 empty] | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0 | 0
1.2.4.8.4.2.1 | 5 | Port C-Lang ingest process to rPI platform & test | [9 empty] | x |  |  |  | D |  | 32 |  |  |  | 32 | 3680 | expert opinion | 3680 |  |  |  |  | 0.57095 |  | 3680 | 3680 | 0
1.2.4.8.4.2.2 | 5 | Integrate rPI platform into PLC infrastructure | [9 empty] | x |  |  |  | D |  | 40 |  |  |  | 40 | 4600 | expert opinion | 4600 |  |  |  |  | 0.71369 |  | 4140 | 4140 | 460
1.2.4.8.4.2.3 | 5 | Document Subsystem | [9 empty] | x |  |  |  | D |  | 40 |  |  |  | 40 | 4600 | expert opinion | 4600 |  |  |  |  | 0.71369 |  | 4140 | 4140 | 460
[33 empty] | 0 | 0
1.2.4.8.5 |  | CS DCC, WT1, and Fuel Daytank | [19 empty] | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0 | 0
1.2.4.8.5.1 | 5 | Design, construct and test master E-stop controller, produce documentation and user instructions | [6 empty] | 3000 |  |  | x |  |  |  | D | Circuit boards, industrial switches, MS connectors, enclosures. This is first article (design duplicated for TOS controllers). Est. | 160 |  | 40 |  | 200 | 21480 | expert opinion | 24480 |  |  |  |  | 3.798 | 3000 | 19332 | 22332 | 2148
1.2.4.8.5.2 | 5 | Design and construct general-purpose I/O box for fuel sled, gather required component stock to install | [6 empty] | 3850 |  |  | x |  |  |  | C | remote i/o without PLC, see breakdown below. | 80 |  |  |  | 80 | 9200 | expert opinion | 13050 |  |  |  |  | 2.0247 | 2000 | 8280 | 10280 | 2770
1.2.4.8.5.3 |  | Procure 20 kW three-phase heater for DCC and 208V breakers | [6 empty] | 3152 |  | x |  |  |  |  | C | heater + spare 2 x $1576 = $3152 This link points to heater quote |  |  | 16 |  | 16 | 1232 | expert opinion | 4384 |  |  |  |  | 0.68017 | 3000 | 1232 | 4232 | 152
1.2.4.8.5.4 | 5 | WT1 VT pump drives: procure, configure, rewire plan | [6 empty] | 5083 |  | x |  |  |  |  | C | 15 hp drives: 2 @ ($2166 + $75.61frame) = $4483 plus $600 for pigtail and connectors config Total = $5083 This link points to AB motor drive quote, see second item from top, 4198292 | 16 |  |  |  | 16 | 1840 | expert opinion | 6923 |  |  |  |  | 1.0741 | 6000 | 1840 | 7840 | -917
1.2.4.8.5.5 | 5 | WT1 VT pump drives: final configure | [9 empty] | x |  |  |  | D |  | 60 |  |  |  | 60 | 6900 | expert opinion | 6900 |  |  |  |  | 1.0705 |  | 6210 | 6210 | 690
1.2.4.8.5.6 | 5 | WT1 VT pump drives: install plan and kit | [6 empty] | 1500 |  |  | x |  |  |  | D | est. for hardware needed for VFD installation kits. This are new install locations, not existing. Material and hardware. 2x drives to install. | 60 |  |  |  | 60 | 6900 | expert opinion | 8400 |  |  |  |  | 1.3033 | 2500 | 6210 | 8710 | -310
1.2.4.8.5.7 |  | Develop PLC-Fuel DayTank SW Functionality | [19 empty] | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0 | 0
1.2.4.8.5.7.1 | 5 | Develop fuel system sensor readout ; (multi-level tank status, control relay status ) | [9 empty] | x |  |  |  | D |  | 36 |  |  |  | 36 | 4140 | expert opinion | 4140 |  |  |  |  | 0.64232 |  | 4140 | 4140 | 0
1.2.4.8.5.7.2 | 5 | Configure/document Point I/O Block | [9 empty] | x |  |  |  | D |  | 16 |  |  |  | 16 | 1840 | expert opinion | 1840 |  |  |  |  | 0.28547 |  | 1840 | 1840 | 0
1.2.4.8.5.7.3 | 5 | Document Subsystem | [9 empty] | x |  |  |  | D |  | 36 |  |  |  | 36 | 4140 | expert opinion | 4140 |  |  |  |  | 0.64232 |  | 4140 | 4140 | 0
1.2.4.8.5.7.4 | 5 | Implement interlocks | [9 empty] | x |  |  |  | D |  | 20 |  |  |  | 20 | 2300 | expert opinion | 2300 |  |  |  |  | 0.35684 |  | 2300 | 2300 | 0
[33 empty] | 0 | 0
1.2.4.8.6 |  | CS Gensets | [19 empty] | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0 | 0
1.2.4.8.6.1 | 5 | CS Gensets HW - identify, procure, assemble | [6 empty] | 3850 |  |  | x |  |  |  | C | remote i/o without PLC, see breakdown below. | 40 |  | 40 |  | 80 | 7680 | expert opinion | 11530 |  |  |  |  | 1.7889 | 4000 | 6912 | 10912 | 618
1.2.4.8.6.2 |  | Develop PLC-Gens MDSs SW Functionality | [19 empty] | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0 | 0
1.2.4.8.6.2.1 | 5 | Develop sensor readout; (bldg temps, fuel temps, supply/return water temps) | [9 empty] | x |  |  |  | D |  | 40 |  |  |  | 40 | 4600 | expert opinion | 4600 |  |  |  |  | 0.71369 |  | 3680 | 3680 | 920
1.2.4.8.6.2.2 | 5 | Develop sensor readout; (engine jacket temps, exhaust temps, drip pan status) | [9 empty] | x |  |  |  | D |  | 40 |  |  |  | 40 | 4600 | expert opinion | 4600 |  |  |  |  | 0.71369 |  | 3680 | 3680 | 920
1.2.4.8.6.2.3 | 5 | Configure/document network switch | [9 empty] | x |  |  |  | D |  | 8 |  |  |  | 8 | 920 | expert opinion | 920 |  |  |  |  | 0.14274 |  | 920 | 920 | 0
1.2.4.8.6.2.4 | 5 | Configure/document RTA gateway to M-DGH interface | [9 empty] | x |  |  |  | D |  | 10 |  |  |  | 10 | 1150 | expert opinion | 1150 |  |  |  |  | 0.17842 |  | 1150 | 1150 | 0
1.2.4.8.6.2.5 | 5 | Configure/document M-DGHs | [9 empty] | x |  |  |  | D |  | 20 |  |  |  | 20 | 2300 | expert opinion | 2300 |  |  |  |  | 0.35684 |  | 2300 | 2300 | 0
1.2.4.8.6.2.6 | 5 | Document Subsystem | [9 empty] | x |  |  |  | D |  | 40 |  |  |  | 40 | 4600 | expert opinion | 4600 |  |  |  |  | 0.71369 |  | 4140 | 4140 | 460
[33 empty] | 0 | 0
1.2.4.8.7 |  | CS HPP | [19 empty] | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0 | 0
1.2.4.8.7.1 |  | CS HPP HW1: Motor Drive Config & Install Kits | [19 empty] | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0 | 0
1.2.4.8.7.1.1 | 4 | Procure HPP motor drives (four PF-755 50 hp vfds) (8 hours, task is finished) | [8 empty] | x |  |  |  |  | D | [5 empty] | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0 | 0
1.2.4.8.7.1.2 | 4 | Configure four HPP VFDs with accessories, connection pigtails, document | [9 empty] | x |  |  |  | D | [5 empty] | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0 | 0
1.2.4.8.7.1.3 | 5 | Develop VFD mechanical and electrical installation strategies & document, procure materials | [6 empty] | 1000 |  |  | x |  |  |  | D | est. for hardware needed for VFD installation kits. Use existing mounting locations but adapt for new form factor. Material and hardware. 4x drives to install. | 72 |  |  |  | 72 | 8280 | expert opinion | 9280 |  |  |  |  | 1.4398 | 16 | 8280 | 8296 | 984
1.2.4.8.7.1.4 | 4 | SW configuration and autotuning | [9 empty] | x |  |  |  | D | [5 empty] | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0 | 0
1.2.4.8.7.2 |  | CS HPP HW2: Signal and Readout Definition, Procedures | [19 empty] | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0 | 0
1.2.4.8.7.2.1 | 5 | Define requirements and procedures for reading signals applied to HPP motor drives | [9 empty] | x |  |  |  | D |  | 16 |  |  |  | 16 | 1840 | expert opinion | 1840 |  |  |  |  | 0.28547 |  | 1840 | 1840 | 0
1.2.4.8.7.2.2 | 5 | Define method of verifying sensor readout accuracy (reading vs stimulus) | [9 empty] | x |  |  |  | D |  | 16 |  |  |  | 16 | 1840 | expert opinion | 1840 |  |  |  |  | 0.28547 |  | 1840 | 1840 | 0
1.2.4.8.7.2.3 | 5 | Develop and document test procedures for on-ice personnel | [9 empty] | x |  |  |  | D |  | 16 |  |  |  | 16 | 1840 | expert opinion | 1840 |  |  |  |  | 0.28547 |  | 1840 | 1840 | 0
1.2.4.8.7.3 |  | CS HPP HW3: PLC Hardware, Box Build, Testing | [19 empty] | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0 | 0
1.2.4.8.7.3.1 | 5 | Define core HPP PLC functions and requirements, define needed I/O connections | [9 empty] | x |  |  |  | D |  | 40 |  |  |  | 40 | 4600 | expert opinion | 4600 |  |  |  |  | 0.71369 |  | 4140 | 4140 | 460
1.2.4.8.7.3.2 | 5 | Select PLC, Enclosure, Power supplies, I/O expansion cards, power distribution, connectors and cables | [9 empty] | x |  |  |  | D |  | 40 |  |  |  | 40 | 4600 | expert opinion | 4600 |  |  |  |  | 0.71369 |  | 4140 | 4140 | 460
1.2.4.8.7.3.3 | 5 | Design and Construct PLC enclosure | [6 empty] | 7050 |  |  | x |  |  |  | C | remote i/o WITH PLC, see breakdown below. | 32 |  | 40 |  | 72 | 6760 | expert opinion | 13810 |  |  |  |  | 2.1426 | 4000 | 5528 | 9528 | 4282
1.2.4.8.7.3.4 | 5 | Test HPP PLC enclosure with HPP Network box | [9 empty] | x |  |  |  | D |  | 24 |  |  |  | 24 | 2760 | expert opinion | 2760 |  |  |  |  | 0.42821 |  | 2760 | 2760 | 0
1.2.4.8.7.4 |  | CS HPP HW4: Charge Pump Motor Controllers | [19 empty] | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0 | 0
1.2.4.8.7.4.1 | 4 | Install PF-70 motor drive in test bed, configure with local control system, test | [9 empty] | x |  |  |  | D | [5 empty] | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0 | 0
1.2.4.8.7.4.2 | 5 | Procure additional drives for charge pumps (4), AC and network pigtail materials | [6 empty] | 14505 |  | x |  |  |  |  | C | AB PF70 drives, $2601/ea x 5 (incl 1x spare) = $13005. AC and network pigtail materials est. $300/drive -> 5x300 = $1500 Total = $14505 This link points to PF70 quote | 16 |  |  |  | 16 | 1840 | expert opinion | 16345 |  |  |  |  | 2.5359 | 12000 | 1840 | 13840 | 2505
1.2.4.8.7.4.3 | 5 | Connectorize four drives with power and network pigtails, test each in test bed |  |  | 0 |  |  |  | 1000 |  |  | x |  |  |  | D | Materials to accomodate this testing in the testBed, mech and elec. Est. | 24 |  | 40 |  | 64 | 5840 | expert opinion | 6840 |  |  |  |  | 1.0612 | 1000 | 5224 | 6224 | 616
1.2.4.8.7.5 |  | CS HPP HW5: Sensor Box Reconfig & Test |  |  | 0 | [16 empty] | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0 | 0
1.2.4.8.7.5.1 | 4 | Build and test a portable network box for sensor box testing (Gateway, power supply, connectors) |  |  | 0 | [6 empty] | x |  |  |  | D | [5 empty] | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0 | 0
1.2.4.8.7.5.2 | 4 | Procure and configure test equipment needed to calibrate individual sensors, provide user instructions |  |  | 0 | [6 empty] | x |  |  |  | D | [5 empty] | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0 | 0
1.2.4.8.7.5.3 | 4 | Connect HPP sensor readout box with sensor box, connect to network box, test all sensors and document |  |  | 0 | [6 empty] | x |  |  |  | D | [5 empty] | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0 | 0
1.2.4.8.7.6 | 4 | CS HPP HW6: Sensor Box DGH Reconfig & Test |  |  | 0 | [6 empty] | x |  |  |  | D | [5 empty] | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0 | 0
1.2.4.8.7.7 |  | CS HPP HW7: Estop box Re-outfitting |  |  | 0 | [16 empty] | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0 | 0
1.2.4.8.7.7.1 | 5 | Select and procure E-stop relays for pump VFD Enable signals |  |  | 0 |  |  |  | 200 |  |  | x |  |  |  | D | est. | 8 |  |  |  | 8 | 920 | expert opinion | 1120 |  |  |  |  | 0.17377 | 200 | 920 | 1120 | 0
1.2.4.8.7.7.2 | 5 | Develop and document rewiring instructions for HPP E-stop box |  |  | 0 | [6 empty] | x |  |  |  | D |  | 16 |  |  |  | 16 | 1840 | expert opinion | 1840 |  |  |  |  | 0.28547 |  | 1840 | 1840 | 0
1.2.4.8.7.8 |  | CS HPP HW8: Network Box Refurb & Config |  |  | 0 | [16 empty] | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0 | 0
1.2.4.8.7.8.1 | 4 | Select and procure a wall-mount managed Ethernet switch for the HPP electrical closet |  |  | 0 | [6 empty] | x |  |  |  | D | [5 empty] | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0 | 0
1.2.4.8.7.8.2 | 4 | Select and procure new power supplies for the network box, procure one RS-485 gateway |  |  | 0 | [6 empty] | x |  |  |  | D | [5 empty] | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0 | 0
1.2.4.8.7.8.3 | 4 | Refurbish the HPP network box, document as-built configureation |  |  | 0 | [6 empty] | x |  |  |  | D | [5 empty] | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0 | 0
1.2.4.8.7.8.4 | 4 | Select and procure HPP network switch enclosure, integrate with switch |  |  | 0 | [6 empty] | x |  |  |  | D | [5 empty] | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0 | 0
1.2.4.8.7.9 |  | CS HPP HW9-10: Maintain Documentation, Prepare Field Plans |  |  | 0 | [16 empty] | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0 | 0
1.2.4.8.7.9.1 | 5 | Develop and document test plans for all HPP system components |  |  | 0 | [6 empty] | x |  |  |  | D |  | 36 |  |  |  | 36 | 4140 | expert opinion | 4140 |  |  |  |  | 0.64232 |  | 4140 | 4140 | 0
1.2.4.8.7.9.2 | 5 | Review Gen-1 docs, identify where sensor connections terminated, plan for field integration and test |  |  | 0 | [6 empty] | x |  |  |  | D |  | 32 |  |  |  | 32 | 3680 | expert opinion | 3680 |  |  |  |  | 0.57095 |  | 3680 | 3680 | 0
1.2.4.8.7.10 |  | Develop Local HPP PLC SW Functionality |  |  | 0 | [16 empty] | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0 | 0
1.2.4.8.7.10.1 | 5 | Develop water path sensor readout; (pressure, temp, flow) |  |  | 0 | [6 empty] | x |  |  |  | D |  | 40 |  |  |  | 40 | 4600 | expert opinion | 4600 |  |  |  |  | 0.71369 |  | 4140 | 4140 | 460
1.2.4.8.7.10.2 | 5 | Develop environmental sensor readout; (bldg temps, smoke, e-stop) |  |  | 0 | [6 empty] | x |  |  |  | D |  | 40 |  |  |  | 40 | 4600 | expert opinion | 4600 |  |  |  |  | 0.71369 |  | 4140 | 4140 | 460
1.2.4.8.7.10.3 | 4 | Build shared data-tagging w/ DCC core controller |  |  | 0 | [6 empty] | x |  |  |  | D | [5 empty] | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0 | 0
1.2.4.8.7.10.4 | 4 | Develop AB drive/pump control; (variable speed velocity drives) |  |  | 0 | [6 empty] | x |  |  |  | D | [5 empty] | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0 | 0
1.2.4.8.7.10.5 | 4 | Develop charge pump control; (variable speed velocity drives OR Soft Starter) |  |  | 0 | [6 empty] | x |  |  |  | D | [5 empty] | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0 | 0
1.2.4.8.7.10.6 | 4 | Configure/document network switch |  |  | 0 | [6 empty] | x |  |  |  | D | [5 empty] | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0 | 0
1.2.4.8.7.10.7 | 4 | Configure/document RTA gateway to M-DGH interface |  |  | 0 | [6 empty] | x |  |  |  | D | [5 empty] | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0 | 0
1.2.4.8.7.10.8 | 4 | Configure/document M-DGHs |  |  | 0 | [6 empty] | x |  |  |  | D | [5 empty] | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0 | 0
1.2.4.8.7.10.9 | 5 | Implement interlocks |  |  | 0 | [6 empty] | x |  |  |  | D |  | 20 |  |  |  | 20 | 2300 | expert opinion | 2300 |  |  |  |  | 0.35684 |  | 2300 | 2300 | 0
1.2.4.8.7.10.10 | 5 | Document Subsystem |  |  | 0 | [6 empty] | x |  |  |  | D |  | 40 |  |  |  | 40 | 4600 | expert opinion | 4600 |  |  |  |  | 0.71369 |  | 4140 | 4140 | 460
[33 empty] | 0 | 0
1.2.4.8.8 |  | CS ARA Rodwell System |  |  | 0 | [16 empty] | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0 | 0
1.2.4.8.8.1 |  | CS ARA Rodwell System |  |  | 0 | [16 empty] | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0 | 0
1.2.4.8.8.1.1 | 4 | CS ARA HW: new system controls and tie-in | [19 empty] | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0 | 0
1.2.4.8.8.1.2 | 4 | Review ARA drill system documentation and develop a new configuration for Rodewell | [19 empty] | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0 | 0
1.2.4.8.8.1.3 | 4 | Select and procure new motor drives for Rodwell pump and combo-cable winch | [19 empty] | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0 | 0
1.2.4.8.8.1.4 | 4 | Procure gateway for monitoring control pane instruments, plan for installation in the control box | [19 empty] | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0 | 0
1.2.4.8.8.1.5 | 4 | Select and procure new hardware to capture flow sensor pulse rates (A-B I/O hardware) | [19 empty] | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0 | 0
1.2.4.8.8.1.6 | 4 | Design and Build network cable, E-stop cable, for connecting rodwell system to drill system | [19 empty] | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0 | 0
1.2.4.8.8.2 |  | Develop PLC-Rodwell SW Functionality | [19 empty] | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0 | 0
1.2.4.8.8.2.1 | 5 | Develop ARA-drill sensor readout; (heater flows, head press, tank level) |  |  | 0 | [6 empty] | x |  |  |  | D |  | 80 |  |  |  | 80 | 9200 | expert opinion | 9200 |  |  |  |  | 1.4274 |  | 8280 | 8280 | 920
1.2.4.8.8.2.2 | 5 | Develop AB drive/pump control; (variable speed velocity drives) |  |  | 0 | [6 empty] | x |  |  |  | D |  | 40 |  |  |  | 40 | 4600 | expert opinion | 4600 |  |  |  |  | 0.71369 |  | 4140 | 4140 | 460
1.2.4.8.8.2.3 | 5 | Configure/document Point I/O Block |  |  | 0 | [6 empty] | x |  |  |  | D |  | 16 |  |  |  | 16 | 1840 | expert opinion | 1840 |  |  |  |  | 0.28547 |  | 1840 | 1840 | 0
1.2.4.8.8.2.4 | 5 | Configure/document network switch |  |  | 0 | [6 empty] | x |  |  |  | D |  | 8 |  |  |  | 8 | 920 | expert opinion | 920 |  |  |  |  | 0.14274 |  | 920 | 920 | 0
1.2.4.8.8.2.5 | 5 | Configure/document RTA gateway to M-DGH interface |  |  | 0 | [6 empty] | x |  |  |  | D |  | 16 |  |  |  | 16 | 1840 | expert opinion | 1840 |  |  |  |  | 0.28547 |  | 1840 | 1840 | 0
1.2.4.8.8.2.6 | 5 | Configure/document M-DGHs | [9 empty] | x |  |  |  | D |  | 20 |  |  |  | 20 | 2300 | expert opinion | 2300 |  |  |  |  | 0.35684 |  | 2300 | 2300 | 0
1.2.4.8.8.2.7 | 5 | Implement interlocks | [9 empty] | x |  |  |  | D |  | 20 |  |  |  | 20 | 2300 | expert opinion | 2300 |  |  |  |  | 0.35684 |  | 2300 | 2300 | 0
1.2.4.8.8.2.8 | 5 | Document Subsystem | [9 empty] | x |  |  |  | D |  | 40 |  |  |  | 40 | 4600 | expert opinion | 4600 |  |  |  |  | 0.71369 |  | 4140 | 4140 | 460
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0 | 0
0
[9 empty] | 82696 | Total Expected Materials Cost | [7 empty] | 4438 | 0 | 788 | 0 | 5226 | 571046 | Total Hours Cost | 644542
Schedule Logic Terms that can be used:
FS = Finish-to-Start
[10 empty] | REMOTE I/O KIT (for est.) |  | This is a representative kit, design is still underway | [14 empty] | SS = Start-Start
[13 empty] | w/ remote PLC | w/o remote PLC | [12 empty] | FF = Finish-Finsh
[10 empty] | Item | Qty | $/ea | subtotal | subtotal | reference | [11 empty] | SF = Start-to-Finish
[10 empty] | Compact Logix PLC | 1 | 3200 | 3200 |  | link - see last line item
[10 empty] | I/O blocks | 3 | 350 | 1050 | 1050 | link - ~ave of discrete and analog i/o modules
[10 empty] | Ethernet IP | 1 | 2100 | 2100 | 2100 | est.
[10 empty] | Power | 1 | 200 | 200 | 200 | est.
[10 empty] | Enclosure | 1 | 500 | 500 | 500 | est.
[13 empty] | 7050 | 3850 | TOTAL