## 1.2.3 TOS
Upgrade Cost Estimate
Name: | 1.2.3 TOS
Parent WBS: | 1.2 Implementation |  | MATERIALS ESTIMATE | [14 empty] | LABOR ESTIMATE | [6 empty] | TOTAL | SCHEDULE INPUT
Description of Scope: | [30 empty] | Mat'l
Initials/Date: |  |  | Quantities | [6 empty] | Basis of Estimate (Select One, See Table Below) | [7 empty] | HOURS | [8 empty] | SCHEDULE LOGIC |  |  |  | 63.5933 | 36.4067 | %
[31 empty] | 36964.59 | 21162
WBS (if known) | Project Year (0-10) | Description | QTY | Spare | Total | Fabricate or Procure? | Procurement Details Manufacturer, Model, P/N, Vendor | Unit Price | Total Expected Price | C1 LOE Tasks | C2 Advanced | C3 Preliminary | C4 Conceptual | C5 Pre- Conceptual | C6 Rough Estimate | Cost Estimating Technique (See Table Below) | Materials Comments/Notes (procurement lead time, shipping restrictions, etc) | ENGR ($115/hr) | CAD ($81/hr) | SHOP ($77/hr) | STUDENT ($15/hr) | Total Hours | Total Hours Cost | Labor Comments/Schedule Inputs (eg. "March" or "After Microturbine running", etc) |  | Duration (Weeks) | Predecessors | Successors | Milestone | % of total | quote | est | orig mat'l | orig labor | orig tot | delta | -8642.61
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0 |  |  |  |  | 0
1.2.3.1 |  | TOS and Tower |  |  | 0 | [16 empty] | 0 | 0 |  | 0 |  |  |  |  | 0
1.2.3.1.5 | 6 | Crescent Emergency Repair Kit Assembly (PY6) |  |  | 0 |  |  |  | 2500 |  |  | X |  |  |  | D | expert opinion. Linkage hardware to splice crescent belt together in-situ | 40 |  |  |  | 40 | 4600 | expert opinion | 7100 |  |  |  |  | 5.6013 |  | 2500
1.2.3.1.6 | 5 | Examine Interface between Dust Logger and Tower & Address as Needed |  |  | 0 |  |  |  | 2400 |  |  |  | X |  |  | D | expert opinion. may require additional sheave(s), rigging, and/or anchoring to route logger cable | 40 |  |  |  | 40 | 4600 | expert opinion | 7000 |  |  |  |  | 5.5224 |  | 2400 | 2400 | 4370 | 6770 | 230
1.2.3.1.7 |  | TOS Load Cells & Encoders |  |  | 0 | [16 empty] | 0 | 0 |  | 0 |  |  |  |  | 0
1.2.3.1.7.2 | 5 | Calibration Load Cell |  |  | 0 |  | MSI MSI-7300-10000 |  | 1789.08 |  | X |  |  |  |  | C | Calibration load cell | 8 |  |  |  | 8 | 920 | expert opinion | 2709.08 |  |  |  |  | 2.1373 | 1789.08 |  | 2500 | 920 | 3420 | -710.92
1.2.3.1.7.3 | 5 | Calibration Load Cell Rigging |  |  | 0 |  | 3x chains, 2x rigging links, 2 shackles |  | 1219.51 |  | X |  |  |  |  | C | see 1.2.3 ChainWithHooks, MasterLink, Shackle_CROSBY here | 8 |  |  |  | 8 | 920 | expert opinion | 2139.51 |  |  |  |  | 1.6879 | 1219.51 |  | 1500 | 920 | 2420 | -280.49
1.2.3.1.8 | 5 | Identify/Procure: TOS & Tower Hardware, Repair Parts (PY5) |  |  | 0 |  |  |  | 10232 |  |  | X |  |  |  | C | Includes: 4 cases (120 rolls) of driller tape x $43.60/roll = $5232 Restock (rigging, tools, etc.) est. ~$5000 Total = $10,232 | 32 |  |  |  | 32 | 3680 | expert opinion | 13912 |  |  |  |  | 10.9755 | 5232 | 5000 | 11000 | 5520 | 16520 | -2608
1.2.3.1.9 | 6 | Identify/Procure: TOS & Tower Hardware, Repair Parts (PY6) |  |  | 0 |  |  |  | 9232 |  |  | X |  |  |  | C | Includes: 4 cases (120 rolls) of driller tape x $43.60/roll = $5232 Restock (rigging, tools, etc.) est. ~$4000 Total = $9,232 | 32 |  |  |  | 32 | 3680 | expert opinion | 12912 |  |  |  |  | 10.1865 | 5232 | 4000 | 11000 | 5520 | 16520 | -3608
1.2.3.1.10 | 7 | Identify/Procure: TOS & Tower Hardware, Repair Parts (PY7) |  |  | 0 |  |  |  | 22992 |  |  | X |  |  |  | C | Includes: Driller tape, 50 rolls/hole x 7 holes = 350 rolls. Plus 4 cases (120 rolls) 470 rolls x $43.60/roll = $20492 Restock (rigging, tools, etc.) est. ~$2500 Total = $22,992 | 32 |  |  |  | 32 | 3680 | expert opinion | 26672 |  |  |  |  | 21.0421 | 20492 | 2500 | 27000 | 5520 | 32520 | -5848
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0 |  |  |  |  | 0
1.2.3.2 |  | Drillheads |  |  | 0 | [16 empty] | 0 | 0 |  | 0 |  |  |  |  | 0
1.2.3.2.10 | 5 | Drillheads: Prepare Crates, Spares, Tools, & Docs x3 |  |  | 0 | [6 empty] | X |  |  |  | D |  | 24 |  | 24 |  | 48 | 4608 | expert opinion | 4608 |  |  |  |  | 3.6353
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0 |  |  |  |  | 0
1.2.3.3 |  | Reels & Winches |  |  | 0 | [16 empty] | 0 | 0 |  | 0 |  |  |  |  | 0
1.2.3.3.7 | 4 | Main Drill Cable Reel/Main Hose Reel Load Sharing (PY4) PY4 task, not captured here |  |  | 0 | [16 empty] | 0 | 0 |  | 0 |  |  |  |  | 0
1.2.3.3.7.5 | 5 | Load Sharing: Full-scale Testing - Load Share & Tuning (PY5) Placeholder, no resources |  |  | 0 | [12 empty] | 0 |  |  |  | 0 | 0 |  | 0 |  |  |  |  | 0
1.2.3.3.9 | 5 | Reels & Winches: Drill Reels Sliprings - Final Testing & Prep |  |  | 0 | [6 empty] | X |  |  |  | D |  | 16 |  |  |  | 16 | 1840 | expert opinion | 1840 |  |  |  |  | 1.4516
1.2.3.3.10 | 5 | Reels & Winches: TU20 Sliprings - Spec, Procure, Test |  |  | 0 |  |  |  | 8412.8 |  |  | X |  |  |  | C | 2x slipring assemblies are requiredUsing MDCR slipring as reference ($2672/ea), + 20% for increased size/channelsAlso add $1000/assem for connectors and interface hardware | 160 |  |  |  | 160 | 18400 | expert opinion. Engineering to define requirements, spec, procure, design interface. Wire and test, interface hardware. | 26812.8 |  |  |  |  | 21.1532 | 1000 | 2672 | 8000 | 18400 | 26400 | 412.8
1.2.3.3.11 | 6 | Reels & Winches: Reel Components & Spares (PY6). TU20 brakes |  |  | 0 |  |  |  | 8770 |  |  | X |  |  |  | C | 3x My-Tee capstan winches @ $2090/ea (2x TOSes plus spare) Also add $2500 for backup hand drill chucks and drill (RWCR & RWHR), and electronic parts for TU20 brake controllers | 80 |  | 40 |  | 120 | 12280 | expert opinion. Procurements, wiring, and tech hardware build | 21050 |  |  |  |  | 16.6068 | 2000 | 2090 | 5000 | 12280 | 17280 | 3770
0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0 |  |  |  |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0 |  |  |  |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0 |  |  |  |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0 |  |  |  |  | 0
[9 empty] | 67547.39 | Total Expected Materials Cost | [7 empty] | 472 | 0 | 64 | 0 | 536 | 46928 | Total Hours Cost | 126755.39
Schedule Logic Terms that can be used:
FS = Finish-to-Start
SS = Start-Start
FF = Finish-Finsh
SF = Start-to-Finish