## 1.2.9.1.3.3
Upgrade Cost Estimate
Name: | 1.2.9.1.3.3 Off-Ice Install: Procure ESD Sensor Handling Equipment
Parent WBS: | 1.2.9 Installation off-ice |  | MATERIALS ESTIMATE | [15 empty] | LABOR ESTIMATE | [6 empty] | TOTAL | SCHEDULE INPUT
Description of Scope: | ESD Protection for Safe Sensor Handling
Initials/Date: | DT 3/9/2022 |  | Quantities | [6 empty] | Basis of Estimate (Select One, See Table Below) | [8 empty] | HOURS | [8 empty] | SCHEDULE LOGIC
WBS (if known) | Project Year (0-10) | Description | QTY | Spare | Total | Fabricate or Procure? | Procurement Details Manufacturer, Model, P/N, Vendor | Unit Price | Total Expected Price | C2 LOE Tasks | C3 Advanced | C4 Preliminary | C5 Conceptual | C6 Pre- Conceptual | C7 Rough Estimate | C8 Beyond SOTA | Cost Estimating Technique (See Table Below) | Materials Comments/Notes (procurement lead time, shipping restrictions, etc) | ENGR ($115/hr) | CAD ($81/hr) | SHOP ($77/hr) | STUDENT ($15/hr) | Total Hours | Total Hours Cost | Labor Comments/Schedule Inputs (eg. "March" or "After Microturbine running", etc) |  | Duration (Weeks) | Predecessors | Successors | Milestone
1.2.9.1.3.3 |  | lab coats (average price, depends on size and quantities) | 12 | 2 | 14 | Procure | https://www.correctproducts.com/371acb-tech-wear-blue-esd-jackets?quantity=1&custcol2=7 | 50 | 700 |  |  | C4 Preliminary |  |  |  |  | D-Expert Opinion | [5 empty] | 0 | 0 |  | 700
1.2.9.1.3.3 |  | ESD mat for SPAT area | 2 | 0 | 2 | Procure | https://www.correctproducts.com/transforming-technologies-fm73648-esd-conductive-chair-floor-mat | 167.15 | 334.3 |  |  | C4 Preliminary |  |  |  |  | D-Expert Opinion | [5 empty] | 0 | 0 |  | 334.3
1.2.9.1.3.3 |  | ESD gloves, 1 box each size | 6 | 0 | 6 | Procure | https://www.correctproducts.com/gl4500p-palm-coated-esd-inspection-gloves | 34.82 | 208.92 |  |  | C4 Preliminary |  |  |  |  | D-Expert Opinion | [5 empty] | 0 | 0 |  | 208.92
1.2.9.1.3.3 |  | ESD grounding | 3 | 0 | 3 | Procure | https://www.correctproducts.com/3m-low-profile-ground-cord | 17.46 | 52.38 |  |  | C4 Preliminary |  |  |  |  | D-Expert Opinion | [5 empty] | 0 | 0 |  | 52.38
1.2.9.1.3.3 |  | ionizing gun - more research needs to be done on the topic to verify how effective one of these would be at zero humidity (many models available) | 3 | 0 | 3 | Procure | https://www.correctproducts.com/esd-cleanroom-products/esd-ionizers/esd-ionizing-guns-nozzles | 1200 | 3600 |  |  | C4 Preliminary |  |  |  |  | D-Expert Opinion | [5 empty] | 0 | 0 |  | 3600
1.2.9.1.3.3 |  | wrist straps | 6 | 3 | 9 | Procure | https://www.correctproducts.com/esd-cleanroom-products/esd-personal-protection/esd-wrist-straps/dual-conductor-wrist-straps | 34 | 306 |  |  | C4 Preliminary |  |  |  |  | D-Expert Opinion | [5 empty] | 0 | 0 |  | 306
1.2.9.1.3.3 |  | wrist strap connectors 10-20ft | 6 | 2 | 8 | Procure | https://www.correctproducts.com/esd-cleanroom-products/esd-personal-protection/esd-wrist-straps/dual-conductor-wrist-straps | 35 | 280 |  |  | C4 Preliminary |  |  |  |  | D-Expert Opinion | [5 empty] | 0 | 0 |  | 280
1.2.9.1.3.3 |  | grounding plug in for wrist straps | 6 | 0 | 6 | Procure | https://www.correctproducts.com/bench-mount-ground | 11.18 | 67.08 |  |  | C4 Preliminary |  |  |  |  | D-Expert Opinion | [5 empty] | 0 | 0 |  | 67.08
[5 empty] | 0 |  |  |  | 0 | [13 empty] | 0 | 0 |  | 0
[5 empty] | 0 |  |  |  | 0 | [13 empty] | 0 | 0 |  | 0
[5 empty] | 0 |  |  |  | 0 | [13 empty] | 0 | 0 |  | 0
[5 empty] | 0 |  |  |  | 0 | [13 empty] | 0 | 0 |  | 0
[5 empty] | 0 |  |  |  | 0 | [13 empty] | 0 | 0 |  | 0
[5 empty] | 0 |  |  |  | 0 | [13 empty] | 0 | 0 |  | 0
[5 empty] | 0 |  |  |  | 0 | [13 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [17 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [17 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [17 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [17 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [17 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [17 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [17 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [17 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [17 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [17 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [17 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [17 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [17 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [17 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [17 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [17 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [17 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [17 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [17 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [17 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [17 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [17 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [17 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [17 empty] | 0 | 0 |  | 0
[9 empty] | 5548.68 | Total Expected Materials Cost | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | Total Hours Cost | 5548.68
Schedule Logic Terms that can be used:
FS = Finish-to-Start
SS = Start-Start
FF = Finish-Finsh
SF = Start-to-Finish

## 1.2.9.2.8
Upgrade Cost Estimate
Name: | 1.2.9.2.8 Installation Hardware
Parent WBS: | 1.2.9 Installation off-ice |  | MATERIALS ESTIMATE | [15 empty] | LABOR ESTIMATE | [6 empty] | TOTAL | SCHEDULE INPUT
Description of Scope: | hardware for installation
Initials/Date: | D.T. 03/22/2022 |  | Quantities | [6 empty] | Basis of Estimate (Select One, See Table Below) | [8 empty] | HOURS | [8 empty] | SCHEDULE LOGIC
WBS (if known) | Project Year (0-10) | Description | QTY | Spare | Total | Fabricate or Procure? | Procurement Details Manufacturer, Model, P/N, Vendor | Unit Price | Total Expected Price | C2 LOE Tasks | C3 Advanced | C4 Preliminary | C5 Conceptual | C6 Pre- Conceptual | C7 Rough Estimate | C8 Beyond SOTA | Cost Estimating Technique (See Table Below) | Materials Comments/Notes (procurement lead time, shipping restrictions, etc) | ENGR ($115/hr) | CAD ($81/hr) | SHOP ($77/hr) | STUDENT ($15/hr) | Total Hours | Total Hours Cost | Labor Comments/Schedule Inputs (eg. "March" or "After Microturbine running", etc) |  | Duration (Weeks) | Predecessors | Successors | Milestone
1.2.9.2.8 | PY5 | Shalllow region installation kit | 127 | 1 | 128 | Procure | See Installation Kits CMD for part number list | 114.3 | 14630.4 |  |  | C4 Preliminary |  |  |  |  | C | Cheaper, lighter alternatives are being considered |  |  |  |  | 0 | 0 |  | 14630.4
| PY5 | Physics region DOM 2-5 installation kit | 420 | 1 | 421 | Procure | See Installation Kits CMD for part number list | 49.64 | 20898.44 |  |  | C4 Preliminary |  |  |  |  | C | [5 empty] | 0 | 0 |  | 20898.44
| PY5 | Physics region DOM 1 installation kit | 105 | 1 | 106 | Procure | See Installation Kits CMD for part number list | 85.35 | 9047.1 |  |  | C4 Preliminary |  |  |  |  | C | [5 empty] | 0 | 0 |  | 9047.1
| PY5 | Physics region DOM 6 installation kit | 105 | 1 | 106 | Procure | See Installation Kits CMD for part number list | 82.58 | 8753.48 |  |  | C4 Preliminary |  |  |  |  | C | [5 empty] | 0 | 0 |  | 8753.48
| PY5 | Add-on Weight (Physics Region DOM 5) | 63 | 0 | 63 | Fabricate | weights available at Pole, finalize design to determine if appropriate | 558 | 35154 |  |  | C4 Preliminary |  |  |  |  | C |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 35154
| PY5 | Deep region short strings installation kit | 24 | 1 | 25 | Procure | See Installation Kits CMD for part number list | 58.81 | 1470.25 |  |  | C4 Preliminary |  |  |  |  | C | [5 empty] | 0 | 0 |  | 1470.25
| PY5 | Deep region long strings installation kit | 15 | 1 | 16 | Procure | See Installation Kits CMD for part number list | 27.15 | 434.4 |  |  | C4 Preliminary |  |  |  |  | C | [5 empty] | 0 | 0 |  | 434.4
| PY5 | Physics region DOWN YG connection installation kit | 105 | 1 | 106 | Procure | See Installation Kits CMD for part number list | 109 | 11554 |  |  | C4 Preliminary |  |  |  |  | C | [5 empty] | 0 | 0 |  | 11554
| PY5 | Physics region UP YG connection installation kit | 105 | 1 | 106 | Procure | should be simpler than UP, guessing 1/2 price | 54.5 | 5777 |  |  | C4 Preliminary |  |  |  |  | C | [5 empty] | 0 | 0 |  | 5777
[5 empty] | 0 |  |  |  | 0 | [13 empty] | 0 | 0 |  | 0
[5 empty] | 0 |  |  |  | 0 | [13 empty] | 0 | 0 |  | 0
[5 empty] | 0 |  |  |  | 0 | [13 empty] | 0 | 0 |  | 0
[5 empty] | 0 |  |  |  | 0 | [13 empty] | 0 | 0 |  | 0
[5 empty] | 0 |  |  |  | 0 | [13 empty] | 0 | 0 |  | 0
[5 empty] | 0 |  |  |  | 0 | [13 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [17 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [17 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [17 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [17 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [17 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [17 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [17 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [17 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [17 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [17 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [17 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [17 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [17 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [17 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [17 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [17 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [17 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [17 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [17 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [17 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [17 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [17 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [17 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [17 empty] | 0 | 0 |  | 0
[9 empty] | 107719.07 | Total Expected Materials Cost | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | Total Hours Cost | 107719.07
Schedule Logic Terms that can be used:
FS = Finish-to-Start
SS = Start-Start
FF = Finish-Finsh
SF = Start-to-Finish

## 1.2.9.2.9
Upgrade Cost Estimate
Name: | 1.2.9.2.9 Ballast weights
Parent WBS: | 1.2.9 Installation off-ice |  | MATERIALS ESTIMATE | [15 empty] | LABOR ESTIMATE | [6 empty] | TOTAL | SCHEDULE INPUT
Description of Scope:
Initials/Date: |  |  | Quantities | [6 empty] | Basis of Estimate (Select One, See Table Below) | [8 empty] | HOURS | [8 empty] | SCHEDULE LOGIC
WBS (if known) | Project Year (0-10) | Description | QTY | Spare | Total | Fabricate or Procure? | Procurement Details Manufacturer, Model, P/N, Vendor | Unit Price | Total Expected Price | C2 LOE Tasks | C3 Advanced | C4 Preliminary | C5 Conceptual | C6 Pre- Conceptual | C7 Rough Estimate | C8 Beyond SOTA | Cost Estimating Technique (See Table Below) | Materials Comments/Notes (procurement lead time, shipping restrictions, etc) | ENGR ($115/hr) | CAD ($81/hr) | SHOP ($77/hr) | STUDENT ($15/hr) | Total Hours | Total Hours Cost | Labor Comments/Schedule Inputs (eg. "March" or "After Microturbine running", etc) |  | Duration (Weeks) | Predecessors | Successors | Milestone
1.2.9.2.9 | PY5 | 100 lbs weight custom made by PSL for string bottom - count takes into account using DM-ice as bottom weight in two strings. | 15 |  | 15 |  | 100 lbs weight custom made by PSL for string bottom | 660 | 9900 |  |  | C4 Preliminary |  |  |  |  | D | Cheaper alternative being researched - thoroid shape would be preferred |  |  |  |  | 0 | 0 |  | 9900
[23 empty] | 0 | 0 |  | 0
[23 empty] | 0 | 0 |  | 0
[23 empty] | 0 | 0 |  | 0
[23 empty] | 0 | 0 |  | 0
[23 empty] | 0 | 0 |  | 0
[23 empty] | 0 | 0 |  | 0
[23 empty] | 0 | 0 |  | 0
[23 empty] | 0 | 0 |  | 0
[23 empty] | 0 | 0 |  | 0
[23 empty] | 0 | 0 |  | 0
[23 empty] | 0 | 0 |  | 0
[23 empty] | 0 | 0 |  | 0
[23 empty] | 0 | 0 |  | 0
[23 empty] | 0 | 0 |  | 0
[23 empty] | 0 | 0 |  | 0
[23 empty] | 0 | 0 |  | 0
[23 empty] | 0 | 0 |  | 0
[23 empty] | 0 | 0 |  | 0
[23 empty] | 0 | 0 |  | 0
[23 empty] | 0 | 0 |  | 0
[23 empty] | 0 | 0 |  | 0
[23 empty] | 0 | 0 |  | 0
[23 empty] | 0 | 0 |  | 0
[23 empty] | 0 | 0 |  | 0
[23 empty] | 0 | 0 |  | 0
[23 empty] | 0 | 0 |  | 0
[23 empty] | 0 | 0 |  | 0
[23 empty] | 0 | 0 |  | 0
[23 empty] | 0 | 0 |  | 0
[23 empty] | 0 | 0 |  | 0
[23 empty] | 0 | 0 |  | 0
[23 empty] | 0 | 0 |  | 0
[23 empty] | 0 | 0 |  | 0
[23 empty] | 0 | 0 |  | 0
[23 empty] | 0 | 0 |  | 0
[23 empty] | 0 | 0 |  | 0
[23 empty] | 0 | 0 |  | 0
[23 empty] | 0 | 0 |  | 0
[9 empty] | 9900 | Total Expected Materials Cost | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | Total Hours Cost | 9900
Schedule Logic Terms that can be used:
FS = Finish-to-Start
SS = Start-Start
FF = Finish-Finsh
SF = Start-to-Finish

## 1.2.9.3.2.1
Upgrade Cost Estimate
Name: | 1.2.9.3.2 Installation Monitor Equipment ICL Quad Connect. Tester
Parent WBS: | 1.2.9 Installation off-ice |  | MATERIALS ESTIMATE | [15 empty] | LABOR ESTIMATE | [6 empty] | TOTAL | SCHEDULE INPUT
Description of Scope: | IME ICL QCT Tester
Initials/Date: | DT 03/31/22 |  | Quantities | [6 empty] | Basis of Estimate (Select One, See Table Below) | [8 empty] | HOURS | [8 empty] | SCHEDULE LOGIC
WBS (if known) | Project Year (0-10) | Description | QTY | Spare | Total | Fabricate or Procure? | Procurement Details Manufacturer, Model, P/N, Vendor | Unit Price | Total Expected Price | C2 LOE Tasks | C3 Advanced | C4 Preliminary | C5 Conceptual | C6 Pre- Conceptual | C7 Rough Estimate | C8 Beyond SOTA | Cost Estimating Technique (See Table Below) | Materials Comments/Notes (procurement lead time, shipping restrictions, etc) | ENGR ($115/hr) | CAD ($81/hr) | SHOP ($77/hr) | STUDENT ($15/hr) | Total Hours | Total Hours Cost | Labor Comments/Schedule Inputs (eg. "March" or "After Microturbine running", etc) |  | Duration (Weeks) | Predecessors | Successors | Milestone
| PY6 | circuit board (prototype) | 4 | 2 | 6 | fabricate |  | 500 | 3000 |  |  |  | x |  |  |  | D | Handheld checker for quad-testing |  |  |  |  | 0 | 0 |  | 3000
| PY6 | circuit board (production) | 3 |  | 3 | fabricate | Prototype. Assume higher costs for N<5 | 600 | 1800 | [7 empty] | D | [5 empty] | 0 | 0 |  | 1800
| PY6 | labor for design, layout, assembly |  |  | 0 |  | WIPAC in-house engineering (TOSI LOE) | [9 empty] | D | Engineering work on the whole system |  |  |  |  | 0 | 0 |  | 0
[17 empty] | D | [5 empty] | 0 | 0 |  | 0
[17 empty] | D | [5 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [17 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [17 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [17 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [17 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [17 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [17 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [17 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [17 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [17 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [17 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [17 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [17 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [17 empty] | 0 | 0 |  | 0
[9 empty] | 4800 | Total Expected Materials Cost | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | Total Hours Cost | 4800
Schedule Logic Terms that can be used:
FS = Finish-to-Start
SS = Start-Start
FF = Finish-Finsh
SF = Start-to-Finish

## 1.2.9.3.3.2
Upgrade Cost Estimate
Name: | 1.2.9.3.3 Installation Monitor Equipment - Depth Sensor Readout
Parent WBS: | 1.2.9 Installation off-ice |  | MATERIALS ESTIMATE | [15 empty] | LABOR ESTIMATE | [6 empty] | TOTAL | SCHEDULE INPUT
Description of Scope: | IME - Depth Sensor Readout
Initials/Date: | DT 3/31/2022 |  | Quantities | [6 empty] | Basis of Estimate (Select One, See Table Below) | [8 empty] | HOURS | [8 empty] | SCHEDULE LOGIC
WBS (if known) | Project Year (0-10) | Description | QTY | Spare | Total | Fabricate or Procure? | Procurement Details Manufacturer, Model, P/N, Vendor | Unit Price | Total Expected Price | C2 LOE Tasks | C3 Advanced | C4 Preliminary | C5 Conceptual | C6 Pre- Conceptual | C7 Rough Estimate | C8 Beyond SOTA | Cost Estimating Technique (See Table Below) | Materials Comments/Notes (procurement lead time, shipping restrictions, etc) | ENGR ($115/hr) | CAD ($81/hr) | SHOP ($77/hr) | STUDENT ($15/hr) | Total Hours | Total Hours Cost | Labor Comments/Schedule Inputs (eg. "March" or "After Microturbine running", etc) |  | Duration (Weeks) | Predecessors | Successors | Milestone
1.2.9.3.3 | PY04,PY05 | IME Data Cable (1 unit in PY4, 2 in PY5) | 1 | 1 | 2 | fabricate |  | 300 | 600 |  |  |  | x |  |  |  | D | one for each TOS. 1 spare,for Q neutralization also |  |  |  |  | 0 | 0 |  | 600
| PY04,PY05 | IME Readout Box (1 unit in PY4, 2 in PY5) | 1 | 1 | 2 | fabricate |  | 600 | 1200 |  |  |  | x |  |  |  | D | one in each TOS. 1 Spare |  |  |  |  | 0 | 0 |  | 1200
| PY04,PY05 | IME Readout Gateway (1 unit in PY4, 2 in PY5) | 1 | 1 | 2 | fabricate | quote in folder | 800 | 1600 |  |  |  | x |  |  |  | D | one in each TOS. 1 Spare Follow this link to quote. |  |  |  |  | 0 | 0 |  | 1600
| x | IME Slip Ring | 2 | 0 | 2 | procure |  | 0 | 0 |  |  | x |  |  |  |  | A | Slip Ring on Tu-20 winch (refurbished/inspected) - slip rings have been inspected by drill team and are now en-route to NPX |  |  |  |  | 0 | 0 |  | 0
| PY04 | Labor for design and development |  |  |  |  | PSL Engineering | [9 empty] | D | Engineering work (planned 80 hours for PY4 but most likely greatly reduced in PY4 due to design change) |  |  |  |  | 0 | 0 |  | 0
| PY05 | Labor for integration |  |  |  |  | PSL Engineering | [9 empty] | D | Engineering work | 60 |  |  |  | 60 | 6900
| PY06 | Labor for production & integration |  |  |  |  | PSL Engineering | [9 empty] | D | Engineering work | 40 |  |  |  | 40 | 4600
[9 empty] | 3400 | Total Expected Materials Cost | [8 empty] | 100 | 0 | 0 | 0 | 100 | 11500 | Total Hours Cost | 3400
Schedule Logic Terms that can be used:
FS = Finish-to-Start
SS = Start-Start
FF = Finish-Finsh
SF = Start-to-Finish

## 1.2.9.3.3.7
Upgrade Cost Estimate
Name: | 1.2.9.3.3 Installation Monitor Equipment Depth Sensors
Parent WBS: | 1.2.9 Installation off-ice |  | MATERIALS ESTIMATE | [15 empty] | LABOR ESTIMATE | [6 empty] | TOTAL | SCHEDULE INPUT
Description of Scope: | IME - Depth Sensor Readout
Initials/Date: | DT 3/31/2022 |  | Quantities | [6 empty] | Basis of Estimate (Select One, See Table Below) | [8 empty] | HOURS | [8 empty] | SCHEDULE LOGIC
WBS (if known) | Project Year (0-10) | Description | QTY | Spare | Total | Fabricate or Procure? | Procurement Details Manufacturer, Model, P/N, Vendor | Unit Price | Total Expected Price | C2 LOE Tasks | C3 Advanced | C4 Preliminary | C5 Conceptual | C6 Pre- Conceptual | C7 Rough Estimate | C8 Beyond SOTA | Cost Estimating Technique (See Table Below) | Materials Comments/Notes (procurement lead time, shipping restrictions, etc) | ENGR ($115/hr) | CAD ($81/hr) | SHOP ($77/hr) | STUDENT ($15/hr) | Total Hours | Total Hours Cost | Labor Comments/Schedule Inputs (eg. "March" or "After Microturbine running", etc) |  | Duration (Weeks) | Predecessors | Successors | Milestone
1.2.9.3.3.7 | PY4 | IME Depth Sensor | 1 | 0 | 1 | procure | Paro Scientific, Model 8CB4000-I, P/N 1700-003-0, SCD 7613-001 Rev T | 11800 |  |  | x | [5 empty] | C | One sensor procures in PY4, rest is pushed to 2025 to minimize drift |  |  |  |  | 0 | 0 |  | 0
1.2.9.3.3.7 | PY6 | IME Depth Sensor | 7 | 1 | 8 | procure | Paro Scientific, Model 8CB4000-I, P/N 1700-003-0, SCD 7613-001 Rev T | 11800 | 94400 |  | x | [5 empty] | C | One sensor procures in PY4, rest is pushed to 2025 to minimize drift Follow this link to quote |  |  |  |  | 0 | 0 |  | 94400
1.2.9.3.3.7 | PY6 | IME Depth Sensor | 7 | 1 | 8 |  | Price increase over 2 years 11% | 1298 | 10384
[9 empty] | 104784 | Total Expected Materials Cost | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | Total Hours Cost | 94400
Schedule Logic Terms that can be used:
FS = Finish-to-Start
SS = Start-Start
FF = Finish-Finsh
SF = Start-to-Finish

## 1.2.9.4.2.3
Upgrade Cost Estimate
Name: | 1.2.9.4.2.3 Calibration Support: Tablets for logbook
Parent WBS: | 1.2.9 Installation off-ice |  | MATERIALS ESTIMATE | [15 empty] | LABOR ESTIMATE | [6 empty] | TOTAL | SCHEDULE INPUT
Description of Scope: | Tablets for electronic logbook
Initials/Date: | DT 3/31/2022 |  | Quantities | [6 empty] | Basis of Estimate (Select One, See Table Below) | [8 empty] | HOURS | [8 empty] | SCHEDULE LOGIC
WBS (if known) | Project Year (0-10) | Description | QTY | Spare | Total | Fabricate or Procure? | Procurement Details Manufacturer, Model, P/N, Vendor | Unit Price | Total Expected Price | C2 LOE Tasks | C3 Advanced | C4 Preliminary | C5 Conceptual | C6 Pre- Conceptual | C7 Rough Estimate | C8 Beyond SOTA | Cost Estimating Technique (See Table Below) | Materials Comments/Notes (procurement lead time, shipping restrictions, etc) | ENGR ($115/hr) | CAD ($81/hr) | SHOP ($77/hr) | STUDENT ($15/hr) | Total Hours | Total Hours Cost | Labor Comments/Schedule Inputs (eg. "March" or "After Microturbine running", etc) |  | Duration (Weeks) | Predecessors | Successors | Milestone
1.2.9.4.2.3 | PY6 | Tablets for logbook | 2 | 1 | 3 | Procure | https://www.dell.com/en-us/work/shop/dell-laptops-and-notebooks/latitude-7220-rugged-extreme-tablet/spd/latitude-12-7220-tablet | 1989 | 5967 |  |  | C4 Preliminary | [5 empty] | cheaper alternatives may be found |  |  |  |  | 0 | 0 |  | 5967
[23 empty] | 0 | 0 |  | 0
[23 empty] | 0 | 0 |  | 0
[23 empty] | 0 | 0 |  | 0
[23 empty] | 0 | 0 |  | 0
[23 empty] | 0 | 0 |  | 0
[23 empty] | 0 | 0 |  | 0
[23 empty] | 0 | 0 |  | 0
[23 empty] | 0 | 0 |  | 0
[23 empty] | 0 | 0 |  | 0
[23 empty] | 0 | 0 |  | 0
[23 empty] | 0 | 0 |  | 0
[23 empty] | 0 | 0 |  | 0
[23 empty] | 0 | 0 |  | 0
[23 empty] | 0 | 0 |  | 0
[23 empty] | 0 | 0 |  | 0
[23 empty] | 0 | 0 |  | 0
[23 empty] | 0 | 0 |  | 0
[23 empty] | 0 | 0 |  | 0
[23 empty] | 0 | 0 |  | 0
[23 empty] | 0 | 0 |  | 0
[23 empty] | 0 | 0 |  | 0
[23 empty] | 0 | 0 |  | 0
[23 empty] | 0 | 0 |  | 0
[23 empty] | 0 | 0 |  | 0
[23 empty] | 0 | 0 |  | 0
[23 empty] | 0 | 0 |  | 0
[23 empty] | 0 | 0 |  | 0
[23 empty] | 0 | 0 |  | 0
[9 empty] | 5967 | Total Expected Materials Cost | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | Total Hours Cost | 0
Schedule Logic Terms that can be used:
FS = Finish-to-Start
SS = Start-Start
FF = Finish-Finsh
SF = Start-to-Finish

## 1.2.9.4.2.5
Upgrade Cost Estimate
Name: | 1.2.9.4.2.5 Calibration Support: Laser rangers, tape measures, supplies
Parent WBS: | 1.2.9 Installation off-ice |  | MATERIALS ESTIMATE | [15 empty] | LABOR ESTIMATE | [6 empty] | TOTAL | SCHEDULE INPUT
Description of Scope:
Initials/Date: | DT 3/31/2022 |  | Quantities | [6 empty] | Basis of Estimate (Select One, See Table Below) | [8 empty] | HOURS | [8 empty] | SCHEDULE LOGIC
WBS (if known) | Project Year (0-10) | Description | QTY | Spare | Total | Fabricate or Procure? | Procurement Details Manufacturer, Model, P/N, Vendor | Unit Price | Total Expected Price | C2 LOE Tasks | C3 Advanced | C4 Preliminary | C5 Conceptual | C6 Pre- Conceptual | C7 Rough Estimate | C8 Beyond SOTA | Cost Estimating Technique (See Table Below) | Materials Comments/Notes (procurement lead time, shipping restrictions, etc) | ENGR ($115/hr) | CAD ($81/hr) | SHOP ($77/hr) | STUDENT ($15/hr) | Total Hours | Total Hours Cost | Labor Comments/Schedule Inputs (eg. "March" or "After Microturbine running", etc) |  | Duration (Weeks) | Predecessors | Successors | Milestone
1.2.9.4.2.5 | PY6 | Laser rangers to be used in tower to measure distance well depth | 2 | 0 | 2 | Procure | https://www.newark.com/pt-BR/fluke/fluke-419d/distance-meter-laser-80m/dp/05W4601 | 499.99 | 999.98 |  |  | C4 Preliminary | [5 empty] | Cheaper alternatives on newark: fluke 419D, 80m, 270 dollars --> not in stock anymore DT100, 100 m, O(140 dollars). Extra devices needed for spares. |  |  |  |  | 0 | 0 |  | 999.98
1.2.9.4.2.5 | PY6 | Shop Lights | 2 | 2 | 4 | Procure | https://www.homedepot.com/p/DEWALT-20-Volt-MAX-Cordless-Jobsite-Spotlight-DCL043/206471311 | 99 | 396 |  |  | C4 Preliminary | [10 empty] | 0 | 0 |  | 396
1.2.9.4.2.5 | PY6 | Harness (included in safety badget) | 0 | 0 | 0 | Procure |  |  | 0 |  |  | C4 Preliminary | [10 empty] | 0 | 0 |  | 0
1.2.9.4.2.5 | PY6 | Miscellanous (notebooks, sharpies, etc) | 7 | 2 | 9 | Procure | rite in the rain, sharpies | 30 | 270 |  |  | C4 Preliminary | [10 empty] | 0 | 0 |  | 270
1.2.9.4.2.5 | PY6 | Tape measure rigid | 2 | 2 | 4 | Procure | https://www.homedepot.com/p/Stanley-25-ft-FATMAX-Tape-Measure-33-725Y/100052995 | 22.97 | 91.88 |  |  | C4 Preliminary | [10 empty] | 0 | 0 |  | 91.88
1.2.9.4.2.5 | PY6 | Tape measure flex | 2 | 2 | 4 | Procure | https://www.grainger.com/product/KESON-100-m-Fiberglass-Metric-Long-3LJX2 | 55.5 | 222 |  |  | C4 Preliminary | [10 empty] | 0 | 0 |  | 222
1.2.9.4.2.5 | PY6 | Helmets (in safety budget) | 0 | 0 | 0 | Procure | https://www.blackdiamondequipment.com/en_US/shop/helmets/ | 59.95 | 0 |  |  | C4 Preliminary | [10 empty] | 0 | 0 |  | 0
1.2.9.4.2.5 | PY6 | Steel Toe Boots | 10 | 0 | 10 | Procure | carolina shoes composite toe | 225 | 2250 |  |  | C4 Preliminary | [10 empty] | 0 | 0 |  | 2250
1.2.9.4.2.5 | PY6 | Safety glasses (in safety budget) | 0 | 0 | 0 | Procure | https://www.grainger.com/product/3M-Safety-Glasses-Anti-Fog-Anti-46F393 | 4.04 | 0 |  |  | C4 Preliminary | [10 empty] | 0 | 0 |  | 0
1.2.9.4.2.5 | PY6 | Driller tape 1 inch | 36 | 3 | 39 | Procure | https://www.plustar.com/products/nitto-permacel-212?gclid=Cj0KCQjwsMDeBRDMARIsAKrOP7GJ8o95SUjsdNXlknerXvgI0OqBQspy_UG9coOb-V6kC12UrPvLTIAaAjAoEALw_wcB | 28.83 | 1124.37 |  |  | C4 Preliminary | [10 empty] | 0 | 0 |  | 1124.37
[5 empty] | 0 |  |  |  | 0 | [13 empty] | 0 | 0 |  | 0
[5 empty] | 0 |  |  |  | 0 | [13 empty] | 0 | 0 |  | 0
[5 empty] | 0 |  |  |  | 0 | [13 empty] | 0 | 0 |  | 0
[5 empty] | 0 |  |  |  | 0 | [13 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [17 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [17 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [17 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [17 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [17 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [17 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [17 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [17 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [17 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [17 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [17 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [17 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [17 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [17 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [17 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [17 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [17 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [17 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [17 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [17 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [17 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [17 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [17 empty] | 0 | 0 |  | 0
[5 empty] | 0 | [17 empty] | 0 | 0 |  | 0
[9 empty] | 5354.23 | Total Expected Materials Cost | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | Total Hours Cost | 5354.23
Schedule Logic Terms that can be used:
FS = Finish-to-Start
SS = Start-Start
FF = Finish-Finsh
SF = Start-to-Finish