## NSFRebaselineRecs_04_2022
Last Update: 7/22/2022
ID | Recommendation | Responsible | Status | Estimated Date for closing | Notes (7/16/2022)
RP_Rec1 | Review the comments in this Panel report and take action as deemed necessary. |  | In progress |  | Comments on separate tab. Note that the PD assumed that whatever was not a fact ("Finding") or recommendation was therefore a comment. It would be useful if the review committee could call out findings and comments separately.
RP_Rec2 | Hire Project Controls effort to support key Project Office functions. These include more rigorous cost estimating, scheduling, EVMS reporting, and risk analysis. Consider engaging outside experts to provide ongoing guidance on such topics. | FF, VO | In progress | 2022-08-31 | Interviewing concluded and suitable candidate not found. We have outside SmartSheet / P6 contractors that we are working with. Looking at engaging other outside contract help.We now have engaged with two different groups who aree working in parallel for an initial port of our smartsheet schedule into P6. We will review progress of both groups and make a decision of which group to go with at the end of August.
RP_Rec3 | Improve Project Office processes to better integrate schedule, cost, and resource information. This will result in a more credible schedule and time-phased costs (e.g., float management, EVMS). The Project should implement rigorous processes that ensure Smartsheet (or a replacement) will demonstrably use activity durations and schedule logic to build a technically-driven schedule with credible early/late start/finish dates, critical path, and correct free float and total float values per activity. These improved processes should follow GAO/NSF best practices and allow quick “what-if” analysis capabilities. Consider engaging outside expertise to guide the team, review schedule changes, and help establish schedule quality metrics (reports) that drive improvements to the schedule. | VO | In progress | 2022-09-15 | We will be moving from Smartsheets to Primavera P6. We have engaged two different contractors to do a preliminary port of the schedule and to ensure the schedule follows GAO/NSF best practices.
RP_Rec4 | Use EVMS reports and practices with the project team to help manage the Project. These include planned value, earned value, and actual costs per month (S-curves), as well as cost and schedule variances, variance analysis reports, and corrective action tracking. | FF/VO/MD | In progress | 2022-09-15 | We are currently calculating EVM variables, and will design and begin using a variance analysis report with corrective action tracking for all areas outside a predefined tolerance. We plan to start this more rigorous tracking along with the rebaselined project on October 1. We will have monthly meetings to go through the EVMS reports and understand and document variances.
RP_Rec5 | Establish appropriate logic links for all activities in the schedule. This will enable the schedule to be used to: assess actual and needed float (e.g., prior to “ready to ship” milestones); perform critical path analysis; explore what-if scenarios; and analyze risks stochastically to determine risk drivers, and compute cost and schedule contingency needs at a high level of confidence. | CAMS/VO/JL | In progress | 2022-07-01 | We have encorporated the logic in the schedule. This logic is now being carried over into the P6 implementation of the schedule, and will be completed by the end of August.
RP_Rec6 | Update the Risk Management Plan to describe more specifically how the project manages risk. For example, summarize or cross-reference management of partner in-kind risks, cargo sequence float management, on-ice risk management, and schedule risk analysis methodology. Clearly delineate the boundary between Project risks and risks owned by the NSF, and ensure this is reflected in the Risk Register. | MD/MZ/VO | closed | 2022-07-15 | We have updated the Risk Management Plan, the Risk Register, and the Risk Evaluation documents. All of the risks that are in the risk register are encorporated as part of the risk evaluation (i.e. even the "NSF" held risks).
RP_Rec7 | Review and improve the Risk Register fields and associated data following best practices, taking the comments in this report into account, and focusing on quantitative (rather than binned) probabilities and impacts. Ensure the following are adequately described: risk mitigations, risk response plans, and the basis of estimates for risk probabilities and minimum, likely, and maximum cost and schedule impacts. | MZ/Team | closed | 2022-07-15 | We have updated the Risk Register taking comments into account. We converted the probabilities to quantitative numbers rather than binned probabilities.
RP_Rec8 | Establish a recognized methodology for performing schedule risk analysis and use it to assess risk-adjusted float and schedule contingency needs. This could consist of schedule risk what-if scenarios, toy Monte Carlo models to aggregate delays to key milestones from associated risks, or a Monte Carlo analysis of all the risks in the full schedule. Include the burn rate costs of risk delays (such as marching army and escalation costs) in the cost risk analysis. | VO/PCMS | In progress | 2022-09-30 | We have used the @risk program, and the schedule in SmartSheets to do a schedule risk analysis. The burn rate of risk delays is negligible, but for risks that carry a full Field Season delay, we also added the cost of continuing the project office for an additional year (which would be the major source of "burn rate". We will repeat this more rigorously in P6/Acumen as part of the project's migration from smart sheets.
RP_Rec9 | Write up Standard Operating Procedures (SOPs), Training Plans (TP), and Field Work Plans (WP) and ensure that Project personnel are familiar with them prior to field deployment. | FF/MZ | In progress | Status and long term plans by 9/1/2022 | FS workplans written spring/summer before FS (as the FSN+1 needs info from FSN). Procedures for many tasks for setup, drilling and installation operations exist or are being revised as work continues. List has been assembled.

## NSFRebaselineComms_04_2022
ID | Comment | Responsible | Status | Estimated Date for closing | Notes
RP_Com1 | Impact of possible loss of in-kind labor contributed by key personnel (e.g. mainboard electrical engineers, software simulation experts, etc.) should be covered by appropriate risk register entries. | MikeD/MikeZ | closed |  | This has been added to the Risk Register.
RP_Com2 | The Drill Control System is all new, potentially a critical path item, a significant cost item, and is a source for a number of identified risks. The Project is encouraged to consider further acceleration of the software development and bench testing off-continent to debug and optimize it before deployment. There is a nearly complete drill mockup at PSL in Madison and nearly all the software can be validated there. The Project is encouraged to finish the software development and carry out the tests early to remove this uncertainty. | TerryB | In progress |  | We agree. We are developing the softare now and plan to complete as much as possible before deployment. While the test system in the North is extensive, not all areas can be tested in the drill mockup at PSL.
RP_Com3 | The Key Assumptions and BOE documents would benefit from some general scrubbing. For example, this involves making sure BOE budgets either match supporting vendor quotes/invoices or have any differences explained in the BOEs. Where the analogy method is used, the logic showing the reasons for deviation from the history needs to be included in the BOE | VO/ICU Team | closed |  | We believe we have done this.
RP_Com4 | The Panel recommends revisiting the early downsizing of the PM staff to determine if past experience was successful because of factors it controlled and can be reasonably assumed to be controllable in the current Project. | VO/KH | closed | 2022-07-15 | We are engaging outside help in project management, scheduling. We believe this, plus the addition of the PD, supports the early downsizing of the PM.
RP_Com5 | Cargo Float Tables flag items with marginal float, but do not include an explanation. A column to capture the reason and what action is being taken would be helpful. | IM | closed |  | Column is created and populated
RP_Com6 | The float information in the Cargo Float Tables did not appear to be derived directly from a master schedule. It is important for all such schedule information to be derived directly from the latest master schedule. | IM/ICU | In progress |  | We agree and we are working on how to do this both in the short term and in the longer term. The information in the Cargo Float Tables are derived from the master schedule, but are entered manually at least monthly.
RP_Com7 | The risk register would benefit from the removal of outdated data (e.g. to a backup copy), for example, obsolete risks, pre-mitigated (and possibly out-of-date) risk assessments. The project should focus on quantitative values for probabilities (percent) and minimum, likely, and maximum cost impacts (dollars) and schedule impacts (months of delay to successor tasks), rather than binning this information and hence losing information. The risk ranking matrix should be reviewed to ensure the top ranked risks align with the top concerns of Project management. | MD/MZ/Project Team | closed | 2022-07-01 | This has been done.
RP_Com8 | With limited time on-ice for each season, the Panel expected that some schedule risks would be more prominent in the overall risk ranking. Project management should consider developing a more balanced strategy for considering cost and schedule in project risk analysis. | MD/MZ/Project Team | closed | 2022-07-01 | We have reviewed all the scheduled risks and implemented the schedule risks in the analysis.
RP_Com9 | No schedule risk analysis nor assessment of needed schedule contingency was presented. This is a notable omission that needs to be addressed. Ideally a risk MC based on the full schedule would be performed. If this is not possible, the project should consider toy MC modeling of subsets of sequential of risks on the critical path or prior to key milestones (e.g. readiness for each field season). At the very least, the project should study various what-if scenarios (after the missing schedule logic has been fixed) to assess the potential consequences of the main schedule risks. | VO/MD/MZ/Project Team | In progress |  | Overlaps with Rec8. Plan to do this rigorously in P6/Acumen as part of migration. Have done a preliminary analysis using @risk and the schedule in smart sheets. This analysis will be repeated whenever the risk register is modified (i.e. risks are retired or new risks are identified).
RP_Com10 | The inflation risk should include uncertainty for labor as well as materials and supplies. The Project should closely monitor prices given the current high levels of inflation, global logistics challenges, and geopolitical uncertainty. | MD/MZ/Project Team | closed | 2022-07-01 | We have revisited both the labor and equipment / M&S inflation (see updated PM1/PM2). We will continue to monitor these risks and update as necessary.
RP_Com11 | The effort for integration of calibration instruments is comprehensive and well-planned. However, this activity could benefit from further planning with regard to descope options, should the higher-risk elements of the upgrade require changes. For example, incorporate a detailed plan for which / how many instruments to deploy if the number of deployed strings must be reduced. |  | In progress |  | We agree. We will work on this in the coming year in order to understand the string configuration vs. # strings deployed before FS3. Once we have a plan in place, the final decision will be made most likely during the drilling season as the schedule unfolds. We need to have multiple plans in advance in order to be flexible during the last season. See the updated Scope Document.
RP_Com12 | The main cable assembly may require an additional external load support. This is tracked as a risk. The Panel recommend that the implementation management group follows this closely as it could impact hardware and procedures managed under the installation group. | DT/Project Team | In progress |  | Absolutely, and the installation management is stracking it. Note that the recently completed (July 2022) pull test seems to indicate that an additional load bearing member will not be necessary.
RP_Com13 | While the scope of work for reworking the EHWD, startup, commissioning, testing, placing in operation and operating seem to be very well understood by the core drill team, more formal documentation of the work plan and detailed activity tasks is recommended. This would enhance confidence in the level of planning, improve on ice efficiency and provides a reference resource for the team, especially if a core team member became unavailable. | TB/Drill Team | In progress |  | Detailed documentation is underway.
RP_Com14 | While there is high confidence in the ability of the team to assemble the spares, supplies and consumables required for the work, more formal documentation linking the spares, supplies and consumables to the rework and drilling tasks and work plans is recommended. This would enhance confidence in the level of planning and provides a reference resource for the team. | DT/Drill Tream | In progress |  | Detailed documentation is underway.
RP_Com15 | With respect to the interfaces between IC/U and USAP Support, the USAP Support requirements are coordinated with scheduled periodic meetings between IC/U personnel and USAP - ASC contacts during project planning and through SIP reports submitted prior to Field Seasons. Furthermore, IC/U has captured USAP – ASC support activities on the project schedule, including dates and durations. However, it is recommended that pertinent details pertaining to the tasks (sizes, capacities, configurations, special tools or equipment, special requirements, etc.) be documented and linked to the scheduled activity for future reference. | ICU/USAP | open |  | We are having regular meetings with ASC and will be working on this documentation within our schedule. We also plan to have a meeting about how to combine or connect the ASC schedules to the ICU P6 schedules once the ICU P6 schedule is available. Right now the activities are duplicated in both schedules, but we plan to work with the ASC scheduler to see how this can be done more transparently and ensure that both schedules are in sync.
RP_Com16 | Risk-based cost contingency is not allocated to cover NSF type risks (logistics issues, funding shortfalls/delays). The assumptions about which risks are covered by NSF should be agreed between the Project and NSF and suitably documented. |  | In progress |  | Overlaps with Rec6 and we are working on it. We have allocated cost contingency fo rthe logistics risks -- we have not done an analysis of funding shortfalls or delays. As additional "NSF-AIL" type risks (i.e. logistics or population) come up, we are working to address them and update any areas of the risk register that require it. As an example, we are in the process of purchasing fuel tanks for overland transport in order to mitigate the "NSF" risks of not being able to fly enough missions to deliver the fuel needed. This was also a mitigation for a risk in our risk register of fuel delays.
RP_Com17 | This is an area in which the Project can improve. Key subaward delivery milestones are included in the schedule. However, the Panel is unsure if subaward task documentation and risk identification are included in the central Project’s PM tools. In our judgement these may have gaps that should be identified and fixed. |  | closed |  | Subaward tasks and risks are included in the central project tools. The central project tools contain tasks, costs, schedule for all areas on the NSF project. For in-kind contributions (where costs are off project), not all tasks are included, but key deliverables are recorded as milestones and these are tracked monthly to assess any schedule / cost impact to the NSF project.
RP_Com18 | The Panel did not have access to the schedule in a standard format (e.g., XER file) that permits interactive scrutiny; therefore, the schedule could not be fully reviewed. It would be helpful for future reviews to have an interactive version of the schedule. | VO/PCMS | open |  | We are planning to move to P6 and have an interactive schedule for future reviews.
RP_Com19 | In-kind contributions are included in the schedule (as uncosted activities), milestones, and in the risk register. As the schedule is scrubbed and the risk analysis is developed, the Project should systematically review all in-kind dependencies and risks to ensure completeness. | MikeD (TC) / Project Team | In progress |  | We agree, and we are doing this regularly with the project team.
RP_Com20 | Logistics Presentation, P11, slide 5 provides an overview of IC/U Planning Capacities based on OPP -AIL furnished allowances. A number of issues are captured in the footnotes in the Table. Recommend those issues be translated into action items and tracked for resolution. |  | closed |  | These are now tracked in the "AIL Planning Capacities FN" tab of this document. (see hyperlink)
RP_Com21 | it is recommended that pertinent details pertaining to ASC tasks (sizes, capacities, configurations, special tools or equipment, special requirements, etc.) be documented and linked to the scheduled activity for future reference. |  | open |  | Overlap with Com15
RP_Com22 | The Risk Management Plan (RMP) describes a general best-practice risk process. The RMP should be updated to describe more specifically how the project actually manages risk. For example, summarize or cross-reference: management of partner in-kind risks, cargo sequence float management, on-ice risk management, and schedule risk analysis (e.g., push tests and what-if scenarios). The RMP should delineate the boundary between risks owned by the project, and risks owned by the NSF. |  | closed |  | See recommendation 6. The Risk Management Plan has been updated.
RP_Com23 | The risk register needs to be scrubbed to focus on the key risk data, for example: remove historical pre-mitigation risk data and retired risks; replace unwieldy risk binning with simple hard numbers, such as percentage probabilities and min/likely/max dollar impacts. Risks should be clearly linked to a handful of key milestones in the schedule, to enable what-if scenarios or simply risk MC models to be explored. |  | closed |  | See recommendation 7. Also the risks are linked to key milestones to do a simple risk MC as described in the Risk Evaluation Document. We elected to "hide" the historical data and not remove it. We took out the binning and used % probabilities and min/likely/max dollar impacts.
RP_Com24 | The Risk Register documents pre-emptive risk mitigations (in the baseline plan) and reactive risk response plans. This documentation should be fleshed out in more detail. In addition, the basis of estimate justification for the post-mitigation risk probabilities and cost and schedule impacts should be summarized in the risk register and reviewed by suitable experts (other than the risk owner) to ensure overall coherence. |  | closed |  | Comment tracked as part of recommendation 7. This has been completed as part of updating the risk register.
RP_Com25 | In-kind contributions are included in the schedule (as uncosted activities), milestones, and in the risk register. As the schedule is scrubbed and the risk analysis is developed, the Project should systematically review all in-kind dependencies and risks to ensure completeness. |  | In progress |  | Overlaps with RP_COM19. We agree and will do it.
RP_Com26 | Project appears to be weak in terms of formal project management skills in the areas of cost estimating, scheduling, risk analysis and EVMS. More training of the project team in these areas (e.g. by physicist PMs from other projects) could be useful, for example to show the practical benefits of having a rigorous and logically-linked project schedule. | VO | In progress |  | We are hiring outside team with lots of expertise in science projects, and will start formal CAM training as we move to P6.
RP_Com27 | The tools and the quality of the associated data should be improved, so they may serve as a coherent master source of trusted cost and schedule data across the project and facilitate regular tasks such as earned-value management, float monitoring, and risk analyses. | VO/Project Team | In progress |  | see responses above.
RP_Com28 | The project team uses schedule information from Smartsheet to calculate CPI and SPI. It was not evident that there is a rigorous process for the evaluation of cost and schedule variances and the management of corrective actions. | VO/Project Team | In progress |  | We agree and this will be addressed during the improvements above. The rebaseline project will carry much more rigor than the project has assumed to date, and the project team understands this.

## AILPlanningCapacitiesFNs
Item (Footnote) | AIL Planning Capacities Footnotes | Responsible | Status | Estimated Date for closing | Notes
Vessel TEUs | FY23 TEUs = 18. If ICU needs more space to move thigs ahead, AIL will find a way to make more TUEs available. | Ian / Project Team | In progress |  | Calculate TEUs needed. Move cargo ahead as much as possible.
Fuel | LC-130 flights may not be enough to move all fuel needed for drilling season. | Ian / ASC / AIL | In progress |  | AIL/ICU/ASC have agreed on a path forward to move fuel overland via tanks. Tanks are currently being purchased by ICU to send to McMurdo this year. Once the tanks are purchased and shipped to NZ, we can close this item.
Poplulation | FY26 population = 46. This is a hard maximum and needs to be reduced if possible. | Ian / ASC / AIL | In progress |  | We cannot reduce the population in FS3 and complete the project. We have begun the conversation with ASC about FY26 population to see if we can mitigate this risk.
Logistics movement | Supportability is dependent on moving as much cargo to Pole as possible in FY24. This means getting as much cargo on the FY23 vessel or, if needed, getting it to MCM via commercial surface shipment / C17 no later than November 2024. | Ian/Project Team/ASC | open
Retro | FY27 info is provided in advance of IPT discussion/clarification on retro requirements. |  | open
DNF/DNDF space | Temperative controlled storage (at MCM and Pole) is likely still and issue that needs to be resolved with this capacity. | Ian / ASC / AIL | closed |  | A solution for DNF space at Pole has been arrived at with ASC.

## StatusList
Status List
In progress
open
closed