## Copy of Rebaseline Schedule PY5
RowID | L2 | WBS | P/C | Task Name | Started | O-L | Duration | Start Date | End Date | Predecessor WBS | % Complete | Status Note | Personnel Notes | Baseline Notes | Float | Is Critical | Baseline Start | Baseline Finish | Variance
1 | 1 | 1 | P | IceCube Phase 1 Upgrade Project | Started | 1 | 2079d | 2018-06-01 | 2026-06-02 |  | 27% |  |  |  | 0 |  | 2018-06-01 | 2026-06-02 | 0
2 | 1.1 | 1.1 | P | Project Office | Not Started | 2 | 949d | 2022-10-01 | 2026-06-02 |  | 0% |  |  |  | 0 |  | 2022-10-01 | 2026-06-02 | 0
3 | 1.1 | 1.1.1 | P | Project Management | Not Started | 3 | 947d | 2022-10-04 | 2026-06-02 |  | 0% |  |  |  | 0 |  | 2022-10-04 | 2026-06-02 | 0
4 | 1.1 | 1.1.1.1 | C | Project Administration (B) | Not Started | 4 | 947d | 2022-10-04 | 2026-06-02 | 38FF, 39SS | 0% |  |  |  | 0 | TRUE | 2022-10-04 | 2026-06-02 | 0
5 | 1.1 | 1.1.1.2 | P | Annual Report | Not Started | 4 | 733d | 2023-06-05 | 2026-04-08 |  | 0% |  |  |  | 40 |  | 2023-06-05 | 2026-04-08 | 0
6 | 1.1 | 1.1.1.2.4 | C | Annual Report 5 | Not Started | 5 | 0 | 2023-06-05 | 2023-06-05 | 39FS +175d | 0% |  |  |  | 773 |  | 2023-06-05 | 2023-06-05 | 0
7 | 1.1 | 1.1.1.2.5 | C | Annual Report 6 | Not Started | 5 | 0 | 2024-06-06 | 2024-06-06 | 6FS +260d | 0% |  |  |  | 513 |  | 2024-06-06 | 2024-06-06 | 0
8 | 1.1 | 1.1.1.2.6 | C | Annual Report 7 | Not Started | 5 | 0 | 2025-06-10 | 2025-06-10 | 7FS +260d | 0% |  |  |  | 253 |  | 2025-06-10 | 2025-06-10 | 0
9 | 1.1 | 1.1.1.2.7 | C | Annual Report 8 | Not Started | 5 | 0 | 2026-04-08 | 2026-04-08 | 36SS | 0% |  |  |  | 40 |  | 2026-04-08 | 2026-04-08 | 0
10 | 1.1 | 1.1.1.5 | P | Project Reviews | Not Started | 4 | 800d | 2023-04-03 | 2026-05-08 |  | 0% |  |  |  | 18 |  | 2023-04-03 | 2026-05-08 | 0
11 | 1.1 | 1.1.1.5.1 | P | Annual NSF Review | Not Started | 5 | 800d | 2023-04-03 | 2026-05-08 |  | 0% |  |  |  | 18 |  | 2023-04-03 | 2026-05-08 | 0
12 | 1.1 | 1.1.1.5.1.5 | C | Annual NSF Review 5 | Not Started | 6 | 0 | 2023-04-03 | 2023-04-03 | 39FS +130d | 0% |  |  |  | 818 |  | 2023-04-03 | 2023-04-03 | 0
13 | 1.1 | 1.1.1.5.1.6 | C | Annual NSF Review 6 | Not Started | 6 | 0 | 2024-04-04 | 2024-04-04 | 12FS +260d | 0% |  |  |  | 558 |  | 2024-04-04 | 2024-04-04 | 0
14 | 1.1 | 1.1.1.5.1.7 | C | Annual NSF Review 7 | Not Started | 6 | 0 | 2025-04-08 | 2025-04-08 | 13FS +260d | 0% |  |  |  | 298 |  | 2025-04-08 | 2025-04-08 | 0
15 | 1.1 | 1.1.1.5.1.8 | C | Annual NSF Review 8 | Not Started | 6 | 0 | 2026-05-08 | 2026-05-08 | 14FS +280d | 0% |  |  |  | 18 |  | 2026-05-08 | 2026-05-08 | 0
16 | 1.1 | 1.1.2 | P | Project Controls | Not Started | 3 | 947d | 2022-10-04 | 2026-06-02 |  | 0% |  |  |  | 0 |  | 2022-10-04 | 2026-06-02 | 0
17 | 1.1 | 1.1.2.1 | C | Project Controls and Finance (B) | Not Started | 4 | 947d | 2022-10-04 | 2026-06-02 | 38FF, 39SS | 0% |  |  |  | 0 | TRUE | 2022-10-04 | 2026-06-02 | 0
18 | 1.1 | 1.1.2.3 | P | Subaward Management | Not Started | 4 | 780d | 2022-11-28 | 2025-12-03 |  | 0% |  |  |  | 128 |  | 2022-11-28 | 2025-12-03 | 0
19 | 1.1 | 1.1.2.3.2 | P | Distributed Funding to Sub-Awardees | Not Started | 5 | 780d | 2022-11-28 | 2025-12-03 |  | 0% |  |  |  | 128 |  | 2022-11-28 | 2025-12-03 | 0
20 | 1.1 | 1.1.2.3.2.5 | C | Distributed Funding to Sub-Awardees 5 | Not Started | 6 | 0 | 2022-11-28 | 2022-11-28 | 39FS +40d | 0% |  |  |  | 908 |  | 2022-11-28 | 2022-11-28 | 0
21 | 1.1 | 1.1.2.3.2.6 | C | Distributed Funding to Sub-Awardees 6 | Not Started | 6 | 0 | 2023-11-28 | 2023-11-28 | 20FS +260d | 0% |  |  |  | 648 |  | 2023-11-28 | 2023-11-28 | 0
22 | 1.1 | 1.1.2.3.2.7 | C | Distributed Funding to Sub-Awardees 7 | Not Started | 6 | 0 | 2024-11-29 | 2024-11-29 | 21FS +260d | 0% |  |  |  | 388 |  | 2024-11-29 | 2024-11-29 | 0
23 | 1.1 | 1.1.2.3.2.8 | C | Distributed Funding to Sub-Awardees 8 | Not Started | 6 | 0 | 2025-12-03 | 2025-12-03 | 22FS +260d | 0% |  |  |  | 128 |  | 2025-12-03 | 2025-12-03 | 0
24 | 1.1 | 1.1.2.4 | C | Financial Reporting | Not Started | 4 | 947d | 2022-10-04 | 2026-06-02 | 38FF, 39SS | 0% |  |  |  | 0 | TRUE | 2022-10-04 | 2026-06-02 | 0
25 | 1.1 | 1.1.3 | P | Quality and Safety | Not Started | 3 | 947d | 2022-10-04 | 2026-06-02 |  | 0% |  |  |  | 0 |  | 2022-10-04 | 2026-06-02 | 0
26 | 1.1 | 1.1.3.1 | C | Quality, Safety Management, Document Control Systems (B) | Not Started | 4 | 947d | 2022-10-04 | 2026-06-02 | 38FF, 39SS | 0% |  |  |  | 0 | TRUE | 2022-10-04 | 2026-06-02 | 0
27 | 1.1 | 1.1.4 | P | Polar Operations | Not Started | 3 | 947d | 2022-10-04 | 2026-06-02 |  | 0% |  |  |  | 0 |  | 2022-10-04 | 2026-06-02 | 0
28 | 1.1 | 1.1.4.1 | C | Logistics (B) | Not Started | 4 | 947d | 2022-10-04 | 2026-06-02 | 38FF, 39SS | 0% |  |  |  | 0 | TRUE | 2022-10-04 | 2026-06-02 | 0
29 | 1.1 | 1.1.5 | P | Project Engineering | Not Started | 3 | 947d | 2022-10-04 | 2026-06-02 |  | 0% |  |  |  | 0 |  | 2022-10-04 | 2026-06-02 | 0
30 | 1.1 | 1.1.5.1 | C | Systems Engineering (B) | Not Started | 4 | 947d | 2022-10-04 | 2026-06-02 | 38FF, 39SS | 0% |  |  |  | 0 | TRUE | 2022-10-04 | 2026-06-02 | 0
31 | 1.1 | 1.1.5.2 | P | System Engineering | Not Started | 4 | 947d | 2022-10-04 | 2026-06-02 |  | 0% |  |  |  | 0 |  | 2022-10-04 | 2026-06-02 | 0
32 | 1.1 | 1.1.5.2.1 | C | System Engineering Support | Not Started | 5 | 947d | 2022-10-04 | 2026-06-02 | 38FF, 39SS | 0% |  |  |  | 0 | TRUE | 2022-10-04 | 2026-06-02 | 0
33 | 1.1 | 1.1.5.3 | C | Production Management | Not Started | 4 | 947d | 2022-10-04 | 2026-06-02 | 38FF, 39SS | 0% |  |  |  | 0 | TRUE | 2022-10-04 | 2026-06-02 | 0
34 | 1.1 | 1.1.5.4 | C | Risk Management | Not Started | 4 | 947d | 2022-10-04 | 2026-06-02 | 38FF, 39SS | 0% |  |  |  | 0 | TRUE | 2022-10-04 | 2026-06-02 | 0
35 | 1.1 | 1.1.5.5 | C | Reliability and Quality Assurance | Not Started | 4 | 947d | 2022-10-04 | 2026-06-02 | 38FF, 39SS | 0% |  |  |  | 0 | TRUE | 2022-10-04 | 2026-06-02 | 0
36 | 1.1 | 1.1.6 | C | Upgrade Project Closeout | Not Started | 3 | 40d | 2026-04-08 | 2026-06-02 | 37 | 0% |  |  |  | 0 | TRUE | 2026-04-08 | 2026-06-02 | 0
37 | 1.1 | 1.1.7 | C | Detector complete and handed off to M&O | Not Started | 3 | 0 | 2026-04-07 | 2026-04-07 | 3308, 3302 |  |  |  |  | 0 | TRUE | 2026-04-07 | 2026-04-07 | 0
38 | 1.1 | 1.1.8 | C | Project Complete | Not Started | 3 | 0 | 2026-06-02 | 2026-06-02 | 36 |  |  |  |  | 0 | TRUE | 2026-06-02 | 2026-06-02 | 0
39 | 1.1 | 1.1.9 | C | RF Project Start | Not Started | 3 | 0 | 2022-10-01 | 2022-10-01 | [5 empty] | -814 |  | 2022-10-01 | 2022-10-01 | 0
40 | 1.2 | 1.2 | P | Upgrade Implementation | Started | 2 | 1982d | 2018-10-01 | 2026-05-18 |  | 36% |  |  |  | 11 |  | 2018-10-01 | 2026-05-18 | 0
41 | 1.2 | 1.2.1 | P | Implementation Management & Systems Engineering | Started | 3 | 1982d | 2018-10-01 | 2026-05-18 |  | 18% |  |  |  | 11 |  | 2018-10-01 | 2026-05-18 | 0
42 | 1.2 | 1.2.1.1 | C | Implementation Management and Controls | Started | 4 | 1951d | 2018-10-01 | 2026-04-03 |  | 17% |  |  |  | 42 |  | 2018-10-01 | 2026-04-03 | 0
43 | 1.2 | 1.2.1.2 | P | Drill Management & Systems Engineering | Started | 4 | 1982d | 2018-10-01 | 2026-05-18 |  | 45% |  |  |  | 11 |  | 2018-10-01 | 2026-05-18 | 0
44 | 1.2 | 1.2.1.2.1 | C | 2018-19 Drill Management & Systems Engineering | Complete | 5 | 261d | 2018-10-01 | 2019-09-30 |  | 100% |  |  |  | 1209 |  | 2018-10-01 | 2019-09-30 | 0
45 | 1.2 | 1.2.1.2.2 | C | 2019-20 Drill Management & Systems Engineering | Complete | 5 | 262d | 2019-10-01 | 2020-09-30 | 44 | 100% |  |  |  | 1209 |  | 2019-10-01 | 2020-09-30 | 0
46 | 1.2 | 1.2.1.2.3 | C | 2020-21 Drill Management & Systems Engineering | Complete | 5 | 261d | 2020-10-01 | 2021-09-30 | 45 | 100% |  |  |  | 1209 |  | 2020-10-01 | 2021-09-30 | 0
47 | 1.2 | 1.2.1.2.4 | P | 2021-22 Drill Management & Systems Engineering | Started | 5 | 260d | 2021-10-01 | 2022-09-29 |  | 41% |  |  |  | 949 |  | 2021-10-01 | 2022-09-29 | 0
48 | 1.2 | 1.2.1.2.4.1 | P | 2021-22 Systems Engineering | Started | 6 | 260d | 2021-10-01 | 2022-09-29 |  | 41% |  |  |  | 949 |  | 2021-10-01 | 2022-09-29 | 0
49 | 1.2 | 1.2.1.2.4.1.1 | C | P&ID and Instrumentation List Development | Started | 7 | 250d | 2021-10-15 | 2022-09-29 |  | 42% |  |  |  | 949 |  | 2021-10-15 | 2022-09-29 | 0
50 | 1.2 | 1.2.1.2.4.1.2 | C | Parameters Documentation Compiled | Started | 7 | 0 | 2022-07-15 | 2022-07-15 |  | 32% |  |  |  | 1004 |  | 2022-07-15 | 2022-07-15 | 0
51 | 1.2 | 1.2.1.2.4.1.3 | C | IV&T Closed out | Started | 7 | 0 | 2022-04-15 | 2022-04-15 |  | 50% |  |  |  | 1069 |  | 2022-04-15 | 2022-04-15 | 0
52 | 1.2 | 1.2.1.2.4.1.4 | C | Drill Procedures Reviewed | Started | 7 | 0 | 2022-08-15 | 2022-08-15 |  | 16% |  |  |  | 983 |  | 2022-08-15 | 2022-08-15 | 0
53 | 1.2 | 1.2.1.2.4.1.5 | C | Process Control Narrative Development | Started | 7 | 250d | 2021-10-01 | 2022-09-15 |  | 40% |  |  |  | 959 |  | 2021-10-01 | 2022-09-15 | 0
54 | 1.2 | 1.2.1.2.5 | P | 2022-23 Drill Management & Systems Engineering | Not Started | 5 | 261d | 2022-10-03 | 2023-10-02 |  | 0% |  |  |  | 687 |  | 2022-10-03 | 2023-10-02 | 0
55 | 1.2 | 1.2.1.2.5.1 | C | 2022-23 Management & Systems Engineering | Not Started | 6 | 261d | 2022-10-03 | 2023-10-02 | 39 | 0% |  | Jeff Cherwinka, Terry Benson | Engineering oversight and systems development - coordination and planning, season planning, ASC interface, SIP, logistics coordination, drill procedures, EVMS, seasonal reports Drill Manager LOE: 0.8 FTE = 1440 hr/yr Team meetings - weekly status, reviews, collaboration mtgs, ASC weekly and annual Weekly status mtgs: 35 wks * 1 hr * 12 people = 420 hr ASC coord: 18 wks * 1 hr * 3 people = 78 hr Total = 558 hr Tech meetings - Tech meetings LOE: 2 hr/wk * 40 wks each year, 8 people = 640 hr | -229 |  | 2022-10-03 | 2023-10-02 | 0
56 | 1.2 | 1.2.1.2.5.2 | C | Drill Procedure Review | Not Started | 6 | 120d | 2023-04-18 | 2023-10-02 | 55FF | 0% |  |  | 1 hr session/wk * 35 wks each year 8 people = 280 hr/yr | 687 |  | 2023-04-18 | 2023-10-02 | 0
57 | 1.2 | 1.2.1.2.5.3 | C | Drill Hole Modeling | Not Started | 6 | 120d | 2023-04-18 | 2023-10-02 | 55FF | 0% |  |  | Hole modeling = 120 hr/yr | 687 |  | 2023-04-18 | 2023-10-02 | 0
58 | 1.2 | 1.2.1.2.5.4 | C | Drill Documentation Support | Not Started | 6 | 120d | 2023-04-18 | 2023-10-02 | 55FF | 0% |  |  | Documentation (team) = 120 hr/yr | 687 |  | 2023-04-18 | 2023-10-02 | 0
59 | 1.2 | 1.2.1.2.6 | P | 2023-24 Drill Management & Systems Engineering | Not Started | 5 | 262d | 2023-10-03 | 2024-10-07 |  | 0% |  | Jeff Cherwinka, Terry Benson |  | 425 |  | 2023-10-03 | 2024-10-07 | 0
60 | 1.2 | 1.2.1.2.6.1 | C | 2023-24 Management & Systems Engineering | Not Started | 6 | 262d | 2023-10-03 | 2024-10-07 | 55 | 0% |  | Jeff Cherwinka, Terry Benson | Engineering oversight and systems development Drill Manager LOE: 0.8 FTE = 1440 hr/yr Team meetings - weekly status, reviews, collaboration mtgs, ASC weekly and annual Weekly status mtgs: 35 wks * 1 hr * 12 people = 420 hr ASC coord: 18 wks * 1 hr * 3 people = 54 hr Total = 1914 hr Tech meetings - Tech meetings LOE: 2 hr/wk * 40 wks each year, 8 people = 540 hr | -109 |  | 2023-10-03 | 2024-10-07 | 0
61 | 1.2 | 1.2.1.2.6.2 | C | PY6 Season Debrief | Not Started | 6 | 1d | 2024-03-14 | 2024-03-14 | 886FS +4w | 0% |  |  | Season Debrief - 30 people, hybrid, 4 hr = 120 hr | 570 |  | 2024-03-14 | 2024-03-14 | 0
62 | 1.2 | 1.2.1.2.6.3 | C | Drill Procedure Review | Not Started | 6 | 120d | 2024-04-23 | 2024-10-07 | 60FF | 0% |  |  | 1 hr session/wk * 35 wks each year 8 people = 280 hr/yr | 425 |  | 2024-04-23 | 2024-10-07 | 0
63 | 1.2 | 1.2.1.2.6.4 | C | PY6 Drill Advisory Panel | Not Started | 6 | 2d | 2024-04-12 | 2024-04-15 | 61FS +4w | 0% |  |  | DAP - 2 days, 12 people = 192 hr | 550 |  | 2024-04-12 | 2024-04-15 | 0
64 | 1.2 | 1.2.1.2.6.5 | C | Drill Hole Modeling | Not Started | 6 | 120d | 2024-04-23 | 2024-10-07 | 60FF | 0% |  |  | Hole modeling = 120 hr/yr | 425 |  | 2024-04-23 | 2024-10-07 | 0
65 | 1.2 | 1.2.1.2.6.6 | C | Drill Documentation Support | Not Started | 6 | 120d | 2024-04-23 | 2024-10-07 | 60FF | 0% |  |  | Documentation (team) = 120 hr/yr | 425 |  | 2024-04-23 | 2024-10-07 | 0
66 | 1.2 | 1.2.1.2.7 | P | 2024-25 Drill Management & Systems Engineering | Not Started | 5 | 261d | 2024-10-08 | 2025-10-10 |  | 0% |  | Jeff Cherwinka, Terry Benson |  | 164 |  | 2024-10-08 | 2025-10-10 | 0
67 | 1.2 | 1.2.1.2.7.1 | C | 2024-25 Management & Systems Engineering | Not Started | 6 | 261d | 2024-10-08 | 2025-10-10 | 60 | 0% |  | Jeff Cherwinka, Terry Benson | System engineering oversight and systems development Drill Manager LOE: 0.8 FTE = 1440 hr/yr Team meetings - weekly status, reviews, collaboration mtgs, ASC weekly and annual Weekly status mtgs: 35 wks * 1 hr * 12 people = 420 hr ASC coord: 18 wks * 1 hr * 3 people = 54 hr Total = 1914 hr Tech meetings - Tech meetings LOE: 2 hr/wk * 40 wks each year, 8 people = 540 hr | 11 |  | 2024-10-08 | 2025-10-10 | 0
68 | 1.2 | 1.2.1.2.7.2 | C | PY7 Season Debrief | Not Started | 6 | 1d | 2025-03-17 | 2025-03-17 | 1246FS +4w | 0% |  |  | Season Debrief - 30 people, hybrid, 4 hr = 120 hr | 311 |  | 2025-03-17 | 2025-03-17 | 0
69 | 1.2 | 1.2.1.2.7.3 | C | Drill Procedure Review | Not Started | 6 | 120d | 2025-04-28 | 2025-10-10 | 67FF | 0% |  |  | 1 hr session/wk * 35 wks each year 8 people = 280 hr/yr | 164 |  | 2025-04-28 | 2025-10-10 | 0
70 | 1.2 | 1.2.1.2.7.4 | C | PY7 Drill Advisory Panel | Not Started | 6 | 2d | 2025-04-15 | 2025-04-16 | 68FS +4w | 0% |  |  | DAP - 2 days, 12 people = 192 hr | 291 |  | 2025-04-15 | 2025-04-16 | 0
71 | 1.2 | 1.2.1.2.7.5 | C | Drill Hole Modeling | Not Started | 6 | 120d | 2025-04-28 | 2025-10-10 | 67FF | 0% |  |  | Hole modeling = 120 hr/yr | 164 |  | 2025-04-28 | 2025-10-10 | 0
72 | 1.2 | 1.2.1.2.7.6 | C | Drill Readiness Review (PSL) | Not Started | 6 | 2d | 2025-07-09 | 2025-07-10 | 1449SS -18w | 0% |  |  | 12 Engineers 2 days @ 8 hrs = 192 hr | 230 |  | 2025-07-09 | 2025-07-10 | 0
73 | 1.2 | 1.2.1.2.7.7 | C | Drill Documentation Support | Not Started | 6 | 120d | 2025-04-28 | 2025-10-10 | 67FF | 0% |  |  | Documentation (team) = 120 hr/yr | 164 |  | 2025-04-28 | 2025-10-10 | 0
74 | 1.2 | 1.2.1.2.8 | P | 2025-26 Drill Management & Systems Engineering | Not Started | 5 | 153d | 2025-10-13 | 2026-05-18 |  | 0% |  | Jeff Cherwinka, Terry Benson |  | 11 |  | 2025-10-13 | 2026-05-18 | 0
75 | 1.2 | 1.2.1.2.8.1 | C | 2025-26 Management & Systems Engineering | Not Started | 6 | 153d | 2025-10-13 | 2026-05-18 | 67 | 0% |  | Jeff Cherwinka, Terry Benson | System Engineer - Oct (pre-deployment) & March/April for closeout. On-ice hours captured in Field Seasons. Drill Manager LOE: Oct (pre-deployment) & March/April for closeout. On-ice hours captured in Field Seasons. Engineering support hours for weekly status meeting & off-ice engineering support | 11 |  | 2025-10-13 | 2026-05-18 | 0
76 | 1.2 | 1.2.1.2.8.2 | C | PY8 Season Debrief | Not Started | 6 | 1d | 2026-03-16 | 2026-03-16 | 1454FS +4w | 0% |  |  | Season Debrief - 30 people, hybrid, 4 hr = 120 hr | 56 |  | 2026-03-16 | 2026-03-16 | 0
77 | 1.2 | 1.2.1.2.8.3 | C | Final Drill Completion Report | Not Started | 6 | 0 | 2026-04-27 | 2026-04-27 | 76FS +6w | 0% |  |  |  | 26 |  | 2026-04-27 | 2026-04-27 | 0
78 | 1.2 | 1.2.1.3 | P | Installation Management & Systems Engineering | Should have Started | 4 | 1197d | 2021-10-01 | 2026-05-15 |  | 0% |  |  |  | 12 |  | 2021-10-01 | 2026-05-15 | 0
79 | 1.2 | 1.2.1.3.1 | P | 2021-22 Management & Systems Engineering | Should have Started | 5 | 261d | 2021-10-01 | 2022-09-30 |  | 0% |  |  |  | 948 |  | 2021-10-01 | 2022-09-30 | 0
80 | 1.2 | 1.2.1.3.1.1 | C | String Management and Controls (2021-2022) | Should have Started | 6 | 261d | 2021-10-01 | 2022-09-30 |  | 0% |  | Tosi - 15% |  | 948 |  | 2021-10-01 | 2022-09-30 | 0
81 | 1.2 | 1.2.1.3.1.2 | C | Installation Engineering (2021-2022) | Should have Started | 6 | 261d | 2021-10-01 | 2022-09-30 |  | 0% |  | Tosi - 25% |  | 948 |  | 2021-10-01 | 2022-09-30 | 0
82 | 1.2 | 1.2.1.3.1.3 | C | Installation Engineering Support (2021-2022) | Should have Started | 6 | 261d | 2021-10-01 | 2022-09-30 |  | 0% |  | Jeff Cherwinka, Terry Benson | Includes PSL tower work | 948 |  | 2021-10-01 | 2022-09-30 | 0
83 | 1.2 | 1.2.1.3.2 | P | 2022-23 Management & Systems Engineering | Not Started | 5 | 261d | 2022-10-03 | 2023-10-02 |  | 0% |  |  |  | 687 |  | 2022-10-03 | 2023-10-02 | 0
84 | 1.2 | 1.2.1.3.2.1 | C | String Management and Controls (2022-2023) | Not Started | 6 | 261d | 2022-10-03 | 2023-10-02 | 39 | 0% |  | Tosi - 15% |  | -553 |  | 2022-10-03 | 2023-10-02 | 0
85 | 1.2 | 1.2.1.3.2.2 | C | Installation Engineering (2022-2023) | Not Started | 6 | 261d | 2022-10-03 | 2023-10-02 | 84SS | 0% |  | Tosi - 25% |  | 687 |  | 2022-10-03 | 2023-10-02 | 0
86 | 1.2 | 1.2.1.3.2.3 | C | Installation Engineering Support (2022-2023) | Not Started | 6 | 261d | 2022-10-03 | 2023-10-02 | 84SS | 0% |  | Jeff Cherwinka, Terry Benson |  | 687 |  | 2022-10-03 | 2023-10-02 | 0
87 | 1.2 | 1.2.1.3.3 | P | 2023-24 Management & Systems Engineering | Not Started | 5 | 262d | 2023-10-03 | 2024-10-07 |  | 0% |  |  |  | 425 |  | 2023-10-03 | 2024-10-07 | 0
88 | 1.2 | 1.2.1.3.3.1 | C | String Management and Controls (2023-2024) | Not Started | 6 | 262d | 2023-10-03 | 2024-10-07 | 84 | 0% |  | Tosi - 10% |  | -292 |  | 2023-10-03 | 2024-10-07 | 0
89 | 1.2 | 1.2.1.3.3.2 | C | Installation Engineering (2023-2024) | Not Started | 6 | 262d | 2023-10-03 | 2024-10-07 | 88SS | 0% |  | Tosi - 30% |  | 425 |  | 2023-10-03 | 2024-10-07 | 0
90 | 1.2 | 1.2.1.3.3.3 | C | Installation Engineering Support (2023-2024) | Not Started | 6 | 262d | 2023-10-03 | 2024-10-07 | 88SS | 0% |  | Jeff Cherwinka, Terry Benson |  | 425 |  | 2023-10-03 | 2024-10-07 | 0
91 | 1.2 | 1.2.1.3.4 | P | 2024-25 Management & Systems Engineering | Not Started | 5 | 261d | 2024-10-08 | 2025-10-10 |  | 0% |  |  |  | 164 |  | 2024-10-08 | 2025-10-10 | 0
92 | 1.2 | 1.2.1.3.4.1 | C | String Management and Controls (2024-2025) | Not Started | 6 | 261d | 2024-10-08 | 2025-10-10 | 88 | 0% | Tosi - 5% | Tosi - 5% |  | -292 |  | 2024-10-08 | 2025-10-10 | 0
93 | 1.2 | 1.2.1.3.4.2 | C | Installation Engineering (2024-2025) | Not Started | 6 | 261d | 2024-10-08 | 2025-10-10 | 92SS | 0% | Tosi - 25% | Tosi - 25% |  | 164 |  | 2024-10-08 | 2025-10-10 | 0
94 | 1.2 | 1.2.1.3.4.3 | C | Installation Engineering Support (2024-2025) | Not Started | 6 | 261d | 2024-10-08 | 2025-10-10 | 92SS | 0% |  | Jeff Cherwinka, Terry Benson |  | 164 |  | 2024-10-08 | 2025-10-10 | 0
95 | 1.2 | 1.2.1.3.5 | P | 2025-26 Management & Systems Engineering | Not Started | 5 | 152d | 2025-10-13 | 2026-05-15 |  | 0% |  |  |  | 12 |  | 2025-10-13 | 2026-05-15 | 0
96 | 1.2 | 1.2.1.3.5.1 | C | String Management and Controls (2025-2026) | Not Started | 6 | 152d | 2025-10-13 | 2026-05-15 | 92 | 0% | Tosi - 5% | Tosi - 5% |  | -140 |  | 2025-10-13 | 2026-05-15 | 0
97 | 1.2 | 1.2.1.3.5.2 | C | Installation Engineering (2025-2026) | Not Started | 6 | 152d | 2025-10-13 | 2026-05-15 | 96SS | 0% | Tosi - 20% | Tosi - 20% |  | 12 |  | 2025-10-13 | 2026-05-15 | 0
98 | 1.2 | 1.2.1.3.5.3 | C | Installation Engineering Support (2025-2026) | Not Started | 6 | 152d | 2025-10-13 | 2026-05-15 | 96SS | 0% |  | Jeff Cherwinka, Terry Benson |  | 12 |  | 2025-10-13 | 2026-05-15 | 0
99 | 1.2 | 1.2.1.3.5.4 | C | Final String Installation Completion Report | Not Started | 6 | 0 | 2026-04-27 | 2026-04-27 | 76FS +6w | 0% |  |  |  | 26 |  | 2026-04-27 | 2026-04-27 | 0
100 | 1.2 | 1.2.1.4 | P | Implementation Quality and Safety | Not Started | 4 | 912d | 2022-10-03 | 2026-04-13 |  | 0% |  |  |  | 36 |  | 2022-10-03 | 2026-04-13 | 0
101 | 1.2 | 1.2.1.4.5 | C | 2022-23 Quality & Safety | Not Started | 5 | 261d | 2022-10-03 | 2023-10-02 | 39 | 0% |  |  | JHA Review - 12 sessions * 2 hr/session each year 6 people = 144 hr/yr | 36 |  | 2022-10-03 | 2023-10-02 | 0
102 | 1.2 | 1.2.1.4.6 | C | 2023-24 Quality & Safety | Not Started | 5 | 261d | 2023-10-03 | 2024-10-04 | 101 | 0% |  |  | JHA Review - 12 sessions * 2 hr/session each year 6 people = 144 hr/yr | 36 |  | 2023-10-03 | 2024-10-04 | 0
103 | 1.2 | 1.2.1.4.7 | C | 2024-25 Quality & Safety | Not Started | 5 | 260d | 2024-10-07 | 2025-10-08 | 102 | 0% |  |  | JHA Review - 12 sessions * 2 hr/session each year 6 people = 144 hr/yr | 36 |  | 2024-10-07 | 2025-10-08 | 0
104 | 1.2 | 1.2.1.4.8 | C | 2025-26 Quality & Safety | Not Started | 5 | 130d | 2025-10-09 | 2026-04-13 | 103 | 0% |  |  | JHA Review - 2 sessions * 2 hr/session each year 6 people = 24 hr/yr October & November | 36 |  | 2025-10-09 | 2026-04-13 | 0
105 | 1.2 | 1.2.1.5 | P | Implementation Travel | Not Started | 4 | 782d | 2022-10-03 | 2025-10-08 |  | 0% |  |  |  | 166 |  | 2022-10-03 | 2025-10-08 | 0
106 | 1.2 | 1.2.1.5.5 | C | 2022-23 Travel (non-deployment) | Not Started | 5 | 260d | 2022-10-03 | 2023-09-29 | 39 | 0% |  |  | Collab Mtg (international): 1x $3600 ASC/Denver (domestic): 5x $1800 = $9k Total = 3.6k+9k = 12.6k | 298 |  | 2022-10-03 | 2023-09-29 | 0
107 | 1.2 | 1.2.1.5.6 | C | 2023-24 Travel (non-deployment) | Not Started | 5 | 195d | 2024-01-05 | 2024-10-03 | 106FS +66d | 0% |  |  | Collab Mtg (international): 1x $3600 ASC/Denver (domestic): 5x $1800 = $9k Total = 3.6k+9k = 12.6k | 232 |  | 2024-01-05 | 2024-10-03 | 0
108 | 1.2 | 1.2.1.5.7 | C | 2024-25 Travel (non-deployment) | Not Started | 5 | 195d | 2025-01-09 | 2025-10-08 | 107FS +66d | 0% |  |  | Collab Mtg (international): 1x $3600 ASC/Denver (domestic): 5x $1800 = $9k Total = 3.6k+9k = 12.6k | 166 |  | 2025-01-09 | 2025-10-08 | 0
109 | 1.2 | 1.2.1.6 | P | Transportation and Logistics | Started | 4 | 1229d | 2020-11-06 | 2025-08-01 |  | 18% |  |  |  | 215 |  | 2020-11-06 | 2025-08-01 | 0
110 | 1.2 | 1.2.1.6.1 | P | Shipment Milestones | Not Started | 5 | 712d | 2022-11-01 | 2025-08-01 |  | 0% |  |  |  | 215 |  | 2022-11-01 | 2025-08-01 | 0
111 | 1.2 | 1.2.1.6.1.1 | C | FY23 USAP Vessel Shipment Departs PSL | Not Started | 6 | 0 | 2022-11-01 | 2022-11-01 |  | 0% |  | USAP Support |  | 927 |  | 2022-11-01 | 2022-11-01 | 0
112 | 1.2 | 1.2.1.6.1.2 | C | FY24 ComSur Shipment Departs PSL | Not Started | 6 | 0 | 2023-08-01 | 2023-08-01 |  | 0% |  |  |  | 731 |  | 2023-08-01 | 2023-08-01 | 0
113 | 1.2 | 1.2.1.6.1.2 | C | FY24 USAP Vessel Shipment Departs PSL | Not Started | 6 | 0 | 2023-11-01 | 2023-11-01 |  | 0% |  | USAP Support |  | 666 |  | 2023-11-01 | 2023-11-01 | 0
114 | 1.2 | 1.2.1.6.1.2 | C | FY25 ComSur Shipment Departs PSL | Not Started | 6 | 0 | 2024-08-01 | 2024-08-01 |  | 0% |  |  |  | 342 |  | 2024-08-01 | 2024-08-01 | 0
115 | 1.2 | 1.2.1.6.1.3 | C | FY25 USAP Vessel Shipment Departs PSL | Not Started | 6 | 0 | 2024-11-01 | 2024-11-01 |  | 0% |  | USAP Support |  | 407 |  | 2024-11-01 | 2024-11-01 | 0
116 | 1.2 | 1.2.1.6.1.4 | C | FY26 ComSur Shipment Departs PSL | Not Started | 6 | 0 | 2025-08-01 | 2025-08-01 |  | 0% |  |  |  | 215 |  | 2025-08-01 | 2025-08-01 | 0
117 | 1.2 | 1.2.1.6.2 | P | Drill Shipment Prep | Started | 5 | 1222d | 2020-11-06 | 2025-07-22 |  | 61% |  |  |  | 222 |  | 2020-11-06 | 2025-07-22 | 0
118 | 1.2 | 1.2.1.6.2.1 | C | Crate Shop Parts - Hose Crimper (Vessel) | Complete | 6 | 15d | 2021-10-17 | 2021-11-04 |  | 100% |  |  |  | 1184 |  | 2021-10-17 | 2021-11-04 | 0
119 | 1.2 | 1.2.1.6.2.2 | C | Crate GEN-2, 3, PDM - Ship Components, Repair Parts (Vessel) | Complete | 6 | 15d | 2021-01-07 | 2021-01-27 | 649SS +70d | 100% |  |  |  | 1385 |  | 2021-01-07 | 2021-01-27 | 0
120 | 1.2 | 1.2.1.6.2.3 | C | Prepare: Cable Reels Main and RWCR (Vessel) | Complete | 6 | 21d | 2021-10-15 | 2021-11-12 |  | 100% |  |  |  | 1178 |  | 2021-10-15 | 2021-11-12 | 0
121 | 1.2 | 1.2.1.6.2.4 | C | Crate WT Repair Parts, Replacements (Vessel) | Complete | 6 | 15d | 2022-09-07 | 2022-09-27 | 677FS +70d | 100% |  |  | Cargo estimates from John Arnolde (Logistics Mgr, PSL): $7,000 - Dedicated truckload ($4,375 alternative, but not reliable, so using the $7k) $ 800 - Typical 4'x4'x8' Crate (weight ~1,500#) $ 300 - Crate Materials (4'x4'x8') 2 - crates | 951 |  | 2022-09-07 | 2022-09-27 | 0
122 | 1.2 | 1.2.1.6.2.5 | C | Prepare GEN-2, 3, PDM - Skis (2021-22) (Vessel) | Complete | 6 | 24d | 2020-12-06 | 2021-01-06 |  | 100% |  |  |  | 1400 |  | 2020-12-06 | 2021-01-06 | 0
123 | 1.2 | 1.2.1.6.2.6 | C | Crate Generator Hoods (2021-22) (Vessel) | Complete | 6 | 7d | 2020-11-06 | 2020-11-16 |  | 100% |  |  | Cargo estimates from John Arnolde (Logistics Mgr, PSL): $7,000 - Dedicated truckload ($4,375 alternative, but not reliable, so using the $7k) $ 800 - Typical 4'x4'x8' Crate (weight ~1,500#) $ 300 - Crate Materials (4'x4'x8') 2 - crates | 1437 |  | 2020-11-06 | 2020-11-16 | 0
124 | 1.2 | 1.2.1.6.2.7 | C | Prepare Surface Hose to PTH (2021-22) Outdoor Storage MCM (Vessel) | Complete | 6 | 7d | 2020-11-06 | 2020-11-16 |  | 100% |  |  |  | 1437 |  | 2020-11-06 | 2020-11-16 | 0
125 | 1.2 | 1.2.1.6.2.8 | C | Crate MHP/PHS Replacements & Spares (FY23 Shipment) (Container C - Vessel) | Started | 6 | 6d | 2022-05-31 | 2022-06-07 | 175 | 80% |  |  |  | 937 |  | 2022-05-31 | 2022-06-07 | 0
126 | 1.2 | 1.2.1.6.2.9 | C | Crate Fuel Systems & Tower Components (Container C - Vessel) | Not Started | 6 | 7d | 2022-05-02 | 2022-05-10 | 194 | 0% |  |  |  | 937 |  | 2022-05-02 | 2022-05-10 | 0
127 | 1.2 | 1.2.1.6.2.10 | C | Crate TOS Components & Spares (Container C - Vessel) | Not Started | 6 | 4d | 2022-06-29 | 2022-07-04 | 204 | 0% |  |  | Collapsible Bulk Container, Black, 34 inH x 32 inL x 30 inW, 1EA w/ lid $425.38 W.W. Grainger Item #8CA51 & #9GFT8 | 937 |  | 2022-06-29 | 2022-07-04 | 0
128 | 1.2 | 1.2.1.6.2.11 | C | Crate Control Systems Components Shipment 1 - DNF (Vessel) | Started | 6 | 5d | 2022-10-03 | 2022-10-07 | 302, 305, 314, 411, 419 | 96% |  |  | Collapsible Bulk Container, Black, 48 inH x 45 inL x 41 inW, 1EA w/ lid $838 W.W. Grainger Item #36XE25 & #1XGG9 | 943 |  | 2022-10-03 | 2022-10-07 | 0
129 | 1.2 | 1.2.1.6.2.12 | C | Crate ARA Drill Subsystem Parts - Crate 1 (Container C - Vessel) | Started | 6 | 7d | 2022-10-06 | 2022-10-14 | 735 | 25% |  |  | Collapsible Bulk Container, Black, 48 inH x 45 inL x 41 inW, 1EA w/ lid $838 W.W. Grainger Item #36XE25 & #1XGG9 | 927 |  | 2022-10-06 | 2022-10-14 | 0
130 | 1.2 | 1.2.1.6.2.13 | C | Crate ARA Drill Subsystem Parts DNF - Crate 2 (Vessel) | Started | 6 | 7d | 2022-10-06 | 2022-10-14 | 735 | 25% |  |  | Collapsible Bulk Container, Black, 34 inH x 32 inL x 30 inW, 1EA w/ lid $425.38 W.W. Grainger Item #8CA51 & #9GFT8 | 938 |  | 2022-10-06 | 2022-10-14 | 0
131 | 1.2 | 1.2.1.6.2.14 | C | Crate Spare Main Drill & Combo Cables (Container C - Vessel) | Not Started | 6 | 6d | 2022-05-01 | 2022-05-06 |  | 0% |  |  | Tie Down Strap, 27 ftL x 2 inW, 1600 lb Load Limit, Ratchet $52.02 x 8 = $416.16, Lumber for spool support $130.88 | 937 |  | 2022-05-01 | 2022-05-06 | 0
132 | 1.2 | 1.2.1.6.2.15 | C | Prepare Bull Wheel for Shipment (Container C - Vessel) | Not Started | 6 | 2d | 2022-07-01 | 2022-07-04 |  | 0% |  |  | Tie Down Strap, 20 ftL x 2 inW, 1600 lb Load Limit, Ratchet $50.62 x 4 = $202.48, Lumber for bull wheel support $65.44 - Total $268 | 937 |  | 2022-07-01 | 2022-07-04 | 0
133 | 1.2 | 1.2.1.6.2.16 | C | Crate Shop Parts - Consumables & Spares, etc. (Container C - Vessel) | Started | 6 | 5d | 2022-09-17 | 2022-09-22 |  | 25% |  |  |  | 937 |  | 2022-09-17 | 2022-09-22 | 0
134 | 1.2 | 1.2.1.6.2.17 | C | Crate Condensate Management Components (Container C - Vessel) | Started | 6 | 4d | 2022-05-30 | 2022-06-02 | 692 | 80% |  |  | Collapsible Bulk Container, Black, 34 inH x 32 inL x 30 inW, 1EA w/ lid $425.38 W.W. Grainger Item #8CA51 & #9GFT8 | 937 |  | 2022-05-30 | 2022-06-02 | 0
135 | 1.2 | 1.2.1.6.2.18 | C | Crate Pump Repair/Replace Components (Container C - Vessel) | Started | 6 | 2d | 2022-04-07 | 2022-04-08 | 682 | 80% |  | Driller_PSL_Lead | Cargo estimates from John Arnolde (Logistics Mgr, PSL): $7,000 - Dedicated truckload ($4,375 alternative, but not reliable, so using the $7k) $ 800 - Typical 4'x4'x8' Crate (weight ~1,500#) $ 300 - Crate Materials (4'x4'x8') 1 - crate | 937 |  | 2022-04-07 | 2022-04-08 | 0
136 | 1.2 | 1.2.1.6.2.19 | C | Crate Hose Reel Heating System (Container C - Vessel) | Not Started | 6 | 5d | 2022-10-05 | 2022-10-11 | 280 | 0% |  |  |  | 930 |  | 2022-10-05 | 2022-10-11 | 0
137 | 1.2 | 1.2.1.6.2.20 | C | Load Container C (Main/Combo Cables, Bull Wheel, Hose Heating Components, ARA Drill Components - Crate 2) (Vessel) | Not Started | 6 | 6d | 2022-10-17 | 2022-10-24 | 125, 126, 127, 129, 131, 132, 133, 134, 135, 136 | 0% |  |  | $6000 estimated for 20' container purchase with delivery. PY3 container procurement was 6k. | 932 |  | 2022-10-17 | 2022-10-24 | 0
138 | 1.2 | 1.2.1.6.2.21 | C | Crate Drill Heads, Spare Parts to PTH (Comsur) - DNF | Not Started | 6 | 6d | 2023-04-10 | 2023-04-17 | 225 | 0% | Confirm McMurdo/Pole multi-year DNF storage space |  |  | 806 |  | 2023-04-10 | 2023-04-17 | 0
139 | 1.2 | 1.2.1.6.2.22 | C | Crate Control Systems Components Shipment 2 - DNF (Comsur) | Started | 6 | 7d | 2023-07-13 | 2023-07-21 | 210, 459, 496, 541, 618, 619 | 96% |  |  | Collapsible Bulk Container, Black, 48 inH x 45 inL x 41 inW, 1EA w/ lid $838 W.W. Grainger Item #36XE25 & #1XGG9 | 738 |  | 2023-07-13 | 2023-07-21 | 0
140 | 1.2 | 1.2.1.6.2.23 | C | Crate Elect. Distribution System Components (ComSur) | Not Started | 6 | 3d | 2023-07-28 | 2023-08-01 | 429 | 0% |  |  |  | 731 |  | 2023-07-28 | 2023-08-01 | 0
141 | 1.2 | 1.2.1.6.2.24 | C | Crate MDS Internal Hoses & Spares Resupply (FS2 Resupply Container - Comsur) | Started | 6 | 15d | 2024-06-06 | 2024-06-26 | 705, 709 | 50% |  |  | Collapsible Bulk Container, Black, 34 inH x 32 inL x 30 inW, 1EA w/ lid $425.38 W.W. Grainger Item #8CA51 & #9GFT8 | 342 |  | 2024-06-06 | 2024-06-26 | 0
142 | 1.2 | 1.2.1.6.2.25 | C | Crate Drill Filtration Resupply (FS2 Resupply Container - Comsur) | Started | 6 | 7d | 2024-07-04 | 2024-07-12 | 187 | 80% |  |  |  | 342 |  | 2024-07-04 | 2024-07-12 | 0
143 | 1.2 | 1.2.1.6.2.26 | C | Crate FS2 SES Interconnect Resupply (FS2 Resupply Container - Comsur) | Not Started | 6 | 10d | 2024-05-16 | 2024-05-29 | 705 | 0% |  |  |  | 342 |  | 2024-05-16 | 2024-05-29 | 0
144 | 1.2 | 1.2.1.6.2.27 | C | Crate MHP/PHS Replacements & Spares (FS2 Resupply Container - Comsur) | Started | 6 | 8d | 2024-07-04 | 2024-07-15 | 187, 181 | 50% |  |  | $250 estimated for packaging materials | 342 |  | 2024-07-04 | 2024-07-15 | 0
145 | 1.2 | 1.2.1.6.2.28 | C | Load FS2 Resupply Container (FS2 Comsur) | Not Started | 6 | 7d | 2024-07-16 | 2024-07-24 | 141, 142, 143, 144 | 0% |  |  |  | 342 |  | 2024-07-16 | 2024-07-24 | 0
146 | 1.2 | 1.2.1.6.2.29 | C | Crate Repair/Replacement Components Resupply (FS2 Resupply DNF - Comsur) | Not Started | 6 | 6d | 2024-07-11 | 2024-07-18 | 403 | 0% |  |  | Cargo estimates from John Arnolde (Logistics Mgr, PSL): $7,000 - Dedicated truckload ($4,375 alternative, but not reliable, so using the $7k) $ 800 - Typical 4'x4'x8' Crate (weight ~1,500#) $ 300 - Crate Materials (4'x4'x8') 1 - crate | 482 |  | 2024-07-11 | 2024-07-18 | 0
147 | 1.2 | 1.2.1.6.2.30 | C | Crate Control Systems Components Shipment 3 - DNF (Comsur) | Started | 6 | 7d | 2025-05-26 | 2025-06-03 | 328 | 96% |  |  |  | 257 |  | 2025-05-26 | 2025-06-03 | 0
148 | 1.2 | 1.2.1.6.2.31 | C | Load FS3 Resupply Container (Comsur) | Not Started | 6 | 7d | 2025-07-14 | 2025-07-22 | 214 | 0% |  |  |  | 222 |  | 2025-07-14 | 2025-07-22 | 0
149 | 1.2 | 1.2.1.6.3 | P | Drill Shipping | Not Started | 5 | 712d | 2022-11-01 | 2025-08-01 |  | 0% |  |  |  | 215 |  | 2022-11-01 | 2025-08-01 | 0
150 | 1.2 | 1.2.1.6.3.1 | C | FY23 - Ship Control Systems Components ARA Drill DNF Shipment (Vessel) | Started | 6 | 0 | 2022-11-01 | 2022-11-01 | 128, 130, 137, 111 | 96% |  |  | Estimated based on November 2021 trucking invoice (SEKO) - October '22 is a full 53' trailer load andon 2021 Reynolds & Reynolds loading support invoice | 927 |  | 2022-11-01 | 2022-11-01 | 0
151 | 1.2 | 1.2.1.6.3.2 | C | FY23 - Ship Container C (Vessel) | Started | 6 | 0 | 2022-11-01 | 2022-11-01 | 137, 111 | 96% |  |  | Estimated based on November 2021 trucking invoice (SEKO) - October '22 is a full 53' trailer load andon 2021 Reynolds & Reynolds loading support invoice | 927 |  | 2022-11-01 | 2022-11-01 | 0
152 | 1.2 | 1.2.1.6.3.3 | C | FY24 - Ship Control Systems Components Shipment 2 - DNF (Comsur) | Started | 6 | 0 | 2023-08-01 | 2023-08-01 | 140, 112, 139 | 96% |  |  | Estimated based on November 2021 trucking invoice (SEKO) - August '23 is a partial truck load | 731 |  | 2023-08-01 | 2023-08-01 | 0
153 | 1.2 | 1.2.1.6.3.4 | C | FY24 - Ship Drill Heads X, Y & R - DNF (Comsur) | Not Started | 6 | 0 | 2023-08-01 | 2023-08-01 | 138, 112 | 0% |  |  | Estimated based on November 2021 trucking invoice (SEKO) - August '24 is a quarter truck load | 731 |  | 2023-08-01 | 2023-08-01 | 0
154 | 1.2 | 1.2.1.6.3.5 | C | FY25 - Ship Control Systems Components Shipment 3 - DNF (Comsur) | Not Started | 6 | 0 | 2024-08-01 | 2024-08-01 | 114, 146 | 0% |  |  | Estimated based on November 2021 trucking invoice (SEKO) - August '24 is a quarter truck load | 473 |  | 2024-08-01 | 2024-08-01 | 0
155 | 1.2 | 1.2.1.6.3.6 | C | FY25 - Refit Resupply Container (Comsur) | Not Started | 6 | 0 | 2024-08-01 | 2024-08-01 | 430, 114, 145 | 0% |  |  | Estimated based on November 2021 trucking invoice (SEKO) - August '24 is a quarter truck load | 342 |  | 2024-08-01 | 2024-08-01 | 0
156 | 1.2 | 1.2.1.6.3.7 | C | FY25 - Ship 8' Resupply Container (Comsur) | Not Started | 6 | 0 | 2025-08-01 | 2025-08-01 | 431, 116, 148 | 0% |  |  | Estimated based on November 2021 trucking invoice (SEKO) - August '25 is a quarter truck load | 215 |  | 2025-08-01 | 2025-08-01 | 0
157 | 1.2 | 1.2.1.6.3.8 | C | FY26 - Ship DNF Resupply Crate (Comsur) | Not Started | 6 | 0 | 2025-08-01 | 2025-08-01 | 431, 116, 147 | 0% |  |  | Estimated based on November 2021 trucking invoice (SEKO) - August '25 is a quarter truck load | 215 |  | 2025-08-01 | 2025-08-01 | 0
158 | 1.2 | 1.2.1.6.4 | P | Installation Shipment Prep | Not Started | 5 | 733d | 2022-09-07 | 2025-07-07 |  | 0% |  | Deployment Lead |  | 233 |  | 2022-09-07 | 2025-07-07 | 0
159 | 1.2 | 1.2.1.6.4.1 | C | Crate Sensor Handling Structure | Not Started | 6 | 18d | 2022-09-07 | 2022-09-30 | 1675 | 0% |  | Deployment Lead |  | 948 |  | 2022-09-07 | 2022-09-30 | 0
160 | 1.2 | 1.2.1.6.4.2 | C | Crate Installation Kits | Not Started | 6 | 14d | 2023-06-21 | 2023-07-10 | 1692 | 0% |  | Deployment Lead | 7x 34"H x 48"L x 40"Wx 7crates at $699/each Grainger 1XGG6 | 747 |  | 2023-06-21 | 2023-07-10 | 0
161 | 1.2 | 1.2.1.6.4.3 | C | Crate String Weights | Not Started | 6 | 5d | 2023-06-21 | 2023-06-27 | 1692 | 0% |  | Deployment Lead | 2x $517/each Collapsible Bulk Container, Black, 34 inH x 48 inL x 45 inW, 1EA Item # 39H823 | 756 |  | 2023-06-21 | 2023-06-27 | 0
162 | 1.2 | 1.2.1.6.4.4 | C | Crate Science Equipment FS2 (SPAT, IME, Pressure Sensors, Laser Rangers) | Not Started | 6 | 5d | 2024-06-06 | 2024-06-12 | 1710, 1721, 3152 | 0% |  | Deployment Lead | $1317 estimated for three 40" x 48" x 25" bulk containers with lids to package hardware for shipping | 508 |  | 2024-06-06 | 2024-06-12 | 0
163 | 1.2 | 1.2.1.6.4.5 | C | Crate Science Equipment FS3 | Not Started | 6 | 5d | 2025-07-01 | 2025-07-07 |  | 0% |  | Deployment Lead | $371/each estimated for two 45" x 48" x 44" bulk containers with lids to package hardware for shipping | 233 |  | 2025-07-01 | 2025-07-07 | 0
164 | 1.2 | 1.2.1.6.5 | P | Installation Shipping | Not Started | 5 | 712d | 2022-11-01 | 2025-08-01 |  | 0% |  | Deployment Lead |  | 215 |  | 2022-11-01 | 2025-08-01 | 0
165 | 1.2 | 1.2.1.6.5.1 | C | FY23 - Ship Sensor Handling Structure (Vessel) | Not Started | 6 | 0 | 2022-11-01 | 2022-11-01 | 159, 111SS | 0% |  | Deployment Lead | DHF ships on truck with Container C | 927 |  | 2022-11-01 | 2022-11-01 | 0
166 | 1.2 | 1.2.1.6.5.2 | C | FY24 - Ship Installation Kits (Vessel) | Not Started | 6 | 0 | 2023-11-01 | 2023-11-01 | 160, 113SS | 0% |  | Deployment Lead |  | 666 |  | 2023-11-01 | 2023-11-01 | 0
167 | 1.2 | 1.2.1.6.5.3 | C | FY24 - Ship String Weights | Not Started | 6 | 0 | 2023-11-01 | 2023-11-01 | 161, 113SS | 0% |  | Deployment Lead |  | 666 |  | 2023-11-01 | 2023-11-01 | 0
168 | 1.2 | 1.2.1.6.5.4 | C | FY25 - Ship Science Crate FS2 (SPAT, IME, Pressure Sensors, Laser Rangers) | Not Started | 6 | 0 | 2024-08-01 | 2024-08-01 | 162, 114SS | 0% |  | Deployment Lead |  | 473 |  | 2024-08-01 | 2024-08-01 | 0
169 | 1.2 | 1.2.1.6.5.5 | C | FY26 - Ship Science Crate FS3 | Not Started | 6 | 0 | 2025-08-01 | 2025-08-01 | 163, 116SS | 0% |  | Deployment Lead |  | 215 |  | 2025-08-01 | 2025-08-01 | 0
170 | 1.2 | 1.2.2 | P | Thermal Plant - Off-ice | Started | 3 | 987d | 2020-10-01 | 2024-07-17 |  | 51% |  |  |  | 483 |  | 2020-10-01 | 2024-07-17 | 0
171 | 1.2 | 1.2.2.1 | P | Main Heating Plants | Started | 4 | 897d | 2021-02-04 | 2024-07-17 |  | 63% |  |  |  | 483 |  | 2021-02-04 | 2024-07-17 | 0
172 | 1.2 | 1.2.2.1.1 | C | Identify Upgrade-Replacements, Spares | Complete | 5 | 401d | 2021-02-04 | 2022-08-18 |  | 100% |  |  |  | 979 |  | 2021-02-04 | 2022-08-18 | 0
173 | 1.2 | 1.2.2.1.2 | C | Assemble and Test Components (Flowmeters, PRV & Control boxes ) | Started | 5 | 37d | 2022-04-01 | 2022-05-23 |  | 85% |  |  |  | 1042 |  | 2022-04-01 | 2022-05-23 | 0
174 | 1.2 | 1.2.2.1.3 | C | Procure MHP Chimney Stacks (PY4) | Not Started | 5 | 30d | 2022-04-12 | 2022-05-23 |  | 0% |  |  | Vessel FY23. Deliverable supports FS1 tasking. | 1042 |  | 2022-04-12 | 2022-05-23 | 0
175 | 1.2 | 1.2.2.1.4 | C | Design and Construct MHP Flush & Pressure Test Kit | Not Started | 5 | 32d | 2022-04-15 | 2022-05-30 |  | 0% |  |  |  | 927 |  | 2022-04-15 | 2022-05-30 | 0
176 | 1.2 | 1.2.2.1.5 | C | Build Electronics Kit for MHP1, Heater 7 | Not Started | 5 | 21d | 2022-05-18 | 2022-06-15 |  | 0% |  |  | ComSur for FY25 season. Deliverable supports FS2 tasking. | 1025 |  | 2022-05-18 | 2022-06-15 | 0
177 | 1.2 | 1.2.2.1.6 | C | Procure MHP Upgrade, Sub-Components, Spares (PY5) | Not Started | 5 | 60d | 2023-04-03 | 2023-06-23 | 825FS +6w | 0% |  |  | Comsur for FY23 season. Deliverable supports FS1 tasking. | 758 |  | 2023-04-03 | 2023-06-23 | 0
178 | 1.2 | 1.2.2.1.7 | C | Develop HPU2 Integrate Plan | Not Started | 5 | 30d | 2024-04-25 | 2024-06-05 | 886FS +10w | 0% |  |  | After FS1 eval | 483 |  | 2024-04-25 | 2024-06-05 | 0
179 | 1.2 | 1.2.2.1.8 | C | Procure and Assemble HPU2 Integration Components | Not Started | 5 | 30d | 2024-06-06 | 2024-07-17 | 178 | 0% |  |  | Comsur 2024 | 483 |  | 2024-06-06 | 2024-07-17 | 0
180 | 1.2 | 1.2.2.1.9 | C | Combustion Analyzers, 3x, Spec-Procure-Validate | Not Started | 5 | 15d | 2022-05-02 | 2022-05-20 |  | 0% | existing equip stopped working, plan to address this in PY4 |  | Vessel FY23. Deliverable supports FS1 tasking. | 1043 |  | 2022-05-02 | 2022-05-20 | 0
181 | 1.2 | 1.2.2.1.10 | C | Procure MHP Upgrade, Sub-Components, Spares (PY6) | Not Started | 5 | 30d | 2024-05-09 | 2024-06-19 | 886FS +12w | 0% |  |  | Vessel FY23. Deliverable supports FS1 tasking. | 342 |  | 2024-05-09 | 2024-06-19 | 0
182 | 1.2 | 1.2.2.2 | P | Pre-Heat System | Started | 4 | 592d | 2022-03-24 | 2024-07-03 |  | 66% |  |  |  | 493 |  | 2022-03-24 | 2024-07-03 | 0
183 | 1.2 | 1.2.2.2.1 | C | Refine PHS Plumbing Upgrade Design | Started | 5 | 20d | 2022-06-02 | 2022-06-29 |  | 69% |  |  | Vessel FY23. Deliverable supports FS1 tasking. | 1015 |  | 2022-06-02 | 2022-06-29 | 0
184 | 1.2 | 1.2.2.2.2 | C | Identify Upgrade, Replacements & Spares Components | Not Started | 5 | 30d | 2022-06-02 | 2022-07-13 |  | 0% |  |  | Vessel FY23. Deliverable supports FS1 tasking. | 1005 |  | 2022-06-02 | 2022-07-13 | 0
185 | 1.2 | 1.2.2.2.3 | C | Procure and Upgrade Control Boxes (PY4) | Started | 5 | 45d | 2022-03-24 | 2022-05-25 |  | 85% |  |  | Comsur for FY25 season. Deliverable supports FS2 tasking. | 1040 |  | 2022-03-24 | 2022-05-25 | 0
186 | 1.2 | 1.2.2.2.4 | C | Procure and Upgrade Control Boxes (PY6) | Started | 5 | 30d | 2024-05-23 | 2024-07-03 | 886FS +14w | 85% |  |  | Comsur for FY25 season. Deliverable supports FS2 tasking. | 493 |  | 2024-05-23 | 2024-07-03 | 0
187 | 1.2 | 1.2.2.2.5 | C | Procure Upgrade, Sub-Components, Spares (PY6) | Started | 5 | 30d | 2024-05-23 | 2024-07-03 | 886FS +14w | 85% |  |  | Comsur for FY25 season. Deliverable supports FS2 tasking. | 342 |  | 2024-05-23 | 2024-07-03 | 0
188 | 1.2 | 1.2.2.3 | P | Fuel Storage and Delivery | Started | 4 | 937d | 2020-10-01 | 2024-05-08 |  | 31% |  |  | Fuel Storage & Delivery is based on the following assumptions: 5,000 fuel tank fleet - is still at NPX, and will be available to the project, minimally, in FY25 and intensively in FY26 The Fuel Tower - currently in use by WISSARD will be available. Logistics need to be planned to traverse this equipment to NPX in FY23 season. | 533 |  | 2020-10-01 | 2024-05-08 | 0
189 | 1.2 | 1.2.2.3.1 | C | Fuel Systems: Review & Redesign (5k Tank-Tower) | Complete | 5 | 80d | 2020-10-01 | 2021-01-20 |  | 100% |  |  |  | 897 |  | 2020-10-01 | 2021-01-20 | 0
190 | 1.2 | 1.2.2.3.2 | C | Procurement (Hose, Valves, Sensors, Controls Etc.) | Started | 5 | 229d | 2021-10-04 | 2022-08-18 | 193FS +210d | 10% |  |  |  | 979 |  | 2021-10-04 | 2022-08-18 | 0
191 | 1.2 | 1.2.2.3.3 | C | Fuel Tower: Review Design & Specs, Field Inputs - Develop Plan | Complete | 5 | 30d | 2020-11-02 | 2020-12-11 | 189SS +22d | 100% |  |  |  | 927 |  | 2020-11-02 | 2020-12-11 | 0
192 | 1.2 | 1.2.2.3.4 | C | Fuel Tower: Redesign Components | Complete | 5 | 30d | 2020-11-02 | 2020-12-11 | 191SS | 100% |  |  |  | 979 |  | 2020-11-02 | 2020-12-11 | 0
193 | 1.2 | 1.2.2.3.5 | C | Fuel Tower: Final Design Review | Complete | 5 | 0 | 2020-12-11 | 2020-12-11 | 192 | 100% |  |  |  | 1050 |  | 2020-12-11 | 2020-12-11 | 0
194 | 1.2 | 1.2.2.3.6 | C | Fuel Tower: Procure Upgrade-Replacements, Spares | Started | 5 | 60d | 2022-02-07 | 2022-04-29 | 193FS +300d | 33% |  | PSL_Engineer | $5927 components $14241 external fuel hose Quote- and Catalog- based see 1.2.2.3 BOE | 927 |  | 2022-02-07 | 2022-04-29 | 0
195 | 1.2 | 1.2.2.3.7 | C | Fuel Sled Panel Updates - Interface Integration | Not Started | 5 | 83d | 2022-05-30 | 2022-09-21 | 193FS +380d | 0% |  |  |  | 955 |  | 2022-05-30 | 2022-09-21 | 0
196 | 1.2 | 1.2.2.3.8 | C | Procure ARA Fueling Hose & Nozzle (PY5) | Not Started | 5 | 20d | 2023-03-20 | 2023-04-14 | 825FS +4w | 0% |  |  |  | 788 |  | 2023-03-20 | 2023-04-14 | 0
197 | 1.2 | 1.2.2.3.9 | C | Procure Racor Fuel Filter Elements and Gauges Replacements (PY5) | Not Started | 5 | 20d | 2023-03-20 | 2023-04-14 | 196SS | 0% |  |  |  | 808 |  | 2023-03-20 | 2023-04-14 | 0
198 | 1.2 | 1.2.2.3.10 | C | Procure Fuel system Upgrade/Maintenance Subcomponents (PY6) | Not Started | 5 | 20d | 2024-04-11 | 2024-05-08 | 886FS +8w | 0% |  |  |  | 513 |  | 2024-04-11 | 2024-05-08 | 0
199 | 1.2 | 1.2.2.3.11 | C | Procure MHP Fuel Heat Exchangers Replacements (PY6) | Not Started | 5 | 20d | 2024-04-11 | 2024-05-08 | 198SS | 0% |  |  |  | 533 |  | 2024-04-11 | 2024-05-08 | 0
200 | 1.2 | 1.2.3 | P | Tower Operations Site (TOS) - Off-ice | Started | 3 | 1764d | 2018-10-01 | 2025-07-11 |  | 68% |  |  |  | 229 |  | 2018-10-01 | 2025-07-11 | 0
201 | 1.2 | 1.2.3.1 | P | TOS and Tower | Started | 4 | 1655d | 2019-03-01 | 2025-07-11 |  | 46% |  |  |  | 229 |  | 2019-03-01 | 2025-07-11 | 0
202 | 1.2 | 1.2.3.1.1 | C | Reassess Down Hole Loads - String/DOM Configurations | Complete | 5 | 306d | 2019-03-01 | 2020-05-01 |  | 100% |  |  |  | 1508 |  | 2019-03-01 | 2020-05-01 | 0
203 | 1.2 | 1.2.3.1.2 | C | Perform Structural Review of Tower & Components | Complete | 5 | 30d | 2021-05-03 | 2021-06-11 | 202FS +260d | 100% |  |  |  | 1248 |  | 2021-05-03 | 2021-06-11 | 0
204 | 1.2 | 1.2.3.1.3 | C | Crescent & Belt Refurbishment (4 ea) | Not Started | 5 | 20d | 2022-06-01 | 2022-06-28 |  | 0% |  |  |  | 927 |  | 2022-06-01 | 2022-06-28 | 0
205 | 1.2 | 1.2.3.1.4 | C | Procure Replacement Tower Hoist | Complete | 5 | 40d | 2021-06-14 | 2021-08-06 | 203 | 100% |  |  |  | 1248 |  | 2021-06-14 | 2021-08-06 | 0
206 | 1.2 | 1.2.3.1.5 | C | Crescent Emergency Repair Kit Assembly (PY6) | Not Started | 5 | 35d | 2024-03-14 | 2024-05-01 | 886FS +4w | 0% |  |  |  | 538 |  | 2024-03-14 | 2024-05-01 | 0
207 | 1.2 | 1.2.3.1.6 | C | Examine Interface between Dust Logger and Tower & Address as Needed | Not Started | 5 | 30d | 2023-06-26 | 2023-08-04 | 825FS +18w | 0% |  |  |  | 728 |  | 2023-06-26 | 2023-08-04 | 0
208 | 1.2 | 1.2.3.1.7 | P | TOS Load Cells | Not Started | 5 | 274d | 2022-03-15 | 2023-03-31 |  | 0% |  |  |  | 818 |  | 2022-03-15 | 2023-03-31 | 0
209 | 1.2 | 1.2.3.1.7.1 | C | Load Cells Procured | Not Started | 6 | 0 | 2022-03-15 | 2022-03-15 |  | 0% |  |  |  | 1092 |  | 2022-03-15 | 2022-03-15 | 0
210 | 1.2 | 1.2.3.1.7.2 | C | Calibration Load Cell | Not Started | 6 | 20d | 2023-02-20 | 2023-03-17 | 825 | 0% |  |  |  | 818 |  | 2023-02-20 | 2023-03-17 | 0
211 | 1.2 | 1.2.3.1.7.3 | C | Calibration Load Cell Rigging | Not Started | 6 | 10d | 2023-03-20 | 2023-03-31 | 210 | 0% |  |  |  | 818 |  | 2023-03-20 | 2023-03-31 | 0
212 | 1.2 | 1.2.3.1.8 | C | Identify/Procure: TOS & Tower Hardware, Repair Parts (PY5) | Started | 5 | 35d | 2023-06-12 | 2023-07-28 | 825FS +16w | 4% |  |  | Driller tape: 4 cases @ 30 rolls/case = 120 rolls $50/roll -> $6k | 733 |  | 2023-06-12 | 2023-07-28 | 0
213 | 1.2 | 1.2.3.1.9 | C | Identify/Procure: TOS & Tower Hardware, Repair Parts (PY6) | Started | 5 | 35d | 2024-06-06 | 2024-07-24 | 886FS +16w | 4% |  |  | Driller tape: 4 cases @ 30 rolls/case = 120 rolls $50/roll -> $6k | 478 |  | 2024-06-06 | 2024-07-24 | 0
214 | 1.2 | 1.2.3.1.10 | C | Identify/Procure: TOS & Tower Hardware, Repair Parts (PY7) | Started | 5 | 25d | 2025-06-09 | 2025-07-11 | 1246FS +16w | 4% |  |  | Driller tape: 50 rolls/hole x 7 holes = 350 rolls Plus 3 cases @ 30 rolls/case = 440 rolls $50/roll -> $22k | 222 |  | 2025-06-09 | 2025-07-11 | 0
215 | 1.2 | 1.2.3.2 | P | Drillheads | Started | 4 | 1050d | 2019-04-01 | 2023-04-07 |  | 90% |  |  |  | 813 |  | 2019-04-01 | 2023-04-07 | 0
216 | 1.2 | 1.2.3.2.1 | C | Initial assessment of 3 drillheads | Complete | 5 | 120d | 2019-04-01 | 2019-09-13 |  | 100% | Initial assessment good, some re-anodizing required |  |  | 818 |  | 2019-04-01 | 2019-09-13 | 0
217 | 1.2 | 1.2.3.2.2 | C | Drillhead and software subsystem testing | Complete | 5 | 20d | 2021-04-16 | 2021-05-13 |  | 100% | Activity restarted 11/19. Qiang is lead engineer. Some progress in May. |  | Test equipment, cabling, computer. | 339 |  | 2021-04-16 | 2021-05-13 | 0
218 | 1.2 | 1.2.3.2.3 | C | Rework/rewrite drillhead software | Complete | 5 | 45d | 2021-03-12 | 2021-05-13 | 217FF | 100% | Major achievements accomplished in May, still working on data processing |  |  | 384 |  | 2021-03-12 | 2021-05-13 | 0
219 | 1.2 | 1.2.3.2.4 | C | Recondition and calibrate Drillhead 1 | Complete | 5 | 311d | 2020-05-25 | 2021-08-02 | 216FS +180d, 218FF -30d | 100% | remaining: pressure and caliper tests |  | From PY09 Gen1 Budget: CE: $16,500 - PM Parts & Upgrades, Incl Caliper Replacement, 4" Collars, Etc ----------------------------------------- M&S: $ 4,000 - Shop labor (PSL) | 638 |  | 2020-05-25 | 2021-08-02 | 0
220 | 1.2 | 1.2.3.2.5 | C | Recondition and calibrate Drillhead 2 | Complete | 5 | 271d | 2020-07-20 | 2021-08-02 | 219FF | 100% |  |  |  | 909 |  | 2020-07-20 | 2021-08-02 | 0
221 | 1.2 | 1.2.3.2.6 | C | Recondition and calibrate Drillhead 3 | Complete | 5 | 231d | 2020-09-14 | 2021-08-02 | 220FF | 100% |  |  |  | 1140 |  | 2020-09-14 | 2021-08-02 | 0
222 | 1.2 | 1.2.3.2.7 | C | Update Drillheads for Cable | Not Started | 5 | 45d | 2022-03-16 | 2022-05-17 | 221FS +161d | 0% |  |  |  | 979 |  | 2022-03-16 | 2022-05-17 | 0
223 | 1.2 | 1.2.3.2.8 | C | Pressure Test Drillhead Hanger & Spare Hose | Not Started | 5 | 45d | 2022-03-16 | 2022-05-17 | 222FF | 0% |  |  |  | 1024 |  | 2022-03-16 | 2022-05-17 | 0
224 | 1.2 | 1.2.3.2.9 | C | Drillheads: Drillheads Updated and Hose Pressure Tested | Not Started | 5 | 0 | 2022-05-31 | 2022-05-31 | 223FS +10d | 0% |  |  |  | 1014 |  | 2022-05-31 | 2022-05-31 | 0
225 | 1.2 | 1.2.3.2.10 | C | Drillheads: Prepare Crates, Spares, Tools, & Docs x3 | Not Started | 5 | 15d | 2023-03-20 | 2023-04-07 | 224, 825FS +4w | 0% |  |  |  | 806 |  | 2023-03-20 | 2023-04-07 | 0
226 | 1.2 | 1.2.3.3 | P | Reels & Winches | Started | 4 | 945d | 2020-11-02 | 2024-06-19 |  | 59% |  |  |  | 503 |  | 2020-11-02 | 2024-06-19 | 0
227 | 1.2 | 1.2.3.3.1 | C | Main Drill Cable Reel (at PSL): Rebuild, Upgrade, Test | Complete | 5 | 80d | 2020-11-02 | 2021-02-19 |  | 100% |  |  | Level wind & Control Bearings - $ ?? Gearbox - $850 Ball Screw - $680 Linear Rail - $1,620 Rail Guides - $314 (x2) Elec Motor - $1625 (x2) Motors & gear box $3,000 Slip Ring - $ ?? Brake System $17,500 Quotes received from: McMaster-Carr, MSC, BBS | 1368 |  | 2020-11-02 | 2021-02-19 | 0
228 | 1.2 | 1.2.3.3.2 | C | Return Water Cable Reel (at PSL): Rebuild, Upgrade, Test | Complete | 5 | 68d | 2021-10-02 | 2022-01-04 |  | 100% |  |  | Slip ring Brake System | -53 |  | 2021-10-02 | 2022-01-04 | 0
229 | 1.2 | 1.2.3.3.3 | C | Main Supply Hose Reel (Big Red at NPX) - Procure Replacement Parts | Started | 5 | 582d | 2022-01-05 | 2024-04-02 | 228 | 75% |  |  | Rotary Union ~$5,000 Limit Switches ~$2,000 Brake Components ~$2,000 Plumbing Refurb ~$2,000 Heating Blanket System? FailSafe Disc Brake - $22,986 Gearbox - $ 850 Ball Screw - $1,700 Linear Rail - $4,050 (x2) Rail Guides - $ 314 (x4) Elec Motor - $2,900 Main Bearing - $5,050 (x2) ----------------------------- Total Cost $47,892 (25% factor = $11,973) | -53 |  | 2022-01-05 | 2024-04-02 | 0
230 | 1.2 | 1.2.3.3.4 | C | Return Water Hose Reel (at NPX) - Procure Replacement Parts | Started | 5 | 612d | 2022-01-05 | 2024-05-14 | 229SS | 75% |  |  | Rotary union Large Ball Valve Motor Manifold | 529 |  | 2022-01-05 | 2024-05-14 | 0
231 | 1.2 | 1.2.3.3.5 | C | TU-20 Winches (at NPX) - Plan/Procure Replacement Parts. Design/Fabricate New Axles | Complete | 5 | 60d | 2021-02-01 | 2021-04-23 |  | 100% |  |  | Recondition slip rings 2 new steel axles from Tulsa Power Electric Brake Replacement Hydraulic lift replacements | 1233 |  | 2021-02-01 | 2021-04-23 | 0
232 | 1.2 | 1.2.3.3.6 | C | Cable Tensioner (at PSL) - Procure Repair Parts | Complete | 5 | 90d | 2021-02-01 | 2021-06-04 | 231SS | 100% |  |  | New Tread | 1293 |  | 2021-02-01 | 2021-06-04 | 0
233 | 1.2 | 1.2.3.3.7 | P | Main Drill Cable Reel/Main Hose Reel Load Sharing (PY4) | Should have Started | 5 | 390d | 2021-12-20 | 2023-06-16 |  | 0% |  |  | Recondition slip rings 2 new steel axles from Tulsa Power Electric Brake Replacement Hydraulic lift replacements | 763 |  | 2021-12-20 | 2023-06-16 | 0
234 | 1.2 | 1.2.3.3.7.1 | C | Load sharing: Coordination, Design, Documentation (PY4) | Should have Started | 6 | 195d | 2021-12-20 | 2022-09-16 |  | 0% |  |  | Recondition slip rings 2 new steel axles from Tulsa Power Electric Brake Replacement Hydraulic lift replacements | 708 |  | 2021-12-20 | 2022-09-16 | 0
235 | 1.2 | 1.2.3.3.7.2 | C | Load sharing: Modeling and Software Development, Bench Testing (PY4) | Should have Started | 6 | 130d | 2021-12-20 | 2022-06-17 | 234SS | 0% |  |  | Recondition slip rings 2 new steel axles from Tulsa Power Electric Brake Replacement Hydraulic lift replacements | 693 |  | 2021-12-20 | 2022-06-17 | 0
236 | 1.2 | 1.2.3.3.7.3 | C | Load sharing: Full scale Test Setup (PY4) | Not Started | 6 | 100d | 2022-04-04 | 2022-08-19 | 235SS +75d | 0% |  |  | Recondition slip rings 2 new steel axles from Tulsa Power Electric Brake Replacement Hydraulic lift replacements | 978 |  | 2022-04-04 | 2022-08-19 | 0
237 | 1.2 | 1.2.3.3.7.4 | C | Load sharing: Full-scale Testing - Diameter Correction and Prelim Load Share (PY4) | Not Started | 6 | 140d | 2022-03-14 | 2022-09-23 | 235SS +60d | 0% |  |  | Recondition slip rings 2 new steel axles from Tulsa Power Electric Brake Replacement Hydraulic lift replacements | 863 |  | 2022-03-14 | 2022-09-23 | 0
238 | 1.2 | 1.2.3.3.7.5 | C | Load Sharing: Full-scale Testing - Load Share & Tuning (PY5) | Not Started | 6 | 90d | 2023-02-13 | 2023-06-16 | 237FS +100d | 0% |  |  | Recondition slip rings 2 new steel axles from Tulsa Power Electric Brake Replacement Hydraulic lift replacements | 763 |  | 2023-02-13 | 2023-06-16 | 0
239 | 1.2 | 1.2.3.3.8 | C | Reels & Winches: Reel Load Sharing Testing Complete | Not Started | 5 | 0 | 2023-06-16 | 2023-06-16 | 234, 235, 236, 237, 238 | 0% |  |  | Recondition slip rings 2 new steel axles from Tulsa Power Electric Brake Replacement Hydraulic lift replacements | 763 |  | 2023-06-16 | 2023-06-16 | 0
240 | 1.2 | 1.2.3.3.9 | C | Reels & Winches: Drill Reels Sliprings - Final Testing & Prep | Not Started | 5 | 10d | 2023-05-01 | 2023-05-12 | 825FS +10w | 0% |  |  | Recondition slip rings 2 new steel axles from Tulsa Power Electric Brake Replacement Hydraulic lift replacements | 728 |  | 2023-05-01 | 2023-05-12 | 0
241 | 1.2 | 1.2.3.3.10 | C | Reels & Winches: TU20 Sliprings - Spec, Procure, Test | Not Started | 5 | 12w | 2023-05-15 | 2023-08-04 | 240 | 0% |  |  | Recondition slip rings 2 new steel axles from Tulsa Power Electric Brake Replacement Hydraulic lift replacements | 728 |  | 2023-05-15 | 2023-08-04 | 0
242 | 1.2 | 1.2.3.3.11 | C | Reels & Winches: Reel Components & Spares (PY6). TU20 brakes | Not Started | 5 | 12w | 2024-03-28 | 2024-06-19 | 886FS +6w | 0% |  |  | Recondition slip rings 2 new steel axles from Tulsa Power Electric Brake Replacement Hydraulic lift replacements | 503 |  | 2024-03-28 | 2024-06-19 | 0
243 | 1.2 | 1.2.3.4 | P | Downhole Main Drill Hose | Complete | 4 | 561d | 2018-10-01 | 2020-11-23 |  | 100% |  |  |  | 1432 |  | 2018-10-01 | 2020-11-23 | 0
244 | 1.2 | 1.2.3.4.1 | C | Request Budgetary Cost Estimate | Complete | 5 | 3d | 2018-10-01 | 2018-10-03 |  | 100% |  |  |  | 1990 |  | 2018-10-01 | 2018-10-03 | 0
245 | 1.2 | 1.2.3.4.2 | C | Confirm & Specify Drill Hose | Complete | 5 | 40d | 2019-10-01 | 2019-11-25 |  | 100% |  |  | Analyze new downhole loads - 5 days Adjust tension members in yellow hose formula - 10 days | 1446 |  | 2019-10-01 | 2019-11-25 | 0
246 | 1.2 | 1.2.3.4.3 | C | Procure drill hose (Manufacture by IVG) | Complete | 5 | 240d | 2019-09-17 | 2020-08-17 | 247, 245SS -10d | 100% | Production started end of Feb, COVID factory shut down 3/27, restart in April, still on schedule |  | Work with IVG to strengthen tension member in yellow hose (We might not need to do this and can just order yellow stripe hose as is - depends on new load requirements) Quote and order drill hose | 1496 |  | 2019-09-17 | 2020-08-17 | 0
247 | 1.2 | 1.2.3.4.4 | C | Procurement - Down Payment (~20%) | Complete | 5 | 1d | 2019-09-13 | 2019-09-13 |  | 100% | Pulled forward to take advantage of discount offered by IVG - Submit PO by 9/15 and receive 10% off |  |  | 1497 |  | 2019-09-13 | 2019-09-13 | 0
248 | 1.2 | 1.2.3.4.5 | C | Procurement - Final Payment (Remainder), Ship to PSL | Complete | 5 | 1d | 2020-08-18 | 2020-08-18 | 246 | 100% | Pulled forward to take advantage of discount offered by IVG - Submit PO by 9/15 and receive 10% off |  | Added $20,000 for Shipment to PSL | 1496 |  | 2020-08-18 | 2020-08-18 | 0
249 | 1.2 | 1.2.3.4.6 | C | Manufacture Strain Reliefs (at PSL) | Complete | 5 | 80d | 2019-09-13 | 2020-01-02 |  | 100% | First article received, PO submitted, parts COVID delay, due mid May |  | Convert drawings to CAD models Make key changes to strain relief design, draw Fabricate at PSL Ship strain reliefs to IVG Labor = $56,672 ($62,340) (per Tom Harrington, PSL Shop Supervisor) Material = $28,328 ($31,160) Shipping to IVG = $3,000 ------------------------------- $96,500 (w/10% MOE) 46 Strain Reliefs (23 hose sections) 8 aluminum sections/relief (16 total) | 1432 |  | 2019-09-13 | 2020-01-02 | 0
250 | 1.2 | 1.2.3.4.7 | C | Ship Strain Reliefs to Italy (Mnftr Install on Hose) | Complete | 5 | 140d | 2020-01-03 | 2020-07-16 | 249 | 100% | Shipping early June |  | Cargo estimates from John Arnolde (Logistics Mgr, PSL): $4,375 - Dedicated Truckload $ 800 - Typical 4'x4'x8' Crate (weight ~1,500#) $ 300 - Crate Materials (4'x4'x8') 2 - crates - shipped internationally $600 materials, $1,200 shipping | 1519 |  | 2020-01-03 | 2020-07-16 | 0
251 | 1.2 | 1.2.3.4.8 | C | Prepare Hose at PSL, Crate for Shipment, Hold 1 Year | Complete | 5 | 5d | 2020-11-17 | 2020-11-23 | 250FS +87d, 248 | 100% |  |  |  | 1432 |  | 2020-11-17 | 2020-11-23 | 0
252 | 1.2 | 1.2.3.4.9 | C | Ship Drill Hose from IVG (ComSur-CHC, Vessel-ZCM, Outdoor storage ZCM) | Complete | 5 | 1d | 2020-10-30 | 2020-10-30 | 250FS +75d | 100% | Drop Ship to CHC by 11/15/20 Vessel to ZCM 11/20 - 2/21 Store (outdoor) ZCM 2/21 - 1/22 Fly ZCM-NPX 1/22 Store (DNF) NPX 1/22 to 11/22 Spool on MSHR 11/22 Drilling begins 12/22 |  |  | 1448 |  | 2020-10-30 | 2020-10-30 | 0
253 | 1.2 | 1.2.3.5 | P | Downhole Main Cables | Complete | 4 | 447d | 2019-10-01 | 2021-06-16 |  | 100% |  |  |  | 1285 |  | 2019-10-01 | 2021-06-16 | 0
254 | 1.2 | 1.2.3.5.1 | C | Main Drill Cable Spec Review & Revisions | Complete | 5 | 119d | 2019-10-01 | 2020-03-13 |  | 100% | RFP still in progress |  |  | 1319 |  | 2019-10-01 | 2020-03-13 | 0
255 | 1.2 | 1.2.3.5.2 | C | Combo Cable - Spec Review & Revisions | Complete | 5 | 119d | 2019-10-01 | 2020-03-13 | 254SS | 100% | delayed, limited access |  |  | 1438 |  | 2019-10-01 | 2020-03-13 | 0
256 | 1.2 | 1.2.3.5.3 | C | Test Combo Cable (2 at PSL) | Complete | 5 | 40d | 2020-03-16 | 2020-05-08 | 255 | 100% | Testing plans delayed (COVID) |  |  | 1438 |  | 2020-03-16 | 2020-05-08 | 0
257 | 1.2 | 1.2.3.5.4 | C | Test Main Drill Cable & Unjacketed Spare | Complete | 5 | 60d | 2020-03-16 | 2020-06-05 | 256SS | 100% | Preliminary electrical tests performed, visual inspection, otherwise delayed |  |  | 1478 |  | 2020-03-16 | 2020-06-05 | 0
258 | 1.2 | 1.2.3.5.5 | C | Procure Main Drill Cable | Complete | 5 | 180d | 2020-10-08 | 2021-06-16 |  | 100% | Shipment delayed until fall 2021 |  | Quote from South Bay - Nov 12, 2018 $42.75/meter @ 3200m Cortland quote from 2008 was $80,300 - Need to confirm includes connectors, shipping, spool, etc. - Also, need 2nd quote from ?? (Cortland) | 1225 |  | 2020-10-08 | 2021-06-16 | 0
259 | 1.2 | 1.2.3.5.6 | C | Jacket Spare Cable (by vendor, currently at PSL) | Complete | 5 | 60d | 2020-06-08 | 2020-08-28 | 257 | 100% | Vendors not able to do this, will probably need to change baseline to procuring another entirely new cable as spare |  | Quote from - Cortland Cable (Doug Bentley) from 2008 was $15,800 (PO # X441652-92041 08/07/2008) I've doubled the amount quoted since it's 10 years old, inflation and material increase, as well as other vendors had no interest in doing this so an uncertainty factor. | 1478 |  | 2020-06-08 | 2020-08-28 | 0
260 | 1.2 | 1.2.3.5.7 | C | Connectors - Procure & Install, Both Cables (at vendor) | Complete | 5 | 60d | 2021-03-25 | 2021-06-16 | 258FF | 100% |  |  | Installed by Fibron (manufacturer) | 1285 |  | 2021-03-25 | 2021-06-16 | 0
261 | 1.2 | 1.2.3.5.8 | C | Spool Main Drill Cable onto Winch/Spool | Complete | 5 | 15d | 2020-08-31 | 2020-09-18 | 259 | 100% | New activity. Requires cable spooler (now at PSL) |  |  | 1478 |  | 2020-08-31 | 2020-09-18 | 0
262 | 1.2 | 1.2.3.6 | P | Design and Construct Main Hose Reel Heating System | Not Started | 4 | 165d | 2022-02-27 | 2022-10-13 | [5 empty] | 939 |  | 2022-02-27 | 2022-10-13 | 0
263 | 1.2 | 1.2.3.6.1 | P | Design, Fabricate and Test Hose Reel Heating System | Not Started | 5 | 46d | 2022-04-11 | 2022-06-13 | [5 empty] | 1027 |  | 2022-04-11 | 2022-06-13 | 0
264 | 1.2 | 1.2.3.6.1.1 | C | Connectorize Heated Blankets | Not Started | 6 | 1w | 2022-04-11 | 2022-04-15 | [5 empty] | 1027 |  | 2022-04-11 | 2022-04-15 | 0
265 | 1.2 | 1.2.3.6.1.2 | C | Attach RTDs to Inner Insulation & Heated Blankets | Not Started | 6 | 4w | 2022-04-18 | 2022-05-13 | 264 |  |  |  |  | 1027 |  | 2022-04-18 | 2022-05-13 | 0
266 | 1.2 | 1.2.3.6.1.3 | C | Design and Fab RTD Patch Panel | Not Started | 6 | 21d | 2022-05-16 | 2022-06-13 | 265 |  |  |  |  | 1027 |  | 2022-05-16 | 2022-06-13 | 0
267 | 1.2 | 1.2.3.6.2 | P | Procure Components for Hose Reel Heating System (Insulated Blankets & Tarps) | Not Started | 5 | 40d | 2022-04-02 | 2022-05-26 | [5 empty] | 1039 |  | 2022-04-02 | 2022-05-26 | 0
268 | 1.2 | 1.2.3.6.2.1 | C | Size and Procure Insulated Tarps for Inner/Outer Layers | Not Started | 6 | 20d | 2022-04-02 | 2022-04-28 | [5 empty] | 1039 |  | 2022-04-02 | 2022-04-28 | 0
269 | 1.2 | 1.2.3.6.2.2 | C | Size and Procure Outer Canvas Tarp | Not Started | 6 | 20d | 2022-04-29 | 2022-05-26 | 268 |  |  |  |  | 1039 |  | 2022-04-29 | 2022-05-26 | 0
270 | 1.2 | 1.2.3.6.3 | P | Hose Reel Heating System Testing | Not Started | 5 | 20d | 2022-02-27 | 2022-03-24 | [5 empty] | 1084 |  | 2022-02-27 | 2022-03-24 | 0
271 | 1.2 | 1.2.3.6.3.1 | C | Cold Test Hose Heating Controller System | Not Started | 6 | 4w | 2022-02-27 | 2022-03-24 | [5 empty] | 927 |  | 2022-02-27 | 2022-03-24 | 0
272 | 1.2 | 1.2.3.6.4 | P | Develop RedLion FlexEdge Controller SW functionality | Not Started | 5 | 135d | 2022-03-25 | 2022-09-29 | [5 empty] | 949 |  | 2022-03-25 | 2022-09-29 | 0
273 | 1.2 | 1.2.3.6.4.1 | C | Develop User Interface, Primarily for Blanket Setpoints, Alarm Setpoints | Not Started | 6 | 3w | 2022-03-25 | 2022-04-14 | 271 |  |  |  |  | 939 |  | 2022-03-25 | 2022-04-14 | 0
274 | 1.2 | 1.2.3.6.4.2 | C | Develop/Test Blanket Temp Control | Not Started | 6 | 4w | 2022-04-15 | 2022-05-12 | 273 |  |  |  |  | 927 |  | 2022-04-15 | 2022-05-12 | 0
275 | 1.2 | 1.2.3.6.4.3 | C | Finalize Data Logging | Not Started | 6 | 10d | 2022-05-13 | 2022-05-26 | 274 |  |  |  |  | 1019 |  | 2022-05-13 | 2022-05-26 | 0
276 | 1.2 | 1.2.3.6.4.4 | C | Develop/Test Alerting Notifications | Not Started | 6 | 10d | 2022-09-16 | 2022-09-29 | 275FS +80d |  |  |  |  | 939 |  | 2022-09-16 | 2022-09-29 | 0
277 | 1.2 | 1.2.3.6.4.5 | C | Document Subsystem | Not Started | 6 | 10d | 2022-09-16 | 2022-09-29 | 276SS |  |  |  |  | 949 |  | 2022-09-16 | 2022-09-29 | 0
278 | 1.2 | 1.2.3.6.5 | C | System Tests | Not Started | 5 | 6w | 2022-08-19 | 2022-09-29 | 274FS +70d |  |  |  |  | 927 |  | 2022-08-19 | 2022-09-29 | 0
279 | 1.2 | 1.2.3.6.6 | C | Make Installation Drawing | Not Started | 5 | 2w | 2022-09-30 | 2022-10-13 | 278 |  |  |  |  | 939 |  | 2022-09-30 | 2022-10-13 | 0
280 | 1.2 | 1.2.3.6.7 | C | Prepare for Shipment | Not Started | 5 | 3d | 2022-09-30 | 2022-10-04 | 278 |  |  |  |  | 927 |  | 2022-09-30 | 2022-10-04 | 0
281 | 1.2 | 1.2.4 | P | Computing and Control System - Off-ice | Started | 3 | 1899d | 2019-01-02 | 2026-04-24 |  | 25% |  |  |  | 27 |  | 2019-01-02 | 2026-04-24 | 0
282 | 1.2 | 1.2.4.1 | P | Architecture | Started | 4 | 1899d | 2019-01-02 | 2026-04-24 |  | 46% |  |  |  | 27 |  | 2019-01-02 | 2026-04-24 | 0
283 | 1.2 | 1.2.4.1.1 | C | Evaluate EHWD system | Complete | 5 | 80d | 2019-01-02 | 2019-04-23 |  | 100% |  |  |  | 1645 |  | 2019-01-02 | 2019-04-23 | 0
284 | 1.2 | 1.2.4.1.2 | C | ICUD Requirements & Architecture Plan | Complete | 5 | 80d | 2019-04-24 | 2019-08-13 | 283 | 100% | underway, SCADA options under evaluation |  |  | 1645 |  | 2019-04-24 | 2019-08-13 | 0
285 | 1.2 | 1.2.4.1.3 | C | Control Systems - Preliminary Design Review | Complete | 5 | 1d | 2019-08-14 | 2019-08-14 | 284 | 100% |  |  |  | 1645 |  | 2019-08-14 | 2019-08-14 | 0
286 | 1.2 | 1.2.4.1.4 | C | System Design | Complete | 5 | 120d | 2019-08-15 | 2020-01-29 | 285 | 100% |  |  |  | 1645 |  | 2019-08-15 | 2020-01-29 | 0
287 | 1.2 | 1.2.4.1.5 | C | Control Systems - 60% Design Review Complete | Not Started | 5 | 0 | 2022-04-15 | 2022-04-15 |  | 0% |  |  |  | 938 |  | 2022-04-15 | 2022-04-15 | 0
288 | 1.2 | 1.2.4.1.6 | C | Control Systems - Electrical Schematic Update 1 | Not Started | 5 | 110d | 2022-02-15 | 2022-07-18 |  | 0% |  |  |  | 936 |  | 2022-02-15 | 2022-07-18 | 0
289 | 1.2 | 1.2.4.1.7 | C | Coordination with USAP IT (PY4) | Not Started | 5 | 2w | 2022-05-15 | 2022-05-26 | [5 empty] | 1039 |  | 2022-05-15 | 2022-05-26 | 0
290 | 1.2 | 1.2.4.1.8 | C | Coordination with USAP IT (PY5) | Not Started | 5 | 4w | 2023-05-29 | 2023-06-23 | 825FS +14w |  |  |  |  | 758 |  | 2023-05-29 | 2023-06-23 | 0
291 | 1.2 | 1.2.4.1.9 | C | CS Drawings & Documentation (PY5) | Not Started | 5 | 12w | 2023-07-11 | 2023-10-02 | 881SF -4w |  |  |  |  | 687 |  | 2023-07-11 | 2023-10-02 | 0
292 | 1.2 | 1.2.4.1.10 | C | CS Drawings & Documentation (PY6) | Not Started | 5 | 12w | 2024-07-12 | 2024-10-03 | 1244SF -4w |  |  |  |  | 427 |  | 2024-07-12 | 2024-10-03 | 0
293 | 1.2 | 1.2.4.1.11 | C | CS Drawings & Documentation (PY7) | Not Started | 5 | 12w | 2025-07-23 | 2025-10-14 | 1449SF -4w |  |  |  |  | 162 |  | 2025-07-23 | 2025-10-14 | 0
294 | 1.2 | 1.2.4.1.12 | C | CS Drawings & Documentation (PY8) | Started | 5 | 8w | 2026-03-02 | 2026-04-24 | 1454FS +2w | 28% |  |  |  | 27 |  | 2026-03-02 | 2026-04-24 | 0
295 | 1.2 | 1.2.4.2 | P | Control System Hardware | Started | 4 | 924d | 2021-11-01 | 2025-05-23 |  | 18% |  |  |  | 264 |  | 2021-11-01 | 2025-05-23 | 0
296 | 1.2 | 1.2.4.2.1 | P | PLC Motor Controllers and Readouts | Not Started | 5 | 103d | 2022-05-10 | 2022-09-29 |  | 0% |  |  |  | 949 |  | 2022-05-10 | 2022-09-29 | 0
297 | 1.2 | 1.2.4.2.1.1 | P | Design, Build and Test New PLC and Network Box for HPP | Not Started | 6 | 52d | 2022-05-10 | 2022-07-20 |  | 0% |  |  |  | 1000 |  | 2022-05-10 | 2022-07-20 | 0
298 | 1.2 | 1.2.4.2.1.1.1 | C | PLC and Network Box for HPP Design & Build | Not Started | 7 | 52d | 2022-05-10 | 2022-07-20 |  | 0% |  |  |  | 1000 |  | 2022-05-10 | 2022-07-20 | 0
299 | 1.2 | 1.2.4.2.1.1.2 | C | PLC and Network Cox for HPP Constructed, Tested & Complete | Not Started | 7 | 0 | 2022-07-20 | 2022-07-20 | 298 | 0% |  |  |  | 1000 |  | 2022-07-20 | 2022-07-20 | 0
300 | 1.2 | 1.2.4.2.1.2 | C | Design, Build & Test RWCR Control Box | Not Started | 6 | 65d | 2022-07-01 | 2022-09-29 |  | 0% |  |  |  | 949 |  | 2022-07-01 | 2022-09-29 | 0
301 | 1.2 | 1.2.4.2.2 | P | Sensors | Started | 5 | 172d | 2022-05-28 | 2023-01-23 |  | 13% |  |  |  | 867 |  | 2022-05-28 | 2023-01-23 | 0
302 | 1.2 | 1.2.4.2.2.1 | C | HPP Sensor Box Testing | Started | 6 | 60d | 2022-06-22 | 2022-09-13 |  | 33% |  |  |  | 956 |  | 2022-06-22 | 2022-09-13 | 0
303 | 1.2 | 1.2.4.2.2.2 | C | Specify, Procure and Test Water Tank Depth & Temp Sensor Box Testing | Started | 6 | 41d | 2022-06-26 | 2022-08-19 |  | 53% |  |  |  | 978 |  | 2022-06-26 | 2022-08-19 | 0
304 | 1.2 | 1.2.4.2.2.3 | C | Specify System Sensors | Not Started | 6 | 90d | 2022-05-28 | 2022-09-29 | [5 empty] | 869 |  | 2022-05-28 | 2022-09-29 | 0
305 | 1.2 | 1.2.4.2.2.4 | C | Procure System Sensors (PY4) | Not Started | 6 | 8w | 2022-06-13 | 2022-08-05 | 304SS +2w |  |  |  |  | 983 |  | 2022-06-13 | 2022-08-05 | 0
306 | 1.2 | 1.2.4.2.2.5 | C | Procure System Sensors (PY5) | Not Started | 6 | 16w | 2022-10-04 | 2023-01-23 | 304FS +2d, 39 |  |  |  |  | 867 |  | 2022-10-04 | 2023-01-23 | 0
307 | 1.2 | 1.2.4.2.3 | P | Network Controllers | Started | 5 | 67d | 2022-04-15 | 2022-07-18 |  | 35% |  |  |  | 1002 |  | 2022-04-15 | 2022-07-18 | 0
308 | 1.2 | 1.2.4.2.3.1 | C | Plan MHP Network Box Upgrade | Started | 6 | 65d | 2022-04-15 | 2022-07-14 | 287 | 70% |  |  |  | 938 |  | 2022-04-15 | 2022-07-14 | 0
309 | 1.2 | 1.2.4.2.3.2 | C | Redesign, Build and Test Network Box for PHS | Not Started | 6 | 66d | 2022-04-18 | 2022-07-18 | 308SS, 288FF | 0% |  |  |  | 1002 |  | 2022-04-18 | 2022-07-18 | 0
310 | 1.2 | 1.2.4.2.4 | C | Indoor Cables (sensor and network) | Started | 5 | 110d | 2022-02-09 | 2022-07-12 |  | 24% |  |  |  | 828 |  | 2022-02-09 | 2022-07-12 | 0
311 | 1.2 | 1.2.4.2.5 | C | Infrastructure Repair & Upgrade (w/sub-tasks) | Started | 5 | 178d | 2022-01-26 | 2022-09-30 | 310SS -10d | 60% |  |  |  | 948 |  | 2022-01-26 | 2022-09-30 | 0
312 | 1.2 | 1.2.4.2.6 | C | Return Water Pump Noise Mitigation Subsys. Testing | Not Started | 5 | 24w | 2022-04-01 | 2022-09-15 |  | 0% |  |  |  | 839 |  | 2022-04-01 | 2022-09-15 | 0
313 | 1.2 | 1.2.4.2.7 | C | TOS pendant I/O box Rebuild & Testing - (one finished, 7 remaining) | Started | 5 | 24w | 2022-04-01 | 2022-09-15 | 312FF | 60% |  |  |  | 959 |  | 2022-04-01 | 2022-09-15 | 0
314 | 1.2 | 1.2.4.2.8 | C | TOS and DCC PLC Box Design, Build, Test (three new boxes) | Started | 5 | 189d | 2022-01-11 | 2022-09-30 |  | 5% |  |  |  | 943 |  | 2022-01-11 | 2022-09-30 | 0
315 | 1.2 | 1.2.4.2.9 | C | Rodwell Control Interface Definition, - (New I/O box for this Unit) | Started | 5 | 75d | 2021-11-01 | 2022-02-11 |  | 15% |  |  |  | 1113 |  | 2021-11-01 | 2022-02-11 | 0
316 | 1.2 | 1.2.4.2.10 | P | Computing Equipment - TestBed | Not Started | 5 | 120d | 2022-02-28 | 2022-08-12 | [5 empty] | 983 |  | 2022-02-28 | 2022-08-12 | 0
317 | 1.2 | 1.2.4.2.10.1 | C | CS HW TestBed Ignition Server Testing | Not Started | 6 | 12w | 2022-02-28 | 2022-05-20 | [5 empty] | 923 |  | 2022-02-28 | 2022-05-20 | 0
318 | 1.2 | 1.2.4.2.10.2 | C | CS HW TestBed Database Server Testing | Not Started | 6 | 12w | 2022-05-23 | 2022-08-12 | 317 |  |  |  |  | 983 |  | 2022-05-23 | 2022-08-12 | 0
319 | 1.2 | 1.2.4.2.10.3 | C | CS HW TestBed Peripherals Testing | Not Started | 6 | 24w | 2022-02-28 | 2022-08-12 | 317SS |  |  |  |  | 983 |  | 2022-02-28 | 2022-08-12 | 0
320 | 1.2 | 1.2.4.2.11 | P | Computing Equipment - Production | Not Started | 5 | 120d | 2023-02-20 | 2023-08-04 | [5 empty] | 728 |  | 2023-02-20 | 2023-08-04 | 0
321 | 1.2 | 1.2.4.2.11.1 | C | CS HW Production Ignition Servers (3x: DCC, TOS1, TOS2) | Not Started | 6 | 12w | 2023-02-20 | 2023-05-12 | 825 |  |  |  |  | 482 |  | 2023-02-20 | 2023-05-12 | 0
322 | 1.2 | 1.2.4.2.11.2 | C | CS HW Production Database Server (1x: DCC) | Not Started | 6 | 12w | 2023-02-20 | 2023-05-12 | 321SS |  |  |  |  | 542 |  | 2023-02-20 | 2023-05-12 | 0
323 | 1.2 | 1.2.4.2.11.3 | C | CS HW Production Peripherals (3x sets: DCC, TOS1, TOS2) | Not Started | 6 | 8w | 2023-03-20 | 2023-05-12 | 322SS +4w |  |  |  |  | 582 |  | 2023-03-20 | 2023-05-12 | 0
324 | 1.2 | 1.2.4.2.11.4 | C | CS HW DCC Core Switch & Security Appliance | Not Started | 6 | 8w | 2023-04-03 | 2023-05-26 | 323SS +2w |  |  |  |  | 612 |  | 2023-04-03 | 2023-05-26 | 0
325 | 1.2 | 1.2.4.2.11.5 | C | CS HW Production Main PLC - PLC (redundant), I/O, network, UPS, in a box (3x: DCC, TOS1, TOS2) | Not Started | 6 | 16w | 2023-04-17 | 2023-08-04 | 324SS +2w |  |  |  |  | 642 |  | 2023-04-17 | 2023-08-04 | 0
326 | 1.2 | 1.2.4.2.12 | C | CS HW Build Mobile DCC | Not Started | 5 | 20d | 2022-04-01 | 2022-04-28 | [5 empty] | 1019 |  | 2022-04-01 | 2022-04-28 | 0
327 | 1.2 | 1.2.4.2.13 | C | CS HW PY6 Resupply | Not Started | 5 | 40d | 2024-03-28 | 2024-05-22 | 886FS +6w |  |  |  |  | 523 |  | 2024-03-28 | 2024-05-22 | 0
328 | 1.2 | 1.2.4.2.14 | C | CS HW PY7 Resupply | Not Started | 5 | 40d | 2025-03-31 | 2025-05-23 | 1246FS +6w |  |  |  |  | 257 |  | 2025-03-31 | 2025-05-23 | 0
329 | 1.2 | 1.2.4.3 | P | Control System Software | Started | 4 | 1242d | 2020-11-04 | 2025-08-15 |  | 19% |  |  |  | 204 |  | 2020-11-04 | 2025-08-15 | 0
330 | 1.2 | 1.2.4.3.1 | C | Motor Controllers and Readouts | Should have Started | 5 | 498d | 2020-11-04 | 2022-09-30 |  | 0% | 1st order placed |  |  | 51 |  | 2020-11-04 | 2022-09-30 | 0
331 | 1.2 | 1.2.4.3.2 | P | Data Acquisition | Started | 5 | 105d | 2021-10-01 | 2022-02-24 |  | 29% |  |  |  | 1104 |  | 2021-10-01 | 2022-02-24 | 0
332 | 1.2 | 1.2.4.3.2.1 | C | DGH Programming, Testing and Cataloging | Should have Started | 6 | 57d | 2021-12-08 | 2022-02-24 | 333FS +5d | 0% |  |  |  | 1104 |  | 2021-12-08 | 2022-02-24 | 0
333 | 1.2 | 1.2.4.3.2.2 | C | Payout Encoder Specify, Procure, and Test | Started | 6 | 43d | 2021-10-01 | 2021-11-30 |  | 40% |  |  |  | 1109 |  | 2021-10-01 | 2021-11-30 | 0
334 | 1.2 | 1.2.4.3.2.3 | C | HPP Sensor DGH Box Testing | Started | 6 | 30d | 2021-10-13 | 2021-11-23 | 333FF -5d | 70% |  |  |  | 1171 |  | 2021-10-13 | 2021-11-23 | 0
335 | 1.2 | 1.2.4.3.3 | P | System Operator Functions - SW/HW Trial in Testbed | Started | 5 | 90d | 2022-05-01 | 2022-09-01 |  | 50% |  |  |  | 969 |  | 2022-05-01 | 2022-09-01 | 0
336 | 1.2 | 1.2.4.3.3.1 | C | Control System Software: System Operator Functions - PY4 software/hardware trials completed | Started | 6 | 90d | 2022-05-01 | 2022-09-01 |  | 50% |  |  |  | 969 |  | 2022-05-01 | 2022-09-01 | 0
337 | 1.2 | 1.2.4.3.4 | C | PLC & Software Development (w/sub-tasks) | Started | 5 | 897d | 2021-04-22 | 2024-10-02 | 330FF +520d | 65% |  |  |  | 428 |  | 2021-04-22 | 2024-10-02 | 0
338 | 1.2 | 1.2.4.3.5 | C | SCADA Monitoring Software and Server Procurement | Not Started | 5 | 151d | 2022-04-01 | 2022-10-28 |  | 0% |  |  |  | 828 |  | 2022-04-01 | 2022-10-28 | 0
339 | 1.2 | 1.2.4.3.6 | C | SCADA Screen Development | Not Started | 5 | 100d | 2022-10-31 | 2023-03-17 | 338 | 0% |  |  |  | 828 |  | 2022-10-31 | 2023-03-17 | 0
340 | 1.2 | 1.2.4.3.7 | C | CS SW Configure Mobile DCC Test System | Not Started | 5 | 8w | 2022-04-29 | 2022-06-23 | 326 | 0% |  |  |  | 1019 |  | 2022-04-29 | 2022-06-23 | 0
341 | 1.2 | 1.2.4.3.8 | P | CS SW TestBed Operator Screen Development (HMI/SCADA) - Develop DCC-MDS SW functionality | Complete | 5 | 10d | 2022-10-31 | 2022-11-11 | 338 | 100% |  |  |  | 918 |  | 2022-10-31 | 2022-11-11 | 0
342 | 1.2 | 1.2.4.3.8.1 | C | TestBed System Screens | Complete | 6 | 2w | 2022-10-31 | 2022-11-11 |  | 100% |  |  |  | 918 |  | 2022-10-31 | 2022-11-11 | 0
343 | 1.2 | 1.2.4.3.8.2 | C | High-Pressure Pump Control Screen | Complete | 6 | 2w | 2022-10-31 | 2022-11-11 |  | 100% |  |  |  | 918 |  | 2022-10-31 | 2022-11-11 | 0
344 | 1.2 | 1.2.4.3.8.3 | C | VT Pump Control Screens | Complete | 6 | 2w | 2022-10-31 | 2022-11-11 |  | 100% |  |  |  | 918 |  | 2022-10-31 | 2022-11-11 | 0
345 | 1.2 | 1.2.4.3.8.4 | C | Heater-based Sensor Readout Screen | Complete | 6 | 2w | 2022-10-31 | 2022-11-11 |  | 100% |  |  |  | 918 |  | 2022-10-31 | 2022-11-11 | 0
346 | 1.2 | 1.2.4.3.8.5 | C | Bldg Sensor Screen | Complete | 6 | 2w | 2022-10-31 | 2022-11-11 |  | 100% |  |  |  | 918 |  | 2022-10-31 | 2022-11-11 | 0
347 | 1.2 | 1.2.4.3.8.6 | C | Heater Control Screen | Complete | 6 | 2w | 2022-10-31 | 2022-11-11 |  | 100% |  |  |  | 918 |  | 2022-10-31 | 2022-11-11 | 0
348 | 1.2 | 1.2.4.3.9 | P | CS SW SES Operator Screen development | Not Started | 5 | 375d | 2023-04-03 | 2024-09-11 |  | 0% |  |  |  | 443 |  | 2023-04-03 | 2024-09-11 | 0
349 | 1.2 | 1.2.4.3.9.1 | P | Develop MHP-MDS UI Screens [x4] | Not Started | 6 | 275d | 2023-04-03 | 2024-04-24 |  | 0% |  |  |  | 543 |  | 2023-04-03 | 2024-04-24 | 0
350 | 1.2 | 1.2.4.3.9.1.1 | C | Local-Panel MDS-specific HMI (PY5) | Not Started | 7 | 2w | 2023-04-03 | 2023-04-14 | 825FS +6w | 0% |  |  |  | 698 |  | 2023-04-03 | 2023-04-14 | 0
351 | 1.2 | 1.2.4.3.9.1.2 | C | Local-Panel MDS-specific HMI (PY6) | Not Started | 7 | 2w | 2024-03-28 | 2024-04-10 | 886FS +6w | 0% |  |  |  | 443 |  | 2024-03-28 | 2024-04-10 | 0
352 | 1.2 | 1.2.4.3.9.1.3 | C | DCC-based SCADA UI (PY5) | Not Started | 7 | 2w | 2023-04-17 | 2023-04-28 | 350 | 0% |  |  |  | 698 |  | 2023-04-17 | 2023-04-28 | 0
353 | 1.2 | 1.2.4.3.9.1.4 | C | DCC-based SCADA UI (PY6) | Not Started | 7 | 2w | 2024-04-11 | 2024-04-24 | 351 | 0% |  |  |  | 443 |  | 2024-04-11 | 2024-04-24 | 0
354 | 1.2 | 1.2.4.3.9.2 | P | Develop FuelSystem-MDS UI Screens | Not Started | 6 | 275d | 2023-05-01 | 2024-05-22 |  | 0% |  |  |  | 523 |  | 2023-05-01 | 2024-05-22 | 0
355 | 1.2 | 1.2.4.3.9.2.1 | C | Local-Panel MDS-specific HMI (PY5) | Not Started | 7 | 2w | 2023-05-01 | 2023-05-12 | 352 | 0% |  |  |  | 698 |  | 2023-05-01 | 2023-05-12 | 0
356 | 1.2 | 1.2.4.3.9.2.2 | C | Local-Panel MDS-specific HMI (PY6) | Not Started | 7 | 2w | 2024-04-25 | 2024-05-08 | 353 | 0% |  |  |  | 443 |  | 2024-04-25 | 2024-05-08 | 0
357 | 1.2 | 1.2.4.3.9.2.3 | C | DCC-based SCADA (PY5) | Not Started | 7 | 2w | 2023-05-15 | 2023-05-26 | 355 | 0% |  |  |  | 698 |  | 2023-05-15 | 2023-05-26 | 0
358 | 1.2 | 1.2.4.3.9.2.4 | C | DCC-based SCADA (PY6) | Not Started | 7 | 2w | 2024-05-09 | 2024-05-22 | 356 | 0% |  |  |  | 443 |  | 2024-05-09 | 2024-05-22 | 0
359 | 1.2 | 1.2.4.3.9.3 | P | Develop GenSets-MDS UI Screens [x3] | Not Started | 6 | 275d | 2023-05-29 | 2024-06-19 |  | 0% |  |  |  | 503 |  | 2023-05-29 | 2024-06-19 | 0
360 | 1.2 | 1.2.4.3.9.3.1 | C | Local-Panel MDS-specific HMI (PY5) | Not Started | 7 | 2w | 2023-05-29 | 2023-06-09 | 357 | 0% |  |  |  | 698 |  | 2023-05-29 | 2023-06-09 | 0
361 | 1.2 | 1.2.4.3.9.3.2 | C | Local-Panel MDS-specific HMI (PY6) | Not Started | 7 | 2w | 2024-05-23 | 2024-06-05 | 358 | 0% |  |  |  | 443 |  | 2024-05-23 | 2024-06-05 | 0
362 | 1.2 | 1.2.4.3.9.3.3 | C | DCC-based SCADA (PY5) | Not Started | 7 | 2w | 2023-06-12 | 2023-06-23 | 360 | 0% |  |  |  | 698 |  | 2023-06-12 | 2023-06-23 | 0
363 | 1.2 | 1.2.4.3.9.3.4 | C | DCC-based SCADA (PY6) | Not Started | 7 | 2w | 2024-06-06 | 2024-06-19 | 361 | 0% |  |  |  | 443 |  | 2024-06-06 | 2024-06-19 | 0
364 | 1.2 | 1.2.4.3.9.4 | P | Develop Rodwell System UI Screens | Not Started | 6 | 275d | 2023-06-26 | 2024-07-17 |  | 0% |  |  |  | 483 |  | 2023-06-26 | 2024-07-17 | 0
365 | 1.2 | 1.2.4.3.9.4.1 | C | Local-Panel MDS-specific HMI (PY5) | Not Started | 7 | 2w | 2023-06-26 | 2023-07-07 | 362 | 0% |  |  |  | 698 |  | 2023-06-26 | 2023-07-07 | 0
366 | 1.2 | 1.2.4.3.9.4.2 | C | Local-Panel MDS-specific HMI (PY6) | Not Started | 7 | 2w | 2024-06-20 | 2024-07-03 | 363 | 0% |  |  |  | 443 |  | 2024-06-20 | 2024-07-03 | 0
367 | 1.2 | 1.2.4.3.9.4.3 | C | DCC-based SCADA (PY5) | Not Started | 7 | 2w | 2023-07-10 | 2023-07-21 | 365 | 0% |  |  |  | 698 |  | 2023-07-10 | 2023-07-21 | 0
368 | 1.2 | 1.2.4.3.9.4.4 | C | DCC-based SCADA (PY6) | Not Started | 7 | 2w | 2024-07-04 | 2024-07-17 | 366 | 0% |  |  |  | 443 |  | 2024-07-04 | 2024-07-17 | 0
369 | 1.2 | 1.2.4.3.9.5 | P | Develop HPP-MDS UI Screens | Not Started | 6 | 275d | 2023-07-24 | 2024-08-14 |  | 0% |  |  |  | 463 |  | 2023-07-24 | 2024-08-14 | 0
370 | 1.2 | 1.2.4.3.9.5.1 | C | Local-Panel MDS-specific HMI (PY5) | Not Started | 7 | 2w | 2023-07-24 | 2023-08-04 | 367 | 0% |  |  |  | 698 |  | 2023-07-24 | 2023-08-04 | 0
371 | 1.2 | 1.2.4.3.9.5.2 | C | Local-Panel MDS-specific HMI (PY6) | Not Started | 7 | 2w | 2024-07-18 | 2024-07-31 | 368 | 0% |  |  |  | 443 |  | 2024-07-18 | 2024-07-31 | 0
372 | 1.2 | 1.2.4.3.9.5.3 | C | DCC-based SCADA (PY5) | Not Started | 7 | 2w | 2023-08-07 | 2023-08-18 | 370 | 0% |  |  |  | 698 |  | 2023-08-07 | 2023-08-18 | 0
373 | 1.2 | 1.2.4.3.9.5.4 | C | DCC-based SCADA (PY6) | Not Started | 7 | 2w | 2024-08-01 | 2024-08-14 | 371 | 0% |  |  |  | 443 |  | 2024-08-01 | 2024-08-14 | 0
374 | 1.2 | 1.2.4.3.9.6 | P | Develop PHS-MDS UI Screens | Not Started | 6 | 275d | 2023-08-21 | 2024-09-11 |  | 0% |  |  |  | 443 |  | 2023-08-21 | 2024-09-11 | 0
375 | 1.2 | 1.2.4.3.9.6.1 | C | Local-Panel MDS-specific HMI (PY5) | Not Started | 7 | 2w | 2023-08-21 | 2023-09-01 | 372 | 0% |  |  |  | 698 |  | 2023-08-21 | 2023-09-01 | 0
376 | 1.2 | 1.2.4.3.9.6.2 | C | Local-Panel MDS-specific HMI (PY6) | Not Started | 7 | 2w | 2024-08-15 | 2024-08-28 | 373 | 0% |  |  |  | 443 |  | 2024-08-15 | 2024-08-28 | 0
377 | 1.2 | 1.2.4.3.9.6.3 | C | DCC-based SCADA (PY5) | Not Started | 7 | 2w | 2023-09-04 | 2023-09-15 | 375 | 0% |  |  |  | 698 |  | 2023-09-04 | 2023-09-15 | 0
378 | 1.2 | 1.2.4.3.9.6.4 | C | DCC-based SCADA (PY6) | Not Started | 7 | 2w | 2024-08-29 | 2024-09-11 | 376 | 0% |  |  |  | 443 |  | 2024-08-29 | 2024-09-11 | 0
379 | 1.2 | 1.2.4.3.10 | P | CS SW TOS Operator Screen Development | Not Started | 5 | 375d | 2023-05-01 | 2024-10-09 |  | 0% |  |  |  | 423 |  | 2023-05-01 | 2024-10-09 | 0
380 | 1.2 | 1.2.4.3.10.1 | C | SCADA - DrillHead (PY5) | Not Started | 6 | 3w | 2023-05-01 | 2023-05-19 | 825FS +10w | 0% |  |  |  | 678 |  | 2023-05-01 | 2023-05-19 | 0
381 | 1.2 | 1.2.4.3.10.2 | C | SCADA - DrillHead (PY6) | Not Started | 6 | 3w | 2024-04-25 | 2024-05-15 | 886FS +10w | 0% |  |  |  | 423 |  | 2024-04-25 | 2024-05-15 | 0
382 | 1.2 | 1.2.4.3.10.3 | C | SCADA - Drill_Settings (PY5) | Not Started | 6 | 3w | 2023-05-22 | 2023-06-09 | 380 | 0% |  |  |  | 678 |  | 2023-05-22 | 2023-06-09 | 0
383 | 1.2 | 1.2.4.3.10.4 | C | SCADA - Drill_Settings (PY6) | Not Started | 6 | 3w | 2024-05-16 | 2024-06-05 | 381 | 0% |  |  |  | 423 |  | 2024-05-16 | 2024-06-05 | 0
384 | 1.2 | 1.2.4.3.10.5 | C | SCADA - Drilling_Drill Control (PY5) | Not Started | 6 | 3w | 2023-06-12 | 2023-06-30 | 382 | 0% |  |  |  | 678 |  | 2023-06-12 | 2023-06-30 | 0
385 | 1.2 | 1.2.4.3.10.6 | C | SCADA - Drilling_Drill Control (PY6) | Not Started | 6 | 3w | 2024-06-06 | 2024-06-26 | 383 | 0% |  |  |  | 423 |  | 2024-06-06 | 2024-06-26 | 0
386 | 1.2 | 1.2.4.3.10.7 | C | SCADA - Drilling_Cable Level Wind (PY5) | Not Started | 6 | 3w | 2023-07-03 | 2023-07-21 | 384 | 0% |  |  |  | 678 |  | 2023-07-03 | 2023-07-21 | 0
387 | 1.2 | 1.2.4.3.10.8 | C | SCADA - Drilling_Cable Level Wind (PY6) | Not Started | 6 | 3w | 2024-06-27 | 2024-07-17 | 385 | 0% |  |  |  | 423 |  | 2024-06-27 | 2024-07-17 | 0
388 | 1.2 | 1.2.4.3.10.9 | C | SCADA - Drilling_Hose Level Wind (PY5) | Not Started | 6 | 3w | 2023-07-24 | 2023-08-11 | 386 | 0% |  |  |  | 678 |  | 2023-07-24 | 2023-08-11 | 0
389 | 1.2 | 1.2.4.3.10.10 | C | SCADA - Drilling_Hose Level Wind (PY6) | Not Started | 6 | 3w | 2024-07-18 | 2024-08-07 | 387 | 0% |  |  |  | 423 |  | 2024-07-18 | 2024-08-07 | 0
390 | 1.2 | 1.2.4.3.10.11 | C | SCADA - Return Water Pump (PY5) | Not Started | 6 | 3w | 2023-08-14 | 2023-09-01 | 388 | 0% |  |  |  | 678 |  | 2023-08-14 | 2023-09-01 | 0
391 | 1.2 | 1.2.4.3.10.12 | C | SCADA - Return Water Pump (PY6) | Not Started | 6 | 3w | 2024-08-08 | 2024-08-28 | 389 | 0% |  |  |  | 423 |  | 2024-08-08 | 2024-08-28 | 0
392 | 1.2 | 1.2.4.3.10.13 | C | SCADA - Deployment - Cable (PY5) | Not Started | 6 | 3w | 2023-09-04 | 2023-09-22 | 390 | 0% |  |  |  | 678 |  | 2023-09-04 | 2023-09-22 | 0
393 | 1.2 | 1.2.4.3.10.14 | C | SCADA - Deployment - Cable (PY6) | Not Started | 6 | 3w | 2024-08-29 | 2024-09-18 | 391 | 0% |  |  |  | 423 |  | 2024-08-29 | 2024-09-18 | 0
394 | 1.2 | 1.2.4.3.10.15 | C | SCADA - Deployment Settings (PY5) | Not Started | 6 | 3w | 2023-09-25 | 2023-10-13 | 392 | 0% |  |  |  | 678 |  | 2023-09-25 | 2023-10-13 | 0
395 | 1.2 | 1.2.4.3.10.16 | C | SCADA - Deployment Settings (PY6) | Not Started | 6 | 3w | 2024-09-19 | 2024-10-09 | 393 | 0% |  |  |  | 423 |  | 2024-09-19 | 2024-10-09 | 0
396 | 1.2 | 1.2.4.3.11 | P | CS SW dB Design, my SQL | Not Started | 5 | 315d | 2023-04-03 | 2024-06-19 |  | 0% |  |  |  | 503 |  | 2023-04-03 | 2024-06-19 | 0
397 | 1.2 | 1.2.4.3.11.1 | C | Build DCC dB schema (PY5) | Not Started | 6 | 4w | 2023-04-03 | 2023-04-28 | 825FS +6w | 0% |  |  |  | 758 |  | 2023-04-03 | 2023-04-28 | 0
398 | 1.2 | 1.2.4.3.11.2 | C | Build DCC dB schema (PY6) | Not Started | 6 | 4w | 2024-03-28 | 2024-04-24 | 886FS +6w | 0% |  |  |  | 503 |  | 2024-03-28 | 2024-04-24 | 0
399 | 1.2 | 1.2.4.3.11.3 | C | Build Drill dB schema (PY5) | Not Started | 6 | 4w | 2023-05-01 | 2023-05-26 | 397 | 0% |  |  |  | 758 |  | 2023-05-01 | 2023-05-26 | 0
400 | 1.2 | 1.2.4.3.11.4 | C | Build Drill dB schema (PY6) | Not Started | 6 | 4w | 2024-04-25 | 2024-05-22 | 398 | 0% |  |  |  | 503 |  | 2024-04-25 | 2024-05-22 | 0
401 | 1.2 | 1.2.4.3.11.5 | C | Build Deploy dB schema (PY5) | Not Started | 6 | 4w | 2023-05-29 | 2023-06-23 | 399 | 0% |  |  |  | 758 |  | 2023-05-29 | 2023-06-23 | 0
402 | 1.2 | 1.2.4.3.11.6 | C | Build Deploy dB schema (PY6) | Not Started | 6 | 4w | 2024-05-23 | 2024-06-19 | 400 | 0% |  |  |  | 503 |  | 2024-05-23 | 2024-06-19 | 0
403 | 1.2 | 1.2.4.3.12 | C | CS SW Standup Production Computing Hardware, Configure, Verify before Shipment (3x systems) (PY6) | Not Started | 5 | 16w | 2024-03-21 | 2024-07-10 | 325FS +32w | 0% |  |  |  | 482 |  | 2024-03-21 | 2024-07-10 | 0
404 | 1.2 | 1.2.4.3.13 | C | CS SW MDS-specific HMI Refinement (PY7) | Not Started | 5 | 20w | 2025-03-31 | 2025-08-15 | 1246FS +6w | 0% |  |  |  | 104 |  | 2025-03-31 | 2025-08-15 | 0
405 | 1.2 | 1.2.4.3.14 | C | CS SW DCC-based SCADA Refinement (PY7) | Not Started | 5 | 20w | 2025-03-31 | 2025-08-15 | 404SS | 0% |  |  |  | 204 |  | 2025-03-31 | 2025-08-15 | 0
406 | 1.2 | 1.2.4.3.15 | C | CS SW TOS-based SCADA Refinement (PY7) | Not Started | 5 | 20w | 2025-03-31 | 2025-08-15 | 404SS | 0% |  |  |  | 204 |  | 2025-03-31 | 2025-08-15 | 0
407 | 1.2 | 1.2.4.3.16 | C | CS SW dB Refinement (PY7) | Not Started | 5 | 20w | 2025-03-31 | 2025-08-15 | 404SS | 0% |  |  |  | 204 |  | 2025-03-31 | 2025-08-15 | 0
408 | 1.2 | 1.2.4.4 | P | Motor Drives | Started | 4 | 840d | 2022-03-09 | 2025-06-04 |  | 16% |  |  |  | 256 |  | 2022-03-09 | 2025-06-04 | 0
409 | 1.2 | 1.2.4.4.1 | C | Requirements, Functional | Not Started | 5 | 110d | 2022-04-14 | 2022-09-14 |  | 0% | This activity was started earlier than planned |  |  | 840 |  | 2022-04-14 | 2022-09-14 | 0
410 | 1.2 | 1.2.4.4.2 | C | Requirements, Electrical | Complete | 5 | 120d | 2022-05-26 | 2022-11-09 | 409SS +30d | 100% | Need to define braking resistors and filters |  |  | 920 |  | 2022-05-26 | 2022-11-09 | 0
411 | 1.2 | 1.2.4.4.3 | C | Specify and Procure | Not Started | 5 | 35d | 2022-08-05 | 2022-09-22 |  | 0% | working on final requirements spring 2020 |  |  | 178 |  | 2022-08-05 | 2022-09-22 | 0
412 | 1.2 | 1.2.4.4.4 | C | Programming and Testing at PSL | Started | 5 | 776d | 2022-06-07 | 2025-06-04 | 411SS -43d | 7% |  |  |  | 256 |  | 2022-06-07 | 2025-06-04 | 0
413 | 1.2 | 1.2.4.4.5 | C | Plan Installations of New Motor Drives in Former Unico Locations | Not Started | 5 | 45d | 2022-03-09 | 2022-05-10 |  | 0% |  |  |  | 1051 |  | 2022-03-09 | 2022-05-10 | 0
414 | 1.2 | 1.2.4.5 | P | E-Stop System | Started | 4 | 1140d | 2021-01-29 | 2025-06-20 |  | 45% |  |  |  | 244 |  | 2021-01-29 | 2025-06-20 | 0
415 | 1.2 | 1.2.4.5.1 | C | Evaluate EHWD system | Complete | 5 | 60d | 2021-01-29 | 2021-04-22 |  | 100% | delayed, limited access to retro |  |  | 1324 |  | 2021-01-29 | 2021-04-22 | 0
416 | 1.2 | 1.2.4.5.2 | C | Define Requirements | Started | 5 | 79d | 2021-10-01 | 2022-01-19 |  | 35% | Requirements definition and redesign underway |  |  | 1130 |  | 2021-10-01 | 2022-01-19 | 0
417 | 1.2 | 1.2.4.5.3 | C | TOS E-stop Box Analysis, Documentation Updates | Started | 5 | 71d | 2021-12-16 | 2022-03-24 | 419SS +54d | 50% |  |  |  | 1084 |  | 2021-12-16 | 2022-03-24 | 0
418 | 1.2 | 1.2.4.5.4 | C | System E-stop Controller Redesign, Build, Test | Started | 5 | 90d | 2021-12-14 | 2022-04-18 |  | 50% |  |  |  | 1067 |  | 2021-12-14 | 2022-04-18 | 0
419 | 1.2 | 1.2.4.5.5 | C | TOS E-stop Controller Redesign, Build, Test | Started | 5 | 102d | 2021-10-01 | 2022-02-21 |  | 50% |  |  |  | 1036 |  | 2021-10-01 | 2022-02-21 | 0
420 | 1.2 | 1.2.4.5.6 | C | E-Stop Resupply (PY6) | Not Started | 5 | 8w | 2024-04-25 | 2024-06-19 | 886FS +10w |  |  |  |  | 503 |  | 2024-04-25 | 2024-06-19 | 0
421 | 1.2 | 1.2.4.5.7 | C | E-Stop Resupply (PY7) | Not Started | 5 | 8w | 2025-04-28 | 2025-06-20 | 1246FS +10w |  |  |  |  | 244 |  | 2025-04-28 | 2025-06-20 | 0
422 | 1.2 | 1.2.4.6 | P | Drill Control Center | Started | 4 | 586d | 2021-04-29 | 2023-07-27 |  | 24% |  |  |  | 734 |  | 2021-04-29 | 2023-07-27 | 0
423 | 1.2 | 1.2.4.6.1 | C | Computing System | Started | 5 | 586d | 2021-04-29 | 2023-07-27 |  | 23% |  |  |  | 734 |  | 2021-04-29 | 2023-07-27 | 0
424 | 1.2 | 1.2.4.6.2 | C | Electrical Improvements - Heater Upgrade Design and Procure | Started | 5 | 15d | 2022-08-15 | 2022-09-02 |  | 40% |  |  |  | 968 |  | 2022-08-15 | 2022-09-02 | 0
425 | 1.2 | 1.2.4.6.3 | C | Update Workspace (desk, chairs), Procure Printer & Accessories | Started | 5 | 30d | 2023-02-20 | 2023-03-31 | 825 | 40% |  |  |  | 818 |  | 2023-02-20 | 2023-03-31 | 0
426 | 1.2 | 1.2.4.7 | P | Outdoor Cables | Should have Started | 4 | 900d | 2022-01-15 | 2025-07-04 |  | 0% |  |  |  | 234 |  | 2022-01-15 | 2025-07-04 | 0
427 | 1.2 | 1.2.4.7.1 | C | Evaluate/Inventory SES & SES to TOS Cables - Signal | Should have Started | 5 | 30d | 2022-01-15 | 2022-02-24 |  | 0% | inventory consolidation from 19/20 season in progress, waiting on access to 19/20 retro |  |  | 773 |  | 2022-01-15 | 2022-02-24 | 0
428 | 1.2 | 1.2.4.7.2 | C | Design and Procure Replacement Components - Signal | Not Started | 5 | 23d | 2022-02-25 | 2022-03-29 | 427 | 0% |  |  |  | 773 |  | 2022-02-25 | 2022-03-29 | 0
429 | 1.2 | 1.2.4.7.3 | C | Fabricate and Test SES & SES to TOS Cables - Signal | Not Started | 5 | 305d | 2022-05-27 | 2023-07-27 | 428FS +42d | 0% |  |  |  | 731 |  | 2022-05-27 | 2023-07-27 | 0
430 | 1.2 | 1.2.4.7.4 | C | CS Cabling Resupply (PY6) | Not Started | 5 | 8w | 2024-05-09 | 2024-07-03 | 886FS +12w | 0% |  |  |  | 342 |  | 2024-05-09 | 2024-07-03 | 0
431 | 1.2 | 1.2.4.7.5 | C | CS Cabling Resupply (PY7) | Not Started | 5 | 8w | 2025-05-12 | 2025-07-04 | 1246FS +12w | 0% |  |  |  | 234 |  | 2025-05-12 | 2025-07-04 | 0
432 | 1.2 | 1.2.4.8 | P | Controls Subsystems (PY5-PY8) | Should have Started | 4 | 710d | 2022-01-03 | 2024-09-25 |  | 0% |  |  |  | 433 |  | 2022-01-03 | 2024-09-25 | 0
433 | 1.2 | 1.2.4.8.1 | P | CS MHPs | Not Started | 5 | 265d | 2022-05-02 | 2023-05-05 |  | 0% |  |  |  | 793 |  | 2022-05-02 | 2023-05-05 | 0
434 | 1.2 | 1.2.4.8.1.1 | P | CS MHP HW1: Network and Network Box Refurb & Config | Not Started | 6 | 60d | 2022-05-02 | 2022-07-22 |  | 0% |  |  |  | 991 |  | 2022-05-02 | 2022-07-22 | 0
435 | 1.2 | 1.2.4.8.1.1.1 | C | Program and catalog replacement flow and control DGH modules for all MHP heaters | Not Started | 7 | 4w | 2022-05-02 | 2022-05-27 |  | 0% |  |  | PY4 carried in 1.2.4.2.3.1 - 80,0,0 | 793 |  | 2022-05-02 | 2022-05-27 | 0
436 | 1.2 | 1.2.4.8.1.1.2 | C | Procure and configure PLC-to-DGH gateways, develop instructions for field installation and test | Not Started | 7 | 4w | 2022-05-30 | 2022-06-24 | 435 | 0% |  |  | PY4 carried in 1.2.4.2.3.1 - 40,0,3600 | 793 |  | 2022-05-30 | 2022-06-24 | 0
437 | 1.2 | 1.2.4.8.1.1.3 | C | Select and procure backup power supplies for MHP network boxes | Not Started | 7 | 4w | 2022-06-27 | 2022-07-22 | 436 | 0% |  |  | PY4 carried in 1.2.4.2.3.1 - 8,0,800 | 843 |  | 2022-06-27 | 2022-07-22 | 0
438 | 1.2 | 1.2.4.8.1.2 | P | CS MHP HW2-3: Heater Controller Temp Displays & Controllers | Not Started | 6 | 140d | 2022-10-03 | 2023-04-14 |  | 0% |  |  |  | 801 |  | 2022-10-03 | 2023-04-14 | 0
439 | 1.2 | 1.2.4.8.1.2.1 | C | Procure sample temperature display and digital thermostat, install in test bed heater, test | Not Started | 7 | 6w | 2022-10-03 | 2022-11-11 | 39 | 0% |  |  | PY4 carried in 1.2.2.1.3 - 32,0,300 | 808 |  | 2022-10-03 | 2022-11-11 | 0
440 | 1.2 | 1.2.4.8.1.2.2 | C | Select and procure temperature display units for heater controls, conversion hardware | Not Started | 7 | 6w | 2022-11-14 | 2022-12-23 | 439 | 0% |  |  | PY4 carried in 1.2.2.1.3 - 32,0,2400 | 808 |  | 2022-11-14 | 2022-12-23 | 0
441 | 1.2 | 1.2.4.8.1.2.3 | C | Replace temperature display units, remove RTD DGHs, transfer net connections, test | Not Started | 7 | 8w | 2022-12-26 | 2023-02-17 | 440 | 0% |  |  | PY4 carried in 1.2.2.1.3 - 40,160,0 | 808 |  | 2022-12-26 | 2023-02-17 | 0
442 | 1.2 | 1.2.4.8.1.2.4 | C | Select and procure digital thermostats for heater controls, conversion hardware | Not Started | 7 | 6w | 2023-02-20 | 2023-03-31 | 441 | 0% |  |  | PY4 carried in 1.2.2.1.3 - 32,0,3200 | 808 |  | 2023-02-20 | 2023-03-31 | 0
443 | 1.2 | 1.2.4.8.1.2.5 | C | Write thermostat field replacement procedure | Not Started | 7 | 2w | 2023-04-03 | 2023-04-14 | 442 | 0% |  |  | PY4 carried in 1.2.2.1.3 - 24,0,0 | 808 |  | 2023-04-03 | 2023-04-14 | 0
444 | 1.2 | 1.2.4.8.1.3 | P | CS MHP HW4-6: Maintain Documentation, Prepare Field Plans | Not Started | 6 | 80d | 2022-10-03 | 2023-01-20 |  | 0% |  |  |  | 868 |  | 2022-10-03 | 2023-01-20 | 0
445 | 1.2 | 1.2.4.8.1.3.1 | C | Write rewiring and test instructions for MHP E-stop boxes (fixes switch contact selections made in Gen 1) | Not Started | 7 | 4w | 2022-10-03 | 2022-10-28 | 437, 39 | 0% |  |  | Deliverable supports FS1 tasking | 793 |  | 2022-10-03 | 2022-10-28 | 0
446 | 1.2 | 1.2.4.8.1.3.2 | C | Write test procedures for dry heater tests | Not Started | 7 | 4w | 2022-10-31 | 2022-11-25 | 445 | 0% |  |  | Deliverable supports FS1 tasking | 793 |  | 2022-10-31 | 2022-11-25 | 0
447 | 1.2 | 1.2.4.8.1.3.3 | C | Assemble equipment to test flow meters (excitation coil and portable pulse generator) | Not Started | 7 | 4w | 2022-11-28 | 2022-12-23 | 446 | 0% |  |  | Deliverable supports FS1 tasking | 793 |  | 2022-11-28 | 2022-12-23 | 0
448 | 1.2 | 1.2.4.8.1.3.4 | C | Write flow meter test procedure and assemble test kit | Not Started | 7 | 4w | 2022-12-26 | 2023-01-20 | 447 | 0% |  |  | Deliverable supports FS1 tasking | 793 |  | 2022-12-26 | 2023-01-20 | 0
449 | 1.2 | 1.2.4.8.1.4 | C | CS MHP HW7: Select and procure MHP network switches (4), mount in protective enclosure | Not Started | 6 | 6w | 2022-06-01 | 2022-07-12 |  | 0% |  |  | PY4 carried in 1.2.4.2.3.1 - 24,40,3200 | 801 |  | 2022-06-01 | 2022-07-12 | 0
450 | 1.2 | 1.2.4.8.1.5 | P | CS MHP SW: Develop PLC-MHP MDS SW Functionality [Entire MHP system] | Not Started | 6 | 213d | 2022-07-13 | 2023-05-05 |  | 0% |  |  |  | 793 |  | 2022-07-13 | 2023-05-05 | 0
451 | 1.2 | 1.2.4.8.1.5.1 | C | Develop heater-based sensor readout; (heater temp/flow manifold pressures | Not Started | 7 | 3w | 2023-01-23 | 2023-02-10 | 448 | 0% |  |  | 1.2.4.3.4 relationship. Deliverable supports FS1 tasking. | 793 |  | 2023-01-23 | 2023-02-10 | 0
452 | 1.2 | 1.2.4.8.1.5.2 | C | Develop environmental sensor readout; (bldg temps, smoke, e-stop) | Not Started | 7 | 3w | 2023-02-13 | 2023-03-03 | 451 | 0% |  |  | 1.2.4.3.4 relationship. Deliverable supports FS1 tasking. | 793 |  | 2023-02-13 | 2023-03-03 | 0
453 | 1.2 | 1.2.4.8.1.5.3 | C | Develop heater control; (ON/OFF, Thermostat setpoint) | Not Started | 7 | 3w | 2023-03-06 | 2023-03-24 | 452 | 0% |  |  | 1.2.4.3.4 relationship. Deliverable supports FS1 tasking. | 793 |  | 2023-03-06 | 2023-03-24 | 0
454 | 1.2 | 1.2.4.8.1.5.4 | C | Configure network switch | Not Started | 7 | 2w | 2022-07-13 | 2022-07-26 | 449 | 0% |  |  | 1.2.4.2.3.1 relationship | 801 |  | 2022-07-13 | 2022-07-26 | 0
455 | 1.2 | 1.2.4.8.1.5.5 | C | Configure RTA gateway to M-DGH interface | Not Started | 7 | 2w | 2022-07-27 | 2022-08-09 | 436, 454 | 0% |  |  | 1.2.4.2.3.1 relationship | 801 |  | 2022-07-27 | 2022-08-09 | 0
456 | 1.2 | 1.2.4.8.1.5.6 | C | Configure M-DGHs | Not Started | 7 | 2w | 2022-08-10 | 2022-08-23 | 455 | 0% |  |  | 1.2.4.2.3.1 relationship | 946 |  | 2022-08-10 | 2022-08-23 | 0
457 | 1.2 | 1.2.4.8.1.5.7 | C | Implement interlocks | Not Started | 7 | 4w | 2023-03-27 | 2023-04-21 | 453, 456 | 0% |  |  | 1.2.4.3.4 relationship. Deliverable supports FS1 tasking. | 793 |  | 2023-03-27 | 2023-04-21 | 0
458 | 1.2 | 1.2.4.8.1.5.8 | C | Document Subsystem | Not Started | 7 | 2w | 2023-04-24 | 2023-05-05 | 457 | 0% |  |  | 1.2.4.1.4 relationship. Deliverable supports FS1 tasking. | 793 |  | 2023-04-24 | 2023-05-05 | 0
459 | 1.2 | 1.2.4.8.1.6 | C | CS MHP HW ready to pack for shipment | Not Started | 6 | 0 | 2023-04-14 | 2023-04-14 | 434, 438, 449, 454, 455, 456 | 0% |  |  | Vessel 2022-DNF | 801 |  | 2023-04-14 | 2023-04-14 | 0
460 | 1.2 | 1.2.4.8.2 | P | CS PHS & WT2 | Not Started | 5 | 299d | 2022-05-01 | 2023-06-21 |  | 0% |  |  |  | 760 |  | 2022-05-01 | 2023-06-21 | 0
461 | 1.2 | 1.2.4.8.2.1 | P | CS PHS HW1: Motor Drive Config & Install Kits | Not Started | 6 | 80d | 2022-07-01 | 2022-10-20 |  | 0% |  |  |  | 927 |  | 2022-07-01 | 2022-10-20 | 0
462 | 1.2 | 1.2.4.8.2.1.1 | C | Procure motor drives (2 transfer pumps) | Not Started | 7 | 8w | 2022-07-01 | 2022-08-25 |  | 0% |  |  | PY4 carried in 1.2.4.4.3 - 8,0,3000 | 934 |  | 2022-07-01 | 2022-08-25 | 0
463 | 1.2 | 1.2.4.8.2.1.2 | C | Configure VFDs with accessories, connection pigtails, document | Not Started | 7 | 6w | 2022-08-26 | 2022-10-06 | 462 | 0% |  |  | PY4 carried in 1.2.4.4.5 - 40,8,0 | 934 |  | 2022-08-26 | 2022-10-06 | 0
464 | 1.2 | 1.2.4.8.2.1.3 | C | Develop VFD installation strategy & document, procure materials | Not Started | 7 | 2w | 2022-10-07 | 2022-10-20 | 463 | 0% |  |  |  | 934 |  | 2022-10-07 | 2022-10-20 | 0
465 | 1.2 | 1.2.4.8.2.2 | P | CS PHS HW2: Estop Box Re-outfitting | Not Started | 6 | 40d | 2022-06-01 | 2022-07-26 |  | 0% |  |  |  | 989 |  | 2022-06-01 | 2022-07-26 | 0
466 | 1.2 | 1.2.4.8.2.2.1 | C | Select and procure E-stop relays | Not Started | 7 | 4w | 2022-06-01 | 2022-06-28 |  | 0% |  |  | PY4 carried in 1.2.4.5.4 - 4,0,200 | 996 |  | 2022-06-01 | 2022-06-28 | 0
467 | 1.2 | 1.2.4.8.2.2.2 | C | Develop and document E-stop box rewiring instructions | Not Started | 7 | 4w | 2022-06-29 | 2022-07-26 | 466 | 0% |  |  | PY4 carried in 1.2.4.5.4 - 4,0,0 | 996 |  | 2022-06-29 | 2022-07-26 | 0
468 | 1.2 | 1.2.4.8.2.3 | P | CS PHS HW3: Network Box Refurb & Config | Not Started | 6 | 100d | 2022-09-01 | 2023-01-18 |  | 0% |  |  |  | 863 |  | 2022-09-01 | 2023-01-18 | 0
469 | 1.2 | 1.2.4.8.2.3.1 | C | Select and procure PHS network switch, mount in protective enclosure | Not Started | 7 | 4w | 2022-09-01 | 2022-09-28 |  | 0% |  |  | PY4 carried in 1.2.4.2.3.2 - 16,32,1200 | 780 |  | 2022-09-01 | 2022-09-28 | 0
470 | 1.2 | 1.2.4.8.2.3.2 | C | Select and procure new power supplies for the network box, procure one RS-485 gateway | Not Started | 7 | 4w | 2022-09-29 | 2022-10-26 | 469 | 0% |  |  |  | 780 |  | 2022-09-29 | 2022-10-26 | 0
471 | 1.2 | 1.2.4.8.2.3.3 | C | Redesign and rebuild PHS network box with new I/O, document as-built configuration | Not Started | 7 | 4w | 2022-10-27 | 2022-11-23 | 470 | 0% |  |  |  | 780 |  | 2022-10-27 | 2022-11-23 | 0
472 | 1.2 | 1.2.4.8.2.3.4 | C | Indicate where approximately 20 sensor and network cables terminate in PHS and document config. plans | Not Started | 7 | 4w | 2022-11-24 | 2022-12-21 | 471 | 0% |  |  |  | 780 |  | 2022-11-24 | 2022-12-21 | 0
473 | 1.2 | 1.2.4.8.2.3.5 | C | Configure heater-mounted DGH modules, develop and document DGH installation and test plans | Not Started | 7 | 4w | 2022-12-22 | 2023-01-18 | 472 | 0% |  |  |  | 780 |  | 2022-12-22 | 2023-01-18 | 0
474 | 1.2 | 1.2.4.8.2.4 | C | CS PHS HW4: New E-stop Slap Switch & Box for Outdoor Location | Not Started | 6 | 2w | 2023-01-19 | 2023-02-01 | 473 | 0% |  |  |  | 780 |  | 2023-01-19 | 2023-02-01 | 0
475 | 1.2 | 1.2.4.8.2.5 | C | CS PHS HW5: Develop heater test procedures, configure test tools, document test plans | Not Started | 6 | 4w | 2023-02-02 | 2023-03-01 | 474 | 0% |  |  |  | 780 |  | 2023-02-02 | 2023-03-01 | 0
476 | 1.2 | 1.2.4.8.2.6 | P | CS PHS HW6: WT Level Sensors | Not Started | 6 | 90d | 2022-05-01 | 2022-09-01 |  | 0% |  |  |  | 962 |  | 2022-05-01 | 2022-09-01 | 0
477 | 1.2 | 1.2.4.8.2.6.1 | C | Select and procure new tank level and temperature sensors | Not Started | 7 | 2w | 2022-05-01 | 2022-05-12 |  | 0% |  |  | PY4 carried in 1.2.4.2.2.2 - 32,0,1200 | 969 |  | 2022-05-01 | 2022-05-12 | 0
478 | 1.2 | 1.2.4.8.2.6.2 | C | Install one level sensors in the test bed and operate over some period | Not Started | 7 | 8w | 2022-05-13 | 2022-07-07 | 477 | 0% |  |  | PY4 carried in 1.2.4.2.2.2 - 24,0,600 | 969 |  | 2022-05-13 | 2022-07-07 | 0
479 | 1.2 | 1.2.4.8.2.6.3 | C | Test level sensor tolerance of environmental conditions and system noise | Not Started | 7 | 2w | 2022-07-08 | 2022-07-21 | 478 | 0% |  |  | PY4 carried in 1.2.4.2.2.2 - 40,8,0 | 969 |  | 2022-07-08 | 2022-07-21 | 0
480 | 1.2 | 1.2.4.8.2.6.4 | C | Design and build cables for tank sensors | Not Started | 7 | 6w | 2022-07-22 | 2022-09-01 | 479 | 0% |  |  | PY4 carried in 1.2.4.2.2.2 - 16,32,400 | 969 |  | 2022-07-22 | 2022-09-01 | 0
481 | 1.2 | 1.2.4.8.2.7 | P | CS PHS HW7-8: Maintain Documentation, Prepare Field Plans | Not Started | 6 | 60d | 2023-03-30 | 2023-06-21 |  | 0% |  |  |  | 760 |  | 2023-03-30 | 2023-06-21 | 0
482 | 1.2 | 1.2.4.8.2.7.1 | C | Develop and document test plans for all PHS system components | Not Started | 7 | 8w | 2023-03-30 | 2023-05-24 | 475FS +4w | 0% |  |  | Deliverable supports FS1 tasking. | 760 |  | 2023-03-30 | 2023-05-24 | 0
483 | 1.2 | 1.2.4.8.2.7.2 | C | Review Gen-1 docs, identify where sensor connections terminated, plan for reconnection and test | Not Started | 7 | 4w | 2023-05-25 | 2023-06-21 | 482 | 0% |  |  | Deliverable supports FS1 tasking. | 760 |  | 2023-05-25 | 2023-06-21 | 0
484 | 1.2 | 1.2.4.8.2.8 | P | Develop PLC-PHS MDS SW Functionality | Not Started | 6 | 167d | 2022-09-29 | 2023-05-19 |  | 0% |  |  |  | 783 |  | 2022-09-29 | 2023-05-19 | 0
485 | 1.2 | 1.2.4.8.2.8.1 | C | Develop heater-based sensor readout; (heater temp/flow manifold pressures) | Not Started | 7 | 4w | 2022-12-26 | 2023-01-20 | 39FS +12w | 0% |  |  | Deliverable supports FS1 tasking. | 783 |  | 2022-12-26 | 2023-01-20 | 0
486 | 1.2 | 1.2.4.8.2.8.2 | C | Develop environmental sensor readout; (bldg temps, smoke, e-stop) | Not Started | 7 | 2w | 2023-01-23 | 2023-02-03 | 485 | 0% |  |  | Deliverable supports FS1 tasking. | 783 |  | 2023-01-23 | 2023-02-03 | 0
487 | 1.2 | 1.2.4.8.2.8.3 | C | Develop water tank sensors readout | Not Started | 7 | 3w | 2023-02-06 | 2023-02-24 | 486 | 0% |  |  | Deliverable supports FS1 tasking. | 783 |  | 2023-02-06 | 2023-02-24 | 0
488 | 1.2 | 1.2.4.8.2.8.4 | C | Develop heater control; (ON/OFF, Thermostat setpoint) | Not Started | 7 | 2w | 2023-02-27 | 2023-03-10 | 487 | 0% |  |  | Deliverable supports FS1 tasking. | 783 |  | 2023-02-27 | 2023-03-10 | 0
489 | 1.2 | 1.2.4.8.2.8.5 | C | Develop AB drive/pump control; (variable speed velocity drives) | Not Started | 7 | 4w | 2023-03-13 | 2023-04-07 | 488 | 0% |  |  | Deliverable supports FS1 tasking. | 783 |  | 2023-03-13 | 2023-04-07 | 0
490 | 1.2 | 1.2.4.8.2.8.6 | C | Configure/document network switch | Not Started | 7 | 2w | 2022-09-29 | 2022-10-12 | 469 | 0% |  |  |  | 863 |  | 2022-09-29 | 2022-10-12 | 0
491 | 1.2 | 1.2.4.8.2.8.7 | C | Configure/document RTA gateway to M-DGH interface | Not Started | 7 | 2w | 2022-10-13 | 2022-10-26 | 490 | 0% |  |  |  | 863 |  | 2022-10-13 | 2022-10-26 | 0
492 | 1.2 | 1.2.4.8.2.8.8 | C | Configure/document Point I/O Block | Not Started | 7 | 2w | 2022-10-27 | 2022-11-09 | 491 | 0% |  |  |  | 863 |  | 2022-10-27 | 2022-11-09 | 0
493 | 1.2 | 1.2.4.8.2.8.9 | C | Configure/document M-DGHs (Heater-mounted + all others) | Not Started | 7 | 2w | 2022-11-10 | 2022-11-23 | 492 | 0% |  |  |  | 880 |  | 2022-11-10 | 2022-11-23 | 0
494 | 1.2 | 1.2.4.8.2.8.10 | C | Implement interlocks | Not Started | 7 | 4w | 2023-04-10 | 2023-05-05 | 493, 489 | 0% |  |  | 1.2.4.3.4 relationship. Deliverable supports FS2 tasking. | 783 |  | 2023-04-10 | 2023-05-05 | 0
495 | 1.2 | 1.2.4.8.2.8.11 | C | Document Subsystem | Not Started | 7 | 2w | 2023-05-08 | 2023-05-19 | 494 | 0% |  |  | Deliverable supports FS2 tasking. | 783 |  | 2023-05-08 | 2023-05-19 | 0
496 | 1.2 | 1.2.4.8.2.9 | C | CS PHS HW ready to pack for shipment | Not Started | 6 | 0 | 2023-01-18 | 2023-01-18 | 461, 465, 468, 476, 490, 491, 492, 493 | 0% |  |  |  | 863 |  | 2023-01-18 | 2023-01-18 | 0
497 | 1.2 | 1.2.4.8.3 | P | CS TOS & Reels | Should have Started | 5 | 445d | 2022-01-03 | 2023-09-15 |  | 0% |  |  |  | 698 |  | 2022-01-03 | 2023-09-15 | 0
498 | 1.2 | 1.2.4.8.3.1 | P | CS TOS HW1: Motor Drive Config & Install Kits | Not Started | 6 | 130d | 2022-08-01 | 2023-01-27 |  | 0% |  |  |  | 863 |  | 2022-08-01 | 2023-01-27 | 0
499 | 1.2 | 1.2.4.8.3.1.1 | C | Procure TOS motor drives (16 VFDs) and accessories | Not Started | 7 | 4w | 2022-08-01 | 2022-08-26 |  | 0% |  |  | PY4 carried in PY4 (1.2.4.4.3) - 0,0,15000 | 738 |  | 2022-08-01 | 2022-08-26 | 0
500 | 1.2 | 1.2.4.8.3.1.2 | C | (PY4) Configure VFDs with accessories, connection pigtails, document | Not Started | 7 | 6w | 2022-08-29 | 2022-10-07 | 499 | 0% |  |  | PY4 carried in PY4 (1.2.4.4.5) - 120,64,6000 | 738 |  | 2022-08-29 | 2022-10-07 | 0
501 | 1.2 | 1.2.4.8.3.1.3 | C | Configure VFDs with accessories, connection pigtails, document | Not Started | 7 | 8w | 2022-10-10 | 2022-12-02 | 500 | 0% |  |  |  | 738 |  | 2022-10-10 | 2022-12-02 | 0
502 | 1.2 | 1.2.4.8.3.1.4 | C | Develop VFD mechanical and electrical installation strategies & document, procure materials | Not Started | 7 | 4w | 2022-12-05 | 2022-12-30 | 501 | 0% |  |  |  | 863 |  | 2022-12-05 | 2022-12-30 | 0
503 | 1.2 | 1.2.4.8.3.1.5 | C | SW configuration and autotuning, make plan - MDCR/LW, DSHR/LW, RWHR, RWCR, Tower Hoist | Not Started | 7 | 4w | 2023-01-02 | 2023-01-27 | 502 | 0% |  |  | Deliverable supports FS1 tasking. | 863 |  | 2023-01-02 | 2023-01-27 | 0
504 | 1.2 | 1.2.4.8.3.2 | P | CS TOS HW2: Estop | Not Started | 6 | 210d | 2022-09-01 | 2023-06-21 |  | 0% |  |  |  | 753 |  | 2022-09-01 | 2023-06-21 | 0
505 | 1.2 | 1.2.4.8.3.2.1 | C | Review Gen 1 documentation against as-built units located at PSL; mark up and update drawings | Not Started | 7 | 2w | 2022-09-01 | 2022-09-14 |  | 0% |  |  | PY4 carried in (1.2.4.1.4) - 80,0,0 | 720 |  | 2022-09-01 | 2022-09-14 | 0
506 | 1.2 | 1.2.4.8.3.2.2 | C | Document changes to E-stop and Reel stop interfaces to motor drives, procure materials, implement | Not Started | 7 | 4w | 2022-09-15 | 2022-10-12 | 505 | 0% |  |  |  | 720 |  | 2022-09-15 | 2022-10-12 | 0
507 | 1.2 | 1.2.4.8.3.2.3 | C | Test refurbished E-stop panels with reel safety junction boxes, I/O boxes, network boxes, drives | Not Started | 7 | 4w | 2022-10-13 | 2022-11-09 | 506 | 0% |  |  |  | 720 |  | 2022-10-13 | 2022-11-09 | 0
508 | 1.2 | 1.2.4.8.3.2.4 | C | Develop and document E-stop switch re-wiring plans for TOS, procure spare slap switches | Not Started | 7 | 8w | 2022-11-10 | 2023-01-04 | 507 | 0% |  |  | PY4 carried in (1.2.4.5.3) - 16,0,400 | 720 |  | 2022-11-10 | 2023-01-04 | 0
509 | 1.2 | 1.2.4.8.3.2.5 | C | (PY4) Design new E-stop controllers for TOS, build and test boxes | Not Started | 7 | 12w | 2023-01-05 | 2023-03-29 | 508 | 0% |  |  | PY4 carried in (1.2.4.4.5) - 40,16,1000 | 720 |  | 2023-01-05 | 2023-03-29 | 0
510 | 1.2 | 1.2.4.8.3.2.6 | C | Design new E-stop controllers for TOS, build and test boxes | Not Started | 7 | 12w | 2023-03-30 | 2023-06-21 | 509 | 0% |  |  |  | 720 |  | 2023-03-30 | 2023-06-21 | 0
511 | 1.2 | 1.2.4.8.3.3 | P | CS TOS HW3: Network & PLC | Not Started | 6 | 160d | 2022-12-01 | 2023-07-12 |  | 0% |  |  |  | 738 |  | 2022-12-01 | 2023-07-12 | 0
512 | 1.2 | 1.2.4.8.3.3.1 | C | Spec and procure new power supplies for TOS network boxes, procure DGH gateway, document changes | Not Started | 7 | 6w | 2022-12-01 | 2023-01-11 |  | 0% |  |  |  | 738 |  | 2022-12-01 | 2023-01-11 | 0
513 | 1.2 | 1.2.4.8.3.3.2 | C | Document plans for TOS network box upgrades, specify and procure tools and materials | Not Started | 7 | 4w | 2023-01-12 | 2023-02-08 | 512 | 0% |  |  |  | 738 |  | 2023-01-12 | 2023-02-08 | 0
514 | 1.2 | 1.2.4.8.3.3.3 | C | Spec TOS network switch location, spec cables to drives, I/O boxes, network box, DCC modem, PC, PLC, e-stop controller | Not Started | 7 | 6w | 2023-02-09 | 2023-03-22 | 513 | 0% |  |  |  | 745 |  | 2023-02-09 | 2023-03-22 | 0
515 | 1.2 | 1.2.4.8.3.3.4 | C | Design enclosures for TOS PLCs and attached I/O used for payout encoders, load cells; procure parts | Not Started | 7 | 8w | 2023-03-23 | 2023-05-17 | 514 | 0% |  |  |  | 745 |  | 2023-03-23 | 2023-05-17 | 0
516 | 1.2 | 1.2.4.8.3.3.5 | C | Construct enclosures for TOS PLCs and attached I/O , test | Not Started | 7 | 8w | 2023-05-18 | 2023-07-12 | 515 | 0% |  |  |  | 745 |  | 2023-05-18 | 2023-07-12 | 0
517 | 1.2 | 1.2.4.8.3.4 | P | CS TOS HW4: I/O Boxes | Not Started | 6 | 190d | 2022-05-02 | 2023-01-20 |  | 0% |  |  |  | 861 |  | 2022-05-02 | 2023-01-20 | 0
518 | 1.2 | 1.2.4.8.3.4.1 | C | Design I/O box upgrades using A-B Point I/O modules, install | Not Started | 7 | 16w | 2022-05-02 | 2022-08-19 |  | 0% |  |  | PY4 carried in (1.2.4.2.7) - 160,24,4000 | 868 |  | 2022-05-02 | 2022-08-19 | 0
519 | 1.2 | 1.2.4.8.3.4.2 | C | Test I/O boxes with pendants and motor drives | Not Started | 7 | 8w | 2022-08-22 | 2022-10-14 | 518 | 0% |  |  | PY4 carried in(1.2.4.2.7) - 32,0,0 | 868 |  | 2022-08-22 | 2022-10-14 | 0
520 | 1.2 | 1.2.4.8.3.4.3 | C | Design and build cables for I/O box connections to motor drives and E-stop box | Not Started | 7 | 8w | 2022-10-17 | 2022-12-09 | 519 | 0% |  |  | PY4 carried in (1.2.4.2.7) - 80,40,3000 | 868 |  | 2022-10-17 | 2022-12-09 | 0
521 | 1.2 | 1.2.4.8.3.4.4 | C | Rebuild two portable I/O boxes, test (used to operate return water cable reel motor drives with pendant) | Not Started | 7 | 6w | 2022-12-12 | 2023-01-20 | 520 | 0% |  |  | PY4 carried in (1.2.4.2.7) - 60,0,3000 | 868 |  | 2022-12-12 | 2023-01-20 | 0
522 | 1.2 | 1.2.4.8.3.5 | P | CS TOS HW5-6: Maintain Documentation, Develop Field Plans | Not Started | 6 | 40d | 2023-06-22 | 2023-08-16 |  | 0% |  |  |  | 720 |  | 2023-06-22 | 2023-08-16 | 0
523 | 1.2 | 1.2.4.8.3.5.1 | C | Develop and document on-ice test plans for E-stop, Reel-Stop, and Fault Detection hardware | Not Started | 7 | 4w | 2023-06-22 | 2023-07-19 | 510 | 0% |  |  |  | 720 |  | 2023-06-22 | 2023-07-19 | 0
524 | 1.2 | 1.2.4.8.3.5.2 | C | Develop and document on-ice test plans for integrated hardware | Not Started | 7 | 4w | 2023-07-20 | 2023-08-16 | 523 | 0% |  |  |  | 720 |  | 2023-07-20 | 2023-08-16 | 0
525 | 1.2 | 1.2.4.8.3.6 | P | CS TOS HW7: Tower Payout Encoders & Load Cells | Should have Started | 6 | 260d | 2022-01-03 | 2022-12-30 |  | 0% |  |  |  | 876 |  | 2022-01-03 | 2022-12-30 | 0
526 | 1.2 | 1.2.4.8.3.6.1 | C | Review documentation, specify hose and cable payout encoders, specify load cells, procure | Should have Started | 7 | 8w | 2022-01-03 | 2022-02-25 |  | 0% |  |  |  | 953 |  | 2022-01-03 | 2022-02-25 | 0
527 | 1.2 | 1.2.4.8.3.6.2 | C | Test load cells and payout encoders with PLC, verify functionality required for payout control, load sharing | Not Started | 7 | 8w | 2022-11-07 | 2022-12-30 | 526FS +36w | 0% |  |  |  | 773 |  | 2022-11-07 | 2022-12-30 | 0
528 | 1.2 | 1.2.4.8.3.7 | C | CS TOS HW8: Line Filters for All Drives in TOS2, Identify and Procure | Not Started | 6 | 8w | 2023-01-02 | 2023-02-24 | 527 | 0% |  |  | PY4 carried in (1.2.5.4.3) - 32,0,3200 | 773 |  | 2023-01-02 | 2023-02-24 | 0
529 | 1.2 | 1.2.4.8.3.8 | C | CS TOS HW9: Tower Hoist Reconnect Materials TOS2, Identify and Procure | Not Started | 6 | 4w | 2023-02-27 | 2023-03-24 | 528 | 0% |  |  |  | 773 |  | 2023-02-27 | 2023-03-24 | 0
530 | 1.2 | 1.2.4.8.3.9 | C | CS TOS HW10: Review deployment plans and HW, integrate with drill | Not Started | 6 | 10w | 2023-03-27 | 2023-06-02 | 529 | 0% |  |  |  | 773 |  | 2023-03-27 | 2023-06-02 | 0
531 | 1.2 | 1.2.4.8.3.10 | P | CS TOS Develop PLC Space SW Functionality | Not Started | 6 | 190d | 2022-12-26 | 2023-09-15 |  | 0% |  |  |  | 698 |  | 2022-12-26 | 2023-09-15 | 0
532 | 1.2 | 1.2.4.8.3.10.1 | C | Develop general control/monitoring software | Not Started | 7 | 10w | 2022-12-26 | 2023-03-03 | 39FS +12w | 0% |  |  | Deliverable supports FS1 tasking. | 698 |  | 2022-12-26 | 2023-03-03 | 0
533 | 1.2 | 1.2.4.8.3.10.2 | C | Develop reel control software(MCR/LW, DSHR/LW, RWHR, RWCR, Tower Winch) | Not Started | 7 | 6w | 2023-03-06 | 2023-04-14 | 532 | 0% |  |  | Deliverable supports FS1 tasking. | 698 |  | 2023-03-06 | 2023-04-14 | 0
534 | 1.2 | 1.2.4.8.3.10.3 | C | Develop tension-sharing algorithm software (MCR/LW, DSHR/LW) | Not Started | 7 | 12w | 2023-04-17 | 2023-07-07 | 533 | 0% |  |  | Deliverable supports FS1 tasking. | 698 |  | 2023-04-17 | 2023-07-07 | 0
535 | 1.2 | 1.2.4.8.3.10.4 | C | Develop drillhead data monitoring interface) | Not Started | 7 | 4w | 2023-07-10 | 2023-08-04 | 534 | 0% |  |  | Deliverable supports FS1 tasking. | 698 |  | 2023-07-10 | 2023-08-04 | 0
536 | 1.2 | 1.2.4.8.3.10.5 | C | Configure/document network switch | Not Started | 7 | 2w | 2023-02-09 | 2023-02-22 | 513 | 0% |  |  |  | 738 |  | 2023-02-09 | 2023-02-22 | 0
537 | 1.2 | 1.2.4.8.3.10.6 | C | Configure RTA gateway to M-DGH interface | Not Started | 7 | 2w | 2023-02-23 | 2023-03-08 | 536 | 0% |  |  |  | 738 |  | 2023-02-23 | 2023-03-08 | 0
538 | 1.2 | 1.2.4.8.3.10.7 | C | Configure M-DGHs | Not Started | 7 | 2w | 2023-03-09 | 2023-03-22 | 537 | 0% |  |  |  | 795 |  | 2023-03-09 | 2023-03-22 | 0
539 | 1.2 | 1.2.4.8.3.10.8 | C | Implement interlocks | Not Started | 7 | 4w | 2023-08-07 | 2023-09-01 | 538, 535 | 0% |  |  | 1.2.4.3.4 Relationship. Deliverable supports FS2 tasking. | 698 |  | 2023-08-07 | 2023-09-01 | 0
540 | 1.2 | 1.2.4.8.3.10.9 | C | Document Subsystem | Not Started | 7 | 2w | 2023-09-04 | 2023-09-15 | 539 | 0% |  |  | Deliverable supports FS2 tasking. | 698 |  | 2023-09-04 | 2023-09-15 | 0
541 | 1.2 | 1.2.4.8.3.11 | C | CS TOS HW ready to pack for shipment | Not Started | 6 | 0 | 2023-07-12 | 2023-07-12 | 499, 500, 501, 502, 504, 511, 517, 525, 536, 537, 538 | 0% |  |  | Comsur2023-DNF | 738 |  | 2023-07-12 | 2023-07-12 | 0
542 | 1.2 | 1.2.4.8.4 | P | CS Drillheads (CS HW, not actual drillheads) | Not Started | 5 | 110d | 2024-04-25 | 2024-09-25 |  | 0% |  |  |  | 433 |  | 2024-04-25 | 2024-09-25 | 0
543 | 1.2 | 1.2.4.8.4.1 | C | CS HW Drillhead sofware/hardware production version | Not Started | 6 | 8w | 2024-04-25 | 2024-06-19 | 886FS +10w | 0% |  |  | RaspPi drillhead configuration and testing Procure components Integrate into drillhead power supply chassis Finalize and test drillhead power supply chassis | 433 |  | 2024-04-25 | 2024-06-19 | 0
544 | 1.2 | 1.2.4.8.4.2 | P | Develop Linux SW Functionality | Not Started | 6 | 70d | 2024-06-20 | 2024-09-25 |  | 0% |  |  |  | 433 |  | 2024-06-20 | 2024-09-25 | 0
545 | 1.2 | 1.2.4.8.4.2.1 | C | Port C-Lang ingest process to rPI platform & test | Not Started | 7 | 6w | 2024-06-20 | 2024-07-31 | 543 | 0% |  |  |  | 433 |  | 2024-06-20 | 2024-07-31 | 0
546 | 1.2 | 1.2.4.8.4.2.2 | C | Integrate rPI platform into PLC infrastructure | Not Started | 7 | 6w | 2024-08-01 | 2024-09-11 | 545 | 0% |  |  |  | 433 |  | 2024-08-01 | 2024-09-11 | 0
547 | 1.2 | 1.2.4.8.4.2.3 | C | Document Subsystem | Not Started | 7 | 2w | 2024-09-12 | 2024-09-25 | 546 | 0% |  |  |  | 433 |  | 2024-09-12 | 2024-09-25 | 0
548 | 1.2 | 1.2.4.8.4.3 | C | CS Drillheads HW ready to pack for shipment | Not Started | 6 | 0 | 2024-09-25 | 2024-09-25 | 543, 544 | 0% |  |  | Vessel 2023-DNF | 433 |  | 2024-09-25 | 2024-09-25 | 0
549 | 1.2 | 1.2.4.8.5 | P | CS DCC, WT1, and Fuel Daytank | Not Started | 5 | 195d | 2022-12-26 | 2023-09-22 |  | 0% |  |  |  | 693 |  | 2022-12-26 | 2023-09-22 | 0
550 | 1.2 | 1.2.4.8.5.1 | C | Design, construct and test master E-stop controller, produce documentation and user instructions | Not Started | 6 | 16w | 2022-12-26 | 2023-04-14 | 39FS +12w | 0% |  |  |  | 693 |  | 2022-12-26 | 2023-04-14 | 0
551 | 1.2 | 1.2.4.8.5.2 | C | Design and construct general-purpose I/O box for fuel sled, gather required component stock to install | Not Started | 6 | 6w | 2023-04-17 | 2023-05-26 | 550 | 0% |  |  |  | 693 |  | 2023-04-17 | 2023-05-26 | 0
552 | 1.2 | 1.2.4.8.5.3 | C | Procure 20 kW three-phase heater for DCC and 208V breakers | Not Started | 6 | 3w | 2023-05-29 | 2023-06-16 | 551 | 0% |  |  |  | 693 |  | 2023-05-29 | 2023-06-16 | 0
553 | 1.2 | 1.2.4.8.5.4 | C | WT1 VT pump drives: procure, configure, rewire plan | Not Started | 6 | 8w | 2023-06-19 | 2023-08-11 | 552 | 0% |  |  |  | 693 |  | 2023-06-19 | 2023-08-11 | 0
554 | 1.2 | 1.2.4.8.5.5 | C | WT1 VT pump drives: final configure | Not Started | 6 | 2w | 2023-08-14 | 2023-08-25 | 553 | 0% |  |  |  | 693 |  | 2023-08-14 | 2023-08-25 | 0
555 | 1.2 | 1.2.4.8.5.6 | C | WT1 VT pump drives: install plan and kit | Not Started | 6 | 4w | 2023-08-28 | 2023-09-22 | 554 | 0% |  |  |  | 693 |  | 2023-08-28 | 2023-09-22 | 0
556 | 1.2 | 1.2.4.8.5.7 | P | Develop PLC-Fuel DayTank SW Functionality | Not Started | 6 | 80d | 2023-05-29 | 2023-09-15 |  | 0% |  |  |  | 698 |  | 2023-05-29 | 2023-09-15 | 0
557 | 1.2 | 1.2.4.8.5.7.1 | C | Develop fuel system sensor readout ; (multi-level tank status, control relay status ) | Not Started | 7 | 6w | 2023-05-29 | 2023-07-07 | 551 | 0% |  |  |  | 698 |  | 2023-05-29 | 2023-07-07 | 0
558 | 1.2 | 1.2.4.8.5.7.2 | C | Configure/document Point I/O Block | Not Started | 7 | 4w | 2023-07-10 | 2023-08-04 | 557 | 0% |  |  |  | 698 |  | 2023-07-10 | 2023-08-04 | 0
559 | 1.2 | 1.2.4.8.5.7.3 | C | Document Subsystem | Not Started | 7 | 2w | 2023-08-07 | 2023-08-18 | 558 | 0% |  |  |  | 698 |  | 2023-08-07 | 2023-08-18 | 0
560 | 1.2 | 1.2.4.8.5.7.4 | C | Implement interlocks | Not Started | 7 | 4w | 2023-08-21 | 2023-09-15 | 559 | 0% |  |  |  | 698 |  | 2023-08-21 | 2023-09-15 | 0
561 | 1.2 | 1.2.4.8.5.8 | C | CS DCC HW ready to pack for shipment | Not Started | 6 | 0 | 2023-09-22 | 2023-09-22 | 550, 551, 552, 553, 554, 555, 556 | 0% |  |  | Vessel 2023-DNF | 693 |  | 2023-09-22 | 2023-09-22 | 0
562 | 1.2 | 1.2.4.8.6 | P | CS Gensets | Not Started | 5 | 130d | 2024-03-14 | 2024-09-11 |  | 0% |  |  |  | 443 |  | 2024-03-14 | 2024-09-11 | 0
563 | 1.2 | 1.2.4.8.6.1 | C | CS Gensets HW - identify, procure, assemble | Not Started | 6 | 10w | 2024-03-14 | 2024-05-22 | 886FS +4w | 0% |  |  |  | 443 |  | 2024-03-14 | 2024-05-22 | 0
564 | 1.2 | 1.2.4.8.6.2 | P | Develop PLC-Gens MDSs SW Functionality | Not Started | 6 | 80d | 2024-05-23 | 2024-09-11 |  | 0% |  |  |  | 443 |  | 2024-05-23 | 2024-09-11 | 0
565 | 1.2 | 1.2.4.8.6.2.1 | C | Develop sensor readout; (bldg temps, fuel temps, supply/return water temps) | Not Started | 7 | 4w | 2024-05-23 | 2024-06-19 | 563 | 0% |  |  |  | 443 |  | 2024-05-23 | 2024-06-19 | 0
566 | 1.2 | 1.2.4.8.6.2.2 | C | Develop sensor readout; (engine jacket temps, exhaust temps, drip pan status) | Not Started | 7 | 4w | 2024-06-20 | 2024-07-17 | 565 | 0% |  |  |  | 443 |  | 2024-06-20 | 2024-07-17 | 0
567 | 1.2 | 1.2.4.8.6.2.3 | C | Configure/document network switch | Not Started | 7 | 2w | 2024-07-18 | 2024-07-31 | 566 | 0% |  |  |  | 443 |  | 2024-07-18 | 2024-07-31 | 0
568 | 1.2 | 1.2.4.8.6.2.4 | C | Configure/document RTA gateway to M-DGH interface | Not Started | 7 | 2w | 2024-08-01 | 2024-08-14 | 567 | 0% |  |  |  | 443 |  | 2024-08-01 | 2024-08-14 | 0
569 | 1.2 | 1.2.4.8.6.2.5 | C | Configure/document M-DGHs | Not Started | 7 | 2w | 2024-08-15 | 2024-08-28 | 568 | 0% |  |  |  | 443 |  | 2024-08-15 | 2024-08-28 | 0
570 | 1.2 | 1.2.4.8.6.2.6 | C | Document Subsystem | Not Started | 7 | 2w | 2024-08-29 | 2024-09-11 | 569 | 0% |  |  |  | 443 |  | 2024-08-29 | 2024-09-11 | 0
571 | 1.2 | 1.2.4.8.6.3 | C | CS Gensets HW ready to pack for shipment | Not Started | 6 | 0 | 2024-08-28 | 2024-08-28 | 563, 569 | 0% |  |  | Vessel 2023-DNF | 453 |  | 2024-08-28 | 2024-08-28 | 0
572 | 1.2 | 1.2.4.8.7 | P | CS HPP | Not Started | 5 | 230d | 2022-10-03 | 2023-08-18 |  | 0% |  |  |  | 718 |  | 2022-10-03 | 2023-08-18 | 0
573 | 1.2 | 1.2.4.8.7.1 | P | CS HPP HW1: Motor Drive Config & Install Kits | Not Started | 6 | 100d | 2022-10-03 | 2023-02-17 |  | 0% |  |  |  | 808 |  | 2022-10-03 | 2023-02-17 | 0
574 | 1.2 | 1.2.4.8.7.1.1 | C | Procure HPP motor drives (four PF-755 50 hp vfds) (8 hours, task is finished) | Not Started | 7 | 8w | 2022-10-03 | 2022-11-25 | 39 | 0% |  |  | PY4 carried in (1.2.4.4.3) - 0,0,5000 | 848 |  | 2022-10-03 | 2022-11-25 | 0
575 | 1.2 | 1.2.4.8.7.1.2 | C | Configure four HPP VFDs with accessories, connection pigtails, document | Not Started | 7 | 4w | 2022-11-28 | 2022-12-23 | 574 | 0% |  |  | PY4 carried in (1.2.4.4.5) - 80,16,0 | 848 |  | 2022-11-28 | 2022-12-23 | 0
576 | 1.2 | 1.2.4.8.7.1.3 | C | Develop VFD mechanical and electrical installation strategies & document, procure materials | Not Started | 7 | 4w | 2022-12-26 | 2023-01-20 | 575 | 0% |  |  |  | 848 |  | 2022-12-26 | 2023-01-20 | 0
577 | 1.2 | 1.2.4.8.7.1.4 | C | SW configuration and autotuning | Not Started | 7 | 4w | 2023-01-23 | 2023-02-17 | 576 | 0% |  |  |  | 848 |  | 2023-01-23 | 2023-02-17 | 0
578 | 1.2 | 1.2.4.8.7.2 | P | CS HPP HW2: Signal and Readout Definition, Procedures | Not Started | 6 | 50d | 2022-10-03 | 2022-12-09 |  | 0% |  |  |  | 858 |  | 2022-10-03 | 2022-12-09 | 0
579 | 1.2 | 1.2.4.8.7.2.1 | C | Define requirements and procedures for reading signals applied to HPP motor drives | Not Started | 7 | 4w | 2022-10-03 | 2022-10-28 | 39 | 0% |  |  |  | 898 |  | 2022-10-03 | 2022-10-28 | 0
580 | 1.2 | 1.2.4.8.7.2.2 | C | Define method of verifying sensor readout accuracy (reading vs stimulus) | Not Started | 7 | 4w | 2022-10-31 | 2022-11-25 | 579 | 0% |  |  |  | 898 |  | 2022-10-31 | 2022-11-25 | 0
581 | 1.2 | 1.2.4.8.7.2.3 | C | Develop and document test procedures for on-ice personnel | Not Started | 7 | 2w | 2022-11-28 | 2022-12-09 | 580 | 0% |  |  |  | 898 |  | 2022-11-28 | 2022-12-09 | 0
582 | 1.2 | 1.2.4.8.7.3 | P | CS HPP HW3: PLC Hardware, Box Build, Testing | Not Started | 6 | 130d | 2022-10-31 | 2023-04-28 |  | 0% |  |  |  | 758 |  | 2022-10-31 | 2023-04-28 | 0
583 | 1.2 | 1.2.4.8.7.3.1 | C | Define core HPP PLC functions and requirements, define needed I/O connections | Not Started | 7 | 6w | 2022-10-31 | 2022-12-09 | 39FS +4w | 0% |  |  |  | 798 |  | 2022-10-31 | 2022-12-09 | 0
584 | 1.2 | 1.2.4.8.7.3.2 | C | Select PLC, Enclosure, Power supplies, I/O expansion cards, power distribution, connectors and cables | Not Started | 7 | 4w | 2022-12-12 | 2023-01-06 | 583 | 0% |  |  |  | 798 |  | 2022-12-12 | 2023-01-06 | 0
585 | 1.2 | 1.2.4.8.7.3.3 | C | Design and Construct PLC enclosure | Not Started | 7 | 8w | 2023-01-09 | 2023-03-03 | 584 | 0% |  |  |  | 798 |  | 2023-01-09 | 2023-03-03 | 0
586 | 1.2 | 1.2.4.8.7.3.4 | C | Test HPP PLC enclosure with HPP Network box | Not Started | 7 | 8w | 2023-03-06 | 2023-04-28 | 585 | 0% |  |  |  | 798 |  | 2023-03-06 | 2023-04-28 | 0
587 | 1.2 | 1.2.4.8.7.4 | P | CS HPP HW4: Charge Pump Motor Controllers | Not Started | 6 | 110d | 2022-11-28 | 2023-04-28 |  | 0% |  |  |  | 758 |  | 2022-11-28 | 2023-04-28 | 0
588 | 1.2 | 1.2.4.8.7.4.1 | C | Install PF-70 motor drive in test bed, configure with local control system, test | Not Started | 7 | 8w | 2022-11-28 | 2023-01-20 | 39FS +8w | 0% |  |  | PY4 carried in (1.2.4.4.4) - 40,0,0 | 798 |  | 2022-11-28 | 2023-01-20 | 0
589 | 1.2 | 1.2.4.8.7.4.2 | C | Procure additional drives for charge pumps (4), AC and network pigtail materials | Not Started | 7 | 10w | 2023-01-23 | 2023-03-31 | 588 | 0% |  |  |  | 798 |  | 2023-01-23 | 2023-03-31 | 0
590 | 1.2 | 1.2.4.8.7.4.3 | C | Connectorize four drives with power and network pigtails, test each in test bed | Not Started | 7 | 4w | 2023-04-03 | 2023-04-28 | 589 | 0% |  |  |  | 798 |  | 2023-04-03 | 2023-04-28 | 0
591 | 1.2 | 1.2.4.8.7.5 | P | CS HPP HW5: Sensor Box Reconfig & Test | Not Started | 6 | 80d | 2022-12-26 | 2023-04-14 |  | 0% |  |  |  | 768 |  | 2022-12-26 | 2023-04-14 | 0
592 | 1.2 | 1.2.4.8.7.5.1 | C | Build and test a portable network box for sensor box testing (Gateway, power supply, connectors) | Not Started | 7 | 8w | 2022-12-26 | 2023-02-17 | 39FS +12w | 0% |  |  | PY4 carried in (1.2.4.2.2.1) - 24,16,1200 | 768 |  | 2022-12-26 | 2023-02-17 | 0
593 | 1.2 | 1.2.4.8.7.5.2 | C | Procure and configure test equipment needed to calibrate individual sensors, provide user instructions | Not Started | 7 | 4w | 2023-02-20 | 2023-03-17 | 592 | 0% |  |  | PY4 carried in (1.2.4.2.2.1) - 24,8,800 | 768 |  | 2023-02-20 | 2023-03-17 | 0
594 | 1.2 | 1.2.4.8.7.5.3 | C | Connect HPP sensor readout box with sensor box, connect to network box, test all sensors and document | Not Started | 7 | 4w | 2023-03-20 | 2023-04-14 | 593 | 0% |  |  | PY4 carried in (1.2.4.2.2.1) - 40,24,0 | 768 |  | 2023-03-20 | 2023-04-14 | 0
595 | 1.2 | 1.2.4.8.7.6 | C | CS HPP HW6: Sensor Box DGH Reconfig & Test | Not Started | 6 | 8w | 2023-04-17 | 2023-06-09 | 594 | 0% |  |  | PY4 carried in (1.2.4.2.2.1, 1.2.4.3.2.3) - 80,0,0 | 768 |  | 2023-04-17 | 2023-06-09 | 0
596 | 1.2 | 1.2.4.8.7.7 | P | CS HPP HW7: Estop box Re-outfitting | Not Started | 6 | 50d | 2023-04-17 | 2023-06-23 |  | 0% |  |  |  | 718 |  | 2023-04-17 | 2023-06-23 | 0
597 | 1.2 | 1.2.4.8.7.7.1 | C | Select and procure E-stop relays for pump VFD Enable signals | Not Started | 7 | 4w | 2023-04-17 | 2023-05-12 | 602 | 0% |  |  |  | 758 |  | 2023-04-17 | 2023-05-12 | 0
598 | 1.2 | 1.2.4.8.7.7.2 | C | Develop and document rewiring instructions for HPP E-stop box | Not Started | 7 | 6w | 2023-05-15 | 2023-06-23 | 597 | 0% |  |  |  | 758 |  | 2023-05-15 | 2023-06-23 | 0
599 | 1.2 | 1.2.4.8.7.8 | P | CS HPP HW8: Network Box Refurb & Config | Not Started | 6 | 130d | 2022-11-28 | 2023-05-26 |  | 0% |  |  |  | 738 |  | 2022-11-28 | 2023-05-26 | 0
600 | 1.2 | 1.2.4.8.7.8.1 | C | Select and procure a wall-mount managed Ethernet switch for the HPP electrical closet | Not Started | 7 | 4w | 2022-11-28 | 2022-12-23 | 39FS +8w | 0% |  |  | PY4 carried in (1.2.4.2.1.1) - 8,0,1400 | 758 |  | 2022-11-28 | 2022-12-23 | 0
601 | 1.2 | 1.2.4.8.7.8.2 | C | Select and procure new power supplies for the network box, procure one RS-485 gateway | Not Started | 7 | 4w | 2022-12-26 | 2023-01-20 | 600 | 0% |  |  | PY4 carried in (1.2.4.2.1.1) - 8,0,400 | 758 |  | 2022-12-26 | 2023-01-20 | 0
602 | 1.2 | 1.2.4.8.7.8.3 | C | Refurbish the HPP network box, document as-built configureation | Not Started | 7 | 12w | 2023-01-23 | 2023-04-14 | 601 | 0% |  |  | PY4 carried in (1.2.4.2.1.1) - 40,8,0 | 758 |  | 2023-01-23 | 2023-04-14 | 0
603 | 1.2 | 1.2.4.8.7.8.4 | C | Select and procure HPP network switch enclosure, integrate with switch | Not Started | 7 | 6w | 2023-04-17 | 2023-05-26 | 602 | 0% |  |  | PY4 carried in (1.2.4.2.1.1) - 16,24,1200 | 778 |  | 2023-04-17 | 2023-05-26 | 0
604 | 1.2 | 1.2.4.8.7.9 | P | CS HPP HW9-10: Maintain Documentation, Prepare Field Plans | Not Started | 6 | 40d | 2023-06-26 | 2023-08-18 |  | 0% |  |  |  | 718 |  | 2023-06-26 | 2023-08-18 | 0
605 | 1.2 | 1.2.4.8.7.9.1 | C | Develop and document test plans for all HPP system components | Not Started | 7 | 4w | 2023-06-26 | 2023-07-21 | 573, 578, 582, 587, 591, 596, 599 | 0% |  |  |  | 718 |  | 2023-06-26 | 2023-07-21 | 0
606 | 1.2 | 1.2.4.8.7.9.2 | C | Review Gen-1 docs, identify where sensor connections terminated, plan for field integration and test | Not Started | 7 | 4w | 2023-07-24 | 2023-08-18 | 605 | 0% |  |  |  | 718 |  | 2023-07-24 | 2023-08-18 | 0
607 | 1.2 | 1.2.4.8.7.10 | P | Develop Local HPP PLC SW Functionality | Not Started | 6 | 130d | 2022-12-26 | 2023-06-23 |  | 0% |  |  |  | 758 |  | 2022-12-26 | 2023-06-23 | 0
608 | 1.2 | 1.2.4.8.7.10.1 | C | Develop water path sensor readout; (pressure, temp, flow) | Not Started | 7 | 4w | 2022-12-26 | 2023-01-20 | 39FS +12w | 0% |  |  | Deliverable supports FS1 tasking. | 751 |  | 2022-12-26 | 2023-01-20 | 0
609 | 1.2 | 1.2.4.8.7.10.2 | C | Develop environmental sensor readout; (bldg temps, smoke, e-stop) | Not Started | 7 | 2w | 2023-01-23 | 2023-02-03 | 608 | 0% |  |  | Deliverable supports FS1 tasking. | 751 |  | 2023-01-23 | 2023-02-03 | 0
610 | 1.2 | 1.2.4.8.7.10.3 | C | Build shared data-tagging w/ DCC core controller | Not Started | 7 | 4w | 2023-02-06 | 2023-03-03 | 609 | 0% |  |  |  | 751 |  | 2023-02-06 | 2023-03-03 | 0
611 | 1.2 | 1.2.4.8.7.10.4 | C | Develop AB drive/pump control; (variable speed velocity drives) | Not Started | 7 | 4w | 2023-03-06 | 2023-03-31 | 610 | 0% |  |  |  | 751 |  | 2023-03-06 | 2023-03-31 | 0
612 | 1.2 | 1.2.4.8.7.10.5 | C | Develop charge pump control; (variable speed velocity drives OR Soft Starter) | Not Started | 7 | 2w | 2023-04-03 | 2023-04-14 | 611 | 0% |  |  |  | 751 |  | 2023-04-03 | 2023-04-14 | 0
613 | 1.2 | 1.2.4.8.7.10.6 | C | Configure/document network switch | Not Started | 7 | 2w | 2023-04-17 | 2023-04-28 | 612 | 0% |  |  |  | 751 |  | 2023-04-17 | 2023-04-28 | 0
614 | 1.2 | 1.2.4.8.7.10.7 | C | Configure/document RTA gateway to M-DGH interface | Not Started | 7 | 2w | 2023-05-01 | 2023-05-12 | 613 | 0% |  |  |  | 751 |  | 2023-05-01 | 2023-05-12 | 0
615 | 1.2 | 1.2.4.8.7.10.8 | C | Configure/document M-DGHs | Not Started | 7 | 2w | 2023-05-15 | 2023-05-26 | 614 | 0% |  |  |  | 758 |  | 2023-05-15 | 2023-05-26 | 0
616 | 1.2 | 1.2.4.8.7.10.9 | C | Implement interlocks | Not Started | 7 | 2w | 2023-05-29 | 2023-06-09 | 615 | 0% |  |  | Deliverable supports FS2 tasking. | 758 |  | 2023-05-29 | 2023-06-09 | 0
617 | 1.2 | 1.2.4.8.7.10.10 | C | Document Subsystem | Not Started | 7 | 2w | 2023-06-12 | 2023-06-23 | 616 | 0% |  |  | 1.2.4.3.4 relationship. Deliverable supports FS2 tasking. | 758 |  | 2023-06-12 | 2023-06-23 | 0
618 | 1.2 | 1.2.4.8.7.11 | C | CS HPP HW Ready to Pack for Shipment | Not Started | 6 | 0 | 2023-06-23 | 2023-06-23 | 573, 578, 582, 587, 591, 596, 599, 610, 611, 612, 613, 614, 615 | 0% |  |  |  | 751 |  | 2023-06-23 | 2023-06-23 | 0
619 | 1.2 | 1.2.4.8.8 | P | CS ARA Rodwell System | Not Started | 5 | 260d | 2022-05-02 | 2023-04-28 |  | 0% |  |  |  | 791 |  | 2022-05-02 | 2023-04-28 | 0
620 | 1.2 | 1.2.4.8.8.1 | P | CS ARA Rodwell System HW | Not Started | 6 | 140d | 2022-05-02 | 2022-11-11 |  | 0% |  |  |  | 918 |  | 2022-05-02 | 2022-11-11 | 0
621 | 1.2 | 1.2.4.8.8.1.1 | C | CS ARA HW: new system controls and tie-in design | Not Started | 7 | 8w | 2022-05-02 | 2022-06-24 |  | 0% |  |  |  | 798 |  | 2022-05-02 | 2022-06-24 | 0
622 | 1.2 | 1.2.4.8.8.1.2 | C | Review ARA drill system documentation and develop a new configuration for Rodewell | Not Started | 7 | 4w | 2022-06-27 | 2022-07-22 | 621 | 0% |  |  | 1.2.6.6.1 relationship. | 798 |  | 2022-06-27 | 2022-07-22 | 0
623 | 1.2 | 1.2.4.8.8.1.3 | C | Select and procure new motor drives for Rodwell pump and combo-cable winch | Not Started | 7 | 6w | 2022-07-25 | 2022-09-02 | 622 | 0% |  |  | 1.2.6.6.2 relationship. | 798 |  | 2022-07-25 | 2022-09-02 | 0
624 | 1.2 | 1.2.4.8.8.1.4 | C | Procure gateway for monitoring control pane instruments, plan for installation in the control box | Not Started | 7 | 2w | 2022-09-05 | 2022-09-16 | 623 | 0% |  |  | 1.2.6.6.2 relationship. | 798 |  | 2022-09-05 | 2022-09-16 | 0
625 | 1.2 | 1.2.4.8.8.1.5 | C | Select and procure new hardware to capture flow sensor pulse rates (A-B I/O hardware) | Not Started | 7 | 4w | 2022-09-19 | 2022-10-14 | 624 | 0% |  |  | 1.2.6.6.2 relationship. | 798 |  | 2022-09-19 | 2022-10-14 | 0
626 | 1.2 | 1.2.4.8.8.1.6 | C | Design and Build network cable, E-stop cable, for connecting rodwell system to drill system | Not Started | 7 | 4w | 2022-10-17 | 2022-11-11 | 625 | 0% |  |  | 1.2.6.6.2 relationship. | 798 |  | 2022-10-17 | 2022-11-11 | 0
627 | 1.2 | 1.2.4.8.8.2 | P | Develop PLC-Rodwell SW Functionality | Not Started | 6 | 120d | 2022-11-14 | 2023-04-28 |  | 0% |  |  |  | 798 |  | 2022-11-14 | 2023-04-28 | 0
628 | 1.2 | 1.2.4.8.8.2.1 | C | Develop ARA-drill sensor readout; (heater flows, head press, tank level) | Not Started | 7 | 4w | 2022-11-14 | 2022-12-09 | 626 | 0% |  |  |  | 798 |  | 2022-11-14 | 2022-12-09 | 0
629 | 1.2 | 1.2.4.8.8.2.2 | C | Develop AB drive/pump control; (variable speed velocity drives) | Not Started | 7 | 6w | 2022-12-12 | 2023-01-20 | 628 | 0% |  |  |  | 798 |  | 2022-12-12 | 2023-01-20 | 0
630 | 1.2 | 1.2.4.8.8.2.3 | C | Configure/document Point I/O Block | Not Started | 7 | 4w | 2023-01-23 | 2023-02-17 | 629 | 0% |  |  |  | 798 |  | 2023-01-23 | 2023-02-17 | 0
631 | 1.2 | 1.2.4.8.8.2.4 | C | Configure/document network switch | Not Started | 7 | 2w | 2023-02-20 | 2023-03-03 | 630 | 0% |  |  |  | 798 |  | 2023-02-20 | 2023-03-03 | 0
632 | 1.2 | 1.2.4.8.8.2.5 | C | Configure/document RTA gateway to M-DGH interface | Not Started | 7 | 2w | 2023-03-06 | 2023-03-17 | 631 | 0% |  |  |  | 798 |  | 2023-03-06 | 2023-03-17 | 0
633 | 1.2 | 1.2.4.8.8.2.6 | C | Configure/document M-DGHs | Not Started | 7 | 2w | 2023-03-20 | 2023-03-31 | 632 | 0% |  |  |  | 798 |  | 2023-03-20 | 2023-03-31 | 0
634 | 1.2 | 1.2.4.8.8.2.7 | C | Implement interlocks | Not Started | 7 | 2w | 2023-04-03 | 2023-04-14 | 633 | 0% |  |  | 1.2.4.3.4 relationship. Deliverable supports FS2 tasking. | 798 |  | 2023-04-03 | 2023-04-14 | 0
635 | 1.2 | 1.2.4.8.8.2.8 | C | Document Subsystem | Not Started | 7 | 2w | 2023-04-17 | 2023-04-28 | 634 | 0% |  |  | Deliverable supports FS2 tasking. | 798 |  | 2023-04-17 | 2023-04-28 | 0
636 | 1.2 | 1.2.4.8.8.3 | C | CS ARA HW Ready to Pack for Shipment | Not Started | 6 | 0 | 2023-03-31 | 2023-03-31 | 620, 628, 629, 630, 631, 632, 633 | 0% |  |  | Comsur 2023-DNF | 818 |  | 2023-03-31 | 2023-03-31 | 0
637 | 1.2 | 1.2.5 | P | Power Generation & Distribution | Started | 3 | 1873d | 2019-01-24 | 2026-04-10 |  | 63% |  |  |  | 37 |  | 2019-01-24 | 2026-04-10 | 0
638 | 1.2 | 1.2.5.1 | P | Generator 1 | Complete | 4 | 186d | 2019-01-24 | 2019-10-10 |  | 100% |  |  |  | 1724 |  | 2019-01-24 | 2019-10-10 | 0
639 | 1.2 | 1.2.5.1.1 | C | GEN-1: Arrange Retro from McMurdo to PTH (Vessel) | Complete | 5 | 60d | 2019-01-24 | 2019-04-17 |  | 100% |  |  |  | 1714 |  | 2019-01-24 | 2019-04-17 | 0
640 | 1.2 | 1.2.5.1.2 | C | GEN-1: Transport from PTH to CAT Vendor | Complete | 5 | 10d | 2019-04-18 | 2019-05-01 | 639 | 100% | Delayed NSF custodian approval |  | Dedicated truck - Port Hueneme to CAT shop $7,000 typ PTH-PSL. Reduced to $4,000 for plan to find CAT shop in CA | 1714 |  | 2019-04-18 | 2019-05-01 | 0
641 | 1.2 | 1.2.5.1.3 | C | GEN-1: Specify SOW and Integration | Complete | 5 | 10d | 2019-05-02 | 2019-05-15 | 640 | 100% |  |  | Travel - Engineer travel to CAT shop to review/define SOW with PP engineers | 1714 |  | 2019-05-02 | 2019-05-15 | 0
642 | 1.2 | 1.2.5.1.4 | C | GEN-1: Generator Overhaul by Vendor | Complete | 5 | 100d | 2019-05-02 | 2019-09-18 | 641SS | 100% |  |  | Capital Cost - Unknown at time of schedule/budget development. ASC recalls other GEN overhauls at <$100k 8 years ago. This figure allows a safety margin of the unknown additional SOW or inflationary costs | 1724 |  | 2019-05-02 | 2019-09-18 | 0
643 | 1.2 | 1.2.5.1.5 | C | GEN-1: Acceptance Testing (at vendor) | Complete | 5 | 5d | 2019-09-19 | 2019-09-25 | 642 | 100% |  |  | Travel - 2 Engineers for testing and approval | 1724 |  | 2019-09-19 | 2019-09-25 | 0
644 | 1.2 | 1.2.5.1.6 | C | GEN-1: Transport from Vendor to PTH | Complete | 5 | 10d | 2019-09-26 | 2019-10-09 | 643 | 100% |  |  | Dedicated truck - CAT shop to Port Hueneme, CA $7,000 typ PSL-PTH. Reduced to $4,000 for plan to find CAT shop in CA | 1724 |  | 2019-09-26 | 2019-10-09 | 0
645 | 1.2 | 1.2.5.1.7 | C | GEN-1: Ship from PTH (VSL-ZCM, Traverse-NPX) | Complete | 5 | 1d | 2019-10-10 | 2019-10-10 | 644 | 100% | GEN-1 is in McMurdo awaiting transport to Pole in 20/21 |  |  | 1724 |  | 2019-10-10 | 2019-10-10 | 0
646 | 1.2 | 1.2.5.2 | P | Generators 2, 3, and PDM | Started | 4 | 1230d | 2019-03-18 | 2023-12-04 |  | 74% |  |  | Arctic Energy's quote for this structure was $500k | 643 |  | 2019-03-18 | 2023-12-04 | 0
647 | 1.2 | 1.2.5.2.1 | C | GEN-2, 3, PDM - Arrange Testing/Repairs at McMurdo | Complete | 5 | 160d | 2019-03-18 | 2019-10-25 |  | 100% |  |  | Develop testing plans, locate engineering drawings, gather historical information, etc. Design Review, Field Input, Planning | 1713 |  | 2019-03-18 | 2019-10-25 | 0
648 | 1.2 | 1.2.5.2.2 | C | GEN-2 - Develop SOW for Gen 2 Repairs Subcontract in New Zealand & Communicate with Vendor | Not Started | 5 | 40d | 2022-03-01 | 2022-04-25 |  | 0% | Write SOW, evaluate responses, and communicate with chosen vendor |  | Sub-Contract to include: - Review of engineering drawings - Tune-up SOW development - CAT Engineer deployment to McMurdo for ~1 month - Perform testing on Gen2 & 3 - Perform tune-up and on-site repairs activities - Develop SOW for any future/recommended repairs | 1062 |  | 2022-03-01 | 2022-04-25 | 0
649 | 1.2 | 1.2.5.2.3 | C | GEN-2, 3, PDM - Procure Testing Equipment/Repair Parts | Complete | 5 | 227d | 2020-10-01 | 2021-08-13 |  | 100% | Spare parts list developed, still researching requirements |  | Syncronize components Replacement switchgear Container repair parts | 1198 |  | 2020-10-01 | 2021-08-13 | 0
650 | 1.2 | 1.2.5.2.4 | C | GEN 1, 2, 3, PDM - Procure/Fabricate Aluminum Skis | Complete | 5 | 45d | 2020-10-01 | 2020-12-02 | 649SS | 100% | Skis required, drawings complete, out for bid |  | $20,000 - Aluminum I-Beams, Plates, Bolts, Hitch Point, Tow Bars, Etc | 1425 |  | 2020-10-01 | 2020-12-02 | 0
651 | 1.2 | 1.2.5.2.5 | C | GEN-2, 3, PDM - Procure Repair Parts | Complete | 5 | 113d | 2021-03-03 | 2021-08-06 |  | 100% |  |  |  | 1248 |  | 2021-03-03 | 2021-08-06 | 0
652 | 1.2 | 1.2.5.2.6 | C | GEN-1, 2, 3 - Procure Batteries | Not Started | 5 | 10d | 2022-10-03 | 2022-10-14 | 39 | 0% |  |  |  | 938 |  | 2022-10-03 | 2022-10-14 | 0
653 | 1.2 | 1.2.5.2.7 | C | Generator 2 Subcontract Repairs in New Zealand | Not Started | 5 | 44d | 2022-10-18 | 2022-12-16 | 855 | 0% |  |  | Round trip trucking (Bascik Transport) from USAP site to Terra Cat $345 NZD plus GST- $275 USD estimated. Terra Cat quoted repair of injection pump governor shaft and electronic controller - $5229.03 USD. Estimated $6500.00 USD for diagnosis/repair/testing of alternator output issue and $2800 for structural repair of the 20' ISO shipping container that houses the power plant. Terra Cat was not willing to quote without diagnosis of alternator/structural issues. Total $14,804.03 USD | 892 |  | 2022-10-18 | 2022-12-16 | 0
654 | 1.2 | 1.2.5.2.8 | C | PDM - Procure Batteries | Not Started | 5 | 10d | 2023-06-26 | 2023-07-07 | 825FS +18w | 0% |  |  |  | 748 |  | 2023-06-26 | 2023-07-07 | 0
655 | 1.2 | 1.2.5.2.9 | C | Develop SOW for South Pole Power Generation Technical Support Subcontract & Communicate with Vendor (PY6) | Not Started | 5 | 44d | 2023-10-03 | 2023-12-04 | 881SS -4w | 0% |  |  | South Pole Contractor cost captured in FS2 (2023-24). | 599 |  | 2023-10-03 | 2023-12-04 | 0
656 | 1.2 | 1.2.5.2.10 | C | Predeployment Coordination with Power Generation Technical Support Subcontract Vendor (PY6) | Not Started | 5 | 44d | 2023-08-08 | 2023-10-06 | 655SS -8w | 0% |  |  |  | 683 |  | 2023-08-08 | 2023-10-06 | 0
657 | 1.2 | 1.2.5.3 | P | ISO-3 Sled (Task removed - left here as place holder w/ Notes Intact) | Complete | 4 | 1d | 2019-03-01 | 2019-03-01 |  | 100% |  |  |  | 1883 |  | 2019-03-01 | 2019-03-01 | 0
658 | 1.2 | 1.2.5.3.1 | C | ISO-3 Sled: Design Review & Custom Specification | Complete | 5 | 1d | 2019-03-01 | 2019-03-01 |  | 100% |  |  |  | 1883 |  | 2019-03-01 | 2019-03-01 | 0
659 | 1.2 | 1.2.5.3.2 | C | ISO-3 Sled: Final Design Review | Complete | 5 | 1d | 2019-03-01 | 2019-03-01 |  | 100% |  |  |  | 1883 |  | 2019-03-01 | 2019-03-01 | 0
660 | 1.2 | 1.2.5.3.3 | C | ISO-3 Sled: Procurement & Fabrication | Complete | 5 | 1d | 2019-03-01 | 2019-03-01 |  | 100% |  |  | $100,000 price tag provided by ASC (Street & Kippenham 11/14/18) ASC has not had these fabricated to date, this estimate (from ASC) is based on ISO-2 sleds actual cost of $65,000/each We added on 20% for some contingency, shipping to PTH costs, as well as any custom fabrications/add-ons for decking, or to accommodate structure attachments. Travel cost is for 2 engineers to visit the fabricator for confirmation and any customizations Consider using our own local fabricator, based on ASC specs, so we can review, monitor, but most importantly design/fabricate our custom decks/rails. | 1883 |  | 2019-03-01 | 2019-03-01 | 0
661 | 1.2 | 1.2.5.3.4 | C | ISO-3 Sled: Ship from vendor (Air-ZCM) | Complete | 5 | 1d | 2019-03-01 | 2019-03-01 |  | 100% |  |  | Cargo estimates from John Arnolde (Logistics Mgr, PSL): $7,000 - Dedicated truckload ($4,375 alternative, but not reliable, so using the $7k) $ 800 - Typical 4'x4'x8' Crate (weight ~1,500#) $ 300 - Crate Materials (4'x4'x8') 1 truckload - ISO Sled, 4-5 Sets of Skis | 1883 |  | 2019-03-01 | 2019-03-01 | 0
662 | 1.2 | 1.2.5.4 | P | System Electrical Distribution | Started | 4 | 1390d | 2020-12-01 | 2026-04-10 |  | 49% |  |  |  | 37 |  | 2020-12-01 | 2026-04-10 | 0
663 | 1.2 | 1.2.5.4.1 | C | System Elec Dist: Evaluate EHWD system | Complete | 5 | 40d | 2020-12-01 | 2021-01-25 |  | 100% |  |  |  | 1327 |  | 2020-12-01 | 2021-01-25 | 0
664 | 1.2 | 1.2.5.4.2 | C | System Elec Dist: Define Requirements | Complete | 5 | 60d | 2021-01-26 | 2021-04-19 | 663 | 100% | compiling additional info post 19/20 season, need to incorporate additional systems |  |  | 1327 |  | 2021-01-26 | 2021-04-19 | 0
665 | 1.2 | 1.2.5.4.3 | C | System Elec Dist: Design & Procure | Started | 5 | 2w | 2022-10-24 | 2022-11-04 | 39FS +3w | 50% |  |  | Replacement cables, connectors, for electrical distribution throughout EHWD & TOS | 795 |  | 2022-10-24 | 2022-11-04 | 0
666 | 1.2 | 1.2.5.4.4 | C | System Elec Dist: Design Review | Complete | 5 | 1d | 2022-08-01 | 2022-08-01 | 665FS -70d | 100% |  |  |  | 884 |  | 2022-08-01 | 2022-08-01 | 0
667 | 1.2 | 1.2.5.4.5 | C | System Elec Dist: Build and Test Subcomponents | Started | 5 | 96d | 2022-12-05 | 2023-04-17 | 666, 665SS +30d | 85% |  |  |  | 795 |  | 2022-12-05 | 2023-04-17 | 0
668 | 1.2 | 1.2.5.4.6 | C | System Electrical Drawings & Documentation (PY5) | Not Started | 5 | 12d | 2023-04-18 | 2023-05-03 | 667 | 0% |  |  |  | 795 |  | 2023-04-18 | 2023-05-03 | 0
669 | 1.2 | 1.2.5.4.7 | C | System Electrical Drawings & Documentation (PY6) | Not Started | 5 | 8w | 2024-03-14 | 2024-05-08 | 886FS +4w | 0% |  |  |  | 503 |  | 2024-03-14 | 2024-05-08 | 0
670 | 1.2 | 1.2.5.4.8 | C | System Electrical Resupply (PY6) | Not Started | 5 | 6w | 2024-04-11 | 2024-05-22 | 669SS +4w | 0% |  |  |  | 523 |  | 2024-04-11 | 2024-05-22 | 0
671 | 1.2 | 1.2.5.4.9 | C | System Electrical Drawings & Documentation (PY7) | Not Started | 5 | 8w | 2025-03-17 | 2025-05-09 | 1246FS +4w | 0% |  |  |  | 244 |  | 2025-03-17 | 2025-05-09 | 0
672 | 1.2 | 1.2.5.4.10 | C | System Electrical Resupply (PY7) | Not Started | 5 | 6w | 2025-04-14 | 2025-05-23 | 671SS +4w | 0% |  |  |  | 264 |  | 2025-04-14 | 2025-05-23 | 0
673 | 1.2 | 1.2.5.4.11 | C | System Electrical Drawings & Documentation (PY8) | Not Started | 5 | 4w | 2026-03-16 | 2026-04-10 | 1454FS +4w | 0% |  |  |  | 37 |  | 2026-03-16 | 2026-04-10 | 0
674 | 1.2 | 1.2.6 | P | Water Handling Systems - Off-ice | Started | 3 | 1231d | 2019-09-13 | 2024-06-05 |  | 63% |  |  |  | 513 |  | 2019-09-13 | 2024-06-05 | 0
675 | 1.2 | 1.2.6.1 | P | Water Tanks | Started | 4 | 870d | 2021-01-04 | 2024-05-08 |  | 73% |  |  |  | 533 |  | 2021-01-04 | 2024-05-08 | 0
676 | 1.2 | 1.2.6.1.1 | C | Identify Upgrades-Replacements and Spares | Complete | 5 | 60d | 2021-01-04 | 2021-03-26 |  | 100% | in progress |  |  | 1343 |  | 2021-01-04 | 2021-03-26 | 0
677 | 1.2 | 1.2.6.1.2 | C | Procure Repair Parts, Replacements (PY4) | Started | 5 | 8d | 2022-05-20 | 2022-05-31 |  | 50% | in progress, no procurements yet |  |  | 1021 |  | 2022-05-20 | 2022-05-31 | 0
678 | 1.2 | 1.2.6.1.3 | C | Procure Repair Parts, Replacements (PY6) | Not Started | 5 | 4w | 2024-04-11 | 2024-05-08 | 886FS +8w | 0% |  |  |  | 533 |  | 2024-04-11 | 2024-05-08 | 0
679 | 1.2 | 1.2.6.2 | P | Pumps | Started | 4 | 901d | 2020-12-04 | 2024-05-22 |  | 57% |  |  |  | 523 |  | 2020-12-04 | 2024-05-22 | 0
680 | 1.2 | 1.2.6.2.1 | C | Identify Upgrades-Replacements and Spares | Complete | 5 | 80d | 2020-12-04 | 2021-03-25 |  | 100% | delayed but still in progress |  |  | 1344 |  | 2020-12-04 | 2021-03-25 | 0
681 | 1.2 | 1.2.6.2.2 | C | Procure Repair/Replacement Components (2020-21) | Complete | 5 | 100d | 2021-10-01 | 2022-02-17 |  | 100% | delayed |  |  | 947 |  | 2021-10-01 | 2022-02-17 | 0
682 | 1.2 | 1.2.6.2.3 | C | Configure Pumps/Plumbing | Started | 5 | 14d | 2022-03-18 | 2022-04-06 | 681FS +20d | 25% |  |  |  | 927 |  | 2022-03-18 | 2022-04-06 | 0
683 | 1.2 | 1.2.6.2.4 | C | Charge Pump Soft-starter Box Rebuild (four units) | Not Started | 5 | 86d | 2022-04-07 | 2022-08-04 | 682 | 0% |  |  |  | 989 |  | 2022-04-07 | 2022-08-04 | 0
684 | 1.2 | 1.2.6.2.5 | C | Procure Repair/Replacement Components (PY5) | Not Started | 5 | 4w | 2023-05-01 | 2023-05-26 | 825FS +10w | 0% |  |  |  | 778 |  | 2023-05-01 | 2023-05-26 | 0
685 | 1.2 | 1.2.6.2.6 | C | Procure Repair/Replacement Components (PY6) | Not Started | 5 | 4w | 2024-04-25 | 2024-05-22 | 886FS +10w | 0% |  |  |  | 523 |  | 2024-04-25 | 2024-05-22 | 0
686 | 1.2 | 1.2.6.3 | P | Filtration and Condensate Management | Started | 4 | 557d | 2020-11-01 | 2022-12-19 |  | 71% |  |  |  | 892 |  | 2020-11-01 | 2022-12-19 | 0
687 | 1.2 | 1.2.6.3.1 | C | Define Requirements & Research Methodologies | Complete | 5 | 45d | 2020-11-01 | 2020-12-31 |  | 100% | need better requirements definition from physics |  |  | 1404 |  | 2020-11-01 | 2020-12-31 | 0
688 | 1.2 | 1.2.6.3.2 | C | Confirm w/ASC & NSF - Disposal of Condensate | Not Started | 5 | 20d | 2022-03-01 | 2022-03-28 |  | 0% | in progress |  |  | 872 |  | 2022-03-01 | 2022-03-28 | 0
689 | 1.2 | 1.2.6.3.3 | C | Develop Drilling Algorithms | Complete | 5 | 75d | 2022-03-01 | 2022-06-13 | 688SS | 100% | Have a baseline set of drill strategies |  |  | 892 |  | 2022-03-01 | 2022-06-13 | 0
690 | 1.2 | 1.2.6.3.4 | C | Review & Identify Filtration Sub-System Upgrades | Complete | 5 | 75d | 2022-06-14 | 2022-09-26 | 689 | 100% | need better requirements definition from physics |  |  | 892 |  | 2022-06-14 | 2022-09-26 | 0
691 | 1.2 | 1.2.6.3.5 | C | Procure Filtration Upgrade-Replacement Components | Started | 5 | 60d | 2022-09-27 | 2022-12-19 | 690 | 95% |  |  |  | 892 |  | 2022-09-27 | 2022-12-19 | 0
692 | 1.2 | 1.2.6.3.6 | C | Build & Test Filtration System | Started | 5 | 22d | 2022-04-28 | 2022-05-27 |  | 95% |  |  |  | 927 |  | 2022-04-28 | 2022-05-27 | 0
693 | 1.2 | 1.2.6.3.7 | C | Design Condensate Collection, Treatment, and Disposal System | Started | 5 | 60d | 2022-02-19 | 2022-05-12 |  | 25% |  |  |  | 1049 |  | 2022-02-19 | 2022-05-12 | 0
694 | 1.2 | 1.2.6.3.8 | C | Procure Condensate Disposal System Components | Not Started | 5 | 23d | 2022-06-15 | 2022-07-15 |  | 0% |  |  |  | 978 |  | 2022-06-15 | 2022-07-15 | 0
695 | 1.2 | 1.2.6.3.9 | C | Construct/Test Condensate Disposal System | Not Started | 5 | 25d | 2022-07-18 | 2022-08-19 | 694 | 0% |  |  |  | 978 |  | 2022-07-18 | 2022-08-19 | 0
696 | 1.2 | 1.2.6.4 | P | Interconnects - External | Started | 4 | 1216d | 2019-09-13 | 2024-05-15 |  | 62% |  |  |  | 528 |  | 2019-09-13 | 2024-05-15 | 0
697 | 1.2 | 1.2.6.4.1 | C | Procure Replacements and Spares/Unheated (IVG Hose) | Complete | 5 | 240d | 2019-09-13 | 2020-08-13 |  | 100% | This activity was started earlier than planned to take advantage of discount offer from IVG. SSJ has been submitted for gov waiver. Optimistic IVG deadline |  |  | 1504 |  | 2019-09-13 | 2020-08-13 | 0
698 | 1.2 | 1.2.6.4.2 | C | Identify/Spec Replacements and Spare Heated Hose | Not Started | 5 | 20d | 2022-05-01 | 2022-05-26 |  | 0% | in progress |  |  | 1009 |  | 2022-05-01 | 2022-05-26 | 0
699 | 1.2 | 1.2.6.4.3 | C | Procure Replacements and Spares | Not Started | 5 | 20d | 2022-05-01 | 2022-05-26 |  | 0% |  |  |  | 1009 |  | 2022-05-01 | 2022-05-26 | 0
700 | 1.2 | 1.2.6.4.4 | C | Procure Remaining Materials & Fabricate Heated Hose | Not Started | 5 | 45d | 2022-05-10 | 2022-07-11 |  | 0% |  |  |  | 1007 |  | 2022-05-10 | 2022-07-11 | 0
701 | 1.2 | 1.2.6.4.5 | C | Assemble Hose End Ball Valves | Complete | 5 | 30d | 2022-05-27 | 2022-07-07 | 698FF, 699 | 100% |  |  |  | 1009 |  | 2022-05-27 | 2022-07-07 | 0
702 | 1.2 | 1.2.6.4.6 | C | Finalize Design Gen Water Loop | Not Started | 5 | 30d | 2022-07-08 | 2022-08-18 |  | 0% |  |  |  | 955 |  | 2022-07-08 | 2022-08-18 | 0
703 | 1.2 | 1.2.6.4.7 | C | Procure Gen Water Loop Materials & Assemble | Not Started | 5 | 24d | 2022-08-19 | 2022-09-21 | 702 | 0% |  |  |  | 955 |  | 2022-08-19 | 2022-09-21 | 0
704 | 1.2 | 1.2.6.4.8 | C | Procure Camp and Surface Hose Insulation (PY4) | Not Started | 5 | 15d | 2022-07-02 | 2022-07-21 |  | 0% |  |  |  | 999 |  | 2022-07-02 | 2022-07-21 | 0
705 | 1.2 | 1.2.6.4.9 | C | Procure External Interconnect Materials (PY6) | Not Started | 5 | 15d | 2024-04-25 | 2024-05-15 | 886FS +10w | 0% |  |  |  | 342 |  | 2024-04-25 | 2024-05-15 | 0
706 | 1.2 | 1.2.6.5 | P | MDS Internal Hoses | Started | 4 | 50d | 2024-03-28 | 2024-06-05 |  | 21% |  |  |  | 513 |  | 2024-03-28 | 2024-06-05 | 0
707 | 1.2 | 1.2.6.5.1 | C | Identify Replacement Water Hoses (1-1/2", 3/4", and 1/2" Hose) | Started | 5 | 20d | 2024-03-28 | 2024-04-24 | 886FS +6w | 36% |  |  |  | 342 |  | 2024-03-28 | 2024-04-24 | 0
708 | 1.2 | 1.2.6.5.2 | C | Identify Replacement Fuel Hoses | Started | 5 | 20d | 2024-03-28 | 2024-04-24 | 707SS | 36% |  |  |  | 342 |  | 2024-03-28 | 2024-04-24 | 0
709 | 1.2 | 1.2.6.5.3 | C | Procure Replacements and Spares | Not Started | 5 | 6w | 2024-04-25 | 2024-06-05 | 707, 708 | 0% |  |  |  | 342 |  | 2024-04-25 | 2024-06-05 | 0
710 | 1.2 | 1.2.6.6 | P | ARA Hot Water Drill Subsystem | Started | 4 | 175d | 2022-02-03 | 2022-10-05 |  | 37% |  |  |  | 945 |  | 2022-02-03 | 2022-10-05 | 0
711 | 1.2 | 1.2.6.6.1 | P | Design & Specify ARA Drill System Upgrades | Started | 5 | 145d | 2022-02-03 | 2022-08-24 |  | 42% |  |  |  | 937 |  | 2022-02-03 | 2022-08-24 | 0
712 | 1.2 | 1.2.6.6.1.1 | C | Overall System Redesign and Integration Plan | Started | 6 | 60d | 2022-02-03 | 2022-04-27 |  | 65% |  |  |  | 945 |  | 2022-02-03 | 2022-04-27 | 0
713 | 1.2 | 1.2.6.6.1.2 | C | Design and Spec Pump and Downhole Assembly | Started | 6 | 15d | 2022-04-28 | 2022-05-18 | 712 | 10% |  |  |  | 945 |  | 2022-04-28 | 2022-05-18 | 0
714 | 1.2 | 1.2.6.6.1.3 | C | Design and Spec Pump Motor Controller Box | Started | 6 | 15d | 2022-05-19 | 2022-06-08 | 713 | 30% |  |  |  | 945 |  | 2022-05-19 | 2022-06-08 | 0
715 | 1.2 | 1.2.6.6.1.4 | C | Specify Sensors | Started | 6 | 10d | 2022-06-09 | 2022-06-22 | 714 | 65% |  |  |  | 945 |  | 2022-06-09 | 2022-06-22 | 0
716 | 1.2 | 1.2.6.6.1.5 | C | Design Network/e-stop Interface Box | Started | 6 | 20d | 2022-06-23 | 2022-07-20 | 715 | 10% |  |  |  | 945 |  | 2022-06-23 | 2022-07-20 | 0
717 | 1.2 | 1.2.6.6.1.6 | C | Design HotBox Plumbing Manifold II | Started | 6 | 25d | 2022-07-21 | 2022-08-24 | 716 | 30% |  |  |  | 945 |  | 2022-07-21 | 2022-08-24 | 0
718 | 1.2 | 1.2.6.6.2 | P | Procure Repair Parts, Replacements, Spares | Started | 5 | 100d | 2022-05-19 | 2022-10-05 |  | 34% |  |  |  | 927 |  | 2022-05-19 | 2022-10-05 | 0
719 | 1.2 | 1.2.6.6.2.1 | C | Pumps & Motors | Started | 6 | 30d | 2022-05-19 | 2022-06-29 | 713 | 34% |  |  |  | 1015 |  | 2022-05-19 | 2022-06-29 | 0
720 | 1.2 | 1.2.6.6.2.2 | C | Downhole Assembly Hardware (Mat'l, Fab, & Nozzles) | Started | 6 | 20d | 2022-05-19 | 2022-06-15 | 713 | 34% |  |  |  | 970 |  | 2022-05-19 | 2022-06-15 | 0
721 | 1.2 | 1.2.6.6.2.3 | C | Pump Motor Control Box | Started | 6 | 15d | 2022-06-09 | 2022-06-29 | 714 | 34% |  |  |  | 985 |  | 2022-06-09 | 2022-06-29 | 0
722 | 1.2 | 1.2.6.6.2.4 | C | Sensors | Started | 6 | 60d | 2022-06-23 | 2022-09-14 | 715 | 34% |  |  |  | 960 |  | 2022-06-23 | 2022-09-14 | 0
723 | 1.2 | 1.2.6.6.2.5 | C | Network/e-stop Interface Box Components | Started | 6 | 15d | 2022-07-21 | 2022-08-10 | 716 | 34% |  |  |  | 955 |  | 2022-07-21 | 2022-08-10 | 0
724 | 1.2 | 1.2.6.6.2.6 | C | HotBox II Plumbing | Started | 6 | 15d | 2022-08-25 | 2022-09-14 | 717 | 34% |  |  |  | 945 |  | 2022-08-25 | 2022-09-14 | 0
725 | 1.2 | 1.2.6.6.2.7 | C | Control Center Instrument tie-in | Started | 6 | 15d | 2022-08-11 | 2022-08-31 | 723 | 34% |  |  |  | 970 |  | 2022-08-11 | 2022-08-31 | 0
726 | 1.2 | 1.2.6.6.2.8 | C | Additional Hose, Cabling, Plumbing, & Hardware | Started | 6 | 15d | 2022-09-15 | 2022-10-05 | 724 | 34% |  |  |  | 945 |  | 2022-09-15 | 2022-10-05 | 0
727 | 1.2 | 1.2.6.6.3 | P | Subsystem Assembly, Integration, & Testing at PSL | Started | 5 | 105d | 2022-04-28 | 2022-09-21 |  | 34% |  |  |  | 937 |  | 2022-04-28 | 2022-09-21 | 0
728 | 1.2 | 1.2.6.6.3.1 | C | Legacy Pump Module Assessment | Started | 6 | 15d | 2022-04-28 | 2022-05-18 | 712 | 34% |  |  |  | 1045 |  | 2022-04-28 | 2022-05-18 | 0
729 | 1.2 | 1.2.6.6.3.2 | C | Fab Downhole Assembly Parts and Assemblies | Started | 6 | 20d | 2022-06-16 | 2022-07-13 | 720 | 34% |  |  |  | 970 |  | 2022-06-16 | 2022-07-13 | 0
730 | 1.2 | 1.2.6.6.3.3 | C | Assemble Downhole Assemblies | Started | 6 | 20d | 2022-07-14 | 2022-08-10 | 729 | 34% |  |  |  | 970 |  | 2022-07-14 | 2022-08-10 | 0
731 | 1.2 | 1.2.6.6.3.4 | C | Configure Pump Motor Controller | Started | 6 | 15d | 2022-06-30 | 2022-07-20 | 721 | 34% |  |  |  | 985 |  | 2022-06-30 | 2022-07-20 | 0
732 | 1.2 | 1.2.6.6.3.5 | C | Test New Downhole Assemblies with Controller | Started | 6 | 15d | 2022-08-11 | 2022-08-31 | 730, 731 | 34% |  |  |  | 970 |  | 2022-08-11 | 2022-08-31 | 0
733 | 1.2 | 1.2.6.6.3.6 | C | Build and Test Network/e-stop Interface Box | Started | 6 | 15d | 2022-08-11 | 2022-08-31 | 723 | 34% |  |  |  | 955 |  | 2022-08-11 | 2022-08-31 | 0
734 | 1.2 | 1.2.6.6.3.7 | C | Test SplashCam Camera System | Started | 6 | 15d | 2022-09-01 | 2022-09-21 | 733 | 34% |  |  |  | 955 |  | 2022-09-01 | 2022-09-21 | 0
735 | 1.2 | 1.2.6.6.4 | C | ARA System Ready to Pack for Shipment | Started | 5 | 0 | 2022-10-05 | 2022-10-05 | 711, 718, 727 | 34% |  |  |  | 927 |  | 2022-10-05 | 2022-10-05 | 0
736 | 1.2 | 1.2.7 | P | Support Equipment - Off-ice | Started | 3 | 1948d | 2018-10-01 | 2026-03-31 |  | 40% |  |  |  | 45 |  | 2018-10-01 | 2026-03-31 | 0
737 | 1.2 | 1.2.7.1 | P | Independent Firn Drill | Started | 4 | 930d | 2019-04-01 | 2022-10-21 |  | 96% |  |  |  | 933 |  | 2019-04-01 | 2022-10-21 | 0
738 | 1.2 | 1.2.7.1.1 | C | System Evalation & Testing at PSL | Complete | 5 | 40d | 2019-04-01 | 2019-05-24 |  | 100% |  |  |  | 1718 |  | 2019-04-01 | 2019-05-24 | 0
739 | 1.2 | 1.2.7.1.2 | C | Identify & Procure Upgrade-Replacements, Spares | Complete | 5 | 40d | 2019-05-27 | 2019-07-19 | 738 | 100% |  |  |  | 1718 |  | 2019-05-27 | 2019-07-19 | 0
740 | 1.2 | 1.2.7.1.3 | C | Final Install & Testing at PSL | Complete | 5 | 60d | 2019-07-22 | 2019-10-11 | 739 | 100% |  |  |  | 1718 |  | 2019-07-22 | 2019-10-11 | 0
741 | 1.2 | 1.2.7.1.4 | C | Prepare to Ship | Complete | 5 | 5d | 2019-10-14 | 2019-10-18 | 740 | 100% |  |  |  | 1718 |  | 2019-10-14 | 2019-10-18 | 0
742 | 1.2 | 1.2.7.1.5 | C | Ship IFD to McMurdo (VSL-ZCM, Traverse-NPX) | Complete | 5 | 0 | 2019-10-18 | 2019-10-18 | 741 | 100% | IFD is in McM |  | Cargo estimates from John Arnolde (Logistics Mgr, PSL): $7,000 - Dedicated truckload ($4,375 alternative, but not reliable, so using the $7k) $ 800 - Typical 4'x4'x8' Crate (weight ~1,500#) $ 300 - Crate Materials (4'x4'x8') 1 - Dedicated truck | 1718 |  | 2019-10-18 | 2019-10-18 | 0
743 | 1.2 | 1.2.7.1.6 | C | Procure Brake Solenoid | Complete | 5 | 5d | 2021-10-21 | 2021-10-27 |  | 100% |  |  | Cargo estimates from John Arnolde (Logistics Mgr, PSL): $7,000 - Dedicated truckload ($4,375 alternative, but not reliable, so using the $7k) $ 800 - Typical 4'x4'x8' Crate (weight ~1,500#) $ 300 - Crate Materials (4'x4'x8') 1 - Dedicated truck | 1190 |  | 2021-10-21 | 2021-10-27 | 0
744 | 1.2 | 1.2.7.1.7 | C | IFD Follow-up Tasks (PY5) | Started | 5 | 15d | 2022-10-03 | 2022-10-21 | 39 | 55% |  |  |  | 933 |  | 2022-10-03 | 2022-10-21 | 0
745 | 1.2 | 1.2.7.2 | P | Maintenance/Repair Inventory | Started | 4 | 893d | 2022-01-01 | 2025-06-11 |  | 37% |  |  |  | 251 |  | 2022-01-01 | 2025-06-11 | 0
746 | 1.2 | 1.2.7.2.1 | C | Identify Spares and Replacements | Started | 5 | 300d | 2022-01-01 | 2023-02-23 |  | 55% |  |  |  | -7 |  | 2022-01-01 | 2023-02-23 | 0
747 | 1.2 | 1.2.7.2.2 | C | Procure Spares and Replacements | Started | 5 | 851d | 2022-03-01 | 2025-06-11 | 746SS +41d | 32% |  |  |  | 251 |  | 2022-03-01 | 2025-06-11 | 0
748 | 1.2 | 1.2.7.2.3 | C | Procure Hose Stock and Fittings (PY4) | Started | 5 | 30d | 2022-02-01 | 2022-03-14 |  | 40% |  |  |  | 1092 |  | 2022-02-01 | 2022-03-14 | 0
749 | 1.2 | 1.2.7.2.4 | C | Procure Hose Stock and Fittings (FY5) | Started | 5 | 30d | 2023-05-01 | 2023-06-09 | 825FS +10w | 40% |  |  |  | 598 |  | 2023-05-01 | 2023-06-09 | 0
750 | 1.2 | 1.2.7.2.5 | C | Spare Parts Inventory and Catalog - Electrical/Controls | Started | 5 | 170d | 2023-05-01 | 2023-12-26 | 749SS | 32% |  |  |  | 628 |  | 2023-05-01 | 2023-12-26 | 0
751 | 1.2 | 1.2.7.3 | P | Shops (MECC, SEW, TOW, OML) | Not Started | 4 | 313d | 2022-06-01 | 2023-08-11 |  | 0% |  |  |  | 723 |  | 2022-06-01 | 2023-08-11 | 0
752 | 1.2 | 1.2.7.3.1 | C | Identify Upgrade-Replacements, Spares | Not Started | 5 | 281d | 2022-06-01 | 2023-06-28 |  | 0% |  |  |  | 551 |  | 2022-06-01 | 2023-06-28 | 0
753 | 1.2 | 1.2.7.3.2 | C | Procure Upgrade-Replacements, Spares | Not Started | 5 | 204d | 2022-11-01 | 2023-08-11 | 752SS +109d | 0% |  |  |  | 723 |  | 2022-11-01 | 2023-08-11 | 0
754 | 1.2 | 1.2.7.4 | P | TestBed | Started | 4 | 1948d | 2018-10-01 | 2026-03-31 |  | 42% |  |  |  | 45 |  | 2018-10-01 | 2026-03-31 | 0
755 | 1.2 | 1.2.7.4.1 | C | Commissioning for Motor Drive Testing (2018) | Complete | 5 | 120d | 2018-10-01 | 2019-03-15 |  | 100% |  |  |  | 1713 |  | 2018-10-01 | 2019-03-15 | 0
756 | 1.2 | 1.2.7.4.2 | C | Identify & Procure Upgrade & Replacement Parts | Complete | 5 | 160d | 2019-03-18 | 2019-10-25 | 755 | 100% |  |  |  | 1713 |  | 2019-03-18 | 2019-10-25 | 0
757 | 1.2 | 1.2.7.4.3 | C | Commission/Maintainence/Decommission (2019) | Complete | 5 | 160d | 2019-04-15 | 2019-11-22 |  | 100% | Shut down activities planned for late Nov, then will be at 100% |  |  | 1693 |  | 2019-04-15 | 2019-11-22 | 0
758 | 1.2 | 1.2.7.4.4 | C | Commission/Maintainence/Decommission (2020) | Complete | 5 | 160d | 2020-04-13 | 2020-11-20 |  | 100% |  |  |  | 1433 |  | 2020-04-13 | 2020-11-20 | 0
759 | 1.2 | 1.2.7.4.5 | C | Commission/Maintenance/Decommission (PY3) | Complete | 5 | 160d | 2021-02-12 | 2021-09-23 |  | 100% |  |  |  | 1214 |  | 2021-02-12 | 2021-09-23 | 0
760 | 1.2 | 1.2.7.4.6 | C | Commission/Maintenance/Decommission (PY4) | Not Started | 5 | 159d | 2022-02-11 | 2022-09-21 |  | 0% |  |  |  | 955 |  | 2022-02-11 | 2022-09-21 | 0
761 | 1.2 | 1.2.7.4.7 | C | Commission/Maintenance/Decommission (PY5) | Not Started | 5 | 260d | 2022-10-03 | 2023-09-29 | 39 | 0% |  |  |  | 45 |  | 2022-10-03 | 2023-09-29 | 0
762 | 1.2 | 1.2.7.4.8 | C | Commission/Maintenance/Decommission (PY6) | Not Started | 5 | 258d | 2023-10-02 | 2024-09-30 | 761 | 0% |  |  |  | 45 |  | 2023-10-02 | 2024-09-30 | 0
763 | 1.2 | 1.2.7.4.9 | C | Commission/Maintenance/Decommission (PY7) | Not Started | 5 | 258d | 2024-10-01 | 2025-09-30 | 762 | 0% |  |  |  | 45 |  | 2024-10-01 | 2025-09-30 | 0
764 | 1.2 | 1.2.7.4.10 | C | Commission/Maintenance/Decommission (PY8) | Not Started | 5 | 127d | 2025-10-01 | 2026-03-31 | 763 | 0% |  |  |  | 45 |  | 2025-10-01 | 2026-03-31 | 0
765 | 1.2 | 1.2.7.5 | P | Tools and Equipment | Started | 4 | 1669d | 2019-03-01 | 2025-07-31 |  | 15% |  |  |  | 215 |  | 2019-03-01 | 2025-07-31 | 0
766 | 1.2 | 1.2.7.5.1 | C | Procure 287B Skidsteer (or similar) | Complete | 5 | 29d | 2019-08-21 | 2019-09-30 |  | 100% |  |  |  | 1702 |  | 2019-08-21 | 2019-09-30 | 0
767 | 1.2 | 1.2.7.5.2 | C | Procure 2 Snowmobiles | Complete | 5 | 29d | 2019-08-21 | 2019-09-30 | 766FF | 100% | 2 snowmos procured and shipped 2019 |  |  | 1731 |  | 2019-08-21 | 2019-09-30 | 0
768 | 1.2 | 1.2.7.5.3 | C | Ship 2 Snowmobiles | Complete | 5 | 1d | 2019-09-30 | 2019-09-30 | 767FF | 100% | 2 snowmos arrived at NPX 12/19, 287 in McMurdo, 2 more snowmos to ship 20/21 |  |  | 1732 |  | 2019-09-30 | 2019-09-30 | 0
769 | 1.2 | 1.2.7.5.4 | C | Identify Tools & Equipment, & Consumables | Should have Started | 5 | 936d | 2019-03-01 | 2022-09-30 |  | 0% |  |  |  | -721 |  | 2019-03-01 | 2022-09-30 | 0
770 | 1.2 | 1.2.7.5.5 | C | Procure Tools & Equipment, & Consumables | Started | 5 | 1669d | 2019-03-01 | 2025-07-31 | 769SS | 20% |  |  |  | 215 |  | 2019-03-01 | 2025-07-31 | 0
771 | 1.2 | 1.2.7.5.6 | C | Complete Hose Crimper Calibration | Complete | 5 | 7d | 2021-10-10 | 2021-10-18 |  | 100% |  |  |  | 1197 |  | 2021-10-10 | 2021-10-18 | 0
772 | 1.2 | 1.2.8 | P | Drill Field Seasons - Antarctica | Started | 3 | 1910d | 2018-11-02 | 2026-03-11 |  | 15% |  |  |  | 59 |  | 2018-11-02 | 2026-03-11 | 0
773 | 1.2 | 1.2.8.1 | P | Seasonal Staffing & Training, Off-Ice Coordination | Started | 4 | 1777d | 2018-11-02 | 2025-09-02 |  | 18% |  |  |  | 192 |  | 2018-11-02 | 2025-09-02 | 0
774 | 1.2 | 1.2.8.1.1 | C | 2019 Off-Ice EHWD & Safety Training - 12 Drillers | Complete | 5 | 5d | 2019-07-29 | 2019-08-02 |  | 100% | Draft training plan developed |  |  | 1773 |  | 2019-07-29 | 2019-08-02 | 0
775 | 1.2 | 1.2.8.1.2 | C | FS1 Off-Ice Safety Training & PPE Procurement - 10 FTE Drillers (10-primary 2-alternates) & 1 Safety Officer | Not Started | 5 | 6d | 2023-08-06 | 2023-08-11 |  | 0% |  |  | Contract staff training/travel labor - 3 Direct Hire + 2 alternates - assuming 7 days @ 8 hours per (280 hours total) Training travel 3 Direct Hire w/ 2 alternates - 5 Total (estimating 2 local, 1 domestic, 2 intl). Duration 7 days. $8200 total travel cost 2 Local - No travel costs 1 Domestic - $1800 2 International - $6400 Assuming 30 hours per PSL team member for training x 10 PSL Engineers. SafeStart, rigging, and Red Cross training - additional training materials added in coordination with USAP contractor. Procurement of replacement smoke detector batteries, smoke detectors, toe warmers, hand warmers, oxygen, CO, H2S, monitors, first aid kit, work gloves, knee pads, goggles, and N95 masks. | 718 |  | 2023-08-06 | 2023-08-11 | 0
776 | 1.2 | 1.2.8.1.3 | C | FS2 Off-Ice Safety Training & PPE Procurement - 16 Drillers (14 - Primary 2 - alternates) & 1 Safety Officer | Not Started | 5 | 11d | 2024-08-04 | 2024-08-16 |  | 0% |  |  | Contract staff training/travel labor - 8 Direct Hire (w/ 2 alternates) - assuming 7 days @ 8 hours per (448 hours total). Training travel 8 Direct Hire w/ 2 alternates Duration 7 days. 2 Local - No travel costs 3 Domestic - $5400 3 International - $9600 PSL staff training labor - Assuming 30 hours per PSL team member for training x 10 PSL Engineers. Red Cross and job specific training TBD - additional training materials added in coordination with USAP contractor. Procurement of replacement smoke detector batteries, smoke detectors, toe warmers, hand warmers, absorbent pads, N95 masks, smoke and CO monitors. | 456 |  | 2024-08-04 | 2024-08-16 | 0
777 | 1.2 | 1.2.8.1.4 | C | FS3 Off-Ice Safety Training & PPE Procurement - 32 Drillers (28 - primary 4 - alternates) & 1 Safety Officer | Not Started | 5 | 11d | 2025-08-03 | 2025-08-15 |  | 0% |  |  | Contract staff training/travel labor - 24 Direct Hire - 20 deploy w/ 4 alternates. Duration 14 - 8 hour days with travel. Contract staff - Training Foreign Travel - 24 Direct Hire - 20 deploy w/ 4 alternates Duration 14 days with travel. 6 Local - No travel costs 12 Domestic - $21600 6 International - $19200 PSL staff training labor - Assuming 60 hours per PSL team member for training x 10 PSL Engineers. SafeStart, rigging, job specific training (TBD) and Red Cross training - additional training materials added in coordination with USAP contractor. Procurement of replacement smoke detector batteries, smoke detectors, toe warmers, hand warmers, absorbent pads, N95 masks, smoke and CO monitors. Logging Winch Training - 3 Drillers 1 day training with IDP support (IDP cost in Calibration WBS) | 196 |  | 2025-08-03 | 2025-08-15 | 0
778 | 1.2 | 1.2.8.1.5 | C | FS3 Off-Ice Logging Winch Training with IDP (3 Drillers 1 day) | Not Started | 5 | 1d | 2025-08-18 | 2025-08-18 | 777 | 0% |  |  |  | 203 |  | 2025-08-18 | 2025-08-18 | 0
779 | 1.2 | 1.2.8.1.6 | C | 2018-19 Season Readiness Review | Complete | 5 | 1d | 2018-11-02 | 2018-11-02 |  | 100% |  |  |  | 1968 |  | 2018-11-02 | 2018-11-02 | 0
780 | 1.2 | 1.2.8.1.7 | C | 2019-20 Season Readiness Review | Complete | 5 | 1d | 2019-09-02 | 2019-09-02 |  | 100% |  |  |  | 1752 |  | 2019-09-02 | 2019-09-02 | 0
781 | 1.2 | 1.2.8.1.8 | C | FS1 Field Season Readiness Review | Not Started | 5 | 1d | 2023-09-02 | 2023-09-02 |  | 0% |  |  |  | 708 |  | 2023-09-02 | 2023-09-02 | 0
782 | 1.2 | 1.2.8.1.9 | C | FS2 Field Season Readiness Review | Not Started | 5 | 1d | 2024-09-02 | 2024-09-02 |  | 0% |  |  |  | 450 |  | 2024-09-02 | 2024-09-02 | 0
783 | 1.2 | 1.2.8.1.10 | C | FS3 Field Season Readiness Review | Not Started | 5 | 1d | 2025-09-02 | 2025-09-02 |  | 0% |  |  |  | 192 |  | 2025-09-02 | 2025-09-02 | 0
784 | 1.2 | 1.2.8.2 | P | 2019/20 On-Ice Activities | Complete | 4 | 156d | 2019-10-26 | 2020-05-29 |  | 100% |  |  | - Deployment/Redeployment - Ground Penetrating Radar - Tower Structural Analysis - Follow-up retro of other at-risk components - Chase things through McM (IFD, PDM, Fuel Tower, SALSA equip) - Begin Component Testing - Begin Repair/Replacements - Fire up heaters (1-2 MDS at a time) * Season cost higher due to no contributed drillers (per Kael 1/11/19) - adds $50k | 1558 |  | 2019-10-26 | 2020-05-29 | 0
785 | 1.2 | 1.2.8.3.1 | P | General | Complete | 5 | 151d | 2019-11-01 | 2020-05-29 |  | 100% |  |  |  | 1558 |  | 2019-11-01 | 2020-05-29 | 0
786 | 1.2 | 1.2.8.3.1.1 | C | Cargo Retro (19/20) | Complete | 6 | 151d | 2019-11-01 | 2020-05-29 |  | 100% | Retro held in Port H. due to COVID |  | Cargo estimates from John Arnolde (Logistics Mgr, PSL): $7,000 - Dedicated truckload ($4,375 alternative, but not reliable, so using the $7k) $ 800 - Typical 4'x4'x8' Crate (weight ~1,500#) $ 300 - Crate Materials (4'x4'x8') 1 truck | 1478 |  | 2019-11-01 | 2020-05-29 | 0
787 | 1.2 | 1.2.8.3.1.2 | C | Deployment Travel & PQ Costs (19/20) | Complete | 6 | 80d | 2019-11-01 | 2020-02-20 | 786SS | 100% | Costs will not hit until expense reports turned in Jan/Feb |  | Team of 8 1-Dennis 5-Direct-Hire Drillers 0-Contributed Drillers (no MOU committments until 2020) 2-PSL Engineers Travel Labor: 48 hrs/ea (Labor) - 3 days paid time during deployment - 3 days paid time during redeployment Travel Cost: $1,200/ea (Travel) PQ Cost: $950/ea (M&S) | 1629 |  | 2019-11-01 | 2020-02-20 | 0
788 | 1.2 | 1.2.8.3.2 | C | START NPX 2019/20 Season - Team (8) Arrives [ReC/Fire/Life Safety] | Complete | 5 | 1d | 2019-11-15 | 2019-11-15 |  | 100% |  |  |  | 1698 |  | 2019-11-15 | 2019-11-15 | 0
789 | 1.2 | 1.2.8.3.3 | P | ASC/CRREL Ground Penetrating Radar | Complete | 5 | 3d | 2019-12-16 | 2019-12-18 |  | 100% |  |  |  | 1675 |  | 2019-12-16 | 2019-12-18 | 0
790 | 1.2 | 1.2.8.3.3.1 | C | Perform GPR - Map Area to be drilled/instrumented | Complete | 6 | 3d | 2019-12-16 | 2019-12-18 |  | 100% | Data requires CRREL interpretation, which will not occur until Aug 2020 |  |  | 1675 |  | 2019-12-16 | 2019-12-18 | 0
791 | 1.2 | 1.2.8.3.4 | P | EHWD: Upgrade & Replacement Work | Complete | 5 | 56d | 2019-11-15 | 2020-01-31 |  | 100% |  |  |  | 1643 |  | 2019-11-15 | 2020-01-31 | 0
792 | 1.2 | 1.2.8.3.4.1 | C | EHWD Air Shipment Arrives, Upgrade Parts | Complete | 6 | 1d | 2019-11-19 | 2019-11-19 | 793 | 100% |  |  |  | 1696 |  | 2019-11-19 | 2019-11-19 | 0
793 | 1.2 | 1.2.8.3.4.2 | C | Excavate EHWD & Equip Berms, Compact Temp-SES (ASC) | Complete | 6 | 2d | 2019-11-15 | 2019-11-18 | 796SS | 100% | Interfacing Milestone/Activity (w/ASC) |  |  | 1691 |  | 2019-11-15 | 2019-11-18 | 0
794 | 1.2 | 1.2.8.3.4.3 | C | Deliver MECC, Power, Heat, Outhouse to EHWD Berm | Complete | 6 | 2d | 2019-11-19 | 2019-11-20 | 793 | 100% |  |  |  | 1691 |  | 2019-11-19 | 2019-11-20 | 0
795 | 1.2 | 1.2.8.3.4.4 | C | Deliver & Layout Test SES for Cable/Hose Review | Complete | 6 | 4d | 2019-11-19 | 2019-11-22 | 794SS | 100% |  |  |  | 1693 |  | 2019-11-19 | 2019-11-22 | 0
796 | 1.2 | 1.2.8.3.4.5 | C | Connect Temporary Station Power throughout SES | Complete | 6 | 4d | 2019-11-15 | 2019-11-20 |  | 100% |  |  |  | 1641 |  | 2019-11-15 | 2019-11-20 | 0
797 | 1.2 | 1.2.8.3.4.6 | C | EHWD: REPAIRS & UPGRADES THROUGHOUT | Complete | 6 | 45d | 2019-11-21 | 2020-01-22 | 796 | 100% |  |  | Team of 8 (1-Drill Mgr, 7-Drillers) - Testing of all DGH's (1 person month) - Electrical review, panels, transformers, module infrastructure - Safety systems review & testing: Fire suppression, etc - MHP: Thorough inspection, cleaning as needed, detailed report & inventory - TU20 Rebuilds: Hydraulics, pkg & ship axles (1 person month) - Drill Tower Structural Analysis - Retro of suspect/test-failed equipment - Pull all hoses and cables for inventory and begin testing - Photograph/Measure Motor Drive Locations to design retrofit kit for new drives | 1641 |  | 2019-11-21 | 2020-01-22 | 0
798 | 1.2 | 1.2.8.3.4.7 | C | Perform Structural Analysis of Drill Towers | Complete | 6 | 5d | 2019-11-19 | 2019-11-25 |  | 100% |  |  | Perform structural analysis and inspection. Methods and criteria need development. | 1692 |  | 2019-11-19 | 2019-11-25 | 0
799 | 1.2 | 1.2.8.3.4.8 | C | ICL: Inspect and develop plan for cable access into east tower (ASC) | Complete | 6 | 16d | 2020-01-10 | 2020-01-31 |  | 100% | ASC Activity - $0 cost to UW |  |  | 1610 |  | 2020-01-10 | 2020-01-31 | 0
800 | 1.2 | 1.2.8.3.4.9 | C | Pre-compact new ICL road relocation (ASC) | Complete | 6 | 16d | 2020-01-10 | 2020-01-31 | 799SS | 100% | Interfacing Milestone/Activity (w/ASC) |  |  | 1626 |  | 2020-01-10 | 2020-01-31 | 0
801 | 1.2 | 1.2.8.3.4.10 | C | Survey & Pre-Compact SES | Complete | 6 | 16d | 2020-01-10 | 2020-01-31 | 800SS | 100% | Interfacing Milestone/Activity (w/ASC) |  |  | 1642 |  | 2020-01-10 | 2020-01-31 | 0
802 | 1.2 | 1.2.8.3.5 | P | End of NPX Season Close-Out Work | Complete | 5 | 5d | 2020-01-23 | 2020-01-29 |  | 100% |  |  |  | 1645 |  | 2020-01-23 | 2020-01-29 | 0
803 | 1.2 | 1.2.8.3.5.1 | C | Document, Photograph Equip & Upgrade Work, Further Req's | Complete | 6 | 5d | 2020-01-23 | 2020-01-29 | 797 | 100% |  |  |  | 1641 |  | 2020-01-23 | 2020-01-29 | 0
804 | 1.2 | 1.2.8.3.5.2 | C | Winterize/Close/Store all EHWD Equipment | Complete | 6 | 2d | 2020-01-23 | 2020-01-24 | 803SS | 100% |  |  |  | 1646 |  | 2020-01-23 | 2020-01-24 | 0
805 | 1.2 | 1.2.8.3.5.3 | C | Retro all components, crate, pack and deliver to cargo | Complete | 6 | 2d | 2020-01-23 | 2020-01-24 | 804SS | 100% | Interfacing Milestone/Activity (w/ASC) |  |  | 1648 |  | 2020-01-23 | 2020-01-24 | 0
806 | 1.2 | 1.2.8.3.6 | C | END NPX 2019/20 Season | Complete | 5 | 1d | 2020-02-03 | 2020-02-03 | 801 | 100% |  |  |  | 1642 |  | 2020-02-03 | 2020-02-03 | 0
807 | 1.2 | 1.2.8.3.7 | P | Other Field Activities (19/20) | Complete | 5 | 71d | 2019-10-26 | 2020-02-01 |  | 100% |  |  |  | 1643 |  | 2019-10-26 | 2020-02-01 | 0
808 | 1.2 | 1.2.8.3.7.7 | C | Prepare work pad (SPoTSA), provide power, fuel & support - McMurdo | Complete | 6 | 5d | 2019-10-26 | 2019-10-31 |  | 100% | Interfacing Milestone/Activity (w/ASC) |  |  | 1709 |  | 2019-10-26 | 2019-10-31 | 0
809 | 1.2 | 1.2.8.3.7.1 | C | GEN 2, 3, PDM: Inspect/Test/Tune in McMurdo (incl subcontract) | Complete | 6 | 23d | 2019-11-18 | 2019-12-18 |  | 100% | Expenses will not hit until Jan/Feb after sub-contractors invoice |  | Work w/ASC to set up testing infrastructure (tank, fuel, hoses, cables, load bank, etc). ASC to move GENs & PDM into/out of position. Sub-contractor and Engineers to determine problems, attempt to repair, develop list of components to procure (off-ice in 2020) for installation/repair work in 2020-21 season. Decide whether to hold PDM at McMurdo for rework in 2020/21 of traverse to NPX and complete tasking there. TOTAL BUDGETED for this is $200,000 2019/20 - $50,000 for sub-contract, equipment, and tune-up parts 2020 - $100,000 for procurements of replacement parts 2020/21 - $50,000 for subcontractor to return to ZCM or NPX to perform repairs | 1675 |  | 2019-11-18 | 2019-12-18 | 0
810 | 1.2 | 1.2.8.3.7.2 | C | Generator-1: Arrives in ZCM (Winter Storage) | Complete | 6 | 1d | 2020-02-01 | 2020-02-01 |  | 100% | Should arrive vessel Feb 2020 |  |  | 1643 |  | 2020-02-01 | 2020-02-01 | 0
811 | 1.2 | 1.2.8.3.7.3 | C | Fuel Tower: Inspect & Test in McMurdo | Complete | 6 | 22d | 2019-11-01 | 2019-12-02 |  | 100% |  |  |  | 1643 |  | 2019-11-01 | 2019-12-02 | 0
812 | 1.2 | 1.2.8.3.7.4 | C | Cable Tensioner: Inspect & Test | Complete | 6 | 22d | 2019-11-01 | 2019-12-02 | 811SS | 100% | This is actually at PSL, will be tested/inspected in summer 2020 |  |  | 1665 |  | 2019-11-01 | 2019-12-02 | 0
813 | 1.2 | 1.2.8.3.7.5 | C | Reel Container: Inspect & Inventory | Complete | 6 | 22d | 2019-11-01 | 2019-12-02 | 812SS | 100% |  |  | Consists of: Reel container Misc other equipment | 1687 |  | 2019-11-01 | 2019-12-02 | 0
814 | 1.2 | 1.2.8.3.7.6 | C | IFD: Arrival (from PSL) & Storage in McMurdo (defunct) | Complete | 6 | 1d | 2020-02-01 | 2020-02-01 |  | 100% |  |  |  | 1643 |  | 2020-02-01 | 2020-02-01 | 0
815 | 1.2 | 1.2.8.3 | P | 2020/21 & 2021/22 On-Ice Activities | Complete | 4 | 1d | 2021-03-01 | 2021-03-01 |  | 100% |  |  |  | 1362 |  | 2021-03-01 | 2021-03-01 | 0
816 | 1.2 | 1.2.8.3.1 | C | Drill Pad/Road Grooming & T&L Support (ASC) | Complete | 5 | 1d | 2021-03-01 | 2021-03-01 |  | 100% |  |  |  | 1362 |  | 2021-03-01 | 2021-03-01 | 0
817 | 1.2 | 1.2.8.4 | P | USAP Field Season 0 (FY23) | Not Started | 4 | 171d | 2022-10-01 | 2023-05-26 |  | 0% |  |  |  | 778 |  | 2022-10-01 | 2023-05-26 | 0
818 | 1.2 | 1.2.8.4.1 | P | Milestones | Not Started | 5 | 111d | 2022-10-01 | 2023-03-06 |  | 0% |  |  |  | 838 |  | 2022-10-01 | 2023-03-06 | 0
819 | 1.2 | 1.2.8.4.1.1 | C | McM Mainbody Season Begins (USAP) | Not Started | 6 | 0 | 2022-10-01 | 2022-10-01 |  | 0% |  | USAP Support |  | 552 |  | 2022-10-01 | 2022-10-01 | 0
820 | 1.2 | 1.2.8.4.1.2 | C | Vessel Arrives - McMurdo (USAP) | Not Started | 6 | 0 | 2023-02-06 | 2023-02-06 | 819FS +90d | 0% |  | USAP Support |  | 783 |  | 2023-02-06 | 2023-02-06 | 0
821 | 1.2 | 1.2.8.4.1.3 | C | South Pole Season Begins (USAP) | Not Started | 6 | 0 | 2022-11-04 | 2022-11-04 | 819FS +24d | 0% |  | USAP Support |  | 552 |  | 2022-11-04 | 2022-11-04 | 0
822 | 1.2 | 1.2.8.4.1.4 | C | SPOT 1 Arrives - South Pole (USAP) | Not Started | 6 | 0 | 2022-12-06 | 2022-12-06 | 819, 821FS +22d | 0% |  | USAP Support |  | 612 |  | 2022-12-06 | 2022-12-06 | 0
823 | 1.2 | 1.2.8.4.1.5 | C | SPOT 2 Arrives - South Pole (USAP) | Not Started | 6 | 0 | 2023-01-04 | 2023-01-04 | 819, 821FS +43d | 0% |  | USAP Support |  | 612 |  | 2023-01-04 | 2023-01-04 | 0
824 | 1.2 | 1.2.8.4.1.6 | C | SPOT 3 Arrives - South Pole (USAP) | Not Started | 6 | 0 | 2023-02-03 | 2023-02-03 | 819, 821FS +65d | 0% |  | USAP Support |  | 859 |  | 2023-02-03 | 2023-02-03 | 0
825 | 1.2 | 1.2.8.4.1.7 | C | Pole Season Ends (USAP) | Not Started | 6 | 0 | 2023-02-20 | 2023-02-20 | 821FS +76d | 0% |  | USAP Support |  | 482 |  | 2023-02-20 | 2023-02-20 | 0
826 | 1.2 | 1.2.8.4.1.8 | C | MCM Season Ends (USAP) | Not Started | 6 | 0 | 2023-03-06 | 2023-03-06 | 819, 821FS +86d | 0% |  | USAP Support |  | 838 |  | 2023-03-06 | 2023-03-06 | 0
827 | 1.2 | 1.2.8.4.2 | P | Cargo Movements (USAP) | Not Started | 5 | 154d | 2022-10-17 | 2023-05-19 |  | 0% |  |  |  | 783 |  | 2022-10-17 | 2023-05-19 | 0
828 | 1.2 | 1.2.8.4.2.1 | P | Pole (USAP) | Not Started | 6 | 119d | 2022-12-06 | 2023-05-19 |  | 0% |  |  |  | 783 |  | 2022-12-06 | 2023-05-19 | 0
829 | 1.2 | 1.2.8.4.2.1.1 | P | LC130 - Pole (USAP) | Not Started | 7 | 75d | 2023-02-06 | 2023-05-19 |  | 0% |  |  |  | 783 |  | 2023-02-06 | 2023-05-19 | 0
830 | 1.2 | 1.2.8.4.2.1.1.1 | C | Fuel - 2 Missions, 6000 gallons (USAP) | Not Started | 8 | 75d | 2023-02-06 | 2023-05-19 | 820, 821 | 0% |  | USAP Support |  | 783 |  | 2023-02-06 | 2023-05-19 | 0
831 | 1.2 | 1.2.8.4.2.1.2 | P | SPOT1 (USAP) | Not Started | 7 | 0 | 2022-12-06 | 2022-12-06 |  | 0% |  |  |  | 902 |  | 2022-12-06 | 2022-12-06 | 0
832 | 1.2 | 1.2.8.4.2.1.2.1 | C | Fuel Tower Arrives (Bermed at SPOTSA) (USAP) | Not Started | 8 | 0 | 2022-12-06 | 2022-12-06 | 819, 821, 822, 862 | 0% |  | USAP Support |  | 902 |  | 2022-12-06 | 2022-12-06 | 0
833 | 1.2 | 1.2.8.4.2.1.2.2 | C | 8' Refit Container Arrives (USAP) | Not Started | 8 | 0 | 2022-12-06 | 2022-12-06 | 819, 821, 822 | 0% |  | USAP Support |  | 902 |  | 2022-12-06 | 2022-12-06 | 0
834 | 1.2 | 1.2.8.4.2.1.2.3 | C | Generator Hoods (SPOTSA Bermed) Arrives (USAP) | Not Started | 8 | 0 | 2022-12-06 | 2022-12-06 | 819, 821, 822, 862 | 0% |  | USAP Support |  | 612 |  | 2022-12-06 | 2022-12-06 | 0
835 | 1.2 | 1.2.8.4.2.1.2.4 | C | Weight Stack (SPOTSA Bermed) Arrives (USAP) | Not Started | 8 | 0 | 2022-12-06 | 2022-12-06 | 819, 821, 822, 862 | 0% |  | USAP Support |  | 902 |  | 2022-12-06 | 2022-12-06 | 0
836 | 1.2 | 1.2.8.4.2.1.2.5 | C | Generator Hoods (Intake) Arrives (USAP) | Not Started | 8 | 0 | 2022-12-06 | 2022-12-06 | 819, 821, 822 | 0% |  | USAP Support |  | 612 |  | 2022-12-06 | 2022-12-06 | 0
837 | 1.2 | 1.2.8.4.2.1.2.6 | C | Generator Hoods (Exhaust) Arrives (USAP) | Not Started | 8 | 0 | 2022-12-06 | 2022-12-06 | 819, 821, 822 | 0% |  | USAP Support |  | 612 |  | 2022-12-06 | 2022-12-06 | 0
838 | 1.2 | 1.2.8.4.2.1.2.7 | C | Container Skis Arrives (USAP) | Not Started | 8 | 0 | 2022-12-06 | 2022-12-06 | 819, 821, 822 | 0% |  | USAP Support |  | 902 |  | 2022-12-06 | 2022-12-06 | 0
839 | 1.2 | 1.2.8.4.2.1.2.8 | C | ARA Trailer Arrives (USAP) | Not Started | 8 | 0 | 2022-12-06 | 2022-12-06 | 819, 821, 822 | 0% |  | USAP Support |  | 902 |  | 2022-12-06 | 2022-12-06 | 0
840 | 1.2 | 1.2.8.4.2.1.2.9 | C | Traverse Accelerometer Logger Arrives (USAP) | Not Started | 8 | 0 | 2022-12-06 | 2022-12-06 | 819, 821, 822 | 0% |  | USAP Support |  | 902 |  | 2022-12-06 | 2022-12-06 | 0
841 | 1.2 | 1.2.8.4.2.1.3 | P | SPOT2 (USAP) | Not Started | 7 | 1d | 2023-01-04 | 2023-01-04 |  | 0% |  |  |  | 880 |  | 2023-01-04 | 2023-01-04 | 0
842 | 1.2 | 1.2.8.4.2.1.3.1 | C | Generator Module 1 Arrives (USAP) | Not Started | 8 | 0 | 2023-01-04 | 2023-01-04 | 819, 821, 823 | 0% |  | USAP Support |  | 876 |  | 2023-01-04 | 2023-01-04 | 0
843 | 1.2 | 1.2.8.4.2.1.3.2 | C | Generator Module 3 Arrives (USAP) | Not Started | 8 | 0 | 2023-01-04 | 2023-01-04 | 819, 821, 823, 862 | 0% |  | USAP Support |  | 876 |  | 2023-01-04 | 2023-01-04 | 0
844 | 1.2 | 1.2.8.4.2.1.3.3 | C | Firn Drill Arrives (USAP) | Not Started | 8 | 0 | 2023-01-04 | 2023-01-04 | 819, 821, 823, 862 | 0% |  | USAP Support |  | 612 |  | 2023-01-04 | 2023-01-04 | 0
845 | 1.2 | 1.2.8.4.2.1.3.4 | C | Refit Container A (20' ISO) Arrives (USAP) | Not Started | 8 | 0 | 2023-01-04 | 2023-01-04 | 819, 821, 823 | 0% |  | USAP Support |  | 881 |  | 2023-01-04 | 2023-01-04 | 0
846 | 1.2 | 1.2.8.4.2.1.3.5 | C | Refit Container B (20' ISO) Arrives (USAP) | Not Started | 8 | 0 | 2023-01-04 | 2023-01-04 | 819, 821, 823 | 0% |  | USAP Support |  | 881 |  | 2023-01-04 | 2023-01-04 | 0
847 | 1.2 | 1.2.8.4.2.1.3.6 | C | Main Cable Reel (MCR) Arrives (USAP) | Not Started | 8 | 0 | 2023-01-04 | 2023-01-04 | 819, 821, 823 | 0% |  | USAP Support |  | 881 |  | 2023-01-04 | 2023-01-04 | 0
848 | 1.2 | 1.2.8.4.2.1.3.7 | C | Return Water Cable Reel (RWCR) Arrives (USAP) | Not Started | 8 | 0 | 2023-01-04 | 2023-01-04 | 819, 821, 823 | 0% |  | USAP Support |  | 881 |  | 2023-01-04 | 2023-01-04 | 0
849 | 1.2 | 1.2.8.4.2.1.3.8 | C | Traverse Accelerometer Logger Arrives (USAP) | Not Started | 8 | 1d | 2023-01-04 | 2023-01-04 | 819, 821, 823 | 0% |  | USAP Support |  | 880 |  | 2023-01-04 | 2023-01-04 | 0
850 | 1.2 | 1.2.8.4.2.1.4 | P | SPOT3 (USAP) | Not Started | 7 | 0 | 2023-02-03 | 2023-02-03 |  | 0% |  |  |  | 859 |  | 2023-02-03 | 2023-02-03 | 0
851 | 1.2 | 1.2.8.4.2.1.4.1 | C | HPU2 Arrives (USAP) | Not Started | 8 | 0 | 2023-02-03 | 2023-02-03 | 819, 821, 824, 862 | 0% |  | USAP Support |  | 859 |  | 2023-02-03 | 2023-02-03 | 0
852 |  | 1.2.8.4.2.2 | P | McMurdo (USAP) | Not Started | 6 | 80d | 2022-10-17 | 2023-02-06 |  | 0% |  |  |  | 857 |  | 2022-10-17 | 2023-02-06 | 0
853 | 1.2 | 1.2.8.4.2.2.1 | P | SAAM (USAP) | Not Started | 7 | 79d | 2022-10-17 | 2023-02-06 |  | 0% |  |  |  | 858 |  | 2022-10-17 | 2023-02-06 | 0
854 | 1.2 | 1.2.8.4.1.2.1.1 | C | Southbound: Accelerometers (For SPoT data gathering) | Not Started | 8 | 0 | 2023-02-06 | 2023-02-06 | 820 | 0% |  | USAP Support |  | 858 |  | 2023-02-06 | 2023-02-06 | 0
855 | 1.2 | 1.2.8.4.1.2.1.2 | C | Northbound: Generator 2 (Destined for Terra Cat) | Not Started | 8 | 0 | 2022-10-17 | 2022-10-17 | 865 | 0% |  | USAP Support |  | 892 |  | 2022-10-17 | 2022-10-17 | 0
856 | 1.2 | 1.2.8.4.2.2.2 | P | Vessel (USAP) | Not Started | 7 | 1d | 2023-02-06 | 2023-02-06 |  | 0% |  |  |  | 857 |  | 2023-02-06 | 2023-02-06 | 0
857 | 1.2 | 1.2.8.4.1.2.2.1 | C | Generator 2 (Return from Terra Cat) | Not Started | 8 | 1d | 2023-02-06 | 2023-02-06 | 820, 855FS +50d, 653 | 0% |  | USAP Support |  | 857 |  | 2023-02-06 | 2023-02-06 | 0
858 | 1.2 | 1.2.8.4.2.2.2.2 | C | Refit Container C (20' ISO) Arrives (USAP) | Not Started | 8 | 1d | 2023-02-06 | 2023-02-06 | 820 | 0% |  | USAP Support |  | 857 |  | 2023-02-06 | 2023-02-06 | 0
859 | 1.2 | 1.2.8.4.2.2.2.3 | C | ARA Drill Components Crate 1 - DNF (USAP) | Not Started | 8 | 1d | 2023-02-06 | 2023-02-06 | 820 | 0% |  | USAP Support |  | 857 |  | 2023-02-06 | 2023-02-06 | 0
860 | 1.2 | 1.2.8.4.2.2.2.5 | C | Controls Component Crates Shipment 1 DNF (USAP) | Not Started | 8 | 1d | 2023-02-06 | 2023-02-06 | 820 | 0% |  | USAP Support |  | 857 |  | 2023-02-06 | 2023-02-06 | 0
861 | 1.2 | 1.2.8.4.3 | P | USAP Deliverables | Not Started | 5 | 170d | 2022-10-03 | 2023-05-26 |  | 0% |  |  |  | 778 |  | 2022-10-03 | 2023-05-26 | 0
862 | 1.2 | 1.2.8.4.3.1 | C | Excavate SPoTSA Storage Site, Transport & Load Cargo McMurdo (USAP) | Not Started | 6 | 10d | 2022-10-03 | 2022-10-14 | 819 | 0% |  | USAP Support |  | 612 |  | 2022-10-03 | 2022-10-14 | 0
863 | 1.2 | 1.2.8.4.3.2 | C | SPOT Cargo Support (USAP) | Not Started | 6 | 90d | 2022-10-17 | 2023-02-17 | 862 | 0% |  | USAP Support |  | 848 |  | 2022-10-17 | 2023-02-17 | 0
864 | 1.2 | 1.2.8.4.3.3 | C | Transportation/Logistics & Fuels Support McMurdo (USAP) | Not Started | 6 | 60d | 2022-10-24 | 2023-01-13 | 819FS +15d | 0% |  | USAP Support |  | 873 |  | 2022-10-24 | 2023-01-13 | 0
865 | 1.2 | 1.2.8.4.3.4 | C | Relocation of Gen 2 to Phoenix from SPOTSA for Shipping to CHC (USAP) | Not Started | 6 | 1d | 2022-10-17 | 2022-10-17 | 862 | 0% |  | USAP Support |  | 892 |  | 2022-10-17 | 2022-10-17 | 0
866 | 1.2 | 1.2.8.4.3.5 | C | Transportation/Logistics & Fuels Support Pole (USAP) | Not Started | 6 | 45d | 2022-11-25 | 2023-01-26 | 821FS +15d | 0% |  | USAP Support |  | 864 |  | 2022-11-25 | 2023-01-26 | 0
867 | 1.2 | 1.2.8.4.3.6 | C | Drill Storage Site Drift Removal (USAP) | Not Started | 6 | 7d | 2022-11-24 | 2022-12-02 | 821FS +14d | 0% |  | USAP Support |  | 903 |  | 2022-11-24 | 2022-12-02 | 0
868 | 1.2 | 1.2.8.4.3.7 | C | CRREL/Survey GPR Support for Trench Lane & Hole Site Proofing (USAP) | Not Started | 6 | 5d | 2022-12-09 | 2022-12-15 | 822FS +3d | 0% |  | USAP Support |  | 894 |  | 2022-12-09 | 2022-12-15 | 0
869 | 1.2 | 1.2.8.4.3.8 | C | Overwinter Storage Electrical Infrastructure Installation (USAP) | Not Started | 6 | 5d | 2022-12-09 | 2022-12-15 | 821FS +25d | 0% |  | USAP Support |  | 872 |  | 2022-12-09 | 2022-12-15 | 0
870 | 1.2 | 1.2.8.4.3.9 | C | Electrician Support - ICL Overwinter Storage & Rack Feeders (USAP) | Not Started | 6 | 22d | 2022-12-16 | 2023-01-16 | 869 | 0% |  | USAP Support |  | 872 |  | 2022-12-16 | 2023-01-16 | 0
871 | 1.2 | 1.2.8.4.3.10 | C | SES & Drill Pad Hardening/Grooming (USAP) | Not Started | 6 | 14d | 2022-12-16 | 2023-01-04 | 821FS +30d | 0% |  | USAP Support |  | 880 |  | 2022-12-16 | 2023-01-04 | 0
872 | 1.2 | 1.2.8.4.3.11 | C | Complete CRREL Gen Maintenance & Repairs and Install Louver Covers (USAP) | Not Started | 6 | 7d | 2022-12-16 | 2022-12-26 | 821FS +30d | 0% |  | USAP Support |  | 884 |  | 2022-12-16 | 2022-12-26 | 0
873 | 1.2 | 1.2.8.4.3.12 | C | Confirm/Inspect CRREL Gen cables 2-100amp w/ Hubbell/Appleton Connectors (USAP) | Not Started | 6 | 3d | 2022-12-27 | 2022-12-29 | 872 | 0% |  | USAP Support |  | 884 |  | 2022-12-27 | 2022-12-29 | 0
874 | 1.2 | 1.2.8.4.3.13 | C | Crane Support Pole for Offload of Cargo & Set Gens on Skis (USAP) | Not Started | 6 | 5d | 2023-01-04 | 2023-01-10 | 842, 843, 823 | 0% |  | USAP Support |  | 876 |  | 2023-01-04 | 2023-01-10 | 0
875 | 1.2 | 1.2.8.4.3.14 | C | Relocation of Gen 2 from Pier to Overwinter Storage Site (USAP) | Not Started | 6 | 1d | 2023-02-15 | 2023-02-15 | 820FS +7d | 0% |  | USAP Support |  | 850 |  | 2023-02-15 | 2023-02-15 | 0
876 | 1.2 | 1.2.8.4.3.15 | C | 287 Loader Repairs & Pole Prep (USAP) - winter | Not Started | 6 | 2w | 2023-05-15 | 2023-05-26 | 825FS +60d | 0% |  | USAP Support |  | 778 |  | 2023-05-15 | 2023-05-26 | 0
877 | 1.2 | 1.2.8.5 | P | USAP Field Season 1 (FY24) | Not Started | 4 | 299d | 2023-01-04 | 2024-03-01 |  | 0% |  |  |  | 582 |  | 2023-01-04 | 2024-03-01 | 0
878 | 1.2 | 1.2.8.5.1 | P | FS1 Milestones | Not Started | 5 | 107d | 2023-10-01 | 2024-03-01 |  | 0% |  |  |  | 582 |  | 2023-10-01 | 2024-03-01 | 0
879 | 1.2 | 1.2.8.5.1.1 | C | McM Mainbody Season Begins (USAP) | Not Started | 6 | 0 | 2023-10-01 | 2023-10-01 |  | 0% |  | USAP Support |  | 342 |  | 2023-10-01 | 2023-10-01 | 0
880 | 1.2 | 1.2.8.5.1.2 | C | Vessel Arrives - McMurdo (USAP) | Not Started | 6 | 0 | 2024-02-06 | 2024-02-06 | 879FS +88d | 0% |  | USAP Support |  | 600 |  | 2024-02-06 | 2024-02-06 | 0
881 | 1.2 | 1.2.8.5.1.3 | C | South Pole Season Begins (USAP) | Not Started | 6 | 0 | 2023-10-31 | 2023-10-31 | 879FS +21d | 0% |  | USAP Support |  | 342 |  | 2023-10-31 | 2023-10-31 | 0
882 | 1.2 | 1.2.8.5.1.4 | C | ICU Team Arrives [Headcount 11] | Not Started | 6 | 0 | 2023-11-10 | 2023-11-10 | 879, 881FS +8d | 0% |  |  |  | 656 |  | 2023-11-10 | 2023-11-10 | 0
883 | 1.2 | 1.2.8.5.1.5 | C | SPOT 1 Arrives - South Pole (USAP) | Not Started | 6 | 0 | 2023-12-01 | 2023-12-01 | 879, 881FS +22d | 0% |  | USAP Support |  | 612 |  | 2023-12-01 | 2023-12-01 | 0
884 | 1.2 | 1.2.8.5.1.6 | C | SPOT 2 Arrives - South Pole (USAP) | Not Started | 6 | 0 | 2023-12-29 | 2023-12-29 | 879, 881FS +41d | 0% |  | USAP Support |  | 626 |  | 2023-12-29 | 2023-12-29 | 0
885 | 1.2 | 1.2.8.5.1.7 | C | SPOT 3 Arrives - South Pole (USAP) | Not Started | 6 | 0 | 2024-02-01 | 2024-02-01 | 879, 881FS +64d | 0% |  | USAP Support |  | 603 |  | 2024-02-01 | 2024-02-01 | 0
886 | 1.2 | 1.2.8.5.1.8 | C | Pole Season Ends (USAP) | Not Started | 6 | 0 | 2024-02-15 | 2024-02-15 | 881FS +74d | 0% |  | USAP Support |  | 342 |  | 2024-02-15 | 2024-02-15 | 0
887 | 1.2 | 1.2.8.5.1.9 | C | MCM Season Ends (USAP) | Not Started | 6 | 0 | 2024-03-01 | 2024-03-01 | 879FS +106d | 0% |  | USAP Support |  | 582 |  | 2024-03-01 | 2024-03-01 | 0
888 | 1.2 | 1.2.8.5.2 | C | PQ, ECW & Deployment Travel Costs (FS1) | Not Started | 5 | 192d | 2023-06-02 | 2024-02-29 |  | 0% |  |  | 1 Drill Manager, 5 days deployment travel 3 days redeployment. 1 Safety Engineer, 5 days deployment travel 3 days redeployment. 3 Seasonal drillers, 5 days deployment travel 3 days redeployment (No Contributed drillers). 9 PSL Engineers (2 Rotators), 5 days deployment travel 3 days redeployment. 16 - PQ's 1 Drill Lead, 1 Safety Engineer, 5 Direct Hire (2 alternate) & 9 PSL Engineers @ $950/each (anticipated cost). 14 - Deployment Travel @ $1800 each. | 582 |  | 2023-06-02 | 2024-02-29 | 0
889 | 1.2 | 1.2.8.5.3 | P | USAP Cargo Movements (FY24) | Not Started | 5 | 67d | 2023-10-31 | 2024-02-06 |  | 0% |  |  |  | 600 |  | 2023-10-31 | 2024-02-06 | 0
890 | 1.2 | 1.2.8.5.3.1 | P | Pole (USAP) | Not Started | 6 | 64d | 2023-10-31 | 2024-02-01 |  | 0% |  |  |  | 603 |  | 2023-10-31 | 2024-02-01 | 0
891 | 1.2 | 1.2.8.5.3.1.1 | P | LC130 - Pole (USAP) | Not Started | 7 | 1d | 2023-10-31 | 2023-10-31 |  | 0% |  |  |  | 666 |  | 2023-10-31 | 2023-10-31 | 0
892 | 1.2 | 1.2.8.5.3.1.1.1 | C | Controls Component Crates Shipment 1 DNF (USAP) | Not Started | 8 | 0 | 2023-10-31 | 2023-10-31 | 879, 881 | 0% |  | USAP Support |  | 667 |  | 2023-10-31 | 2023-10-31 | 0
893 | 1.2 | 1.2.8.5.3.1.1.2 | C | Controls Component Crates Shipment 2 DNF (USAP) | Not Started | 8 | 0 | 2023-10-31 | 2023-10-31 | 879, 881 | 0% |  | USAP Support |  | 667 |  | 2023-10-31 | 2023-10-31 | 0
894 | 1.2 | 1.2.8.5.3.1.1.3 | C | ARA Drill System Components - Crate 1 (DNF) (USAP) | Not Started | 8 | 0 | 2023-10-31 | 2023-10-31 | 879, 881 | 0% |  | USAP Support |  | 667 |  | 2023-10-31 | 2023-10-31 | 0
895 | 1.2 | 1.2.8.5.3.2.1.2 | C | Drill Heads X, Y, & R - DNF (USAP) | Not Started | 8 | 1d | 2023-10-31 | 2023-10-31 | 879, 881, 153 | 0% |  | USAP Support |  | 666 |  | 2023-10-31 | 2023-10-31 | 0
896 | 1.2 | 1.2.8.5.3.1.1.5 | C | Fuel - 3 Missions, 9000 gallons (USAP) | Not Started | 8 | 0 | 2023-10-31 | 2023-10-31 | 879, 881 | 0% |  | USAP Support |  | 642 |  | 2023-10-31 | 2023-10-31 | 0
897 | 1.2 | 1.2.8.5.3.1.2 | P | SPOT1 - Pole (USAP) | Not Started | 7 | 0 | 2023-12-01 | 2023-12-01 |  | 0% |  |  |  | 645 |  | 2023-12-01 | 2023-12-01 | 0
898 | 1.2 | 1.2.8.5.3.1.2.1 | C | Gen 1 & 3 (USAP) | Not Started | 8 | 0 | 2023-12-01 | 2023-12-01 | 881, 883 | 0% |  | USAP Support |  | 612 |  | 2023-12-01 | 2023-12-01 | 0
899 | 1.2 | 1.2.8.5.3.1.2.2 | C | Refit Container C (20' ISO) Arrives (USAP) | Not Started | 8 | 0 | 2023-12-01 | 2023-12-01 | 881, 883 | 0% |  | USAP Support |  | 645 |  | 2023-12-01 | 2023-12-01 | 0
900 | 1.2 | 1.2.8.5.3.1.3 | P | SPOT2 - Pole (USAP) | Not Started | 7 | 0 | 2023-12-29 | 2023-12-29 |  | 0% |  |  |  | 626 |  | 2023-12-29 | 2023-12-29 | 0
901 | 1.2 | 1.2.8.5.3.1.3.1 | C | Fuel - 19,812 gallons (3 ISO 25k liter tank containers) | Not Started | 8 | 0 | 2023-12-29 | 2023-12-29 | 881, 884 | 0% |  | USAP Support |  | 626 |  | 2023-12-29 | 2023-12-29 | 0
902 | 1.2 | 1.2.8.5.3.1.4 | P | SPOT3 - Pole (USAP) | Not Started | 7 | 0 | 2024-02-01 | 2024-02-01 |  | 0% |  |  |  | 603 |  | 2024-02-01 | 2024-02-01 | 0
903 | 1.2 | 1.2.8.5.3.1.4.1 | C | Fuel - 6.604 gallons (1 ISO 25k liter tank containers) | Not Started | 8 | 0 | 2024-02-01 | 2024-02-01 | 881, 885 | 0% |  | USAP Support |  | 603 |  | 2024-02-01 | 2024-02-01 | 0
904 | 1.2 | 1.2.8.5.3.2 | P | MCM (USAP) | Not Started | 6 | 67d | 2023-10-31 | 2024-02-06 |  | 0% |  |  |  | 600 |  | 2023-10-31 | 2024-02-06 | 0
905 | 1.2 | 1.2.8.5.3.2.1 | P | SAAM (ComSur) (USAP) | Not Started | 7 | 55d | 2023-10-31 | 2024-01-18 |  | 0% |  |  |  | 612 |  | 2023-10-31 | 2024-01-18 | 0
906 | 1.2 | 1.2.8.5.3.2.1.1 | C | Controls Component Crates Shipment 2 DNF (USAP) | Not Started | 8 | 0 | 2023-10-31 | 2023-10-31 | 879, 881 | 0% |  | USAP Support |  | 666 |  | 2023-10-31 | 2023-10-31 | 0
907 | 1.2 | 1.2.8.5.3.2.1.2 | C | Drill Heads X, Y, & R - DNF (USAP) | Not Started | 8 | 1d | 2024-01-18 | 2024-01-18 | 879FS +75d | 0% |  | USAP Support |  | 612 |  | 2024-01-18 | 2024-01-18 | 0
908 | 1.2 | 1.2.8.5.3.2.2 | P | Vessel - MCM (USAP) | Not Started | 7 | 0 | 2024-02-06 | 2024-02-06 |  | 0% |  |  |  | 600 |  | 2024-02-06 | 2024-02-06 | 0
909 | 1.2 | 1.2.8.5.3.2.2.1 | C | TBD | Not Started | 8 | 0 | 2024-02-06 | 2024-02-06 | 880 | 0% |  | USAP Support |  | 600 |  | 2024-02-06 | 2024-02-06 | 0
910 | 1.2 | 1.2.8.5.3.3 | C | Retrograde Cargo Heads North (USAP) | Not Started | 6 | 0 | 2024-01-22 | 2024-01-22 | 1233 | 0% |  | USAP Support |  | 610 |  | 2024-01-22 | 2024-01-22 | 0
911 | 1.2 | 1.2.8.5.4 | P | Early Season Kick-off Tasking | Not Started | 5 | 68d | 2023-11-03 | 2024-02-09 |  | 0% |  |  |  | 592 |  | 2023-11-03 | 2024-02-09 | 0
912 | 1.2 | 1.2.8.5.4.1 | C | Excavate EHWD & Equipment Berms for Access (USAP) | Not Started | 6 | 3d | 2023-11-03 | 2023-11-07 | 881FS +3d | 0% |  | USAP Support |  | 601 |  | 2023-11-03 | 2023-11-07 | 0
913 | 1.2 | 1.2.8.5.4.2 | C | Deliver MECC & Fuel Tank, Shop, SEW, and Fuel Tanks to Cryo (USAP) | Not Started | 6 | 3d | 2023-11-08 | 2023-11-10 | 912 | 0% |  | USAP Support |  | 596 |  | 2023-11-08 | 2023-11-10 | 0
914 | 1.2 | 1.2.8.5.4.3 | C | Inspect and Test Cryo Worksite Power Feed (USAP) | Not Started | 6 | 1d | 2023-11-08 | 2023-11-08 | 913SS | 0% |  | USAP Support |  | 660 |  | 2023-11-08 | 2023-11-08 | 0
915 | 1.2 | 1.2.8.5.4.4 | C | Set-up MECC & Shop for Season Activities (Driller) | Not Started | 6 | 2d | 2023-11-13 | 2023-11-14 | 913, 882 | 0% |  |  |  | 656 |  | 2023-11-13 | 2023-11-14 | 0
916 | 1.2 | 1.2.8.5.4.5 | C | Re-establish SES Pad, Groom & Compact Roads (USAP) | Not Started | 6 | 8d | 2023-11-15 | 2023-11-27 | 912FS +5d | 0% |  | USAP Support |  | 609 |  | 2023-11-15 | 2023-11-27 | 0
917 | 1.2 | 1.2.8.5.4.6 | C | Provide Heaters (PolarTherm) (USAP) | Not Started | 6 | 62d | 2023-11-13 | 2024-02-09 | 913 | 0% |  | USAP Support |  | 596 |  | 2023-11-13 | 2024-02-09 | 0
918 | 1.2 | 1.2.8.5.4.7 | C | Provide 287B Skidsteer & Snomo's (USAP) | Not Started | 6 | 1d | 2023-11-13 | 2023-11-13 | 913 | 0% |  | USAP Support |  | 657 |  | 2023-11-13 | 2023-11-13 | 0
919 | 1.2 | 1.2.8.5.4.8 | C | Provide Fire Extinguishers (USAP) | Not Started | 6 | 1d | 2023-11-13 | 2023-11-13 | 913 | 0% |  | USAP Support |  | 657 |  | 2023-11-13 | 2023-11-13 | 0
920 | 1.2 | 1.2.8.5.4.9 | P | SEW Season Prep Activities | Not Started | 6 | 3d | 2023-11-10 | 2023-11-14 |  | 0% |  |  |  | 656 |  | 2023-11-10 | 2023-11-14 | 0
921 | 1.2 | 1.2.8.5.4.9.1 | C | Stock Shelves/Cabinets w/ Needed Hardware and Tools | Not Started | 7 | 3d | 2023-11-10 | 2023-11-14 | 882 | 0% |  |  |  | 656 |  | 2023-11-10 | 2023-11-14 | 0
922 | 1.2 | 1.2.8.5.4.9.2 | C | Install new DGH Gateway/Ethernet box, Connect to Gen-1 Network Box, M-DGHs & Test | Not Started | 7 | 2d | 2023-11-10 | 2023-11-13 | 882 | 0% |  |  |  | 657 |  | 2023-11-10 | 2023-11-13 | 0
923 | 1.2 | 1.2.8.5.5 | P | Generators & PDM | Not Started | 5 | 33d | 2023-11-17 | 2024-01-05 |  | 0% |  |  |  | 621 |  | 2023-11-17 | 2024-01-05 | 0
924 | 1.2 | 1.2.8.5.5.1 | C | Receive & Set Gen 2 on Skis with Crane & Deliver to Cryo (USAP) | Not Started | 6 | 1d | 2023-12-01 | 2023-12-01 | 898 | 0% |  | USAP Support |  | 612 |  | 2023-12-01 | 2023-12-01 | 0
925 | 1.2 | 1.2.8.5.5.2 | C | Generators 1, 3 & PDM Delivered to Cryo (USAP) | Not Started | 6 | 1d | 2023-12-01 | 2023-12-01 | 924SS, 912 | 0% |  | USAP Support |  | 612 |  | 2023-12-01 | 2023-12-01 | 0
926 | 1.2 | 1.2.8.5.5.3 | C | CRELL Gen Delivered to Cryo (USAP) | Not Started | 6 | 1d | 2023-11-17 | 2023-11-17 | 912FS +7d | 0% |  | USAP Support |  | 612 |  | 2023-11-17 | 2023-11-17 | 0
927 | 1.2 | 1.2.8.5.5.4 | C | Prepare CRREL Gen for Firn Drill Testing (USAP) | Not Started | 6 | 5d | 2023-11-30 | 2023-12-06 | 926FS +7d | 0% |  | USAP Support |  | 629 |  | 2023-11-30 | 2023-12-06 | 0
928 | 1.2 | 1.2.8.5.5.5 | C | Generators 1,3 & PDM - Repairs & Pre-operational Checks | Not Started | 6 | 7d | 2023-12-04 | 2023-12-12 | 925 | 0% |  | E_Engineer/Generator_Contractor |  | 612 |  | 2023-12-04 | 2023-12-12 | 0
929 | 1.2 | 1.2.8.5.5.8 | C | Install 3rd Disconnect on PDM (USAP) | Not Started | 6 | 2d | 2023-12-04 | 2023-12-05 | 925 | 0% |  | E_Engineer/USAP Electrician |  | 612 |  | 2023-12-04 | 2023-12-05 | 0
930 | 1.2 | 1.2.8.5.5.9 | C | Gen3 Preventative Maintenance (PM) (Driller & USAP) | Not Started | 6 | 2d | 2023-12-11 | 2023-12-12 | 928FF | 0% |  | USAP Support |  | 612 |  | 2023-12-11 | 2023-12-12 | 0
931 | 1.2 | 1.2.8.5.5.10 | C | Deliver Fuel Tank & Fuel (USAP) | Not Started | 6 | 2d | 2023-12-04 | 2023-12-05 | 926, 925 | 0% |  | USAP Fuelie |  | 612 |  | 2023-12-04 | 2023-12-05 | 0
932 | 1.2 | 1.2.8.5.5.11 | C | Ready, Start-up & Exercise Gen1, Gen 2, & Gen3 (Driller & USAP) | Not Started | 6 | 2d | 2023-12-13 | 2023-12-14 | 928, 929, 930, 931 | 0% |  | E_Engineer/USAP Electrician |  | 612 |  | 2023-12-13 | 2023-12-14 | 0
933 | 1.2 | 1.2.8.5.5.12 | C | Install Intake & Exhaust Hoods | Not Started | 6 | 4d | 2023-12-15 | 2023-12-20 | 932, 834, 836, 837 | 0% |  | E_Engineer/Generator_Contractor |  | 617 |  | 2023-12-15 | 2023-12-20 | 0
934 | 1.2 | 1.2.8.5.5.13 | C | Intake & Exhaust Hoods Installation Support (953 w/ stinger) (USAP) | Not Started | 6 | 4d | 2023-12-15 | 2023-12-20 | 932, 834, 836, 837 | 0% |  | Drillers/USAP HEO |  | 626 |  | 2023-12-15 | 2023-12-20 | 0
935 | 1.2 | 1.2.8.5.5.14 | C | Relocate Gen 1, Gen 2, & Gen 3, & PDM from Cryo to SES (USAP) | Not Started | 6 | 3d | 2023-12-21 | 2023-12-26 | 934 | 0% |  | USAP Support |  | 626 |  | 2023-12-21 | 2023-12-26 | 0
936 | 1.2 | 1.2.8.5.5.15 | C | Winterize Gen Modules and PDM (Driller & USAP) | Not Started | 6 | 2d | 2024-01-04 | 2024-01-05 | 935FS +5d | 0% |  | USAP Support |  | 621 |  | 2024-01-04 | 2024-01-05 | 0
937 | 1.2 | 1.2.8.5.6 | P | EHWD: Upgrade & Replacement Work | Not Started | 5 | 289d | 2023-01-04 | 2024-02-15 |  | 0% |  |  |  | 592 |  | 2023-01-04 | 2024-02-15 | 0
938 | 1.2 | 1.2.8.5.6.1 | P | Global Computing & Controls | Not Started | 6 | 5d | 2023-11-09 | 2023-11-15 |  | 0% |  |  |  | 655 |  | 2023-11-09 | 2023-11-15 | 0
939 | 1.2 | 1.2.8.5.6.1.1 | C | Assess SES/TOS Interconnect Inventory | Not Started | 7 | 3d | 2023-11-09 | 2023-11-13 | 1073 | 0% |  |  |  | 657 |  | 2023-11-09 | 2023-11-13 | 0
940 | 1.2 | 1.2.8.5.6.1.2 | C | Install and Test Modbus DGH Modules | Not Started | 7 | 2d | 2023-11-14 | 2023-11-15 | 1073FS +3d | 0% |  |  |  | 655 |  | 2023-11-14 | 2023-11-15 | 0
941 | 1.2 | 1.2.8.5.6.2 | P | Drill Control Center (DCC) | Not Started | 6 | 2d | 2023-11-07 | 2023-11-09 |  | 0% |  |  |  | 659 |  | 2023-11-07 | 2023-11-09 | 0
942 | 1.2 | 1.2.8.5.6.2.1 | C | DCC Relocated to Cryo (USAP) | Not Started | 7 | 0 | 2023-11-07 | 2023-11-07 | 912 | 0% |  | USAP Support |  | 659 |  | 2023-11-07 | 2023-11-07 | 0
943 | 1.2 | 1.2.8.5.6.2.2 | C | Replace Electric Heater in Electrical Closet | Not Started | 7 | 2d | 2023-11-08 | 2023-11-09 | 942 | 0% |  |  |  | 659 |  | 2023-11-08 | 2023-11-09 | 0
944 | 1.2 | 1.2.8.5.6.2.3 | C | Clean-up Workspace & Configure | Not Started | 7 | 2d | 2023-11-08 | 2023-11-09 | 942 | 0% |  |  |  | 659 |  | 2023-11-08 | 2023-11-09 | 0
945 | 1.2 | 1.2.8.5.6.3 | P | Main Heating Plants (MHP) | Not Started | 6 | 17d | 2023-11-08 | 2023-12-02 |  | 0% |  |  |  | 644 |  | 2023-11-08 | 2023-12-02 | 0
946 | 1.2 | 1.2.8.5.6.3.1 | C | MHP Relocation Support (USAP) | Not Started | 7 | 1d | 2023-11-08 | 2023-11-08 | 912 | 0% |  | USAP Support |  | 609 |  | 2023-11-08 | 2023-11-08 | 0
947 | 1.2 | 1.2.8.5.6.3.2 | C | Install MHP Fall Restraint Towers (USAP) | Not Started | 7 | 1d | 2023-11-09 | 2023-11-09 | 946 | 0% |  | USAP Support |  | 609 |  | 2023-11-09 | 2023-11-09 | 0
948 | 1.2 | 1.2.8.5.6.3.3 | P | MHP1 | Not Started | 7 | 14d | 2023-11-08 | 2023-11-29 |  | 0% |  |  |  | 646 |  | 2023-11-08 | 2023-11-29 | 0
949 | 1.2 | 1.2.8.5.6.3.3.1 | P | Mechanical Refit & Repairs (MHP1) | Not Started | 8 | 11d | 2023-11-08 | 2023-11-25 |  | 0% |  |  |  | 649 |  | 2023-11-08 | 2023-11-25 | 0
950 | 1.2 | 1.2.8.5.6.3.3.1.1 | C | Heater Flush and Pressure Test | Not Started | 9 | e4d | 2023-11-08 | 2023-11-12 | 946 | 0% |  |  |  | 609 |  | 2023-11-08 | 2023-11-12 | 0
951 | 1.2 | 1.2.8.5.6.3.3.1.2 | C | Plumbing Upgrades & Repairs | Not Started | 9 | e3d | 2023-11-21 | 2023-11-24 | 968 | 0% |  |  |  | 609 |  | 2023-11-21 | 2023-11-24 | 0
952 | 1.2 | 1.2.8.5.6.3.3.1.3 | C | Fuel System Upgrades and Repairs | Not Started | 9 | e1d | 2023-11-08 | 2023-11-09 | 946 | 0% |  |  |  | 609 |  | 2023-11-08 | 2023-11-09 | 0
953 | 1.2 | 1.2.8.5.6.3.3.1.4 | C | Exhaust System Upgrades and Repairs | Not Started | 9 | e1d | 2023-11-09 | 2023-11-10 | 946, 947 | 0% |  |  |  | 609 |  | 2023-11-09 | 2023-11-10 | 0
954 | 1.2 | 1.2.8.5.6.3.3.1.5 | C | MHP Subsystem Evaluation | Not Started | 9 | e1d | 2023-11-24 | 2023-11-25 | 951, 953, 950, 952FS +1d | 0% |  |  |  | 609 |  | 2023-11-24 | 2023-11-25 | 0
955 | 1.2 | 1.2.8.5.6.3.3.1.6 | C | MHP1 Mechanical Complete | Not Started | 9 | 0 | 2023-11-25 | 2023-11-25 | 954 | 0% |  |  |  | 609 |  | 2023-11-25 | 2023-11-25 | 0
956 | 1.2 | 1.2.8.5.6.3.3.2 | P | Electrical/Controls Refit & Repairs (MHP1) | Not Started | 8 | 14d | 2023-11-08 | 2023-11-29 |  | 0% |  |  |  | 646 |  | 2023-11-08 | 2023-11-29 | 0
957 | 1.2 | 1.2.8.5.6.3.3.2.1 | C | Install PLC-to-DGH Gateway in Network Box, Install M-DGHs, & Test | Not Started | 9 | e1d | 2023-11-11 | 2023-11-12 | 974 | 0% |  |  |  | 609 |  | 2023-11-11 | 2023-11-12 | 0
958 | 1.2 | 1.2.8.5.6.3.3.2.2 | C | Install Refurbished Heater Control Assemblies on All Heaters (M-DGHs pre-installed) | Not Started | 9 | e3d | 2023-11-08 | 2023-11-11 | 946 | 0% |  |  |  | 609 |  | 2023-11-08 | 2023-11-11 | 0
959 | 1.2 | 1.2.8.5.6.3.3.2.3 | C | Replace Thermostats in Heaters & Test | Not Started | 9 | e2d | 2023-11-26 | 2023-11-28 | 976 | 0% |  |  |  | 609 |  | 2023-11-26 | 2023-11-28 | 0
960 | 1.2 | 1.2.8.5.6.3.3.2.4 | C | Reconfigure MHP E-stop Panel to Function with N.C. Slap Switch Contacts | Not Started | 9 | e1d | 2023-11-12 | 2023-11-13 | 957 | 0% |  |  |  | 609 |  | 2023-11-12 | 2023-11-13 | 0
961 | 1.2 | 1.2.8.5.6.3.3.2.5 | C | Test E-stop and Heater Controls with No Water | Not Started | 9 | e2d | 2023-11-13 | 2023-11-15 | 960 | 0% |  |  |  | 609 |  | 2023-11-13 | 2023-11-15 | 0
962 | 1.2 | 1.2.8.5.6.3.3.2.6 | C | Test Flow Sensor Operation with No Water | Not Started | 9 | e1d | 2023-11-28 | 2023-11-29 | 959 | 0% |  |  |  | 609 |  | 2023-11-28 | 2023-11-29 | 0
963 | 1.2 | 1.2.8.5.6.3.3.2.7 | C | Install Ethernet Switch, Connect to Network Box, Route Cable to DCC & Test | Not Started | 9 | e1d | 2023-11-24 | 2023-11-25 | 979 | 0% |  |  |  | 609 |  | 2023-11-24 | 2023-11-25 | 0
964 | 1.2 | 1.2.8.5.6.3.3.2.8 | C | MHP1 Controls Complete | Not Started | 9 | 0 | 2023-11-29 | 2023-11-29 | 957, 958, 959, 960, 961, 962, 963FS +1d | 0% |  |  |  | 609 |  | 2023-11-29 | 2023-11-29 | 0
965 | 1.2 | 1.2.8.5.6.3.4 | P | MHP2 | Not Started | 7 | 14d | 2023-11-09 | 2023-11-30 |  | 0% |  |  |  | 645 |  | 2023-11-09 | 2023-11-30 | 0
966 | 1.2 | 1.2.8.5.6.3.4.1 | P | Mechanical Refit & Repairs (MHP2) | Not Started | 8 | 9d | 2023-11-09 | 2023-11-22 |  | 0% |  |  |  | 650 |  | 2023-11-09 | 2023-11-22 | 0
967 | 1.2 | 1.2.8.5.6.3.4.1.1 | C | Heater Flush and Pressure Test | Not Started | 9 | e3d | 2023-11-12 | 2023-11-15 | 950 | 0% |  |  |  | 609 |  | 2023-11-12 | 2023-11-15 | 0
968 | 1.2 | 1.2.8.5.6.3.4.1.2 | C | Plumbing Upgrades & Repairs | Not Started | 9 | e3d | 2023-11-18 | 2023-11-21 | 984 | 0% |  |  |  | 609 |  | 2023-11-18 | 2023-11-21 | 0
969 | 1.2 | 1.2.8.5.6.3.4.1.3 | C | Fuel System Upgrades and Repairs | Not Started | 9 | e1d | 2023-11-09 | 2023-11-10 | 952 | 0% |  |  |  | 609 |  | 2023-11-09 | 2023-11-10 | 0
970 | 1.2 | 1.2.8.5.6.3.4.1.4 | C | Exhaust System Upgrades and Repairs | Not Started | 9 | e1d | 2023-11-10 | 2023-11-11 | 953 | 0% |  |  |  | 609 |  | 2023-11-10 | 2023-11-11 | 0
971 | 1.2 | 1.2.8.5.6.3.4.1.5 | C | MHP2 Subsystem Evaluation | Not Started | 9 | e1d | 2023-11-21 | 2023-11-22 | 967, 968, 970, 969FS +1d | 0% |  |  |  | 609 |  | 2023-11-21 | 2023-11-22 | 0
972 | 1.2 | 1.2.8.5.6.3.4.1.6 | C | MHP2 Mechanical Complete | Not Started | 9 | 0 | 2023-11-22 | 2023-11-22 | 971 | 0% |  |  |  | 609 |  | 2023-11-22 | 2023-11-22 | 0
973 | 1.2 | 1.2.8.5.6.3.4.2 | P | Electrical/Controls Refit & Repairs (MHP2) | Not Started | 8 | 13d | 2023-11-10 | 2023-11-30 |  | 0% |  |  |  | 645 |  | 2023-11-10 | 2023-11-30 | 0
974 | 1.2 | 1.2.8.5.6.3.4.2.1 | C | Install PLC-to-DGH Gateway in Network Box, Install M-DGHs, & Test | Not Started | 9 | e1d | 2023-11-10 | 2023-11-11 | 990 | 0% |  |  |  | 609 |  | 2023-11-10 | 2023-11-11 | 0
975 | 1.2 | 1.2.8.5.6.3.4.2.2 | C | Install Refurbished Heater Control Assemblies on All Heaters (M-DGHs pre-installed) | Not Started | 9 | e3d | 2023-11-11 | 2023-11-14 | 958 | 0% |  |  |  | 609 |  | 2023-11-11 | 2023-11-14 | 0
976 | 1.2 | 1.2.8.5.6.3.4.2.3 | C | Replace Thermostats in Heaters & Test | Not Started | 9 | e2d | 2023-11-24 | 2023-11-26 | 992 | 0% |  |  |  | 609 |  | 2023-11-24 | 2023-11-26 | 0
977 | 1.2 | 1.2.8.5.6.3.4.2.4 | C | Test E-stop and Heater Controls with No Water | Not Started | 9 | e2d | 2023-11-15 | 2023-11-17 | 961 | 0% |  |  |  | 609 |  | 2023-11-15 | 2023-11-17 | 0
978 | 1.2 | 1.2.8.5.6.3.4.2.5 | C | Test Flow Sensor Operation with No Water | Not Started | 9 | e1d | 2023-11-29 | 2023-11-30 | 962 | 0% |  |  |  | 609 |  | 2023-11-29 | 2023-11-30 | 0
979 | 1.2 | 1.2.8.5.6.3.4.2.6 | C | Install Ethernet Switch, Connect to Network Box, Route Cable to DCC & Test | Not Started | 9 | e1d | 2023-11-23 | 2023-11-24 | 995 | 0% |  |  |  | 609 |  | 2023-11-23 | 2023-11-24 | 0
980 | 1.2 | 1.2.8.5.6.3.4.2.7 | C | MHP2 Controls Complete | Not Started | 9 | 0 | 2023-11-30 | 2023-11-30 | 974, 975, 976, 977, 978, 979 | 0% |  |  |  | 609 |  | 2023-11-30 | 2023-11-30 | 0
981 | 1.2 | 1.2.8.5.6.3.5 | P | MHP3 | Not Started | 7 | 15d | 2023-11-09 | 2023-12-01 |  | 0% |  |  |  | 644 |  | 2023-11-09 | 2023-12-01 | 0
982 | 1.2 | 1.2.8.5.6.3.5.1 | P | Mechanical Refit & Repairs (MHP3) | Not Started | 8 | 5d | 2023-11-10 | 2023-11-19 |  | 0% |  |  |  | 653 |  | 2023-11-10 | 2023-11-19 | 0
983 | 1.2 | 1.2.8.5.6.3.5.1.1 | C | Heater Flush and Pressure Test | Not Started | 9 | e3d | 2023-11-15 | 2023-11-18 | 967 | 0% |  |  |  | 609 |  | 2023-11-15 | 2023-11-18 | 0
984 | 1.2 | 1.2.8.5.6.3.5.1.2 | C | Plumbing Upgrades & Repairs | Not Started | 9 | e3d | 2023-11-15 | 2023-11-18 | 1000 | 0% |  |  |  | 609 |  | 2023-11-15 | 2023-11-18 | 0
985 | 1.2 | 1.2.8.5.6.3.5.1.3 | C | Fuel System Upgrades and Repairs | Not Started | 9 | e1d | 2023-11-10 | 2023-11-11 | 969 | 0% |  |  |  | 609 |  | 2023-11-10 | 2023-11-11 | 0
986 | 1.2 | 1.2.8.5.6.3.5.1.4 | C | Exhaust System Upgrades and Repairs | Not Started | 9 | e1d | 2023-11-11 | 2023-11-12 | 970 | 0% |  |  |  | 609 |  | 2023-11-11 | 2023-11-12 | 0
987 | 1.2 | 1.2.8.5.6.3.5.1.5 | C | MHP3 Subsystem Evaluation | Not Started | 9 | e1d | 2023-11-18 | 2023-11-19 | 983, 984, 986, 985 | 0% |  |  |  | 609 |  | 2023-11-18 | 2023-11-19 | 0
988 | 1.2 | 1.2.8.5.6.3.5.1.6 | C | MHP3 Mechanical Complete | Not Started | 9 | 0 | 2023-11-19 | 2023-11-19 | 987 | 0% |  |  |  | 609 |  | 2023-11-19 | 2023-11-19 | 0
989 | 1.2 | 1.2.8.5.6.3.5.2 | P | Electrical/Controls Refit & Repairs (MHP3) | Not Started | 8 | 15d | 2023-11-09 | 2023-12-01 |  | 0% |  |  |  | 644 |  | 2023-11-09 | 2023-12-01 | 0
990 | 1.2 | 1.2.8.5.6.3.5.2.1 | C | Install PLC-to-DGH Gateway in Network Box, Install M-DGHs, & Test | Not Started | 9 | e1d | 2023-11-09 | 2023-11-10 | 1006 | 0% |  |  |  | 609 |  | 2023-11-09 | 2023-11-10 | 0
991 | 1.2 | 1.2.8.5.6.3.5.2.2 | C | Install Refurbished Heater Control Assemblies on All Heaters (M-DGHs pre-installed) | Not Started | 9 | e3d | 2023-11-14 | 2023-11-17 | 975 | 0% |  |  |  | 609 |  | 2023-11-14 | 2023-11-17 | 0
992 | 1.2 | 1.2.8.5.6.3.5.2.3 | C | Replace Thermostats in Heaters & Test | Not Started | 9 | e2d | 2023-11-22 | 2023-11-24 | 1008 | 0% |  |  |  | 609 |  | 2023-11-22 | 2023-11-24 | 0
993 | 1.2 | 1.2.8.5.6.3.5.2.4 | C | Test E-stop and Heater Controls with No Water | Not Started | 9 | e2d | 2023-11-17 | 2023-11-19 | 977 | 0% |  |  |  | 609 |  | 2023-11-17 | 2023-11-19 | 0
994 | 1.2 | 1.2.8.5.6.3.5.2.5 | C | Test Flow Sensor Operation with No Water | Not Started | 9 | e1d | 2023-11-30 | 2023-12-01 | 978 | 0% |  |  |  | 609 |  | 2023-11-30 | 2023-12-01 | 0
995 | 1.2 | 1.2.8.5.6.3.5.2.6 | C | Install Ethernet Switch, Connect to Network Box, Route Cable to DCC & Test | Not Started | 9 | e1d | 2023-11-22 | 2023-11-23 | 1011 | 0% |  |  |  | 609 |  | 2023-11-22 | 2023-11-23 | 0
996 | 1.2 | 1.2.8.5.6.3.5.2.7 | C | MHP3 Controls Complete | Not Started | 9 | 0 | 2023-12-01 | 2023-12-01 | 990, 991, 992, 993, 994, 995 | 0% |  |  |  | 609 |  | 2023-12-01 | 2023-12-01 | 0
997 | 1.2 | 1.2.8.5.6.3.6 | P | MHP4 | Not Started | 7 | 16d | 2023-11-08 | 2023-12-02 |  | 0% |  |  |  | 644 |  | 2023-11-08 | 2023-12-02 | 0
998 | 1.2 | 1.2.8.5.6.3.6.1 | P | Mechanical Refit & Repairs (MHP4) | Not Started | 8 | 7d | 2023-11-11 | 2023-11-21 |  | 0% |  |  |  | 651 |  | 2023-11-11 | 2023-11-21 | 0
999 | 1.2 | 1.2.8.5.6.3.6.1.1 | C | Heater Flush and Pressure Test | Not Started | 9 | e2d | 2023-11-18 | 2023-11-20 | 983 | 0% |  |  |  | 609 |  | 2023-11-18 | 2023-11-20 | 0
1000 | 1.2 | 1.2.8.5.6.3.6.1.2 | C | Plumbing Upgrades & Repairs | Not Started | 9 | e3d | 2023-11-12 | 2023-11-15 | 1001 | 0% |  |  |  | 609 |  | 2023-11-12 | 2023-11-15 | 0
1001 | 1.2 | 1.2.8.5.6.3.6.1.3 | C | Fuel System Upgrades and Repairs | Not Started | 9 | e1d | 2023-11-11 | 2023-11-12 | 985 | 0% |  |  |  | 609 |  | 2023-11-11 | 2023-11-12 | 0
1002 | 1.2 | 1.2.8.5.6.3.6.1.4 | C | Exhaust System Upgrades and Repairs | Not Started | 9 | e1d | 2023-11-12 | 2023-11-13 | 986 | 0% |  |  |  | 609 |  | 2023-11-12 | 2023-11-13 | 0
1003 | 1.2 | 1.2.8.5.6.3.6.1.5 | C | MHP4 Subsystem Evaluation | Not Started | 9 | e1d | 2023-11-20 | 2023-11-21 | 999, 1000, 1001, 1002 | 0% |  |  |  | 609 |  | 2023-11-20 | 2023-11-21 | 0
1004 | 1.2 | 1.2.8.5.6.3.6.1.6 | C | MHP4 Mechanical Complete | Not Started | 9 | 0 | 2023-11-21 | 2023-11-21 | 1003 | 0% |  |  |  | 609 |  | 2023-11-21 | 2023-11-21 | 0
1005 | 1.2 | 1.2.8.5.6.3.6.2 | P | Electrical/Controls Refit & Repairs (MHP4) | Not Started | 8 | 16d | 2023-11-08 | 2023-12-02 |  | 0% |  |  |  | 644 |  | 2023-11-08 | 2023-12-02 | 0
1006 | 1.2 | 1.2.8.5.6.3.6.2.1 | C | Install PLC-to-DGH Gateway in Network Box, Install M-DGHs, & Test | Not Started | 9 | e1d | 2023-11-08 | 2023-11-09 | 946 | 0% |  |  |  | 609 |  | 2023-11-08 | 2023-11-09 | 0
1007 | 1.2 | 1.2.8.5.6.3.6.2.2 | C | Install Refurbished Heater Control Assemblies on All Heaters (M-DGHs pre-installed) | Not Started | 9 | e3d | 2023-11-17 | 2023-11-20 | 991 | 0% |  |  |  | 609 |  | 2023-11-17 | 2023-11-20 | 0
1008 | 1.2 | 1.2.8.5.6.3.6.2.3 | C | Replace Thermostats in Heaters & Test | Not Started | 9 | e2d | 2023-11-20 | 2023-11-22 | 1007 | 0% |  |  |  | 609 |  | 2023-11-20 | 2023-11-22 | 0
1009 | 1.2 | 1.2.8.5.6.3.6.2.4 | C | Test E-stop and Heater Controls with No Water | Not Started | 9 | e2d | 2023-11-19 | 2023-11-21 | 993 | 0% |  |  |  | 609 |  | 2023-11-19 | 2023-11-21 | 0
1010 | 1.2 | 1.2.8.5.6.3.6.2.5 | C | Test Flow Sensor Operation with No Water | Not Started | 9 | e1d | 2023-12-01 | 2023-12-02 | 994 | 0% |  |  |  | 609 |  | 2023-12-01 | 2023-12-02 | 0
1011 | 1.2 | 1.2.8.5.6.3.6.2.6 | C | Install Ethernet Switch, Connect to Network Box, Route Cable to DCC & Test | Not Started | 9 | e1d | 2023-11-21 | 2023-11-22 | 1009 | 0% |  |  |  | 609 |  | 2023-11-21 | 2023-11-22 | 0
1012 | 1.2 | 1.2.8.5.6.3.6.2.7 | C | MHP4 Controls Complete | Not Started | 9 | 0 | 2023-12-02 | 2023-12-02 | 1006, 1007, 1008, 1009, 1010, 1011 | 0% |  |  |  | 609 |  | 2023-12-02 | 2023-12-02 | 0
1013 | 1.2 | 1.2.8.5.6.4 | P | Pre-Heat System (PHS) | Not Started | 6 | 12d | 2023-11-21 | 2023-12-07 |  | 0% |  |  |  | 640 |  | 2023-11-21 | 2023-12-07 | 0
1014 | 1.2 | 1.2.8.5.6.4.1 | C | PHS Relocation Support (USAP) | Not Started | 7 | 1d | 2023-11-21 | 2023-11-21 | 912FS +9d | 0% |  | USAP Support |  | 608 |  | 2023-11-21 | 2023-11-21 | 0
1015 | 1.2 | 1.2.8.5.6.4.2 | C | Install PHS Fall Restraint Towers (USAP) | Not Started | 7 | 1d | 2023-11-22 | 2023-11-22 | 1014 | 0% |  | USAP Support |  | 609 |  | 2023-11-22 | 2023-11-22 | 0
1016 | 1.2 | 1.2.8.5.6.4.3 | P | Mechanical Refit & Repairs (PHS) | Not Started | 7 | 11d | 2023-11-22 | 2023-12-07 |  | 0% |  |  |  | 640 |  | 2023-11-22 | 2023-12-07 | 0
1017 | 1.2 | 1.2.8.5.6.4.3.1 | C | Heater Flush and Pressure Test | Not Started | 8 | 2d | 2023-11-22 | 2023-11-24 | 1014 | 0% |  |  |  | 609 |  | 2023-11-22 | 2023-11-24 | 0
1018 | 1.2 | 1.2.8.5.6.4.3.2 | C | Plumbing Upgrades & Repairs | Not Started | 8 | 1d | 2023-11-27 | 2023-11-27 | 1017 | 0% |  |  |  | 609 |  | 2023-11-27 | 2023-11-27 | 0
1019 | 1.2 | 1.2.8.5.6.4.3.3 | C | Fuel System Upgrades & Repairs | Not Started | 8 | 1d | 2023-11-28 | 2023-11-28 | 1018 | 0% |  |  |  | 647 |  | 2023-11-28 | 2023-11-28 | 0
1020 | 1.2 | 1.2.8.5.6.4.3.4 | C | Exhaust System Upgrades & Repairs | Not Started | 8 | 1d | 2023-11-24 | 2023-11-24 | 1015 | 0% |  |  |  | 609 |  | 2023-11-24 | 2023-11-24 | 0
1021 | 1.2 | 1.2.8.5.6.4.3.5 | C | Install Condensate System | Not Started | 8 | 6d | 2023-11-28 | 2023-12-05 | 1018 | 0% |  |  |  | 609 |  | 2023-11-28 | 2023-12-05 | 0
1022 | 1.2 | 1.2.8.5.6.4.3.6 | C | Install Filtration System | Not Started | 8 | 6d | 2023-11-28 | 2023-12-05 | 1018 | 0% |  |  |  | 609 |  | 2023-11-28 | 2023-12-05 | 0
1023 | 1.2 | 1.2.8.5.6.4.3.7 | C | PHS Subsystem Evaluation | Not Started | 8 | 1d | 2023-12-07 | 2023-12-07 | 1033, 1022 | 0% |  |  |  | 609 |  | 2023-12-07 | 2023-12-07 | 0
1024 | 1.2 | 1.2.8.5.6.4.3.8 | C | PHS Mechanical Complete | Not Started | 8 | 0 | 2023-12-07 | 2023-12-07 | 1017, 1018, 1020, 1021, 1022, 1023 | 0% |  |  |  | 609 |  | 2023-12-07 | 2023-12-07 | 0
1025 | 1.2 | 1.2.8.5.6.4.4 | P | Electrical/Controls Refit & Repairs (PHS) | Not Started | 7 | 11d | 2023-11-22 | 2023-12-07 |  | 0% |  |  |  | 640 |  | 2023-11-22 | 2023-12-07 | 0
1026 | 1.2 | 1.2.8.5.6.4.4.1 | C | Mount 4 Motor Drives, Connect AC Input and Output Leads | Not Started | 8 | 4d | 2023-11-22 | 2023-11-28 | 1014 | 0% |  |  |  | 609 |  | 2023-11-22 | 2023-11-28 | 0
1027 | 1.2 | 1.2.8.5.6.4.4.2 | C | Install New Motor-enable Relays in E-stop Box, Test with Motor Drives | Not Started | 8 | 2d | 2023-11-29 | 2023-11-30 | 1026 | 0% |  |  |  | 609 |  | 2023-11-29 | 2023-11-30 | 0
1028 | 1.2 | 1.2.8.5.6.4.4.3 | C | Install Refurbished Network Box and Heater M-DGHs, Connect Sensor Cables, & Test | Not Started | 8 | 3d | 2023-11-29 | 2023-12-01 | 1026 | 0% |  |  |  | 609 |  | 2023-11-29 | 2023-12-01 | 0
1029 | 1.2 | 1.2.8.5.6.4.4.4 | C | Replace Outdoor E-stop Slap Switch | Not Started | 8 | 0.5d | 2023-12-04 | 2023-12-04 | 1028 | 0% |  |  |  | 609 |  | 2023-12-04 | 2023-12-04 | 0
1030 | 1.2 | 1.2.8.5.6.4.4.5 | C | Test Heater Controls | Not Started | 8 | 2d | 2023-12-01 | 2023-12-04 | 1027 | 0% |  |  |  | 609 |  | 2023-12-01 | 2023-12-04 | 0
1031 | 1.2 | 1.2.8.5.6.4.4.6 | C | Connect and Test Tank Temperature and Level Sensors | Not Started | 8 | 2d | 2023-12-04 | 2023-12-06 | 1029 | 0% |  |  |  | 609 |  | 2023-12-04 | 2023-12-06 | 0
1032 | 1.2 | 1.2.8.5.6.4.4.7 | C | Test Integrated Subsystem with Mobile HMI: Controls, Feedback, Operational Logic | Not Started | 8 | 3d | 2023-12-05 | 2023-12-07 | 1030 | 0% |  |  |  | 609 |  | 2023-12-05 | 2023-12-07 | 0
1033 | 1.2 | 1.2.8.5.6.4.4.8 | C | Connect and Test Environmental Sensors (temperature, fire/smoke, flooding) | Not Started | 8 | 2d | 2023-12-05 | 2023-12-06 | 1030 | 0% |  |  |  | 609 |  | 2023-12-05 | 2023-12-06 | 0
1034 | 1.2 | 1.2.8.5.6.4.4.9 | C | PHS Subsystem Evaluation | Not Started | 8 | 1d | 2023-12-07 | 2023-12-07 | 1033, 1022 | 0% |  |  |  | 609 |  | 2023-12-07 | 2023-12-07 | 0
1035 | 1.2 | 1.2.8.5.6.4.4.10 | C | PHS Controls Complete | Not Started | 8 | 0 | 2023-12-07 | 2023-12-07 | 1026, 1027, 1028, 1029, 1030, 1031, 1032, 1033, 1034 | 0% |  |  |  | 609 |  | 2023-12-07 | 2023-12-07 | 0
1036 | 1.2 | 1.2.8.5.6.5 | P | HPP | Not Started | 6 | 21d | 2023-12-04 | 2024-01-03 |  | 0% |  |  |  | 623 |  | 2023-12-04 | 2024-01-03 | 0
1037 | 1.2 | 1.2.8.5.6.5.1 | C | HPP Relocation Support (USAP) | Not Started | 7 | 1d | 2023-12-04 | 2023-12-04 | 1210 | 0% |  | USAP Support |  | 609 |  | 2023-12-04 | 2023-12-04 | 0
1038 | 1.2 | 1.2.8.5.6.5.2 | C | Install HPP Fall Restraint Towers (USAP) | Not Started | 7 | 1d | 2023-12-05 | 2023-12-05 | 1037 | 0% |  | USAP Support |  | 641 |  | 2023-12-05 | 2023-12-05 | 0
1039 | 1.2 | 1.2.8.5.6.5.3 | P | Mechanical Refit & Repairs (HPP) | Not Started | 7 | 6d | 2023-12-05 | 2023-12-12 |  | 0% |  |  |  | 637 |  | 2023-12-05 | 2023-12-12 | 0
1040 | 1.2 | 1.2.8.5.6.5.3.1 | C | Plumbing Upgrades & Repairs | Not Started | 8 | 2d | 2023-12-05 | 2023-12-06 | 1210FS +1d | 0% |  |  |  | 609 |  | 2023-12-05 | 2023-12-06 | 0
1041 | 1.2 | 1.2.8.5.6.5.3.2 | C | Fuel System Upgrades and Repairs | Not Started | 8 | 1d | 2023-12-05 | 2023-12-05 | 1037 | 0% |  |  |  | 642 |  | 2023-12-05 | 2023-12-05 | 0
1042 | 1.2 | 1.2.8.5.6.5.3.3 | C | Exhaust System Upgrades and Repairs | Not Started | 8 | 1d | 2023-12-06 | 2023-12-06 | 1038 | 0% |  |  |  | 641 |  | 2023-12-06 | 2023-12-06 | 0
1043 | 1.2 | 1.2.8.5.6.5.3.4 | C | High Pressure Pump Upgrade & Repairs | Not Started | 8 | 3d | 2023-12-07 | 2023-12-11 | 1040 | 0% |  |  |  | 609 |  | 2023-12-07 | 2023-12-11 | 0
1044 | 1.2 | 1.2.8.5.6.5.3.5 | C | HPP Subsystem Evaluation | Not Started | 8 | 1d | 2023-12-12 | 2023-12-12 | 1043 | 0% |  |  |  | 637 |  | 2023-12-12 | 2023-12-12 | 0
1045 | 1.2 | 1.2.8.5.6.5.3.6 | C | HPP Mechanical Complete | Not Started | 8 | 0 | 2023-12-11 | 2023-12-11 | 1043 | 0% |  |  |  | 609 |  | 2023-12-11 | 2023-12-11 | 0
1046 | 1.2 | 1.2.8.5.6.5.4 | P | Electrical/Controls Refit & Repairs (HPP) | Not Started | 7 | 18d | 2023-12-07 | 2024-01-03 |  | 0% |  |  |  | 623 |  | 2023-12-07 | 2024-01-03 | 0
1047 | 1.2 | 1.2.8.5.6.5.4.1 | C | Mount 4 Motor Drives, Connect AC Input & Output Leads | Not Started | 8 | 4d | 2023-12-07 | 2023-12-12 | 1040 | 0% |  |  |  | 609 |  | 2023-12-07 | 2023-12-12 | 0
1048 | 1.2 | 1.2.8.5.6.5.4.2 | C | Test Motor Drive Connections to E-stop, Sensors, Air Dampers, Inlet Pressure Switches | Not Started | 8 | 2d | 2023-12-13 | 2023-12-14 | 1047 | 0% |  |  |  | 609 |  | 2023-12-13 | 2023-12-14 | 0
1049 | 1.2 | 1.2.8.5.6.5.4.3 | C | Install New PLC box in HPP, Connect to Network Box, Test with Mobile HMI | Not Started | 8 | 4d | 2023-12-07 | 2023-12-12 | 1040 | 0% |  |  |  | 609 |  | 2023-12-07 | 2023-12-12 | 0
1050 | 1.2 | 1.2.8.5.6.5.4.4 | C | Install 4 Refurbished Soft-Start Boxes in HPP, Connect to AC & New PLC Box | Not Started | 8 | 2d | 2023-12-13 | 2023-12-14 | 1049 | 0% |  |  |  | 609 |  | 2023-12-13 | 2023-12-14 | 0
1051 | 1.2 | 1.2.8.5.6.5.4.5 | C | Install Re-built Pressure and Flow Sensor Box in HPP & Test | Not Started | 8 | 2d | 2023-12-15 | 2023-12-18 | 1048 | 0% |  |  |  | 609 |  | 2023-12-15 | 2023-12-18 | 0
1052 | 1.2 | 1.2.8.5.6.5.4.6 | C | Install Rebuilt DGH box for Reading Pressure and Flow Sensors & Test | Not Started | 8 | 2d | 2023-12-15 | 2023-12-18 | 1050 | 0% |  |  |  | 609 |  | 2023-12-15 | 2023-12-18 | 0
1053 | 1.2 | 1.2.8.5.6.5.4.7 | C | Install New Motor-enable Relays in E-stop box, Test with Motor Drives | Not Started | 8 | 2d | 2023-12-19 | 2023-12-20 | 1051 | 0% |  |  |  | 609 |  | 2023-12-19 | 2023-12-20 | 0
1054 | 1.2 | 1.2.8.5.6.5.4.8 | C | Install Refurbished Network box with M-DGHs, Connect Sensor Cables, & Test | Not Started | 8 | 3d | 2023-12-19 | 2023-12-21 | 1052 | 0% |  |  |  | 609 |  | 2023-12-19 | 2023-12-21 | 0
1055 | 1.2 | 1.2.8.5.6.5.4.9 | C | Test Integrated Subsystem with Mobile HMI: Controls, Feedback, & Operational Logic | Not Started | 8 | 5d | 2023-12-21 | 2023-12-28 | 1054FS -1d | 0% |  |  |  | 609 |  | 2023-12-21 | 2023-12-28 | 0
1056 | 1.2 | 1.2.8.5.6.5.4.10 | C | Connect and Test Environmental Sensors (temperature, fire/smoke, flooding) | Not Started | 8 | 2d | 2023-12-29 | 2024-01-02 | 1055 | 0% |  |  |  | 609 |  | 2023-12-29 | 2024-01-02 | 0
1057 | 1.2 | 1.2.8.5.6.5.4.11 | C | Test Air-handling System in HPP | Not Started | 8 | 2d | 2023-12-19 | 2023-12-20 | 1037FS +10d | 0% |  |  |  | 609 |  | 2023-12-19 | 2023-12-20 | 0
1058 | 1.2 | 1.2.8.5.6.5.4.12 | C | HPP Subsystem Evaluation | Not Started | 8 | 1d | 2024-01-03 | 2024-01-03 | 1047, 1048, 1049, 1050, 1051, 1052, 1053, 1054, 1055, 1056, 1057 | 0% |  |  |  | 609 |  | 2024-01-03 | 2024-01-03 | 0
1059 | 1.2 | 1.2.8.5.6.5.4.13 | C | HPP Controls Complete | Not Started | 8 | 0 | 2024-01-03 | 2024-01-03 | 1058 | 0% |  |  |  | 609 |  | 2024-01-03 | 2024-01-03 | 0
1060 | 1.2 | 1.2.8.5.6.6 | P | Water Tanks & Handling Systems (VT & Submersible) | Not Started | 6 | 8d | 2023-12-05 | 2023-12-14 |  | 0% |  |  |  | 635 |  | 2023-12-05 | 2023-12-14 | 0
1061 | 1.2 | 1.2.8.5.6.6.1 | C | Water Tank Relocation Support (USAP) | Not Started | 7 | 1d | 2023-12-06 | 2023-12-06 | 1211, 1212 | 0% |  | USAP Support |  | 609 |  | 2023-12-06 | 2023-12-06 | 0
1062 | 1.2 | 1.2.8.5.6.6.2 | P | Water Tanks Mechanical Refit & Repairs (VT & Submersible) | Not Started | 7 | 8d | 2023-12-05 | 2023-12-14 |  | 0% |  |  |  | 635 |  | 2023-12-05 | 2023-12-14 | 0
1063 | 1.2 | 1.2.8.5.6.6.2.1 | C | Water Tank Modifications (Railings & Ladders) | Not Started | 8 | 4d | 2023-12-07 | 2023-12-12 | 1061 | 0% |  |  |  | 609 |  | 2023-12-07 | 2023-12-12 | 0
1064 | 1.2 | 1.2.8.5.6.6.2.2 | C | Water Tanks Plumbing (Vert pumps, Sub. Pumps, Manifolds) | Not Started | 8 | 4d | 2023-12-11 | 2023-12-14 | 1063FS -2d | 0% |  |  |  | 609 |  | 2023-12-11 | 2023-12-14 | 0
1065 | 1.2 | 1.2.8.5.6.6.2.3 | C | Crane Support for Vertical Turbine Pump Installation (USAP) | Not Started | 8 | 1d | 2023-12-13 | 2023-12-13 | 1064SS +2d | 0% |  | USAP Support |  | 609 |  | 2023-12-13 | 2023-12-13 | 0
1066 | 1.2 | 1.2.8.5.6.6.2.4 | C | Construct and Install Water Tank Doghouses (USAP) | Not Started | 8 | 7d | 2023-12-05 | 2023-12-13 | 1064FF -1d | 0% |  | USAP Support |  | 609 |  | 2023-12-05 | 2023-12-13 | 0
1067 | 1.2 | 1.2.8.5.6.6.2.5 | C | Water Tank Subsystem Evaluation | Not Started | 8 | 1d | 2023-12-14 | 2023-12-14 | 1064FF | 0% |  |  |  | 609 |  | 2023-12-14 | 2023-12-14 | 0
1068 | 1.2 | 1.2.8.5.6.6.2.6 | C | Water Tank Mechanicals Complete | Not Started | 8 | 0 | 2023-12-14 | 2023-12-14 | 1063, 1064, 1065, 1066, 1067 | 0% |  |  |  | 609 |  | 2023-12-14 | 2023-12-14 | 0
1069 | 1.2 | 1.2.8.5.6.6.3 | P | Water Tanks Electrical/Controls Refit & Repairs (VT & Submersible) | Not Started | 7 | 1d | 2023-12-14 | 2023-12-14 |  | 0% |  |  |  | 635 |  | 2023-12-14 | 2023-12-14 | 0
1070 | 1.2 | 1.2.8.5.6.6.3.1 | C | Sensor Updates and Wiring Evaluation | Not Started | 8 | 1d | 2023-12-14 | 2023-12-14 | 1064FF | 0% |  |  |  | 635 |  | 2023-12-14 | 2023-12-14 | 0
1071 | 1.2 | 1.2.8.5.6.6.3.2 | C | Water Tank Electrical/Controls Complete | Not Started | 8 | 0 | 2023-12-14 | 2023-12-14 | 1063, 1064, 1065, 1066, 1067 | 0% |  |  |  | 635 |  | 2023-12-14 | 2023-12-14 | 0
1072 | 1.2 | 1.2.8.5.6.7 | P | TOS & Towers | Not Started | 6 | 35d | 2023-11-08 | 2023-12-28 |  | 0% |  |  |  | 626 |  | 2023-11-08 | 2023-12-28 | 0
1073 | 1.2 | 1.2.8.5.6.7.1 | C | TOS/Tower Relocation Support (USAP) | Not Started | 7 | 1d | 2023-11-08 | 2023-11-08 | 912 | 0% |  | USAP Support |  | 601 |  | 2023-11-08 | 2023-11-08 | 0
1074 | 1.2 | 1.2.8.5.6.7.2 | P | TOS Team 1 | Not Started | 7 | 7d | 2023-11-08 | 2023-11-17 |  | 0% |  |  |  | 653 |  | 2023-11-08 | 2023-11-17 | 0
1075 | 1.2 | 1.2.8.5.6.7.2.1 | C | Mate TOS1/Tower1 | Not Started | 8 | e1d | 2023-11-08 | 2023-11-09 | 1073 | 0% |  |  |  | 601 |  | 2023-11-08 | 2023-11-09 | 0
1076 | 1.2 | 1.2.8.5.6.7.2.2 | C | Mate TOS2/Tower2 | Not Started | 8 | e1d | 2023-11-08 | 2023-11-09 | 1073 | 0% |  |  |  | 601 |  | 2023-11-08 | 2023-11-09 | 0
1077 | 1.2 | 1.2.8.5.6.7.2.3 | C | Evaluate Structures & Inventory TOS2/Tower2 | Not Started | 8 | e2d | 2023-11-09 | 2023-11-11 | 1076 | 0% |  |  |  | 601 |  | 2023-11-09 | 2023-11-11 | 0
1078 | 1.2 | 1.2.8.5.6.7.2.4 | C | Evaluate Structures & Inventory TOS1/Tower1 | Not Started | 8 | e2d | 2023-11-11 | 2023-11-13 | 1077 | 0% |  |  |  | 601 |  | 2023-11-11 | 2023-11-13 | 0
1079 | 1.2 | 1.2.8.5.6.7.2.5 | C | Fuel and Exhaust System Upgrades and Repairs TOS1/Tower1 | Not Started | 8 | e1d | 2023-11-13 | 2023-11-14 | 1078 | 0% |  |  |  | 601 |  | 2023-11-13 | 2023-11-14 | 0
1080 | 1.2 | 1.2.8.5.6.7.2.6 | C | Fuel and Exhaust System Upgrades and Repairs TOS2/Tower2 | Not Started | 8 | e1d | 2023-11-14 | 2023-11-15 | 1079 | 0% |  |  |  | 601 |  | 2023-11-14 | 2023-11-15 | 0
1081 | 1.2 | 1.2.8.5.6.7.2.7 | C | Evaluate TOS/Tower Interconnects TOS2/Tower2 | Not Started | 8 | e1d | 2023-11-15 | 2023-11-16 | 1080 | 0% |  |  |  | 601 |  | 2023-11-15 | 2023-11-16 | 0
1082 | 1.2 | 1.2.8.5.6.7.2.8 | C | Evaluate TOS/Tower Interconnects TOS1/Tower1 | Not Started | 8 | e1d | 2023-11-16 | 2023-11-17 | 1081 | 0% |  |  |  | 601 |  | 2023-11-16 | 2023-11-17 | 0
1083 | 1.2 | 1.2.8.5.6.7.2.9 | C | TOS/Tower Team 1 Tasking Complete | Not Started | 8 | 0 | 2023-11-17 | 2023-11-17 | 1075, 1076, 1077, 1078, 1079, 1080, 1081, 1082 | 0% |  |  |  | 601 |  | 2023-11-17 | 2023-11-17 | 0
1084 | 1.2 | 1.2.8.5.6.7.3 | P | TOS Team 2 | Not Started | 7 | 33d | 2023-11-09 | 2023-12-28 |  | 0% |  |  |  | 626 |  | 2023-11-09 | 2023-12-28 | 0
1085 | 1.2 | 1.2.8.5.6.7.3.1 | C | TOS1 - Install 8 Motor Drives, Connect AC Input & Output Leads, Connect to Network & I/O Boxes | Not Started | 8 | e8d | 2023-11-09 | 2023-11-17 | 1076 | 0% |  |  |  | 601 |  | 2023-11-09 | 2023-11-17 | 0
1086 | 1.2 | 1.2.8.5.6.7.3.2 | C | TOS2 - Install 8 Motor Drives, Connect AC Input & Output Leads, Connect to Network & I/O Boxes | Not Started | 8 | e8d | 2023-11-17 | 2023-11-25 | 1085 | 0% |  |  |  | 601 |  | 2023-11-17 | 2023-11-25 | 0
1087 | 1.2 | 1.2.8.5.6.7.3.3 | C | TOS2 - Install and Test New Payout Encoders, Load Cells, and Connections to new PLC Box | Not Started | 8 | e4d | 2023-11-25 | 2023-11-29 | 1086 | 0% |  |  |  | 601 |  | 2023-11-25 | 2023-11-29 | 0
1088 | 1.2 | 1.2.8.5.6.7.3.4 | C | TOS1 - Install and Test New Payout Encoders, Load Cells, and Connections to new PLC Box | Not Started | 8 | e4d | 2023-11-29 | 2023-12-03 | 1087 | 0% |  |  |  | 601 |  | 2023-11-29 | 2023-12-03 | 0
1089 | 1.2 | 1.2.8.5.6.7.3.5 | C | TOS2 - Install Missing TOS2 Line Filters for all Motor Drives (removed in 2010 by G.T.) | Not Started | 8 | 3d | 2023-12-04 | 2023-12-06 | 1088 | 0% |  |  |  | 601 |  | 2023-12-04 | 2023-12-06 | 0
1090 | 1.2 | 1.2.8.5.6.7.3.6 | C | TOS2 - Test MCR Drives w/ SHR motors, Limit Switches, E/R-stops, Pendant and Sensors | Not Started | 8 | e4d | 2023-12-06 | 2023-12-10 | 1089 | 0% |  |  |  | 601 |  | 2023-12-06 | 2023-12-10 | 0
1091 | 1.2 | 1.2.8.5.6.7.3.7 | C | TOS1 - Test MCR Drives w/ SHR motors, Limit Switches, E/R-stops, Pendant and Sensors | Not Started | 8 | e4d | 2023-12-10 | 2023-12-14 | 1090 | 0% |  |  |  | 601 |  | 2023-12-10 | 2023-12-14 | 0
1092 | 1.2 | 1.2.8.5.6.7.3.8 | C | TOS1 - Test MSHR Drives with SHR Motors, Limit Switches, E/R-stops, Pendant and Sensors | Not Started | 8 | e4d | 2023-12-14 | 2023-12-18 | 1091 | 0% |  |  |  | 601 |  | 2023-12-14 | 2023-12-18 | 0
1093 | 1.2 | 1.2.8.5.6.7.3.9 | C | TOS2 - Test MSHR Drives with SHR Motors, Limit Switches, E/R-stops, Pendant and Sensors | Not Started | 8 | e4d | 2023-12-18 | 2023-12-22 | 1092 | 0% |  |  |  | 601 |  | 2023-12-18 | 2023-12-22 | 0
1094 | 1.2 | 1.2.8.5.6.7.3.10 | C | TOS2 - Test Return Water Pump Motor Drive | Not Started | 8 | e3d | 2023-12-22 | 2023-12-25 | 1093 | 0% |  |  |  | 601 |  | 2023-12-22 | 2023-12-25 | 0
1095 | 1.2 | 1.2.8.5.6.7.3.11 | C | TOS1 - Test Return Water Pump Motor Drive | Not Started | 8 | e3d | 2023-12-25 | 2023-12-28 | 1094 | 0% |  |  |  | 601 |  | 2023-12-25 | 2023-12-28 | 0
1096 | 1.2 | 1.2.8.5.6.7.3.12 | C | TOS/Tower Team 2 Tasking Complete | Not Started | 8 | 0 | 2023-12-28 | 2023-12-28 | 1085, 1086, 1087, 1088, 1089, 1090, 1091, 1092, 1093, 1094, 1095 | 0% |  |  |  | 601 |  | 2023-12-28 | 2023-12-28 | 0
1097 | 1.2 | 1.2.8.5.6.7.4 | P | TOS/Tower Team 3 | Not Started | 7 | 32d | 2023-11-09 | 2023-12-27 |  | 0% |  |  |  | 627 |  | 2023-11-09 | 2023-12-27 | 0
1098 | 1.2 | 1.2.8.5.6.7.4.1 | C | TOS2 - Install and Test Refurbished E-stop Box | Not Started | 8 | e3d | 2023-11-09 | 2023-11-12 | 1085SS | 0% |  |  |  | 601 |  | 2023-11-09 | 2023-11-12 | 0
1099 | 1.2 | 1.2.8.5.6.7.4.2 | C | TOS1 - Install and Test Refurbished E-stop Box | Not Started | 8 | e3d | 2023-11-12 | 2023-11-15 | 1098 | 0% |  |  |  | 601 |  | 2023-11-12 | 2023-11-15 | 0
1100 | 1.2 | 1.2.8.5.6.7.4.3 | C | TOS1 - Install 4 Rebuilt I/O Boxes for Cable Reel, Hose Reel, & RW Hose Reel | Not Started | 8 | e4d | 2023-11-15 | 2023-11-19 | 1099 | 0% |  |  |  | 601 |  | 2023-11-15 | 2023-11-19 | 0
1101 | 1.2 | 1.2.8.5.6.7.4.4 | C | TOS2 - Install 4 Rebuilt I/O Boxes for Cable Reel, Hose Reel, RW Hose Reel, & Tower Hoist Wiring | Not Started | 8 | e4d | 2023-11-19 | 2023-11-23 | 1100 | 0% |  |  |  | 601 |  | 2023-11-19 | 2023-11-23 | 0
1102 | 1.2 | 1.2.8.5.6.7.4.5 | C | Aerial Lift Support for Tower 2 Hoist Rewire (USAP) | Not Started | 8 | e4d | 2023-11-21 | 2023-11-25 | 1101SS +1d | 0% |  | USAP Support |  | 650 |  | 2023-11-21 | 2023-11-25 | 0
1103 | 1.2 | 1.2.8.5.6.7.4.6 | C | TOS1 - Install all Local Ethernet, E-stop, Fault Connections & Test | Not Started | 8 | e4d | 2023-11-23 | 2023-11-27 | 1101 | 0% |  |  |  | 601 |  | 2023-11-23 | 2023-11-27 | 0
1104 | 1.2 | 1.2.8.5.6.7.4.7 | C | TOS2 - Install all Local Ethernet, E-stop, Fault Connections & Test | Not Started | 8 | e4d | 2023-11-27 | 2023-12-01 | 1103 | 0% |  |  |  | 601 |  | 2023-11-27 | 2023-12-01 | 0
1105 | 1.2 | 1.2.8.5.6.7.4.8 | C | TOS1 - Install New DGH Gateway/Ethernet Switch/PLC box, Connect to Gen-1 Network Box | Not Started | 8 | e2d | 2023-12-01 | 2023-12-03 | 1104 | 0% |  |  |  | 601 |  | 2023-12-01 | 2023-12-03 | 0
1106 | 1.2 | 1.2.8.5.6.7.4.9 | C | TOS2 - Install New DGH Gateway/Ethernet Switch/PLC box, Connect to Gen-1 Network Box | Not Started | 8 | e2d | 2023-12-03 | 2023-12-05 | 1105 | 0% |  |  |  | 601 |  | 2023-12-03 | 2023-12-05 | 0
1107 | 1.2 | 1.2.8.5.6.7.4.10 | C | TOS2 - Test RWCR Motor, E & Reel Stops, Pendant and Sensors | Not Started | 8 | e2d | 2023-12-05 | 2023-12-07 | 1106 | 0% |  |  |  | 601 |  | 2023-12-05 | 2023-12-07 | 0
1108 | 1.2 | 1.2.8.5.6.7.4.11 | C | TOS1 - Test RWCR Motor, E & Reel Stops, Pendant and Sensors | Not Started | 8 | e2d | 2023-12-07 | 2023-12-09 | 1107 | 0% |  |  |  | 601 |  | 2023-12-07 | 2023-12-09 | 0
1109 | 1.2 | 1.2.8.5.6.7.4.12 | C | TOS1 - Test RWHR Motor, E & Reel Stops, Pendant and Sensors | Not Started | 8 | e2d | 2023-12-09 | 2023-12-11 | 1108 | 0% |  |  |  | 601 |  | 2023-12-09 | 2023-12-11 | 0
1110 | 1.2 | 1.2.8.5.6.7.4.13 | C | TOS2 - Test RWHR Motor, E & Reel Stops, Pendant and Sensors | Not Started | 8 | e2d | 2023-12-11 | 2023-12-13 | 1109 | 0% |  |  |  | 601 |  | 2023-12-11 | 2023-12-13 | 0
1111 | 1.2 | 1.2.8.5.6.7.4.14 | C | TOS2 - Install and Test Tower Hoist AC and Encoder Wiring (cut when hoist was removed for WISSARD) | Not Started | 8 | e2d | 2023-12-13 | 2023-12-15 | 1110 | 0% |  |  |  | 601 |  | 2023-12-13 | 2023-12-15 | 0
1112 | 1.2 | 1.2.8.5.6.7.4.15 | C | TOS2 - Test Tower Winch, E-stop, Reel Stop, Pendant, & Limit Switches | Not Started | 8 | e2d | 2023-12-15 | 2023-12-17 | 1111 | 0% |  |  |  | 601 |  | 2023-12-15 | 2023-12-17 | 0
1113 | 1.2 | 1.2.8.5.6.7.4.16 | C | TOS1 - Test Tower Winch, E-stop, Reel Stop, Pendant, & Limit Switches | Not Started | 8 | e2d | 2023-12-17 | 2023-12-19 | 1112 | 0% |  |  |  | 601 |  | 2023-12-17 | 2023-12-19 | 0
1114 | 1.2 | 1.2.8.5.6.7.4.17 | C | TOS2 - Test Integrated Subsystem with Mobile HMI: Controls, Feedback, Operational Logic | Not Started | 8 | e4d | 2023-12-19 | 2023-12-23 | 1113 | 0% |  |  |  | 601 |  | 2023-12-19 | 2023-12-23 | 0
1115 | 1.2 | 1.2.8.5.6.7.4.18 | C | TOS1 - Test Integrated Subsystem with Mobile HMI: Controls, Feedback, Operational Logic | Not Started | 8 | e4d | 2023-12-23 | 2023-12-27 | 1114 | 0% |  |  |  | 601 |  | 2023-12-23 | 2023-12-27 | 0
1116 | 1.2 | 1.2.8.5.6.7.4.19 | C | TOS/Tower Team 3 Tasking Complete | Not Started | 8 | 0 | 2023-12-27 | 2023-12-27 | 1098, 1099, 1100, 1101, 1103, 1104, 1105, 1106, 1107, 1108, 1109, 1110, 1111, 1112, 1113, 1114, 1115 | 0% |  |  |  | 601 |  | 2023-12-27 | 2023-12-27 | 0
1117 | 1.2 | 1.2.8.5.6.7.5 | C | Subsystem Evaluation | Not Started | 6 | 0 | 2023-12-28 | 2023-12-28 | 1083, 1096, 1116 | 0% |  |  |  | 601 |  | 2023-12-28 | 2023-12-28 | 0
1118 | 1.2 | 1.2.8.5.6.7.6 | C | TOS/Tower Refit Complete | Not Started | 6 | 0 | 2023-12-28 | 2023-12-28 | 1117 | 0% |  |  |  | 601 |  | 2023-12-28 | 2023-12-28 | 0
1119 | 1.2 | 1.2.8.5.6.8 | P | Reels | Not Started | 6 | 20d | 2023-12-15 | 2024-01-15 |  | 0% |  |  |  | 615 |  | 2023-12-15 | 2024-01-15 | 0
1120 | 1.2 | 1.2.8.5.6.8.1 | P | Main Supply Hose Reel (MSHR) | Not Started | 7 | 10d | 2023-12-15 | 2023-12-29 |  | 0% |  |  |  | 625 |  | 2023-12-15 | 2023-12-29 | 0
1121 | 1.2 | 1.2.8.5.6.8.1.1 | C | MSHR Relocation Support (USAP) | Not Started | 8 | 1d | 2023-12-15 | 2023-12-15 | 1216FS -1d, 912 | 0% |  | USAP Support |  | 622 |  | 2023-12-15 | 2023-12-15 | 0
1122 | 1.2 | 1.2.8.5.6.8.1.2 | C | Install Manifold, Heat Trace & Insulation | Not Started | 8 | 4d | 2023-12-19 | 2023-12-22 | 1092, 1121 | 0% |  |  |  | 617 |  | 2023-12-19 | 2023-12-22 | 0
1123 | 1.2 | 1.2.8.5.6.8.1.3 | C | Inspect Drive and Control Components, Energize & Test | Not Started | 8 | 2d | 2023-12-26 | 2023-12-27 | 1122 | 0% |  |  |  | 615 |  | 2023-12-26 | 2023-12-27 | 0
1124 | 1.2 | 1.2.8.5.6.8.1.4 | C | MSHR Repairs & Refit Complete | Not Started | 8 | 2d | 2023-12-28 | 2023-12-29 | 1121, 1122, 1123 | 0% |  |  |  | 623 |  | 2023-12-28 | 2023-12-29 | 0
1125 | 1.2 | 1.2.8.5.6.8.2 | P | Return Water Hose Reel (RWHR) | Not Started | 7 | 8d | 2024-01-03 | 2024-01-12 |  | 0% |  |  |  | 616 |  | 2024-01-03 | 2024-01-12 | 0
1126 | 1.2 | 1.2.8.5.6.8.2.1 | C | RWHR Relocation Support (USAP) | Not Started | 8 | 1d | 2024-01-03 | 2024-01-03 | 912FS +37d | 0% |  | USAP Support |  | 615 |  | 2024-01-03 | 2024-01-03 | 0
1127 | 1.2 | 1.2.8.5.6.8.2.2 | C | Install Microbrake & Service Drum Brake and Gear Box | Not Started | 8 | 2d | 2024-01-04 | 2024-01-05 | 1126 | 0% |  |  |  | 615 |  | 2024-01-04 | 2024-01-05 | 0
1128 | 1.2 | 1.2.8.5.6.8.2.3 | C | Install Heat Trace & Insulation on Water Plumbing | Not Started | 8 | 1d | 2024-01-08 | 2024-01-08 | 1127 | 0% |  |  |  | 615 |  | 2024-01-08 | 2024-01-08 | 0
1129 | 1.2 | 1.2.8.5.6.8.2.4 | C | Install Motor | Not Started | 8 | 2d | 2024-01-09 | 2024-01-10 | 1128 | 0% |  |  |  | 615 |  | 2024-01-09 | 2024-01-10 | 0
1130 | 1.2 | 1.2.8.5.6.8.2.5 | C | Inspect Drive and Control Components, Energize & Test | Not Started | 8 | 2d | 2024-01-11 | 2024-01-12 | 1129 | 0% |  |  |  | 615 |  | 2024-01-11 | 2024-01-12 | 0
1131 | 1.2 | 1.2.8.5.6.8.2.6 | C | RWHR Refit & Repairs Complete | Not Started | 8 | 0 | 2024-01-12 | 2024-01-12 | 1126, 1127, 1128, 1129, 1130 | 0% |  |  |  | 615 |  | 2024-01-12 | 2024-01-12 | 0
1132 | 1.2 | 1.2.8.5.6.8.4 | P | Return Water Cable Reel (RWCR) | Not Started | 7 | 6d | 2024-01-02 | 2024-01-09 |  | 0% |  |  |  | 619 |  | 2024-01-02 | 2024-01-09 | 0
1133 | 1.2 | 1.2.8.5.6.8.4.1 | C | RWCR Relocation Support (USAP) | Not Started | 8 | 1d | 2024-01-02 | 2024-01-02 | 912FS +36d | 0% |  | USAP Support |  | 618 |  | 2024-01-02 | 2024-01-02 | 0
1134 | 1.2 | 1.2.8.5.6.8.4.2 | C | Install Slip Rings | Not Started | 8 | 3d | 2024-01-03 | 2024-01-05 | 1133 | 0% |  |  |  | 618 |  | 2024-01-03 | 2024-01-05 | 0
1135 | 1.2 | 1.2.8.5.6.8.4.3 | C | Inspect Drive and Control Components, Energize & Test | Not Started | 8 | 2d | 2024-01-08 | 2024-01-09 | 1134 | 0% |  |  |  | 618 |  | 2024-01-08 | 2024-01-09 | 0
1136 | 1.2 | 1.2.8.5.6.8.4.4 | C | RWCR Repairs & Refit Complete | Not Started | 8 | 0 | 2024-01-09 | 2024-01-09 | 1134, 1135 | 0% |  |  |  | 618 |  | 2024-01-09 | 2024-01-09 | 0
1137 | 1.2 | 1.2.8.5.6.8.5 | P | Main Cable Reel (MCR) | Not Started | 7 | 4d | 2023-12-15 | 2023-12-20 |  | 0% |  |  |  | 631 |  | 2023-12-15 | 2023-12-20 | 0
1138 | 1.2 | 1.2.8.5.6.8.5.1 | C | MCR Relocation Support (USAP) | Not Started | 8 | 1d | 2023-12-15 | 2023-12-15 | 1216FS -1d | 0% |  | USAP Support |  | 630 |  | 2023-12-15 | 2023-12-15 | 0
1139 | 1.2 | 1.2.8.5.6.8.5.2 | C | Install Slip Ring | Not Started | 8 | 1d | 2023-12-18 | 2023-12-18 | 1138 | 0% |  |  |  | 632 |  | 2023-12-18 | 2023-12-18 | 0
1140 | 1.2 | 1.2.8.5.6.8.5.3 | C | Inspect Drive and Control Components, Energize & Test | Not Started | 8 | 3d | 2023-12-18 | 2023-12-20 | 1091, 1138 | 0% |  |  |  | 630 |  | 2023-12-18 | 2023-12-20 | 0
1141 | 1.2 | 1.2.8.5.6.8.5.4 | C | MCR Repair & Refit Complete | Not Started | 8 | 0 | 2023-12-20 | 2023-12-20 | 1138, 1139, 1140 | 0% |  |  |  | 630 |  | 2023-12-20 | 2023-12-20 | 0
1142 | 1.2 | 1.2.8.5.6.8.6 | C | Berm all Reels for Winter (USAP) | Not Started | 7 | 1d | 2024-01-15 | 2024-01-15 | 1124, 1131, 1136, 1141 | 0% |  | USAP Support |  | 615 |  | 2024-01-15 | 2024-01-15 | 0
1143 | 1.2 | 1.2.8.5.6.9 | P | Winches (TU-15, TU-20s) | Not Started | 6 | 10d | 2024-01-09 | 2024-01-22 |  | 0% |  |  |  | 610 |  | 2024-01-09 | 2024-01-22 | 0
1144 | 1.2 | 1.2.8.5.6.9.2 | C | TU20 x 2 - Replace Hydraulic Pump & Upgrade Hydraulic Plumbing | Not Started | 7 | 4d | 2024-01-09 | 2024-01-12 | 912FS +41d | 0% |  |  |  | 610 |  | 2024-01-09 | 2024-01-12 | 0
1145 | 1.2 | 1.2.8.5.6.9.3 | C | TU15 - Replace Hydraulic Pump & Upgrade Hydraulic Plumbing | Not Started | 7 | 2d | 2024-01-15 | 2024-01-16 | 1144 | 0% |  |  |  | 610 |  | 2024-01-15 | 2024-01-16 | 0
1146 | 1.2 | 1.2.8.5.6.9.4 | C | TU20 Test Brake/Control Interface Boxes w/ Brakes (FW rectifier and fuse) | Not Started | 7 | 2d | 2024-01-15 | 2024-01-16 | 1144 | 0% |  |  |  | 610 |  | 2024-01-15 | 2024-01-16 | 0
1147 | 1.2 | 1.2.8.5.6.9.5 | C | TU20 - Install Slip Rings & Test | Not Started | 7 | 3d | 2024-01-15 | 2024-01-17 | 1146SS | 0% |  |  |  | 610 |  | 2024-01-15 | 2024-01-17 | 0
1148 | 1.2 | 1.2.8.5.6.9.6 | C | Inspect Drive and Control Components, Energize & Test | Not Started | 7 | 2d | 2024-01-18 | 2024-01-19 | 1147, 1146, 1145, 1144 | 0% |  |  |  | 610 |  | 2024-01-18 | 2024-01-19 | 0
1149 | 1.2 | 1.2.8.5.6.9.7 | C | Winches Complete | Not Started | 7 | 0 | 2024-01-19 | 2024-01-19 | 1144, 1145, 1146, 1147, 1148 | 0% |  |  |  | 610 |  | 2024-01-19 | 2024-01-19 | 0
1150 | 1.2 | 1.2.8.5.6.9.8 | C | Berm Winches for Winter (USAP) | Not Started | 7 | 1d | 2024-01-22 | 2024-01-22 | 1149 | 0% |  | USAP Support |  | 610 |  | 2024-01-22 | 2024-01-22 | 0
1151 | 1.2 | 1.2.8.5.6.10 | P | Independent Firn Drill (IFD) | Not Started | 6 | 269d | 2023-01-04 | 2024-01-18 |  | 0% |  |  |  | 612 |  | 2023-01-04 | 2024-01-18 | 0
1152 | 1.2 | 1.2.8.5.6.10.1 | P | Refit, Repairs, & Testing (IFD) | Not Started | 7 | 265d | 2023-01-04 | 2024-01-12 |  | 0% |  |  |  | 616 |  | 2023-01-04 | 2024-01-12 | 0
1153 | 1.2 | 1.2.8.5.6.10.1.1 | C | Deliver Firn Drill to Cryo Worksite (USAP) | Not Started | 8 | 1d | 2023-01-04 | 2023-01-04 | 844 | 0% |  | USAP Support |  | 612 |  | 2023-01-04 | 2023-01-04 | 0
1154 | 1.2 | 1.2.8.5.6.10.1.2 | C | Integrate & Support CRREL Gen for Firn Drill Testing (USAP) | Not Started | 8 | 5d | 2024-01-03 | 2024-01-09 | 927FS +17d, 1153 | 0% |  | USAP Support |  | 612 |  | 2024-01-03 | 2024-01-09 | 0
1155 | 1.2 | 1.2.8.5.6.10.1.10 | C | Replace Appleton Disconnect (USAP) | Not Started | 8 | 2d | 2023-01-05 | 2023-01-06 | 1153 | 0% |  | USAP Support |  | 612 |  | 2023-01-05 | 2023-01-06 | 0
1156 | 1.2 | 1.2.8.5.6.10.1.3 | C | Install Sheave - Crane or Station Hoist | Not Started | 8 | 2d | 2023-01-09 | 2023-01-10 | 1155 | 0% |  |  |  | 612 |  | 2023-01-09 | 2023-01-10 | 0
1157 | 1.2 | 1.2.8.5.6.10.1.4 | C | Crane or Station Hoist Support for Sheave Installation (USAP) | Not Started | 8 | 2d | 2023-01-09 | 2023-01-10 | 1155 | 0% |  | USAP Support |  | 869 |  | 2023-01-09 | 2023-01-10 | 0
1158 | 1.2 | 1.2.8.5.6.10.1.5 | C | Install Brake Pump & Solenoid | Not Started | 8 | 1d | 2023-01-05 | 2023-01-05 | 1153 | 0% |  |  |  | 872 |  | 2023-01-05 | 2023-01-05 | 0
1159 | 1.2 | 1.2.8.5.6.10.1.6 | C | Install DNF - Black box, Thermostats, Power Meter, & Inst. Readout | Not Started | 8 | 2d | 2023-01-05 | 2023-01-06 | 1153 | 0% |  |  |  | 612 |  | 2023-01-05 | 2023-01-06 | 0
1160 | 1.2 | 1.2.8.5.6.10.1.7 | C | Load Cell Calibration/Verification | Not Started | 8 | 1d | 2023-01-11 | 2023-01-11 | 1156 | 0% |  | USAP Support |  | 868 |  | 2023-01-11 | 2023-01-11 | 0
1161 | 1.2 | 1.2.8.5.6.10.1.8 | C | Supply Glycol PG (USAP) | Not Started | 8 | 0 | 2023-01-06 | 2023-01-06 | 1159 | 0% |  | USAP Support |  | 612 |  | 2023-01-06 | 2023-01-06 | 0
1162 | 1.2 | 1.2.8.5.6.10.1.9 | C | Fill System w/ Glycol | Not Started | 8 | 1d | 2023-01-09 | 2023-01-09 | 1161 | 0% |  |  |  | 870 |  | 2023-01-09 | 2023-01-09 | 0
1163 | 1.2 | 1.2.8.5.6.10.1.11 | C | Test Firn Drill | Not Started | 8 | 3d | 2024-01-10 | 2024-01-12 | 1154, 1156, 1157, 1158, 1159, 1160, 1161, 1162, 1155 | 0% |  |  |  | 612 |  | 2024-01-10 | 2024-01-12 | 0
1164 | 1.2 | 1.2.8.5.6.10.2 | C | Winterize (IFD) 2ME 2 TE | Not Started | 7 | 2d | 2024-01-15 | 2024-01-16 | 1163 | 0% |  |  |  | 612 |  | 2024-01-15 | 2024-01-16 | 0
1165 | 1.2 | 1.2.8.5.6.10.2 | C | Stored IFD for Winter (USAP) | Not Started | 7 | 2d | 2024-01-17 | 2024-01-18 | 1164 | 0% |  | USAP Support |  | 612 |  | 2024-01-17 | 2024-01-18 | 0
1166 | 1.2 | 1.2.8.5.6.11 | P | Integrate ARA Drill (RodWell system) | Not Started | 6 | 17d | 2023-12-29 | 2024-01-23 |  | 0% |  |  |  | 609 |  | 2023-12-29 | 2024-01-23 | 0
1167 | 1.2 | 1.2.8.5.6.11.1 | C | Deliver ARA Drill To Cryo Worksite - Precommission | Not Started | 7 | 1d | 2023-12-29 | 2023-12-29 | 912FS +35d | 0% |  |  |  | 601 |  | 2023-12-29 | 2023-12-29 | 0
1168 | 1.2 | 1.2.8.5.6.11.2 | P | White Generator - Commission | Not Started | 7 | 3d | 2024-01-02 | 2024-01-04 |  | 0% |  |  |  | 622 |  | 2024-01-02 | 2024-01-04 | 0
1169 | 1.2 | 1.2.8.5.6.11.2.1 | C | Warm-up, Inspect Gen, Fill fluids, Install Fire Extinguisher, & Test-run John Deere with External Load | Not Started | 8 | 1d | 2024-01-02 | 2024-01-02 | 1167 | 0% |  |  |  | 609 |  | 2024-01-02 | 2024-01-02 | 0
1170 | 1.2 | 1.2.8.5.6.11.2.2 | C | White Gen Electrical Rework | Not Started | 8 | 2d | 2024-01-02 | 2024-01-03 | 1167 | 0% |  |  |  | 601 |  | 2024-01-02 | 2024-01-03 | 0
1171 | 1.2 | 1.2.8.5.6.11.2.3 | C | Electrician Support for White Gen Rework (USAP) | Not Started | 8 | 2d | 2024-01-02 | 2024-01-03 | 1170SS | 0% |  | USAP Support |  | 601 |  | 2024-01-02 | 2024-01-03 | 0
1172 | 1.2 | 1.2.8.5.6.11.2.4 | C | Install Control Interface Panel, Downhole Pump Controller, Ext. E-stop Slap, & Power up from Cryo | Not Started | 8 | 1d | 2024-01-04 | 2024-01-04 | 1171 | 0% |  |  |  | 601 |  | 2024-01-04 | 2024-01-04 | 0
1173 | 1.2 | 1.2.8.5.6.11.3 | P | Sled 2 Water Tank Sled - Precommission | Not Started | 7 | 3d | 2024-01-03 | 2024-01-05 |  | 0% |  |  |  | 621 |  | 2024-01-03 | 2024-01-05 | 0
1174 | 1.2 | 1.2.8.5.6.11.3.1 | C | Warm-up & Inspect, Check HMW Sheets, & Tie-offs, Glycol Tank, Glycol Heater, Hoses & Connections | Not Started | 8 | 1d | 2024-01-03 | 2024-01-03 | 1169 | 0% |  |  |  | 609 |  | 2024-01-03 | 2024-01-03 | 0
1175 | 1.2 | 1.2.8.5.6.11.3.2 | C | Install ePump, Accessories, & ePump Controller (DNF-requires power) | Not Started | 8 | 1d | 2024-01-04 | 2024-01-04 | 1174 | 0% |  |  |  | 609 |  | 2024-01-04 | 2024-01-04 | 0
1176 | 1.2 | 1.2.8.5.6.11.3.3 | C | Checkout & Testing Sled 2 | Not Started | 8 | 1d | 2024-01-05 | 2024-01-05 | 1175 | 0% |  |  |  | 609 |  | 2024-01-05 | 2024-01-05 | 0
1177 | 1.2 | 1.2.8.5.6.11.4 | P | Sled 3 Drilling Sled - Precommission | Not Started | 7 | 10d | 2024-01-05 | 2024-01-18 |  | 0% |  |  |  | 612 |  | 2024-01-05 | 2024-01-18 | 0
1178 | 1.2 | 1.2.8.5.6.11.4.1 | C | Warm-up & Inspect Components, Install Stacks, Install Hoist, Top-off Fuel Tank, Reel Brake, Heat Trace | Not Started | 8 | 2d | 2024-01-08 | 2024-01-09 | 1176 | 0% |  |  |  | 609 |  | 2024-01-08 | 2024-01-09 | 0
1179 | 1.2 | 1.2.8.5.6.11.4.2 | C | Plumbing Upgrades & Repairs | Not Started | 8 | 2d | 2024-01-10 | 2024-01-11 | 1178 | 0% |  |  |  | 609 |  | 2024-01-10 | 2024-01-11 | 0
1180 | 1.2 | 1.2.8.5.6.11.4.3 | C | ARA DCC Upgrades & Install | Not Started | 8 | 2d | 2024-01-05 | 2024-01-08 | 1172 | 0% |  |  |  | 601 |  | 2024-01-05 | 2024-01-08 | 0
1181 | 1.2 | 1.2.8.5.6.11.4.4 | C | Hose Cable Bundle Replace | Not Started | 8 | 5d | 2024-01-12 | 2024-01-18 | 1179 | 0% |  |  |  | 609 |  | 2024-01-12 | 2024-01-18 | 0
1182 | 1.2 | 1.2.8.5.6.11.5 | P | Rodwell Drill Head Commissioning | Not Started | 7 | 2d | 2024-01-19 | 2024-01-22 |  | 0% |  |  |  | 610 |  | 2024-01-19 | 2024-01-22 | 0
1183 | 1.2 | 1.2.8.5.6.11.5.1 | C | Locate Components, Set-up Drillheads on Bench, Inspect, Sensor tests | Not Started | 8 | 1d | 2024-01-19 | 2024-01-19 | 1181 | 0% |  |  |  | 609 |  | 2024-01-19 | 2024-01-19 | 0
1184 | 1.2 | 1.2.8.5.6.11.5.2 | C | Drillhead Chain Testing & Verification | Not Started | 8 | 1d | 2024-01-22 | 2024-01-22 | 1183 | 0% |  |  |  | 609 |  | 2024-01-22 | 2024-01-22 | 0
1185 | 1.2 | 1.2.8.5.6.11.6 | P | System Commissioning | Not Started | 7 | 11d | 2024-01-09 | 2024-01-23 |  | 0% |  |  |  | 609 |  | 2024-01-09 | 2024-01-23 | 0
1186 | 1.2 | 1.2.8.5.6.11.6.1 | C | System Commissioning Set-up Tasks & Global Tests | Not Started | 8 | 1d | 2024-01-23 | 2024-01-23 | 1184 | 0% |  |  |  | 609 |  | 2024-01-23 | 2024-01-23 | 0
1187 | 1.2 | 1.2.8.5.6.11.6.2 | C | Hose Reel Commissioning | Not Started | 8 | 2d | 2024-01-09 | 2024-01-10 | 1180 | 0% |  |  |  | 601 |  | 2024-01-09 | 2024-01-10 | 0
1188 | 1.2 | 1.2.8.5.6.11.6.3 | C | Circulation Testing, w/ Glycol - Staged Approach | Not Started | 8 | 1d | 2024-01-11 | 2024-01-11 | 1187 | 0% |  |  |  | 601 |  | 2024-01-11 | 2024-01-11 | 0
1189 | 1.2 | 1.2.8.5.6.11.6.4 | C | Heater Commissioning | Not Started | 8 | 1d | 2024-01-12 | 2024-01-12 | 1188 | 0% |  |  |  | 601 |  | 2024-01-12 | 2024-01-12 | 0
1190 | 1.2 | 1.2.8.5.6.11.6.5 | C | Global Controls & E-stop Testing | Not Started | 8 | 1d | 2024-01-11 | 2024-01-11 | 1187 | 0% |  |  |  | 617 |  | 2024-01-11 | 2024-01-11 | 0
1191 | 1.2 | 1.2.8.5.6.11.6.6 | C | System Testing in Test Well | Not Started | 8 | 1d | 2024-01-15 | 2024-01-15 | 1189 | 0% |  |  |  | 601 |  | 2024-01-15 | 2024-01-15 | 0
1192 | 1.2 | 1.2.8.5.6.11.7 | P | System Winterize and Store | Not Started | 7 | 3d | 2024-01-16 | 2024-01-18 |  | 0% |  |  |  | 612 |  | 2024-01-16 | 2024-01-18 | 0
1193 | 1.2 | 1.2.8.5.6.11.7.1 | C | Drain & Blow-out System | Not Started | 8 | 1d | 2024-01-16 | 2024-01-16 | 1191 | 0% |  |  |  | 601 |  | 2024-01-16 | 2024-01-16 | 0
1194 | 1.2 | 1.2.8.5.6.11.7.2 | C | Remove and Store DNF Hardware | Not Started | 8 | 1d | 2024-01-17 | 2024-01-17 | 1193 | 0% |  |  |  | 612 |  | 2024-01-17 | 2024-01-17 | 0
1195 | 1.2 | 1.2.8.5.6.11.7.3 | C | Tarp, Cover, & Plug | Not Started | 8 | 1d | 2024-01-18 | 2024-01-18 | 1194 | 0% |  |  |  | 612 |  | 2024-01-18 | 2024-01-18 | 0
1196 | 1.2 | 1.2.8.5.6.12 | P | Fuel Tower | Not Started | 6 | 10d | 2023-11-21 | 2023-12-05 |  | 0% |  |  |  | 642 |  | 2023-11-21 | 2023-12-05 | 0
1197 | 1.2 | 1.2.8.5.6.12.1 | C | Fuel Tower Relocation Support (USAP) | Not Started | 7 | 1d | 2023-11-21 | 2023-11-21 | 1014FF | 0% |  | USAP Support |  | 619 |  | 2023-11-21 | 2023-11-21 | 0
1198 | 1.2 | 1.2.8.5.6.12.2 | C | Mechanical Repairs & Upgrades | Not Started | 7 | 2d | 2023-11-28 | 2023-11-29 | 1197FS +3d | 0% |  |  |  | 612 |  | 2023-11-28 | 2023-11-29 | 0
1199 | 1.2 | 1.2.8.5.6.12.3 | C | Test Existing Local Hardware, Control Functionality, Document | Not Started | 7 | 2d | 2023-12-04 | 2023-12-05 | 1198FS +2d | 0% |  |  |  | 642 |  | 2023-12-04 | 2023-12-05 | 0
1200 | 1.2 | 1.2.8.5.6.12.4 | C | Fill Fuel Tower with Fuel | Not Started | 7 | 1d | 2023-12-04 | 2023-12-04 | 1198FS +2d | 0% |  |  |  | 612 |  | 2023-12-04 | 2023-12-04 | 0
1201 | 1.2 | 1.2.8.5.6.12.5 | C | Fuel Tower Ready to Supply Fuel | Not Started | 7 | 0 | 2023-12-04 | 2023-12-04 | 1198FS +2d, 1200 | 0% |  |  |  | 612 |  | 2023-12-04 | 2023-12-04 | 0
1202 | 1.2 | 1.2.8.5.6.13 | P | Heat Pump Unit 2 (HPU2) | Not Started | 6 | 43d | 2023-12-15 | 2024-02-15 |  | 0% |  |  |  | 592 |  | 2023-12-15 | 2024-02-15 | 0
1203 | 1.2 | 1.2.8.5.6.13.1 | C | HPU Relocation Support (USAP) | Not Started | 7 | 4d | 2024-02-12 | 2024-02-15 | 911, 927 | 0% |  | USAP Support |  | 592 |  | 2024-02-12 | 2024-02-15 | 0
1204 | 1.2 | 1.2.8.5.6.13.2 | C | Initial Evaluation & Refit (HPU2) | Not Started | 7 | 10d | 2023-12-15 | 2023-12-29 | 932 | 0% |  |  |  | 625 |  | 2023-12-15 | 2023-12-29 | 0
1205 | 1.2 | 1.2.8.5.7 | P | Seasonal Equipment Site (SES) Setup | Not Started | 5 | 28d | 2023-12-01 | 2024-01-11 |  | 0% |  |  |  | 617 |  | 2023-12-01 | 2024-01-11 | 0
1206 | 1.2 | 1.2.8.5.7.1 | P | MHP Relocation to SES | Not Started | 6 | 28d | 2023-12-01 | 2024-01-11 |  | 0% |  |  |  | 617 |  | 2023-12-01 | 2024-01-11 | 0
1207 | 1.2 | 1.2.8.5.7.1.1 | C | Deliver Kuma Heated Warm-up Shack (USAP) | Not Started | 7 | 1d | 2023-12-05 | 2023-12-05 | 1212 | 0% |  | USAP Support |  | 642 |  | 2023-12-05 | 2023-12-05 | 0
1208 | 1.2 | 1.2.8.5.7.1.2 | C | Driller Support for MHP Relocation (Driller) | Not Started | 7 | 4d | 2024-01-08 | 2024-01-11 | 1209SS, 1210FF, 1211, 1212, 1213, 1214, 1215, 1216, 1217, 1218, 1219, 1220 | 0% |  |  |  | 617 |  | 2024-01-08 | 2024-01-11 | 0
1209 | 1.2 | 1.2.8.5.7.1.3 | C | MHP1 Relocation to SES (USAP) | Not Started | 7 | 1d | 2023-12-04 | 2023-12-04 | 955, 964, 1210, 916FS +1d | 0% |  | USAP Support |  | 609 |  | 2023-12-04 | 2023-12-04 | 0
1210 | 1.2 | 1.2.8.5.7.1.4 | C | MHP2 Relocation to SES (USAP) | Not Started | 7 | 1d | 2023-12-01 | 2023-12-01 | 972, 980, 916FS +1d | 0% |  | USAP Support |  | 609 |  | 2023-12-01 | 2023-12-01 | 0
1211 | 1.2 | 1.2.8.5.7.1.5 | C | MHP3 Relocation to SES (USAP) | Not Started | 7 | 1d | 2023-12-05 | 2023-12-05 | 988, 996, 916, 1212 | 0% |  | USAP Support |  | 609 |  | 2023-12-05 | 2023-12-05 | 0
1212 | 1.2 | 1.2.8.5.7.1.6 | C | MHP4 Relocation to SES (USAP) | Not Started | 7 | 1d | 2023-12-04 | 2023-12-04 | 1004, 1012, 916 | 0% |  | USAP Support |  | 609 |  | 2023-12-04 | 2023-12-04 | 0
1213 | 1.2 | 1.2.8.5.7.1.7 | C | PHS Relocation to SES (USAP) | Not Started | 7 | 1d | 2024-01-05 | 2024-01-05 | 1024, 1035, 916, 1215 | 0% |  | USAP Support |  | 609 |  | 2024-01-05 | 2024-01-05 | 0
1214 | 1.2 | 1.2.8.5.7.1.8 | C | Fuel Tower Relocation to SES (USAP) | Not Started | 7 | 1d | 2024-01-05 | 2024-01-05 | 1201, 1213FF | 0% |  | USAP Support |  | 612 |  | 2024-01-05 | 2024-01-05 | 0
1215 | 1.2 | 1.2.8.5.7.1.9 | C | HPP Relocation to SES (USAP) | Not Started | 7 | 1d | 2024-01-04 | 2024-01-04 | 1045, 1059, 916 | 0% |  | USAP Support |  | 609 |  | 2024-01-04 | 2024-01-04 | 0
1216 | 1.2 | 1.2.8.5.7.1.10 | C | Water Tanks Relocation to SES (USAP) | Not Started | 7 | 1d | 2023-12-15 | 2023-12-15 | 1068, 916 | 0% |  | USAP Support |  | 609 |  | 2023-12-15 | 2023-12-15 | 0
1217 | 1.2 | 1.2.8.5.7.1.11 | C | Gen1 Relocation to SES (USAP) | Not Started | 7 | 1d | 2023-12-21 | 2023-12-21 | 933 | 0% |  | USAP Support |  | 621 |  | 2023-12-21 | 2023-12-21 | 0
1218 | 1.2 | 1.2.8.5.7.1.12 | C | Gen2 Relocation to SES (USAP) | Not Started | 7 | 1d | 2023-12-21 | 2023-12-21 | 933 | 0% |  | USAP Support |  | 621 |  | 2023-12-21 | 2023-12-21 | 0
1219 | 1.2 | 1.2.8.5.7.1.13 | C | Gen3 Relocation to SES (USAP) | Not Started | 7 | 1d | 2023-12-21 | 2023-12-21 | 933 | 0% |  | USAP Support |  | 621 |  | 2023-12-21 | 2023-12-21 | 0
1220 | 1.2 | 1.2.8.5.7.1.14 | C | PDM Relocation to SES (USAP) | Not Started | 7 | 1d | 2023-12-21 | 2023-12-21 | 933 | 0% |  | USAP Support |  | 621 |  | 2023-12-21 | 2023-12-21 | 0
1221 | 1.2 | 1.2.8.5.7.2 | C | Provide Small Temp Generator for SES and Establish (USAP) | Not Started | 6 | 1d | 2023-12-05 | 2023-12-05 | 1212 | 0% |  | USAP Support |  | 642 |  | 2023-12-05 | 2023-12-05 | 0
1222 | 1.2 | 1.2.8.5.7.3 | P | Interconnect Evaluation - Hoses, Cables & Cable Trays for SES | Not Started | 6 | 4d | 2024-01-08 | 2024-01-11 |  | 0% |  |  |  | 617 |  | 2024-01-08 | 2024-01-11 | 0
1223 | 1.2 | 1.2.8.5.7.3.1 | C | Cable Trays - Mount/Install | Not Started | 7 | 4d | 2024-01-08 | 2024-01-11 | 1209, 1210, 1211, 1212, 1213, 1215, 1216 | 0% |  |  |  | 613 |  | 2024-01-08 | 2024-01-11 | 0
1224 | 1.2 | 1.2.8.5.7.3.2 | C | Hoses - Layout, Inventory, Repair & Test | Not Started | 7 | 4d | 2024-01-08 | 2024-01-11 | 1223SS | 0% |  |  |  | 617 |  | 2024-01-08 | 2024-01-11 | 0
1225 | 1.2 | 1.2.8.5.7.3.3 | C | Cables - Layout, Inventory, Repair & Test | Not Started | 7 | 4d | 2024-01-08 | 2024-01-11 | 1223SS | 0% |  |  |  | 617 |  | 2024-01-08 | 2024-01-11 | 0
1226 | 1.2 | 1.2.8.5.7.4 | C | Establish Fuel Tower at SES | Not Started | 6 | 2d | 2024-01-08 | 2024-01-09 | 1214 | 0% |  |  |  | 619 |  | 2024-01-08 | 2024-01-09 | 0
1227 | 1.2 | 1.2.8.5.7.5 | C | SES Initial Setup Complete | Not Started | 6 | 0 | 2024-01-05 | 2024-01-05 | 1209, 1210, 1211, 1212, 1213, 1214, 1215, 1216, 1217, 1218, 1219, 1220 | 0% |  |  |  | 617 |  | 2024-01-05 | 2024-01-05 | 0
1228 | 1.2 | 1.2.8.5.8 | P | End of NPX Season Close-Out Work | Not Started | 5 | 16d | 2024-01-12 | 2024-02-02 |  | 0% |  |  |  | 601 |  | 2024-01-12 | 2024-02-02 | 0
1229 | 1.2 | 1.2.8.5.8.1 | C | Document, Photograph Equip & Upgrade Work, Further Req's | Not Started | 6 | 4d | 2024-01-15 | 2024-01-18 | 1227FS +5d | 0% |  |  |  | 612 |  | 2024-01-15 | 2024-01-18 | 0
1230 | 1.2 | 1.2.8.5.8.2 | C | Remove DNF (Computer Equip, Drives, & Capacitors) & Store | Not Started | 6 | 4d | 2024-01-17 | 2024-01-22 | 1118, 1193 | 0% |  |  |  | 601 |  | 2024-01-17 | 2024-01-22 | 0
1231 | 1.2 | 1.2.8.5.8.3 | C | Winterize/Close/Store all EHWD Equipment | Not Started | 6 | e4d | 2024-01-15 | 2024-01-19 | 1227FS +5d, 1118FS +5d | 0% |  |  |  | 612 |  | 2024-01-15 | 2024-01-19 | 0
1232 | 1.2 | 1.2.8.5.8.4 | C | Setup & Connect Hose Heating Controller, Test over FS1-FS2 winter | Not Started | 6 | 2d | 2024-01-23 | 2024-01-24 | 1124FS +15d | 0% |  |  |  | 608 |  | 2024-01-23 | 2024-01-24 | 0
1233 | 1.2 | 1.2.8.5.8.5 | C | Crate, Pack and Deliver Retro to Cargo | Not Started | 6 | 7d | 2024-01-12 | 2024-01-22 | 1230FF | 0% |  |  |  | 601 |  | 2024-01-12 | 2024-01-22 | 0
1234 | 1.2 | 1.2.8.5.8.6 | C | Winter Storage Support: TOS 1 & 2 (USAP) | Not Started | 6 | 9d | 2024-01-23 | 2024-02-02 | 1233 | 0% |  | USAP Support |  | 601 |  | 2024-01-23 | 2024-02-02 | 0
1235 | 1.2 | 1.2.8.5.9 | P | Other Field Activities (FS1) | Not Started | 5 | 18d | 2023-10-23 | 2023-11-15 |  | 0% |  |  |  | 655 |  | 2023-10-23 | 2023-11-15 | 0
1236 | 1.2 | 1.2.8.5.9.1 | C | MCM Logistics Rep (Driller) | Not Started | 6 | 18d | 2023-10-23 | 2023-11-15 | 879FS +15d | 0% |  |  |  | 655 |  | 2023-10-23 | 2023-11-15 | 0
1237 | 1.2 | 1.2.8.5.10 | C | ICU Field Team Redeployed | Not Started | 5 | 0 | 2024-01-26 | 2024-01-26 | 1230, 1231, 1232FS +2d | 0% |  |  |  | 606 |  | 2024-01-26 | 2024-01-26 | 0
1238 | 1.2 | 1.2.8.5.11 | C | On-Ice Labor (FS1) | Not Started | 5 | 192d | 2023-06-02 | 2024-02-29 |  | 0% |  |  | EE/ME Engineer Labor Totals from Population file. Assumes 2 days in McMurdo southbound and 0 days northbound. Technician Labor Totals from Population file. Assumes 2 days in McMurdo southbound and 0 days northbound. Safety Engineer Labor Totals from Population file. Assumes 2 days in McMurdo southbound and 0 days northbound. | 582 |  | 2023-06-02 | 2024-02-29 | 0
1239 | 1.2 | 1.2.8.5.12 | C | END NPX FS1 Season | Not Started | 5 | 0 | 2024-02-02 | 2024-02-02 | 1228FF | 0% |  |  |  | 601 |  | 2024-02-02 | 2024-02-02 | 0
1240 | 1.2 | 1.2.8.6 | P | USAP Field Season 2 (FY25) | Not Started | 4 | 582d | 2023-10-31 | 2026-02-03 |  | 0% |  |  |  | 85 |  | 2023-10-31 | 2026-02-03 | 0
1241 | 1.2 | 1.2.8.6.1 | P | FS2 Milestones | Not Started | 5 | 106d | 2024-10-01 | 2025-03-01 |  | 0% |  |  |  | 325 |  | 2024-10-01 | 2025-03-01 | 0
1242 | 1.2 | 1.2.8.6.1.1 | C | McM Mainbody Season Begins (USAP) | Not Started | 6 | 0 | 2024-10-01 | 2024-10-01 |  | 0% |  | USAP Support |  | 305 |  | 2024-10-01 | 2024-10-01 | 0
1243 | 1.2 | 1.2.8.6.1.2 | C | Vessel Arrives (USAP) | Not Started | 6 | 0 | 2025-02-05 | 2025-02-05 | 1242FS +88d | 0% |  | USAP Support |  | 342 |  | 2025-02-05 | 2025-02-05 | 0
1244 | 1.2 | 1.2.8.6.1.3 | C | South Pole Season Begins (USAP) | Not Started | 6 | 0 | 2024-11-01 | 2024-11-01 | 1242FS +23d | 0% |  | USAP Support |  | 306 |  | 2024-11-01 | 2024-11-01 | 0
1245 | 1.2 | 1.2.8.6.1.4 | C | ICU Team Arrives [Headcount 14] | Not Started | 6 | 0 | 2024-11-12 | 2024-11-12 | 1242, 1244FS +7d | 0% |  |  |  | 337 |  | 2024-11-12 | 2024-11-12 | 0
1246 | 1.2 | 1.2.8.6.1.5 | C | Pole Season Ends (USAP) | Not Started | 6 | 0 | 2025-02-15 | 2025-02-15 |  | 0% |  | USAP Support |  | 4 |  | 2025-02-15 | 2025-02-15 | 0
1247 | 1.2 | 1.2.8.6.1.6 | C | MCM Season Ends (USAP) | Not Started | 6 | 0 | 2025-03-01 | 2025-03-01 |  | 0% |  | USAP Support |  | 325 |  | 2025-03-01 | 2025-03-01 | 0
1248 | 1.2 | 1.2.8.6.2 | C | PQ, ECW & Deployment Travel Costs (FS2) Team | Not Started | 5 | 157d | 2024-07-01 | 2025-02-07 |  | 0% |  |  | 1 Drill Manager, 5 days deployment travel 3 days redeployment. 1 Safety Engineer, 5 days deployment travel 3 days redeployment. 6 PSL Direct Hire, 5 days deployment travel 3 days redeployment. 9 PSL Engineers w/ 2 Rotators, 5 days deployment travel 3 days redeployment. 19 - PQ's @ $950/each (anticipated cost) - 2 Alternates and 17 Primaries. 17 - Deploy travel costs w/ 2 PSL rotator @ $1800 each. | 339 |  | 2024-07-01 | 2025-02-07 | 0
1249 | 1.2 | 1.2.8.6.3 | P | USAP Cargo Movements (FY25) | Not Started | 5 | 322d | 2023-10-31 | 2025-01-31 |  | 0% |  |  |  | 345 |  | 2023-10-31 | 2025-01-31 | 0
1250 | 1.2 | 1.2.8.6.3.1 | P | Pole (USAP) | Not Started | 6 | 322d | 2023-10-31 | 2025-01-31 |  | 0% |  |  |  | 345 |  | 2023-10-31 | 2025-01-31 | 0
1251 | 1.2 | 1.2.8.6.3.1.1 | P | LC130 - Pole (USAP) | Not Started | 7 | 270d | 2023-10-31 | 2024-11-15 |  | 0 |  |  |  | 397 |  | 2023-10-31 | 2024-11-15 | 0
1252 | 1.2 | 1.2.8.6.3.1.1.1 | C | Controls Component Crates Shipment 3, DNF (USAP) | Not Started | 8 | 0 | 2024-11-13 | 2024-11-13 | 1244FS +8d, 155 | 0% |  | USAP Support |  | 342 |  | 2024-11-13 | 2024-11-13 | 0
1253 | 1.2 | 1.2.8.6.3.1.1.2 | C | Driller Resupply/Refit Container (8' ISO) (USAP) | Not Started | 8 | 0 | 2024-11-13 | 2024-11-13 | 1244FS +8d, 155 | 0% |  | USAP Support |  | 399 |  | 2024-11-13 | 2024-11-13 | 0
1254 | 1.2 | 1.2.8.6.3.1.1.3 | C | Drill Refit Components Crate, DNF (USAP) | Not Started | 8 | 0 | 2024-11-13 | 2024-11-13 | 1244FS +8d, 155 | 0% |  | USAP Support |  | 399 |  | 2024-11-13 | 2024-11-13 | 0
1255 | 1.2 | 1.2.8.6.3.1.1.4 | C | Drill Heads X, Y, & R - DNF (USAP) | Not Started | 8 | 1d | 2023-10-31 | 2023-10-31 | 879, 881, 906 | 0% |  | USAP Support |  | 666 |  | 2023-10-31 | 2023-10-31 | 0
1256 | 1.2 | 1.2.8.6.3.1.1.5 | C | Fuel - 0 Missions, 0 gallons (USAP) | Not Started | 8 | 0 | 2024-11-15 | 2024-11-15 |  | 0% |  | USAP Support |  | 397 |  | 2024-11-15 | 2024-11-15 | 0
1257 | 1.2 | 1.2.8.6.3.1.2 | P | SPOT1 - Pole (USAP) | Not Started | 7 | 0 | 2024-11-29 | 2024-11-29 |  | 0% |  |  |  | 388 |  | 2024-11-29 | 2024-11-29 | 0
1258 | 1.2 | 1.2.8.6.3.1.2.1 | C | Drill Hose x 12 (USAP) | Not Started | 8 | 0 | 2024-11-29 | 2024-11-29 | 1242, 1244FS +19d | 0% |  | USAP Support |  | 344 |  | 2024-11-29 | 2024-11-29 | 0
1259 | 1.2 | 1.2.8.6.3.1.3 | P | SPOT2 - Pole (USAP) | Not Started | 7 | 0 | 2024-12-31 | 2024-12-31 |  | 0% |  |  |  | 367 |  | 2024-12-31 | 2024-12-31 | 0
1260 | 1.2 | 1.2.8.6.3.1.3.1 | C | Fuel - 19,812 gallons (3 ISO 25k liter tank containers) | Not Started | 8 | 0 | 2024-12-31 | 2024-12-31 | 1242, 1244FS +40d | 0% |  | USAP Support |  | 367 |  | 2024-12-31 | 2024-12-31 | 0
1261 | 1.2 | 1.2.8.6.3.1.4 | P | SPOT3 - Pole (USAP) | Not Started | 7 | 0 | 2025-01-31 | 2025-01-31 |  | 0% |  |  |  | 345 |  | 2025-01-31 | 2025-01-31 | 0
1262 | 1.2 | 1.2.8.6.3.1.4.1 | C | Fuel - 6,604 gallons (1 ISO 25k liter tank container) | Not Started | 8 | 0 | 2025-01-31 | 2025-01-31 | 1242, 1244FS +62d | 0% |  | USAP Support |  | 345 |  | 2025-01-31 | 2025-01-31 | 0
1263 | 1.2 | 1.2.8.6.3.2 | P | MCM (USAP) | Not Started | 6 | 63d | 2024-10-15 | 2025-01-15 |  | 0% |  |  |  | 357 |  | 2024-10-15 | 2025-01-15 | 0
1264 | 1.2 | 1.2.8.6.3.2.1 | P | SAAM - ComSur (USAP) | Not Started | 7 | 0 | 2024-10-15 | 2024-10-15 |  | 0% |  |  |  | 420 |  | 2024-10-15 | 2024-10-15 | 0
1265 | 1.2 | 1.2.8.6.3.2.1.1 | C | Controls Component Crates Shipment 3 - DNF (USAP) | Not Started | 8 | 0 | 2024-10-15 | 2024-10-15 | 1242FS +10d, 155 | 0% |  | USAP Support |  | 420 |  | 2024-10-15 | 2024-10-15 | 0
1266 | 1.2 | 1.2.8.6.3.2.1.2 | C | Driller Resupply/Refit Container (8' ISO) (USAP) | Not Started | 8 | 0 | 2024-10-15 | 2024-10-15 | 1242FS +10d, 155 | 0% |  | USAP Support |  | 420 |  | 2024-10-15 | 2024-10-15 | 0
1267 | 1.2 | 1.2.8.6.3.2.1.3 | C | Driller Resupply/Refit Crate - DNF (USAP) | Not Started | 8 | 0 | 2024-10-15 | 2024-10-15 | 1242FS +10d, 155 | 0% |  | USAP Support |  | 420 |  | 2024-10-15 | 2024-10-15 | 0
1268 | 1.2 | 1.2.8.6.3.2.2 | P | Vessel (USAP) | Not Started | 7 | 0 | 2025-01-15 | 2025-01-15 |  | 0% |  |  |  | 357 |  | 2025-01-15 | 2025-01-15 | 0
1269 | 1.2 | 1.2.8.6.3.2.2.1 | C | Placeholder | Not Started | 8 | 0 | 2025-01-15 | 2025-01-15 |  | 0% |  |  |  | 357 |  | 2025-01-15 | 2025-01-15 | 0
1270 | 1.2 | 1.2.8.6.3.3 | C | Retrograde Shipment Northbound - (USAP) | Not Started | 5 | 1d | 2025-01-31 | 2025-01-31 | 1435FS +2d | 0% |  | USAP Support |  | 344 |  | 2025-01-31 | 2025-01-31 | 0
1271 | 1.2 | 1.2.8.6.4 | P | Opening Activities & Seasonal Equipment Site (SES) Set-up | Not Started | 5 | 55d | 2024-11-06 | 2025-01-24 |  | 0% |  |  |  | 349 |  | 2024-11-06 | 2025-01-24 | 0
1272 | 1.2 | 1.2.8.6.4.1 | C | Re-establish SES Drill Pad, Excavate SES and ICL Road, Groom & Compact Roads (USAP) | Not Started | 6 | 4d | 2024-11-07 | 2024-11-12 | 1244FS +4d | 0% |  | USAP Support |  | 308 |  | 2024-11-07 | 2024-11-12 | 0
1273 | 1.2 | 1.2.8.6.4.2 | C | Provide Support Generators - CRREL/Onan Genset (USAP) | Not Started | 6 | 12d | 2024-11-13 | 2024-11-29 | 1272 | 0% |  | USAP Support |  | 345 |  | 2024-11-13 | 2024-11-29 | 0
1274 | 1.2 | 1.2.8.6.4.3 | C | Deliver Early Season SES Warm-up Shack (USAP) | Not Started | 6 | 1d | 2024-11-14 | 2024-11-14 | 1272SS, 1278SS | 0% |  | USAP Support |  | 397 |  | 2024-11-14 | 2024-11-14 | 0
1275 | 1.2 | 1.2.8.6.4.4 | C | Provide Heaters, 953 Loader, 287B Skidsteer, Pax Van, & Snomo's (USAP) | Not Started | 6 | 50d | 2024-11-13 | 2025-01-24 | 1272 | 0% |  | USAP Support |  | 337 |  | 2024-11-13 | 2025-01-24 | 0
1276 | 1.2 | 1.2.8.6.4.5 | C | Excavate Winter Storage Berms & Deliver Towers/Equipment (USAP) | Not Started | 6 | 6d | 2024-11-06 | 2024-11-13 | 1244FS +3d | 0% |  | USAP Support |  | 327 |  | 2024-11-06 | 2024-11-13 | 0
1277 | 1.2 | 1.2.8.6.4.6 | C | Excavate ICL Storage Site & Deliver TOS1/2, DCC, & MSHR to SES (USAP) | Not Started | 6 | 2d | 2024-11-13 | 2024-11-14 | 1272 | 0% |  | USAP Support |  | 342 |  | 2024-11-13 | 2024-11-14 | 0
1278 | 1.2 | 1.2.8.6.4.7 | C | Driller Support for SES Digout | Not Started | 6 | 5d | 2024-11-14 | 2024-11-20 | 1245FS +2d | 0% |  |  |  | 337 |  | 2024-11-14 | 2024-11-20 | 0
1279 | 1.2 | 1.2.8.6.4.8 | C | Build Ramp to Water Tank 1 (USAP) | Not Started | 6 | 1d | 2024-11-15 | 2024-11-15 | 1272FS +2d | 0% |  | USAP Support |  | 344 |  | 2024-11-15 | 2024-11-15 | 0
1280 | 1.2 | 1.2.8.6.4.9 | C | SES Drill Camp Excavated & Established (USAP) | Not Started | 6 | 0 | 2024-11-15 | 2024-11-15 | 1272, 1273SS +2d, 1277, 1279 | 0% |  | USAP Support |  | 345 |  | 2024-11-15 | 2024-11-15 | 0
1281 | 1.2 | 1.2.8.6.4.10 | C | SES IT Support Activities (USAP) | Not Started | 6 | 1d | 2024-11-18 | 2024-11-18 | 1280, 1283SS | 0% |  | USAP Support |  | 389 |  | 2024-11-18 | 2024-11-18 | 0
1282 | 1.2 | 1.2.8.6.4.11 | C | Fuel Tower: Connect, Test and Make Ready | Not Started | 6 | 2d | 2024-11-13 | 2024-11-14 | 1272 | 0% |  |  |  | 389 |  | 2024-11-13 | 2024-11-14 | 0
1283 | 1.2 | 1.2.8.6.4.12 | C | Make Ready all SES Modules (DCC, PHS, MHPs, MECC, WTs, All) | Not Started | 6 | 9d | 2024-11-13 | 2024-11-25 | 1272, 1275SS | 0% |  |  |  | 337 |  | 2024-11-13 | 2024-11-25 | 0
1284 | 1.2 | 1.2.8.6.4.13 | C | Complete Interconnects (DCC, PHS, MHPs, MECC, WTs, Gens, & PDMs) | Not Started | 6 | 5d | 2024-11-13 | 2024-11-19 | 1272 | 0% |  |  |  | 337 |  | 2024-11-13 | 2024-11-19 | 0
1285 | 1.2 | 1.2.8.6.4.14 | C | Furnace Checkout & Fire Up (All Modules) | Not Started | 6 | 3d | 2024-11-21 | 2024-11-25 | 1275SS +1d, 1278, 1284SS, 1283SS | 0% |  |  |  | 337 |  | 2024-11-21 | 2024-11-25 | 0
1286 | 1.2 | 1.2.8.6.4.15 | C | Perform Emergency Incident Drill & Safety Training | Not Started | 6 | 2d | 2024-11-26 | 2024-11-27 | 1283 | 0% |  |  |  | 388 |  | 2024-11-26 | 2024-11-27 | 0
1287 | 1.2 | 1.2.8.6.4.16 | C | Provide Fire Extinguishers (USAP) | Not Started | 6 | 0 | 2024-11-15 | 2024-11-15 | 1280SS | 0% |  | USAP Support |  | 389 |  | 2024-11-15 | 2024-11-15 | 0
1288 | 1.2 | 1.2.8.6.4.17 | C | Top-off TOS Fuel Day Tank & Position 3k or 5k Fuel Tanks (USAP) | Not Started | 6 | 3d | 2024-11-21 | 2024-11-25 | 1280FS +3d | 0% |  | USAP Support |  | 345 |  | 2024-11-21 | 2024-11-25 | 0
1289 | 1.2 | 1.2.8.6.4.19 | C | Fuel Tanks Connection Support (USAP) | Not Started | 6 | 9d | 2024-11-21 | 2024-12-04 | 1288SS | 0% |  | USAP Support |  | 384 |  | 2024-11-21 | 2024-12-04 | 0
1290 | 1.2 | 1.2.8.6.4.20 | C | SES Operational | Not Started | 6 | 0 | 2024-11-25 | 2024-11-25 | 1280, 1282, 1281, 1285, 1287, 1288SS | 0% |  | USAP Support |  | 389 |  | 2024-11-25 | 2024-11-25 | 0
1291 | 1.2 | 1.2.8.6.5 | P | Seasonal Equipment Site (SES) Maintenance & Support | Not Started | 5 | 62d | 2024-11-13 | 2025-02-11 |  | 0% |  |  |  | 337 |  | 2024-11-13 | 2025-02-11 | 0
1292 | 1.2 | 1.2.8.6.5.1 | C | SES Maintenance Activities - Season-long Driller Support | Not Started | 6 | 53d | 2024-11-26 | 2025-02-11 | 1285 | 0% |  |  |  | 337 |  | 2024-11-26 | 2025-02-11 | 0
1293 | 1.2 | 1.2.8.6.5.2 | C | Sustaining Fuel Deliveries - Day Tanks & 3k or 5k Fuel Tanks (USAP) | Not Started | 6 | 45d | 2024-11-26 | 2025-01-30 | 1288 | 0% |  | USAP Support |  | 345 |  | 2024-11-26 | 2025-01-30 | 0
1294 | 1.2 | 1.2.8.6.5.3 | C | General Equipment Support - Moves, Season Snow Removal, Road Maint. (USAP) | Not Started | 6 | 52d | 2024-11-13 | 2025-01-28 | 1272 | 0% |  | USAP Support |  | 347 |  | 2024-11-13 | 2025-01-28 | 0
1295 | 1.2 | 1.2.8.6.5.4 | C | Deliver 3000 gals Seed Water from Station (USAP) | Not Started | 6 | 2d | 2024-11-22 | 2024-11-25 | 1279FS +4d | 0% |  | USAP Support |  | 344 |  | 2024-11-22 | 2024-11-25 | 0
1296 | 1.2 | 1.2.8.6.5.5 | C | Create Storage Berms, End-of-the-World & SES (USAP) | Not Started | 6 | 6d | 2024-12-16 | 2024-12-23 | 1244FS +30d | 0% |  | USAP Support |  | 371 |  | 2024-12-16 | 2024-12-23 | 0
1297 | 1.2 | 1.2.8.6.5.6 | C | Build Firn Hole Covers (USAP) | Not Started | 6 | 5d | 2024-12-02 | 2024-12-06 | 1244FS +20d | 0% |  | USAP Support |  | 382 |  | 2024-12-02 | 2024-12-06 | 0
1298 | 1.2 | 1.2.8.6.5.7 | C | Deliver Compressor to SES (USAP) | Not Started | 6 | 1d | 2024-12-02 | 2024-12-02 | 1290FS +3d | 0% |  | USAP Support |  | 386 |  | 2024-12-02 | 2024-12-02 | 0
1299 | 1.2 | 1.2.8.6.5.8 | C | Deliver & Warm Up Glycol Tank (USAP) | Not Started | 6 | 1d | 2024-12-02 | 2024-12-02 | 1290FS +3d | 0% |  | USAP Support |  | 386 |  | 2024-12-02 | 2024-12-02 | 0
1300 | 1.2 | 1.2.8.6.5.9 | C | Create SES Snow Supply Stockpile (USAP) | Not Started | 6 | 1d | 2024-12-02 | 2024-12-02 | 1290FS +3d | 0% |  | USAP Support |  | 386 |  | 2024-12-02 | 2024-12-02 | 0
1301 | 1.2 | 1.2.8.6.6 | P | Generators & PDM | Not Started | 5 | 48d | 2024-11-13 | 2025-01-23 |  | 0% |  |  |  | 350 |  | 2024-11-13 | 2025-01-23 | 0
1302 | 1.2 | 1.2.8.6.6.1 | C | Deliver CRREL Gen for Early Season for SES Power (USAP) | Not Started | 6 | e1d | 2024-11-13 | 2024-11-14 | 1276 | 0% |  | USAP Support |  | 394 |  | 2024-11-13 | 2024-11-14 | 0
1303 | 1.2 | 1.2.8.6.6.2 | C | Supply Heat for CRREL Gen (USAP) | Not Started | 6 | e2d | 2024-11-14 | 2024-11-16 | 1302 | 0% |  | USAP Support |  | 394 |  | 2024-11-14 | 2024-11-16 | 0
1304 | 1.2 | 1.2.8.6.6.3 | C | Connect CRREL Gen to SES through Transformer Skid & Start (Driller & USAP) | Not Started | 6 | e2d | 2024-11-14 | 2024-11-16 | 1303FF | 0% |  | E_Engineer/USAP Electrician |  | 396 |  | 2024-11-14 | 2024-11-16 | 0
1305 | 1.2 | 1.2.8.6.6.4 | C | Temp SES Power Established | Not Started | 6 | 0 | 2024-11-22 | 2024-11-22 | 1288SS +1d, 1278 | 0% |  | E_Engineer/Generator_Contractor |  | 392 |  | 2024-11-22 | 2024-11-22 | 0
1306 | 1.2 | 1.2.8.6.6.5 | C | Connect Fuel Hoses & Prime Gens 1-3 (Driller & USAP) | Not Started | 6 | e2d | 2024-11-22 | 2024-11-24 | 1288SS +1d, 1278 | 0% |  | Driller/USAP Fuelie |  | 376 |  | 2024-11-22 | 2024-11-24 | 0
1307 | 1.2 | 1.2.8.6.6.6 | C | Generators & PDM - Pre-operational Checks | Not Started | 6 | e2d | 2024-11-22 | 2024-11-24 | 1306SS | 0% |  | E_Engineer/Generator_Contractor |  | 376 |  | 2024-11-22 | 2024-11-24 | 0
1308 | 1.2 | 1.2.8.6.6.7 | C | Contract Gen Tech Arrives | Not Started | 6 | 0 | 2024-11-19 | 2024-11-19 | 1244FS +12d | 0% |  | USAP Support |  | 393 |  | 2024-11-19 | 2024-11-19 | 0
1309 | 1.2 | 1.2.8.6.6.8 | C | Ready & Start-up Gen1, Gen 2, & Gen3 (Driller & USAP) | Not Started | 6 | e2d | 2024-11-24 | 2024-11-26 | 1306, 1307 | 0% |  | E_Engineer/USAP Electrician |  | 374 |  | 2024-11-24 | 2024-11-26 | 0
1310 | 1.2 | 1.2.8.6.6.9 | C | Parallel Gens through PDM Bays (Driller & Contract Gen Tech) | Not Started | 6 | e3d | 2024-11-26 | 2024-11-29 | 1308, 1309 | 0% |  | ME/Contract Gen Tech | Estimated 18 days of contractor cost @ $250 per hour 9 hour days plus travel & PQ allowance of $1200 for a total of $41,700 or $5957 for each of the 7 days of work at the Pole. | 388 |  | 2024-11-26 | 2024-11-29 | 0
1311 | 1.2 | 1.2.8.6.6.10 | C | Load Test using Resistance Heaters (Driller & Contract Gen Tech) | Not Started | 6 | e2d | 2024-11-29 | 2024-12-01 | 1309FS +2d | 0% |  |  | Estimated 18 days of contractor cost @ $250 per hour 9 hour days plus travel & PQ allowance of $1200 for a total of $41,700 or $5957 for each of the 7 days of work at the Pole. | 374 |  | 2024-11-29 | 2024-12-01 | 0
1312 | 1.2 | 1.2.8.6.6.11 | C | Test Safety Shut-downs (Driller & Contract Gen Tech) | Not Started | 6 | e2d | 2024-12-01 | 2024-12-03 | 1311 | 0% |  |  | Estimated 18 days of contractor cost @ $250 per hour 9 hour days plus travel & PQ allowance of $1200 for a total of $41,700 or $5957 for each of the 7 days of work at the Pole. | 374 |  | 2024-12-01 | 2024-12-03 | 0
1313 | 1.2 | 1.2.8.6.6.12 | C | SES Power Plant Online | Not Started | 6 | 0 | 2024-12-03 | 2024-12-03 | 1312 | 0% |  |  |  | 374 |  | 2024-12-03 | 2024-12-03 | 0
1314 | 1.2 | 1.2.8.6.6.13 | C | Integrate and test new generator and PDM controls/point I/O | Not Started | 6 | 4d | 2024-12-03 | 2024-12-06 | 1313 | 0% |  |  |  | 382 |  | 2024-12-03 | 2024-12-06 | 0
1315 | 1.2 | 1.2.8.6.6.14 | C | Scheduled Preventive Maintenance (Driller & USAP) | Not Started | 6 | e20d | 2024-12-12 | 2025-01-01 | 1313FS +7d | 0% |  | Driller/VMF Mechanic |  | 367 |  | 2024-12-12 | 2025-01-01 | 0
1316 | 1.2 | 1.2.8.6.6.15 | C | Winterize Gen Modules and PDM (Driller & USAP) | Not Started | 6 | e2d | 2025-01-21 | 2025-01-23 | 1438FF | 0% |  | Driller/VMF Mechanic |  | 350 |  | 2025-01-21 | 2025-01-23 | 0
1317 | 1.2 | 1.2.8.6.7 | P | EHWD: Final Upgrade & Replacement Work | Not Started | 5 | 46d | 2024-11-14 | 2025-01-21 |  | 0% |  |  |  | 352 |  | 2024-11-14 | 2025-01-21 | 0
1318 | 1.2 | 1.2.8.6.7.1 | P | Drill Control Center (DCC) & Global Control System | Not Started | 6 | 33d | 2024-11-14 | 2025-01-02 |  | 0% |  |  |  | 365 |  | 2024-11-14 | 2025-01-02 | 0
1319 | 1.2 | 1.2.8.6.7.1.1 | C | Relocate DCC to Cryo & Power-up (USAP) | Not Started | 7 | 1d | 2024-11-14 | 2024-11-14 | 1276 | 0% |  | USAP Support |  | 341 |  | 2024-11-14 | 2024-11-14 | 0
1320 | 1.2 | 1.2.8.6.7.1.2 | C | Electrical Closet Rework (USAP) | Not Started | 7 | 2d | 2024-11-15 | 2024-11-18 | 1319 | 0% |  | USAP Support |  | 341 |  | 2024-11-15 | 2024-11-18 | 0
1321 | 1.2 | 1.2.8.6.7.1.3 | C | Install New Fuel Day Tank System Controls | Not Started | 7 | 1d | 2024-11-19 | 2024-11-19 | 1320 | 0% |  |  |  | 341 |  | 2024-11-19 | 2024-11-19 | 0
1322 | 1.2 | 1.2.8.6.7.1.4 | C | Install and Wire 2x Motor Drives for WT1 VT Pumps | Not Started | 7 | 1d | 2024-11-20 | 2024-11-20 | 1321 | 0% |  |  |  | 343 |  | 2024-11-20 | 2024-11-20 | 0
1323 | 1.2 | 1.2.8.6.7.1.5 | C | Install New E-Stop Controller Equipment | Not Started | 7 | 2d | 2024-11-21 | 2024-11-22 | 1322 | 0% |  |  |  | 342 |  | 2024-11-21 | 2024-11-22 | 0
1324 | 1.2 | 1.2.8.6.7.1.6 | C | Install Racks & Computing Equipment | Not Started | 7 | 2d | 2024-11-25 | 2024-11-26 | 1323 | 0% |  |  |  | 344 |  | 2024-11-25 | 2024-11-26 | 0
1325 | 1.2 | 1.2.8.6.7.1.7 | C | Install Core PLC System in DCC | Not Started | 7 | 2d | 2024-11-27 | 2024-11-29 | 1324 | 0% |  |  |  | 344 |  | 2024-11-27 | 2024-11-29 | 0
1326 | 1.2 | 1.2.8.6.7.1.8 | C | Connect and Configure Hub and Spoke Elements, including Motor Drives | Not Started | 7 | 2d | 2024-12-02 | 2024-12-03 | 1325 | 0% |  |  |  | 344 |  | 2024-12-02 | 2024-12-03 | 0
1327 | 1.2 | 1.2.8.6.7.1.9 | C | Relocate DCC to SES & Position (USAP) | Not Started | 7 | 3d | 2024-12-04 | 2024-12-06 | 1326 | 0% |  | USAP Support |  | 382 |  | 2024-12-04 | 2024-12-06 | 0
1328 | 1.2 | 1.2.8.6.7.1.10 | C | Install and Commission Latest Software, SCADA, and Database | Not Started | 7 | 3d | 2024-12-04 | 2024-12-06 | 1326 | 0% |  |  |  | 344 |  | 2024-12-04 | 2024-12-06 | 0
1329 | 1.2 | 1.2.8.6.7.1.11 | C | QA on Controls By SES Subsystem - Wet System | Not Started | 7 | 10d | 2024-12-18 | 2025-01-02 | 1328, 1295, 1409 | 0% |  |  |  | 344 |  | 2024-12-18 | 2025-01-02 | 0
1330 | 1.2 | 1.2.8.6.7.1.12 | C | Global Control System Online | Not Started | 7 | 0 | 2025-01-02 | 2025-01-02 | 1329 | 0% |  |  |  | 365 |  | 2025-01-02 | 2025-01-02 | 0
1331 | 1.2 | 1.2.8.6.7.2 | P | Main Heating Plants | Not Started | 6 | 9d | 2024-11-20 | 2024-12-03 |  | 0% |  |  |  | 385 |  | 2024-11-20 | 2024-12-03 | 0
1332 | 1.2 | 1.2.8.6.7.2.1 | P | Mechanical Refit & Repairs (MHP) | Not Started | 7 | 9d | 2024-11-20 | 2024-12-03 |  | 0% |  |  |  | 385 |  | 2024-11-20 | 2024-12-03 | 0
1333 | 1.2 | 1.2.8.6.7.2.1.1 | C | Final Upgrade & Replacement Activities | Not Started | 8 | 5d | 2024-11-20 | 2024-11-26 | 1284 | 0% |  |  | Flush heaters w epump to clean out debris, pressure test heaters with proof pump. | 384 |  | 2024-11-20 | 2024-11-26 | 0
1334 | 1.2 | 1.2.8.6.7.2.1.2 | C | System Evaluation | Not Started | 8 | 5d | 2024-11-26 | 2024-12-03 | 1333FS -1d | 0% |  |  | Flush heaters w epump to clean out debris, pressure test heaters with proof pump. | 385 |  | 2024-11-26 | 2024-12-03 | 0
1335 | 1.2 | 1.2.8.6.7.2.2 | P | Electrical/Controls Refit & Repairs (MHP) | Not Started | 7 | 9d | 2024-11-20 | 2024-12-03 |  | 0% |  |  |  | 385 |  | 2024-11-20 | 2024-12-03 | 0
1336 | 1.2 | 1.2.8.6.7.2.2.1 | C | Final Upgrade & Replacement Activities | Not Started | 8 | 5d | 2024-11-20 | 2024-11-26 | 1284 | 0% |  |  |  | 384 |  | 2024-11-20 | 2024-11-26 | 0
1337 | 1.2 | 1.2.8.6.7.2.2.2 | C | System Evaluation and Final Testing | Not Started | 8 | 5d | 2024-11-26 | 2024-12-03 | 1336FS -1d | 0% |  |  |  | 385 |  | 2024-11-26 | 2024-12-03 | 0
1338 | 1.2 | 1.2.8.6.7.3 | P | Pre-Heat System | Not Started | 6 | 9d | 2024-11-20 | 2024-12-03 |  | 0% |  |  |  | 385 |  | 2024-11-20 | 2024-12-03 | 0
1339 | 1.2 | 1.2.8.6.7.3.1 | P | Mechanical Refit & Repairs (PHS) | Not Started | 7 | 9d | 2024-11-20 | 2024-12-03 |  | 0% |  |  |  | 385 |  | 2024-11-20 | 2024-12-03 | 0
1340 | 1.2 | 1.2.8.6.7.3.1.1 | C | Install Filters in H2O System | Not Started | 8 | 1d | 2024-11-20 | 2024-11-20 | 1341SS | 0% |  |  |  | 393 |  | 2024-11-20 | 2024-11-20 | 0
1341 | 1.2 | 1.2.8.6.7.3.1.2 | C | Final Upgrade & Replacement Activities | Not Started | 8 | 5d | 2024-11-20 | 2024-11-26 | 1284 | 0% |  |  | Flush heaters w epump to clean out debris, pressure test heaters with proof pump. | 384 |  | 2024-11-20 | 2024-11-26 | 0
1342 | 1.2 | 1.2.8.6.7.3.1.3 | C | System Evaluation | Not Started | 8 | 5d | 2024-11-26 | 2024-12-03 | 1341FS -1d | 0% |  |  | Flush heaters w epump to clean out debris, pressure test heaters with proof pump. | 385 |  | 2024-11-26 | 2024-12-03 | 0
1343 | 1.2 | 1.2.8.6.7.3.2 | P | Electrical/Controls Refit & Repairs (PHS) | Not Started | 7 | 9d | 2024-11-20 | 2024-12-03 |  | 0% |  |  |  | 385 |  | 2024-11-20 | 2024-12-03 | 0
1344 | 1.2 | 1.2.8.6.7.3.2.1 | C | Final Upgrade & Replacement Activities | Not Started | 8 | 5d | 2024-11-20 | 2024-11-26 | 1284 | 0% |  |  |  | 384 |  | 2024-11-20 | 2024-11-26 | 0
1345 | 1.2 | 1.2.8.6.7.3.2.2 | C | System Evaluation and Final Testing | Not Started | 8 | 5d | 2024-11-26 | 2024-12-03 | 1344FS -1d | 0% |  |  |  | 385 |  | 2024-11-26 | 2024-12-03 | 0
1346 | 1.2 | 1.2.8.6.7.4 | P | Water Tanks & Handling Systems (VT & Submersible) | Not Started | 6 | 9d | 2024-11-20 | 2024-12-03 |  | 0% |  |  |  | 385 |  | 2024-11-20 | 2024-12-03 | 0
1347 | 1.2 | 1.2.8.6.7.4.1 | C | Final Upgrade & Replacement Activities | Not Started | 7 | 5d | 2024-11-20 | 2024-11-26 | 1284 | 0% |  |  |  | 384 |  | 2024-11-20 | 2024-11-26 | 0
1348 | 1.2 | 1.2.8.6.7.4.2 | C | System Evaluation and Final Testing | Not Started | 7 | 5d | 2024-11-26 | 2024-12-03 | 1347FS -1d | 0% |  |  |  | 385 |  | 2024-11-26 | 2024-12-03 | 0
1349 | 1.2 | 1.2.8.6.7.5 | P | Water Tanks & Handling Systems (VT & Submersible) | Not Started | 6 | 9d | 2024-11-20 | 2024-12-03 |  | 0% |  |  |  | 385 |  | 2024-11-20 | 2024-12-03 | 0
1350 | 1.2 | 1.2.8.6.7.5.1 | P | Mechanical Refit & Repairs (HPP) | Not Started | 7 | 9d | 2024-11-20 | 2024-12-03 |  | 0% |  |  |  | 385 |  | 2024-11-20 | 2024-12-03 | 0
1351 | 1.2 | 1.2.8.6.7.5.1.1 | C | Final Upgrade & Replacement Activities | Not Started | 8 | 5d | 2024-11-20 | 2024-11-26 | 1284 | 0% |  |  | Flush heaters w epump to clean out debris, pressure test heaters with proof pump. | 384 |  | 2024-11-20 | 2024-11-26 | 0
1352 | 1.2 | 1.2.8.6.7.5.1.2 | C | Pump Testing & System Evaluation | Not Started | 8 | 5d | 2024-11-26 | 2024-12-03 | 1351FS -1d | 0% |  |  | Flush heaters w epump to clean out debris, pressure test heaters with proof pump. | 385 |  | 2024-11-26 | 2024-12-03 | 0
1353 | 1.2 | 1.2.8.6.7.5.2 | P | Electrical/Controls Refit & Repairs (HPP) | Not Started | 7 | 9d | 2024-11-20 | 2024-12-03 |  | 0% |  |  |  | 385 |  | 2024-11-20 | 2024-12-03 | 0
1354 | 1.2 | 1.2.8.6.7.5.2.1 | C | Final Upgrade & Replacement Activities | Not Started | 8 | 5d | 2024-11-20 | 2024-11-26 | 1284 | 0% |  |  |  | 389 |  | 2024-11-20 | 2024-11-26 | 0
1355 | 1.2 | 1.2.8.6.7.5.2.2 | C | System Evaluation and Final Testing | Not Started | 8 | 5d | 2024-11-26 | 2024-12-03 | 1351FS -1d | 0% |  |  |  | 385 |  | 2024-11-26 | 2024-12-03 | 0
1356 | 1.2 | 1.2.8.6.7.6 | P | HPU2 | Not Started | 6 | 14d | 2024-11-15 | 2024-12-05 |  | 0% |  |  |  | 383 |  | 2024-11-15 | 2024-12-05 | 0
1357 | 1.2 | 1.2.8.6.7.6.1 | C | Relocate HPU2 to SES, Position | Not Started | 7 | 1d | 2024-11-15 | 2024-11-15 | 1277 | 0% |  |  |  | 385 |  | 2024-11-15 | 2024-11-15 | 0
1358 | 1.2 | 1.2.8.6.7.6.2 | C | Supply Power to HPU2, Warm Up | Not Started | 7 | 1d | 2024-11-20 | 2024-11-20 | 1284, 1357 | 0% |  |  | Flush heaters w epump to clean out debris, pressure test heaters with proof pump. | 383 |  | 2024-11-20 | 2024-11-20 | 0
1359 | 1.2 | 1.2.8.6.7.6.3 | C | Initiate final Refit/Integration (HPU2) | Not Started | 7 | 10d | 2024-11-21 | 2024-12-05 | 1358 | 0% |  |  | Flush heaters w epump to clean out debris, pressure test heaters with proof pump. | 383 |  | 2024-11-21 | 2024-12-05 | 0
1360 | 1.2 | 1.2.8.6.7.7 | P | Fuel Tower | Not Started | 6 | 5d | 2024-11-27 | 2024-12-04 |  | 0% |  |  |  | 384 |  | 2024-11-27 | 2024-12-04 | 0
1361 | 1.2 | 1.2.8.6.7.7.1 | C | Install New Point I/O, connect to DCC, and configure/troubleshoot | Not Started | 7 | 1d | 2024-11-27 | 2024-11-27 | 1252FS +10d | 0% |  |  |  | 384 |  | 2024-11-27 | 2024-11-27 | 0
1362 | 1.2 | 1.2.8.6.7.7.2 | C | Fuel Tower: Commission - NPX | Not Started | 7 | 4d | 2024-11-29 | 2024-12-04 | 1361 | 0% |  |  |  | 384 |  | 2024-11-29 | 2024-12-04 | 0
1363 | 1.2 | 1.2.8.6.7.8 | P | Shops, MECC (SEW, TOW, OML) | Not Started | 6 | 6d | 2024-11-18 | 2024-11-25 |  | 0% |  |  |  | 390 |  | 2024-11-18 | 2024-11-25 | 0
1364 | 1.2 | 1.2.8.6.7.8.1 | C | Final Upgrade/Retrofit Shops, MECC | Not Started | 7 | 6d | 2024-11-18 | 2024-11-25 | 1280 | 0% |  |  |  | 390 |  | 2024-11-18 | 2024-11-25 | 0
1365 | 1.2 | 1.2.8.6.7.9 | P | Reels | Not Started | 6 | 31d | 2024-12-06 | 2025-01-21 |  | 0% |  |  |  | 352 |  | 2024-12-06 | 2025-01-21 | 0
1366 | 1.2 | 1.2.8.6.7.9.1 | P | Main Supply Hose Reel (MSHR) | Not Started | 7 | 31d | 2024-12-06 | 2025-01-21 |  | 0% |  |  |  | 352 |  | 2024-12-06 | 2025-01-21 | 0
1367 | 1.2 | 1.2.8.6.7.9.1.1 | C | Install Inner Insulation Layer & RTDs | Not Started | 8 | 2d | 2024-12-06 | 2024-12-09 | 1277FS +14d | 0% | 2 people x 2 days => ~36 hrs |  |  | 344 |  | 2024-12-06 | 2024-12-09 | 0
1368 | 1.2 | 1.2.8.6.7.9.1.2 | C | Install Drill Hose on Reel | Not Started | 8 | 5d | 2024-12-10 | 2024-12-16 | 1367, 1258 | 0% | 4 people x 5 days => ~180 hrs |  |  | 344 |  | 2024-12-10 | 2024-12-16 | 0
1369 | 1.2 | 1.2.8.6.7.9.1.3 | C | Final Upgrades & Testing (MSHR) | Not Started | 8 | 2d | 2024-12-17 | 2024-12-18 | 1368 | 0% |  |  |  | 374 |  | 2024-12-17 | 2024-12-18 | 0
1370 | 1.2 | 1.2.8.6.7.9.1.4 | C | Install Hose Heating Blankets & RTDs & Install Outer Cover | Not Started | 8 | 2d | 2025-01-16 | 2025-01-17 | 1428SS +2d | 0% | 2 people x 3 days => ~54 hrs |  |  | 352 |  | 2025-01-16 | 2025-01-17 | 0
1371 | 1.2 | 1.2.8.6.7.9.1.5 | C | Install Hose Heating Controller, Connect to Power, & Test | Not Started | 8 | 2d | 2025-01-20 | 2025-01-21 | 1429, 1370 | 0% | 4 people x 5 days => ~180 hrs |  |  | 352 |  | 2025-01-20 | 2025-01-21 | 0
1372 | 1.2 | 1.2.8.6.7.9.2 | P | Return Water Hose Reel (RWHR) | Not Started | 7 | 10d | 2024-12-09 | 2024-12-20 |  | 0% |  |  |  | 372 |  | 2024-12-09 | 2024-12-20 | 0
1373 | 1.2 | 1.2.8.6.7.9.2.1 | C | Install Return Hose on Reel | Not Started | 8 | 5d | 2024-12-09 | 2024-12-13 | 1368SS -1d | 0% | 4 people x 5 days => ~180 hrs |  |  | 360 |  | 2024-12-09 | 2024-12-13 | 0
1374 | 1.2 | 1.2.8.6.7.9.2.2 | C | Final Upgrades & Testing | Not Started | 8 | 5d | 2024-12-16 | 2024-12-20 | 1373 | 0% |  |  |  | 372 |  | 2024-12-16 | 2024-12-20 | 0
1375 | 1.2 | 1.2.8.6.7.9.3 | P | Return Water Cable Reel (RWCR) | Not Started | 7 | 5d | 2024-12-09 | 2024-12-13 |  | 0% |  |  |  | 377 |  | 2024-12-09 | 2024-12-13 | 0
1376 | 1.2 | 1.2.8.6.7.9.3.1 | C | Final Upgrades & Testing | Not Started | 8 | 5d | 2024-12-09 | 2024-12-13 | 1373SS | 0% |  |  |  | 377 |  | 2024-12-09 | 2024-12-13 | 0
1377 | 1.2 | 1.2.8.6.7.9.4 | P | Main Cable Reel (MCR) | Not Started | 7 | 5d | 2024-12-09 | 2024-12-13 |  | 0% |  |  |  | 377 |  | 2024-12-09 | 2024-12-13 | 0
1378 | 1.2 | 1.2.8.6.7.9.4.1 | C | Final Upgrades & Testing | Not Started | 8 | 5d | 2024-12-09 | 2024-12-13 | 1373SS | 0% |  |  |  | 365 |  | 2024-12-09 | 2024-12-13 | 0
1379 | 1.2 | 1.2.8.6.7.10 | P | Winches | Not Started | 6 | 12d | 2024-12-13 | 2024-12-31 |  | 0% |  |  |  | 366 |  | 2024-12-13 | 2024-12-31 | 0
1380 | 1.2 | 1.2.8.6.7.10.1 | C | Winches Final Integration & Testing (TU-20, TU-15) | Not Started | 7 | 12d | 2024-12-13 | 2024-12-31 | 1378FS -1d | 0% |  |  |  | 366 |  | 2024-12-13 | 2024-12-31 | 0
1381 | 1.2 | 1.2.8.6.7.11 | P | TOS/Tower | Not Started | 6 | 22d | 2024-11-18 | 2024-12-18 |  | 0% |  |  |  | 374 |  | 2024-11-18 | 2024-12-18 | 0
1382 | 1.2 | 1.2.8.6.7.11.1 | P | TOS1 - Core Controls Install, Commissioning & Check Out | Not Started | 7 | 11d | 2024-11-18 | 2024-12-03 |  | 0% |  |  |  | 385 |  | 2024-11-18 | 2024-12-03 | 0
1383 | 1.2 | 1.2.8.6.7.11.1.1 | C | TOS1 - Install Racks & Computing Equipment | Not Started | 8 | 2d | 2024-11-18 | 2024-11-19 | 1277FS +1d, 1252 | 0% |  |  |  | 342 |  | 2024-11-18 | 2024-11-19 | 0
1384 | 1.2 | 1.2.8.6.7.11.1.2 | C | TOS1 - Install Core PLC System | Not Started | 8 | 1d | 2024-11-20 | 2024-11-20 | 1383 | 0% |  |  | Flush heaters w epump to clean out debris, pressure test heaters with proof pump. | 342 |  | 2024-11-20 | 2024-11-20 | 0
1385 | 1.2 | 1.2.8.6.7.11.1.3 | C | TOS1 - Connect & Configure I/O & Motor Drives | Not Started | 8 | 2d | 2024-11-21 | 2024-11-22 | 1384 | 0% |  |  | Flush heaters w epump to clean out debris, pressure test heaters with proof pump. | 342 |  | 2024-11-21 | 2024-11-22 | 0
1386 | 1.2 | 1.2.8.6.7.11.1.4 | C | TOS1 - Install & Commission Latest Software, SCADA | Not Started | 8 | 2d | 2024-11-25 | 2024-11-26 | 1385 | 0% |  |  |  | 342 |  | 2024-11-25 | 2024-11-26 | 0
1387 | 1.2 | 1.2.8.6.7.11.1.5 | C | TOS1 - Connect Reels & Perform QA on Controls | Not Started | 8 | 2d | 2024-11-27 | 2024-11-29 | 1386 | 0% |  |  |  | 342 |  | 2024-11-27 | 2024-11-29 | 0
1388 | 1.2 | 1.2.8.6.7.11.1.6 | C | TOS1 - Install Drill Head Power Supply | Not Started | 8 | 1d | 2024-12-02 | 2024-12-02 | 1387 | 0% |  |  | Flush heaters w epump to clean out debris, pressure test heaters with proof pump. | 342 |  | 2024-12-02 | 2024-12-02 | 0
1389 | 1.2 | 1.2.8.6.7.11.1.7 | C | TOS1 - Test Drill Head Data Chain With Actual Drill Head | Not Started | 8 | 1d | 2024-12-03 | 2024-12-03 | 1388 | 0% |  |  | Flush heaters w epump to clean out debris, pressure test heaters with proof pump. | 342 |  | 2024-12-03 | 2024-12-03 | 0
1390 | 1.2 | 1.2.8.6.7.11.1.8 | C | TOS1 - TOS Control System Online | Not Started | 8 | 0 | 2024-12-03 | 2024-12-03 | 1389 | 0% |  |  | Flush heaters w epump to clean out debris, pressure test heaters with proof pump. | 342 |  | 2024-12-03 | 2024-12-03 | 0
1391 | 1.2 | 1.2.8.6.7.11.2 | P | TOS2 - Core Controls Install, Commissioning & Check Out | Not Started | 7 | 11d | 2024-12-04 | 2024-12-18 |  | 0% |  |  |  | 374 |  | 2024-12-04 | 2024-12-18 | 0
1392 | 1.2 | 1.2.8.6.7.11.2.1 | C | TOS2 - Install Racks & Computing Equipment | Not Started | 8 | 2d | 2024-12-04 | 2024-12-05 | 1277FS +1d, 1390, 1252 | 0% |  |  |  | 342 |  | 2024-12-04 | 2024-12-05 | 0
1393 | 1.2 | 1.2.8.6.7.11.2.2 | C | TOS2 - Install Core PLC System | Not Started | 8 | 1d | 2024-12-06 | 2024-12-06 | 1392 | 0% |  |  | Flush heaters w epump to clean out debris, pressure test heaters with proof pump. | 341 |  | 2024-12-06 | 2024-12-06 | 0
1394 | 1.2 | 1.2.8.6.7.11.2.3 | C | TOS2 - Connect & Configure I/O & Motor Drives | Not Started | 8 | 2d | 2024-12-09 | 2024-12-10 | 1393 | 0% |  |  | Flush heaters w epump to clean out debris, pressure test heaters with proof pump. | 341 |  | 2024-12-09 | 2024-12-10 | 0
1395 | 1.2 | 1.2.8.6.7.11.2.4 | C | TOS2 - Install & Commission Latest Software, SCADA | Not Started | 8 | 2d | 2024-12-11 | 2024-12-12 | 1394 | 0% |  |  |  | 343 |  | 2024-12-11 | 2024-12-12 | 0
1396 | 1.2 | 1.2.8.6.7.11.2.5 | C | TOS2 - Connect Reels & Perform QA on Controls | Not Started | 8 | 2d | 2024-12-13 | 2024-12-16 | 1395 | 0% |  |  |  | 342 |  | 2024-12-13 | 2024-12-16 | 0
1397 | 1.2 | 1.2.8.6.7.11.2.6 | C | TOS2 - Install Drill Head Power Supply | Not Started | 8 | 1d | 2024-12-17 | 2024-12-17 | 1396 | 0% |  |  | Flush heaters w epump to clean out debris, pressure test heaters with proof pump. | 344 |  | 2024-12-17 | 2024-12-17 | 0
1398 | 1.2 | 1.2.8.6.7.11.2.7 | C | TOS2 - Test Drill Head Data Chain With Actual Drill Head | Not Started | 8 | 1d | 2024-12-18 | 2024-12-18 | 1397 | 0% |  |  | Flush heaters w epump to clean out debris, pressure test heaters with proof pump. | 344 |  | 2024-12-18 | 2024-12-18 | 0
1399 | 1.2 | 1.2.8.6.7.11.2.8 | C | TOS2 - TOS Control System Online | Not Started | 8 | 0 | 2024-12-18 | 2024-12-18 | 1398 | 0% |  |  | Flush heaters w epump to clean out debris, pressure test heaters with proof pump. | 344 |  | 2024-12-18 | 2024-12-18 | 0
1400 | 1.2 | 1.2.8.6.7.12 | P | Rodwell System (ARA) | Not Started | 6 | 39d | 2024-11-21 | 2025-01-17 |  | 0% |  |  |  | 354 |  | 2024-11-21 | 2025-01-17 | 0
1401 | 1.2 | 1.2.8.6.7.12.1 | C | Commission Sled 1 - Generator Sled | Not Started | 7 | 4d | 2024-11-21 | 2024-11-26 | 1276FS +5d | 0% |  |  |  | 341 |  | 2024-11-21 | 2024-11-26 | 0
1402 | 1.2 | 1.2.8.6.7.12.2 | C | Commission Sled 2 - Water Tank Sled | Not Started | 7 | 4d | 2024-11-27 | 2024-12-03 | 1401 | 0% |  |  |  | 341 |  | 2024-11-27 | 2024-12-03 | 0
1403 | 1.2 | 1.2.8.6.7.12.3 | C | Commission Sled 3 - Heater/reel Sled | Not Started | 7 | 4d | 2024-12-04 | 2024-12-09 | 1402 | 0% |  |  |  | 341 |  | 2024-12-04 | 2024-12-09 | 0
1404 | 1.2 | 1.2.8.6.7.12.4 | C | System Commissioning and Checkout | Not Started | 7 | 3d | 2024-12-10 | 2024-12-12 | 1401, 1402, 1403 | 0% |  |  |  | 343 |  | 2024-12-10 | 2024-12-12 | 0
1405 | 1.2 | 1.2.8.6.7.12.5 | C | Fill System with Seed Water | Not Started | 7 | 1d | 2024-12-10 | 2024-12-10 | 1404SS | 0% |  |  |  | 380 |  | 2024-12-10 | 2024-12-10 | 0
1406 | 1.2 | 1.2.8.6.7.12.6 | C | Decommission & Store ARA | Not Started | 7 | 3d | 2025-01-15 | 2025-01-17 | 1428SS +1d | 0% |  |  |  | 354 |  | 2025-01-15 | 2025-01-17 | 0
1407 | 1.2 | 1.2.8.6.8 | P | Rodwell System (ARA) Ops - Condensate Bulbs | Not Started | 5 | 20d | 2024-12-13 | 2025-01-13 |  | 0% |  |  | Condensate will not be used for drilling operations. Filtered water will be delivered to bulb. | 358 |  | 2024-12-13 | 2025-01-13 | 0
1408 | 1.2 | 1.2.8.6.8.1 | C | Setup ARA System over mini FS2 Condensate Bulb Firn Hole Location | Not Started | 6 | 1d | 2024-12-13 | 2024-12-13 | 1404 | 0% |  |  |  | 342 |  | 2024-12-13 | 2024-12-13 | 0
1409 | 1.2 | 1.2.8.6.8.2 | C | Drill Dry Pilot Hole, Develop, Pump Out (mini cond) | Not Started | 6 | 2d | 2024-12-16 | 2024-12-17 | 1408 | 0% |  |  |  | 341 |  | 2024-12-16 | 2024-12-17 | 0
1410 | 1.2 | 1.2.8.6.8.3 | C | Setup ARA System over main FS3 Condensate Bulb Hole Location | Not Started | 6 | 1d | 2024-12-19 | 2024-12-19 | 1409FS +1d | 0% |  |  |  | 344 |  | 2024-12-19 | 2024-12-19 | 0
1411 | 1.2 | 1.2.8.6.8.4 | C | Drill Dry Pilot Hole (main cond) | Not Started | 6 | 1d | 2024-12-20 | 2024-12-20 | 1410 | 0% |  |  |  | 344 |  | 2024-12-20 | 2024-12-20 | 0
1412 | 1.2 | 1.2.8.6.8.5 | C | Develop Bulb (main cond) | Not Started | 6 | 4d | 2024-12-23 | 2024-12-27 | 1411 | 0% |  |  |  | 344 |  | 2024-12-23 | 2024-12-27 | 0
1413 | 1.2 | 1.2.8.6.8.6 | C | Maintain Bulb for Test, then Pump out Water (main cond) | Not Started | 6 | 10d | 2024-12-30 | 2025-01-13 | 1412 | 0% |  |  |  | 344 |  | 2024-12-30 | 2025-01-13 | 0
1414 | 1.2 | 1.2.8.6.9 | P | Firn Drilling - Independent Firn Drill (IFD) | Not Started | 5 | 40d | 2024-11-14 | 2025-01-13 |  | 0% |  |  |  | 358 |  | 2024-11-14 | 2025-01-13 | 0
1415 | 1.2 | 1.2.8.6.9.1 | C | Deliver CRREL Gen and Firn Drill (USAP) | Not Started | 6 | 1d | 2024-11-14 | 2024-11-14 | 1276 | 0% |  | USAP Support |  | 332 |  | 2024-11-14 | 2024-11-14 | 0
1416 | 1.2 | 1.2.8.6.9.2 | C | Drill and CRREL Integration and Commissioning | Not Started | 6 | 6d | 2024-11-15 | 2024-11-22 | 1415 | 0% |  |  |  | 334 |  | 2024-11-15 | 2024-11-22 | 0
1417 | 1.2 | 1.2.8.6.9.3 | C | Excavation of 7 x Firn Hole Pits 4' x 4' x 2' (Set String Anchor in Each Hole) | Not Started | 6 | 2d | 2024-11-15 | 2024-11-18 | 1416SS | 0% |  |  |  | 393 |  | 2024-11-15 | 2024-11-18 | 0
1418 | 1.2 | 1.2.8.6.9.4 | C | Trenching for Setting the String Anchors for all the 7 x Firn Hole (USAP) | Not Started | 6 | 2d | 2024-11-15 | 2024-11-18 | 1417SS | 0% |  | USAP Support |  | 395 |  | 2024-11-15 | 2024-11-18 | 0
1419 | 1.2 | 1.2.8.6.9.5 | C | Drill 9 Firn Holes w/ Independent Firn Drill (IFD) | Not Started | 6 | 25d | 2024-11-27 | 2025-01-03 | 1416FS +2d | 0% |  |  |  | 332 |  | 2024-11-27 | 2025-01-03 | 0
1420 | 1.2 | 1.2.8.6.9.6 | C | Refueling Support - Firn Drilling (USAP) | Not Started | 6 | 25d | 2024-11-27 | 2025-01-03 | 1419SS, 896 | 0% |  | USAP Support |  | 364 |  | 2024-11-27 | 2025-01-03 | 0
1421 | 1.2 | 1.2.8.6.9.7 | C | 9 Holes Drilled, Covered and Flagged | Not Started | 6 | 0 | 2025-01-03 | 2025-01-03 | 1419 | 0% |  | USAP Support |  | 364 |  | 2025-01-03 | 2025-01-03 | 0
1422 | 1.2 | 1.2.8.6.9.8 | C | Winterize & Store IFD | Not Started | 6 | 6d | 2025-01-06 | 2025-01-13 | 1419 | 0% |  |  |  | 358 |  | 2025-01-06 | 2025-01-13 | 0
1423 | 1.2 | 1.2.8.6.10 | P | EHWD: Full Systems Wet-Test | Not Started | 5 | 30d | 2024-12-05 | 2025-01-17 |  | 0% |  |  |  | 354 |  | 2024-12-05 | 2025-01-17 | 0
1424 | 1.2 | 1.2.8.6.10.1 | C | Setup TOS, Tower, Reels over Rodwell Hole Location | Not Started | 6 | 3d | 2024-12-05 | 2024-12-09 | 1419SS +5d | 0% |  |  |  | 344 |  | 2024-12-05 | 2024-12-09 | 0
1425 | 1.2 | 1.2.8.6.10.2 | C | Phase 1: TOS Motion control testing and Tuning | Not Started | 6 | 7d | 2024-12-19 | 2024-12-30 | 1424FS +3d, 1368, 1399 | 0% |  |  |  | 344 |  | 2024-12-19 | 2024-12-30 | 0
1426 | 1.2 | 1.2.8.6.10.3 | C | Readiness Review, Safety Refresher, Emergency & Safety Systems Tested | Not Started | 6 | 1d | 2024-12-31 | 2024-12-31 | 1425 | 0% |  |  |  | 344 |  | 2024-12-31 | 2024-12-31 | 0
1427 | 1.2 | 1.2.8.6.10.4 | C | Phase 2: Full System Wet-Test | Not Started | 6 | 7d | 2025-01-03 | 2025-01-13 | 1426, 1329, 1413SS | 0% |  |  |  | 344 |  | 2025-01-03 | 2025-01-13 | 0
1428 | 1.2 | 1.2.8.6.10.5 | C | Blow Out Systems | Not Started | 6 | 4d | 2025-01-14 | 2025-01-17 | 1427 | 0% |  |  |  | 343 |  | 2025-01-14 | 2025-01-17 | 0
1429 | 1.2 | 1.2.8.6.10.6 | C | Wet-Test Operations Complete | Not Started | 6 | 0 | 2025-01-17 | 2025-01-17 | 1428 | 0% |  |  |  | 340 |  | 2025-01-17 | 2025-01-17 | 0
1430 | 1.2 | 1.2.8.6.11 | P | Installation Support Activities | Not Started | 5 | 9d | 2024-12-04 | 2024-12-16 |  | 0% |  |  |  | 376 |  | 2024-12-04 | 2024-12-16 | 0
1431 | 1.2 | 1.2.8.6.11.1 | C | Sensor Handling Facility Construction Oversight | Not Started | 6 | 9d | 2024-12-04 | 2024-12-16 | 1812SS | 0% |  |  |  | 376 |  | 2024-12-04 | 2024-12-16 | 0
1432 | 1.2 | 1.2.8.6.12 | P | Season Close-Out Work | Not Started | 5 | 26d | 2024-12-24 | 2025-01-30 |  | 0% |  |  |  | 345 |  | 2024-12-24 | 2025-01-30 | 0
1433 | 1.2 | 1.2.8.6.12.1 | C | Document, Photograph Equip & Upgrade Work, Further Req's | Not Started | 6 | 2d | 2024-12-24 | 2024-12-26 | 1206SS, | 0% |  |  |  | 369 |  | 2024-12-24 | 2024-12-26 | 0
1434 | 1.2 | 1.2.8.6.12.2 | C | Collect Video Record of Condensate Bulb and Rodwell | Not Started | 6 | 2d | 2025-01-20 | 2025-01-21 | 1429 | 0% |  |  |  | 352 |  | 2025-01-20 | 2025-01-21 | 0
1435 | 1.2 | 1.2.8.6.12.3 | C | Prepare Retrograde for Shipment | Not Started | 6 | 7d | 2025-01-20 | 2025-01-28 | 1429 | 0% |  |  |  | 346 |  | 2025-01-20 | 2025-01-28 | 0
1436 | 1.2 | 1.2.8.6.12.4 | C | Demo Snow Ramp (USAP) | Not Started | 6 | 1d | 2025-01-20 | 2025-01-20 | 1429 | 0% |  | USAP Support |  | 353 |  | 2025-01-20 | 2025-01-20 | 0
1437 | 1.2 | 1.2.8.6.12.5 | P | Winterize EHWD | Not Started | 6 | 10d | 2025-01-17 | 2025-01-30 |  | 0% |  |  |  | 345 |  | 2025-01-17 | 2025-01-30 | 0
1438 | 1.2 | 1.2.8.6.12.5.1 | C | Remove DNF, Computer Equip, Drives, Capacitors, Etc | Not Started | 7 | 4d | 2025-01-20 | 2025-01-23 | 1429 | 0% |  |  |  | 344 |  | 2025-01-20 | 2025-01-23 | 0
1439 | 1.2 | 1.2.8.6.12.5.2 | C | Winterize SES & TOS, Disconnect All Cables Hoses, Connections | Not Started | 7 | 6d | 2025-01-17 | 2025-01-24 | 1438FS -5d | 0% |  |  |  | 345 |  | 2025-01-17 | 2025-01-24 | 0
1440 | 1.2 | 1.2.8.6.12.5.3 | C | Winter Storage Support: Drill Hose Reel, TOS 1 & 2 (USAP) | Not Started | 7 | 3d | 2025-01-27 | 2025-01-29 | 1439 | 0% |  | USAP Support |  | 345 |  | 2025-01-27 | 2025-01-29 | 0
1441 | 1.2 | 1.2.8.6.12.5.4 | C | All EHWD Equipment Winterized | Not Started | 7 | 1d | 2025-01-30 | 2025-01-30 | 1438, 1439, 1440 | 0% |  |  |  | 345 |  | 2025-01-30 | 2025-01-30 | 0
1442 | 1.2 | 1.2.8.6.13 | C | Other Field Activities (FS2) | Not Started | 5 | 77d | 2025-10-15 | 2026-02-03 |  | 0% |  |  |  | 85 |  | 2025-10-15 | 2026-02-03 | 0
1443 | 1.2 | 1.2.8.6.14 | C | ICU Field Team Redeployed | Not Started | 5 | 1d | 2025-01-31 | 2025-01-31 | 1438, 1439, 1435FS +2d | 0% |  |  |  | 344 |  | 2025-01-31 | 2025-01-31 | 0
1444 | 1.2 | 1.2.8.6.15 | C | On-ice Labor FS2 | Not Started | 5 | 60d | 2024-11-08 | 2025-02-04 |  | 0% |  |  | EE/ME Engineer Labor Totals from Population file. Assumes 2 days in McMurdo southbound and 1 day northbound. Technician Labor Totals from Population file. Assumes 2 days in McMurdo southbound and 1 day northbound. Safety Engineer Labor Totals from Population file. Assumes 2 days in McMurdo southbound and 1 day northbound. | 342 |  | 2024-11-08 | 2025-02-04 | 0
1445 | 1.2 | 1.2.8.6.16 | C | END ICU NPX FS2 Season | Not Started | 5 | 0 | 2025-01-31 | 2025-01-31 | 1441, 1443 | 0% |  |  |  | 344 |  | 2025-01-31 | 2025-01-31 | 0
1446 | 1.2 | 1.2.8.7 | P | USAP Field Season 3 (FY26) | Not Started | 4 | 201d | 2025-06-01 | 2026-03-11 |  | 0% |  |  |  | 59 |  | 2025-06-01 | 2026-03-11 | 0
1447 | 1.2 | 1.2.8.7.1 | P | FS3 Milestones | Not Started | 5 | 104d | 2025-10-01 | 2026-02-27 |  | 0% |  |  |  | 68 |  | 2025-10-01 | 2026-02-27 | 0
1448 | 1.2 | 1.2.8.7.1.1 | C | McM Mainbody Season Begins (USAP) | Not Started | 6 | 0 | 2025-10-01 | 2025-10-01 |  | 0% |  | USAP Support |  | -2841 |  | 2025-10-01 | 2025-10-01 | 0
1449 | 1.2 | 1.2.8.7.1.2 | C | South Pole Season Begins (USAP) | Not Started | 6 | 0 | 2025-11-12 | 2025-11-12 | 1448FS +30d | 0% |  | USAP Support |  | -2841 |  | 2025-11-12 | 2025-11-12 | 0
1450 | 1.2 | 1.2.8.7.1.3 | P | ICU Team Arrivals [Headcount 29] | Not Started | 6 | 10d | 2025-11-11 | 2025-11-25 |  | 0% |  |  |  | 133 |  | 2025-11-11 | 2025-11-25 | 0
1451 | 1.2 | 1.2.8.7.1.3.1 | C | ICU Team Arrives - Wave I | Not Started | 7 | 0 | 2025-11-11 | 2025-11-11 |  | 0% |  |  |  | 0 | TRUE | 2025-11-11 | 2025-11-11 | 0
1452 | 1.2 | 1.2.8.7.1.3.2 | C | ICU Team Arrives - Wave II | Not Started | 7 | 0 | 2025-11-18 | 2025-11-18 |  | 0% |  |  |  | 138 |  | 2025-11-18 | 2025-11-18 | 0
1453 | 1.2 | 1.2.8.7.1.3.3 | C | ICU Team Arrives - Wave III | Not Started | 7 | 0 | 2025-11-25 | 2025-11-25 |  | 0% |  |  |  | 128 |  | 2025-11-25 | 2025-11-25 | 0
1454 | 1.2 | 1.2.8.7.1.4 | C | Pole Season Ends (USAP) | Not Started | 6 | 0 | 2026-02-16 | 2026-02-16 | 1449FS +65d | 0% |  | USAP Support |  | 37 |  | 2026-02-16 | 2026-02-16 | 0
1455 | 1.2 | 1.2.8.7.1.5 | C | MCM Season Ends (USAP) | Not Started | 6 | 0 | 2026-02-27 | 2026-02-27 | 1448FS +104d | 0% |  | USAP Support |  | 68 |  | 2026-02-27 | 2026-02-27 | 0
1456 | 1.2 | 1.2.8.7.2 | C | PQ, ECW & Deployment Travel Costs (FS3) | Not Started | 5 | 195d | 2025-06-01 | 2026-03-03 |  | 0% |  |  | 1 (Drill Manager), 5 days deployment travel 3 days redeployment 1 (Safety Engineer), 5 days deployment travel 3 days redeployment 20 (PSL Direct Hire), 5 days deployment travel 3 days redeployment 8 (PSL Engineers), 5 days deployment travel 3 days redeployment 33 - PQ's @ $950/each (anticipated cost) 28 Drillers, Safety Engineer & 4 Alternates 29 - Deploy travel costs 29 (28 Drillers & 1 Safety Engineer) @ $1800 each | 65 |  | 2025-06-01 | 2026-03-03 | 0
1457 | 1.2 | 1.2.8.7.3 | P | USAP Cargo Movements (FY26) | Not Started | 5 | 66d | 2025-10-31 | 2026-02-05 |  | 0% |  |  |  | 84 |  | 2025-10-31 | 2026-02-05 | 0
1458 | 1.2 | 1.2.8.7.3.1 | P | Pole (USAP) | Not Started | 6 | 44d | 2025-11-26 | 2026-01-30 |  | 0% |  |  |  | 88 |  | 2025-11-26 | 2026-01-30 | 0
1459 | 1.2 | 1.2.8.7.3.1.1 | P | LC130 - Pole (USAP) | Not Started | 7 | 0 | 2025-11-26 | 2025-11-26 |  | 0% |  |  |  | 132 |  | 2025-11-26 | 2025-11-26 | 0
1460 | 1.2 | 1.2.8.7.3.1.1.1 | C | Fuel 1,152 Gallons (USAP) | Not Started | 8 | 0 | 2025-11-26 | 2025-11-26 | 1448, 1449FS +10d | 0% |  | USAP Support |  | 132 |  | 2025-11-26 | 2025-11-26 | 0
1461 | 1.2 | 1.2.8.7.3.1.2 | P | SPOT1 - Pole (USAP) | Not Started | 7 | 0 | 2025-12-01 | 2025-12-01 |  | 0% |  | USAP Support |  | 130 |  | 2025-12-01 | 2025-12-01 | 0
1462 | 1.2 | 1.2.8.6.3.1.2.1 | C | Fuel - 6604 gallons (1 ISO 25k liter tank containers) | Not Started | 8 | 0 | 2025-12-01 | 2025-12-01 | 1448, 1449FS +12d | 0% |  | USAP Support |  | -2841 |  | 2025-12-01 | 2025-12-01 | 0
1463 | 1.2 | 1.2.8.7.3.1.3 | P | SPOT2 - Pole (USAP) | Not Started | 7 | 0 | 2025-12-31 | 2025-12-31 |  | 0% |  | USAP Support |  | 109 |  | 2025-12-31 | 2025-12-31 | 0
1464 | 1.2 | 1.2.8.7.3.1.3.1 | C | Fuel - 19,812 gallons (3 ISO 25k liter tank containers) | Not Started | 8 | 0 | 2025-12-31 | 2025-12-31 | 1448, 1449FS +33d | 0% |  | USAP Support |  | 109 |  | 2025-12-31 | 2025-12-31 | 0
1465 | 1.2 | 1.2.8.7.3.1.4 | P | SPOT3 - Pole (USAP) | Not Started | 7 | 0 | 2026-01-30 | 2026-01-30 |  | 0% |  | USAP Support |  | 88 |  | 2026-01-30 | 2026-01-30 | 0
1466 | 1.2 | 1.2.8.7.3.1.4.1 | C | TBD | Not Started | 8 | 0 | 2026-01-30 | 2026-01-30 | 1448, 1449FS +54d | 0% |  | USAP Support |  | 88 |  | 2026-01-30 | 2026-01-30 | 0
1467 | 1.2 | 1.2.8.7.3.1.5 | P | SPOT3 - North (USAP) | Not Started | 7 | 0 | 2026-01-26 | 2026-01-26 |  | 0% |  | USAP Support |  | 91 |  | 2026-01-26 | 2026-01-26 | 0
1468 | 1.2 | 1.2.8.7.3.1.5.1 | C | Drill Hose - 13 hose spools | Not Started | 8 | 0 | 2026-01-26 | 2026-01-26 | 1448, 1449FS +10d, 1646 | 0% |  | USAP Support |  | 91 |  | 2026-01-26 | 2026-01-26 | 0
1469 | 1.2 | 1.2.8.7.3.2 | P | MCM (USAP) | Not Started | 6 | 66d | 2025-10-31 | 2026-02-05 |  | 0% |  |  |  | 84 |  | 2025-10-31 | 2026-02-05 | 0
1470 | 1.2 | 1.2.8.7.3.2.1 | P | SAAM - ComSur (USAP) | Not Started | 7 | 0 | 2025-10-31 | 2025-10-31 |  | 0% |  |  |  | 150 |  | 2025-10-31 | 2025-10-31 | 0
1471 | 1.2 | 1.2.8.6.3.2.1.1 | C | Driller Resupply/Refit Container (8' ISO) (USAP) | Not Started | 8 | 0 | 2025-10-31 | 2025-10-31 | 1448FS +22d, 156 | 0% |  | USAP Support |  | 150 |  | 2025-10-31 | 2025-10-31 | 0
1472 | 1.2 | 1.2.8.6.3.2.1.2 | C | Drill Refit Components Crate - DNF (USAP) | Not Started | 8 | 0 | 2025-10-31 | 2025-10-31 | 1448FS +22d, 157 | 0% |  | USAP Support |  | 150 |  | 2025-10-31 | 2025-10-31 | 0
1473 | 1.2 | 1.2.8.7.3.2.2 | P | Vessel (USAP) | Not Started | 7 | 0 | 2026-02-05 | 2026-02-05 |  | 0% |  |  |  | 84 |  | 2026-02-05 | 2026-02-05 | 0
1474 | 1.2 | 1.2.8.7.3.2.2.1 | C | Placeholder | Not Started | 8 | 0 | 2026-02-05 | 2026-02-05 |  | 0% |  |  |  | 84 |  | 2026-02-05 | 2026-02-05 | 0
1475 | 1.2 | 1.2.8.7.3.3 | P | Retrograde (USAP) | Not Started | 6 | 2d | 2026-02-03 | 2026-02-04 |  | 0% |  |  |  | 84 |  | 2026-02-03 | 2026-02-04 | 0
1476 | 1.2 | 1.2.8.7.3.3.1 | C | Drill Hose - SPOT 3 (USAP) | Not Started | 7 | 2d | 2026-02-03 | 2026-02-04 | 1647 | 0% |  | USAP Support |  | 84 |  | 2026-02-03 | 2026-02-04 | 0
1477 | 1.2 | 1.2.8.7.3.4 | C | Cargo Storage Support Pole & MCM (USAP) | Not Started | 6 | 58d | 2025-11-12 | 2026-02-04 | 1448, 1449 | 0% |  | USAP Support |  | 84 |  | 2025-11-12 | 2026-02-04 | 0
1478 | 1.2 | 1.2.8.7.4 | P | Opening Activities & Seasonal Equipment Site (SES) Setup | Not Started | 5 | 68d | 2025-11-05 | 2026-02-11 |  | 0% |  |  |  | 79 |  | 2025-11-05 | 2026-02-11 | 0
1479 | 1.2 | 1.2.8.7.4.1 | C | Excavate Winter Storage Berms (USAP) | Not Started | 6 | 8d | 2025-11-05 | 2025-11-14 | 1449FS -5d | 0% |  | USAP Support |  | 103 |  | 2025-11-05 | 2025-11-14 | 0
1480 | 1.2 | 1.2.8.7.4.2 | C | Excavate and Groom SES (USAP) | Not Started | 6 | 8d | 2025-11-07 | 2025-11-18 | 1449FS -3d | 0% |  | USAP Support |  | 70 |  | 2025-11-07 | 2025-11-18 | 0
1481 | 1.2 | 1.2.8.7.4.3 | C | SES Dig-out (Driller) | Not Started | 6 | 3d | 2025-11-13 | 2025-11-17 | 1449, 1451FS +2d | 0% |  |  |  | 0 | TRUE | 2025-11-13 | 2025-11-17 | 0
1482 | 1.2 | 1.2.8.7.4.4 | C | Groom & Compact Roads/Drill Pad (USAP) | Not Started | 6 | 2d | 2025-11-14 | 2025-11-17 | 1481SS +1d | 0% |  | USAP Support |  | 0 | TRUE | 2025-11-14 | 2025-11-17 | 0
1483 | 1.2 | 1.2.8.7.4.5 | C | Build Water Tank Ramp (USAP) | Not Started | 6 | 2d | 2025-11-14 | 2025-11-17 | 1481SS +1d | 0% |  | USAP Support |  | -2841 |  | 2025-11-14 | 2025-11-17 | 0
1484 | 1.2 | 1.2.8.7.4.6 | C | Deliver TOS1, TOS2, Drill Towers, DCC (to SES), Main Hose Reel (ASC), Reels (TU-20, TU-15) | Not Started | 6 | 3d | 2025-12-03 | 2025-12-05 | 1479, 1482, 1486FS +10d | 0% |  |  |  | 103 |  | 2025-12-03 | 2025-12-05 | 0
1485 | 1.2 | 1.2.8.7.4.7 | C | IT Integration Activities for SES (USAP) | Not Started | 6 | 4d | 2025-11-20 | 2025-11-25 | 1492 | 0% |  | USAP Support |  | 132 |  | 2025-11-20 | 2025-11-25 | 0
1486 | 1.2 | 1.2.8.7.4.8 | C | SES & Drill Pad Excavated & Established | Not Started | 6 | 0 | 2025-11-17 | 2025-11-17 | 1482FF | 0% |  |  |  | 0 | TRUE | 2025-11-17 | 2025-11-17 | 0
1487 | 1.2 | 1.2.8.7.4.9 | C | Provide PolarTherm Heaters (USAP) | Not Started | 6 | 59d | 2025-11-18 | 2026-02-11 | 1486 | 0% |  | USAP Support |  | 70 |  | 2025-11-18 | 2026-02-11 | 0
1488 | 1.2 | 1.2.8.7.4.10 | C | Provide Support Generators (CRREL / Onan Genset) (USAP) | Not Started | 6 | 58d | 2025-11-18 | 2026-02-10 | 1486, 1487SS | 0% |  | USAP Support |  | 70 |  | 2025-11-18 | 2026-02-10 | 0
1489 | 1.2 | 1.2.8.7.4.11 | C | Provide 953 Loader, 287B Skidsteer, Pax Van, & Snomo's (USAP) | Not Started | 6 | 1d | 2025-11-12 | 2025-11-12 | 1449, 1451 | 0% |  | USAP Support |  | 141 |  | 2025-11-12 | 2025-11-12 | 0
1490 | 1.2 | 1.2.8.7.4.12 | C | Begin Delivery - 5k Fuel Tanks (USAP) | Not Started | 6 | 1d | 2025-11-28 | 2025-11-28 | 1486FS +7d | 0% |  | USAP Support |  | 0 | TRUE | 2025-11-28 | 2025-11-28 | 0
1491 | 1.2 | 1.2.8.7.4.13 | C | Make Ready all SES Modules (DCC, PHS, MHPs, MECC, WTs, All) | Not Started | 6 | 9d | 2025-11-14 | 2025-11-26 | 1481SS +1d | 0% |  |  |  | 82 |  | 2025-11-14 | 2025-11-26 | 0
1492 | 1.2 | 1.2.8.7.4.14 | C | Furnace Checkout & Fire Up (All modules) | Not Started | 6 | 4d | 2025-11-14 | 2025-11-19 | 1491SS | 0% |  |  |  | 82 |  | 2025-11-14 | 2025-11-19 | 0
1493 | 1.2 | 1.2.8.7.4.15 | C | SES and Equipment Maintenance Activities | Not Started | 6 | 51d | 2025-11-14 | 2026-01-28 | 1492SS | 0% |  |  |  | 89 |  | 2025-11-14 | 2026-01-28 | 0
1494 | 1.2 | 1.2.8.7.4.16 | C | SES IT Integration (USAP) | Not Started | 6 | 4d | 2025-11-20 | 2025-11-25 | 1492 | 0% |  | USAP Support |  | 122 |  | 2025-11-20 | 2025-11-25 | 0
1495 | 1.2 | 1.2.8.7.4.17 | C | Drill Control Center Set-up, Integration, & Commissioning | Not Started | 6 | 6d | 2025-11-20 | 2025-11-28 | 1494SS | 0% |  |  |  | 122 |  | 2025-11-20 | 2025-11-28 | 0
1496 | 1.2 | 1.2.8.7.4.18 | C | Seed Water Delivery (3000 gallons) (USAP) | Not Started | 6 | 1d | 2025-11-18 | 2025-11-18 | 1486, 1483 | 0% |  | USAP Support |  | -2841 |  | 2025-11-18 | 2025-11-18 | 0
1497 | 1.2 | 1.2.8.7.4.19 | C | Deliver Compressor to SES (USAP) | Not Started | 6 | 1d | 2025-11-28 | 2025-11-28 | 1486, 1491, 1496SS | 0% |  | USAP Support |  | 129 |  | 2025-11-28 | 2025-11-28 | 0
1498 | 1.2 | 1.2.8.7.4.20 | C | Deliver & Warm Up Glycol Tank (USAP) | Not Started | 6 | 1d | 2025-11-28 | 2025-11-28 | 1486, 1491, 1497SS | 0% |  | USAP Support |  | 130 |  | 2025-11-28 | 2025-11-28 | 0
1499 | 1.2 | 1.2.8.7.4.21 | C | T&L Support - Cargo Deliveries (USAP) | Not Started | 6 | 59d | 2025-11-11 | 2026-02-04 | 1451 | 0% |  | USAP Support |  | 84 |  | 2025-11-11 | 2026-02-04 | 0
1500 | 1.2 | 1.2.8.7.4.22 | C | Ready Antarctic Rodwell Apparatus (ARA) for Service | Not Started | 6 | 5d | 2025-11-28 | 2025-12-04 | 1492FS +5d | 0% |  |  |  | 90 |  | 2025-11-28 | 2025-12-04 | 0
1501 | 1.2 | 1.2.8.7.4.23 | C | Build SES Snow Stockpile (USAP) | Not Started | 6 | 36d | 2025-12-05 | 2026-01-27 | 1500 | 0% |  | USAP Support |  | 90 |  | 2025-12-05 | 2026-01-27 | 0
1502 | 1.2 | 1.2.8.7.4.24 | C | Perform Emergency Incident Drill & Safety Training | Not Started | 6 | 3d | 2025-12-01 | 2025-12-03 | 1495 | 0% |  |  |  | 121 |  | 2025-12-01 | 2025-12-03 | 0
1503 | 1.2 | 1.2.8.7.4.25 | C | Perform Emergency Incident Drill & Safety Training Complete | Not Started | 6 | 0 | 2025-12-03 | 2025-12-03 | 1502 | 0% |  |  |  | 121 |  | 2025-12-03 | 2025-12-03 | 0
1504 | 1.2 | 1.2.8.7.4.26 | C | Final SES Readiness Assessment | Not Started | 6 | 2d | 2025-12-05 | 2025-12-08 | 1490, 1491, 1492, 1496, 1500, 1503 | 0% |  |  |  | 121 |  | 2025-12-05 | 2025-12-08 | 0
1505 | 1.2 | 1.2.8.7.4.27 | C | SES Ready | Not Started | 6 | 0 | 2025-12-08 | 2025-12-08 | 1504 | 0% |  |  |  | 121 |  | 2025-12-08 | 2025-12-08 | 0
1506 | 1.2 | 1.2.8.7.5 | P | Generators & PDM | Not Started | 5 | 5d | 2026-02-12 | 2026-02-18 |  | 0% |  |  |  | 74 |  | 2026-02-12 | 2026-02-18 | 0
1507 | 1.2 | 1.2.8.7.5.1 | C | Generator & PDM: Commission - NPX | Not Started | 6 | 5d | 2026-02-12 | 2026-02-18 | 1480, 1481, 1487, 1488, 1490 | 0% |  |  |  | 74 |  | 2026-02-12 | 2026-02-18 | 0
1508 | 1.2 | 1.2.8.7.5.2 | C | Electrician Support for Power Generation (USAP) | Not Started | 6 | 3d | 2026-02-13 | 2026-02-17 | 1507SS +1d | 0% |  | USAP Support |  | 75 |  | 2026-02-13 | 2026-02-17 | 0
1509 | 1.2 | 1.2.8.7.5.3 | C | Generators Ready | Not Started | 6 | 0 | 2026-02-18 | 2026-02-18 | 1507FS -1d, 1508FS -1d | 0% |  |  |  | 75 |  | 2026-02-18 | 2026-02-18 | 0
1510 | 1.2 | 1.2.8.7.5.4 | C | Change from Temp Power to Generators (USAP) | Not Started | 6 | 0 | 2026-02-18 | 2026-02-18 | 1509SS | 0% |  | USAP Support |  | 75 |  | 2026-02-18 | 2026-02-18 | 0
1511 | 1.2 | 1.2.8.7.6 | P | TOS1 / Tower1 Setup | Not Started | 5 | 15d | 2025-11-18 | 2025-12-09 |  | 0% |  |  |  | 123 |  | 2025-11-18 | 2025-12-09 | 0
1512 | 1.2 | 1.2.8.7.6.1 | C | Uncover Hole 1 / String 87 | Not Started | 6 | 1h | 2025-11-18 | 2025-11-18 | 1482 | 0% |  |  |  | 121 |  | 2025-11-18 | 2025-11-18 | 0
1513 | 1.2 | 1.2.8.7.6.2 | C | Relocate TOS1 and Main Hose Reel to Hole 1 / String 87 | Not Started | 6 | 1d | 2025-11-18 | 2025-11-19 | 1512 | 0% |  |  |  | 122 |  | 2025-11-18 | 2025-11-19 | 0
1514 | 1.2 | 1.2.8.7.6.3 | C | Heavy Equipment Support for TOS1 and Main Hose Reel Relocation to Hole 1 / String 87 (USAP) | Not Started | 6 | 1d | 2025-11-18 | 2025-11-19 | 1513SS | 0% |  | USAP Support |  | 136.875 |  | 2025-11-18 | 2025-11-19 | 0
1515 | 1.2 | 1.2.8.7.6.4 | C | Position Sensor Handling Structure | Not Started | 6 | 1d | 2025-11-19 | 2025-11-20 | 1513 | 0% |  |  |  | 134.875 |  | 2025-11-19 | 2025-11-20 | 0
1516 | 1.2 | 1.2.8.7.6.5 | C | Trench & Install Reel Anchors (Hole 1 & 2) | Not Started | 6 | 1d | 2025-11-19 | 2025-11-20 | 1513 | 0% |  |  |  | 127.875 |  | 2025-11-19 | 2025-11-20 | 0
1517 | 1.2 | 1.2.8.7.6.6 | C | Position Hose & Cable Reels (Hole 1) | Not Started | 6 | 2d | 2025-11-19 | 2025-11-21 | 1516FS -1d | 0% |  |  |  | 127.875 |  | 2025-11-19 | 2025-11-21 | 0
1518 | 1.2 | 1.2.8.7.6.7 | C | Hose & Cable Delivery & Layout SES-TOS | Not Started | 6 | 3d | 2025-11-21 | 2025-11-26 | 1517 | 0% |  |  |  | 127.875 |  | 2025-11-21 | 2025-11-26 | 0
1519 | 1.2 | 1.2.8.7.6.8 | C | TOS1 Network/Comms Set-up | Not Started | 6 | 3d | 2025-11-21 | 2025-11-26 | 1517 | 0% |  |  |  | 127.875 |  | 2025-11-21 | 2025-11-26 | 0
1520 | 1.2 | 1.2.8.7.6.9 | C | Make TOS1 Operational, Deliver Fuel, Fire Furnace | Not Started | 6 | 2d | 2025-11-26 | 2025-12-01 | 1513, 1505FS -8d, 1519, 1518 | 0% |  |  |  | 127.875 |  | 2025-11-26 | 2025-12-01 | 0
1521 | 1.2 | 1.2.8.7.6.10 | C | Prepare MCA (Mount on TU20, test slip ring), Setup both TU20 (Hole 1 & 2) | Not Started | 6 | 2d | 2025-12-08 | 2025-12-09 | 1484 | 0% |  |  |  | 123 |  | 2025-12-08 | 2025-12-09 | 0
1522 | 1.2 | 1.2.8.7.6.11 | C | Connect Hose Loop & Circulate Water | Not Started | 6 | 2d | 2025-11-28 | 2025-12-02 | 1520FS -1d | 0% |  |  |  | 128.875 |  | 2025-11-28 | 2025-12-02 | 0
1523 | 1.2 | 1.2.8.7.6.12 | C | Pull Drill Heads from ICL & Final Testing in TOS | Not Started | 6 | 1d | 2025-12-01 | 2025-12-02 | 1520 | 0% |  |  |  | 128.875 |  | 2025-12-01 | 2025-12-02 | 0
1524 | 1.2 | 1.2.8.7.6.13 | C | TOS1/Tower1 Site Ready for Drilling | Not Started | 6 | 0 | 2025-12-02 | 2025-12-02 | 1523, 1522, 1520, 1519 | 0% |  |  |  | 128.875 |  | 2025-12-02 | 2025-12-02 | 0
1525 | 1.2 | 1.2.8.7.7 | P | TOS2 / Tower2 Setup | Not Started | 5 | 5.125d | 2025-11-18 | 2025-11-25 |  | 0% |  |  |  | 132.875 |  | 2025-11-18 | 2025-11-25 | 0
1526 | 1.2 | 1.2.8.7.7.1 | C | Uncover Hole 2 / String 88 | Not Started | 6 | 1h | 2025-11-18 | 2025-11-18 | 1482 | 0% |  |  |  | 129.875 |  | 2025-11-18 | 2025-11-18 | 0
1527 | 1.2 | 1.2.8.7.7.2 | C | Relocate TOS2 to Hole 2 / String 88 | Not Started | 6 | 1d | 2025-11-18 | 2025-11-19 | 1526 | 0% |  |  |  | 129.875 |  | 2025-11-18 | 2025-11-19 | 0
1528 | 1.2 | 1.2.8.7.7.3 | C | Heavy Support for TOS2 Relocation to Hole 2 / String 88 (USAP) | Not Started | 6 | 1d | 2025-11-18 | 2025-11-19 | 1527SS | 0% |  | USAP Support |  | 136.875 |  | 2025-11-18 | 2025-11-19 | 0
1529 | 1.2 | 1.2.8.7.7.4 | C | Cable Layout SES to TOS2 | Not Started | 6 | 3d | 2025-11-19 | 2025-11-24 | 1527 | 0% |  |  |  | 130.875 |  | 2025-11-19 | 2025-11-24 | 0
1530 | 1.2 | 1.2.8.7.7.5 | C | TOS2 Network/Comms Install | Not Started | 6 | 3d | 2025-11-19 | 2025-11-24 | 1529SS | 0% |  |  |  | 133.875 |  | 2025-11-19 | 2025-11-24 | 0
1531 | 1.2 | 1.2.8.7.7.6 | C | Make TOS2 Operational, Deliver Fuel, Fire Furnace | Not Started | 6 | 1d | 2025-11-24 | 2025-11-25 | 1529 | 0% |  |  |  | 132.875 |  | 2025-11-24 | 2025-11-25 | 0
1532 | 1.2 | 1.2.8.7.7.7 | C | TOS2/Tower2 Site Ready for Drilling | Not Started | 6 | 0 | 2025-11-25 | 2025-11-25 | 1531 | 0% |  |  |  | 132.875 |  | 2025-11-25 | 2025-11-25 | 0
1533 | 1.2 | 1.2.8.7.8 | P | EHWD: Drill Commissioning | Not Started | 5 | 14d | 2025-12-01 | 2025-12-18 |  | 0% |  |  |  | 116 |  | 2025-12-01 | 2025-12-18 | 0
1534 | 1.2 | 1.2.8.7.8.1 | C | Begin Circulation of Water & Fire Boilers | Not Started | 6 | 5d | 2025-12-01 | 2025-12-05 | 1496, 1490 | 0% |  |  |  | 0 | TRUE | 2025-12-01 | 2025-12-05 | 0
1535 | 1.2 | 1.2.8.7.8.2 | C | Develop & Establish Rodwell | Not Started | 6 | e14d | 2025-12-04 | 2025-12-18 | 1534SS +3d | 0% |  |  |  | 117 |  | 2025-12-04 | 2025-12-18 | 0
1536 | 1.2 | 1.2.8.7.8.3 | C | New Driller Training | Not Started | 6 | 5d | 2025-12-08 | 2025-12-12 | 1534, 1453 | 0% |  |  |  | 120 |  | 2025-12-08 | 2025-12-12 | 0
1537 | 1.2 | 1.2.8.7.8.4 | C | Emergency & Safety Systems Tests | Not Started | 6 | 4d | 2025-12-08 | 2025-12-11 | 1534 | 0% |  |  |  | 0 | TRUE | 2025-12-08 | 2025-12-11 | 0
1538 | 1.2 | 1.2.8.7.8.5 | C | Perform Complete Systems Testing (Wet-test & Comm) | Not Started | 6 | e4d | 2025-12-11 | 2025-12-15 | 1537 | 0% |  |  |  | 0 | TRUE | 2025-12-11 | 2025-12-15 | 0
1539 | 1.2 | 1.2.8.7.8.6 | C | Readiness Review/Safety Refresher | Not Started | 6 | e3d | 2025-12-15 | 2025-12-18 | 1538 | 0% |  |  |  | 0 | TRUE | 2025-12-15 | 2025-12-18 | 0
1540 | 1.2 | 1.2.8.7.8.7 | C | EHWD System Ready for Drilling | Not Started | 6 | 0 | 2025-12-18 | 2025-12-18 | 1539, 1538, 1537, 1462 | 0% |  |  |  | 0 | TRUE | 2025-12-18 | 2025-12-18 | 0
1541 | 1.2 | 1.2.8.7.9 | P | Deep Drilling FS3 | Not Started | 5 | 19d | 2025-12-18 | 2026-01-16 |  | 0% |  |  |  | 97 |  | 2025-12-18 | 2026-01-16 | 0
1542 | 1.2 | 1.2.8.7.9.1 | P | DRILL HOLE 1 / String 87 | Not Started | 6 | 3d | 2025-12-18 | 2025-12-23 |  | 0% |  |  |  | 113 |  | 2025-12-18 | 2025-12-23 | 0
1543 | 1.2 | 1.2.8.7.9.1.1 | C | Drill Hole 1 / String 87 | Not Started | 7 | e52h | 2025-12-18 | 2025-12-20 | 1540 | 0% |  |  |  | 0 | TRUE | 2025-12-18 | 2025-12-20 | 0
1544 | 1.2 | 1.2.8.7.9.1.2 | C | Hole 1 Drilling Complete, Turn Over to Installation Team | Not Started | 7 | 0 | 2025-12-20 | 2025-12-20 | 1543 | 0% |  |  |  | 0 | TRUE | 2025-12-20 | 2025-12-20 | 0
1545 | 1.2 | 1.2.8.7.9.1.3 | C | Installation - Hole 1 / String 87 - Driller Supported | Not Started | 7 | e48h | 2025-12-20 | 2025-12-22 | 1922FF | 0% |  |  |  | 114 |  | 2025-12-20 | 2025-12-22 | 0
1546 | 1.2 | 1.2.8.7.9.1.4 | C | Relocate Hose, Cable Reels to Hole 2 / String 88 | Not Started | 7 | e12h | 2025-12-20 | 2025-12-21 | 1544, 1516 | 0% |  |  |  | 115.875 |  | 2025-12-20 | 2025-12-21 | 0
1547 | 1.2 | 1.2.8.7.9.1.5 | C | Heavy Support for Main Hose Reel Relocation (USAP) to Hole 2 / String 88 | Not Started | 7 | e4h | 2025-12-20 | 2025-12-21 | 1546SS | 0% |  | USAP Support |  | 116 |  | 2025-12-20 | 2025-12-21 | 0
1548 | 1.2 | 1.2.8.7.9.1.6 | C | Relocate Sensor Handling Structure to Hole 2 / String 88 | Not Started | 7 | e2h | 2025-12-22 | 2025-12-22 | 1923FF | 0% |  |  |  | 113 |  | 2025-12-22 | 2025-12-22 | 0
1549 | 1.2 | 1.2.8.7.9.1.7 | C | Uncover Hole 3 / String 89 | Not Started | 7 | e1h | 2025-12-23 | 2025-12-23 | 1550SF | 0% |  |  |  | 113.75 |  | 2025-12-23 | 2025-12-23 | 0
1550 | 1.2 | 1.2.8.7.9.1.8 | C | Closeout & Relocate Tower & TOS-1 to Hole 3 / String 89 | Not Started | 7 | e8h | 2025-12-23 | 2025-12-23 | 1925SS | 0% |  |  |  | 21 |  | 2025-12-23 | 2025-12-23 | 0
1551 | 1.2 | 1.2.8.7.9.1.9 | C | Heavy Support to Relocate Tower & TOS-1 to Hole 3 / String 89 (USAP) | Not Started | 7 | e2h | 2025-12-23 | 2025-12-23 | 1550SS | 0% |  | USAP Support |  | 21 |  | 2025-12-23 | 2025-12-23 | 0
1552 | 1.2 | 1.2.8.7.9.1.10 | C | Trench & Install Reel Anchors at Hole 3 / String 89 | Not Started | 7 | e4h | 2025-12-23 | 2025-12-23 | 1551 | 0% |  |  |  | 21 |  | 2025-12-23 | 2025-12-23 | 0
1553 | 1.2 | 1.2.8.7.9.1.11 | C | Trenching Support at Hole 3 / String 89 (USAP) | Not Started | 7 | e4h | 2025-12-23 | 2025-12-23 | 1552SS | 0% |  | USAP Support |  | 21 |  | 2025-12-23 | 2025-12-23 | 0
1554 | 1.2 | 1.2.8.7.9.1.12 | C | Prepare MCA Cable (Mount on TU20, test slip ring) for Hole 3 / String 89 | Not Started | 7 | e8h | 2025-12-23 | 2025-12-23 | 1925 | 0% |  |  |  | 112.75 |  | 2025-12-23 | 2025-12-23 | 0
1555 | 1.2 | 1.2.8.7.9.1.13 | C | Heavy Support for Main Cable Loading (USAP) for Hole 3 / String 89 | Not Started | 7 | e2h | 2025-12-23 | 2025-12-23 | 1554SS | 0% |  | USAP Support |  | 113.125 |  | 2025-12-23 | 2025-12-23 | 0
1556 | 1.2 | 1.2.8.7.9.2 | C | Operational Debrief/Drill Maintenance | Not Started | 6 | e24h | 2025-12-23 | 2025-12-24 | 1550 | 0% |  |  |  | 21 |  | 2025-12-23 | 2025-12-24 | 0
1557 | 1.2 | 1.2.8.7.9.3 | P | DRILL HOLE 2 / String 88 | Not Started | 6 | 1.125d | 2025-12-24 | 2025-12-29 |  | 0% |  |  |  | 110.875 |  | 2025-12-24 | 2025-12-29 | 0
1558 | 1.2 | 1.2.8.7.9.3.1 | C | Drill Hole 2 / String 88 | Not Started | 7 | e52h | 2025-12-24 | 2025-12-26 | 1556 | 0% |  |  |  | 21 |  | 2025-12-24 | 2025-12-26 | 0
1559 | 1.2 | 1.2.8.7.9.3.2 | C | Hole 2 Drilling Complete, Turn Over to Installation Team | Not Started | 7 | 0 | 2025-12-26 | 2025-12-26 | 1558 | 0% |  |  |  | 21 |  | 2025-12-26 | 2025-12-26 | 0
1560 | 1.2 | 1.2.8.7.9.3.3 | C | Installation - Hole 2 / String 88 - Driller Supported | Not Started | 7 | e24h | 2025-12-26 | 2025-12-27 | 1938FF | 0% |  |  |  | 111 |  | 2025-12-26 | 2025-12-27 | 0
1561 | 1.2 | 1.2.8.7.9.3.4 | C | Relocate Hose, Cable Reels to Hole 3 / String 89 | Not Started | 7 | e12h | 2025-12-26 | 2025-12-27 | 1559, 1552 | 0% |  |  |  | 21 |  | 2025-12-26 | 2025-12-27 | 0
1562 | 1.2 | 1.2.8.7.9.3.5 | C | Heavy Support for Main Hose Reel Relocation to Hole 3 / String 89 (USAP) | Not Started | 7 | e4h | 2025-12-26 | 2025-12-27 | 1561SS | 0% |  | USAP Support |  | 112 |  | 2025-12-26 | 2025-12-27 | 0
1563 | 1.2 | 1.2.8.7.9.3.6 | C | Relocate Sensor Handling Structure to Hole 3 / String 89 | Not Started | 7 | e2h | 2025-12-27 | 2025-12-27 | 1939FF | 0% |  |  |  | 111 |  | 2025-12-27 | 2025-12-27 | 0
1564 | 1.2 | 1.2.8.7.9.3.7 | C | Uncover Hole 4 / String 90 | Not Started | 7 | e1h | 2025-12-28 | 2025-12-28 | 1567SF | 0% |  |  |  | 111 |  | 2025-12-28 | 2025-12-28 | 0
1565 | 1.2 | 1.2.8.7.9.3.12 | C | Prepare MCA (Mount on TU20, test slip ring) - Prep for Hole 4 / String 90 | Not Started | 7 | e8h | 2025-12-29 | 2025-12-29 | 1942 | 0% |  |  |  | 110.875 |  | 2025-12-29 | 2025-12-29 | 0
1566 | 1.2 | 1.2.8.7.9.3.13 | C | Heavy Support for Main Cable Loading - Hole 4 / String 90 (USAP) | Not Started | 7 | e2h | 2025-12-29 | 2025-12-29 | 1565SS | 0% |  | USAP Support |  | 111 |  | 2025-12-29 | 2025-12-29 | 0
1567 | 1.2 | 1.2.8.7.9.3.8 | C | Closeout & Relocate Tower & TOS2 to Hole 4 / String 90 | Not Started | 7 | e8h | 2025-12-28 | 2025-12-29 | 1941 | 0% |  |  |  | 21 |  | 2025-12-28 | 2025-12-29 | 0
1568 | 1.2 | 1.2.8.7.9.3.9 | C | Heavy Support to Relocate Tower & TOS2 to Hole 4 / String 90 (USAP) | Not Started | 7 | e2h | 2025-12-28 | 2025-12-29 | 1567SS | 0% |  | USAP Support |  | 21 |  | 2025-12-28 | 2025-12-29 | 0
1569 | 1.2 | 1.2.8.7.9.3.10 | C | Trench & Install Reel Anchors at Hole 4 / String 90 | Not Started | 7 | e4h | 2025-12-29 | 2025-12-29 | 1568 | 0% |  |  |  | 21 |  | 2025-12-29 | 2025-12-29 | 0
1570 | 1.2 | 1.2.8.7.9.3.11 | C | Trenching Support at Hole 4 / String 90 (USAP) | Not Started | 7 | e4h | 2025-12-29 | 2025-12-29 | 1569SS | 0% |  | USAP Support |  | 21 |  | 2025-12-29 | 2025-12-29 | 0
1571 | 1.2 | 1.2.8.7.9.4 | P | DRILL HOLE 3 / String 89 | Not Started | 6 | 3.5d | 2025-12-27 | 2025-12-31 |  | 0% |  |  |  | 108.25 |  | 2025-12-27 | 2025-12-31 | 0
1572 | 1.2 | 1.2.8.7.9.4.1 | C | Drill Hole 3 / String 89 | Not Started | 7 | e52h | 2025-12-27 | 2025-12-29 | 1561, 1550, 1553 | 0% |  |  |  | 21 |  | 2025-12-27 | 2025-12-29 | 0
1573 | 1.2 | 1.2.8.7.9.4.2 | C | Hole 3 Drilling Complete, Turn Over to Installation Team | Not Started | 7 | 0 | 2025-12-29 | 2025-12-29 | 1572 | 0% |  |  |  | 21 |  | 2025-12-29 | 2025-12-29 | 0
1574 | 1.2 | 1.2.8.7.9.4.3 | C | Installation - Hole 3 / String 89 - Driller Supported | Not Started | 7 | e24h | 2025-12-29 | 2025-12-30 | 1954FF | 0% |  |  |  | 109.375 |  | 2025-12-29 | 2025-12-30 | 0
1575 | 1.2 | 1.2.8.7.9.4.4 | C | Relocate Hose, Cable Reels to Hole 4 / String 90 | Not Started | 7 | e12h | 2025-12-29 | 2025-12-30 | 1573, 1569 | 0% |  |  |  | 21 |  | 2025-12-29 | 2025-12-30 | 0
1576 | 1.2 | 1.2.8.7.9.4.5 | C | Heavy Support for Main Hose Reel Relocation to Hole 4 / String 90 (USAP) | Not Started | 7 | e4h | 2025-12-29 | 2025-12-29 | 1575SS | 0% |  | USAP Support |  | 110 |  | 2025-12-29 | 2025-12-29 | 0
1577 | 1.2 | 1.2.8.7.9.4.6 | C | Relocate Sensor Handling Structure to Hole 4 / String 90 | Not Started | 7 | e2h | 2025-12-30 | 2025-12-30 | 1956FF | 0% |  |  |  | 108.25 |  | 2025-12-30 | 2025-12-30 | 0
1578 | 1.2 | 1.2.8.7.9.4.12 | C | Prepare MCA (Mount on TU20, test slip ring) - Prep for Hole 5 / String 91 | Not Started | 7 | e8h | 2025-12-31 | 2025-12-31 | 1958 | 0% |  |  |  | 108.125 |  | 2025-12-31 | 2025-12-31 | 0
1579 | 1.2 | 1.2.8.7.9.4.13 | C | Heavy Support for Main Cable Loading - Hole 5 / String 91 (USAP) | Not Started | 7 | e2h | 2025-12-31 | 2025-12-31 | 1578SS | 0% |  | USAP Support |  | 108.875 |  | 2025-12-31 | 2025-12-31 | 0
1580 | 1.2 | 1.2.8.7.9.4.7 | C | Uncover Hole 5 / String 91 | Not Started | 7 | e1h | 2025-12-31 | 2025-12-31 | 1581SF | 0% |  |  |  | 109 |  | 2025-12-31 | 2025-12-31 | 0
1581 | 1.2 | 1.2.8.7.9.4.8 | C | Closeout & Relocate Tower & TOS1 to Hole 5 / String 91 | Not Started | 7 | e8h | 2025-12-31 | 2025-12-31 | 1958SS | 0% |  |  |  | 21 |  | 2025-12-31 | 2025-12-31 | 0
1582 | 1.2 | 1.2.8.7.9.4.9 | C | Heavy Support to Relocate Tower & TOS1 to Hole 5 / String 91 (USAP) | Not Started | 7 | e2h | 2025-12-31 | 2025-12-31 | 1581SS | 0% |  | USAP Support |  | 21 |  | 2025-12-31 | 2025-12-31 | 0
1583 | 1.2 | 1.2.8.7.9.4.10 | C | Trench & Install Reel Anchors at Hole 5 / String 91 | Not Started | 7 | e4h | 2025-12-31 | 2025-12-31 | 1582 | 0% |  |  |  | 21 |  | 2025-12-31 | 2025-12-31 | 0
1584 | 1.2 | 1.2.8.7.9.4.11 | C | Trenching Support at at Hole 5 / String 91 (USAP) | Not Started | 7 | e4h | 2025-12-31 | 2025-12-31 | 1583SS | 0% |  | USAP Support |  | 21 |  | 2025-12-31 | 2025-12-31 | 0
1585 | 1.2 | 1.2.8.7.9.5 | C | Operational Debrief / Drill Maintenance | Not Started | 6 | e24h | 2025-12-31 | 2026-01-01 | 1570, 1575, 1581 | 0% |  |  |  | 21 |  | 2025-12-31 | 2026-01-01 | 0
1586 | 1.2 | 1.2.8.7.9.6 | P | DRILL HOLE 4 / String 90 | Not Started | 6 | 2.5d | 2026-01-01 | 2026-01-05 |  | 0% |  |  |  | 106.125 |  | 2026-01-01 | 2026-01-05 | 0
1587 | 1.2 | 1.2.8.7.9.6.1 | C | Drill Hole 4 / String 90 | Not Started | 7 | e52h | 2026-01-01 | 2026-01-03 | 1585 | 0% |  |  |  | 21 |  | 2026-01-01 | 2026-01-03 | 0
1588 | 1.2 | 1.2.8.7.9.6.2 | C | Hole 4 Drilling Complete, Turn Over to Installation Team | Not Started | 7 | 0 | 2026-01-03 | 2026-01-03 | 1587 | 0% |  |  |  | 21 |  | 2026-01-03 | 2026-01-03 | 0
1589 | 1.2 | 1.2.8.7.9.6.3 | C | Installation - Hole 4 / String 90 - Driller Supported | Not Started | 7 | e24h | 2026-01-03 | 2026-01-04 | 1971FF | 0% |  |  |  | 107.25 |  | 2026-01-03 | 2026-01-04 | 0
1590 | 1.2 | 1.2.8.7.9.6.4 | C | Relocate Hose, Cable Reels to Hole 5 / String 91 | Not Started | 7 | e12h | 2026-01-03 | 2026-01-04 | 1588 | 0% |  |  |  | 21 |  | 2026-01-03 | 2026-01-04 | 0
1591 | 1.2 | 1.2.8.7.9.6.5 | C | Heavy Support for Main Hose Reel Relocation to Hole 5 / String 91 (USAP) | Not Started | 7 | e4h | 2026-01-03 | 2026-01-03 | 1590SS | 0% |  | USAP Support |  | 107 |  | 2026-01-03 | 2026-01-03 | 0
1592 | 1.2 | 1.2.8.7.9.6.6 | C | Relocate Sensor Handling Structure to Hole 5 / String 91 | Not Started | 7 | e2h | 2026-01-04 | 2026-01-04 | 1972FF | 0% |  |  |  | 106.125 |  | 2026-01-04 | 2026-01-04 | 0
1593 | 1.2 | 1.2.8.7.9.6.12 | C | Prepare MCA Cable (Mount on TU20, test slip ring) - Prep for Hole 6 / String 92 | Not Started | 7 | e8h | 2026-01-05 | 2026-01-05 | 1974 | 0% |  |  |  | 105.875 |  | 2026-01-05 | 2026-01-05 | 0
1594 | 1.2 | 1.2.8.7.9.6.13 | C | Heavy Support for Main Cable Loading for Hole 6 / String 92 (USAP) | Not Started | 7 | e2h | 2026-01-05 | 2026-01-05 | 1593SS | 0% |  | USAP Support |  | 106.75 |  | 2026-01-05 | 2026-01-05 | 0
1595 | 1.2 | 1.2.8.7.9.6.7 | C | Uncover Hole 6 / String 92 | Not Started | 7 | e1h | 2026-01-05 | 2026-01-05 | 1596SF | 0% |  |  |  | 107 |  | 2026-01-05 | 2026-01-05 | 0
1596 | 1.2 | 1.2.8.7.9.6.8 | C | Closeout & Relocate Tower & TOS2 for Hole 6 / String 92 | Not Started | 7 | e8h | 2026-01-05 | 2026-01-05 | 1974SS | 0% |  |  |  | 105.625 |  | 2026-01-05 | 2026-01-05 | 0
1597 | 1.2 | 1.2.8.7.9.6.9 | C | Heavy Support to Relocate Tower & TOS2 to Hole 6 / String 92 (USAP) | Not Started | 7 | e2h | 2026-01-05 | 2026-01-05 | 1596SS | 0% |  | USAP Support |  | 106.5 |  | 2026-01-05 | 2026-01-05 | 0
1598 | 1.2 | 1.2.8.7.9.6.10 | C | Trench & Install Reel Anchors at Hole 6 / String 92 | Not Started | 7 | e4h | 2026-01-05 | 2026-01-05 | 1597 | 0% |  |  |  | 106.5 |  | 2026-01-05 | 2026-01-05 | 0
1599 | 1.2 | 1.2.8.7.9.6.11 | C | Trenching Support at at Hole 6 / String 92 (USAP) | Not Started | 7 | e4h | 2026-01-05 | 2026-01-05 | 1598SS | 0% |  | USAP Support |  | 106.75 |  | 2026-01-05 | 2026-01-05 | 0
1600 | 1.2 | 1.2.8.7.9.7 | P | DRILL HOLE 5 / String 91 | Not Started | 6 | 4d | 2026-01-04 | 2026-01-08 |  | 0% |  |  |  | 104 |  | 2026-01-04 | 2026-01-08 | 0
1601 | 1.2 | 1.2.8.7.9.7.1 | C | Drill Hole 5 / String 91 | Not Started | 7 | e52h | 2026-01-04 | 2026-01-06 | 1582, 1584, 1590 | 0% |  |  |  | 21 |  | 2026-01-04 | 2026-01-06 | 0
1602 | 1.2 | 1.2.8.7.9.7.2 | C | Hole 5 Drilling Complete, Turn Over to Installation Team | Not Started | 7 | 0 | 2026-01-06 | 2026-01-06 | 1601 | 0% |  |  |  | 21 |  | 2026-01-06 | 2026-01-06 | 0
1603 | 1.2 | 1.2.8.7.9.7.3 | C | Installation - Hole 5 / String 91 - Driller Supported | Not Started | 7 | e24h | 2026-01-06 | 2026-01-07 | 1991FF | 0% |  |  |  | 105 |  | 2026-01-06 | 2026-01-07 | 0
1604 | 1.2 | 1.2.8.7.9.7.4 | C | Relocate Hose, Cable Reels to Hole 6 / String 92 | Not Started | 7 | e12h | 2026-01-06 | 2026-01-06 | 1602 | 0% |  |  |  | 21 |  | 2026-01-06 | 2026-01-06 | 0
1605 | 1.2 | 1.2.8.7.9.7.5 | C | Heavy Support for Main Hose Reel Relocation to Hole 6 / String 92 (USAP) | Not Started | 7 | e4h | 2026-01-06 | 2026-01-06 | 1604SS | 0% |  | USAP Support |  | 105.625 |  | 2026-01-06 | 2026-01-06 | 0
1606 | 1.2 | 1.2.8.7.9.7.6 | C | Relocate Sensor Handling Structure to Hole 6 / String 92 | Not Started | 7 | e2h | 2026-01-07 | 2026-01-07 | 1992FF | 0% |  |  |  | 104 |  | 2026-01-07 | 2026-01-07 | 0
1607 | 1.2 | 1.2.8.7.9.7.7 | C | Uncover Hole 7 / String 93 | Not Started | 7 | e1h | 2026-01-07 | 2026-01-07 | 1611SF | 0% |  |  |  | 104 |  | 2026-01-07 | 2026-01-07 | 0
1608 | 1.2 | 1.2.8.7.9.7.11 | C | Trenching Support at at Hole 7 / String 93 (USAP) | Not Started | 7 | e4h | 2026-01-07 | 2026-01-08 | 1613SS | 0% |  | USAP Support |  | 104 |  | 2026-01-07 | 2026-01-08 | 0
1609 | 1.2 | 1.2.8.7.9.7.12 | C | Prepare MCA Cable (Mount on TU20, test slip ring) - Prep for Hole 7 / String 93 | Not Started | 7 | e8h | 2026-01-08 | 2026-01-08 | 1994 | 0% |  |  |  | 104 |  | 2026-01-08 | 2026-01-08 | 0
1610 | 1.2 | 1.2.8.7.9.7.13 | C | Heavy Support for Main Cable Loading for Hole 7 / String 93 (USAP) | Not Started | 7 | e2h | 2026-01-08 | 2026-01-08 | 1609SS | 0% |  | USAP Support |  | 104 |  | 2026-01-08 | 2026-01-08 | 0
1611 | 1.2 | 1.2.8.7.9.7.8 | C | Closeout & Relocate Tower & TOS1 to Hole 7 / String 93 | Not Started | 7 | e8h | 2026-01-07 | 2026-01-08 | 1994SS | 0% |  |  |  | 21 |  | 2026-01-07 | 2026-01-08 | 0
1612 | 1.2 | 1.2.8.7.9.7.9 | C | Heavy Support to Relocate Tower & TOS1 to Hole 7 / String 93 (USAP) | Not Started | 7 | e2h | 2026-01-07 | 2026-01-07 | 1611SS | 0% |  | USAP Support |  | 21 |  | 2026-01-07 | 2026-01-07 | 0
1613 | 1.2 | 1.2.8.7.9.7.10 | C | Trench & Install Reel Anchors at Hole 7 / String 93 | Not Started | 7 | e4h | 2026-01-07 | 2026-01-08 | 1612 | 0% |  |  |  | 21 |  | 2026-01-07 | 2026-01-08 | 0
1614 | 1.2 | 1.2.8.7.9.8 | C | Operational Debrief | Not Started | 6 | e1d | 2026-01-08 | 2026-01-09 | 1613, 1604, 1611 | 0% |  |  |  | 21 |  | 2026-01-08 | 2026-01-09 | 0
1615 | 1.2 | 1.2.8.7.9.9 | P | DRILL HOLE 6 / String 92 | Not Started | 6 | 3d | 2026-01-09 | 2026-01-13 |  | 0% |  |  |  | 100 |  | 2026-01-09 | 2026-01-13 | 0
1616 | 1.2 | 1.2.8.7.9.9.1 | C | Drill Hole 6 / String 92 | Not Started | 7 | e52h | 2026-01-09 | 2026-01-11 | 1614 | 0% |  |  |  | 21 |  | 2026-01-09 | 2026-01-11 | 0
1617 | 1.2 | 1.2.8.7.9.9.2 | C | Hole 6 Drilling Complete, Turn Over to Installation Team | Not Started | 7 | 0 | 2026-01-11 | 2026-01-11 | 1616 | 0% |  |  |  | 21 |  | 2026-01-11 | 2026-01-11 | 0
1618 | 1.2 | 1.2.8.7.9.9.3 | C | Driller Support for Dust Logging Activities | Not Started | 7 | e12h | 2026-01-11 | 2026-01-11 | 2008FF | 0% |  |  |  | 102 |  | 2026-01-11 | 2026-01-11 | 0
1619 | 1.2 | 1.2.8.7.9.9.4 | C | Installation - Hole 6 / String 92 - Driller Supported | Not Started | 7 | e24h | 2026-01-11 | 2026-01-12 | 2010FF | 0% |  |  |  | 101 |  | 2026-01-11 | 2026-01-12 | 0
1620 | 1.2 | 1.2.8.7.9.9.5 | C | Relocate Hose & Cable Reels to Hole 7/ String 93 | Not Started | 7 | e12h | 2026-01-11 | 2026-01-11 | 1617 | 0% |  |  |  | 21 |  | 2026-01-11 | 2026-01-11 | 0
1621 | 1.2 | 1.2.8.7.9.9.6 | C | Heavy Support for Main Hose Reel Relocation to Hole 6 / String 92 (USAP) | Not Started | 7 | e4h | 2026-01-11 | 2026-01-11 | 1620SS | 0% |  | USAP Support |  | 102.5 |  | 2026-01-11 | 2026-01-11 | 0
1622 | 1.2 | 1.2.8.7.9.9.7 | C | Relocate Sensor Handling Structure to Hole 7 / String 93 | Not Started | 7 | e2h | 2026-01-12 | 2026-01-12 | 2011 | 0% |  |  |  | 100 |  | 2026-01-12 | 2026-01-12 | 0
1623 | 1.2 | 1.2.8.7.9.9.8 | C | Closeout & Relocate Tower & TOS2 to Storage | Not Started | 7 | e8h | 2026-01-13 | 2026-01-13 | 2013SS | 0% |  |  |  | 99.625 |  | 2026-01-13 | 2026-01-13 | 0
1624 | 1.2 | 1.2.8.7.9.9.9 | C | Heavy Support to Relocate Tower & TOS2 to Storage (USAP) | Not Started | 7 | e4h | 2026-01-13 | 2026-01-13 | 1623SS | 0% |  | USAP Support |  | 100.5 |  | 2026-01-13 | 2026-01-13 | 0
1625 | 1.2 | 1.2.8.7.9.10 | P | DRILL HOLE 7 / String 93 | Not Started | 6 | 4d | 2026-01-11 | 2026-01-16 |  | 0% |  |  |  | 98 |  | 2026-01-11 | 2026-01-16 | 0
1626 | 1.2 | 1.2.8.7.9.10.1 | C | Drill Hole 7 / String 93 | Not Started | 7 | e52h | 2026-01-11 | 2026-01-13 | 1611, 1613, 1620 | 0% |  |  |  | 21 |  | 2026-01-11 | 2026-01-13 | 0
1627 | 1.2 | 1.2.8.7.9.10.2 | C | Hole 7 Drilling Complete, Turn Over to Installation Team | Not Started | 7 | 0 | 2026-01-13 | 2026-01-13 | 1626 | 0% |  |  |  | 21 |  | 2026-01-13 | 2026-01-13 | 0
1628 | 1.2 | 1.2.8.7.9.10.3 | C | Installation - Hole 7 / String 93 - Driller Supported | Not Started | 7 | e24h | 2026-01-14 | 2026-01-14 | 2023FF | 0% |  |  |  | 99 |  | 2026-01-14 | 2026-01-14 | 0
1629 | 1.2 | 1.2.8.7.9.10.4 | C | Closeout & Relocate Tower & TOS1 to Storage | Not Started | 7 | e12h | 2026-01-15 | 2026-01-16 | 2026SS | 0% |  |  |  | 21 |  | 2026-01-15 | 2026-01-16 | 0
1630 | 1.2 | 1.2.8.7.9.10.5 | C | Heavy Support to Relocate Main Hose Reel, Tower & TOS1 to Storage (USAP) | Not Started | 7 | e6h | 2026-01-15 | 2026-01-15 | 1629SS | 0% |  | USAP Support |  | 98 |  | 2026-01-15 | 2026-01-15 | 0
1631 | 1.2 | 1.2.8.7.9.11 | C | Drilling & Installation Complete | Not Started | 6 | 0 | 2026-01-16 | 2026-01-16 | 1629 | 0% |  |  |  | 21 |  | 2026-01-16 | 2026-01-16 | 0
1632 | 1.2 | 1.2.8.7.9.12 | C | Operational Debrief | Not Started | 6 | 1d | 2026-01-16 | 2026-01-16 | 1629 | 0% |  |  |  | 97 |  | 2026-01-16 | 2026-01-16 | 0
1633 | 1.2 | 1.2.8.7.9.13 | C | Drill and Safety Lessons Learned Complete | Not Started | 6 | 0 | 2026-01-16 | 2026-01-16 | 1631 | 0% |  |  |  | 21 |  | 2026-01-16 | 2026-01-16 | 0
1634 | 1.2 | 1.2.8.7.10 | P | Decommission and Store EHWD | Not Started | 5 | 66d | 2025-12-08 | 2026-03-11 |  | 0% |  |  |  | 59 |  | 2025-12-08 | 2026-03-11 | 0
1635 | 1.2 | 1.2.8.7.10.1 | C | Create Storage Berms - End-of-the-World Site (USAP) | Not Started | 6 | 22d | 2025-12-08 | 2026-01-08 | 1449, 1479, 1482, 1483, 1484 | 0% |  | USAP Support |  | 103 |  | 2025-12-08 | 2026-01-08 | 0
1636 | 1.2 | 1.2.8.7.10.2 | C | Drain and Decommission EHWD Components | Not Started | 6 | 4d | 2026-01-19 | 2026-01-22 | 1633FS +1d | 0% |  |  |  | 21 |  | 2026-01-19 | 2026-01-22 | 0
1637 | 1.2 | 1.2.8.7.10.3 | C | Remove & Retro/Store All DNF | Not Started | 6 | 5d | 2026-01-19 | 2026-01-23 | 1636SS | 0% |  |  |  | 80 |  | 2026-01-19 | 2026-01-23 | 0
1638 | 1.2 | 1.2.8.7.10.4 | C | Disconnect all Interconnect Cables & Hoses (All including SES to TOS) | Not Started | 6 | 6d | 2026-01-19 | 2026-01-26 | 1636SS | 0% |  |  |  | 91 |  | 2026-01-19 | 2026-01-26 | 0
1639 | 1.2 | 1.2.8.7.10.5 | C | Decommission SES | Not Started | 6 | 6d | 2026-01-19 | 2026-01-26 | 1636SS | 0% |  |  |  | 20 |  | 2026-01-19 | 2026-01-26 | 0
1640 | 1.2 | 1.2.8.7.10.6 | C | Decommission TOS | Not Started | 6 | 6d | 2026-01-19 | 2026-01-26 | 1636SS | 0% |  |  |  | 20 |  | 2026-01-19 | 2026-01-26 | 0
1641 | 1.2 | 1.2.8.7.10.7 | C | Winterize all EHWD Equipment | Not Started | 6 | 5d | 2026-01-27 | 2026-02-02 | 1640, 1639 | 0% |  |  |  | 20 |  | 2026-01-27 | 2026-02-02 | 0
1642 | 1.2 | 1.2.8.7.10.8 | C | Removal of Snow Ramp (USAP) | Not Started | 6 | 2d | 2026-02-03 | 2026-02-04 | 1641 | 0% |  | USAP Support |  | 21 |  | 2026-02-03 | 2026-02-04 | 0
1643 | 1.2 | 1.2.8.7.10.9 | C | Tow and Place EHWD onto Berms for Long-Term Storage (USAP) | Not Started | 6 | 2d | 2026-02-03 | 2026-02-04 | 1642SS | 0% |  | USAP Support |  | 20 |  | 2026-02-03 | 2026-02-04 | 0
1644 | 1.2 | 1.2.8.7.10.10 | P | Remove Drill Hose from MSHR, Respool & Ship to ZCM | Not Started | 6 | 9d | 2026-01-21 | 2026-02-02 |  | 0% |  |  |  | 86 |  | 2026-01-21 | 2026-02-02 | 0
1645 | 1.2 | 1.2.8.7.10.10.1 | C | Remove Drill Hose from MSHR and Respool Individually | Not Started | 7 | 4d | 2026-01-21 | 2026-01-26 | 1636SS +2d | 0% |  |  |  | 21 |  | 2026-01-21 | 2026-01-26 | 0
1646 | 1.2 | 1.2.8.7.10.10.2 | C | Drill Hose Respooled | Not Started | 7 | 0 | 2026-01-26 | 2026-01-26 | 1645 | 0% |  |  |  | 20 |  | 2026-01-26 | 2026-01-26 | 0
1647 | 1.2 | 1.2.8.7.10.10.3 | C | Deliver to Cargo Yard and Prepare for Shipping (Driller & USAP) | Not Started | 7 | 5d | 2026-01-27 | 2026-02-02 | 1646 | 0% |  | USAP Support |  | 84 |  | 2026-01-27 | 2026-02-02 | 0
1648 | 1.2 | 1.2.8.7.10.11 | C | Winterization and Storage of EHWD Equipment Complete | Not Started | 6 | 0 | 2026-02-04 | 2026-02-04 | 1646, 1643, 1641 | 0% |  |  |  | 20 |  | 2026-02-04 | 2026-02-04 | 0
1649 | 1.2 | 1.2.8.7.10.12 | C | Inventory & Photograph EHWD, Document Repairs Needed | Not Started | 6 | 3d | 2026-01-23 | 2026-01-27 | 1637FS -1d | 0% |  |  |  | 87 |  | 2026-01-23 | 2026-01-27 | 0
1650 | 1.2 | 1.2.8.7.10.13 | C | UNL Equipment - Deliver to Cargo for Retro or Redistribution | Not Started | 6 | 3d | 2026-01-27 | 2026-01-29 | 1649FS -1d | 0% |  |  |  | 88 |  | 2026-01-27 | 2026-01-29 | 0
1651 | 1.2 | 1.2.8.7.10.14 | C | Crate and Deliver EHWD Equipment to Cargo for Retrograde or Redistribution | Not Started | 6 | 5d | 2026-01-26 | 2026-01-30 | 1631, 1636, 1637 | 0% |  |  |  | 79 |  | 2026-01-26 | 2026-01-30 | 0
1652 | 1.2 | 1.2.8.7.10.15 | C | Storage and Retrograde Complete | Not Started | 6 | 0 | 2026-02-02 | 2026-02-02 | 1651FS +1d | 0% |  |  |  | 86 |  | 2026-02-02 | 2026-02-02 | 0
1653 | 1.2 | 1.2.8.7.10.16 | C | Pole and MCM Cargo Retro Support (USAP) | Not Started | 6 | 8d | 2026-01-26 | 2026-02-04 | 1651SS | 0% |  | USAP Support |  | 84 |  | 2026-01-26 | 2026-02-04 | 0
1654 | 1.2 | 1.2.8.7.10.17 | C | MCM Receive and Berm Drill Hose at the MCM (USAP) | Not Started | 6 | 0 | 2026-03-11 | 2026-03-11 | 1476FS +25d | 0% |  | USAP Support |  | 59 |  | 2026-03-11 | 2026-03-11 | 0
1655 | 1.2 | 1.2.8.7.11 | P | Other Field Activities (FS3 Season) | Not Started | 5 | 80d | 2025-10-01 | 2026-01-23 |  | 0% |  |  |  | 92 |  | 2025-10-01 | 2026-01-23 | 0
1656 | 1.2 | 1.2.8.7.11.1 | C | MCM Field Logistics Rep (PSL) | Not Started | 6 | 30d | 2025-10-01 | 2025-11-11 | 1448 | 0% |  |  |  | 142 |  | 2025-10-01 | 2025-11-11 | 0
1657 | 1.2 | 1.2.8.7.11.6 | C | Survey Support for As-Built Drawing (USAP) | Not Started | 6 | 6d | 2026-01-16 | 2026-01-23 | 1631 | 0% |  | USAP Support |  | 92 |  | 2026-01-16 | 2026-01-23 | 0
1658 | 1.2 | 1.2.8.7.12 | C | ICU Field Team Redeployed | Not Started | 5 | 0 | 2026-02-05 | 2026-02-05 | 1652, 1641, 1637, 1648FS +1d | 0% |  |  |  | 83 |  | 2026-02-05 | 2026-02-05 | 0
1659 | 1.2 | 1.2.8.7.13 | C | On-Ice Labor (FS3) | Not Started | 5 | 64d | 2025-11-04 | 2026-02-04 | 1648FF | 0% |  |  | EE/ME Engineer Labor Totals from Population file. Assumes 2 days in McMurdo southbound and 1 day northbound. Technician Labor Totals from Population file. Assumes 2 days in McMurdo southbound and 1 day northbound. Safety Engineer Labor Totals from Population file. Assumes 2 days in McMurdo southbound and 1 day northbound. | 84 |  | 2025-11-04 | 2026-02-04 | 0
1660 | 1.2 | 1.2.8.7.14 | C | NPX Activities Complete (FS3 Season) | Not Started | 5 | 0 | 2026-02-04 | 2026-02-04 | 1648 | 0% |  |  |  | 84 |  | 2026-02-04 | 2026-02-04 | 0
1661 | 1.2 | 1.2.9 | P | Installation - Off-ice | Should have Started | 3 | 864d | 2021-11-01 | 2025-02-28 |  | 0% |  |  |  | 324 |  | 2021-11-01 | 2025-02-28 | 0
1662 | 1.2 | 1.2.9.1 | P | Sensor Handling & Testing: Process & Equipment | Should have Started | 4 | 638d | 2022-01-02 | 2024-06-14 |  | 0% |  |  |  | 506 |  | 2022-01-02 | 2024-06-14 | 0
1663 | 1.2 | 1.2.9.1.1 | C | Finalize Sensor Handling Process | Should have Started | 5 | 30d | 2022-01-02 | 2022-02-10 |  | 0% |  | Installation Lead |  | 1035 |  | 2022-01-02 | 2022-02-10 | 0
1664 | 1.2 | 1.2.9.1.2 | C | South Pole Acceptance Testing (SPAT) Ready to be shipped from UW | Not Started | 5 | 0 | 2024-06-14 | 2024-06-14 | 3152FS +7d | 0% |  |  |  | 506 |  | 2024-06-14 | 2024-06-14 | 0
1665 | 1.2 | 1.2.9.1.3 | P | Sensor Handling Equipment | Not Started | 5 | 46d | 2022-08-15 | 2022-10-17 |  | 0% |  |  |  | 937 |  | 2022-08-15 | 2022-10-17 | 0
1666 | 1.2 | 1.2.9.1.3.1 | C | Spec Sensor Handling Equipment | Not Started | 6 | 24d | 2022-08-15 | 2022-09-15 |  | 0% |  | PSL Eng |  | 919 |  | 2022-08-15 | 2022-09-15 | 0
1667 | 1.2 | 1.2.9.1.3.2 | C | Procure Sensor Handling Equipment | Not Started | 6 | 20d | 2022-09-16 | 2022-10-13 | 1666 | 0% |  | Installation Lead |  | 919 |  | 2022-09-16 | 2022-10-13 | 0
1668 | 1.2 | 1.2.9.1.3.3 | C | Procure ESD Mitigation Equipment | Not Started | 6 | 20d | 2022-09-20 | 2022-10-17 | 1667SS +2d | 0% |  | Installation Lead | Lab coats, ESDgloves, ESD runners | 937 |  | 2022-09-20 | 2022-10-17 | 0
1669 | 1.2 | 1.2.9.1.4 | P | Sensor Handling Facility | Should have Started | 5 | 168d | 2022-01-15 | 2022-09-06 |  | 0% |  |  |  | 966 |  | 2022-01-15 | 2022-09-06 | 0
1670 | 1.2 | 1.2.9.1.4.1 | C | Finalize Sensor Handling Facility Design | Should have Started | 6 | 20d | 2022-01-15 | 2022-02-10 |  | 0% |  | PSL Eng, PSL drafter, Installation Lead |  | 1114 |  | 2022-01-15 | 2022-02-10 | 0
1671 | 1.2 | 1.2.9.1.4.2 | C | Sensor Handling Facility Design Review | Not Started | 6 | 1d | 2022-02-15 | 2022-02-15 |  | 0% |  | PSL Eng, Installation Lead |  | 951 |  | 2022-02-15 | 2022-02-15 | 0
1672 | 1.2 | 1.2.9.1.4.3 | C | Sensor Handling Facility Design Complete | Not Started | 6 | 0 | 2022-02-24 | 2022-02-24 | 1671FS +7d | 0% |  |  |  | 1104 |  | 2022-02-24 | 2022-02-24 | 0
1673 | 1.2 | 1.2.9.1.4.4 | C | Procure Sensor Handling Facility Materials (or Administer Subcontract) | Not Started | 6 | 60d | 2022-02-16 | 2022-05-10 | 1671 | 0% |  | PSL Eng, Installation Lead |  | 951 |  | 2022-02-16 | 2022-05-10 | 0
1674 | 1.2 | 1.2.9.1.4.5 | C | Fabricate and Assemble Sensor Handling Structure at PSL and Verify Function | Not Started | 6 | 75d | 2022-05-11 | 2022-08-23 | 1673 | 0% |  | PSL Tech, PSL Eng, Installation Lead |  | 951 |  | 2022-05-11 | 2022-08-23 | 0
1675 | 1.2 | 1.2.9.1.4.6 | C | Disassemble Sensor Handling Structure Marking for Reassembly | Not Started | 6 | 7d | 2022-08-29 | 2022-09-06 | 1674FS +3d | 0% |  | PSL Tech, Installation Lead |  | 948 |  | 2022-08-29 | 2022-09-06 | 0
1676 | 1.2 | 1.2.9.1.5 | P | Sensor Sleds | Not Started | 5 | 79d | 2022-02-11 | 2022-06-01 |  | 0% |  |  |  | 1035 |  | 2022-02-11 | 2022-06-01 | 0
1677 | 1.2 | 1.2.9.1.5.1 | C | Finalize Sensor Sled Design in Collaboration with USAP Contractor | Not Started | 6 | 79d | 2022-02-11 | 2022-06-01 | 1663 | 0% |  | Installation Lead | Pending usage request of existing sleds | 1035 |  | 2022-02-11 | 2022-06-01 | 0
1678 | 1.2 | 1.2.9.1.5.2 | C | Sensor Sled Design Complete | Not Started | 6 | 0 | 2022-06-01 | 2022-06-01 | 1677 | 0% |  |  |  | 1035 |  | 2022-06-01 | 2022-06-01 | 0
1679 | 1.2 | 1.2.9.1.6 | P | Sensor Testing Tent | Not Started | 5 | 79d | 2022-02-11 | 2022-06-01 |  | 0% |  |  |  | 1035 |  | 2022-02-11 | 2022-06-01 | 0
1680 | 1.2 | 1.2.9.1.6.1 | C | Coordinate with USAP Contractor on Requirements, Tent Availability, and Sensor Staging Site | Not Started | 6 | 79d | 2022-02-11 | 2022-06-01 | 1663 | 0% |  | Installation Lead | Pending usage request of existing tent | 1035 |  | 2022-02-11 | 2022-06-01 | 0
1681 | 1.2 | 1.2.9.2 | P | Rigging Hardware for String Installation | Started | 4 | 427d | 2021-11-01 | 2023-06-20 |  | 2% |  |  |  | 761 |  | 2021-11-01 | 2023-06-20 | 0
1682 | 1.2 | 1.2.9.2.1 | C | Procure Installation Hardware Samples | Should have Started | 5 | 196d | 2021-11-01 | 2022-08-01 |  | 0% |  | Installation Lead | Tosi LOE hours covered 1.2.1 | 680 |  | 2021-11-01 | 2022-08-01 | 0
1683 | 1.2 | 1.2.9.2.2 | C | Preliminary Installation Hardware Sample Test | Started | 5 | 67d | 2022-03-01 | 2022-06-01 | 1682SS +86d | 17% |  | Installation Lead |  | 650 |  | 2022-03-01 | 2022-06-01 | 0
1684 | 1.2 | 1.2.9.2.3 | C | Preliminary Installation Procedure Draft | Not Started | 5 | 120d | 2022-03-01 | 2022-08-15 | 1683SS | 0% |  | Installation Lead |  | 658 |  | 2022-03-01 | 2022-08-15 | 0
1685 | 1.2 | 1.2.9.2.4 | C | Preliminary Installation Procedure Test | Not Started | 5 | 97d | 2022-04-01 | 2022-08-15 | 1684FF | 0% |  | Installation Lead, PLS Eng, PSL Tech |  | 672 |  | 2022-04-01 | 2022-08-15 | 0
1686 | 1.2 | 1.2.9.2.5 | C | Installation Hardware and Procedure Review | Started | 5 | 1d | 2022-09-15 | 2022-09-15 | 1685FS +22d | 5% |  | Installation Lead |  | 672 |  | 2022-09-15 | 2022-09-15 | 0
1687 | 1.2 | 1.2.9.2.6 | C | Finalize Installation Hardware and Procedure | Started | 5 | 21d | 2022-09-16 | 2022-10-14 | 1686 | 5% |  | Installation Lead |  | 658 |  | 2022-09-16 | 2022-10-14 | 0
1688 | 1.2 | 1.2.9.2.7 | C | Installation Hardware and Procedure Finalized | Started | 5 | 0 | 2022-10-14 | 2022-10-14 | 1687 | 5% |  | Installation Lead |  | 658 |  | 2022-10-14 | 2022-10-14 | 0
1689 | 1.2 | 1.2.9.2.8 | C | Procure Installation Hardware | Started | 5 | 62d | 2022-11-04 | 2023-01-30 | 1688FS +14d | 5% |  | Installation Lead | Dr. Tosi will procure. Labor hours covered in LOE 1.2.1.3 | 862 |  | 2022-11-04 | 2023-01-30 | 0
1690 | 1.2 | 1.2.9.2.9 | C | Procure Installation Weights | Not Started | 5 | 44d | 2022-11-04 | 2023-01-04 | 1688FS +14d | 0% |  | Installation Lead | Dr. Tosi will be primary on procurement with her labor hours covered in LOE 1.2.1.3. PSL Engineering support required for product review. | 756 |  | 2022-11-04 | 2023-01-04 | 0
1691 | 1.2 | 1.2.9.2.10 | C | Receive, & Inspect Installation Materials | Not Started | 5 | 20d | 2023-03-01 | 2023-03-28 | 1690SS +83d | 0% |  | Installation Lead | Tosi LOE hours covered 1.2.1 | 747 |  | 2023-03-01 | 2023-03-28 | 0
1692 | 1.2 | 1.2.9.2.11 | C | Assemble Installation Kits | Not Started | 5 | 60d | 2023-03-29 | 2023-06-20 | 1691 | 0% |  | Installation Lead | Tosi LOE hours covered 1.2.1 | 747 |  | 2023-03-29 | 2023-06-20 | 0
1693 | 1.2 | 1.2.9.3 | P | Installation Monitor Equipment: Depth Monitor & Handheld Connectivity Testers | Not Started | 4 | 652d | 2022-04-01 | 2024-10-03 |  | 0% |  |  |  | 427 |  | 2022-04-01 | 2024-10-03 | 0
1694 | 1.2 | 1.2.9.3.1 | P | IME TOS Connectivity Tester | Not Started | 5 | 545d | 2022-06-01 | 2024-07-05 |  | 0% |  | PSL Engineer, WIPAC Engineer |  | 491 |  | 2022-06-01 | 2024-07-05 | 0
1695 | 1.2 | 1.2.9.3.1.1 | C | IME TOS Connectivity Tester Design & Initial Procurement for Prototype (2021-22) | Not Started | 6 | 88d | 2022-06-01 | 2022-09-30 |  | 0% |  | PSL Engineer, WIPAC Engineer | See IME estimate (Installation Monitor Equipment). Sandstrom LOE1. IME Depth Readout and all the Connectivity Tester (can't add separate line) | 230 |  | 2022-06-01 | 2022-09-30 | 0
1696 | 1.2 | 1.2.9.3.1.2 | C | IME TOS Connectivity Tester Development and System Integration (2022-23) | Not Started | 6 | 261d | 2022-10-03 | 2023-10-02 | 1695 | 0% |  | PSL Engineer, WIPAC Engineer | WIPAC Engineering - LOE | 230 |  | 2022-10-03 | 2023-10-02 | 0
1697 | 1.2 | 1.2.9.3.1.3 | C | IME TOS Connectivity Tester Final Procurement and System Integration (2023-24) | Not Started | 6 | 457d | 2022-10-03 | 2024-07-05 | 1696SS | 0% |  | PSL Engineer, WIPAC Engineer | PSL Engineering support for integration with the DCC - 20k for slip ring module for DOM connectivity, 4 k for hand held devices | 491 |  | 2022-10-03 | 2024-07-05 | 0
1698 | 1.2 | 1.2.9.3.1.4 | C | IME TOS Connectivity Tester Fabrication Complete | Not Started | 6 | 0 | 2024-07-05 | 2024-07-05 | 1697 | 0% |  |  |  | 491 |  | 2024-07-05 | 2024-07-05 | 0
1699 | 1.2 | 1.2.9.3.2 | P | IME ICL Quad Connectivity Tester Design, Prototype, Production (2023-24) | Not Started | 5 | 262d | 2023-10-01 | 2024-10-03 |  | 0% |  | WIPAC Engineer LoE |  | 427 |  | 2023-10-01 | 2024-10-03 | 0
1700 | 1.2 | 1.2.9.3.2.1 | C | IME ICL Quad Connectivity Tester Design, Prototype, Production (2023-24) | Not Started | 6 | 262d | 2023-10-01 | 2024-10-03 |  | 0% |  | WIPAC Engineer LoE | 80 hours, LoE. IME ICL QCT. IME ICL QCT 1 domestic travel to NTS at MSU. | 427 |  | 2023-10-01 | 2024-10-03 | 0
1701 | 1.2 | 1.2.9.3.2.2 | C | IME ICL Quad Connectivity Tester Fabrication Complete | Not Started | 6 | 0 | 2024-10-03 | 2024-10-03 | 1700 | 0% |  |  |  | 427 |  | 2024-10-03 | 2024-10-03 | 0
1702 | 1.2 | 1.2.9.3.3 | P | IME Depth Readout | Not Started | 5 | 589d | 2022-04-01 | 2024-07-08 |  | 0% |  | PSL Engineer |  | 490 |  | 2022-04-01 | 2024-07-08 | 0
1703 | 1.2 | 1.2.9.3.3.1 | C | IME Depth Readout Design & Initial Procurement for Prototype (2021-22) | Not Started | 6 | 131d | 2022-04-01 | 2022-09-30 |  | 0% |  | PSL Engineer | PSL Labor copied to PY5 due to change in design (PY4 labor is mostly in house) See IME estimate. 1 IME Depth Readout and all the Connectivity Tester (can't add separate line). | 490 |  | 2022-04-01 | 2022-09-30 | 0
1704 | 1.2 | 1.2.9.3.3.2 | C | IME Depth Readout Development and System Integration (2022-23) | Not Started | 6 | 261d | 2022-10-03 | 2023-10-02 | 1703 | 0% |  | PSL Engineer | Duplicate system (1/TOS plus spares). 1 domestic trip ($1800/person) to MSU for testing with full length quad. Purchasing 2x materials for spares. | 490 |  | 2022-10-03 | 2023-10-02 | 0
1705 | 1.2 | 1.2.9.3.3.3 | C | IME Depth Readout System Final Integration (2023-24) | Not Started | 6 | 197d | 2023-10-03 | 2024-07-08 | 1704 | 0% |  | PSL Engineer | Test of all Paro Sensors | 490 |  | 2023-10-03 | 2024-07-08 | 0
1706 | 1.2 | 1.2.9.3.3.4 | C | IME Depth Readout Fabrication Complete | Not Started | 6 | 0 | 2024-07-08 | 2024-07-08 | 1705 | 0% |  |  |  | 490 |  | 2024-07-08 | 2024-07-08 | 0
1707 | 1.2 | 1.2.9.3.3.5 | C | Define Pressure Sensor Requirements | Not Started | 6 | 20d | 2022-04-01 | 2022-04-28 |  | 0% |  | Installation Lead | Mostly by Tosi/Sandstrom (LOE), verification by PSL | 994 |  | 2022-04-01 | 2022-04-28 | 0
1708 | 1.2 | 1.2.9.3.3.6 | C | Procure Pressure Sensor Sample | Not Started | 6 | 15d | 2022-04-29 | 2022-05-19 | 1707 | 0% |  | Installation Lead | May delay pressure sensor procurement if calibration shelf life duration in question | 1044 |  | 2022-04-29 | 2022-05-19 | 0
1709 | 1.2 | 1.2.9.3.3.7 | C | Procure Pressure Sensors | Not Started | 6 | 60d | 2024-02-01 | 2024-04-24 | 1707, 1704FS +84d | 0% |  | Installation Lead | Large purchase (around 100k), sole source documentation needed. LoE Tosi. May delay pressure sensor procurement if calibration shelf life duration in question. Vendor quote for 2022 is 11800/each, with increment of 3-5% / year. | 538 |  | 2024-02-01 | 2024-04-24 | 0
1710 | 1.2 | 1.2.9.3.3.8 | C | Pressure Sensors Received | Not Started | 6 | 0 | 2024-05-22 | 2024-05-22 | 1709FS +20d | 0% |  | Installation Lead |  | 518 |  | 2024-05-22 | 2024-05-22 | 0
1711 | 1.2 | 1.2.9.4 | P | Logging & Calibration Support | Not Started | 4 | 627d | 2022-03-01 | 2024-07-29 |  | 0% |  |  |  | 475 |  | 2022-03-01 | 2024-07-29 | 0
1712 | 1.2 | 1.2.9.4.1 | P | Logging Coordination | Not Started | 5 | 176d | 2022-03-01 | 2022-11-01 |  | 0% |  | Installation Lead |  | 926 |  | 2022-03-01 | 2022-11-01 | 0
1713 | 1.2 | 1.2.9.4.1.1 | C | Coordinate IDP Winch Loan or Winch Procurement | Not Started | 6 | 154d | 2022-03-01 | 2022-09-30 |  | 0% |  | Installation Lead |  | 926 |  | 2022-03-01 | 2022-09-30 | 0
1714 | 1.2 | 1.2.9.4.1.2 | C | IDP Winch Loan Secured | Not Started | 6 | 0 | 2022-09-30 | 2022-09-30 | 1713 | 0% |  | Installation Lead |  | 926 |  | 2022-09-30 | 2022-09-30 | 0
1715 | 1.2 | 1.2.9.4.1.3 | C | Coordinate Winch Training | Not Started | 6 | 22d | 2022-10-03 | 2022-11-01 | 1714 | 0% |  | Installation Lead |  | 926 |  | 2022-10-03 | 2022-11-01 | 0
1716 | 1.2 | 1.2.9.4.2 | P | Logbook & Geometry Support | Not Started | 5 | 141d | 2024-01-15 | 2024-07-29 |  | 0% |  |  |  | 475 |  | 2024-01-15 | 2024-07-29 | 0
1717 | 1.2 | 1.2.9.4.2.1 | C | Define Logbook Requirements | Not Started | 6 | 22d | 2024-01-15 | 2024-02-13 |  | 0% |  | Installation Lead |  | 429 |  | 2024-01-15 | 2024-02-13 | 0
1718 | 1.2 | 1.2.9.4.2.2 | C | Develop Logbook | Not Started | 6 | 60d | 2024-04-17 | 2024-07-09 | 1717FS +45d | 0% |  | Installation Lead |  | 429 |  | 2024-04-17 | 2024-07-09 | 0
1719 | 1.2 | 1.2.9.4.2.3 | C | Procure Logbook Tablets | Not Started | 6 | 60d | 2024-04-17 | 2024-07-09 | 1718SS | 0% |  | Installation Lead | Two rugged tablets for logbook keeping | 489 |  | 2024-04-17 | 2024-07-09 | 0
1720 | 1.2 | 1.2.9.4.2.4 | C | Logbook Complete | Not Started | 6 | 0 | 2024-07-29 | 2024-07-29 | 1718FS +14d | 0% |  | Installation Lead |  | 475 |  | 2024-07-29 | 2024-07-29 | 0
1721 | 1.2 | 1.2.9.4.2.5 | C | Procure Laser Rangers, Tape Measures, Shop Lights, Helmets for Installation | Not Started | 6 | 90d | 2024-02-01 | 2024-06-05 |  | 0% |  | Installation Lead | Laser ranges to measure well depth and distance between DOMs (2) | 508 |  | 2024-02-01 | 2024-06-05 | 0
1722 | 1.2 | 1.2.9.5 | C | Develop Installation Training Package | Not Started | 4 | 33d | 2025-01-15 | 2025-02-28 |  | 0% | Tosi LoE | Installation Lead | Develop training package | 324 |  | 2025-01-15 | 2025-02-28 | 0
1723 | 1.2 | 1.2.10 | P | Installation Field Seasons - Antarctica | Not Started | 3 | 962d | 2022-06-01 | 2026-02-18 |  | 0% |  |  |  | 74 |  | 2022-06-01 | 2026-02-18 | 0
1724 | 1.2 | 1.2.10.1 | P | Seasonal Staffing & Training, Off-Ice Coordination | Not Started | 4 | 522d | 2023-08-14 | 2025-08-20 |  | 0% |  |  |  | 201 |  | 2023-08-14 | 2025-08-20 | 0
1725 | 1.2 | 1.2.10.1.1 | C | FS1 Off-Ice Installation Training (Installers, including alternates) - Place Holder | Not Started | 5 | 5d | 2023-08-14 | 2023-08-18 | 775SS +5d | 0% |  |  | No off ice installation training (place holder) | 718 |  | 2023-08-14 | 2023-08-18 | 0
1726 | 1.2 | 1.2.10.1.2 | C | FS2 Off-Ice Installation Training (Installers, including alternates) | Not Started | 5 | 5d | 2024-08-12 | 2024-08-16 | 776SS +5d | 0% |  |  |  | 461 |  | 2024-08-12 | 2024-08-16 | 0
1727 | 1.2 | 1.2.10.1.3 | C | FS3 Off-Ice Installation Training (Drillers, Installers, Management, including alternates) | Not Started | 5 | 8d | 2025-08-11 | 2025-08-20 | 777SS +5d | 0% |  |  | 3x8 hours installation training (sensor handling, practice at the tower). Need (3+1 spare)x3=12 drillers 9 installer training + 3 alternates: 2 days safety training, 3 days specific training 9 installer training + 3 alternates: 2 days safety training, 3 days specific training 4 managers, only installation specific installation training (3 days). Marked as IK as all Management Personnel Labor is included elsewhere. | 201 |  | 2025-08-11 | 2025-08-20 | 0
1728 | 1.2 | 1.2.10.1.4 | C | FS3 Off-Ice Logging Winch Training (Installation Manager) | Not Started | 5 | 1d | 2025-08-01 | 2025-08-01 | 777SS -1d | 0% |  | Installation Lead | installation lead gets trained on the IDP winch (1 day) | 214 |  | 2025-08-01 | 2025-08-01 | 0
1729 | 1.2 | 1.2.10.2 | P | USAP Field Season 0 (FY23) | Not Started | 4 | 186d | 2022-06-01 | 2023-02-15 |  | 0% |  |  |  | 850 |  | 2022-06-01 | 2023-02-15 | 0
1730 | 1.2 | 1.2.10.2.1 | C | Installation Team FS0 Arrives (Placeholder) | Not Started | 5 | 0 | 2022-11-15 | 2022-11-15 |  | 0% |  |  |  | 917 |  | 2022-11-15 | 2022-11-15 | 0
1731 | 1.2 | 1.2.10.2.2 | C | PQ, ECW, Deployment Travel Costs Installation Team FS0 (Placeholder) | Not Started | 5 | 186d | 2022-06-01 | 2023-02-15 |  | 0% |  |  |  | 850 |  | 2022-06-01 | 2023-02-15 | 0
1732 | 1.2 | 1.2.10.2.3 | P | Cargo Movements (USAP) | Not Started | 5 | 0 | 2023-02-06 | 2023-02-06 |  | 0% |  |  |  | 858 |  | 2023-02-06 | 2023-02-06 | 0
1733 | 1.2 | 1.2.10.2.3.1 | C | Pole (USAP) PlaceHolder | Not Started | 6 | 0 | 2023-02-06 | 2023-02-06 |  | 0% |  | USAP Support |  | 858 |  | 2023-02-06 | 2023-02-06 | 0
1734 | 1.2 | 1.2.10.2.3.2 | P | MCM (USAP) | Not Started | 6 | 0 | 2023-02-06 | 2023-02-06 |  | 0% |  |  |  | 858 |  | 2023-02-06 | 2023-02-06 | 0
1735 | 1.2 | 1.2.10.2.3.2.1 | P | MCM SAAM - ComSur (USAP) | Not Started | 7 | 0 | 2023-02-06 | 2023-02-06 |  | 0% |  |  |  | 858 |  | 2023-02-06 | 2023-02-06 | 0
1736 | 1.2 | 1.2.10.2.3.2.1.1 | C | TBD | Not Started | 8 | 0 | 2023-02-06 | 2023-02-06 |  | 0% |  | USAP Support |  | 858 |  | 2023-02-06 | 2023-02-06 | 0
1737 | 1.2 | 1.2.10.2.3.2.2 | P | Vessel FY23 (USAP) | Not Started | 7 | 0 | 2023-02-06 | 2023-02-06 |  | 0% |  |  |  | 858 |  | 2023-02-06 | 2023-02-06 | 0
1738 | 1.2 | 1.2.10.2.3.2.2.1 | C | Surface Cables Assemblies (SCAs) Arrive (USAP) | Not Started | 8 | 0 | 2023-02-06 | 2023-02-06 | 820, 2786 | 0% |  | USAP Support |  | 858 |  | 2023-02-06 | 2023-02-06 | 0
1739 | 1.2 | 1.2.10.2.3.2.2.2 | C | SJBs Arrive (USAP) | Not Started | 8 | 0 | 2023-02-06 | 2023-02-06 | 820, 2795 | 0% |  | USAP Support |  | 858 |  | 2023-02-06 | 2023-02-06 | 0
1740 | 1.2 | 1.2.10.2.3.2.2.3 | C | Sensor Handling Facility Arrives (USAP) | Not Started | 8 | 0 | 2023-02-06 | 2023-02-06 | 165, 820 | 0% |  | USAP Support |  | 858 |  | 2023-02-06 | 2023-02-06 | 0
1741 | 1.2 | 1.2.10.3 | P | USAP Field Season 1 (FY24) | Not Started | 4 | 269d | 2023-02-06 | 2024-02-20 |  | 0% |  |  |  | 589 |  | 2023-02-06 | 2024-02-20 | 0
1742 | 1.2 | 1.2.10.3.1 | C | Installation Team FS1 Arrives (Placeholder) | Not Started | 5 | 0 | 2023-02-06 | 2023-02-06 |  | 0% |  |  |  | 858 |  | 2023-02-06 | 2023-02-06 | 0
1743 | 1.2 | 1.2.10.3.2 | C | PQ, ECW, Deployment Travel Costs Installation Team FS1 (Placeholder) | Not Started | 5 | 0 | 2023-02-06 | 2023-02-06 |  | 0% |  |  |  | 858 |  | 2023-02-06 | 2023-02-06 | 0
1744 | 1.2 | 1.2.10.3.3 | P | Cargo Movements (USAP) | Not Started | 5 | 269d | 2023-02-06 | 2024-02-20 |  | 0% |  |  |  | 589 |  | 2023-02-06 | 2024-02-20 | 0
1745 | 1.2 | 1.2.10.3.3.1 | P | Pole (USAP) | Not Started | 6 | 269d | 2023-02-06 | 2024-02-20 |  | 0% |  |  |  | 589 |  | 2023-02-06 | 2024-02-20 | 0
1746 | 1.2 | 1.2.10.3.3.1.1 | P | SPoT 1 | Not Started | 7 | 0 | 2023-02-06 | 2023-02-06 |  | 0% |  |  |  | 858 |  | 2023-02-06 | 2023-02-06 | 0
1747 | 1.2 | 1.2.10.3.3.1.1.1 | C | Sensor Handling Facility Arrives - Pole (USAP) | Not Started | 8 | 0 | 2023-02-06 | 2023-02-06 | 1740, 822 | 0% |  | USAP Support |  | 858 |  | 2023-02-06 | 2023-02-06 | 0
1748 | 1.2 | 1.2.10.3.3.1.1.2 | C | SJBs Arrive - Pole (USAP) | Not Started | 8 | 0 | 2023-02-06 | 2023-02-06 | 1739, 822 | 0% |  | USAP Support |  | 858 |  | 2023-02-06 | 2023-02-06 | 0
1749 | 1.2 | 1.2.10.3.3.1.2 | P | SPoT 2 | Not Started | 7 | 0 | 2024-01-01 | 2024-01-01 |  | 0% |  |  |  | 626 |  | 2024-01-01 | 2024-01-01 | 0
1750 | 1.2 | 1.2.10.3.3.1.2.1 | C | Placeholder | Not Started | 8 | 0 | 2024-01-01 | 2024-01-01 |  | 0% |  |  |  | 626 |  | 2024-01-01 | 2024-01-01 | 0
1751 | 1.2 | 1.2.10.3.3.1.3 | P | SPoT 3 | Not Started | 7 | 0 | 2024-02-01 | 2024-02-01 |  | 0% |  |  |  | 603 |  | 2024-02-01 | 2024-02-01 | 0
1752 | 1.2 | 1.2.10.3.3.1.3.1 | C | Placeholder | Not Started | 8 | 0 | 2024-02-01 | 2024-02-01 |  | 0% |  |  |  | 603 |  | 2024-02-01 | 2024-02-01 | 0
1753 | 1.2 | 1.2.10.3.3.1.4 | P | LC-130 | Not Started | 7 | 67d | 2023-11-15 | 2024-02-20 |  | 0% |  |  |  | 589 |  | 2023-11-15 | 2024-02-20 | 0
1754 | 1.2 | 1.2.10.3.3.1.4.1 | C | Placeholder | Not Started | 8 | 67d | 2023-11-15 | 2024-02-20 |  | 0% |  |  |  | 589 |  | 2023-11-15 | 2024-02-20 | 0
1755 | 1.2 | 1.2.10.3.3.2 | P | MCM (USAP) | Not Started | 6 | 3d | 2024-02-06 | 2024-02-08 |  | 0% |  |  |  | 597 |  | 2024-02-06 | 2024-02-08 | 0
1756 | 1.2 | 1.2.10.3.3.2.1 | P | MCM SAAM - ComSur (USAP) | Not Started | 7 | 1d | 2024-02-08 | 2024-02-08 |  | 0% |  |  |  | 597 |  | 2024-02-08 | 2024-02-08 | 0
1757 | 1.2 | 1.2.10.3.3.2.1.1 | C | Placeholder | Not Started | 8 | 1d | 2024-02-08 | 2024-02-08 |  | 0% |  |  |  | 597 |  | 2024-02-08 | 2024-02-08 | 0
1758 | 1.2 | 1.2.10.3.3.2.2 | P | Vessel (USAP) | Not Started | 7 | 0 | 2024-02-06 | 2024-02-06 |  | 0% |  |  |  | 600 |  | 2024-02-06 | 2024-02-06 | 0
1759 | 1.2 | 1.2.10.3.3.2.2.1 | C | Installation Weights Arrive - MCM (USAP) | Not Started | 8 | 0 | 2024-02-06 | 2024-02-06 | 167, 880 | 0% |  | USAP Support |  | 600 |  | 2024-02-06 | 2024-02-06 | 0
1760 | 1.2 | 1.2.10.3.3.2.2.2 | C | Installation Kits Arrive - MCM (USAP) | Not Started | 8 | 0 | 2024-02-06 | 2024-02-06 | 166, 880 | 0% |  | USAP Support |  | 600 |  | 2024-02-06 | 2024-02-06 | 0
1761 | 1.2 | 1.2.10.3.3.3 | P | Retrograde (USAP) | Not Started | 6 | 1d | 2024-02-09 | 2024-02-09 |  | 0% |  |  |  | 596 |  | 2024-02-09 | 2024-02-09 | 0
1762 | 1.2 | 1.2.10.3.3.3.1 | C | Placeholder | Not Started | 7 | 1d | 2024-02-09 | 2024-02-09 |  | 0% |  |  |  | 596 |  | 2024-02-09 | 2024-02-09 | 0
1763 | 1.2 | 1.2.10.3.3.4 | C | Cargo Storage Support Pole & MCM (USAP) | Not Started | 6 | 4d | 2023-12-01 | 2023-12-06 |  | 0% |  | Installation Lead |  | 641 |  | 2023-12-01 | 2023-12-06 | 0
1764 | 1.2 | 1.2.10.4 | P | USAP Field Season 2 (FY25) | Not Started | 4 | 186d | 2024-06-01 | 2025-02-19 |  | 0% |  |  |  | 331 |  | 2024-06-01 | 2025-02-19 | 0
1765 | 1.2 | 1.2.10.4.1 | C | Installation Team FS2 Arrives (Headcount 1) | Not Started | 5 | 0 | 2024-12-10 | 2024-12-10 |  | 0% |  |  |  | 341 |  | 2024-12-10 | 2024-12-10 | 0
1766 | 1.2 | 1.2.10.4.2 | C | PQ, ECW, Deployment Travel Costs Installation Team FS2 (Headcount 1) | Not Started | 5 | 186d | 2024-06-01 | 2025-02-19 |  | 0% |  |  | 1 - PQ @ $700/each (anticipated cost) 1 - ECW allowance @ $250/each 1 - International Travel (3 nights southbound, 2 nights northbound, plus per diem) @ $1800/each | 331 |  | 2024-06-01 | 2025-02-19 | 0
1767 | 1.2 | 1.2.10.4.3 | P | Cargo Movements (USAP) | Not Started | 5 | 75d | 2024-11-01 | 2025-02-18 |  | 0% |  |  |  | 332 |  | 2024-11-01 | 2025-02-18 | 0
1768 | 1.2 | 1.2.10.4.3.1 | P | Pole (USAP) | Not Started | 6 | 54d | 2024-12-01 | 2025-02-15 |  | 0% |  |  |  | 335 |  | 2024-12-01 | 2025-02-15 | 0
1769 | 1.2 | 1.2.10.4.3.1.1 | P | LC-130 (USAP) | Not Started | 7 | 54d | 2024-12-01 | 2025-02-15 |  | 0% |  |  |  | 335 |  | 2024-12-01 | 2025-02-15 | 0
1770 | 1.2 | 1.2.10.4.3.1.1.1 | C | ICL Power and Timing Electronics Arrive - Pole (USAP) | Not Started | 8 | 0 | 2024-12-01 | 2024-12-01 |  | 0% |  | USAP Support |  | 388 |  | 2024-12-01 | 2024-12-01 | 0
1771 | 1.2 | 1.2.10.4.3.1.1.2 | C | ICL Patch Cables and Patch Panels Arrive - Pole (USAP) | Not Started | 8 | 0 | 2024-12-01 | 2024-12-01 |  | 0% |  | USAP Support |  | 388 |  | 2024-12-01 | 2024-12-01 | 0
1772 | 1.2 | 1.2.10.4.3.1.1.3 | C | Field Hub Electronics - Pole (USAP) | Not Started | 8 | 0 | 2024-12-01 | 2024-12-01 |  | 0% |  | USAP Support |  | 388 |  | 2024-12-01 | 2024-12-01 | 0
1773 | 1.2 | 1.2.10.4.3.1.1.4 | C | Science Crate SF2 (SPAT, IME, Pressure Sensors, Laser Rangers) Equipment Arrives - Pole (USAP) | Not Started | 8 | 0 | 2024-12-01 | 2024-12-01 |  | 0% |  | USAP Support |  | 10 |  | 2024-12-01 | 2024-12-01 | 0
1774 | 1.2 | 1.2.10.4.3.1.1.5 | C | String 87 & 88 Sensors Arrive (D-Eggs from Japan, mDOMs from Germany) - Pole (USAP) | Not Started | 8 | 0 | 2024-12-15 | 2024-12-15 |  | 0% |  | USAP Support |  | 378 |  | 2024-12-15 | 2024-12-15 | 0
1775 | 1.2 | 1.2.10.4.3.1.1.6 | C | String 87 & 88 Calibration Devices Arrive (Europe, USA) - Pole (USAP) | Not Started | 8 | 0 | 2024-12-15 | 2024-12-15 |  | 0% |  | USAP Support |  | 349 |  | 2024-12-15 | 2024-12-15 | 0
1776 | 1.2 | 1.2.10.4.3.1.1.7 | C | String 87 & 88 Special Devices Arrive (Europe, USA) - Pole (USAP) | Not Started | 8 | 0 | 2024-12-15 | 2024-12-15 |  | 0% |  | USAP Support |  | 378 |  | 2024-12-15 | 2024-12-15 | 0
1777 | 1.2 | 1.2.10.4.3.1.1.8 | C | String 87 & 88 BCAs Arrive - Pole (USAP) | Not Started | 8 | 0 | 2025-02-15 | 2025-02-15 |  | 0% |  | USAP Support |  | 335 |  | 2025-02-15 | 2025-02-15 | 0
1778 | 1.2 | 1.2.10.4.3.1.2 | P | SPOT 1 (USAP) | Not Started | 7 | 0 | 2024-12-01 | 2024-12-01 |  | 0% |  |  |  | 388 |  | 2024-12-01 | 2024-12-01 | 0
1779 | 1.2 | 1.2.10.4.3.1.2.1 | C | SCA x7 Arrive - Pole (USAP) | Not Started | 8 | 0 | 2024-12-01 | 2024-12-01 |  | 0% |  | USAP Support |  | 388 |  | 2024-12-01 | 2024-12-01 | 0
1780 | 1.2 | 1.2.10.4.3.1.3 | P | SPOT 2 (USAP) | Not Started | 7 | 0 | 2025-01-01 | 2025-01-01 |  | 0% |  |  |  | 367 |  | 2025-01-01 | 2025-01-01 | 0
1781 | 1.2 | 1.2.10.4.3.1.3.1 | C | Installation Kits Arrive - Pole (USAP) | Not Started | 8 | 0 | 2025-01-01 | 2025-01-01 |  | 0% |  | USAP Support |  | 367 |  | 2025-01-01 | 2025-01-01 | 0
1782 | 1.2 | 1.2.10.4.3.1.3.2 | C | Installation Weights Arrive - Pole (USAP) | Not Started | 8 | 0 | 2025-01-01 | 2025-01-01 |  | 0% |  | USAP Support |  | 364 |  | 2025-01-01 | 2025-01-01 | 0
1783 | 1.2 | 1.2.10.4.3.1.4 | P | SPOT 3 (USAP) | Not Started | 7 | 0 | 2025-02-01 | 2025-02-01 |  | 0% |  |  |  | 345 |  | 2025-02-01 | 2025-02-01 | 0
1784 | 1.2 | 1.2.10.4.3.1.4.1 | C | Placeholder | Not Started | 8 | 0 | 2025-02-01 | 2025-02-01 |  | 0% |  |  |  | 345 |  | 2025-02-01 | 2025-02-01 | 0
1785 | 1.2 | 1.2.10.4.3.2 | P | MCM (USAP) | Not Started | 6 | 66d | 2024-11-01 | 2025-02-06 |  | 0% |  |  |  | 341 |  | 2024-11-01 | 2025-02-06 | 0
1786 | 1.2 | 1.2.10.4.3.2.1 | P | MCM SAAM - ComSur (USAP) | Not Started | 7 | 0 | 2024-11-01 | 2024-11-01 |  | 0% |  |  |  | 407 |  | 2024-11-01 | 2024-11-01 | 0
1787 | 1.2 | 1.2.10.4.3.1.1.1 | C | ICL Power and Timing Electronics Arrive (USAP) | Not Started | 8 | 0 | 2024-11-01 | 2024-11-01 |  | 0% |  | USAP Support |  | 407 |  | 2024-11-01 | 2024-11-01 | 0
1788 | 1.2 | 1.2.10.4.3.1.1.2 | C | ICL Patch Cables and Patch Panels Arrive (USAP) | Not Started | 8 | 0 | 2024-11-01 | 2024-11-01 |  | 0% |  | USAP Support |  | 407 |  | 2024-11-01 | 2024-11-01 | 0
1789 | 1.2 | 1.2.10.4.3.1.1.3 | C | Field Hub Electronics (USAP) | Not Started | 8 | 0 | 2024-11-01 | 2024-11-01 |  | 0% |  | USAP Support |  | 407 |  | 2024-11-01 | 2024-11-01 | 0
1790 | 1.2 | 1.2.10.4.3.1.1.4 | C | Science Crate SF2 (SPAT, IME, Pressure Sensors, Laser Rangers) Equipment (USAP) | Not Started | 8 | 0 | 2024-11-01 | 2024-11-01 |  | 0% |  | USAP Support |  | 407 |  | 2024-11-01 | 2024-11-01 | 0
1791 | 1.2 | 1.2.10.4.3.1.1.5 | C | String 87 & 88 Sensors Arrive (D-Eggs from Japan, mDOMs from Germany) (USAP) | Not Started | 8 | 0 | 2024-11-01 | 2024-11-01 |  | 0% |  | USAP Support |  | 407 |  | 2024-11-01 | 2024-11-01 | 0
1792 | 1.2 | 1.2.10.4.3.1.1.6 | C | String 87 & 88 Calibration Devices Arrive (Europe, USA) (USAP) | Not Started | 8 | 0 | 2024-11-01 | 2024-11-01 |  | 0% |  | USAP Support |  | 407 |  | 2024-11-01 | 2024-11-01 | 0
1793 | 1.2 | 1.2.10.4.3.1.1.7 | C | String 87 & 88 Special Devices Arrive (Europe, USA) (USAP) | Not Started | 8 | 0 | 2024-11-01 | 2024-11-01 |  | 0% |  | USAP Support |  | 407 |  | 2024-11-01 | 2024-11-01 | 0
1794 | 1.2 | 1.2.10.4.3.2.2 | P | Vessel (USAP) | Not Started | 7 | 0 | 2025-02-06 | 2025-02-06 |  | 0% |  |  |  | 341 |  | 2025-02-06 | 2025-02-06 | 0
1795 | 1.2 | 1.2.10.4.3.2.2.1 | C | Downhole MCAs - (USAP) | Not Started | 8 | 0 | 2025-02-06 | 2025-02-06 |  | 0% |  | USAP Support |  | 341 |  | 2025-02-06 | 2025-02-06 | 0
1796 | 1.2 | 1.2.10.4.3.2.2.2 | C | Downhole Load Members ? - (USAP) | Not Started | 8 | 0 | 2025-02-06 | 2025-02-06 |  | 0% |  | USAP Support |  | 341 |  | 2025-02-06 | 2025-02-06 | 0
1797 | 1.2 | 1.2.10.4.3.2.2.3 | C | String 87 & 88 BCAs - (USAP) | Not Started | 8 | 0 | 2025-02-06 | 2025-02-06 |  | 0% |  | USAP Support |  | 341 |  | 2025-02-06 | 2025-02-06 | 0
1798 | 1.2 | 1.2.10.4.3.2.2.4 | C | String 89-93 BCAs (USAP) | Not Started | 8 | 0 | 2025-02-06 | 2025-02-06 |  | 0% |  | USAP Support |  | 341 |  | 2025-02-06 | 2025-02-06 | 0
1799 | 1.2 | 1.2.10.4.3.3 | C | Retrograde (USAP) | Not Started | 6 | 0 | 2025-02-06 | 2025-02-06 |  | 0% |  |  |  | 341 |  | 2025-02-06 | 2025-02-06 | 0
1800 | 1.2 | 1.2.10.4.3.4 | C | Cargo Storage Support Pole & MCM (USAP) | Not Started | 6 | 56d | 2024-12-01 | 2025-02-18 |  | 0% |  | USAP Support |  | 332 |  | 2024-12-01 | 2025-02-18 | 0
1801 | 1.2 | 1.2.10.4.4 | P | Sensor Sleds & Tent | Not Started | 5 | 10d | 2024-12-10 | 2024-12-24 |  | 0% |  |  |  | 371 |  | 2024-12-10 | 2024-12-24 | 0
1802 | 1.2 | 1.2.10.4.4.1 | C | Sensor Sleds Construction/Prep Oversight | Not Started | 6 | 4d | 2024-12-10 | 2024-12-13 | 1765 | 0% |  | Installation Lead |  | 349 |  | 2024-12-10 | 2024-12-13 | 0
1803 | 1.2 | 1.2.10.4.4.2 | C | Sensor Sleds Construction/Prep Support (USAP) | Not Started | 6 | 5d | 2024-12-10 | 2024-12-16 | 1802SS, 1802FF | 0% |  | USAP Support |  | 349 |  | 2024-12-10 | 2024-12-16 | 0
1804 | 1.2 | 1.2.10.4.4.3 | C | Sensor Sleds Ready | Not Started | 6 | 0 | 2024-12-16 | 2024-12-16 | 1803 | 0% |  |  |  | 349 |  | 2024-12-16 | 2024-12-16 | 0
1805 | 1.2 | 1.2.10.4.4.4 | C | Sensor Testing Tent Prep Oversight | Not Started | 6 | 5d | 2024-12-10 | 2024-12-16 | 1765 | 0% |  | Installation Lead |  | 349 |  | 2024-12-10 | 2024-12-16 | 0
1806 | 1.2 | 1.2.10.4.4.5 | C | Sensor Testing Tent Prep Support (USAP) | Not Started | 6 | 5d | 2024-12-10 | 2024-12-16 | 1805SS, 1805FF | 0% |  | USAP Support |  | 349 |  | 2024-12-10 | 2024-12-16 | 0
1807 | 1.2 | 1.2.10.4.4.6 | C | Sensor Testing Tent Ready | Not Started | 6 | 0 | 2024-12-16 | 2024-12-16 | 1806 | 0% |  |  |  | 349 |  | 2024-12-16 | 2024-12-16 | 0
1808 | 1.2 | 1.2.10.4.4.7 | C | Setup SPAT in tent | Not Started | 6 | e7d | 2024-12-17 | 2024-12-24 | 1773FS +1d, 3153FS +1d | 0% | support from 1.6 personnel | Installation Lead, 1.6 SPAT SME |  | 10 |  | 2024-12-17 | 2024-12-24 | 0
1809 | 1.2 | 1.2.10.4.4.8 | C | SPAT ready | Not Started | 6 | 0 | 2024-12-24 | 2024-12-24 | 1808 | 0% |  |  |  | 9 |  | 2024-12-24 | 2024-12-24 | 0
1810 | 1.2 | 1.2.10.4.5 | P | Sensor Handling Facility Assembly | Not Started | 5 | 17d | 2024-12-04 | 2024-12-27 |  | 0% |  |  |  | 368 |  | 2024-12-04 | 2024-12-27 | 0
1811 | 1.2 | 1.2.10.4.5.1 | C | Sensor Handling Facility Assembly Oversight | Not Started | 6 | 14d | 2024-12-04 | 2024-12-23 |  | 0% |  | Installation Lead | oversight of ASC activity, 2 hours/day, 16 working days | 348 |  | 2024-12-04 | 2024-12-23 | 0
1812 | 1.2 | 1.2.10.4.5.2 | C | Sensor Handling Facility Assembly - Assemble Skis and Deck, Erect Walls, Construct Walls, Construct Roof (USAP) | Not Started | 6 | 14d | 2024-12-04 | 2024-12-23 | 1811SS | 0% |  | USAP Support |  | 362 |  | 2024-12-04 | 2024-12-23 | 0
1813 | 1.2 | 1.2.10.4.5.3 | C | Sensor Handling Facility Assembly Crane Support (USAP) | Not Started | 6 | 14d | 2024-12-04 | 2024-12-23 | 1811SS | 0% |  | USAP Support |  | 365 |  | 2024-12-04 | 2024-12-23 | 0
1814 | 1.2 | 1.2.10.4.5.4 | C | Sensor Handling Facility Construction Complete | Not Started | 6 | 0 | 2024-12-23 | 2024-12-23 | 1813, 1812 | 0% |  |  |  | 365 |  | 2024-12-23 | 2024-12-23 | 0
1815 | 1.2 | 1.2.10.4.5.5 | C | Position Sensor Handling Facility near Tower | Not Started | 6 | 1d | 2024-12-24 | 2024-12-24 | 1814 | 0% |  |  | oversight of ASC activity, 2 hours/day, 16 working days | 365 |  | 2024-12-24 | 2024-12-24 | 0
1816 | 1.2 | 1.2.10.4.5.6 | C | Sensor Handling Dry Run | Not Started | 6 | 2d | 2024-12-26 | 2024-12-27 | 1815 | 0% |  |  |  | 365 |  | 2024-12-26 | 2024-12-27 | 0
1817 | 1.2 | 1.2.10.4.6 | P | String Component Activities | Not Started | 5 | 24d | 2024-12-15 | 2025-01-20 |  | 0% |  |  | adjustment of rollers and tables, training | 354 |  | 2024-12-15 | 2025-01-20 | 0
1818 | 1.2 | 1.2.10.4.6.1 | C | Receive and Inspect Installation Kits & Weights Shipments | Not Started | 6 | 3d | 2025-01-02 | 2025-01-06 | 1782 | 0% |  | Installation Lead | 1 person, 1/2 day (in kind) | 363 |  | 2025-01-02 | 2025-01-06 | 0
1819 | 1.2 | 1.2.10.4.6.2 | C | Receive and Inspect String 87 & 88 Sensors, Calibration & Special Devices Shipments | Not Started | 6 | e1d | 2024-12-15 | 2024-12-16 | 1775 | 0% |  | Installation Lead | 1 person, 2x1/2 day | 377 |  | 2024-12-15 | 2024-12-16 | 0
1820 | 1.2 | 1.2.10.4.6.3 | C | Load String 87 Sensors on Sleds 1,2 for testing prior to storage | Not Started | 6 | e6h | 2024-12-26 | 2024-12-26 | 1775FS +1d, 1809FS +1d, 1804FS +1d, 1807FS +1d, 1808 | 0% |  | 1.6 SPAT SME | support to USAP activity (spotter, placement) | 352 |  | 2024-12-26 | 2024-12-26 | 0
1821 | 1.2 | 1.2.10.4.6.4 | C | Load String 87 Sensors on Sleds 1,2 for testing prior to storage (USAP) | Not Started | 6 | e6h | 2024-12-26 | 2024-12-26 | 1820SS | 0% |  | 1.6 SPAT SME |  | 352.625 |  | 2024-12-26 | 2024-12-26 | 0
1822 | 1.2 | 1.2.10.4.6.5 | C | Load String 88 Sensors on Sleds 3,4 for testing prior to storage | Not Started | 6 | e6h | 2024-12-27 | 2024-12-27 | 1809FS +1d, 1804FS +1d, 1807FS +1d, 1821FS +1d | 0% |  | 1.6 SPAT SME | support to USAP activity (spotter, placement) | 351.625 |  | 2024-12-27 | 2024-12-27 | 0
1823 | 1.2 | 1.2.10.4.6.6 | C | Load String 88 Sensors on Sleds 3,4 for testing prior to storage (USAP) | Not Started | 6 | e6h | 2024-12-27 | 2024-12-27 | 1822SS | 0% |  | 1.6 SPAT SME |  | 352 |  | 2024-12-27 | 2024-12-27 | 0
1824 | 1.2 | 1.2.10.4.6.7 | C | Conduct South Pole Acceptance Testing (SPAT) String 87 | Not Started | 6 | e7d | 2024-12-26 | 2025-01-02 | 1775FS +1d, 1809FS +1d, 1804FS +1d, 1807FS +1d | 0% |  | 1.6 SPAT SME | one week | 350 |  | 2024-12-26 | 2025-01-02 | 0
1825 | 1.2 | 1.2.10.4.6.8 | C | Conduct South Pole Acceptance Testing (SPAT) String 88 | Not Started | 6 | e7d | 2025-01-03 | 2025-01-10 | 1823FS +1d, 1824FS +1d | 0% |  | 1.6 SPAT SME | one week | 349 |  | 2025-01-03 | 2025-01-10 | 0
1826 | 1.2 | 1.2.10.4.6.9 | C | Conduct South Pole Acceptance Testing (SPAT) Special Devices String 87-88 | Not Started | 6 | e7d | 2025-01-13 | 2025-01-20 | 1825FS +1d | 0% |  | 1.6 SPAT SME | one week | 348 |  | 2025-01-13 | 2025-01-20 | 0
1827 | 1.2 | 1.2.10.4.6.10 | C | IME deployment and integration | Not Started | 6 | 20d | 2024-12-18 | 2025-01-16 |  | 0% |  | UW / PSL | 1 person part time on the task, with support from engineering team on site | 347 |  | 2024-12-18 | 2025-01-16 | 0
1828 | 1.2 | 1.2.10.4.7 | P | Surface Cable Activities (SJB to ICL) | Not Started | 5 | 54d | 2024-11-10 | 2025-01-27 |  | 0% |  |  |  | 348 |  | 2024-11-10 | 2025-01-27 | 0
1829 | 1.2 | 1.2.10.4.7.1 | C | Survey Trenches, Surface Junction Boxes and Holes (USAP) | Not Started | 6 | 3d | 2024-11-10 | 2024-11-12 |  | 0% |  | USAP Support |  | 399 |  | 2024-11-10 | 2024-11-12 | 0
1830 | 1.2 | 1.2.10.4.7.2 | C | Prep & Compact Surface Near ICL for Cable Install (USAP) | Not Started | 6 | 3d | 2024-12-01 | 2024-12-03 |  | 0% |  | USAP Support |  | 347 |  | 2024-12-01 | 2024-12-03 | 0
1831 | 1.2 | 1.2.10.4.7.3 | C | Open and Modify Tower, Bridge & ICL for Cable Routing (USAP) | Not Started | 6 | 4d | 2024-12-04 | 2024-12-09 | 1830 | 0% |  | USAP Support |  | 347 |  | 2024-12-04 | 2024-12-09 | 0
1832 | 1.2 | 1.2.10.4.7.4 | C | Excavate ICL Tower for Cable Entry & Routing (USAP) | Not Started | 6 | 1d | 2024-12-10 | 2024-12-10 | 1831 | 0% |  | USAP Support |  | 347 |  | 2024-12-10 | 2024-12-10 | 0
1833 | 1.2 | 1.2.10.4.7.5 | C | Prep/Uncrate Cable Spools; Load on 953 Loader | Not Started | 6 | 7d | 2024-12-17 | 2024-12-26 | 1832, 2821FS +1d | 0% | support from 1.4 personnel | Install Team, 1.4 CPT (Cables, SBJs) | Assist with loading cable spool on fork 3.5 days (1/2 day per cable, interlaced with activities below) | 347 |  | 2024-12-17 | 2024-12-26 | 0
1834 | 1.2 | 1.2.10.4.7.6 | C | Prep/Uncrate Cable Spools; Load on 953 Loader (USAP) | Not Started | 6 | 7d | 2024-12-11 | 2024-12-19 | 1832 | 0% |  | USAP Support |  | 373 |  | 2024-12-11 | 2024-12-19 | 0
1835 | 1.2 | 1.2.10.4.7.7 | C | Install 7 Surface Cables into ICL Tower, Across Bridge, into ICL | Not Started | 6 | 7d | 2024-12-17 | 2024-12-26 | 1833SS | 0% | support from 1.4 personnel | Install Team, 1.4 CPT (Cables, SBJs) | Estimate a full day prep, 1 day for cable 1, then 1/2 day for each other cable. Total 4 days. 4 people on the job, in addition to ASC. | 347 |  | 2024-12-17 | 2024-12-26 | 0
1836 | 1.2 | 1.2.10.4.7.8 | C | Install 7 Surface Cables into ICL Tower, Across Bridge, into ICL (USAP) | Not Started | 6 | 7d | 2024-12-17 | 2024-12-26 | 1833SS | 0% |  | USAP Support |  | 367 |  | 2024-12-17 | 2024-12-26 | 0
1837 | 1.2 | 1.2.10.4.7.9 | C | Close ICL Tower Bridge (USAP) | Not Started | 6 | 1d | 2024-12-30 | 2024-12-30 | 1836FS +1d | 0% |  | USAP Support |  | 367 |  | 2024-12-30 | 2024-12-30 | 0
1838 | 1.2 | 1.2.10.4.7.10 | C | Prep Cables & Attach to Grounding System in ICL | Not Started | 6 | 2d | 2024-12-27 | 2024-12-30 | 1836 | 0% | support from 1.4 personnel | 1.4 CPT (Cables, SBJs) | 2.5 days 1 person (in kind) | 367 |  | 2024-12-27 | 2024-12-30 | 0
1839 | 1.2 | 1.2.10.4.7.11 | C | Prep Cables & Attach to Grounding System in ICL (USAP) | Not Started | 6 | 2d | 2024-12-27 | 2024-12-30 | 1836 | 0% |  | USAP Support |  | 367 |  | 2024-12-27 | 2024-12-30 | 0
1840 | 1.2 | 1.2.10.4.7.12 | C | Excavate Surface Junction Box Pits (USAP) | Not Started | 6 | 1d | 2024-12-10 | 2024-12-10 | 1832SS | 0% |  | USAP Support |  | 380 |  | 2024-12-10 | 2024-12-10 | 0
1841 | 1.2 | 1.2.10.4.7.13 | C | Trench (mechanical) from SJB to ICL Tower (USAP) | Not Started | 6 | 2d | 2024-12-27 | 2024-12-30 | 1835 | 0% |  | USAP Support |  | 349 |  | 2024-12-27 | 2024-12-30 | 0
1842 | 1.2 | 1.2.10.4.7.14 | C | Unspool & Lay Surface Cables from Tower to SJB Pits | Not Started | 6 | 2d | 2024-12-30 | 2024-12-31 | 1841FS -1d | 0% | support from 1.4 personnel | 1.4 CPT (Cables, SBJs) | 2 days 2 people working with ASC | 366 |  | 2024-12-30 | 2024-12-31 | 0
1843 | 1.2 | 1.2.10.4.7.15 | C | Unspool & Lay Surface Cables from Tower to SJB Pits (USAP) | Not Started | 6 | 2d | 2024-12-30 | 2024-12-31 | 1841FS -1d | 0% |  | USAP Support |  | 350 |  | 2024-12-30 | 2024-12-31 | 0
1844 | 1.2 | 1.2.10.4.7.16 | C | Install SJB's in Pits (2); Connect Cables | Not Started | 6 | 2d | 2025-01-02 | 2025-01-03 | 1843 | 0% | support from 1.4 personnel | 1.4 CPT (Cables, SBJs) | 1 day, two people | 349 |  | 2025-01-02 | 2025-01-03 | 0
1845 | 1.2 | 1.2.10.4.7.17 | C | Build & Install Temp-Vault w/Lid (8'x10'x4'h) (USAP) | Not Started | 6 | 3d | 2025-01-02 | 2025-01-06 | 1844SS | 0% | 3 (where is a vault construction) | USAP Support |  | 363 |  | 2025-01-02 | 2025-01-06 | 0
1846 | 1.2 | 1.2.10.4.7.18 | C | Survey (as built), Backfill, and Flag Pits & Trenches (USAP) | Not Started | 6 | 3d | 2025-01-03 | 2025-01-07 | 1844FS -1d | 0% |  | USAP Support |  | 362 |  | 2025-01-03 | 2025-01-07 | 0
1847 | 1.2 | 1.2.10.4.7.19 | C | Surface Cable Continuity Test | Not Started | 6 | 2d | 2025-01-07 | 2025-01-08 | 1844FS +1d | 0% | support from 1.4 personnel | 1.4 CPT (Cables, SBJs) |  | 361 |  | 2025-01-07 | 2025-01-08 | 0
1848 | 1.2 | 1.2.10.4.7.20 | C | Maintain access to SJBs (USAP) | Not Started | 6 | 15d | 2025-01-07 | 2025-01-27 | 1844FS +1d | 0% |  | USAP Support |  | 348 |  | 2025-01-07 | 2025-01-27 | 0
1849 | 1.2 | 1.2.10.4.8 | P | ICL Upgrade Activities | Not Started | 5 | 56d | 2024-11-06 | 2025-01-27 |  | 0% |  |  |  | 348 |  | 2024-11-06 | 2025-01-27 | 0
1850 | 1.2 | 1.2.10.4.8.1 | C | ICL Upgrade Activities | Not Started | 6 | 19d | 2024-11-06 | 2024-12-03 | 2856SS, 2816FF | 0% |  |  |  | 385 |  | 2024-11-06 | 2024-12-03 | 0
1851 | 1.2 | 1.20.10.4.8.1 | C | Field Hubs, timing system, patch panels and patch cables installation | Not Started | 6 | 19d | 2024-12-31 | 2025-01-27 |  | 0% |  |  |  | 348 |  | 2024-12-31 | 2025-01-27 | 0
1852 | 1.2 | 1.2.10.4.9 | P | End of NPX Season Installation Close-Out Work | Not Started | 5 | 19d | 2024-12-31 | 2025-01-27 |  | 0% |  |  |  | 348 |  | 2024-12-31 | 2025-01-27 | 0
1853 | 1.2 | 1.2.10.4.9.1 | C | Store Sensor Handling Facility for Winter (USAP) | Not Started | 6 | 3d | 2024-12-31 | 2025-01-03 | 1816FS +1d | 0% |  | USAP Support |  | 364 |  | 2024-12-31 | 2025-01-03 | 0
1854 | 1.2 | 1.2.10.4.9.2 | C | Sensor Sleds Winter Storage (USAP) | Not Started | 6 | 5d | 2025-01-21 | 2025-01-27 | 1855 | 0% |  | USAP Support |  | 348 |  | 2025-01-21 | 2025-01-27 | 0
1855 | 1.2 | 1.2.10.4.9.3 | C | Store 87 & 88 Sensors in Cryo Helium Bay for Winter | Not Started | 6 | 3d | 2025-01-16 | 2025-01-20 | 1827FS -1d | 0% |  |  | 1 day 1 person (in kind) working with ASC | 348 |  | 2025-01-16 | 2025-01-20 | 0
1856 | 1.2 | 1.2.10.4.9.4 | C | Support Storage 87 & 88 Sensors in Cryo Helium Bay for Winter (USAP) | Not Started | 6 | 3d | 2025-01-16 | 2025-01-20 | 1855SS | 0% |  | USAP Support |  | 353 |  | 2025-01-16 | 2025-01-20 | 0
1857 | 1.2 | 1.2.10.4.9.5 | C | Store 87 & 88 Special Devices and BCAs in ICL for Winter | Not Started | 6 | 3d | 2025-01-16 | 2025-01-20 | 1827FS -1d | 0% |  |  | 1 day 1 person (in kind) working with ASC | 353 |  | 2025-01-16 | 2025-01-20 | 0
1858 | 1.2 | 1.2.10.4.9.6 | C | Clean up Testing Tent & Store SPAT | Not Started | 6 | 3d | 2025-01-21 | 2025-01-23 | 1826FS +1d | 0% |  | USAP Support |  | 347 |  | 2025-01-21 | 2025-01-23 | 0
1859 | 1.2 | 1.2.10.4.9.7 | C | Clean up Testing Tent & Store SPAT (USAP) | Not Started | 6 | 3d | 2025-01-21 | 2025-01-23 | 1858SS | 0% |  | USAP Support |  | 350 |  | 2025-01-21 | 2025-01-23 | 0
1860 | 1.2 | 1.2.10.4.10 | C | Installation: On-Ice Labor (FS2) | Not Started | 5 | 40d | 2024-12-10 | 2025-02-05 | 1765SS, 1861FF | 0% |  | Installation Lead |  | 341 |  | 2024-12-10 | 2025-02-05 | 0
1861 | 1.2 | 1.2.10.4.11 | C | END NPX Installation FS2 Season | Not Started | 5 | 0 | 2025-02-05 | 2025-02-05 |  | 0% |  |  |  | 302 |  | 2025-02-05 | 2025-02-05 | 0
1862 | 1.2 | 1.2.10.5 | P | USAP Field Season 3 (FY26) | Not Started | 4 | 267d | 2025-02-06 | 2026-02-18 |  | 0% |  |  |  | 74 |  | 2025-02-06 | 2026-02-18 | 0
1863 | 1.2 | 1.2.10.5.1 | P | Installation Team Arrives | Not Started | 5 | 11d | 2025-11-20 | 2025-12-08 |  | 0% |  |  |  | 125 |  | 2025-11-20 | 2025-12-08 | 0
1864 | 1.2 | 1.2.10.5.1.1 | C | Installation Team I arrives (1 + 1 In-kind) | Not Started | 6 | 0 | 2025-11-20 | 2025-11-20 |  | 0% |  | Install Lead, Install Night Shift Lead |  | 82 |  | 2025-11-20 | 2025-11-20 | 0
1865 | 1.2 | 1.2.10.5.1.2 | C | Installation Team II arrives (8 all in kind) | Not Started | 6 | 0 | 2025-12-08 | 2025-12-08 |  | 0% |  | 8 Installers, In-kind |  | 120 |  | 2025-12-08 | 2025-12-08 | 0
1866 | 1.2 | 1.2.10.5.2 | C | PQ, ECW, Deployment Travel Costs Install FS2 Installation Team | Not Started | 5 | 186d | 2025-06-01 | 2026-02-18 |  | 0% |  |  | 1 - PQ @ $700/each (anticipated cost) 1 - ECW allowance @ $250/each 1 - International Travel (3 nights southbound, 2 nights northbound, plus per diem) @ $1800/each | 74 |  | 2025-06-01 | 2026-02-18 | 0
1867 | 1.2 | 1.2.10.5.3 | P | Cargo Movements (USAP) | Not Started | 5 | 263d | 2025-02-06 | 2026-02-12 |  | 0% |  |  |  | 78 |  | 2025-02-06 | 2026-02-12 | 0
1868 | 1.2 | 1.2.10.5.3.1 | P | Pole (USAP) | Not Started | 6 | 3d | 2025-11-25 | 2025-12-01 |  | 0% |  |  |  | 130 |  | 2025-11-25 | 2025-12-01 | 0
1869 | 1.2 | 1.2.10.5.3.1.1 | P | LC-130 (USAP) | Not Started | 7 | 0 | 2025-11-25 | 2025-11-25 |  | 0% |  |  |  | 133 |  | 2025-11-25 | 2025-11-25 | 0
1870 | 1.2 | 1.2.10.5.3.1.1.1 | C | 89-93 BCAs Arrive - Pole (USAP) | Not Started | 8 | 0 | 2025-11-25 | 2025-11-25 |  | 0% |  | USAP Support |  | 133 |  | 2025-11-25 | 2025-11-25 | 0
1871 | 1.2 | 1.2.10.5.3.1.1.2 | C | Science Crate FS3 Arrive - Pole (USAP) | Not Started | 8 | 0 | 2025-11-25 | 2025-11-25 |  | 0% |  | USAP Support |  | 133 |  | 2025-11-25 | 2025-11-25 | 0
1872 | 1.2 | 1.2.10.5.3.1.1.3 | C | String 89-93 BCAs Arrive (McMurdo) - Pole (USAP) | Not Started | 8 | 0 | 2025-11-25 | 2025-11-25 |  | 0% |  | USAP Support |  | 131 |  | 2025-11-25 | 2025-11-25 | 0
1873 | 1.2 | 1.2.10.5.3.1.1.4 | C | String 89-93 Sensors Arrive (Japan, USA, Europe) - Pole (USAP) | Not Started | 8 | 0 | 2025-11-25 | 2025-11-25 |  | 0% |  | USAP Support |  | 131 |  | 2025-11-25 | 2025-11-25 | 0
1874 | 1.2 | 1.2.10.5.3.1.1.5 | C | String 89-93 Special Devices (Germany, USA) Arrive Pole (USAP) | Not Started | 8 | 0 | 2025-11-25 | 2025-11-25 |  | 0% |  | USAP Support |  | 133 |  | 2025-11-25 | 2025-11-25 | 0
1875 | 1.2 | 1.2.10.5.3.1.1.6 | C | String 89-93 Calibration Devices (Europe, USA) Arrive Pole (USAP) | Not Started | 8 | 0 | 2025-11-25 | 2025-11-25 |  | 0% |  | USAP Support |  | 133 |  | 2025-11-25 | 2025-11-25 | 0
1876 | 1.2 | 1.2.10.5.3.1.1.7 | C | Dust Logger and Dust Logger Winch Arrives Pole (USAP) | Not Started | 8 | 0 | 2025-11-25 | 2025-11-25 |  | 0% |  | USAP Support |  | 128 |  | 2025-11-25 | 2025-11-25 | 0
1877 | 1.2 | 1.2.10.5.3.1.1.8 | C | DM-Ice (USAP) | Not Started | 8 | 0 | 2025-11-25 | 2025-11-25 |  | 0% |  |  |  | 133 |  | 2025-11-25 | 2025-11-25 | 0
1878 | 1.2 | 1.2.10.5.3.1.2 | P | SPOT 1 (USAP) | Not Started | 7 | 0 | 2025-12-01 | 2025-12-01 |  | 0% |  |  |  | 130 |  | 2025-12-01 | 2025-12-01 | 0
1879 | 1.2 | 1.2.10.5.3.1.2.1 | C | MCAs Arrive - Pole (USAP) | Not Started | 8 | 0 | 2025-12-01 | 2025-12-01 |  | 0% |  | USAP Support |  | 127 |  | 2025-12-01 | 2025-12-01 | 0
1880 | 1.2 | 1.2.10.5.3.1.2.2 | C | Load Members Arrive - Pole (USAP) | Not Started | 8 | 0 | 2025-12-01 | 2025-12-01 |  | 0% |  | USAP Support |  | 130 |  | 2025-12-01 | 2025-12-01 | 0
1881 | 1.2 | 1.2.10.5.3.1.3 | P | SPOT 2 (USAP) | Not Started | 7 | 0 | 2025-11-25 | 2025-11-25 |  | 0% |  |  |  | 133 |  | 2025-11-25 | 2025-11-25 | 0
1882 | 1.2 | 1.2.10.5.3.1.3.1 | C | Placeholder | Not Started | 8 | 0 | 2025-11-25 | 2025-11-25 |  | 0% |  |  |  | 133 |  | 2025-11-25 | 2025-11-25 | 0
1883 | 1.2 | 1.2.10.5.3.1.4 | P | SPOT 3 (USAP) | Not Started | 7 | 0 | 2025-11-25 | 2025-11-25 |  | 0% |  |  |  | 133 |  | 2025-11-25 | 2025-11-25 | 0
1884 | 1.2 | 1.2.10.5.3.1.4.1 | C | Placeholder | Not Started | 8 | 0 | 2025-11-25 | 2025-11-25 |  | 0% |  |  |  | 133 |  | 2025-11-25 | 2025-11-25 | 0
1885 | 1.2 | 1.2.10.5.3.2 | P | MCM (USAP) | Not Started | 6 | 0 | 2025-11-01 | 2025-11-01 |  | 0% |  |  |  | 150 |  | 2025-11-01 | 2025-11-01 | 0
1886 | 1.2 | 1.2.10.5.3.2.1 | P | MCM SAAM - ComSur (USAP) | Not Started | 7 | 0 | 2025-11-01 | 2025-11-01 |  | 0% |  |  |  | 150 |  | 2025-11-01 | 2025-11-01 | 0
1887 | 1.2 | 1.2.10.5.3.2.1.1 | C | Science Crate FS3 Arrive - (USAP) | Not Started | 8 | 0 | 2025-11-01 | 2025-11-01 |  | 0% |  | USAP Support |  | 150 |  | 2025-11-01 | 2025-11-01 | 0
1888 | 1.2 | 1.2.10.5.3.2.1.2 | C | String 89-93 BCAs Arrive (McMurdo) - (USAP) | Not Started | 8 | 0 | 2025-11-01 | 2025-11-01 |  | 0% |  | USAP Support |  | 150 |  | 2025-11-01 | 2025-11-01 | 0
1889 | 1.2 | 1.2.10.5.3.2.1.3 | C | String 89-93 Sensors Arrive (Japan, USA, Europe) - (USAP) | Not Started | 8 | 0 | 2025-11-01 | 2025-11-01 |  | 0% |  | USAP Support |  | 150 |  | 2025-11-01 | 2025-11-01 | 0
1890 | 1.2 | 1.2.10.5.3.2.1.4 | C | String 89-93 Special Devices (Germany, USA) Arrive Pole - (USAP) | Not Started | 8 | 0 | 2025-11-01 | 2025-11-01 |  | 0% |  | USAP Support |  | 150 |  | 2025-11-01 | 2025-11-01 | 0
1891 | 1.2 | 1.2.10.5.3.2.1.5 | C | String 89-93 Calibration Devices (Europe, USA) - (USAP) | Not Started | 8 | 0 | 2025-11-01 | 2025-11-01 |  | 0% |  | USAP Support |  | 150 |  | 2025-11-01 | 2025-11-01 | 0
1892 | 1.2 | 1.2.10.5.3.2.1.6 | C | Dust Logger and Dust Logger Winch - (USAP) | Not Started | 8 | 0 | 2025-11-01 | 2025-11-01 |  | 0% |  | USAP Support |  | 150 |  | 2025-11-01 | 2025-11-01 | 0
1893 | 1.2 | 1.2.10.5.3.2.1.7 | C | DM-Ice (USAP) | Not Started | 8 | 0 | 2025-11-01 | 2025-11-01 |  | 0% |  |  |  | 150 |  | 2025-11-01 | 2025-11-01 | 0
1894 | 1.2 | 1.2.10.5.3.2.2 | P | Vessel (USAP) | Not Started | 7 | 0 | 2025-11-01 | 2025-11-01 |  | 0% |  |  |  | 150 |  | 2025-11-01 | 2025-11-01 | 0
1895 | 1.2 | 1.2.10.5.3.2.2.1 | C | Placeholder | Not Started | 8 | 0 | 2025-11-01 | 2025-11-01 |  | 0% |  |  |  | 150 |  | 2025-11-01 | 2025-11-01 | 0
1896 | 1.2 | 1.2.10.5.3.3 | C | Retrograde (USAP) | Not Started | 6 | 0 | 2025-02-06 | 2025-02-06 |  | 0% |  |  |  | 341 |  | 2025-02-06 | 2025-02-06 | 0
1897 | 1.2 | 1.2.10.5.3.4 | C | Cargo Storage Support Pole & MCM (USAP) | Not Started | 6 | 52d | 2025-12-01 | 2026-02-12 |  | 0% |  | USAP Support |  | 78 |  | 2025-12-01 | 2026-02-12 | 0
1898 | 1.2 | 1.2.10.5.4 | P | Pre-Installation Activities | Not Started | 5 | 19d | 2025-11-21 | 2025-12-18 |  | 0% |  |  |  | 116 |  | 2025-11-21 | 2025-12-18 | 0
1899 | 1.2 | 1.2.10.5.4.1 | C | Prep Sensor Testing Tent for SPAT & De-Berm Sleds | Not Started | 6 | 3d | 2025-11-21 | 2025-11-25 | 1864FS +1d, 1905SF -1d | 0% |  | Install Lead | 2 people (in kind), 1 day to prep tent, 2 people, 1 days to dig out sleds, work with ASC | 129 |  | 2025-11-21 | 2025-11-25 | 0
1900 | 1.2 | 1.2.10.5.4.2 | C | Prep Sensor Testing Tent for SPAT & De-Berm Sleds (USAP) | Not Started | 6 | 3d | 2025-11-21 | 2025-11-25 | 1899SS | 0% |  | USAP Support |  | 132 |  | 2025-11-21 | 2025-11-25 | 0
1901 | 1.2 | 1.2.10.5.4.3 | C | Prep Sensor Handling Facility | Not Started | 6 | 3d | 2025-11-21 | 2025-11-25 | 1864FS +1d | 0% |  | SPAT SME, Install Shift 1 | 2 people (in kind), one day, work with ASC | 131 |  | 2025-11-21 | 2025-11-25 | 0
1902 | 1.2 | 1.2.10.5.4.4 | C | On-ice Sensor Handling Training | Not Started | 6 | 1d | 2025-12-10 | 2025-12-10 | 1901, 1865FS +2d, 1515 | 0% |  | Install Lead, Install Shift 1, Install Night Shift Lead, Install Shift 2 | refresher on process, adjustment to rollers, crane practice refresher on process, adjustment to rollers, crane practice, Install Personnel Shift 1 refresher on process, adjustment to rollers, crane practice, Install Personnel Shift 2 | 122 |  | 2025-12-10 | 2025-12-10 | 0
1903 | 1.2 | 1.2.10.5.4.5 | C | Receive and Inspect MCAs & load members | Not Started | 6 | 3d | 2025-12-01 | 2025-12-03 | 1879, 2897 | 0% |  | CPT SME (Cables/SJBs), Install Lead | 2 people, 1 day | 127 |  | 2025-12-01 | 2025-12-03 | 0
1904 | 1.2 | 1.2.10.5.4.6 | C | Receive and Inspect BCAs & String 89-93 Sensors | Not Started | 6 | 2d | 2025-11-25 | 2025-11-26 | 1872, 1873 | 0% |  | Install Lead, Install Night Shift Lead | 2 people, 1 day | 131 |  | 2025-11-25 | 2025-11-26 | 0
1905 | 1.2 | 1.2.10.5.4.7 | C | Take out String 87 Sensors from Storage; Load sensor String 87 on sleds 1 & 2 | Not Started | 6 | e12h | 2025-11-21 | 2025-11-21 | 3155FS +1d | 0% |  | SPAT SME, Install Lead | oversight and direct loader, make sure pallets are lined up with AIP. 12 picks 1/2 day? | 118 |  | 2025-11-21 | 2025-11-21 | 0
1906 | 1.2 | 1.2.10.5.4.8 | C | Take out String 87 Sensors from Storage; Load sensor String 87 on sleds 1 & 2 (USAP) | Not Started | 6 | e12h | 2025-11-21 | 2025-11-21 | 1905SS | 0% |  | USAP Support |  | 134 |  | 2025-11-21 | 2025-11-21 | 0
1907 | 1.2 | 1.2.10.5.4.9 | C | SPAT String 87 | Not Started | 6 | e7d | 2025-12-02 | 2025-12-09 | 1905, 1910SF -1d | 0% |  | SPAT SME, Install Lead | 2 people at the computer (teacher/learner), then still 2 to connect/disconnect, 2x normal (2 ppl, 1 day) as first spat | 123 |  | 2025-12-02 | 2025-12-09 | 0
1908 | 1.2 | 1.2.10.5.4.10 | C | Take out String 88 Sensors from Storage; Load sensor String 88 on sleds 3 & 4 | Not Started | 6 | e12h | 2025-11-21 | 2025-11-22 | 1905 | 0% |  | SPAT SME, Install Lead | oversight and direct loader, make sure pallets are lined up with AIP. 12 picks 1/2 day? | 118 |  | 2025-11-21 | 2025-11-22 | 0
1909 | 1.2 | 1.2.10.5.4.11 | C | Take out String 88 Sensors from Storage; Load sensor String 88 on sleds 3 & 4 (USAP) | Not Started | 6 | e12h | 2025-11-21 | 2025-11-22 | 1908SS | 0% |  | USAP Support |  | 106 |  | 2025-11-21 | 2025-11-22 | 0
1910 | 1.2 | 1.2.10.5.4.12 | C | SPAT String 88 | Not Started | 6 | e7d | 2025-12-10 | 2025-12-17 | 1909, 1543SF -2d | 0% |  | SPAT SME, Install Lead | 2x12 hours shifts, 2 people | 112 |  | 2025-12-10 | 2025-12-17 | 0
1911 | 1.2 | 1.2.10.5.4.13 | C | Excavation Pit #1 | Not Started | 6 | 3d | 2025-12-15 | 2025-12-17 | 1543FF -2d | 0% |  | CPT SME (Cables/SJBs), Install Lead | 1 day, 2 people help ASC | 114 |  | 2025-12-15 | 2025-12-17 | 0
1912 | 1.2 | 1.2.10.5.4.14 | C | Excavation Pit #1 (USAP) | Not Started | 6 | 3d | 2025-12-15 | 2025-12-17 | 1911SS | 0% |  | USAP Support |  | 117 |  | 2025-12-15 | 2025-12-17 | 0
1913 | 1.2 | 1.2.10.5.4.15 | C | Dust Logger / Dust Logger Winch On-ice Test | Not Started | 6 | 5d | 2025-11-21 | 2025-11-28 | 1876SF +1d, 1864FS +1d, 1513FS +1d | 0% |  | Install Lead, PSL Driller | 1 day | 130 |  | 2025-11-21 | 2025-11-28 | 0
1914 | 1.2 | 1.2.10.5.4.16 | C | Installation Team On Ice Training and Installation Preparation | Not Started | 6 | 5d | 2025-12-08 | 2025-12-12 | 1865 | 0% |  | Install Lead, Install Night Shift Lead, Install Shift 1, Install Shift 2 | 5 days, on-ice training, preparation for installation, test of logbook | 120 |  | 2025-12-08 | 2025-12-12 | 0
1915 | 1.2 | 1.2.10.5.4.17 | C | On-Ice Readiness Review for 1st Hole Drill/Deployment | Not Started | 6 | 1d | 2025-12-18 | 2025-12-18 | 1539FF | 0% |  | Install Lead, Install Night Shift Lead, Install Shift 1, Install Shift 2 | 8 hours for 9 people | 116 |  | 2025-12-18 | 2025-12-18 | 0
1916 | 1.2 | 1.2.10.5.4.18 | C | Installation Team Ready for Deployment | Not Started | 6 | 0 | 2025-12-12 | 2025-12-12 | 1914 | 0% |  |  |  | 120 |  | 2025-12-12 | 2025-12-12 | 0
1917 | 1.2 | 1.2.10.5.5 | P | String Installation Field Activities | Not Started | 5 | 26.5d | 2025-12-09 | 2026-01-16 |  | 0% |  |  |  | 97.5 |  | 2025-12-09 | 2026-01-16 | 0
1918 | 1.2 | 1.2.10.5.5.1 | P | Installation - String 87 - Hole 1 | Not Started | 6 | 11d | 2025-12-09 | 2025-12-24 |  | 0% |  |  |  | 113 |  | 2025-12-09 | 2025-12-24 | 0
1919 | 1.2 | 1.2.10.5.5.1.1 | C | Load String 87 Sensors in Sensor Handling Facility | Not Started | 7 | e12h | 2025-12-09 | 2025-12-09 | 1515, 1907 | 0% |  | Install Night Shift Lead, Install Shift 2 | 1 person on crane,1 spotter, 1 pallet jack, 2 get DHF ready for deployment | 123 |  | 2025-12-09 | 2025-12-09 | 0
1920 | 1.2 | 1.2.10.5.5.1.2 | C | Load String 87 Special/Calibration Devices, Rigging Hardware and BCAs in Sensor Handling Facility | Not Started | 7 | e12h | 2025-12-09 | 2025-12-10 | 1919 | 0% |  | Install Lead, Install Shift 1 | All manual labor. Organize special devices and calibration devices and BCAs in TOS. One shift 9 hours, 5 people. | 123 |  | 2025-12-09 | 2025-12-10 | 0
1921 | 1.2 | 1.2.10.5.5.1.3 | C | Install String 87 / Hole 1 | Not Started | 7 | e48h | 2025-12-20 | 2025-12-22 | 1544 | 0% |  | Install Lead, Install Shift 1, Install Night Shift Lead, Install Shift 2 | 12 hours shift, day shift 4 people, 12 hours (in kind) + 3 drillers (taken into account in 1.2.8), night shift 5 people, 12 hours (in kind) + 3 drillers (taken into account in 1.2.8) | 0 | TRUE | 2025-12-20 | 2025-12-22 | 0
1922 | 1.2 | 1.2.10.5.5.1.4 | C | Install String 87 / Hole 1 Complete | Not Started | 7 | 0 | 2025-12-22 | 2025-12-22 | 1921 | 0% |  |  |  | 0 | TRUE | 2025-12-22 | 2025-12-22 | 0
1923 | 1.2 | 1.2.10.5.5.1.5 | C | Anchor String 87 / Hole 1 | Not Started | 7 | e1h | 2025-12-22 | 2025-12-22 | 1922 | 0% |  | Install Lead | 1 hour: 1 person setting anchor, 1 person driving TU-20 | 21 |  | 2025-12-22 | 2025-12-22 | 0
1924 | 1.2 | 1.2.10.5.5.1.6 | C | TOS Clean Up - Wait 12 hours for Anchor to Set | Not Started | 7 | e12h | 2025-12-22 | 2025-12-23 | 1923 | 0% |  | Install Shift 1 |  | 21 |  | 2025-12-22 | 2025-12-23 | 0
1925 | 1.2 | 1.2.10.5.5.1.7 | C | String 87 / Hole 1 Cable drag | Not Started | 7 | e4h | 2025-12-23 | 2025-12-23 | 1924 | 0% |  | Install Shift 1 | 6 people, 4 hours | 21 |  | 2025-12-23 | 2025-12-23 | 0
1926 | 1.2 | 1.2.10.5.5.1.8 | C | Trench Hole 1 / String 87 to Pit #1 | Not Started | 7 | e4h | 2025-12-23 | 2025-12-23 | 1550 | 0% |  | CPT SME (Cables/SJBs) |  | 113 |  | 2025-12-23 | 2025-12-23 | 0
1927 | 1.2 | 1.2.10.5.5.1.9 | C | Trench Hole 1 / String 87 to Pit #1 (USAP) | Not Started | 7 | e4h | 2025-12-23 | 2025-12-23 | 1926SS | 0% |  | USAP Support |  | 113 |  | 2025-12-23 | 2025-12-23 | 0
1928 | 1.2 | 1.2.10.5.5.1.10 | C | Connect in-ice Cable to SJB 87 in Pit #1 | Not Started | 7 | e4h | 2025-12-23 | 2025-12-24 | 1927 | 0% |  | CPT SME (Cables/SJBs) | 4 hr | 113 |  | 2025-12-23 | 2025-12-24 | 0
1929 | 1.2 | 1.2.10.5.5.1.11 | C | Backfill Hole 1 / String 87 to Pit #1 | Not Started | 7 | e4h | 2025-12-24 | 2025-12-24 | 1928 | 0% |  | CPT SME (Cables/SJBs) |  | 113 |  | 2025-12-24 | 2025-12-24 | 0
1930 | 1.2 | 1.2.10.5.5.1.12 | C | Backfill Hole 1 / String 87 to Pit #1 (USAP) | Not Started | 7 | e4h | 2025-12-24 | 2025-12-24 | 1929SS | 0% |  | USAP Support |  | 113 |  | 2025-12-24 | 2025-12-24 | 0
1931 | 1.2 | 1.2.10.5.5.1.13 | C | Load Sensor String 89 (Hole 3) on Sleds 1 & 2 | Not Started | 7 | e4h | 2025-12-20 | 2025-12-21 | 1921SS | 0% |  | SPAT SME | 4h spotter for USAP | 113 |  | 2025-12-20 | 2025-12-21 | 0
1932 | 1.2 | 1.2.10.5.5.1.14 | C | Load Sensor String 89 (Hole 3) on Sleds 1 & 2 (USAP) | Not Started | 7 | e4h | 2025-12-20 | 2025-12-21 | 1931SS | 0% |  | USAP Support |  | 113 |  | 2025-12-20 | 2025-12-21 | 0
1933 | 1.2 | 1.2.10.5.5.1.15 | C | SPAT String 89 | Not Started | 7 | e72h | 2025-12-21 | 2025-12-24 | 1932 | 0% |  | SPAT SME |  | 113 |  | 2025-12-21 | 2025-12-24 | 0
1934 | 1.2 | 1.2.10.5.5.2 | P | Installation - String 88 - Hole 2 | Not Started | 6 | 4d | 2025-12-22 | 2025-12-30 |  | 0% |  |  |  | 110 |  | 2025-12-22 | 2025-12-30 | 0
1935 | 1.2 | 1.2.10.5.5.2.1 | C | Load String 88 Sensors in Sensor Handling Facility | Not Started | 7 | e12h | 2025-12-22 | 2025-12-23 | 1548, 1910 | 0% |  | Install Lead, Install Shift 1 |  | 113 |  | 2025-12-22 | 2025-12-23 | 0
1936 | 1.2 | 1.2.10.5.5.2.2 | C | Load String 88 Calibration/Special Devices & BCAs in Sensor Handling Facility | Not Started | 7 | e12h | 2025-12-23 | 2025-12-23 | 1935 | 0% |  | Install Night Shift Lead, Install Shift 2 |  | 113 |  | 2025-12-23 | 2025-12-23 | 0
1937 | 1.2 | 1.2.10.5.5.2.3 | C | Install String 88 / Hole 2 | Not Started | 7 | e24h | 2025-12-26 | 2025-12-27 | 1559 | 0% |  | Install Lead, Install Shift 1, Install Night Shift Lead, Install Shift 2 |  | 21 |  | 2025-12-26 | 2025-12-27 | 0
1938 | 1.2 | 1.2.10.5.5.2.4 | C | Install String 88 / Hole 2 Complete | Not Started | 7 | 0 | 2025-12-27 | 2025-12-27 | 1937 | 0% |  |  |  | 21 |  | 2025-12-27 | 2025-12-27 | 0
1939 | 1.2 | 1.2.10.5.5.2.5 | C | Anchor String 88 / Hole 2 | Not Started | 7 | e1h | 2025-12-27 | 2025-12-27 | 1938 | 0% |  | Install Lead |  | 21 |  | 2025-12-27 | 2025-12-27 | 0
1940 | 1.2 | 1.2.10.5.5.2.6 | C | TOS Clean Up - Wait 12 hours for Anchor to Set | Not Started | 7 | e12h | 2025-12-27 | 2025-12-28 | 1939 | 0% |  | Install Shift 1 |  | 21 |  | 2025-12-27 | 2025-12-28 | 0
1941 | 1.2 | 1.2.10.5.5.2.7 | C | Christmas Break | Not Started | 7 | e24h | 2025-12-27 | 2025-12-28 | 1940SS | 0% |  | Install Shift 1 |  | 21 |  | 2025-12-27 | 2025-12-28 | 0
1942 | 1.2 | 1.2.10.5.5.2.8 | C | String 88 / Hole 2 Cable drag | Not Started | 7 | e2h | 2025-12-28 | 2025-12-29 | 1941 | 0% |  | Install Shift 1 |  | 110.875 |  | 2025-12-28 | 2025-12-29 | 0
1943 | 1.2 | 1.2.10.5.5.2.9 | C | Trench Hole 2 / String 88 to Pit #1 | Not Started | 7 | e4h | 2025-12-29 | 2025-12-29 | 1567 | 0% |  | CPT SME (Cables/SJBs) |  | 109.375 |  | 2025-12-29 | 2025-12-29 | 0
1944 | 1.2 | 1.2.10.5.5.2.10 | C | Trench Hole 2 / String 88 to Pit #1 (USAP) | Not Started | 7 | e4h | 2025-12-29 | 2025-12-29 | 1943SS | 0% |  | USAP Support |  | 109.75 |  | 2025-12-29 | 2025-12-29 | 0
1945 | 1.2 | 1.2.10.5.5.2.11 | C | Connect in-ice Cable to SJB 88 in Pit #1 | Not Started | 7 | e4h | 2025-12-29 | 2025-12-29 | 1944 | 0% |  | CPT SME (Cables/SJBs) |  | 109.75 |  | 2025-12-29 | 2025-12-29 | 0
1946 | 1.2 | 1.2.10.5.5.2.12 | C | Backfill Hole 2 / String 88 to Pit #1 | Not Started | 7 | e4h | 2025-12-29 | 2025-12-29 | 1945 | 0% |  | CPT SME (Cables/SJBs) |  | 109.75 |  | 2025-12-29 | 2025-12-29 | 0
1947 | 1.2 | 1.2.10.5.5.2.13 | C | Backfill Hole 2 / String 88 to Pit #1 (USAP) | Not Started | 7 | e4h | 2025-12-29 | 2025-12-29 | 1946SS | 0% |  | USAP Support |  | 110 |  | 2025-12-29 | 2025-12-29 | 0
1948 | 1.2 | 1.2.10.5.5.2.14 | C | Load sensor String 90 (Hole 4) on sleds 3,4 | Not Started | 7 | e4h | 2025-12-26 | 2025-12-27 | 1937SS | 0% |  | SPAT SME |  | 109 |  | 2025-12-26 | 2025-12-27 | 0
1949 | 1.2 | 1.2.10.5.5.2.15 | C | Load sensor String 90 (Hole 4) on sleds 3,4 (USAP) | Not Started | 7 | e4h | 2025-12-26 | 2025-12-27 | 1948SS | 0% |  | USAP Support |  | 109 |  | 2025-12-26 | 2025-12-27 | 0
1950 | 1.2 | 1.2.10.5.5.2.16 | C | SPAT String 90 | Not Started | 7 | e72h | 2025-12-27 | 2025-12-30 | 1949 | 0% |  | SPAT SME |  | 109 |  | 2025-12-27 | 2025-12-30 | 0
1951 | 1.2 | 1.2.10.5.5.3 | P | Installation - String 89 - Hole 3 | Not Started | 6 | 3d | 2025-12-27 | 2026-01-01 |  | 0% |  |  |  | 108 |  | 2025-12-27 | 2026-01-01 | 0
1952 | 1.2 | 1.2.10.5.5.3.1 | C | Load String 89 (Hole 3) Sensors in Sensor Handling Facility | Not Started | 7 | e12h | 2025-12-27 | 2025-12-28 | 1563, 1933 | 0% |  | Installation Team |  | 111 |  | 2025-12-27 | 2025-12-28 | 0
1953 | 1.2 | 1.2.10.5.5.3.2 | C | Load String 89 (Hole 3) Calibration/Special Devices & BCAs in Sensor Handling Facility | Not Started | 7 | e12h | 2025-12-28 | 2025-12-28 | 1952 | 0% |  | Install Night Shift Lead, Install Shift 2 |  | 111 |  | 2025-12-28 | 2025-12-28 | 0
1954 | 1.2 | 1.2.10.5.5.3.3 | C | Install String 89 / Hole 3 | Not Started | 7 | e24h | 2025-12-29 | 2025-12-30 | 1573 | 0% |  | Installation Team |  | 21 |  | 2025-12-29 | 2025-12-30 | 0
1955 | 1.2 | 1.2.10.5.5.3.4 | C | Install String 89 / Hole 3 Complete | Not Started | 7 | 0 | 2025-12-30 | 2025-12-30 | 1954 | 0% |  |  |  | 21 |  | 2025-12-30 | 2025-12-30 | 0
1956 | 1.2 | 1.2.10.5.5.3.5 | C | Anchor String 89 / Hole 3 | Not Started | 7 | e1h | 2025-12-30 | 2025-12-30 | 1955 | 0% |  | Installation Team |  | 21 |  | 2025-12-30 | 2025-12-30 | 0
1957 | 1.2 | 1.2.10.5.5.3.6 | C | TOS Clean Up - Wait 12 hours for Anchor to Set | Not Started | 7 | e12h | 2025-12-30 | 2025-12-31 | 1956 | 0% |  | Install Shift 1 |  | 21 |  | 2025-12-30 | 2025-12-31 | 0
1958 | 1.2 | 1.2.10.5.5.3.7 | C | String 89 / Hole 3 Cable drag | Not Started | 7 | e4h | 2025-12-31 | 2025-12-31 | 1957 | 0% |  | Install Shift 1 |  | 21 |  | 2025-12-31 | 2025-12-31 | 0
1959 | 1.2 | 1.2.10.5.5.3.8 | C | Trench Hole 3 / String 89 to Pit #1 | Not Started | 7 | e4h | 2025-12-31 | 2025-12-31 | 1581 | 0% |  | CPT SME |  | 107.625 |  | 2025-12-31 | 2025-12-31 | 0
1960 | 1.2 | 1.2.10.5.5.3.9 | C | Trench Hole 3 / String 89 to Pit #1 (USAP) | Not Started | 7 | e4h | 2025-12-31 | 2025-12-31 | 1959SS | 0% |  | USAP Support |  | 108 |  | 2025-12-31 | 2025-12-31 | 0
1961 | 1.2 | 1.2.10.5.5.3.10 | C | Connect in-ice cable to SJB 89 in Pit #1 | Not Started | 7 | e4h | 2025-12-31 | 2025-12-31 | 1960 | 0% |  | Installation Personnel |  | 108 |  | 2025-12-31 | 2025-12-31 | 0
1962 | 1.2 | 1.2.10.5.5.3.11 | C | Backfill Hole 3 / String 89 to Pit #1 | Not Started | 7 | e4h | 2025-12-31 | 2025-12-31 | 1961 | 0% |  | Installation Personnel |  | 108 |  | 2025-12-31 | 2025-12-31 | 0
1963 | 1.2 | 1.2.10.5.5.3.12 | C | Backfill Hole 3 / String 89 to Pit #1 (USAP) | Not Started | 7 | e4h | 2025-12-31 | 2025-12-31 | 1962SS | 0% |  | USAP Support |  | 108 |  | 2025-12-31 | 2025-12-31 | 0
1964 | 1.2 | 1.2.10.5.5.3.13 | C | Load sensor String 91 (Hole 5) on sleds 1 & 2 | Not Started | 7 | e4h | 2025-12-29 | 2025-12-29 | 1954SS | 0% |  | SPAT SME |  | 107.125 |  | 2025-12-29 | 2025-12-29 | 0
1965 | 1.2 | 1.2.10.5.5.3.14 | C | Load sensor String 91 (Hole 5) on sleds 1 & 2 (USAP) | Not Started | 7 | e4h | 2025-12-29 | 2025-12-29 | 1964SS | 0% |  | USAP Support |  | 110 |  | 2025-12-29 | 2025-12-29 | 0
1966 | 1.2 | 1.2.10.5.5.3.15 | C | SPAT String 91 | Not Started | 7 | e72h | 2025-12-29 | 2026-01-01 | 1964 | 0% |  | SPAT SME |  | 107.125 |  | 2025-12-29 | 2026-01-01 | 0
1967 | 1.2 | 1.2.10.5.5.4 | P | Installation - String 90 - Hole 4 | Not Started | 6 | 4.25d | 2025-12-30 | 2026-01-06 |  | 0% |  |  |  | 105 |  | 2025-12-30 | 2026-01-06 | 0
1968 | 1.2 | 1.2.10.5.5.4.1 | C | Load String 90 (Hole 4) Sensors in Sensor Handling Facility | Not Started | 7 | e12h | 2025-12-30 | 2025-12-31 | 1577, 1950 | 0% |  | Installation Personnel |  | 108.25 |  | 2025-12-30 | 2025-12-31 | 0
1969 | 1.2 | 1.2.10.5.5.4.2 | C | Load String 90 (Hole 4) Calibration/Special Devices & BCAs in Sensor Handling Facility | Not Started | 7 | e12h | 2025-12-31 | 2025-12-31 | 1968 | 0% |  | Install Night Shift Lead, Install Shift 2 |  | 108.25 |  | 2025-12-31 | 2025-12-31 | 0
1970 | 1.2 | 1.2.10.5.5.4.3 | C | Install String 90 | Not Started | 7 | e24h | 2026-01-03 | 2026-01-04 | 1588 | 0% |  | Installation Personnel |  | 103 |  | 2026-01-03 | 2026-01-04 | 0
1971 | 1.2 | 1.2.10.5.5.4.4 | C | Install String 90 / Hole 4 Complete | Not Started | 7 | 0 | 2026-01-04 | 2026-01-04 | 1970 | 0% |  |  |  | 104.625 |  | 2026-01-04 | 2026-01-04 | 0
1972 | 1.2 | 1.2.10.5.5.4.5 | C | Anchor String 90 / Hole 4 | Not Started | 7 | e1h | 2026-01-04 | 2026-01-04 | 1971 | 0% |  | Installation Personnel |  | 105.125 |  | 2026-01-04 | 2026-01-04 | 0
1973 | 1.2 | 1.2.10.5.5.4.6 | C | TOS Clean Up - Wait 12 hours for Anchor to Set | Not Started | 7 | e12h | 2026-01-04 | 2026-01-05 | 1972 | 0% |  | Install Shift 1 |  | 105.5 |  | 2026-01-04 | 2026-01-05 | 0
1974 | 1.2 | 1.2.10.5.5.4.7 | C | String 90 / Hole 4 Cable drag | Not Started | 7 | e4h | 2026-01-05 | 2026-01-05 | 1973 | 0% |  | Install Shift 1 |  | 105.625 |  | 2026-01-05 | 2026-01-05 | 0
1975 | 1.2 | 1.2.10.5.5.4.8 | C | Trench Hole 4 / String 90 to Pit #1 | Not Started | 7 | e4h | 2026-01-05 | 2026-01-05 | 1596 | 0% |  | CPT SME |  | 105.75 |  | 2026-01-05 | 2026-01-05 | 0
1976 | 1.2 | 1.2.10.5.5.4.9 | C | Trench Hole 4 / String 90 to Pit #1 (USAP) | Not Started | 7 | e4h | 2026-01-05 | 2026-01-05 | 1975SS | 0% |  | USAP Support |  | 106.125 |  | 2026-01-05 | 2026-01-05 | 0
1977 | 1.2 | 1.2.10.5.5.4.10 | C | Connect in-ice cable to SJB 90 in Pit #1 | Not Started | 7 | e4h | 2026-01-05 | 2026-01-05 | 1975 | 0% |  | CPT SME |  | 106 |  | 2026-01-05 | 2026-01-05 | 0
1978 | 1.2 | 1.2.10.5.5.4.11 | C | Backfill Hole 4 / String 90 to Pit #1 | Not Started | 7 | e4h | 2026-01-05 | 2026-01-05 | 1977 | 0% |  | CPT SME |  | 106 |  | 2026-01-05 | 2026-01-05 | 0
1979 | 1.2 | 1.2.10.5.5.4.12 | C | Backfill Hole 4 / String 90 to Pit #1 (USAP) | Not Started | 7 | e4h | 2026-01-05 | 2026-01-05 | 1978SS | 0% |  | USAP Support |  | 106 |  | 2026-01-05 | 2026-01-05 | 0
1980 | 1.2 | 1.2.10.5.5.4.13 | C | Backfill, Remove Temp Vault, Flag and Survey Pit #1 | Not Started | 7 | e4h | 2026-01-05 | 2026-01-05 | 1978SS | 0% |  | CPT SME |  | 106 |  | 2026-01-05 | 2026-01-05 | 0
1981 | 1.2 | 1.2.10.5.5.4.14 | C | Backfill, Remove Temp Vault, Flag and Survey Pit #1 (USAP) | Not Started | 7 | e4h | 2026-01-05 | 2026-01-05 | 1980SS | 0% |  | USAP Support |  | 106 |  | 2026-01-05 | 2026-01-05 | 0
1982 | 1.2 | 1.2.10.5.5.4.15 | C | Load Sensor String 92 (Hole 6) on Sleds 3 & 4 | Not Started | 7 | e4h | 2026-01-03 | 2026-01-03 | 1970SS | 0% |  | SPAT SME |  | 103.75 |  | 2026-01-03 | 2026-01-03 | 0
1983 | 1.2 | 1.2.10.5.5.4.16 | C | Load Sensor String 92 (Hole 6) on sleds 3 & 4 (USAP) | Not Started | 7 | e4h | 2026-01-03 | 2026-01-03 | 1982SS | 0% |  | USAP Support |  | 104 |  | 2026-01-03 | 2026-01-03 | 0
1984 | 1.2 | 1.2.10.5.5.4.17 | C | SPAT String 92 | Not Started | 7 | e72h | 2026-01-03 | 2026-01-06 | 1983 | 0% |  | SPAT SME |  | 104 |  | 2026-01-03 | 2026-01-06 | 0
1985 | 1.2 | 1.2.10.5.5.5 | P | Installation - String 91 - Hole 5 | Not Started | 6 | 4.5d | 2026-01-04 | 2026-01-09 |  | 0% |  |  |  | 102.625 |  | 2026-01-04 | 2026-01-09 | 0
1986 | 1.2 | 1.2.10.5.5.5.1 | C | Excavation Pit #2 (Assist) | Not Started | 7 | e8h | 2026-01-06 | 2026-01-06 | 1981 | 0% |  | Installation Personnel |  | 106 |  | 2026-01-06 | 2026-01-06 | 0
1987 | 1.2 | 1.2.10.5.5.5.2 | C | Excavation Pit #2 (USAP) | Not Started | 7 | e8h | 2026-01-06 | 2026-01-06 | 1986SS | 0% |  | USAP Support |  | 106 |  | 2026-01-06 | 2026-01-06 | 0
1988 | 1.2 | 1.2.10.5.5.5.3 | C | Load String 91 (Hole 5) Sensors in Sensor Handling Facility | Not Started | 7 | e12h | 2026-01-04 | 2026-01-05 | 1592, 1966 | 0% |  | Installation Personnel |  | 106.125 |  | 2026-01-04 | 2026-01-05 | 0
1989 | 1.2 | 1.2.10.5.5.5.4 | C | Load String 91 (Hole 5) Calibration/Special Devices & BCAs in Sensor Handling Facility | Not Started | 7 | e12h | 2026-01-05 | 2026-01-05 | 1988 | 0% |  | Install Night Shift Lead, Install Shift 2 |  | 106.125 |  | 2026-01-05 | 2026-01-05 | 0
1990 | 1.2 | 1.2.10.5.5.5.5 | C | Install String 91 / Hole 5 | Not Started | 7 | e24h | 2026-01-06 | 2026-01-07 | 1602 | 0% |  | Installation Personnel |  | 21 |  | 2026-01-06 | 2026-01-07 | 0
1991 | 1.2 | 1.2.10.5.5.5.6 | C | Install String 91 / Hole 5 Complete | Not Started | 7 | 0 | 2026-01-07 | 2026-01-07 | 1990 | 0% |  |  |  | 21 |  | 2026-01-07 | 2026-01-07 | 0
1992 | 1.2 | 1.2.10.5.5.5.7 | C | Anchor String 91 / Hole 5 | Not Started | 7 | e1h | 2026-01-07 | 2026-01-07 | 1991 | 0% |  | Installation Personnel |  | 21 |  | 2026-01-07 | 2026-01-07 | 0
1993 | 1.2 | 1.2.10.5.5.5.8 | C | TOS Clean Up - Wait 12 hours for Anchor to Set | Not Started | 7 | e12h | 2026-01-07 | 2026-01-07 | 1992 | 0% |  | Install Shift 1 |  | 21 |  | 2026-01-07 | 2026-01-07 | 0
1994 | 1.2 | 1.2.10.5.5.5.9 | C | String 91 / Hole 5 Cable drag | Not Started | 7 | e4h | 2026-01-07 | 2026-01-07 | 1993 | 0% |  | Install Shift 1 |  | 21 |  | 2026-01-07 | 2026-01-07 | 0
1995 | 1.2 | 1.2.10.5.5.5.10 | C | Trench Hole 5 / String 91 to Pit #2 | Not Started | 7 | e4h | 2026-01-08 | 2026-01-08 | 1611 | 0% |  | 1.4 CPT (Cables, SJBs), Installation Personnel |  | 102.75 |  | 2026-01-08 | 2026-01-08 | 0
1996 | 1.2 | 1.2.10.5.5.5.11 | C | Trench Hole 5 / String 91 to Pit #2 (USAP) | Not Started | 7 | e4h | 2026-01-08 | 2026-01-08 | 1995SS | 0% |  | USAP Support |  | 104 |  | 2026-01-08 | 2026-01-08 | 0
1997 | 1.2 | 1.2.10.5.5.5.12 | C | Connect in-ice Cable to SJB 91 in Pit #2 | Not Started | 7 | e4h | 2026-01-08 | 2026-01-08 | 1995 | 0% |  | 1.4 CPT (Cables, SJBs) |  | 102.75 |  | 2026-01-08 | 2026-01-08 | 0
1998 | 1.2 | 1.2.10.5.5.5.13 | C | Backfill Hole 5 / String 91 to Pit #2 | Not Started | 7 | e4h | 2026-01-08 | 2026-01-08 | 1997 | 0% |  | 1.4 CPT (Cables, SJBs), Installation Personnel |  | 102.75 |  | 2026-01-08 | 2026-01-08 | 0
1999 | 1.2 | 1.2.10.5.5.5.14 | C | Backfill Hole 5 / String 91 to Pit #2 (USAP) | Not Started | 7 | e4h | 2026-01-08 | 2026-01-08 | 1998SS | 0% |  | USAP Support |  | 103.125 |  | 2026-01-08 | 2026-01-08 | 0
2000 | 1.2 | 1.2.10.5.5.5.15 | C | Load Sensor String 93 (Hole 7) on Sleds 3 & 4 | Not Started | 7 | e4h | 2026-01-06 | 2026-01-06 | 1990SS | 0% |  | 1.6 SPAT SME, Installation Personnel |  | 101.625 |  | 2026-01-06 | 2026-01-06 | 0
2001 | 1.2 | 1.2.10.5.5.5.16 | C | Load Sensor String 93 (Hole 7) on Sleds 3 & 4 (USAP) | Not Started | 7 | e4h | 2026-01-06 | 2026-01-06 | 2000SS | 0% |  | USAP Support |  | 105.625 |  | 2026-01-06 | 2026-01-06 | 0
2002 | 1.2 | 1.2.10.5.5.5.17 | C | SPAT String 93 | Not Started | 7 | e72h | 2026-01-06 | 2026-01-09 | 2000 | 0% |  | 1.6 SPAT SME, Installation Personnel |  | 101.625 |  | 2026-01-06 | 2026-01-09 | 0
2003 | 1.2 | 1.2.10.5.5.6 | P | Installation - String 92 - Hole 6 | Not Started | 6 | 5d | 2026-01-07 | 2026-01-14 |  | 0% |  |  |  | 100 |  | 2026-01-07 | 2026-01-14 | 0
2004 | 1.2 | 1.2.10.5.5.6.1 | C | Load String 92 (Hole 6) Sensors in Sensor Handling Facility | Not Started | 7 | e12h | 2026-01-07 | 2026-01-07 | 1606, 1984 | 0% |  | Installation Personnel |  | 104 |  | 2026-01-07 | 2026-01-07 | 0
2005 | 1.2 | 1.2.10.5.5.6.2 | C | Load String 92 (Hole 6) Calibration/Special Devices & BCAs in Sensor Handling Facility | Not Started | 7 | e12h | 2026-01-07 | 2026-01-08 | 2004 | 0% |  | Install Night Shift Lead, Install Shift 2 |  | 104 |  | 2026-01-07 | 2026-01-08 | 0
2006 | 1.2 | 1.2.10.5.5.6.3 | C | Set-up Logging Winch | Not Started | 7 | e4h | 2026-01-11 | 2026-01-11 | 1617FF | 0% |  | Installation Personnel |  | 103 |  | 2026-01-11 | 2026-01-11 | 0
2007 | 1.2 | 1.2.10.5.5.6.4 | C | Dust Logging | Not Started | 7 | e12h | 2026-01-11 | 2026-01-11 | 1617 | 0% |  | Installation Personnel |  | 48 |  | 2026-01-11 | 2026-01-11 | 0
2008 | 1.2 | 1.2.10.5.5.6.5 | C | Dust Logging Complete | Not Started | 7 | 0 | 2026-01-11 | 2026-01-11 | 2007 | 0% |  |  |  | 48 |  | 2026-01-11 | 2026-01-11 | 0
2009 | 1.2 | 1.2.10.5.5.6.6 | C | Install String 92 / Hole 6 | Not Started | 7 | e24h | 2026-01-11 | 2026-01-12 | 2008 | 0% |  | Installation Personnel |  | 98.75 |  | 2026-01-11 | 2026-01-12 | 0
2010 | 1.2 | 1.2.10.5.5.6.7 | C | Install String 92 / Hole 6 Complete | Not Started | 7 | 0 | 2026-01-12 | 2026-01-12 | 2009 | 0% |  |  |  | 98.75 |  | 2026-01-12 | 2026-01-12 | 0
2011 | 1.2 | 1.2.10.5.5.6.8 | C | Anchor String 92 / Hole 6 | Not Started | 7 | e1h | 2026-01-12 | 2026-01-12 | 2010 | 0% |  | Installation Personnel |  | 98.75 |  | 2026-01-12 | 2026-01-12 | 0
2012 | 1.2 | 1.2.10.5.5.6.9 | C | TOS Clean Up - Wait 12 hours for Anchor to Set | Not Started | 7 | e12h | 2026-01-12 | 2026-01-13 | 2011 | 0% |  | Install Shift 1 |  | 99.125 |  | 2026-01-12 | 2026-01-13 | 0
2013 | 1.2 | 1.2.10.5.5.6.10 | C | String 92 / Hole 6 Cable drag | Not Started | 7 | e4h | 2026-01-13 | 2026-01-13 | 2012 | 0% |  | Install Shift 1 |  | 99.125 |  | 2026-01-13 | 2026-01-13 | 0
2014 | 1.2 | 1.2.10.5.5.6.11 | C | Trench Hole 6 / String 92 to Pit #2 | Not Started | 7 | e4h | 2026-01-13 | 2026-01-13 | 1623 | 0% |  | CPT SME |  | 100 |  | 2026-01-13 | 2026-01-13 | 0
2015 | 1.2 | 1.2.10.5.5.6.12 | C | Trench Hole 6 / String 92 to Pit #2 (USAP) | Not Started | 7 | e4h | 2026-01-13 | 2026-01-13 | 2014SS | 0% |  | USAP Support |  | 100 |  | 2026-01-13 | 2026-01-13 | 0
2016 | 1.2 | 1.2.10.5.5.6.13 | C | Connect in-ice Cable to SJB 92 in Pit #2 | Not Started | 7 | e4h | 2026-01-13 | 2026-01-14 | 2014 | 0% |  | CPT SME |  | 100 |  | 2026-01-13 | 2026-01-14 | 0
2017 | 1.2 | 1.2.10.5.5.6.14 | C | Backfill Hole 6 / String 92 to Pit #2 | Not Started | 7 | e4h | 2026-01-14 | 2026-01-14 | 2016 | 0% |  | CPT SME |  | 100 |  | 2026-01-14 | 2026-01-14 | 0
2018 | 1.2 | 1.2.10.5.5.6.15 | C | Backfill Hole 6 / String 92 to Pit #2 (USAP) | Not Started | 7 | e4h | 2026-01-14 | 2026-01-14 | 2017SS | 0% |  | USAP Support |  | 100 |  | 2026-01-14 | 2026-01-14 | 0
2019 | 1.2 | 1.2.10.5.5.7 | P | Installation - String 93 - Hole 7 | Not Started | 6 | 3.5d | 2026-01-12 | 2026-01-16 |  | 0% |  |  |  | 97.5 |  | 2026-01-12 | 2026-01-16 | 0
2020 | 1.2 | 1.2.10.5.5.7.1 | C | Load String 93 (Hole 7) Sensors into Sensor Handling Facility | Not Started | 7 | e12h | 2026-01-12 | 2026-01-13 | 1622, 2002 | 0% |  | Install Lead, Install Shift 1 |  | 100 |  | 2026-01-12 | 2026-01-13 | 0
2021 | 1.2 | 1.2.10.5.5.7.2 | C | Load String 93 (Hole 7) Calibration/Special Devices & BCAs in Sensor Handling Facility | Not Started | 7 | e12h | 2026-01-13 | 2026-01-13 | 2020 | 0% |  | Install Night Shift Lead, Install Shift 2 |  | 100 |  | 2026-01-13 | 2026-01-13 | 0
2022 | 1.2 | 1.2.10.5.5.7.3 | C | Install String 93 / Hole 7 | Not Started | 7 | e24h | 2026-01-14 | 2026-01-14 | 1627 | 0% |  | Installation Personnel |  | 21 |  | 2026-01-14 | 2026-01-14 | 0
2023 | 1.2 | 1.2.10.5.5.7.4 | C | Install String 93 / Hole 7 Complete | Not Started | 7 | 0 | 2026-01-14 | 2026-01-14 | 2022 | 0% |  |  |  | 21 |  | 2026-01-14 | 2026-01-14 | 0
2024 | 1.2 | 1.2.10.5.5.7.5 | C | Anchor String 93 / Hole 7 | Not Started | 7 | e1h | 2026-01-15 | 2026-01-15 | 2023 | 0% |  | Tosi |  | 21 |  | 2026-01-15 | 2026-01-15 | 0
2025 | 1.2 | 1.2.10.5.5.7.6 | C | TOS Clean Up - Wait 12 hours for Anchor to Set | Not Started | 7 | e12h | 2026-01-15 | 2026-01-15 | 2024 | 0% |  | Install Shift 2 |  | 21 |  | 2026-01-15 | 2026-01-15 | 0
2026 | 1.2 | 1.2.10.5.5.7.7 | C | String 93 / Hole 7 Cable drag | Not Started | 7 | e4h | 2026-01-15 | 2026-01-15 | 2025 | 0% |  | Install Shift 1 |  | 21 |  | 2026-01-15 | 2026-01-15 | 0
2027 | 1.2 | 1.2.10.5.5.7.8 | C | Trench Hole 7 / String 93 to Pit #2 | Not Started | 7 | e4h | 2026-01-16 | 2026-01-16 | 1629 | 0% |  | 1.4 CPT (Cables, SJBs), Installation Personnel |  | 91.875 |  | 2026-01-16 | 2026-01-16 | 0
2028 | 1.2 | 1.2.10.5.5.7.9 | C | Trench Hole 7 / String 93 to Pit #2 (USAP) | Not Started | 7 | e4h | 2026-01-16 | 2026-01-16 | 2027SS | 0% |  | USAP Support |  | 98 |  | 2026-01-16 | 2026-01-16 | 0
2029 | 1.2 | 1.2.10.5.5.7.10 | C | Connect in-ice Cable to SJB 93 in Pit #2 | Not Started | 7 | e4h | 2026-01-16 | 2026-01-16 | 2027 | 0% |  | 1.4 CPT (Cables, SJBs) |  | 91.875 |  | 2026-01-16 | 2026-01-16 | 0
2030 | 1.2 | 1.2.10.5.5.7.11 | C | Backfill Hole 7 / String 93 to Pit #2 | Not Started | 7 | e4h | 2026-01-16 | 2026-01-16 | 2029 | 0% |  | Installation Personnel |  | 96.75 |  | 2026-01-16 | 2026-01-16 | 0
2031 | 1.2 | 1.2.10.5.5.7.12 | C | Backfill Hole 7 / String 93 to Pit #2 (USAP) | Not Started | 7 | e4h | 2026-01-16 | 2026-01-16 | 2030SS | 0% |  | USAP Support |  | 97.5 |  | 2026-01-16 | 2026-01-16 | 0
2032 | 1.2 | 1.2.10.5.5.7.13 | C | Backfill, Remove Temp Vault, Flag and Survey Pit #2 | Not Started | 7 | e4h | 2026-01-16 | 2026-01-16 | 2030SS | 0% |  | 1.4 CPT (Cables, SJBs), Installation Personnel |  | 97.125 |  | 2026-01-16 | 2026-01-16 | 0
2033 | 1.2 | 1.2.10.5.5.7.14 | C | Backfill, Remove Temp Vault, Flag and Survey Pit #2 (USAP) | Not Started | 7 | e4h | 2026-01-16 | 2026-01-16 | 2032SS | 0% |  | USAP Support |  | 97.5 |  | 2026-01-16 | 2026-01-16 | 0
2034 | 1.2 | 1.2.10.5.6 | P | String Installation ICL Activities | Not Started | 5 | 31d | 2025-12-05 | 2026-01-20 |  | 0% |  |  |  | 95 |  | 2025-12-05 | 2026-01-20 | 0
2035 | 1.2 | 1.2.10.5.6.1 | C | M&O/Upgrade liaison [ongoing] | Not Started | 6 | 31d | 2025-12-07 | 2026-01-20 |  | 0% |  |  |  | 95 |  | 2025-12-07 | 2026-01-20 | 0
2036 | 1.2 | 1.2.10.5.6.2 | C | Update CPT installation firmware, software (pre-deployment) [1.5 days] | Not Started | 6 | 1.5d | 2025-12-18 | 2025-12-19 | 2037SF | 0% |  |  |  | 115.5 |  | 2025-12-18 | 2025-12-19 | 0
2037 | 1.2 | 1.2.10.5.6.3 | C | Final DOM power system configuration (pre-deployment) [0.5 day] | Not Started | 6 | 0.5d | 2025-12-19 | 2025-12-19 | 2038SF | 0% |  |  |  | 113.5 |  | 2025-12-19 | 2025-12-19 | 0
2038 | 1.2 | 1.2.10.5.6.4 | C | CPT final pre-deployment checkout [1 day] | Not Started | 6 | 1d | 2025-12-22 | 2025-12-22 | 1922SF | 0% |  |  |  | 112 |  | 2025-12-22 | 2025-12-22 | 0
2039 | 1.2 | 1.2.10.5.6.5 | C | Low-level Communications and Timing Commissioning: String 87 | Not Started | 6 | 3d | 2025-12-23 | 2025-12-26 | 1922 | 0% |  |  |  | 111 |  | 2025-12-23 | 2025-12-26 | 0
2040 | 1.2 | 1.2.10.5.6.6 | C | Low-level Communications and Timing Commissioning: String 88 | Not Started | 6 | 1d | 2025-12-29 | 2025-12-29 | 1938 | 0% |  |  |  | 110 |  | 2025-12-29 | 2025-12-29 | 0
2041 | 1.2 | 1.2.10.5.6.7 | C | Low-level Communications and Timing Commissioning: String 89 | Not Started | 6 | 1d | 2025-12-30 | 2025-12-31 | 1955 | 0% |  |  |  | 108.375 |  | 2025-12-30 | 2025-12-31 | 0
2042 | 1.2 | 1.2.10.5.6.8 | C | Low-level Communications and Timing Commissioning: String 90 | Not Started | 6 | 1d | 2026-01-05 | 2026-01-05 | 1971 | 0% |  |  |  | 106 |  | 2026-01-05 | 2026-01-05 | 0
2043 | 1.2 | 1.2.10.5.6.9 | C | Low-level Communications and Timing Commissioning: String 91 | Not Started | 6 | 1d | 2026-01-07 | 2026-01-07 | 1991 | 0% |  |  |  | 104 |  | 2026-01-07 | 2026-01-07 | 0
2044 | 1.2 | 1.2.10.5.6.10 | C | Low-level Communications and Timing Commissioning: String 92 | Not Started | 6 | 1d | 2026-01-13 | 2026-01-13 | 2010 | 0% |  |  |  | 100 |  | 2026-01-13 | 2026-01-13 | 0
2045 | 1.2 | 1.2.10.5.6.11 | C | Low-level Communications and Timing Commissioning: String 93 | Not Started | 6 | 1d | 2026-01-15 | 2026-01-15 | 2023 | 0% |  |  |  | 97 |  | 2026-01-15 | 2026-01-15 | 0
2046 | 1.2 | 1.2.10.5.6.12 | C | ICL patch cabling / surface cabling / SJB debug support [ongoing] | Not Started | 6 | 31d | 2025-12-05 | 2026-01-20 |  | 0% |  |  |  | 95 |  | 2025-12-05 | 2026-01-20 | 0
2047 | 1.2 | 1.2.10.5.6.13 | C | FieldHub / DAQ software integration support [ongoing] | Not Started | 6 | 31d | 2025-12-05 | 2026-01-20 |  | 0% |  |  |  | 95 |  | 2025-12-05 | 2026-01-20 | 0
2048 | 1.2 | 1.2.10.5.6.14 | C | Enable FieldHub and power supply monitoring [1 day] | Not Started | 6 | 1d | 2026-01-16 | 2026-01-16 | 2045 | 0% |  |  |  | 97 |  | 2026-01-16 | 2026-01-16 | 0
2049 | 1.2 | 1.2.10.5.7 | P | Installation Closeout | Not Started | 5 | 5d | 2026-01-16 | 2026-01-23 |  | 0% |  |  |  | 92.875 |  | 2026-01-16 | 2026-01-23 | 0
2050 | 1.2 | 1.2.10.5.7.1 | C | Operational Debrief - String & Cable Installation | Not Started | 6 | 1d | 2026-01-16 | 2026-01-19 | 2029 | 0% |  | Installation Personnel |  | 91.875 |  | 2026-01-16 | 2026-01-19 | 0
2051 | 1.2 | 1.2.10.5.7.2 | C | Installation and Safety Lessons Learned Complete | Not Started | 6 | 0 | 2026-01-19 | 2026-01-19 | 2050FF | 0% |  | Installation Personnel |  | 91.875 |  | 2026-01-19 | 2026-01-19 | 0
2052 | 1.2 | 1.2.10.5.7.3 | C | Breakdown Sensor Packaging for Entrance into USAP Waste Stream | Not Started | 6 | 2d | 2026-01-19 | 2026-01-21 | 2051 | 0% |  | Installation Personnel |  | 94.875 |  | 2026-01-19 | 2026-01-21 | 0
2053 | 1.2 | 1.2.10.5.7.4 | C | Stow Installation Equipment | Not Started | 6 | 2d | 2026-01-19 | 2026-01-21 | 2051 | 0% |  | Installation Personnel |  | 91.875 |  | 2026-01-19 | 2026-01-21 | 0
2054 | 1.2 | 1.2.10.5.7.5 | C | Crate Installation Retrograde and Deliver to Cargo | Not Started | 6 | 2d | 2026-01-21 | 2026-01-23 | 2053 | 0% |  | Installation Personnel |  | 91.875 |  | 2026-01-21 | 2026-01-23 | 0
2055 | 1.2 | 1.2.10.5.7.6 | C | Store SPAT Equipment | Not Started | 6 | 2d | 2026-01-19 | 2026-01-21 | 2051 | 0% |  | Installation Personnel |  | 94.875 |  | 2026-01-19 | 2026-01-21 | 0
2056 | 1.2 | 1.2.10.5.8 | C | Installation: On-Ice Labor (FS3) | Not Started | 5 | 54d | 2025-11-20 | 2026-02-06 | 1864SS | 0% |  |  | Team 2 shifts each of: 5 in-kind personnel + 3 drillers (drillers cost absorbed in 1.2.8) Travel Labor: 0 hrs/ea (In Kind Labor) - 3 days paid time during deployment - 3 days paid time during redeployment Travel Cost: $1,800/ea (Travel) - Covered by Institution for in-kind labor PQ Cost: $950/ea (M&S) - Also covered by Institution | 82 |  | 2025-11-20 | 2026-02-06 | 0
2057 | 1.2 | 1.2.10.5.9 | C | END NPX Installation FS3 Season | Not Started | 5 | 1d | 2026-01-23 | 2026-01-26 | 2054 | 0% |  |  |  | 91.875 |  | 2026-01-23 | 2026-01-26 | 0
2058 | 1.3 | 1.3 | P | Sensors | Started | 2 | 1980d | 2018-10-01 | 2026-05-14 |  | 50% |  |  |  | 13 |  | 2018-10-01 | 2026-05-14 | 0
2059 | 1.3 | 1.3.1 | P | mDOM | Started | 3 | 1818d | 2018-10-01 | 2025-09-25 |  | 67% |  |  |  | 175 |  | 2018-10-01 | 2025-09-25 | 0
2060 | 1.3 | 1.3.1.1 | P | mDOM DAQ Electronics | Started | 4 | 1140d | 2018-10-01 | 2023-02-10 |  | 66% |  |  |  | 853 |  | 2018-10-01 | 2023-02-10 | 0
2061 | 1.3 | 1.3.1.1.1 | P | Preliminary design phase | Complete | 5 | 261d | 2018-10-01 | 2019-09-30 |  | 100% |  |  |  | 1732 |  | 2018-10-01 | 2019-09-30 | 0
2062 | 1.3 | 1.3.1.1.1.1 | C | Mainboard conceptual design | Complete | 6 | 55d | 2018-10-01 | 2018-12-14 |  | 100% |  |  |  | 1732 |  | 2018-10-01 | 2018-12-14 | 0
2063 | 1.3 | 1.3.1.1.1.2 | C | Schematic development | Complete | 6 | 60d | 2018-12-17 | 2019-03-08 | 2062 | 100% |  |  | Activity Removed | 1877 |  | 2018-12-17 | 2019-03-08 | 0
2064 | 1.3 | 1.3.1.1.1.3 | C | mDOM DAQ schematic ready | Complete | 6 | 1d | 2019-03-11 | 2019-03-11 | 2063 | 100% | Need to update schedule due to the introduction of an additional revision of the mDOM mainboard. First articles of the intermediate revision have been delivered and will be characterized and reviewed at the mDOM electronics PDR in August 2019 |  | Activity Removed | 1877 |  | 2019-03-11 | 2019-03-11 | 0
2065 | 1.3 | 1.3.1.1.1.4 | C | Build 4 ch. analog-front end (AFE) demonstrator board | Complete | 6 | 50d | 2018-12-17 | 2019-02-22 | 2062 | 100% |  |  |  | 1868 |  | 2018-12-17 | 2019-02-22 | 0
2066 | 1.3 | 1.3.1.1.1.5 | C | Characterization of AFE performance | Complete | 6 | 20d | 2019-02-25 | 2019-03-22 | 2065 | 100% | Will be finished in time for the mDOM electronics PDR scheduled for August 26, 2019 |  |  | 1868 |  | 2019-02-25 | 2019-03-22 | 0
2067 | 1.3 | 1.3.1.1.1.6 | C | Test Mainboard (mDOT) schematic development | Complete | 6 | 80d | 2018-12-17 | 2019-04-05 | 2062 | 100% |  |  | New Activity | 1732 |  | 2018-12-17 | 2019-04-05 | 0
2068 | 1.3 | 1.3.1.1.1.7 | C | Test Mainboard (mDOT) layout | Complete | 6 | 30d | 2019-04-08 | 2019-05-17 | 2067 | 100% |  |  | New Activity | 1732 |  | 2019-04-08 | 2019-05-17 | 0
2069 | 1.3 | 1.3.1.1.1.8 | C | Test mainboard (mDOT) production | Complete | 6 | 20d | 2019-05-20 | 2019-06-14 | 2068 | 100% |  |  | New Activity | 1732 |  | 2019-05-20 | 2019-06-14 | 0
2070 | 1.3 | 1.3.1.1.1.9 | C | Test mainboard (mDOT) shipment to PSU | Complete | 6 | 10d | 2019-06-17 | 2019-06-28 | 2069 | 100% |  |  | New Activity | 1732 |  | 2019-06-17 | 2019-06-28 | 0
2071 | 1.3 | 1.3.1.1.1.10 | C | Test mainboard (mDOT) firmware development | Complete | 6 | 20d | 2019-07-01 | 2019-07-26 | 2070 | 100% | Delayed in favor of D-Egg mainboard firmware development |  | New Activity | 1732 |  | 2019-07-01 | 2019-07-26 | 0
2072 | 1.3 | 1.3.1.1.1.11 | C | Test mainboard (mDOT) characterization | Complete | 6 | 46d | 2019-07-29 | 2019-09-30 | 2071 | 100% | Catching up to complete this in time for WBS 1.3.1.1.2.7 |  | New Activity | 1732 |  | 2019-07-29 | 2019-09-30 | 0
2073 | 1.3 | 1.3.1.1.2 | P | Final design phase | Started | 5 | 879d | 2019-10-01 | 2023-02-10 |  | 64% |  |  |  | 853 |  | 2019-10-01 | 2023-02-10 | 0
2074 | 1.3 | 1.3.1.1.2.1 | P | mDOM Mainboard Rev1 | Complete | 6 | 319d | 2019-10-01 | 2020-12-18 |  | 100% | Delayed due to priorization of mini-Field Hub work |  | Activity Renamed | 1413 |  | 2019-10-01 | 2020-12-18 | 0
2075 | 1.3 | 1.3.1.1.2.1.1 | C | Mainboard layout | Complete | 7 | 20d | 2019-12-24 | 2020-01-20 | 2078 | 100% | Delayed due to priorization of mini-Field Hub work |  | Activity Renamed | 1602 |  | 2019-12-24 | 2020-01-20 | 0
2076 | 1.3 | 1.3.1.1.2.1.2 | C | Commissioning | Complete | 7 | 20d | 2020-02-18 | 2020-03-16 | 2077 | 100% |  |  |  | 1602 |  | 2020-02-18 | 2020-03-16 | 0
2077 | 1.3 | 1.3.1.1.2.1.4 | C | Mainboard production | Complete | 7 | 20d | 2020-01-21 | 2020-02-17 | 2075 | 100% |  |  | Activity Renamed | 1602 |  | 2020-01-21 | 2020-02-17 | 0
2078 | 1.3 | 1.3.1.1.2.1.5 | C | Mainboard schematic development | Complete | 7 | 60d | 2019-10-01 | 2019-12-23 |  | 100% | Delayed due to priorization of mini-Field Hub work |  | New Activity | 1602 |  | 2019-10-01 | 2019-12-23 | 0
2079 | 1.3 | 1.3.1.1.2.1.6 | C | Ship Rev1 Mainboards to WIPAC and PSU | Complete | 7 | 10d | 2020-12-07 | 2020-12-18 | 2076FS +189d | 100% | Delayed due to priorization of mini-Field Hub work |  | New Activity | 1413 |  | 2020-12-07 | 2020-12-18 | 0
2080 | 1.3 | 1.3.1.1.2.2 | P | mDOM Mainboard Rev2 | Started | 6 | 300d | 2021-01-25 | 2022-03-18 |  | 85% |  |  |  | 1088 |  | 2021-01-25 | 2022-03-18 | 0
2081 | 1.3 | 1.3.1.1.2.2.1 | C | Schematic changes | Complete | 7 | 5d | 2021-01-25 | 2021-01-29 |  | 100% |  |  |  | 1348 |  | 2021-01-25 | 2021-01-29 | 0
2082 | 1.3 | 1.3.1.1.2.2.2 | C | Layout changes | Complete | 7 | 5d | 2021-02-01 | 2021-02-05 | 2081 | 100% |  |  |  | 1348 |  | 2021-02-01 | 2021-02-05 | 0
2083 | 1.3 | 1.3.1.1.2.2.3 | C | Production and assembly of 15 PCBs | Complete | 7 | 20d | 2021-02-08 | 2021-03-05 | 2082 | 100% |  |  |  | 1348 |  | 2021-02-08 | 2021-03-05 | 0
2084 | 1.3 | 1.3.1.1.2.2.4 | C | Comissioning | Complete | 7 | 10d | 2021-03-08 | 2021-03-19 | 2083 | 100% |  |  |  | 1348 |  | 2021-03-08 | 2021-03-19 | 0
2085 | 1.3 | 1.3.1.1.2.2.5 | C | (14) Rev. 2 Mainboards available for testing | Complete | 7 | 0 | 2021-09-20 | 2021-09-20 |  | 100% |  |  |  | 1203 |  | 2021-09-20 | 2021-09-20 | 0
2086 | 1.3 | 1.3.1.1.2.2.6 | C | Rev. 2 Mainboard design verification | Complete | 7 | 15d | 2021-09-20 | 2021-10-08 | 2085 | 100% |  |  |  | 1203 |  | 2021-09-20 | 2021-10-08 | 0
2087 | 1.3 | 1.3.1.1.2.2.7 | C | Ship remaining parts to DESY HH for test production | Complete | 7 | 10d | 2021-11-01 | 2021-11-12 |  | 100% |  |  |  | 1178 |  | 2021-11-01 | 2021-11-12 | 0
2088 | 1.3 | 1.3.1.1.2.2.8 | C | Test production of (8) Rev. 2 Mainboards at DESY HH, pt. 1 | Complete | 7 | 30d | 2021-12-13 | 2022-01-21 |  | 100% |  |  |  | 1088 |  | 2021-12-13 | 2022-01-21 | 0
2089 | 1.3 | 1.3.1.1.2.2.9 | C | Setting up automated impedance testing and testing of (8) Rev. 2 Mainboards | Complete | 7 | 20d | 2022-01-24 | 2022-02-18 | 2088 | 100% |  |  |  | 1088 |  | 2022-01-24 | 2022-02-18 | 0
2090 | 1.3 | 1.3.1.1.2.2.10 | C | Ship (2) HH Mainboards to WIPAC for HALT | Not Started | 7 | 10d | 2022-02-21 | 2022-03-04 | 2089 | 0% |  |  |  | 1088 |  | 2022-02-21 | 2022-03-04 | 0
2091 | 1.3 | 1.3.1.1.2.2.11 | C | mDOM Mainboard HALT | Not Started | 7 | 10d | 2022-03-07 | 2022-03-18 | 2090 | 0% |  |  |  | 1088 |  | 2022-03-07 | 2022-03-18 | 0
2092 | 1.3 | 1.3.1.1.2.3 | P | mDOM Mainboard Rev3 | Started | 6 | 470d | 2021-04-26 | 2023-02-10 |  | 27% |  |  |  | 853 |  | 2021-04-26 | 2023-02-10 | 0
2093 | 1.3 | 1.3.1.1.2.3.1 | C | Schematic changes | Complete | 7 | 5d | 2021-04-26 | 2021-04-30 |  | 100% |  |  |  | 1273 |  | 2021-04-26 | 2021-04-30 | 0
2094 | 1.3 | 1.3.1.1.2.3.2 | C | Layout changes | Complete | 7 | 5d | 2021-05-03 | 2021-05-07 | 2093 | 100% |  |  |  | 1273 |  | 2021-05-03 | 2021-05-07 | 0
2095 | 1.3 | 1.3.1.1.2.3.3 | C | Production and assembly of test series | Complete | 7 | 20d | 2021-05-10 | 2021-06-04 | 2094 | 100% |  |  |  | 1273 |  | 2021-05-10 | 2021-06-04 | 0
2096 | 1.3 | 1.3.1.1.2.3.4 | C | Comissioning and final design verification | Complete | 7 | 20d | 2021-06-07 | 2021-07-02 | 2095 | 100% |  |  |  | 1273 |  | 2021-06-07 | 2021-07-02 | 0
2097 | 1.3 | 1.3.1.1.2.3.5 | P | Production and testing of 450 mDOM Mainboards | Started | 7 | 265d | 2022-01-10 | 2023-01-13 |  | 15% |  |  |  | 873 |  | 2022-01-10 | 2023-01-13 | 0
2098 | 1.3 | 1.3.1.1.2.3.5.1 | C | Production of (40) Mainboards with available parts | Not Started | 8 | 20d | 2022-02-28 | 2022-03-25 |  | 0% | POs for all parts for (40) MBs have been placed throughout 2021; not all parts received, yet |  |  | 1083 |  | 2022-02-28 | 2022-03-25 | 0
2099 | 1.3 | 1.3.1.1.2.3.5.2 | C | Tender and procurement of parts for main production run | Started | 8 | 130d | 2022-01-10 | 2022-07-08 |  | 33% |  |  |  | 683 |  | 2022-01-10 | 2022-07-08 | 0
2100 | 1.3 | 1.3.1.1.2.3.5.3 | C | Parts delivery | Not Started | 8 | 100d | 2022-07-11 | 2022-11-25 | 2099 | 0% | All the uncertainty about worldwide supply chains lives in this activity. Uncertainty is very high! |  |  | 683 |  | 2022-07-11 | 2022-11-25 | 0
2101 | 1.3 | 1.3.1.1.2.3.5.4 | C | All components for mDOM Mainboard production available | Not Started | 8 | 0 | 2022-11-25 | 2022-11-25 | 2100 | 0% |  |  |  | 683 |  | 2022-11-25 | 2022-11-25 | 0
2102 | 1.3 | 1.3.1.1.2.3.5.5 | C | Production and burn-in of mainboards (rate: (60) / week), pt. 1 | Not Started | 8 | 20d | 2022-11-28 | 2022-12-23 | 2101 | 0% |  |  |  | 683 |  | 2022-11-28 | 2022-12-23 | 0
2103 | 1.3 | 1.3.1.1.2.3.5.6 | C | Holiday Break | Not Started | 8 | 5d | 2022-12-26 | 2022-12-30 | 2102 | 0% |  |  |  | 853 |  | 2022-12-26 | 2022-12-30 | 0
2104 | 1.3 | 1.3.1.1.2.3.5.7 | C | Production and burn-in of mainboards (rate: (60) / week), pt. 2 | Not Started | 8 | 10d | 2023-01-02 | 2023-01-13 | 2103 | 0% |  |  |  | 853 |  | 2023-01-02 | 2023-01-13 | 0
2105 | 1.3 | 1.3.1.1.2.3.6 | C | Ship mainboards to MSU | Not Started | 7 | 20d | 2023-01-16 | 2023-02-10 | 2104 | 0% |  |  |  | 853 |  | 2023-01-16 | 2023-02-10 | 0
2106 | 1.3 | 1.3.1.1.2.4 | C | Design of mDOM Mainboard burn-in and acceptance testing | Complete | 6 | 40d | 2021-01-04 | 2021-02-26 |  | 100% |  |  |  | 1303 |  | 2021-01-04 | 2021-02-26 | 0
2107 | 1.3 | 1.3.1.1.2.5 | C | Construction and commissioning of mDOM Mainboard burn-in and acceptance testing | Started | 6 | 60d | 2021-03-01 | 2021-05-21 | 2106 | 33% |  |  |  | 1303 |  | 2021-03-01 | 2021-05-21 | 0
2108 | 1.3 | 1.3.1.1.3 | C | mDOM Mainboard firmware development | Complete | 5 | 456d | 2020-01-02 | 2021-09-30 |  | 100% |  |  |  | 1209 |  | 2020-01-02 | 2021-09-30 | 0
2109 | 1.3 | 1.3.1.1.4 | C | Tender and procurement (test production) | Started | 5 | 120d | 2020-04-22 | 2020-10-06 |  | 75% |  |  |  | 1266 |  | 2020-04-22 | 2020-10-06 | 0
2110 | 1.3 | 1.3.1.1.5 | C | Tender and procurement (series production) | Should have Started | 5 | 200d | 2020-04-22 | 2021-01-26 | 2109SS | 0% |  |  |  | 1386 |  | 2020-04-22 | 2021-01-26 | 0
2111 | 1.3 | 1.3.1.1.6 | P | mDOM Adapter Board (mDAB) | Started | 5 | 180d | 2022-01-31 | 2022-10-07 |  | 6% |  |  |  | 943 |  | 2022-01-31 | 2022-10-07 | 0
2112 | 1.3 | 1.3.1.1.6.1 | C | Procurement of parts for (40) mDABs | Started | 6 | 20d | 2022-01-31 | 2022-02-25 |  | 50% |  |  |  | 943 |  | 2022-01-31 | 2022-02-25 | 0
2113 | 1.3 | 1.3.1.1.6.2 | C | Production of (40) mDABs in the DESY Zeuthen workshop | Not Started | 6 | 20d | 2022-02-28 | 2022-03-25 | 2112 | 0% |  |  |  | 943 |  | 2022-02-28 | 2022-03-25 | 0
2114 | 1.3 | 1.3.1.1.6.3 | C | Procurement of parts for mDAB main production run | Not Started | 6 | 60d | 2022-03-28 | 2022-06-17 | 2113 | 0% |  |  |  | 943 |  | 2022-03-28 | 2022-06-17 | 0
2115 | 1.3 | 1.3.1.1.6.4 | C | All components for mDAB production available | Not Started | 6 | 0 | 2022-06-17 | 2022-06-17 | 2114 | 0% |  |  |  | 943 |  | 2022-06-17 | 2022-06-17 | 0
2116 | 1.3 | 1.3.1.1.6.5 | C | Series production of mDABs in the DESY Zeuthen workshop | Not Started | 6 | 80d | 2022-06-20 | 2022-10-07 | 2115 | 0% |  |  |  | 943 |  | 2022-06-20 | 2022-10-07 | 0
2117 | 1.3 | 1.3.1.2 | P | mDOM PMT | Started | 4 | 1047d | 2018-10-01 | 2022-10-04 |  | 88% |  |  |  | 946 |  | 2018-10-01 | 2022-10-04 | 0
2118 | 1.3 | 1.3.1.2.1 | P | Preliminary design phase | Complete | 5 | 40d | 2018-10-01 | 2018-11-23 |  | 100% |  |  |  | 1953 |  | 2018-10-01 | 2018-11-23 | 0
2119 | 1.3 | 1.3.1.2.1.1 | C | Qualification of Hamamatsu R12199 | Complete | 6 | 40d | 2018-10-01 | 2018-11-23 |  | 100% |  |  |  | 1891 |  | 2018-10-01 | 2018-11-23 | 0
2120 | 1.3 | 1.3.1.2.2 | P | Final design phase | Complete | 5 | 61d | 2018-11-26 | 2019-02-18 |  | 100% |  |  |  | 1892 |  | 2018-11-26 | 2019-02-18 | 0
2121 | 1.3 | 1.3.1.2.2.1 | C | Delivery of 48 HZC PMTs | Complete | 6 | 1d | 2018-11-26 | 2018-11-26 | 2119 | 100% |  |  |  | 1891 |  | 2018-11-26 | 2018-11-26 | 0
2122 | 1.3 | 1.3.1.2.2.2 | C | Qualification of HZC PMTs | Complete | 6 | 60d | 2018-11-26 | 2019-02-15 | 2121SS | 100% |  |  |  | 1892 |  | 2018-11-26 | 2019-02-15 | 0
2123 | 1.3 | 1.3.1.2.2.3 | C | Decision on baseline PMT | Complete | 6 | 1d | 2019-02-18 | 2019-02-18 | 2122 | 100% |  |  |  | 1892 |  | 2019-02-18 | 2019-02-18 | 0
2124 | 1.3 | 1.3.1.2.3 | C | Procurement of PMTs for DVT | Complete | 5 | 60d | 2019-10-01 | 2019-12-23 |  | 100% | Vendor specifications have been submitted to Hamamatsu and HZC Photonics |  |  | 1672 |  | 2019-10-01 | 2019-12-23 | 0
2125 | 1.3 | 1.3.1.2.5 | P | Tender and procurement (series production) | Complete | 5 | 340d | 2019-09-02 | 2020-12-18 |  | 100% |  |  | Activity Renamed | 1413 |  | 2019-09-02 | 2020-12-18 | 0
2126 | 1.3 | 1.3.1.2.5.1 | C | Publish tender | Complete | 6 | 49d | 2019-09-02 | 2019-11-07 |  | 100% |  |  | New Activity | 1412 |  | 2019-09-02 | 2019-11-07 | 0
2127 | 1.3 | 1.3.1.2.5.2 | C | PMT Purchase Order placed | Complete | 6 | 1d | 2019-11-08 | 2019-11-08 | 2126 | 100% |  |  | New Activity | 1412 |  | 2019-11-08 | 2019-11-08 | 0
2128 | 1.3 | 1.3.1.2.5.3 | C | Production preparation by manufacturer | Complete | 6 | 120d | 2019-11-08 | 2020-04-23 | 2127SS | 100% |  |  | New Activity | 1413 |  | 2019-11-08 | 2020-04-23 | 0
2129 | 1.3 | 1.3.1.2.5.4 | C | PMT Production Batch #1 (Qty. 1250) | Complete | 6 | 19d | 2020-04-24 | 2020-05-20 | 2128 | 100% |  |  | New Activity | 1413 |  | 2020-04-24 | 2020-05-20 | 0
2130 | 1.3 | 1.3.1.2.5.5 | C | PMT Production Batch #2 (Qty. 1250) | Complete | 6 | 22d | 2020-05-21 | 2020-06-19 | 2129 | 100% |  |  | New Activity | 1413 |  | 2020-05-21 | 2020-06-19 | 0
2131 | 1.3 | 1.3.1.2.5.6 | C | PMT Production Batch #3 (Qty. 1375) | Complete | 6 | 21d | 2020-06-22 | 2020-07-20 | 2130 | 100% |  |  | New Activity | 1413 |  | 2020-06-22 | 2020-07-20 | 0
2132 | 1.3 | 1.3.1.2.5.7 | C | PMT Production Batch #4 (Qty. 1375) | Complete | 6 | 23d | 2020-07-21 | 2020-08-20 | 2131 | 100% |  |  | New Activity | 1413 |  | 2020-07-21 | 2020-08-20 | 0
2133 | 1.3 | 1.3.1.2.5.8 | C | PMT Production Batch #5 (Qty. 1375) | Complete | 6 | 21d | 2020-08-21 | 2020-09-18 | 2132 | 100% |  |  | New Activity | 1413 |  | 2020-08-21 | 2020-09-18 | 0
2134 | 1.3 | 1.3.1.2.5.9 | C | PMT Production Batch #6 (Qty. 1375) | Complete | 6 | 22d | 2020-09-21 | 2020-10-20 | 2133 | 100% |  |  | New Activity | 1413 |  | 2020-09-21 | 2020-10-20 | 0
2135 | 1.3 | 1.3.1.2.5.10 | C | PMT Production Batch #7 (Qty. 2000) | Complete | 6 | 23d | 2020-10-21 | 2020-11-20 | 2134 | 100% |  |  | New Activity | 1413 |  | 2020-10-21 | 2020-11-20 | 0
2136 | 1.3 | 1.3.1.2.5.11 | C | PMT Production Batch #8 (Qty. 500) | Complete | 6 | 20d | 2020-11-23 | 2020-12-18 | 2135 | 100% |  |  | New Activity | 1413 |  | 2020-11-23 | 2020-12-18 | 0
2137 | 1.3 | 1.3.1.2.6 | P | Production of PMT+Base assembly | Complete | 5 | 300d | 2019-11-08 | 2020-12-31 |  | 100% |  |  | New Activity | 1404 |  | 2019-11-08 | 2020-12-31 | 0
2138 | 1.3 | 1.3.1.2.6.1 | C | Preparation of soldering of PMT Base PCAs with PMT manufacturer | Complete | 6 | 120d | 2019-11-08 | 2020-04-23 |  | 100% |  |  | New Activity | 1504 |  | 2019-11-08 | 2020-04-23 | 0
2139 | 1.3 | 1.3.1.2.6.2 | C | PMT+Base Assy. Production Batch #1 (Qty. 1250) | Complete | 6 | 10d | 2020-06-03 | 2020-06-16 | 2138FS +28d | 100% |  |  | New Activity | 1476 |  | 2020-06-03 | 2020-06-16 | 0
2140 | 1.3 | 1.3.1.2.6.3 | C | PMT+Base Assy. Production Batch #2 (Qty. 1250) | Complete | 6 | 10d | 2020-06-17 | 2020-06-30 | 2139 | 100% |  |  | New Activity | 1476 |  | 2020-06-17 | 2020-06-30 | 0
2141 | 1.3 | 1.3.1.2.6.4 | C | PMT+Base Assy. Production Batch #3 (Qty. 1375) | Complete | 6 | 10d | 2020-07-01 | 2020-07-14 | 2140 | 100% |  |  | New Activity | 1476 |  | 2020-07-01 | 2020-07-14 | 0
2142 | 1.3 | 1.3.1.2.6.5 | C | PMT+Base Assy. Production Batch #4 (Qty. 1375) | Complete | 6 | 10d | 2020-07-24 | 2020-08-06 | 2141FS +7d | 100% |  |  | New Activity | 1469 |  | 2020-07-24 | 2020-08-06 | 0
2143 | 1.3 | 1.3.1.2.6.6 | C | PMT+Base Assy. Production Batch #5 (Qty. 1375) | Complete | 6 | 10d | 2020-08-27 | 2020-09-09 | 2142FS +14d | 100% |  |  | New Activity | 1455 |  | 2020-08-27 | 2020-09-09 | 0
2144 | 1.3 | 1.3.1.2.6.7 | C | PMT+Base Assy. Production Batch #6 (Qty. 1375) | Complete | 6 | 10d | 2020-10-09 | 2020-10-22 | 2143FS +21d | 100% |  |  | New Activity | 1434 |  | 2020-10-09 | 2020-10-22 | 0
2145 | 1.3 | 1.3.1.2.6.8 | C | PMT+Base Assy. Production Batch #7 (Qty. 2000) | Complete | 6 | 10d | 2020-11-18 | 2020-12-01 | 2144FS +18d | 100% |  |  | New Activity | 1416 |  | 2020-11-18 | 2020-12-01 | 0
2146 | 1.3 | 1.3.1.2.6.9 | C | PMT+Base Assy. Production Batch #8 (Qty. 500) | Complete | 6 | 10d | 2020-12-18 | 2020-12-31 | 2145FS +12d | 100% |  |  | New Activity | 1404 |  | 2020-12-18 | 2020-12-31 | 0
2147 | 1.3 | 1.3.1.2.7 | P | Acceptance testing and calibration of incoming PMT+Base assemblies | Complete | 5 | 567d | 2019-01-01 | 2021-03-03 |  | 100% |  |  | New Activity | 1360 |  | 2019-01-01 | 2021-03-03 | 0
2148 | 1.3 | 1.3.1.2.7.1 | C | Development and construction of test facilities | Complete | 6 | 360d | 2019-01-01 | 2020-05-18 |  | 100% |  |  | New Activity | 1567 |  | 2019-01-01 | 2020-05-18 | 0
2149 | 1.3 | 1.3.1.2.7.2 | C | Incoming PMT+Base Test Batch #1 (Qty. 1250) | Complete | 6 | 20d | 2020-07-01 | 2020-07-28 |  | 100% |  |  | New Activity | 1376 |  | 2020-07-01 | 2020-07-28 | 0
2150 | 1.3 | 1.3.1.2.7.3 | C | Incoming PMT+Base Test Batch #2 (Qty. 1250) | Complete | 6 | 20d | 2020-07-29 | 2020-08-25 | 2149 | 100% |  |  | New Activity | 1376 |  | 2020-07-29 | 2020-08-25 | 0
2151 | 1.3 | 1.3.1.2.7.4 | C | Incoming PMT+Base Test Batch #3 (Qty. 1375) | Complete | 6 | 20d | 2020-08-26 | 2020-09-22 | 2150 | 100% |  |  | New Activity | 1376 |  | 2020-08-26 | 2020-09-22 | 0
2152 | 1.3 | 1.3.1.2.7.5 | C | Incoming PMT+Base Test Batch #4 (Qty. 1375) | Complete | 6 | 20d | 2020-09-23 | 2020-10-20 | 2151 | 100% |  |  | New Activity | 1376 |  | 2020-09-23 | 2020-10-20 | 0
2153 | 1.3 | 1.3.1.2.7.6 | C | Incoming PMT+Base Test Batch #5 (Qty. 1375) | Complete | 6 | 20d | 2020-11-02 | 2020-11-27 | 2152FS +8d | 100% |  |  | New Activity | 1368 |  | 2020-11-02 | 2020-11-27 | 0
2154 | 1.3 | 1.3.1.2.7.7 | C | Incoming PMT+Base Test Batch #6 (Qty. 1375) | Complete | 6 | 20d | 2020-12-02 | 2020-12-29 | 2153FS +2d | 100% |  |  | New Activity | 1366 |  | 2020-12-02 | 2020-12-29 | 0
2155 | 1.3 | 1.3.1.2.7.8 | C | Incoming PMT+Base Test Batch #7 (Qty. 2000) | Complete | 6 | 20d | 2021-01-01 | 2021-01-28 | 2154FS +2d | 100% |  |  | New Activity | 1364 |  | 2021-01-01 | 2021-01-28 | 0
2156 | 1.3 | 1.3.1.2.7.9 | C | Incoming PMT+Base Test Batch #8 (Qty. 500) | Complete | 6 | 20d | 2021-02-04 | 2021-03-03 | 2155FS +4d | 100% |  |  | New Activity | 1360 |  | 2021-02-04 | 2021-03-03 | 0
2157 | 1.3 | 1.3.1.2.8 | P | Incoming PMT+uBase Testing | Started | 5 | 312d | 2021-07-26 | 2022-10-04 |  | 35% |  |  |  | 946 |  | 2021-07-26 | 2022-10-04 | 0
2158 | 1.3 | 1.3.1.2.8.1 | P | Aachen Site | Started | 6 | 312d | 2021-07-26 | 2022-10-04 |  | 35% |  |  |  | 946 |  | 2021-07-26 | 2022-10-04 | 0
2159 | 1.3 | 1.3.1.2.8.1.1 | C | (5600) PMT Assemblies available in Aachen | Complete | 7 | 0 | 2021-07-26 | 2021-07-26 |  | 100% |  |  |  | 1258 |  | 2021-07-26 | 2021-07-26 | 0
2160 | 1.3 | 1.3.1.2.8.1.2 | C | (4) Rev. 1 mDOM Mainboard available in Aachen | Complete | 7 | 0 | 2021-09-20 | 2021-09-20 |  | 100% |  |  |  | 946 |  | 2021-09-20 | 2021-09-20 | 0
2161 | 1.3 | 1.3.1.2.8.1.3 | C | Commissioning of Aachen test stand | Complete | 7 | 55d | 2021-09-20 | 2021-12-03 | 2160 | 100% |  |  |  | 946 |  | 2021-09-20 | 2021-12-03 | 0
2162 | 1.3 | 1.3.1.2.8.1.4 | C | Screening of high-dark count rate PMTs | Complete | 7 | 40d | 2021-12-06 | 2022-01-28 | 2161 | 100% |  |  |  | 946 |  | 2021-12-06 | 2022-01-28 | 0
2163 | 1.3 | 1.3.1.2.8.1.5 | C | Optimization of Aachen test stand | Started | 7 | 40d | 2022-01-31 | 2022-03-25 | 2162 | 2% |  |  |  | 946 |  | 2022-01-31 | 2022-03-25 | 0
2164 | 1.3 | 1.3.1.2.8.1.6 | C | Aachen test stand ready for production | Not Started | 7 | 0 | 2022-03-25 | 2022-03-25 | 2163 | 0% |  |  |  | 946 |  | 2022-03-25 | 2022-03-25 | 0
2165 | 1.3 | 1.3.1.2.8.1.7 | C | Test of (500) PMT Assemblies | Not Started | 7 | 20d | 2022-03-28 | 2022-04-22 | 2164 | 0% |  |  |  | 946 |  | 2022-03-28 | 2022-04-22 | 0
2166 | 1.3 | 1.3.1.2.8.1.8 | C | Test of (500) PMT Assemblies | Not Started | 7 | 20d | 2022-04-25 | 2022-05-20 | 2165 | 0% |  |  |  | 946 |  | 2022-04-25 | 2022-05-20 | 0
2167 | 1.3 | 1.3.1.2.8.1.9 | C | Test of (500) PMT Assemblies | Not Started | 7 | 15d | 2022-05-23 | 2022-06-10 | 2166 | 0% |  |  |  | 946 |  | 2022-05-23 | 2022-06-10 | 0
2168 | 1.3 | 1.3.1.2.8.1.10 | C | Test of (500) PMT Assemblies | Not Started | 7 | 10d | 2022-06-13 | 2022-06-24 | 2167 | 0% |  |  |  | 946 |  | 2022-06-13 | 2022-06-24 | 0
2169 | 1.3 | 1.3.1.2.8.1.11 | C | Test of (500) PMT Assemblies | Not Started | 7 | 10d | 2022-06-27 | 2022-07-08 | 2168 | 0% |  |  |  | 946 |  | 2022-06-27 | 2022-07-08 | 0
2170 | 1.3 | 1.3.1.2.8.1.12 | C | Test of (500) PMT Assemblies | Not Started | 7 | 10d | 2022-07-11 | 2022-07-22 | 2169 | 0% |  |  |  | 946 |  | 2022-07-11 | 2022-07-22 | 0
2171 | 1.3 | 1.3.1.2.8.1.13 | C | Test of (500) PMT Assemblies | Not Started | 7 | 10d | 2022-07-25 | 2022-08-05 | 2170 | 0% |  |  |  | 946 |  | 2022-07-25 | 2022-08-05 | 0
2172 | 1.3 | 1.3.1.2.8.1.14 | C | Test of (500) PMT Assemblies | Not Started | 7 | 10d | 2022-08-08 | 2022-08-19 | 2171 | 0% |  |  |  | 946 |  | 2022-08-08 | 2022-08-19 | 0
2173 | 1.3 | 1.3.1.2.8.1.15 | C | Test of (500) PMT Assemblies | Not Started | 7 | 10d | 2022-08-22 | 2022-09-02 | 2172 | 0% |  |  |  | 946 |  | 2022-08-22 | 2022-09-02 | 0
2174 | 1.3 | 1.3.1.2.8.1.16 | C | Test of (500) PMT Assemblies | Not Started | 7 | 10d | 2022-09-05 | 2022-09-16 | 2173 | 0% |  |  |  | 946 |  | 2022-09-05 | 2022-09-16 | 0
2175 | 1.3 | 1.3.1.2.8.1.17 | C | Test of (500) PMT Assemblies | Not Started | 7 | 10d | 2022-09-19 | 2022-09-30 | 2174 | 0% |  |  |  | 946 |  | 2022-09-19 | 2022-09-30 | 0
2176 | 1.3 | 1.3.1.2.8.1.18 | C | Test of (100) PMT Assemblies | Not Started | 7 | 2d | 2022-10-03 | 2022-10-04 | 2175 | 0% |  |  |  | 946 |  | 2022-10-03 | 2022-10-04 | 0
2177 | 1.3 | 1.3.1.2.8.1.19 | C | PMT Testing in Aachen complete | Not Started | 7 | 0 | 2022-10-04 | 2022-10-04 | 2176 | 0% |  |  |  | 946 |  | 2022-10-04 | 2022-10-04 | 0
2178 | 1.3 | 1.3.1.2.8.2 | P | Dortmund Site | Started | 6 | 261d | 2021-08-30 | 2022-08-29 |  | 35% |  |  |  | 972 |  | 2021-08-30 | 2022-08-29 | 0
2179 | 1.3 | 1.3.1.2.8.2.1 | C | (4) Rev. 1 mDOM Mainboard available in Dortmund | Complete | 7 | 0 | 2021-10-11 | 2021-10-11 |  | 100% |  |  |  | 972 |  | 2021-10-11 | 2021-10-11 | 0
2180 | 1.3 | 1.3.1.2.8.2.2 | C | Reference PMTs available in Dortmund | Complete | 7 | 0 | 2021-09-27 | 2021-09-27 |  | 100% |  |  |  | 982 |  | 2021-09-27 | 2021-09-27 | 0
2181 | 1.3 | 1.3.1.2.8.2.3 | C | Arrival of (720) PMT Assemblies in Dortmund | Complete | 7 | 0 | 2021-08-30 | 2021-08-30 |  | 100% |  |  |  | 1122 |  | 2021-08-30 | 2021-08-30 | 0
2182 | 1.3 | 1.3.1.2.8.2.4 | C | Arrival of (720) PMT Assemblies in Dortmund | Complete | 7 | 0 | 2021-10-01 | 2021-10-01 |  | 100% |  |  |  | 1118 |  | 2021-10-01 | 2021-10-01 | 0
2183 | 1.3 | 1.3.1.2.8.2.5 | C | Arrival of (1620) PMT Assemblies in Dortmund | Complete | 7 | 0 | 2021-11-01 | 2021-11-01 |  | 100% |  |  |  | 972 |  | 2021-11-01 | 2021-11-01 | 0
2184 | 1.3 | 1.3.1.2.8.2.6 | C | Arrival of (1720) PMT Assemblies in Dortmund | Complete | 7 | 0 | 2021-12-01 | 2021-12-01 |  | 100% |  |  |  | 972 |  | 2021-12-01 | 2021-12-01 | 0
2185 | 1.3 | 1.3.1.2.8.2.7 | C | Commissioning of Dortmund test stand | Complete | 7 | 40d | 2021-10-11 | 2021-12-03 | 2179, 2180 | 100% |  |  |  | 972 |  | 2021-10-11 | 2021-12-03 | 0
2186 | 1.3 | 1.3.1.2.8.2.8 | C | Screening of high-dark count rate PMTs | Complete | 7 | 40d | 2021-12-06 | 2022-01-28 | 2185 | 100% |  |  |  | 972 |  | 2021-12-06 | 2022-01-28 | 0
2187 | 1.3 | 1.3.1.2.8.2.9 | C | Optimization of Dortmund test stand | Started | 7 | 40d | 2022-01-31 | 2022-03-25 | 2186 | 2% |  |  |  | 972 |  | 2022-01-31 | 2022-03-25 | 0
2188 | 1.3 | 1.3.1.2.8.2.10 | C | Dortmund test stand ready for production | Not Started | 7 | 0 | 2022-03-25 | 2022-03-25 | 2187 | 0% |  |  |  | 972 |  | 2022-03-25 | 2022-03-25 | 0
2189 | 1.3 | 1.3.1.2.8.2.11 | C | Test of (500) PMT Assemblies | Not Started | 7 | 20d | 2022-03-28 | 2022-04-22 | 2181, 2188 | 0% |  |  |  | 972 |  | 2022-03-28 | 2022-04-22 | 0
2190 | 1.3 | 1.3.1.2.8.2.12 | C | Test of (500) PMT Assemblies | Not Started | 7 | 15d | 2022-04-25 | 2022-05-13 | 2182, 2189 | 0% |  |  |  | 972 |  | 2022-04-25 | 2022-05-13 | 0
2191 | 1.3 | 1.3.1.2.8.2.13 | C | Test of (500) PMT Assemblies | Not Started | 7 | 10d | 2022-05-16 | 2022-05-27 | 2183, 2190 | 0% |  |  |  | 972 |  | 2022-05-16 | 2022-05-27 | 0
2192 | 1.3 | 1.3.1.2.8.2.14 | C | Test of (500) PMT Assemblies | Not Started | 7 | 10d | 2022-05-30 | 2022-06-10 | 2183, 2191 | 0% |  |  |  | 972 |  | 2022-05-30 | 2022-06-10 | 0
2193 | 1.3 | 1.3.1.2.8.2.15 | C | Test of (500) PMT Assemblies | Not Started | 7 | 10d | 2022-06-13 | 2022-06-24 | 2183, 2192 | 0% |  |  |  | 972 |  | 2022-06-13 | 2022-06-24 | 0
2194 | 1.3 | 1.3.1.2.8.2.16 | C | Test of (500) PMT Assemblies | Not Started | 7 | 10d | 2022-06-27 | 2022-07-08 | 2193 | 0% |  |  |  | 972 |  | 2022-06-27 | 2022-07-08 | 0
2195 | 1.3 | 1.3.1.2.8.2.17 | C | Test of (500) PMT Assemblies | Not Started | 7 | 10d | 2022-07-11 | 2022-07-22 | 2184, 2194 | 0% |  |  |  | 972 |  | 2022-07-11 | 2022-07-22 | 0
2196 | 1.3 | 1.3.1.2.8.2.18 | C | Test of (500) PMT Assemblies | Not Started | 7 | 10d | 2022-07-25 | 2022-08-05 | 2184, 2195 | 0% |  |  |  | 972 |  | 2022-07-25 | 2022-08-05 | 0
2197 | 1.3 | 1.3.1.2.8.2.19 | C | Test of (500) PMT Assemblies | Not Started | 7 | 10d | 2022-08-08 | 2022-08-19 | 2184, 2196 | 0% |  |  |  | 972 |  | 2022-08-08 | 2022-08-19 | 0
2198 | 1.3 | 1.3.1.2.8.2.20 | C | Test of (280) PMT Assemblies | Not Started | 7 | 6d | 2022-08-22 | 2022-08-29 | 2184, 2197 | 0% |  |  |  | 972 |  | 2022-08-22 | 2022-08-29 | 0
2199 | 1.3 | 1.3.1.2.8.2.21 | C | PMT Testing in Dortmund complete | Not Started | 7 | 0 | 2022-08-29 | 2022-08-29 | 2198 | 0% |  |  |  | 972 |  | 2022-08-29 | 2022-08-29 | 0
2200 | 1.3 | 1.3.1.3 | P | mDOM High Voltage Subsystem | Complete | 4 | 546d | 2018-10-01 | 2020-11-02 |  | 100% |  |  |  | 1447 |  | 2018-10-01 | 2020-11-02 | 0
2201 | 1.3 | 1.3.1.3.1 | C | Preliminary design phase | Complete | 5 | 120d | 2018-10-01 | 2019-03-15 |  | 100% |  |  |  | 1873 |  | 2018-10-01 | 2019-03-15 | 0
2202 | 1.3 | 1.3.1.3.2 | C | Final design phase | Complete | 5 | 210d | 2019-02-18 | 2019-12-06 |  | 100% |  |  |  | 1683 |  | 2019-02-18 | 2019-12-06 | 0
2203 | 1.3 | 1.3.1.3.4 | P | Tender and procurement | Complete | 5 | 285d | 2019-10-01 | 2020-11-02 |  | 100% |  |  | Activity Renamed | 1447 |  | 2019-10-01 | 2020-11-02 | 0
2204 | 1.3 | 1.3.1.3.4.1 | C | Identification of contract manufacturer for PMT Base PCA | Complete | 6 | 60d | 2019-10-01 | 2019-12-23 |  | 100% |  |  | New Activity | 1357 |  | 2019-10-01 | 2019-12-23 | 0
2205 | 1.3 | 1.3.1.3.4.2 | C | Development and construction of test station for PMT Base PCA | Complete | 6 | 60d | 2019-10-01 | 2019-12-23 | 2204SS | 100% |  |  | New Activity | 1422 |  | 2019-10-01 | 2019-12-23 | 0
2206 | 1.3 | 1.3.1.3.4.3 | C | Production and test of 50 PMT Base PCAs | Complete | 6 | 40d | 2019-12-31 | 2020-02-24 | 2205FS +5d | 100% |  |  | New Activity | 1417 |  | 2019-12-31 | 2020-02-24 | 0
2207 | 1.3 | 1.3.1.3.4.4 | C | PMT Base PCA Production Batch #1 (Qty. 3000) | Complete | 6 | 60d | 2020-02-25 | 2020-05-18 | 2206 | 100% |  |  | New Activity | 1417 |  | 2020-02-25 | 2020-05-18 | 0
2208 | 1.3 | 1.3.1.3.4.5 | C | Shipment of Batch #1 to PMT Manufacturer | Complete | 6 | 10d | 2020-05-19 | 2020-06-01 | 2207 | 100% |  |  | New Activity | 1417 |  | 2020-05-19 | 2020-06-01 | 0
2209 | 1.3 | 1.3.1.3.4.6 | C | PMT Base PCA Production Batch #2 (Qty. 3000) | Complete | 6 | 40d | 2020-05-19 | 2020-07-13 | 2208SS | 100% |  |  | New Activity | 1427 |  | 2020-05-19 | 2020-07-13 | 0
2210 | 1.3 | 1.3.1.3.4.7 | C | Shipment of Batch #2 to PMT Manufacturer | Complete | 6 | 10d | 2020-07-14 | 2020-07-27 | 2209 | 100% |  |  | New Activity | 1427 |  | 2020-07-14 | 2020-07-27 | 0
2211 | 1.3 | 1.3.1.3.4.8 | C | PMT Base PCA Production Batch #3 (Qty. 3000) | Complete | 6 | 40d | 2020-07-14 | 2020-09-07 | 2210SS | 100% |  |  | New Activity | 1437 |  | 2020-07-14 | 2020-09-07 | 0
2212 | 1.3 | 1.3.1.3.4.9 | C | Shipment of Batch #3 to PMT Manufacturer | Complete | 6 | 10d | 2020-09-08 | 2020-09-21 | 2211 | 100% |  |  | New Activity | 1437 |  | 2020-09-08 | 2020-09-21 | 0
2213 | 1.3 | 1.3.1.3.4.10 | C | PMT Base PCA Production Batch #4 (Qty. 2000) | Complete | 6 | 30d | 2020-09-08 | 2020-10-19 | 2212SS | 100% |  |  | New Activity | 1447 |  | 2020-09-08 | 2020-10-19 | 0
2214 | 1.3 | 1.3.1.3.4.11 | C | Shipment of Batch #4 to PMT Manufacturer | Complete | 6 | 10d | 2020-10-20 | 2020-11-02 | 2213 | 100% |  |  | New Activity | 1447 |  | 2020-10-20 | 2020-11-02 | 0
2215 | 1.3 | 1.3.1.3.5 | C | mDOM High Voltage Subsystem Final Design Review | Complete | 5 | 1d | 2019-12-23 | 2019-12-23 | 2205FF | 100% | Informal internal review held on 2019-12-17 |  | New Activity | 1672 |  | 2019-12-23 | 2019-12-23 | 0
2216 | 1.3 | 1.3.1.4 | P | mDOM Pressure Vessel | Complete | 4 | 607d | 2018-10-01 | 2021-01-26 |  | 100% |  |  |  | 1386 |  | 2018-10-01 | 2021-01-26 | 0
2217 | 1.3 | 1.3.1.4.1 | P | Preliminary design phase | Complete | 5 | 40d | 2018-10-01 | 2018-11-23 |  | 100% |  |  |  | 1953 |  | 2018-10-01 | 2018-11-23 | 0
2218 | 1.3 | 1.3.1.4.1.1 | C | Qualification of Nautilus pressure vessels | Complete | 6 | 40d | 2018-10-01 | 2018-11-23 |  | 100% |  |  |  | 1713 |  | 2018-10-01 | 2018-11-23 | 0
2219 | 1.3 | 1.3.1.4.2 | C | Final design phase | Complete | 5 | 180d | 2018-11-26 | 2019-08-02 | 2218 | 100% |  |  |  | 1713 |  | 2018-11-26 | 2019-08-02 | 0
2220 | 1.3 | 1.3.1.4.3 | C | Procurement of pressure vessels for DVT | Complete | 5 | 60d | 2019-08-05 | 2019-10-25 | 2219 | 100% |  |  |  | 1713 |  | 2019-08-05 | 2019-10-25 | 0
2221 | 1.3 | 1.3.1.4.4 | C | Tender and procurement (test production) | Complete | 5 | 120d | 2020-04-22 | 2020-10-06 |  | 100% |  |  |  | 442 |  | 2020-04-22 | 2020-10-06 | 0
2222 | 1.3 | 1.3.1.4.5 | C | Tender and procurement (series production) | Complete | 5 | 200d | 2020-04-22 | 2021-01-26 | 2221SS | 100% |  |  |  | 642 |  | 2020-04-22 | 2021-01-26 | 0
2223 | 1.3 | 1.3.1.5 | P | mDOM PMT Support Structure and Reflector Rings | Started | 4 | 1195d | 2018-10-01 | 2023-04-28 |  | 23% |  |  |  | 798 |  | 2018-10-01 | 2023-04-28 | 0
2224 | 1.3 | 1.3.1.5.1 | C | Preliminary design phase | Complete | 5 | 40d | 2018-10-01 | 2018-11-23 |  | 100% |  |  |  | 1693 |  | 2018-10-01 | 2018-11-23 | 0
2225 | 1.3 | 1.3.1.5.2 | C | Final design phase | Started | 5 | 180d | 2018-11-26 | 2019-08-02 | 2224 | 90% |  |  |  | 1693 |  | 2018-11-26 | 2019-08-02 | 0
2226 | 1.3 | 1.3.1.5.3 | C | Procurement of PMT support structures for DVT | Complete | 5 | 60d | 2019-08-05 | 2019-10-25 | 2225 | 100% |  |  |  | 1693 |  | 2019-08-05 | 2019-10-25 | 0
2227 | 1.3 | 1.3.1.5.4 | C | Procurement of reflector rings for DVT | Complete | 5 | 20d | 2019-08-05 | 2019-08-30 | 2226SS | 100% |  |  |  | 1753 |  | 2019-08-05 | 2019-08-30 | 0
2228 | 1.3 | 1.3.1.5.5 | C | Tender and procurement of support structures (test production) | Should have Started | 5 | 120d | 2020-04-22 | 2020-10-06 |  | 0% |  |  |  | 642 |  | 2020-04-22 | 2020-10-06 | 0
2229 | 1.3 | 1.3.1.5.6 | C | Procurement of reflector rings (test production) | Started | 5 | 20d | 2020-09-09 | 2020-10-06 | 2228FF | 66% |  |  |  | 1466 |  | 2020-09-09 | 2020-10-06 | 0
2230 | 1.3 | 1.3.1.5.7 | C | Tender and procurement of support structures (series production) | Should have Started | 5 | 200d | 2020-04-22 | 2021-01-26 | 2228SS, 2222FF | 0% |  |  |  | 732 |  | 2020-04-22 | 2021-01-26 | 0
2231 | 1.3 | 1.3.1.5.8 | C | Procurement of reflector rings (series production) | Should have Started | 5 | 40d | 2020-12-02 | 2021-01-26 | 2230FF | 0% |  |  |  | 1386 |  | 2020-12-02 | 2021-01-26 | 0
2232 | 1.3 | 1.3.1.5.9 | C | Decision on Support Structure design for series production | Complete | 5 | 0 | 2022-01-10 | 2022-01-10 |  | 100% |  |  |  | 1058 |  | 2022-01-10 | 2022-01-10 | 0
2233 | 1.3 | 1.3.1.5.10 | C | EU-wide tender for PMT Support Structures | Started | 5 | 40d | 2022-01-10 | 2022-03-04 | 2232 | 33% |  |  |  | 1058 |  | 2022-01-10 | 2022-03-04 | 0
2234 | 1.3 | 1.3.1.5.11 | C | Purchase order for support structures signed | Not Started | 5 | 0 | 2022-03-04 | 2022-03-04 | 2233 | 0% |  |  |  | 1058 |  | 2022-03-04 | 2022-03-04 | 0
2235 | 1.3 | 1.3.1.5.12 | C | Preparation of production at manufacturer | Not Started | 5 | 10d | 2022-03-07 | 2022-03-18 | 2234 | 0% |  |  |  | 1058 |  | 2022-03-07 | 2022-03-18 | 0
2236 | 1.3 | 1.3.1.5.13 | P | Production of PMT Support Structures (expected rate: 18 hemispheres / week) | Not Started | 5 | 270d | 2022-03-21 | 2023-03-31 |  | 0% |  |  |  | 818 |  | 2022-03-21 | 2023-03-31 | 0
2237 | 1.3 | 1.3.1.5.13.1 | C | Pre-series production of support structure (20 mDOMs, expected rate: 18 hemispheres / week) | Not Started | 6 | 15d | 2022-03-21 | 2022-04-08 | 2235 | 0% |  |  |  | 1058 |  | 2022-03-21 | 2022-04-08 | 0
2238 | 1.3 | 1.3.1.5.13.2 | C | Production of (54) support structures (Batch #1) | Not Started | 6 | 15d | 2022-05-09 | 2022-05-27 |  | 0% |  |  |  | 678 |  | 2022-05-09 | 2022-05-27 | 0
2239 | 1.3 | 1.3.1.5.13.3 | C | Production of (54) support structures (Batch #2) | Not Started | 6 | 15d | 2022-05-30 | 2022-06-17 | 2238 | 0% |  |  |  | 678 |  | 2022-05-30 | 2022-06-17 | 0
2240 | 1.3 | 1.3.1.5.13.4 | C | Production of (54) support structures (Batch #3) | Not Started | 6 | 15d | 2022-06-20 | 2022-07-08 | 2239 | 0% |  |  |  | 678 |  | 2022-06-20 | 2022-07-08 | 0
2241 | 1.3 | 1.3.1.5.13.5 | C | Production of (54) support structures (Batch #4) | Not Started | 6 | 15d | 2022-07-11 | 2022-07-29 | 2240 | 0% |  |  |  | 678 |  | 2022-07-11 | 2022-07-29 | 0
2242 | 1.3 | 1.3.1.5.13.6 | C | Production of (54) support structures (Batch #5) | Not Started | 6 | 15d | 2022-08-01 | 2022-08-19 | 2241 | 0% |  |  |  | 678 |  | 2022-08-01 | 2022-08-19 | 0
2243 | 1.3 | 1.3.1.5.13.7 | C | Production of (54) support structures (Batch #6) | Not Started | 6 | 15d | 2022-08-22 | 2022-09-09 | 2242 | 0% |  |  |  | 678 |  | 2022-08-22 | 2022-09-09 | 0
2244 | 1.3 | 1.3.1.5.13.8 | C | Production of (54) support structures (Batch #7) | Not Started | 6 | 15d | 2022-09-12 | 2022-09-30 | 2243 | 0% |  |  |  | 678 |  | 2022-09-12 | 2022-09-30 | 0
2245 | 1.3 | 1.3.1.5.13.9 | C | Production of (54) support structures (Batch #8) | Not Started | 6 | 15d | 2022-10-03 | 2022-10-21 | 2244 | 0% |  |  |  | 678 |  | 2022-10-03 | 2022-10-21 | 0
2246 | 1.3 | 1.3.1.5.13.10 | C | Production of (54) support structures (Batch #9) | Not Started | 6 | 15d | 2022-10-24 | 2022-11-11 | 2245 | 0% |  |  |  | 678 |  | 2022-10-24 | 2022-11-11 | 0
2247 | 1.3 | 1.3.1.5.13.11 | C | Production of (54) support structures (Batch #10) | Not Started | 6 | 15d | 2022-11-14 | 2022-12-02 | 2246 | 0% |  |  |  | 678 |  | 2022-11-14 | 2022-12-02 | 0
2248 | 1.3 | 1.3.1.5.13.12 | C | Production of (54) support structures (Batch #11) | Not Started | 6 | 15d | 2022-12-05 | 2022-12-23 | 2247 | 0% |  |  |  | 678 |  | 2022-12-05 | 2022-12-23 | 0
2249 | 1.3 | 1.3.1.5.13.13 | C | Production of (54) support structures (Batch #12) | Not Started | 6 | 15d | 2022-12-26 | 2023-01-13 | 2248 | 0% |  |  |  | 683 |  | 2022-12-26 | 2023-01-13 | 0
2250 | 1.3 | 1.3.1.5.13.14 | C | Production of (54) support structures (Batch #13) | Not Started | 6 | 15d | 2023-01-16 | 2023-02-03 | 2249 | 0% |  |  |  | 683 |  | 2023-01-16 | 2023-02-03 | 0
2251 | 1.3 | 1.3.1.5.13.15 | C | Production of (54) support structures (Batch #14) | Not Started | 6 | 15d | 2023-02-06 | 2023-02-24 | 2250 | 0% |  |  |  | 683 |  | 2023-02-06 | 2023-02-24 | 0
2252 | 1.3 | 1.3.1.5.13.16 | C | Production of (54) support structures (Batch #15) | Not Started | 6 | 15d | 2023-02-27 | 2023-03-17 | 2251 | 0% |  |  |  | 733 |  | 2023-02-27 | 2023-03-17 | 0
2253 | 1.3 | 1.3.1.5.13.17 | C | Production of (30) support structures (Batch #16) | Not Started | 6 | 10d | 2023-03-20 | 2023-03-31 | 2252 | 0% |  |  |  | 808 |  | 2023-03-20 | 2023-03-31 | 0
2254 | 1.3 | 1.3.1.5.13.18 | C | Production of PMT Support Structures completed | Not Started | 6 | 0 | 2023-03-31 | 2023-03-31 | 2253 | 0% |  |  |  | 818 |  | 2023-03-31 | 2023-03-31 | 0
2255 | 1.3 | 1.3.1.5.14 | C | Procurement of Reflector Rings for Batch #0 | Not Started | 5 | 20d | 2022-02-28 | 2022-03-25 |  | 0% |  |  |  | 678 |  | 2022-02-28 | 2022-03-25 | 0
2256 | 1.3 | 1.3.1.5.15 | C | Tender and Procurement for Reflector Rings | Not Started | 5 | 40d | 2022-03-28 | 2022-05-20 | 2255 | 0% |  |  |  | 678 |  | 2022-03-28 | 2022-05-20 | 0
2257 | 1.3 | 1.3.1.5.16 | P | Pre-assembly of PMT Support Structures in Münster (expected rate: 18 hemispheres / week) | Not Started | 5 | 280d | 2022-04-04 | 2023-04-28 |  | 0% |  |  |  | 798 |  | 2022-04-04 | 2023-04-28 | 0
2258 | 1.3 | 1.3.1.5.16.1 | C | Pre-assembly of (40) support structures (pre-series) | Not Started | 6 | 15d | 2022-04-04 | 2022-04-22 | 2237SS +10d, 2255 | 0% |  |  |  | 1063 |  | 2022-04-04 | 2022-04-22 | 0
2259 | 1.3 | 1.3.1.5.16.2 | C | Pre-assembly of (54) support structures (Batch #1) | Not Started | 6 | 20d | 2022-05-23 | 2022-06-17 | 2238SS +10d, 2256 | 0% |  |  |  | 678 |  | 2022-05-23 | 2022-06-17 | 0
2260 | 1.3 | 1.3.1.5.16.3 | C | Pre-assembly of (54) support structures (Batch #2) | Not Started | 6 | 20d | 2022-06-20 | 2022-07-15 | 2239SS +10d, 2259 | 0% |  |  |  | 678 |  | 2022-06-20 | 2022-07-15 | 0
2261 | 1.3 | 1.3.1.5.16.4 | C | Pre-assembly of (54) support structures (Batch #3) | Not Started | 6 | 15d | 2022-07-18 | 2022-08-05 | 2240SS +10d, 2260 | 0% |  |  |  | 678 |  | 2022-07-18 | 2022-08-05 | 0
2262 | 1.3 | 1.3.1.5.16.5 | C | Pre-assembly of (54) support structures (Batch #4) | Not Started | 6 | 15d | 2022-08-08 | 2022-08-26 | 2241SS +10d, 2261 | 0% |  |  |  | 678 |  | 2022-08-08 | 2022-08-26 | 0
2263 | 1.3 | 1.3.1.5.16.6 | C | Pre-assembly of (54) support structures (Batch #5) | Not Started | 6 | 15d | 2022-08-29 | 2022-09-16 | 2242SS +10d, 2262 | 0% |  |  |  | 678 |  | 2022-08-29 | 2022-09-16 | 0
2264 | 1.3 | 1.3.1.5.16.7 | C | Pre-assembly of (54) support structures (Batch #6) | Not Started | 6 | 15d | 2022-09-19 | 2022-10-07 | 2243SS +10d, 2263 | 0% |  |  |  | 678 |  | 2022-09-19 | 2022-10-07 | 0
2265 | 1.3 | 1.3.1.5.16.8 | C | Pre-assembly of (54) support structures (Batch #7) | Not Started | 6 | 15d | 2022-10-10 | 2022-10-28 | 2244SS +10d, 2264 | 0% |  |  |  | 678 |  | 2022-10-10 | 2022-10-28 | 0
2266 | 1.3 | 1.3.1.5.16.9 | C | Pre-assembly of (54) support structures (Batch #8) | Not Started | 6 | 15d | 2022-10-31 | 2022-11-18 | 2245SS +10d, 2265 | 0% |  |  |  | 678 |  | 2022-10-31 | 2022-11-18 | 0
2267 | 1.3 | 1.3.1.5.16.10 | C | Pre-assembly of (54) support structures (Batch #9) | Not Started | 6 | 15d | 2022-11-21 | 2022-12-09 | 2246SS +10d, 2266 | 0% |  |  |  | 678 |  | 2022-11-21 | 2022-12-09 | 0
2268 | 1.3 | 1.3.1.5.16.11 | C | Pre-assembly of (54) support structures (Batch #10) | Not Started | 6 | 15d | 2022-12-12 | 2022-12-30 | 2247SS +10d, 2267 | 0% |  |  |  | 678 |  | 2022-12-12 | 2022-12-30 | 0
2269 | 1.3 | 1.3.1.5.16.12 | C | Pre-assembly of (54) support structures (Batch #11) | Not Started | 6 | 15d | 2023-01-02 | 2023-01-20 | 2248SS +10d, 2268 | 0% |  |  |  | 678 |  | 2023-01-02 | 2023-01-20 | 0
2270 | 1.3 | 1.3.1.5.16.13 | C | Ship pre-assembled support structures to MSU | Not Started | 6 | 30d | 2023-01-23 | 2023-03-03 | 2263, 2264, 2265, 2266, 2267, 2268, 2269 | 0% |  |  |  | 678 |  | 2023-01-23 | 2023-03-03 | 0
2271 | 1.3 | 1.3.1.5.16.14 | C | Pre-assembly of (54) support structures (Batch #12) | Not Started | 6 | 15d | 2023-01-23 | 2023-02-10 | 2249SS +10d, 2269 | 0% |  |  |  | 683 |  | 2023-01-23 | 2023-02-10 | 0
2272 | 1.3 | 1.3.1.5.16.15 | C | Pre-assembly of (54) support structures (Batch #13) | Not Started | 6 | 15d | 2023-02-13 | 2023-03-03 | 2250SS +10d, 2271 | 0% |  |  |  | 683 |  | 2023-02-13 | 2023-03-03 | 0
2273 | 1.3 | 1.3.1.5.16.16 | C | Pre-assembly of (54) support structures (Batch #14) | Not Started | 6 | 15d | 2023-03-06 | 2023-03-24 | 2251SS +10d, 2272 | 0% |  |  |  | 683 |  | 2023-03-06 | 2023-03-24 | 0
2274 | 1.3 | 1.3.1.5.16.17 | C | Pre-assembly of (54) support structures (Batch #15) | Not Started | 6 | 15d | 2023-03-27 | 2023-04-14 | 2252SS +10d, 2273 | 0% |  |  |  | 733 |  | 2023-03-27 | 2023-04-14 | 0
2275 | 1.3 | 1.3.1.5.16.18 | C | Pre-assembly of (30) support structures (Batch #16) | Not Started | 6 | 10d | 2023-04-17 | 2023-04-28 | 2253SS +10d, 2274 | 0% |  |  |  | 798 |  | 2023-04-17 | 2023-04-28 | 0
2276 | 1.3 | 1.3.1.5.16.19 | C | Pre-assembly of PMT Support Structures completed | Not Started | 6 | 0 | 2023-04-28 | 2023-04-28 | 2275 | 0% |  |  |  | 798 |  | 2023-04-28 | 2023-04-28 | 0
2277 | 1.3 | 1.3.1.6 | P | mDOM Optical Gel | Complete | 4 | 607d | 2018-10-01 | 2021-01-26 |  | 100% |  |  |  | 1386 |  | 2018-10-01 | 2021-01-26 | 0
2278 | 1.3 | 1.3.1.6.1 | C | Preliminary design phase | Complete | 5 | 40d | 2018-10-01 | 2018-11-23 |  | 100% |  |  |  | 549 |  | 2018-10-01 | 2018-11-23 | 0
2279 | 1.3 | 1.3.1.6.2 | C | Final design phase | Complete | 5 | 180d | 2018-11-26 | 2019-08-02 | 2278 | 100% |  |  |  | 529 |  | 2018-11-26 | 2019-08-02 | 0
2280 | 1.3 | 1.3.1.6.3 | C | Procurement of optical gel for DVT | Complete | 5 | 60d | 2019-12-23 | 2020-03-13 | 2279FS +100d | 100% |  |  |  | 642 |  | 2019-12-23 | 2020-03-13 | 0
2281 | 1.3 | 1.3.1.6.4 | C | Tender and procurement (test production) | Complete | 5 | 120d | 2020-04-13 | 2020-09-25 | 2280FS +20d | 100% |  |  |  | 732 |  | 2020-04-13 | 2020-09-25 | 0
2282 | 1.3 | 1.3.1.6.5 | C | Tender and procurement (series production) | Complete | 5 | 200d | 2020-04-22 | 2021-01-26 | 2281SS, 2230FF | 100% |  |  |  | 847 |  | 2020-04-22 | 2021-01-26 | 0
2283 | 1.3 | 1.3.1.7 | P | mDOM Harness | Started | 4 | 1050d | 2018-10-01 | 2022-10-07 |  | 77% |  |  |  | 943 |  | 2018-10-01 | 2022-10-07 | 0
2284 | 1.3 | 1.3.1.7.1 | C | Preliminary design phase | Complete | 5 | 40d | 2018-10-01 | 2018-11-23 |  | 100% |  |  |  | 1713 |  | 2018-10-01 | 2018-11-23 | 0
2285 | 1.3 | 1.3.1.7.2 | C | Final design phase | Complete | 5 | 240d | 2018-11-26 | 2019-10-25 | 2284 | 100% |  |  |  | 1713 |  | 2018-11-26 | 2019-10-25 | 0
2286 | 1.3 | 1.3.1.7.3 | C | Tender and procurement (test production) | Complete | 5 | 120d | 2020-04-22 | 2020-10-06 |  | 100% |  |  |  | 847 |  | 2020-04-22 | 2020-10-06 | 0
2287 | 1.3 | 1.3.1.7.4 | C | Tender and procurement (series production) | Complete | 5 | 200d | 2020-04-22 | 2021-01-26 | 2286SS, 2282FF | 100% |  |  |  | 847 |  | 2020-04-22 | 2021-01-26 | 0
2288 | 1.3 | 1.3.1.7.5 | P | Production in Wuppertal | Started | 5 | 266d | 2021-10-01 | 2022-10-07 |  | 25% |  |  |  | 943 |  | 2021-10-01 | 2022-10-07 | 0
2289 | 1.3 | 1.3.1.7.5.1 | C | Welding stand construction | Complete | 6 | 30d | 2021-10-01 | 2021-11-11 |  | 100% |  |  |  | 1179 |  | 2021-10-01 | 2021-11-11 | 0
2290 | 1.3 | 1.3.1.7.5.2 | C | Hire personnel | Complete | 6 | 30d | 2021-12-01 | 2022-01-11 |  | 100% |  |  |  | 1136 |  | 2021-12-01 | 2022-01-11 | 0
2291 | 1.3 | 1.3.1.7.5.3 | C | Start of mDOM Harness production | Complete | 6 | 0 | 2022-01-31 | 2022-01-31 |  | 100% |  |  |  | 943 |  | 2022-01-31 | 2022-01-31 | 0
2292 | 1.3 | 1.3.1.7.5.4 | C | Production of 50 harnesses | Started | 6 | 30d | 2022-01-31 | 2022-03-11 | 2291 | 2% |  |  |  | 943 |  | 2022-01-31 | 2022-03-11 | 0
2293 | 1.3 | 1.3.1.7.5.5 | C | Production of 50 harnesses | Not Started | 6 | 30d | 2022-03-14 | 2022-04-22 | 2292 | 0% |  |  |  | 943 |  | 2022-03-14 | 2022-04-22 | 0
2294 | 1.3 | 1.3.1.7.5.6 | C | Production of 100 harnesses | Not Started | 6 | 30d | 2022-04-25 | 2022-06-03 | 2293 | 0% |  |  |  | 943 |  | 2022-04-25 | 2022-06-03 | 0
2295 | 1.3 | 1.3.1.7.5.7 | C | Production of 100 harnesses | Not Started | 6 | 30d | 2022-06-06 | 2022-07-15 | 2294 | 0% |  |  |  | 943 |  | 2022-06-06 | 2022-07-15 | 0
2296 | 1.3 | 1.3.1.7.5.8 | C | Production of 100 harnesses | Not Started | 6 | 30d | 2022-07-18 | 2022-08-26 | 2295 | 0% |  |  |  | 943 |  | 2022-07-18 | 2022-08-26 | 0
2297 | 1.3 | 1.3.1.7.5.9 | C | Production of 50 harnesses | Not Started | 6 | 30d | 2022-08-29 | 2022-10-07 | 2296 | 0% |  |  |  | 943 |  | 2022-08-29 | 2022-10-07 | 0
2298 | 1.3 | 1.3.1.7.5.10 | C | mDOM Harness production completed | Not Started | 6 | 0 | 2022-10-07 | 2022-10-07 | 2297 | 0% |  |  |  | 943 |  | 2022-10-07 | 2022-10-07 | 0
2299 | 1.3 | 1.3.1.8 | P | Integrated mDOM | Started | 4 | 970d | 2018-10-01 | 2022-06-17 |  | 78% |  |  |  | 1023 |  | 2018-10-01 | 2022-06-17 | 0
2300 | 1.3 | 1.3.1.8.1 | P | Integrated module design | Started | 5 | 310d | 2018-10-01 | 2019-12-06 |  | 93% |  |  |  | 1683 |  | 2018-10-01 | 2019-12-06 | 0
2301 | 1.3 | 1.3.1.8.1.1 | C | Preliminary design phase | Complete | 6 | 100d | 2018-10-01 | 2019-02-15 |  | 100% |  |  |  | 909 |  | 2018-10-01 | 2019-02-15 | 0
2302 | 1.3 | 1.3.1.8.1.2 | C | Final design phase | Started | 6 | 210d | 2019-02-18 | 2019-12-06 | 2301 | 90% |  |  |  | 812 |  | 2019-02-18 | 2019-12-06 | 0
2303 | 1.3 | 1.3.1.8.2 | C | Packaging and shipping tools and procedures | Complete | 5 | 120d | 2019-11-06 | 2020-04-21 | 2302FS -23d | 100% |  |  |  | 847 |  | 2019-11-06 | 2020-04-21 | 0
2304 | 1.3 | 1.3.1.8.3 | C | Deployment tools and procedures | Complete | 5 | 120d | 2019-11-06 | 2020-04-21 | 2303SS | 100% |  |  |  | 847 |  | 2019-11-06 | 2020-04-21 | 0
2305 | 1.3 | 1.3.1.8.4 | C | Build 10 modules for DVT | Started | 5 | 20d | 2021-01-20 | 2021-02-16 | 2304FS +188d, 2287FS -5d | 60% |  |  |  | 847 |  | 2021-01-20 | 2021-02-16 | 0
2306 | 1.3 | 1.3.1.8.5 | C | DVT preparation using Rev. 1 Mainboard | Complete | 5 | 30d | 2021-02-17 | 2021-03-30 | 2305 | 100% |  |  |  | 847 |  | 2021-02-17 | 2021-03-30 | 0
2307 | 1.3 | 1.3.1.8.6 | C | Install Rev. 2 Mainboard in DVT mDOMs | Complete | 5 | 5d | 2021-03-31 | 2021-04-06 | 2306 | 100% |  |  |  | 847 |  | 2021-03-31 | 2021-04-06 | 0
2308 | 1.3 | 1.3.1.8.7 | C | Design Verification Testing | Started | 5 | 253d | 2021-04-07 | 2022-03-25 | 2307 | 50% |  |  |  | 847 |  | 2021-04-07 | 2022-03-25 | 0
2309 | 1.3 | 1.3.1.8.8 | C | mDOM Final Design Review | Not Started | 5 | 0 | 2022-03-25 | 2022-03-25 | 2308 | 0% |  |  |  | 827 |  | 2022-03-25 | 2022-03-25 | 0
2310 | 1.3 | 1.3.1.8.9 | C | Ship DVT modules to NTS | Not Started | 5 | 10d | 2022-03-28 | 2022-04-08 | 2309 | 0% |  |  |  | 1073 |  | 2022-03-28 | 2022-04-08 | 0
2311 | 1.3 | 1.3.1.8.10 | P | uBase UART Cable (ribbon cable) | Started | 5 | 150d | 2021-08-19 | 2022-03-16 |  | 85% |  |  |  | 1090 |  | 2021-08-19 | 2022-03-16 | 0
2312 | 1.3 | 1.3.1.8.10.1 | C | Purchase order signed | Complete | 6 | 0 | 2021-08-19 | 2021-08-19 |  | 100% |  |  |  | 1090 |  | 2021-08-19 | 2021-08-19 | 0
2313 | 1.3 | 1.3.1.8.10.2 | C | Production of ribbon cables | Started | 6 | 150d | 2021-08-19 | 2022-03-16 | 2312 | 85% | 30 weeks lead time due to non-availability of 3M connectors |  |  | 1090 |  | 2021-08-19 | 2022-03-16 | 0
2314 | 1.3 | 1.3.1.8.10.3 | C | Delivery of ribbon cables for 40 mDOMs | Complete | 6 | 0 | 2022-03-16 | 2022-03-16 |  | 100% | We reduced the initial production of flasher cables to get some uBase UART cables early |  |  | 1091 |  | 2022-03-16 | 2022-03-16 | 0
2315 | 1.3 | 1.3.1.8.10.4 | C | Delivery of ribbon cables for 440 mDOMs | Not Started | 6 | 0 | 2022-03-16 | 2022-03-16 | 2313 | 0% |  |  |  | 1090 |  | 2022-03-16 | 2022-03-16 | 0
2316 | 1.3 | 1.3.1.8.11 | P | uBase Signal Cable (coaxial cable) | Started | 5 | 185d | 2021-10-04 | 2022-06-17 |  | 61% |  |  |  | 1023 |  | 2021-10-04 | 2022-06-17 | 0
2317 | 1.3 | 1.3.1.8.11.1 | C | Decision of 50-ohm vs. 75-ohm cables | Complete | 6 | 0 | 2021-10-04 | 2021-10-04 |  | 100% |  |  |  | 1023 |  | 2021-10-04 | 2021-10-04 | 0
2318 | 1.3 | 1.3.1.8.11.2 | C | Vendor qualification | Complete | 6 | 60d | 2021-10-04 | 2021-12-24 | 2317 | 100% |  |  |  | 1023 |  | 2021-10-04 | 2021-12-24 | 0
2319 | 1.3 | 1.3.1.8.11.3 | C | Holiday Break | Complete | 6 | 5d | 2021-12-27 | 2021-12-31 | 2318 | 100% |  |  |  | 1023 |  | 2021-12-27 | 2021-12-31 | 0
2320 | 1.3 | 1.3.1.8.11.4 | C | Tender for coaxial cables | Started | 6 | 80d | 2022-01-03 | 2022-04-22 | 2319 | 35% |  |  |  | 1023 |  | 2022-01-03 | 2022-04-22 | 0
2321 | 1.3 | 1.3.1.8.11.5 | C | Production of coaxial cables | Started | 6 | 40d | 2022-04-25 | 2022-06-17 | 2320 | 50% |  |  |  | 1023 |  | 2022-04-25 | 2022-06-17 | 0
2322 | 1.3 | 1.3.1.8.11.6 | C | Delivery of coaxial cables | Not Started | 6 | 0 | 2022-06-17 | 2022-06-17 | 2321 | 0% |  |  |  | 1023 |  | 2022-06-17 | 2022-06-17 | 0
2323 | 1.3 | 1.3.1.9 | P | mDOM Production Facilities | Started | 4 | 965d | 2019-02-18 | 2022-10-28 |  | 77% |  |  |  | 928 |  | 2019-02-18 | 2022-10-28 | 0
2324 | 1.3 | 1.3.1.9.1 | P | DESY Production Facility | Started | 5 | 915d | 2019-02-18 | 2022-08-19 |  | 81% |  |  |  | 978 |  | 2019-02-18 | 2022-08-19 | 0
2325 | 1.3 | 1.3.1.9.1.1 | P | Set up facilities and hire personel | Started | 6 | 910d | 2019-02-18 | 2022-08-12 |  | 87% |  |  |  | 983 |  | 2019-02-18 | 2022-08-12 | 0
2326 | 1.3 | 1.3.1.9.1.1.1 | P | Production facilities | Started | 7 | 720d | 2019-02-18 | 2021-11-19 |  | 94% |  |  |  | 1173 |  | 2019-02-18 | 2021-11-19 | 0
2327 | 1.3 | 1.3.1.9.1.1.1.1 | C | Development of assembly procedures and tools | Complete | 8 | 180d | 2019-02-18 | 2019-10-25 |  | 100% |  |  |  | 1713 |  | 2019-02-18 | 2019-10-25 | 0
2328 | 1.3 | 1.3.1.9.1.1.1.2 | C | Tendering for HVAC | Complete | 8 | 23d | 2020-10-27 | 2020-11-26 |  | 100% |  |  |  | 1429 |  | 2020-10-27 | 2020-11-26 | 0
2329 | 1.3 | 1.3.1.9.1.1.1.3 | C | Installation of HVAC in Schoenefeld | Complete | 8 | 85d | 2021-01-04 | 2021-04-30 |  | 100% | Construction of facility in newly rented hall has commenced |  |  | 1318 |  | 2021-01-04 | 2021-04-30 | 0
2330 | 1.3 | 1.3.1.9.1.1.1.4 | C | Production site installation | Started | 8 | 20d | 2021-10-25 | 2021-11-19 |  | 66% |  |  |  | 1173 |  | 2021-10-25 | 2021-11-19 | 0
2331 | 1.3 | 1.3.1.9.1.1.1.5 | C | DESY production site ready | Should have Started | 8 | 0 | 2021-11-19 | 2021-11-19 | 2330 | 0% |  |  |  | 1173 |  | 2021-11-19 | 2021-11-19 | 0
2332 | 1.3 | 1.3.1.9.1.1.1.6 | C | Development of logistics and packaging to transport mDOMs between production and FAT sites | Started | 8 | 60d | 2021-01-04 | 2021-03-26 |  | 75% |  |  |  | 1343 |  | 2021-01-04 | 2021-03-26 | 0
2333 | 1.3 | 1.3.1.9.1.1.2 | P | FAT facilities | Started | 7 | 130d | 2022-01-03 | 2022-07-01 |  | 23% |  |  |  | 1013 |  | 2022-01-03 | 2022-07-01 | 0
2334 | 1.3 | 1.3.1.9.1.1.2.1 | C | Design room temperature FAT | Started | 8 | 50d | 2022-01-03 | 2022-03-11 |  | 60% | Identified resources at universities Mainz and Erlangen to work on this in the context of the German university funding |  |  | 1058 |  | 2022-01-03 | 2022-03-11 | 0
2335 | 1.3 | 1.3.1.9.1.1.2.2 | C | Construction of room temperature FAT setup | Not Started | 8 | 20d | 2022-03-14 | 2022-04-08 | 2334 | 0% | Identified resources at universities Mainz and Erlangen to work on this in the context of the German university funding |  |  | 1058 |  | 2022-03-14 | 2022-04-08 | 0
2336 | 1.3 | 1.3.1.9.1.1.2.3 | C | Commissioning of room temperature FAT setup | Not Started | 8 | 15d | 2022-04-11 | 2022-04-29 | 2335 | 0% |  |  |  | 1058 |  | 2022-04-11 | 2022-04-29 | 0
2337 | 1.3 | 1.3.1.9.1.1.2.4 | C | DFL Commissioning Phase 1 | Not Started | 8 | 40d | 2022-03-14 | 2022-05-06 |  | 0% |  |  |  | 1053 |  | 2022-03-14 | 2022-05-06 | 0
2338 | 1.3 | 1.3.1.9.1.1.2.5 | C | DFL Commissioning Phase 2 | Not Started | 8 | 5d | 2022-06-27 | 2022-07-01 | 2342 |  |  |  |  | 978 |  | 2022-06-27 | 2022-07-01 | 0
2339 | 1.3 | 1.3.1.9.1.1.2.6 | C | DESY DFL fully commissioned | Not Started | 8 | 0 | 2022-07-01 | 2022-07-01 | 2336, 2338 | 0% |  |  |  | 1013 |  | 2022-07-01 | 2022-07-01 | 0
2340 | 1.3 | 1.3.1.9.1.1.3 | C | Personnel | Complete | 7 | 240d | 2019-08-01 | 2020-07-01 |  | 100% |  |  |  | 1535 |  | 2019-08-01 | 2020-07-01 | 0
2341 | 1.3 | 1.3.1.9.1.1.4 | C | mDOM Production Readiness Review (in Germany) | Not Started | 7 | 0 | 2022-08-12 | 2022-08-12 | 2343 | 0% |  |  |  | 983 |  | 2022-08-12 | 2022-08-12 | 0
2342 | 1.3 | 1.3.1.9.1.2 | C | Test production (Batch #0, Qty. 20) | Not Started | 6 | 30d | 2022-05-16 | 2022-06-24 |  | 0% | Key personnel not available earlier |  |  | 683 |  | 2022-05-16 | 2022-06-24 | 0
2343 | 1.3 | 1.3.1.9.1.3 | C | FAT Test Production | Not Started | 6 | 30d | 2022-07-04 | 2022-08-12 | 2338 | 0% |  |  |  | 978 |  | 2022-07-04 | 2022-08-12 | 0
2344 | 1.3 | 1.3.1.9.1.4 | C | Packing Test Production | Not Started | 6 | 5d | 2022-08-15 | 2022-08-19 | 2343 | 0% |  |  |  | 978 |  | 2022-08-15 | 2022-08-19 | 0
2345 | 1.3 | 1.3.1.9.1.5 | C | Transfer equipment from temporary production site to Schoenefeld | Complete | 6 | 5d | 2021-07-26 | 2021-07-30 |  | 100% |  |  |  | 1253 |  | 2021-07-26 | 2021-07-30 | 0
2346 | 1.3 | 1.3.1.9.2 | P | MSU Production Facility | Started | 5 | 847d | 2019-08-01 | 2022-10-28 |  | 72% |  |  |  | 928 |  | 2019-08-01 | 2022-10-28 | 0
2347 | 1.3 | 1.3.1.9.2.1 | P | Set up facilities and hire personel | Started | 6 | 842d | 2019-08-01 | 2022-10-21 |  | 81% |  |  |  | 933 |  | 2019-08-01 | 2022-10-21 | 0
2348 | 1.3 | 1.3.1.9.2.1.1 | C | Production Facilities | Complete | 7 | 170d | 2019-08-01 | 2020-03-25 |  | 100% |  |  |  | 1605 |  | 2019-08-01 | 2020-03-25 | 0
2349 | 1.3 | 1.3.1.9.2.1.2 | P | FAT Facilities | Started | 7 | 115d | 2022-02-07 | 2022-07-15 |  | 14% |  |  |  | 1003 |  | 2022-02-07 | 2022-07-15 | 0
2350 | 1.3 | 1.3.1.9.2.1.2.1 | C | Optical FAT construction | Not Started | 8 | 15d | 2022-06-06 | 2022-06-24 | [5 empty] | 1003 |  | 2022-06-06 | 2022-06-24 | 0
2351 | 1.3 | 1.3.1.9.2.1.2.2 | C | Optical FAT comissioning | Not Started | 8 | 15d | 2022-06-27 | 2022-07-15 | 2350 |  |  |  |  | 1003 |  | 2022-06-27 | 2022-07-15 | 0
2352 | 1.3 | 1.3.1.9.2.1.2.3 | C | DFL comissioning | Complete | 8 | 5d | 2022-02-07 | 2022-02-11 |  | 100% |  |  |  | 1113 |  | 2022-02-07 | 2022-02-11 | 0
2353 | 1.3 | 1.3.1.9.2.1.3 | C | Personnel | Complete | 7 | 240d | 2019-08-01 | 2020-07-01 |  | 100% |  |  |  | 1535 |  | 2019-08-01 | 2020-07-01 | 0
2354 | 1.3 | 1.3.1.9.2.1.4 | C | mDOM Production Readiness Review (in US at MSU) | Not Started | 7 | 0 | 2022-10-21 | 2022-10-21 | 2356 | 0% |  |  |  | 933 |  | 2022-10-21 | 2022-10-21 | 0
2355 | 1.3 | 1.3.1.9.2.2 | C | Test production (Batch #0, Qty. 20) | Not Started | 6 | 30d | 2022-08-01 | 2022-09-09 | 2358 | 0% |  |  |  | 928 |  | 2022-08-01 | 2022-09-09 | 0
2356 | 1.3 | 1.3.1.9.2.3 | C | FAT Test Production | Not Started | 6 | 30d | 2022-09-12 | 2022-10-21 | 2355 | 0% |  |  |  | 928 |  | 2022-09-12 | 2022-10-21 | 0
2357 | 1.3 | 1.3.1.9.2.4 | C | Packing Test Production | Not Started | 6 | 5d | 2022-10-24 | 2022-10-28 | 2356 | 0% |  |  |  | 928 |  | 2022-10-24 | 2022-10-28 | 0
2358 | 1.3 | 1.3.1.9.2.5 | C | Shipping of mDOM components from DESY to MSU | Not Started | 6 | 40d | 2022-06-06 | 2022-07-29 |  | 0% |  |  |  | 928 |  | 2022-06-06 | 2022-07-29 | 0
2359 | 1.3 | 1.3.1.10 | P | mDOM Series Production | Not Started | 4 | 843d | 2022-06-24 | 2025-09-25 |  | 0% |  |  |  | 175 |  | 2022-06-24 | 2025-09-25 | 0
2360 | 1.3 | 1.3.1.10.1 | P | Series Production | Not Started | 5 | 320d | 2022-06-24 | 2023-09-15 |  | 0% |  |  |  | 698 |  | 2022-06-24 | 2023-09-15 | 0
2361 | 1.3 | 1.3.1.10.1.1 | P | DESY Production Facility | Not Started | 6 | 295d | 2022-06-24 | 2023-08-11 |  | 0% |  |  |  | 723 |  | 2022-06-24 | 2023-08-11 | 0
2362 | 1.3 | 1.3.1.10.1.1.1 | C | Start of mDOM series production at DESY | Not Started | 7 | 0 | 2022-06-24 | 2022-06-24 | 2259SS +15d, 2342 | 0% |  |  |  | 683 |  | 2022-06-24 | 2022-06-24 | 0
2363 | 1.3 | 1.3.1.10.1.1.2 | C | Integration of (54) half-mDOMs (Batch #1) | Not Started | 7 | 30d | 2022-06-27 | 2022-08-05 | 2362 | 0% | Seal (1) mDOM / week to check for bubbles or delaminations (Q: Do half-modules need to be stored at 500 mbar to avoid bubbles?). Need storage space for half-mDOMs/ |  |  | 683 |  | 2022-06-27 | 2022-08-05 | 0
2364 | 1.3 | 1.3.1.10.1.1.3 | C | Integration of (54) half-mDOMs (Batch #2) | Not Started | 7 | 20d | 2022-08-08 | 2022-09-02 | 2260, 2363 | 0% | Seal (1) mDOM / week to check for bubbles or delaminations (Q: Do half-modules need to be stored at 500 mbar to avoid bubbles?). Need storage space for half-mDOMs/ |  |  | 683 |  | 2022-08-08 | 2022-09-02 | 0
2365 | 1.3 | 1.3.1.10.1.1.4 | C | Integration of (54) half-mDOMs (Batch #3) | Not Started | 7 | 20d | 2022-09-05 | 2022-09-30 | 2261, 2364 | 0% | Seal (1) mDOM / week to check for bubbles or delaminations (Q: Do half-modules need to be stored at 500 mbar to avoid bubbles?). Need storage space for half-mDOMs/ |  |  | 683 |  | 2022-09-05 | 2022-09-30 | 0
2366 | 1.3 | 1.3.1.10.1.1.5 | C | Integration of (54) half-mDOMs (Batch #4) | Not Started | 7 | 15d | 2022-10-03 | 2022-10-21 | 2262, 2365 | 0% | Seal (1) mDOM / week to check for bubbles or delaminations (Q: Do half-modules need to be stored at 500 mbar to avoid bubbles?). Need storage space for half-mDOMs/ |  |  | 683 |  | 2022-10-03 | 2022-10-21 | 0
2367 | 1.3 | 1.3.1.10.1.1.6 | C | Mainboard integration and sealing Batch #1, pt. 1 | Not Started | 7 | 5d | 2022-12-19 | 2022-12-23 | 2102SS +15d | 0% |  |  |  | 683 |  | 2022-12-19 | 2022-12-23 | 0
2368 | 1.3 | 1.3.1.10.1.1.7 | C | Holiday Break | Not Started | 7 | 5d | 2022-12-26 | 2022-12-30 | 2367 | 0% |  |  |  | 683 |  | 2022-12-26 | 2022-12-30 | 0
2369 | 1.3 | 1.3.1.10.1.1.8 | C | Mainboard integration and sealing Batch #1, pt. 2 | Not Started | 7 | 10d | 2023-01-02 | 2023-01-13 | 2368 | 0% |  |  |  | 683 |  | 2023-01-02 | 2023-01-13 | 0
2370 | 1.3 | 1.3.1.10.1.1.9 | C | FAT Batch #1 | Not Started | 7 | 30d | 2023-01-16 | 2023-02-24 | 2369 | 0% |  |  |  | 683 |  | 2023-01-16 | 2023-02-24 | 0
2371 | 1.3 | 1.3.1.10.1.1.10 | C | Mounting of harness wires and packing (Batch #1) | Not Started | 7 | 5d | 2023-02-27 | 2023-03-03 | 2370 | 0% |  |  |  | 838 |  | 2023-02-27 | 2023-03-03 | 0
2372 | 1.3 | 1.3.1.10.1.1.11 | C | Mainboard integration and sealing Batch #2 | Not Started | 7 | 10d | 2023-01-16 | 2023-01-27 | 2364, 2369 | 0% |  |  |  | 683 |  | 2023-01-16 | 2023-01-27 | 0
2373 | 1.3 | 1.3.1.10.1.1.12 | C | FAT Batch #2 | Not Started | 7 | 20d | 2023-02-27 | 2023-03-24 | 2370, 2372 | 0% |  |  |  | 683 |  | 2023-02-27 | 2023-03-24 | 0
2374 | 1.3 | 1.3.1.10.1.1.13 | C | Mounting of harness wires and packing (Batch #2) | Not Started | 7 | 5d | 2023-03-27 | 2023-03-31 | 2373 | 0% |  |  |  | 818 |  | 2023-03-27 | 2023-03-31 | 0
2375 | 1.3 | 1.3.1.10.1.1.14 | C | Mainboard integration and sealing Batch #3 | Not Started | 7 | 10d | 2023-01-30 | 2023-02-10 | 2365, 2372 | 0% |  |  |  | 683 |  | 2023-01-30 | 2023-02-10 | 0
2376 | 1.3 | 1.3.1.10.1.1.15 | C | FAT Batch #3 | Not Started | 7 | 20d | 2023-03-27 | 2023-04-21 | 2373, 2375 | 0% |  |  |  | 683 |  | 2023-03-27 | 2023-04-21 | 0
2377 | 1.3 | 1.3.1.10.1.1.16 | C | Mounting of harness wires and packing (Batch #3) | Not Started | 7 | 5d | 2023-04-24 | 2023-04-28 | 2376 | 0% |  |  |  | 798 |  | 2023-04-24 | 2023-04-28 | 0
2378 | 1.3 | 1.3.1.10.1.1.17 | C | Mainboard integration and sealing Batch #4 | Not Started | 7 | 10d | 2023-02-13 | 2023-02-24 | 2366, 2375 | 0% |  |  |  | 683 |  | 2023-02-13 | 2023-02-24 | 0
2379 | 1.3 | 1.3.1.10.1.1.18 | C | FAT Batch #4 | Not Started | 7 | 15d | 2023-04-24 | 2023-05-12 | 2376, 2378 | 0% |  |  |  | 683 |  | 2023-04-24 | 2023-05-12 | 0
2380 | 1.3 | 1.3.1.10.1.1.19 | C | Mounting of harness wires and packing (Batch #4) | Not Started | 7 | 5d | 2023-05-15 | 2023-05-19 | 2379 | 0% |  |  |  | 703 |  | 2023-05-15 | 2023-05-19 | 0
2381 | 1.3 | 1.3.1.10.1.1.20 | C | 128 mDOMs for Strings 87-88 ready to ship to CHC | Not Started | 7 | 0 | 2023-05-19 | 2023-05-19 | 2380 | 0% |  |  |  | 703 |  | 2023-05-19 | 2023-05-19 | 0
2382 | 1.3 | 1.3.1.10.1.1.21 | C | Production Batch #5 (Qty. 27) | Not Started | 7 | 15d | 2023-03-06 | 2023-03-24 | 2271FS +15d, 2378 | 0% |  |  |  | 683 |  | 2023-03-06 | 2023-03-24 | 0
2383 | 1.3 | 1.3.1.10.1.1.22 | C | FAT Batch #5 | Not Started | 7 | 15d | 2023-05-15 | 2023-06-02 | 2379, 2382 | 0% |  |  |  | 683 |  | 2023-05-15 | 2023-06-02 | 0
2384 | 1.3 | 1.3.1.10.1.1.23 | C | Mounting of harness wires and packing (Batch #5) | Not Started | 7 | 5d | 2023-06-05 | 2023-06-09 | 2383 | 0% |  |  |  | 768 |  | 2023-06-05 | 2023-06-09 | 0
2385 | 1.3 | 1.3.1.10.1.1.24 | C | Production Batch #6 (Qty. 27) | Not Started | 7 | 15d | 2023-03-27 | 2023-04-14 | 2272, 2382 | 0% |  |  |  | 683 |  | 2023-03-27 | 2023-04-14 | 0
2386 | 1.3 | 1.3.1.10.1.1.25 | C | FAT Batch #6 | Not Started | 7 | 15d | 2023-06-05 | 2023-06-23 | 2383, 2385 | 0% |  |  |  | 683 |  | 2023-06-05 | 2023-06-23 | 0
2387 | 1.3 | 1.3.1.10.1.1.26 | C | Mounting of harness wires and packing (Batch #6) | Not Started | 7 | 5d | 2023-06-26 | 2023-06-30 | 2386 | 0% |  |  | Activity Renamed | 753 |  | 2023-06-26 | 2023-06-30 | 0
2388 | 1.3 | 1.3.1.10.1.1.27 | C | Production Batch #7 (Qty. 27) | Not Started | 7 | 15d | 2023-04-17 | 2023-05-05 | 2273, 2385 | 0% |  |  | New Activity | 683 |  | 2023-04-17 | 2023-05-05 | 0
2389 | 1.3 | 1.3.1.10.1.1.28 | C | FAT Batch #7 | Not Started | 7 | 15d | 2023-06-26 | 2023-07-14 | 2386, 2388 | 0% |  |  | New Activity | 683 |  | 2023-06-26 | 2023-07-14 | 0
2390 | 1.3 | 1.3.1.10.1.1.29 | C | Mounting of harness wires and packing (Batch #7) | Not Started | 7 | 5d | 2023-07-17 | 2023-07-21 | 2389 | 0% |  |  |  | 738 |  | 2023-07-17 | 2023-07-21 | 0
2391 | 1.3 | 1.3.1.10.1.1.30 | C | Production Batch #8 (Qty. 16) | Not Started | 7 | 15d | 2023-04-17 | 2023-05-05 | 2274, 2385 | 0% |  |  |  | 733 |  | 2023-04-17 | 2023-05-05 | 0
2392 | 1.3 | 1.3.1.10.1.1.31 | C | FAT Batch #8 | Not Started | 7 | 15d | 2023-07-17 | 2023-08-04 | 2389, 2391 | 0% |  |  |  | 683 |  | 2023-07-17 | 2023-08-04 | 0
2393 | 1.3 | 1.3.1.10.1.1.32 | C | Mounting of harness wires and packing (Batch #8) | Not Started | 7 | 5d | 2023-08-07 | 2023-08-11 | 2392 | 0% |  |  |  | 683 |  | 2023-08-07 | 2023-08-11 | 0
2394 | 1.3 | 1.3.1.10.1.1.33 | C | 96 mDOMs for Strings 89-93 ready to ship to CHC | Not Started | 7 | 0 | 2023-08-11 | 2023-08-11 | 2393 | 0% |  |  |  | 683 |  | 2023-08-11 | 2023-08-11 | 0
2395 | 1.3 | 1.3.1.10.1.2 | P | MSU Production Facility | Not Started | 6 | 140d | 2023-03-03 | 2023-09-15 |  | 0% |  |  |  | 698 |  | 2023-03-03 | 2023-09-15 | 0
2396 | 1.3 | 1.3.1.10.1.2.1 | C | Start of mDOM series production at MSU | Not Started | 7 | 0 | 2023-03-03 | 2023-03-03 | 2270 | 0% |  |  |  | 678 |  | 2023-03-03 | 2023-03-03 | 0
2397 | 1.3 | 1.3.1.10.1.2.2 | C | Production Batch #1 (Qty. 27) | Not Started | 7 | 20d | 2023-03-06 | 2023-03-31 | 2396 | 0% |  |  |  | 678 |  | 2023-03-06 | 2023-03-31 | 0
2398 | 1.3 | 1.3.1.10.1.2.3 | C | FAT Batch #1 | Not Started | 7 | 20d | 2023-04-03 | 2023-04-28 | 2397 | 0% |  |  |  | 678 |  | 2023-04-03 | 2023-04-28 | 0
2399 | 1.3 | 1.3.1.10.1.2.4 | C | Mounting of harness wires and packing (Batch #1) | Not Started | 7 | 5d | 2023-05-01 | 2023-05-05 | 2398 | 0% |  |  |  | 793 |  | 2023-05-01 | 2023-05-05 | 0
2400 | 1.3 | 1.3.1.10.1.2.5 | C | Production Batch #2 (Qty. 27) | Not Started | 7 | 20d | 2023-04-03 | 2023-04-28 | 2397 | 0% |  |  |  | 678 |  | 2023-04-03 | 2023-04-28 | 0
2401 | 1.3 | 1.3.1.10.1.2.6 | C | FAT Batch #2 | Not Started | 7 | 20d | 2023-05-01 | 2023-05-26 | 2398, 2400 | 0% |  |  |  | 678 |  | 2023-05-01 | 2023-05-26 | 0
2402 | 1.3 | 1.3.1.10.1.2.7 | C | Mounting of harness wires and packing (Batch #2) | Not Started | 7 | 5d | 2023-05-29 | 2023-06-02 | 2401 | 0% |  |  |  | 773 |  | 2023-05-29 | 2023-06-02 | 0
2403 | 1.3 | 1.3.1.10.1.2.8 | C | Production Batch #3 (Qty. 27) | Not Started | 7 | 15d | 2023-05-01 | 2023-05-19 | 2400 | 0% |  |  |  | 678 |  | 2023-05-01 | 2023-05-19 | 0
2404 | 1.3 | 1.3.1.10.1.2.9 | C | FAT Batch #3 | Not Started | 7 | 15d | 2023-05-29 | 2023-06-16 | 2401, 2403 | 0% |  |  |  | 678 |  | 2023-05-29 | 2023-06-16 | 0
2405 | 1.3 | 1.3.1.10.1.2.10 | C | Mounting of harness wires and packing (Batch #3) | Not Started | 7 | 5d | 2023-06-19 | 2023-06-23 | 2404 | 0% |  |  |  | 758 |  | 2023-06-19 | 2023-06-23 | 0
2406 | 1.3 | 1.3.1.10.1.2.11 | C | Production Batch #4 (Qty. 27) | Not Started | 7 | 15d | 2023-05-22 | 2023-06-09 | 2403 | 0% |  |  |  | 678 |  | 2023-05-22 | 2023-06-09 | 0
2407 | 1.3 | 1.3.1.10.1.2.12 | C | FAT Batch #4 | Not Started | 7 | 15d | 2023-06-19 | 2023-07-07 | 2404, 2406 | 0% |  |  |  | 678 |  | 2023-06-19 | 2023-07-07 | 0
2408 | 1.3 | 1.3.1.10.1.2.13 | C | Mounting of harness wires and packing (Batch #4) | Not Started | 7 | 5d | 2023-07-10 | 2023-07-14 | 2407 | 0% |  |  |  | 743 |  | 2023-07-10 | 2023-07-14 | 0
2409 | 1.3 | 1.3.1.10.1.2.14 | C | Production Batch #5 (Qty. 27) | Not Started | 7 | 15d | 2023-06-12 | 2023-06-30 | 2406 | 0% |  |  |  | 678 |  | 2023-06-12 | 2023-06-30 | 0
2410 | 1.3 | 1.3.1.10.1.2.15 | C | FAT Batch #5 | Not Started | 7 | 15d | 2023-07-10 | 2023-07-28 | 2407, 2409 | 0% |  |  |  | 678 |  | 2023-07-10 | 2023-07-28 | 0
2411 | 1.3 | 1.3.1.10.1.2.16 | C | Mounting of harness wires and packing (Batch #5) | Not Started | 7 | 5d | 2023-07-31 | 2023-08-04 | 2410 | 0% |  |  |  | 728 |  | 2023-07-31 | 2023-08-04 | 0
2412 | 1.3 | 1.3.1.10.1.2.17 | C | Production Batch #6 (Qty. 27) | Not Started | 7 | 15d | 2023-07-03 | 2023-07-21 | 2409 | 0% |  |  |  | 678 |  | 2023-07-03 | 2023-07-21 | 0
2413 | 1.3 | 1.3.1.10.1.2.18 | C | FAT Batch #6 | Not Started | 7 | 15d | 2023-07-31 | 2023-08-18 | 2410, 2412 | 0% |  |  | Activity Renamed | 678 |  | 2023-07-31 | 2023-08-18 | 0
2414 | 1.3 | 1.3.1.10.1.2.19 | C | Mounting of harness wires and packing (Batch #6) | Not Started | 7 | 5d | 2023-08-21 | 2023-08-25 | 2413 | 0% |  |  | New Activity | 713 |  | 2023-08-21 | 2023-08-25 | 0
2415 | 1.3 | 1.3.1.10.1.2.20 | C | Production Batch #7 (Qty. 23) | Not Started | 7 | 15d | 2023-07-24 | 2023-08-11 | 2412 | 0% |  |  |  | 683 |  | 2023-07-24 | 2023-08-11 | 0
2416 | 1.3 | 1.3.1.10.1.2.21 | C | FAT Batch #7 | Not Started | 7 | 15d | 2023-08-21 | 2023-09-08 | 2413, 2415 | 0% |  |  |  | 678 |  | 2023-08-21 | 2023-09-08 | 0
2417 | 1.3 | 1.3.1.10.1.2.22 | C | Mounting of harness wires and packing (Batch #7) | Not Started | 7 | 5d | 2023-09-11 | 2023-09-15 | 2416 | 0% |  |  |  | 678 |  | 2023-09-11 | 2023-09-15 | 0
2418 | 1.3 | 1.3.1.10.1.2.23 | C | 200 mDOMs for Strings 89-93 ready to ship to Pt. Hueneme | Not Started | 7 | 0 | 2023-09-15 | 2023-09-15 | 2417 | 0% |  |  |  | 678 |  | 2023-09-15 | 2023-09-15 | 0
2419 | 1.3 | 1.3.1.10.2 | C | Ship 116 + 12 spare mDOMs for Strings 87-88 from DESY to CHC | Not Started | 5 | 40d | 2024-08-01 | 2024-09-25 | 2381FS +310d | 0% |  |  |  | 393 |  | 2024-08-01 | 2024-09-25 | 0
2420 | 1.3 | 1.3.1.10.3 | C | Ship 96 mDOMs for Strings 89-93 from DESY to CHC | Not Started | 5 | 40d | 2025-08-01 | 2025-09-25 | 2394FS +508d | 0% |  |  |  | 175 |  | 2025-08-01 | 2025-09-25 | 0
2421 | 1.3 | 1.3.1.10.4 | C | Ship 190 + 10 spare mDOMs for Strings 89-93 from MSU to Pt. Hueneme | Not Started | 5 | 20d | 2025-08-01 | 2025-08-28 | 2418FS +483d | 0% |  |  |  | 195 |  | 2025-08-01 | 2025-08-28 | 0
2422 | 1.3 | 1.3.2 | P | D-Egg | Started | 3 | 1838d | 2018-10-01 | 2025-10-23 |  | 84% |  |  |  | 155 |  | 2018-10-01 | 2025-10-23 | 0
2423 | 1.3 | 1.3.2.1 | P | D-Egg DAQ Electronics | Complete | 4 | 653d | 2018-10-01 | 2021-03-31 |  | 100% |  |  |  | 1340 |  | 2018-10-01 | 2021-03-31 | 0
2424 | 1.3 | 1.3.2.1.1 | P | Preliminary design phase | Complete | 5 | 251d | 2018-10-01 | 2019-09-16 |  | 100% |  |  |  | 1742 |  | 2018-10-01 | 2019-09-16 | 0
2425 | 1.3 | 1.3.2.1.1.1 | C | Rev. 2 mainboard schematics and layout | Complete | 6 | 175d | 2018-10-01 | 2019-05-31 |  | 100% |  |  | Activity Renamed | 1732 |  | 2018-10-01 | 2019-05-31 | 0
2426 | 1.3 | 1.3.2.1.1.2 | C | Rev. 2 mainboard production | Complete | 6 | 15d | 2019-06-03 | 2019-06-21 | 2425 | 100% |  |  |  | 1732 |  | 2019-06-03 | 2019-06-21 | 0
2427 | 1.3 | 1.3.2.1.1.3 | C | Rev. 2 mainboard prototypes available | Complete | 6 | 1d | 2019-06-24 | 2019-06-24 | 2426 | 100% |  |  |  | 1732 |  | 2019-06-24 | 2019-06-24 | 0
2428 | 1.3 | 1.3.2.1.1.4 | C | Rev. 2 mainboard testing | Complete | 6 | 60d | 2019-06-25 | 2019-09-16 | 2427 | 100% | Delays in development. Dates are driven by Japanese funding agency, not the project needs |  |  | 1732 |  | 2019-06-25 | 2019-09-16 | 0
2429 | 1.3 | 1.3.2.1.1.5 | C | Rev. 2 mainboard communication tests | Complete | 6 | 10d | 2019-08-20 | 2019-09-02 | 2428FF -10d | 100% | Scheduled for 2020-01-10 |  |  | 1752 |  | 2019-08-20 | 2019-09-02 | 0
2430 | 1.3 | 1.3.2.1.2 | P | Final design phase | Complete | 5 | 501d | 2019-05-01 | 2021-03-31 |  | 100% |  |  |  | 1340 |  | 2019-05-01 | 2021-03-31 | 0
2431 | 1.3 | 1.3.2.1.2.1 | C | Rev. 3 mainboard design | Complete | 6 | 40d | 2019-07-08 | 2019-08-30 |  | 100% | Delays in development. Dates are driven by Japanese funding agency, not the project needs |  |  | 1578 |  | 2019-07-08 | 2019-08-30 | 0
2432 | 1.3 | 1.3.2.1.2.2 | C | Firmware development | Complete | 6 | 501d | 2019-05-01 | 2021-03-31 |  | 100% | Delays in development. Dates are driven by Japanese funding agency, not the project needs |  |  | 1340 |  | 2019-05-01 | 2021-03-31 | 0
2433 | 1.3 | 1.3.2.1.2.3 | C | Production of 15 Rev. 3 mainboards for DVT | Complete | 6 | 25d | 2019-09-02 | 2019-10-04 | 2431 | 100% | Delays in development. Dates are driven by Japanese funding agency, not the project needs |  | Activity Renamed | 1578 |  | 2019-09-02 | 2019-10-04 | 0
2434 | 1.3 | 1.3.2.1.2.4 | C | Commissioning and Design Verification | Complete | 6 | 20d | 2019-10-07 | 2019-11-01 | 2433 | 100% | Delays in development. Dates are driven by Japanese funding agency, not the project needs |  | Activity Renamed | 1578 |  | 2019-10-07 | 2019-11-01 | 0
2435 | 1.3 | 1.3.2.1.3 | C | Production | Complete | 5 | 80d | 2019-10-21 | 2020-02-07 | 2434FS -10d | 100% | Delays in development. Dates are driven by Japanese funding agency, not the project needs |  |  | 1588 |  | 2019-10-21 | 2020-02-07 | 0
2436 | 1.3 | 1.3.2.1.4 | C | Testing | Complete | 5 | 50d | 2019-12-09 | 2020-02-14 | 2435SS +35d | 100% | Delays in development. Dates are driven by Japanese funding agency, not the project needs |  |  | 1633 |  | 2019-12-09 | 2020-02-14 | 0
2437 | 1.3 | 1.3.2.2 | P | D-Egg PMT | Complete | 4 | 281d | 2018-10-01 | 2019-10-28 |  | 100% |  |  |  | 1712 |  | 2018-10-01 | 2019-10-28 | 0
2438 | 1.3 | 1.3.2.2.1 | P | PMT Production | Complete | 5 | 281d | 2018-10-01 | 2019-10-28 |  | 100% |  |  |  | 1712 |  | 2018-10-01 | 2019-10-28 | 0
2439 | 1.3 | 1.3.2.2.1.1 | C | PMT Batch #1 (Qty. 300) | Complete | 6 | 80d | 2018-10-01 | 2019-01-18 |  | 100% |  |  |  | 1913 |  | 2018-10-01 | 2019-01-18 | 0
2440 | 1.3 | 1.3.2.2.1.2 | C | PMT Batch #2 (Qty. 300) | Complete | 6 | 120d | 2019-04-01 | 2019-09-13 |  | 100% |  |  |  | 1743 |  | 2019-04-01 | 2019-09-13 | 0
2441 | 1.3 | 1.3.2.2.1.3 | C | PMT Spares (Qty. 15) | Complete | 6 | 20d | 2019-10-01 | 2019-10-28 |  | 100% |  |  |  | 1712 |  | 2019-10-01 | 2019-10-28 | 0
2442 | 1.3 | 1.3.2.3 | P | D-Egg High Voltage Subsystem | Complete | 4 | 330d | 2018-10-01 | 2020-01-03 |  | 100% |  |  |  | 1663 |  | 2018-10-01 | 2020-01-03 | 0
2443 | 1.3 | 1.3.2.3.1 | C | Preliminary design phase | Complete | 5 | 120d | 2018-10-01 | 2019-03-15 |  | 100% |  |  |  | 1873 |  | 2018-10-01 | 2019-03-15 | 0
2444 | 1.3 | 1.3.2.3.2 | C | Final design phase | Complete | 5 | 100d | 2019-04-01 | 2019-08-16 |  | 100% |  |  |  | 1763 |  | 2019-04-01 | 2019-08-16 | 0
2445 | 1.3 | 1.3.2.3.3 | P | Tender and procurement | Complete | 5 | 310d | 2018-10-01 | 2019-12-06 |  | 100% |  |  |  | 1683 |  | 2018-10-01 | 2019-12-06 | 0
2446 | 1.3 | 1.3.2.3.3.1 | C | Ferrite core (Qty. 600) | Complete | 6 | 20d | 2018-10-01 | 2018-10-26 |  | 100% |  |  |  | 1973 |  | 2018-10-01 | 2018-10-26 | 0
2447 | 1.3 | 1.3.2.3.3.2 | C | HV generator (Qty. 600) | Complete | 6 | 60d | 2019-09-04 | 2019-11-26 |  | 100% | Delays in development. Dates are driven by Japanese funding agency, not the project needs |  |  | 1691 |  | 2019-09-04 | 2019-11-26 | 0
2448 | 1.3 | 1.3.2.3.3.3 | C | HV board (Qty. 600) | Complete | 6 | 60d | 2019-09-16 | 2019-12-06 |  | 100% | Delays in development. Dates are driven by Japanese funding agency, not the project needs |  |  | 1683 |  | 2019-09-16 | 2019-12-06 | 0
2449 | 1.3 | 1.3.2.3.4 | C | Acceptance testing | Complete | 5 | 60d | 2019-10-14 | 2020-01-03 |  | 100% | Delays in development. Dates are driven by Japanese funding agency, not the project needs |  | Activity Renamed | 1663 |  | 2019-10-14 | 2020-01-03 | 0
2450 | 1.3 | 1.3.2.4 | P | D-Egg Pressure Vessel | Complete | 4 | 673d | 2018-10-01 | 2021-04-28 |  | 100% |  |  |  | 1320 |  | 2018-10-01 | 2021-04-28 | 0
2451 | 1.3 | 1.3.2.4.1 | P | Pressure Vessel production | Complete | 5 | 673d | 2018-10-01 | 2021-04-28 |  | 100% |  |  |  | 1320 |  | 2018-10-01 | 2021-04-28 | 0
2452 | 1.3 | 1.3.2.4.1.1 | C | PV Batch #1 (Qty. 40) | Complete | 6 | 40d | 2018-10-01 | 2018-11-23 |  | 100% |  |  |  | 1953 |  | 2018-10-01 | 2018-11-23 | 0
2453 | 1.3 | 1.3.2.4.1.2 | C | PV Batch #2 (Qty. 130) | Complete | 6 | 60d | 2019-04-01 | 2019-06-21 |  | 100% |  |  |  | 1803 |  | 2019-04-01 | 2019-06-21 | 0
2454 | 1.3 | 1.3.2.4.1.3 | C | PV Batch #3 (Qty. 130) | Complete | 6 | 60d | 2020-04-01 | 2020-06-23 |  | 100% |  |  |  | 1541 |  | 2020-04-01 | 2020-06-23 | 0
2455 | 1.3 | 1.3.2.4.1.4 | C | PV Spare | Complete | 6 | 20d | 2021-04-01 | 2021-04-28 |  | 100% |  |  |  | 1320 |  | 2021-04-01 | 2021-04-28 | 0
2456 | 1.3 | 1.3.2.5 | P | D-Egg Optical Gel | Complete | 4 | 323d | 2018-10-01 | 2019-12-25 |  | 100% |  |  |  | 1670 |  | 2018-10-01 | 2019-12-25 | 0
2457 | 1.3 | 1.3.2.5.1 | C | Final design phase | Complete | 5 | 120d | 2018-10-01 | 2019-03-15 |  | 100% |  |  |  | 1813 |  | 2018-10-01 | 2019-03-15 | 0
2458 | 1.3 | 1.3.2.5.2 | C | Procurement of optical gel for DVT | Complete | 5 | 60d | 2019-03-18 | 2019-06-07 | 2457 | 100% |  |  |  | 1813 |  | 2019-03-18 | 2019-06-07 | 0
2459 | 1.3 | 1.3.2.5.3 | C | Tender and procurement | Complete | 5 | 39d | 2019-11-01 | 2019-12-25 |  | 100% |  |  |  | 1670 |  | 2019-11-01 | 2019-12-25 | 0
2460 | 1.3 | 1.3.2.6 | P | D-Egg Harness | Complete | 4 | 398d | 2018-10-04 | 2020-04-13 |  | 100% |  |  |  | 1592 |  | 2018-10-04 | 2020-04-13 | 0
2461 | 1.3 | 1.3.2.6.1 | C | Final design phase | Complete | 5 | 180d | 2018-10-04 | 2019-06-12 |  | 100% | Delays in development. Dates are driven by Japanese funding agency, not the project needs |  |  | 1810 |  | 2018-10-04 | 2019-06-12 | 0
2462 | 1.3 | 1.3.2.6.2 | C | Construction of production tools | Complete | 5 | 60d | 2019-10-01 | 2019-12-23 |  | 100% | Delays in development. Dates are driven by Japanese funding agency, not the project needs |  |  | 1592 |  | 2019-10-01 | 2019-12-23 | 0
2463 | 1.3 | 1.3.2.6.3 | C | Production of harnesses for DVT | Complete | 5 | 20d | 2019-12-24 | 2020-01-20 | 2462 | 100% |  |  |  | 1592 |  | 2019-12-24 | 2020-01-20 | 0
2464 | 1.3 | 1.3.2.6.4 | C | Tender and procurement | Complete | 5 | 60d | 2020-01-21 | 2020-04-13 | 2463 | 100% |  |  |  | 1592 |  | 2020-01-21 | 2020-04-13 | 0
2465 | 1.3 | 1.3.2.7 | P | Integrated D-Egg | Started | 4 | 670d | 2018-10-01 | 2021-04-23 |  | 98% |  |  |  | 1323 |  | 2018-10-01 | 2021-04-23 | 0
2466 | 1.3 | 1.3.2.7.1 | P | Integrated module design | Complete | 5 | 220d | 2018-10-01 | 2019-08-02 |  | 100% |  |  |  | 1773 |  | 2018-10-01 | 2019-08-02 | 0
2467 | 1.3 | 1.3.2.7.1.1 | C | Preliminary design phase | Complete | 6 | 120d | 2018-10-01 | 2019-03-15 |  | 100% |  |  |  | 1773 |  | 2018-10-01 | 2019-03-15 | 0
2468 | 1.3 | 1.3.2.7.1.2 | C | Final design phase | Complete | 6 | 20d | 2019-03-18 | 2019-04-12 | 2467 | 100% |  |  |  | 1773 |  | 2019-03-18 | 2019-04-12 | 0
2469 | 1.3 | 1.3.2.7.1.3 | C | Construction of production tools for internal structure | Complete | 6 | 20d | 2019-04-15 | 2019-05-10 | 2468 | 100% |  |  |  | 1773 |  | 2019-04-15 | 2019-05-10 | 0
2470 | 1.3 | 1.3.2.7.1.4 | C | Production of internal structures for DVT | Complete | 6 | 20d | 2019-05-13 | 2019-06-07 | 2469 | 100% |  |  |  | 1773 |  | 2019-05-13 | 2019-06-07 | 0
2471 | 1.3 | 1.3.2.7.1.5 | C | Tender and procurement of internal structures | Complete | 6 | 40d | 2019-06-10 | 2019-08-02 | 2470 | 100% |  |  |  | 1773 |  | 2019-06-10 | 2019-08-02 | 0
2472 | 1.3 | 1.3.2.7.2 | C | Packaging and shipping tools and procedures | Complete | 5 | 120d | 2020-11-09 | 2021-04-23 |  | 100% |  |  |  | 1203 |  | 2020-11-09 | 2021-04-23 | 0
2473 | 1.3 | 1.3.2.7.3 | C | Deployment tools and and procedures | Complete | 5 | 120d | 2020-11-09 | 2021-04-23 | 2472SS | 100% |  |  |  | 1323 |  | 2020-11-09 | 2021-04-23 | 0
2474 | 1.3 | 1.3.2.7.4 | C | Build 10 modules for DVT | Complete | 5 | 15d | 2019-10-21 | 2019-11-08 |  | 100% | Scheduled for Jan. 2020 |  |  | 1653 |  | 2019-10-21 | 2019-11-08 | 0
2475 | 1.3 | 1.3.2.7.5 | C | Design Verification Test | Complete | 5 | 40d | 2019-11-26 | 2020-01-20 | 2474, 2476 | 100% | Scheduled for Jan./Feb. 2020 |  |  | 1642 |  | 2019-11-26 | 2020-01-20 | 0
2476 | 1.3 | 1.3.2.7.6 | C | Integrated D-Egg Final Design Review | Complete | 5 | 1d | 2019-11-25 | 2019-11-25 |  | 100% | Scheduled for 2020-02-13+14 |  |  | 1642 |  | 2019-11-25 | 2019-11-25 | 0
2477 | 1.3 | 1.3.2.7.7 | C | Ship DVT modules to NTS | Started | 5 | 10d | 2020-01-21 | 2020-02-03 | 2475 | 20% |  |  |  | 1642 |  | 2020-01-21 | 2020-02-03 | 0
2478 | 1.3 | 1.3.2.8 | P | D-Egg Production Facility | Complete | 4 | 656d | 2018-10-01 | 2021-04-05 |  | 100% |  |  |  | 1337 |  | 2018-10-01 | 2021-04-05 | 0
2479 | 1.3 | 1.3.2.8.1 | C | Set up facilities and hire personel | Complete | 5 | 60d | 2018-10-01 | 2018-12-21 |  | 100% |  |  |  | 1893 |  | 2018-10-01 | 2018-12-21 | 0
2480 | 1.3 | 1.3.2.8.2 | C | Test Production (Qty. 40 half-D-Eggs) | Complete | 5 | 40d | 2018-12-24 | 2019-02-15 | 2479 | 100% | Qty. has been reduced |  | Activity Renamed | 1893 |  | 2018-12-24 | 2019-02-15 | 0
2481 | 1.3 | 1.3.2.8.3 | C | Improve production site and procedures | Complete | 5 | 60d | 2019-04-23 | 2019-07-15 |  | 100% |  |  |  | 1787 |  | 2019-04-23 | 2019-07-15 | 0
2482 | 1.3 | 1.3.2.8.4 | C | Production facility audit for assembly, handling, and shipping | Complete | 5 | 1d | 2019-09-20 | 2019-09-20 |  | 100% |  |  | New Activity | 1738 |  | 2019-09-20 | 2019-09-20 | 0
2483 | 1.3 | 1.3.2.8.5 | C | D-Egg Production Readiness Review | Complete | 5 | 1d | 2021-04-05 | 2021-04-05 |  | 100% | Delayed until after initial test production of 50 D-Eggs |  | New Activity | 1337 |  | 2021-04-05 | 2021-04-05 | 0
2484 | 1.3 | 1.3.2.9 | P | D-Egg Series Production | Started | 4 | 1487d | 2020-02-04 | 2025-10-23 |  | 41% |  |  |  | 155 |  | 2020-02-04 | 2025-10-23 | 0
2485 | 1.3 | 1.3.2.9.1 | P | Series production | Started | 5 | 854d | 2020-02-04 | 2023-05-12 |  | 47% |  |  |  | 788 |  | 2020-02-04 | 2023-05-12 | 0
2486 | 1.3 | 1.3.2.9.1.1 | P | FAT rehearsal | Complete | 6 | 65d | 2020-12-07 | 2021-03-05 |  | 100% |  |  | Activity Removed | 1358 |  | 2020-12-07 | 2021-03-05 | 0
2487 | 1.3 | 1.3.2.9.1.1.1 | C | Preparation, debugging | Complete | 7 | 50d | 2020-12-07 | 2021-02-12 |  | 100% |  |  | Activity Removed | 1358 |  | 2020-12-07 | 2021-02-12 | 0
2488 | 1.3 | 1.3.2.9.1.1.2 | C | Dry-run with to be re-sealed D-Eggs | Complete | 7 | 15d | 2021-02-15 | 2021-03-05 | 2487 | 100% |  |  | Activity Removed | 1358 |  | 2021-02-15 | 2021-03-05 | 0
2489 | 1.3 | 1.3.2.9.1.2 | P | D-Egg Batch #1 (Qty. 50) | Started | 6 | 599d | 2020-02-04 | 2022-05-20 |  | 52% |  |  | Activity Renamed | 1043 |  | 2020-02-04 | 2022-05-20 | 0
2490 | 1.3 | 1.3.2.9.1.2.1 | C | PMT potting, camera / flasher installation | Complete | 7 | 40d | 2020-02-04 | 2020-03-30 |  | 100% |  | pending confirmation from Erik |  | 1602 |  | 2020-02-04 | 2020-03-30 | 0
2491 | 1.3 | 1.3.2.9.1.2.2 | C | Camera installation (Qty. 36) | Complete | 7 | 9d | 2020-09-10 | 2020-09-22 |  | 100% |  | pending confirmation from Erik |  | 1476 |  | 2020-09-10 | 2020-09-22 | 0
2492 | 1.3 | 1.3.2.9.1.2.3 | C | MB / PCA installation, sealing | Complete | 7 | 16d | 2021-04-05 | 2021-04-26 |  | 100% |  | pending confirmation from Erik |  | 1322 |  | 2021-04-05 | 2021-04-26 | 0
2493 | 1.3 | 1.3.2.9.1.2.4 | C | Start of D-Egg Final Acceptance Testing | Not Started | 7 | 0 | 2022-02-28 | 2022-02-28 |  | 0% |  |  |  | 728 |  | 2022-02-28 | 2022-02-28 | 0
2494 | 1.3 | 1.3.2.9.1.2.5 | C | FAT | Not Started | 7 | 60d | 2022-02-28 | 2022-05-20 | 2493 | 0% |  | pending confirmation from Erik |  | 728 |  | 2022-02-28 | 2022-05-20 | 0
2495 | 1.3 | 1.3.2.9.1.3 | P | D-Egg Batch #2 (Qty. 110) | Started | 6 | 480d | 2020-12-14 | 2022-10-14 |  | 42% |  | pending confirmation from Erik |  | 938 |  | 2020-12-14 | 2022-10-14 | 0
2496 | 1.3 | 1.3.2.9.1.3.1 | C | Integration at NME | Complete | 7 | 75d | 2020-12-14 | 2021-03-26 |  | 100% |  |  | Activity Renamed | 1343 |  | 2020-12-14 | 2021-03-26 | 0
2497 | 1.3 | 1.3.2.9.1.3.2 | C | FAT | Not Started | 7 | 105d | 2022-05-23 | 2022-10-14 | 2494 | 0% |  |  | Activity Renamed | 728 |  | 2022-05-23 | 2022-10-14 | 0
2498 | 1.3 | 1.3.2.9.1.4 | P | D-Egg Batch #3 (Qty. 150) | Started | 6 | 527d | 2021-05-06 | 2023-05-12 |  | 39% |  |  | Activity Renamed | 788 |  | 2021-05-06 | 2023-05-12 | 0
2499 | 1.3 | 1.3.2.9.1.4.1 | C | Integration at NME | Complete | 7 | 97d | 2021-05-06 | 2021-09-17 |  | 100% |  |  | Activity Renamed | 1218 |  | 2021-05-06 | 2021-09-17 | 0
2500 | 1.3 | 1.3.2.9.1.4.2 | C | FAT | Not Started | 7 | 150d | 2022-10-17 | 2023-05-12 | 2497 | 0% |  |  | Activity Renamed | 728 |  | 2022-10-17 | 2023-05-12 | 0
2501 | 1.3 | 1.3.2.9.1.5 | C | 78 + 18 spares D-Eggs for Strings 87-88 ready to ship to CHC | Not Started | 6 | 0 | 2022-07-25 | 2022-07-25 | 2497SS +45d | 0% |  | pending confirmation from Erik |  | 938 |  | 2022-07-25 | 2022-07-25 | 0
2502 | 1.3 | 1.3.2.9.1.6 | C | 197 + 11 spare D-Eggs for Strings 89-93 ready to ship to CHC | Not Started | 6 | 0 | 2023-05-12 | 2023-05-12 | 2500 | 0% |  |  | Activity Renamed | 728 |  | 2023-05-12 | 2023-05-12 | 0
2503 | 1.3 | 1.3.2.9.1.7 | C | Production of 310 D-Eggs completed | Not Started | 6 | 0 | 2023-05-12 | 2023-05-12 | 2502 | 0% |  |  |  | 788 |  | 2023-05-12 | 2023-05-12 | 0
2504 | 1.3 | 1.3.2.9.2 | C | Ship 78 + 18 spare D-Eggs for Strings 87-88 to CHC | Not Started | 5 | 60d | 2024-08-01 | 2024-10-23 | 2501FS +525d | 0% |  |  | Activity Renamed | 413 |  | 2024-08-01 | 2024-10-23 | 0
2505 | 1.3 | 1.3.2.9.3 | C | Ship 197 + 11 spare D-Eggs for Strings 89-93 to CHC | Not Started | 5 | 60d | 2025-08-01 | 2025-10-23 | 2502FS +573d | 0% |  |  | Activity Renamed | 155 |  | 2025-08-01 | 2025-10-23 | 0
2506 | 1.3 | 1.3.3 | P | PDOM | Started | 3 | 1683d | 2019-03-11 | 2025-08-28 |  | 47% |  |  |  | 195 |  | 2019-03-11 | 2025-08-28 | 0
2507 | 1.3 | 1.3.3.1 | P | PDOM DAQ Electronics | Started | 4 | 940d | 2019-03-11 | 2022-10-14 |  | 87% |  |  |  | 938 |  | 2019-03-11 | 2022-10-14 | 0
2508 | 1.3 | 1.3.3.1.1 | P | PDOM Rev2 Mainboard | Complete | 5 | 175d | 2019-03-11 | 2019-11-08 |  | 100% |  |  |  | 1703 |  | 2019-03-11 | 2019-11-08 | 0
2509 | 1.3 | 1.3.3.1.1.1 | C | Update schematics | Complete | 6 | 25d | 2019-04-01 | 2019-05-03 |  | 100% |  |  |  | 1603 |  | 2019-04-01 | 2019-05-03 | 0
2510 | 1.3 | 1.3.3.1.1.2 | C | Layout | Complete | 6 | 30d | 2019-05-06 | 2019-06-14 | 2509 | 100% | Delays in development due to unification of PDOM and D-Egg mainboards |  |  | 1603 |  | 2019-05-06 | 2019-06-14 | 0
2511 | 1.3 | 1.3.3.1.1.3 | C | PDOM Rev2 Mainboard production (Qty. 10) | Complete | 6 | 30d | 2019-06-17 | 2019-07-26 | 2510 | 100% | Delays in development due to unification of PDOM and D-Egg mainboards |  |  | 1603 |  | 2019-06-17 | 2019-07-26 | 0
2512 | 1.3 | 1.3.3.1.1.4 | C | Firmware | Complete | 6 | 100d | 2019-03-11 | 2019-07-26 | 2511FF | 100% | Delays in development due to unification of PDOM and D-Egg mainboards |  |  | 1703 |  | 2019-03-11 | 2019-07-26 | 0
2513 | 1.3 | 1.3.3.1.1.5 | C | Testing | Complete | 6 | 75d | 2019-07-29 | 2019-11-08 | 2512 | 100% | Delays in development due to unification of PDOM and D-Egg mainboards |  |  | 1703 |  | 2019-07-29 | 2019-11-08 | 0
2514 | 1.3 | 1.3.3.1.2 | P | PDOM Rev3 Mainboard | Started | 5 | 641d | 2020-05-01 | 2022-10-14 |  | 83% |  |  |  | 938 |  | 2020-05-01 | 2022-10-14 | 0
2515 | 1.3 | 1.3.3.1.2.1 | C | Update schematics | Complete | 6 | 20d | 2020-05-01 | 2020-05-28 |  | 100% |  |  |  | 1529 |  | 2020-05-01 | 2020-05-28 | 0
2516 | 1.3 | 1.3.3.1.2.2 | C | Layout | Complete | 6 | 30d | 2020-05-29 | 2020-07-09 | 2515 | 100% |  |  |  | 1529 |  | 2020-05-29 | 2020-07-09 | 0
2517 | 1.3 | 1.3.3.1.2.3 | C | PDOM Rev3 Mainboard production (Qty. 8) | Complete | 6 | 30d | 2021-09-27 | 2021-11-05 |  | 100% |  |  |  | 978 |  | 2021-09-27 | 2021-11-05 | 0
2518 | 1.3 | 1.3.3.1.2.6 | C | Adapt D-Egg Firmware to PDOM Mainboard and verify design | Started | 6 | 205d | 2021-09-27 | 2022-07-08 | 2517SS | 95% |  |  |  | 1008 |  | 2021-09-27 | 2022-07-08 | 0
2519 | 1.3 | 1.3.3.1.2.4 | C | Testing | Started | 6 | 30d | 2022-04-04 | 2022-05-13 |  | 33% |  |  |  | 195 |  | 2022-04-04 | 2022-05-13 | 0
2520 | 1.3 | 1.3.3.1.2.5 | C | PDOM Rev3 Mainboard production (Qty. 27) | Not Started | 6 | 30d | 2022-09-05 | 2022-10-14 | 2529 | 0% |  |  |  | 195 |  | 2022-09-05 | 2022-10-14 | 0
2521 | 1.3 | 1.3.3.2 | P | PDOM High Voltage Subsystem | Started | 4 | 903d | 2019-05-01 | 2022-10-14 |  | 54% |  |  |  | 938 |  | 2019-05-01 | 2022-10-14 | 0
2522 | 1.3 | 1.3.3.2.1 | C | PDOM HV System Preliminary Design | Complete | 5 | 120d | 2019-05-01 | 2019-10-15 |  | 100% |  |  |  | 1721 |  | 2019-05-01 | 2019-10-15 | 0
2523 | 1.3 | 1.3.3.2.2 | P | PDOM HV System Final Design | Started | 5 | 359d | 2021-06-01 | 2022-10-14 |  | 38% |  |  |  | 938 |  | 2021-06-01 | 2022-10-14 | 0
2524 | 1.3 | 1.3.3.2.2.1 | C | Update schematics | Complete | 6 | 20d | 2021-06-01 | 2021-06-28 |  | 100% |  |  |  | 1277 |  | 2021-06-01 | 2021-06-28 | 0
2525 | 1.3 | 1.3.3.2.2.2 | C | Layout | Complete | 6 | 30d | 2022-01-17 | 2022-02-25 |  | 100% |  |  |  | 195 |  | 2022-01-17 | 2022-02-25 | 0
2526 | 1.3 | 1.3.3.2.2.3 | C | PDOM HV System production (Qty. 8) | Not Started | 6 | 30d | 2022-02-28 | 2022-04-08 | 2525 | 0% |  |  |  | 195 |  | 2022-02-28 | 2022-04-08 | 0
2527 | 1.3 | 1.3.3.2.2.4 | C | Testing | Not Started | 6 | 20d | 2022-04-11 | 2022-05-06 | 2526 | 0% |  |  |  | 195 |  | 2022-04-11 | 2022-05-06 | 0
2528 | 1.3 | 1.3.3.2.2.5 | C | PDOM HV system production (Qty. 27) | Not Started | 6 | 30d | 2022-09-05 | 2022-10-14 | 2529 | 0% |  |  |  | 195 |  | 2022-09-05 | 2022-10-14 | 0
2529 | 1.3 | 1.3.3.3 | C | PDOM Final Design Review | Not Started | 4 | 0 | 2022-09-02 | 2022-09-02 | 2532 | 0% |  |  |  | 195 |  | 2022-09-02 | 2022-09-02 | 0
2530 | 1.3 | 1.3.3.4 | P | IceCube DOM Refurbishment | Not Started | 4 | 923d | 2022-02-07 | 2025-08-28 |  | 0% |  |  |  | 195 |  | 2022-02-07 | 2025-08-28 | 0
2531 | 1.3 | 1.3.3.4.1 | C | Refurbish 10 IceCube DOMs | Not Started | 5 | 20d | 2022-06-13 | 2022-07-08 | 2519, 2527, 2551, 2556, 2561 | 0% |  |  |  | 195 |  | 2022-06-13 | 2022-07-08 | 0
2532 | 1.3 | 1.3.3.4.2 | C | Design Verification Test | Not Started | 5 | 40d | 2022-07-11 | 2022-09-02 | 2531 | 0% |  |  |  | 195 |  | 2022-07-11 | 2022-09-02 | 0
2533 | 1.3 | 1.3.3.4.3 | C | Ship DVT modules to NTS | Not Started | 5 | 10d | 2022-09-05 | 2022-09-16 | 2532 | 0% |  |  |  | 958 |  | 2022-09-05 | 2022-09-16 | 0
2534 | 1.3 | 1.3.3.4.4 | P | Facilities | Not Started | 5 | 60d | 2022-02-07 | 2022-04-29 |  | 0% |  |  |  | 1058 |  | 2022-02-07 | 2022-04-29 | 0
2535 | 1.3 | 1.3.3.4.4.1 | C | Set up refurbishment Facility | Not Started | 6 | 60d | 2022-02-07 | 2022-04-29 |  | 0% |  |  |  | 195 |  | 2022-02-07 | 2022-04-29 | 0
2536 | 1.3 | 1.3.3.4.4.2 | C | DOM Refurbishment Facilities Ready | Not Started | 6 | 0 | 2022-04-29 | 2022-04-29 | 2535 | 0% |  |  |  | 195 |  | 2022-04-29 | 2022-04-29 | 0
2537 | 1.3 | 1.3.3.4.5 | P | Refurbish 20 IceCube DOMs with Rev3 Mainboards | Not Started | 5 | 65d | 2022-10-17 | 2023-01-13 |  | 0% |  |  |  | 873 |  | 2022-10-17 | 2023-01-13 | 0
2538 | 1.3 | 1.3.3.4.5.1 | C | Refurbishment Batch #1 (Qty. 20) | Not Started | 6 | 30d | 2022-10-17 | 2022-11-25 | 2520, 2528, 2536 | 0% |  |  |  | 195 |  | 2022-10-17 | 2022-11-25 | 0
2539 | 1.3 | 1.3.3.4.5.2 | C | FAT Batch #1 | Not Started | 6 | 30d | 2022-11-28 | 2023-01-06 | 2538 | 0% |  |  |  | 115 |  | 2022-11-28 | 2023-01-06 | 0
2540 | 1.3 | 1.3.3.4.5.3 | C | Packing Batch #1 | Not Started | 6 | 5d | 2023-01-09 | 2023-01-13 | 2539 | 0% |  |  |  | 135 |  | 2023-01-09 | 2023-01-13 | 0
2541 | 1.3 | 1.3.3.4.5.4 | C | 2 + 2 spare PDOMs for Strings 87-88 ready to ship to Pt. Hueneme | Not Started | 6 | 0 | 2023-01-13 | 2023-01-13 | 2540 | 0% |  |  | New Activity | 413 |  | 2023-01-13 | 2023-01-13 | 0
2542 | 1.3 | 1.3.3.4.5.5 | C | 12 + 4 spare PDOMs for Strings 89-93 ready to ship to Pt. Hueneme | Not Started | 6 | 0 | 2023-01-13 | 2023-01-13 | 2540 | 0% |  |  | New Activity | 155 |  | 2023-01-13 | 2023-01-13 | 0
2543 | 1.3 | 1.3.3.4.5.6 | C | Refurbishment of 20 PDOMs completed | Not Started | 6 | 0 | 2023-01-13 | 2023-01-13 | 2542 | 0% |  |  | New Activity | 873 |  | 2023-01-13 | 2023-01-13 | 0
2544 | 1.3 | 1.3.3.4.6 | C | Ship 2 + 1 spare PDOMs for Strings 87-88 to Pt. Hueneme | Not Started | 5 | 20d | 2024-08-01 | 2024-08-28 | 2541FS +400d | 0% |  |  | Activity Renamed | 433 |  | 2024-08-01 | 2024-08-28 | 0
2545 | 1.3 | 1.3.3.4.7 | C | Ship 12 + 1 spare PDOMs for Strings 89-93 to Pt. Hueneme | Not Started | 5 | 20d | 2025-08-01 | 2025-08-28 | 2542FS +658d | 0% |  |  | Activity Renamed | 175 |  | 2025-08-01 | 2025-08-28 | 0
2546 | 1.3 | 1.3.3.5 | P | PDOM Calibration Subsystem | Started | 4 | 115d | 2022-01-03 | 2022-06-10 |  | 36% |  |  |  | 1028 |  | 2022-01-03 | 2022-06-10 | 0
2547 | 1.3 | 1.3.3.5.1 | P | PDOM Calibration Board | Started | 5 | 115d | 2022-01-03 | 2022-06-10 |  | 43% |  |  |  | 1028 |  | 2022-01-03 | 2022-06-10 | 0
2548 | 1.3 | 1.3.3.5.1.1 | C | PDOM Calibration Board Design | Started | 6 | 70d | 2022-01-03 | 2022-04-08 |  | 70% |  |  |  | 195 |  | 2022-01-03 | 2022-04-08 | 0
2549 | 1.3 | 1.3.3.5.1.2 | C | PDOM Calibration Board Implementation | Not Started | 6 | 25d | 2022-04-11 | 2022-05-13 | 2548 | 0% |  |  |  | 195 |  | 2022-04-11 | 2022-05-13 | 0
2550 | 1.3 | 1.3.3.5.1.3 | C | PDOM Calibration Board Testing | Not Started | 6 | 20d | 2022-05-16 | 2022-06-10 | 2549 | 0% |  |  |  | 195 |  | 2022-05-16 | 2022-06-10 | 0
2551 | 1.3 | 1.3.3.5.1.4 | C | PDOM Calibration Board production ready | Not Started | 6 | 0 | 2022-06-10 | 2022-06-10 | 2550 | 0% |  |  |  | 195 |  | 2022-06-10 | 2022-06-10 | 0
2552 | 1.3 | 1.3.3.5.2 | P | PDOM Camera Illuminators | Started | 5 | 70d | 2022-01-31 | 2022-05-06 |  | 39% |  |  |  | 1053 |  | 2022-01-31 | 2022-05-06 | 0
2553 | 1.3 | 1.3.3.5.2.1 | C | PDOM Camera Illuminators Design | Started | 6 | 30d | 2022-01-31 | 2022-03-11 |  | 90% |  |  |  | 195 |  | 2022-01-31 | 2022-03-11 | 0
2554 | 1.3 | 1.3.3.5.2.2 | C | PDOM Camera Illuminators Implementation | Not Started | 6 | 20d | 2022-03-14 | 2022-04-08 | 2553 | 0% |  |  |  | 195 |  | 2022-03-14 | 2022-04-08 | 0
2555 | 1.3 | 1.3.3.5.2.3 | C | PDOM Camera Illuminators Testing | Not Started | 6 | 20d | 2022-04-11 | 2022-05-06 | 2554 | 0% |  |  |  | 195 |  | 2022-04-11 | 2022-05-06 | 0
2556 | 1.3 | 1.3.3.5.2.4 | C | PDOM Camera Illuminators production ready | Not Started | 6 | 0 | 2022-05-06 | 2022-05-06 | 2555 | 0% |  |  |  | 195 |  | 2022-05-06 | 2022-05-06 | 0
2557 | 1.3 | 1.3.3.5.3 | P | Acoustic Receiver Integration | Started | 5 | 70d | 2022-02-28 | 2022-06-03 |  | 21% |  |  |  | 1033 |  | 2022-02-28 | 2022-06-03 | 0
2558 | 1.3 | 1.3.3.5.3.1 | C | Acoustic Receiver Integration Design | Started | 6 | 30d | 2022-02-28 | 2022-04-08 |  | 50% |  |  |  | 195 |  | 2022-02-28 | 2022-04-08 | 0
2559 | 1.3 | 1.3.3.5.3.2 | C | Acoustic Receiver Integration Implementation | Not Started | 6 | 20d | 2022-04-11 | 2022-05-06 | 2558 | 0% |  |  |  | 195 |  | 2022-04-11 | 2022-05-06 | 0
2560 | 1.3 | 1.3.3.5.3.3 | C | Acoustic Receiver Integration Testing | Not Started | 6 | 20d | 2022-05-09 | 2022-06-03 | 2559 | 0% |  |  |  | 195 |  | 2022-05-09 | 2022-06-03 | 0
2561 | 1.3 |  | C | PDOM Acoustic Receiver Integration design complete | Not Started | 6 | 0 | 2022-06-03 | 2022-06-03 | 2560 | 0% |  |  |  | 195 |  | 2022-06-03 | 2022-06-03 | 0
2562 | 1.3 | 1.3.4 | P | Ice Comms Module | Started | 3 | 1891d | 2019-02-01 | 2026-05-14 |  | 42% |  |  |  | 13 |  | 2019-02-01 | 2026-05-14 | 0
2563 | 1.3 | 1.3.4.1 | P | ICM Electronics | Complete | 4 | 664d | 2019-02-01 | 2021-08-18 |  | 100% |  |  |  | 1240 |  | 2019-02-01 | 2021-08-18 | 0
2564 | 1.3 | 1.3.4.1.1 | C | Interface of ICM to DOM mainboard defined | Complete | 5 | 1d | 2019-02-01 | 2019-02-01 |  | 100% |  |  |  | 1780 |  | 2019-02-01 | 2019-02-01 | 0
2565 | 1.3 | 1.3.4.1.2 | C | Schematic / BOM development | Complete | 5 | 20d | 2019-02-04 | 2019-03-01 | 2564 | 100% |  |  |  | 1780 |  | 2019-02-04 | 2019-03-01 | 0
2566 | 1.3 | 1.3.4.1.3 | C | Conceptual design available | Complete | 5 | 2d | 2019-03-04 | 2019-03-05 | 2565 | 100% |  |  |  | 1780 |  | 2019-03-04 | 2019-03-05 | 0
2567 | 1.3 | 1.3.4.1.4 | C | Preliminary design phase | Complete | 5 | 40d | 2019-03-04 | 2019-04-26 | 2566SS | 100% |  |  |  | 1782 |  | 2019-03-04 | 2019-04-26 | 0
2568 | 1.3 | 1.3.4.1.5 | C | First working prototype available | Complete | 5 | 1d | 2019-04-29 | 2019-04-29 | 2567 | 100% |  |  |  | 1782 |  | 2019-04-29 | 2019-04-29 | 0
2569 | 1.3 | 1.3.4.1.6 | C | Production of Stand-alone PCBs for Cable Verification | Complete | 5 | 50d | 2019-04-29 | 2019-07-05 | 2568SS | 100% | Cable verification has been done at DESY |  |  | 1783 |  | 2019-04-29 | 2019-07-05 | 0
2570 | 1.3 | 1.3.4.1.7 | C | Shipping to NTS | Complete | 5 | 10d | 2019-07-08 | 2019-07-19 | 2569 | 100% | Printed circuit assemblies of the final design are available; firmware development is ongoing, but firmware will be required for design verification |  |  | 1783 |  | 2019-07-08 | 2019-07-19 | 0
2571 | 1.3 | 1.3.4.1.8 | C | Final design phase | Complete | 5 | 87d | 2019-04-26 | 2019-08-26 |  | 100% | Printed circuit assemblies of the final design are available; firmware development is ongoing, but firmware will be required for design verification |  | Activity Renamed | 1607 |  | 2019-04-26 | 2019-08-26 | 0
2572 | 1.3 | 1.3.4.1.9 | C | Ice Comms Module FDR | Complete | 5 | 1d | 2019-08-27 | 2019-08-27 | 2571 | 100% | Printed circuit assemblies of the final design are available; firmware development is ongoing, but firmware will be required for design verification |  | Activity Renamed | 1607 |  | 2019-08-27 | 2019-08-27 | 0
2573 | 1.3 | 1.3.4.1.10 | C | Production of 15 ICMs for D-Egg DVT | Complete | 5 | 29d | 2019-08-27 | 2019-10-04 | 2572SS | 100% | Printed circuit assemblies of the final design are available; firmware development is ongoing, but firmware will be required for design verification |  |  | 1608 |  | 2019-08-27 | 2019-10-04 | 0
2574 | 1.3 | 1.3.4.1.11 | C | Tender and Procurement (series production) | Complete | 5 | 80d | 2019-06-17 | 2019-10-04 | 2573FF | 100% |  |  |  | 1688 |  | 2019-06-17 | 2019-10-04 | 0
2575 | 1.3 | 1.3.4.1.12 | P | Production of 900 ICMs for in-ice modules | Complete | 5 | 488d | 2019-10-07 | 2021-08-18 |  | 100% |  |  |  | 1240 |  | 2019-10-07 | 2021-08-18 | 0
2576 | 1.3 | 1.3.4.1.12.1 | C | Production Batch #1 (Qty. 72) | Complete | 6 | 40d | 2019-10-07 | 2019-11-29 | 2574 | 100% |  |  |  | 1688 |  | 2019-10-07 | 2019-11-29 | 0
2577 | 1.3 | 1.3.4.1.12.2 | C | Production Batch #2 (Qty. 264) | Complete | 6 | 60d | 2020-08-03 | 2020-10-23 |  | 100% | Cable verification has been done at DESY |  |  | 1453 |  | 2020-08-03 | 2020-10-23 | 0
2578 | 1.3 | 1.3.4.1.12.3 | C | Production Batch #3 (Qty. 500) | Complete | 6 | 15d | 2021-03-08 | 2021-03-26 |  | 100% | Printed circuit assemblies of the final design are available; firmware development is ongoing, but firmware will be required for design verification |  |  | 1313 |  | 2021-03-08 | 2021-03-26 | 0
2579 | 1.3 | 1.3.4.1.12.4 | C | Testing Batch #3 (Qty. 500) | Complete | 6 | 30d | 2021-03-29 | 2021-05-07 | 2578 | 100% | Printed circuit assemblies of the final design are available; firmware development is ongoing, but firmware will be required for design verification |  | Activity Renamed | 1313 |  | 2021-03-29 | 2021-05-07 | 0
2580 | 1.3 | 1.3.4.1.12.5 | C | Production Batch #4 (Qty. 200) | Complete | 6 | 15d | 2021-07-01 | 2021-07-21 |  | 100% | Printed circuit assemblies of the final design are available; firmware development is ongoing, but firmware will be required for design verification |  | Activity Renamed | 1240 |  | 2021-07-01 | 2021-07-21 | 0
2581 | 1.3 | 1.3.4.1.12.6 | C | Testing Batch #4 (Qty. 200) | Complete | 6 | 20d | 2021-07-22 | 2021-08-18 | 2580 | 100% | Printed circuit assemblies of the final design are available; firmware development is ongoing, but firmware will be required for design verification |  |  | 1240 |  | 2021-07-22 | 2021-08-18 | 0
2582 | 1.3 | 1.3.4.2 | P | ICM Firmware | Started | 4 | 1415d | 2020-11-30 | 2026-05-14 |  | 10% |  |  |  | 13 |  | 2020-11-30 | 2026-05-14 | 0
2583 | 1.3 | 1.3.4.2.1 | C | Parallel communication to multiple devices | Complete | 5 | 10d | 2020-11-30 | 2020-12-11 |  | 100% |  |  |  | 1413 |  | 2020-11-30 | 2020-12-11 | 0
2584 | 1.3 | 1.3.4.2.3 | P | RAPCAL Firmware | Started | 5 | 1405d | 2020-12-14 | 2026-05-14 |  | 9% |  |  |  | 13 |  | 2020-12-14 | 2026-05-14 | 0
2585 | 1.3 | 1.3.4.2.3.1 | P | Implementation | Complete | 6 | 25d | 2020-12-14 | 2021-01-15 |  | 100% |  |  |  | 1393 |  | 2020-12-14 | 2021-01-15 | 0
2586 | 1.3 | 1.3.4.2.3.1.1 | C | Part 1 (before holidays) | Complete | 7 | 5d | 2020-12-14 | 2020-12-18 | 2583 | 100% |  |  | Activity Renamed | 1413 |  | 2020-12-14 | 2020-12-18 | 0
2587 | 1.3 | 1.3.4.2.3.1.2 | C | Part 2 (after holidays) | Complete | 7 | 10d | 2021-01-04 | 2021-01-15 |  | 100% |  |  | Activity Renamed | 1253 |  | 2021-01-04 | 2021-01-15 | 0
2588 | 1.3 | 1.3.4.2.3.2 | C | Debugging | Complete | 6 | 20d | 2021-01-18 | 2021-02-12 | 2587 | 100% |  |  |  | 1253 |  | 2021-01-18 | 2021-02-12 | 0
2589 | 1.3 | 1.3.4.2.3.3 | C | Firmware support during D-Egg FAT | Not Started | 6 | 315d | 2022-02-28 | 2023-05-12 | 2494SS | 0% |  |  |  | 788 |  | 2022-02-28 | 2023-05-12 | 0
2590 | 1.3 | 1.3.4.2.3.4 | C | Firmware preparation for mDOM FAT | Not Started | 6 | 30d | 2022-06-27 | 2022-08-05 |  | 0% | hen |  |  | 988 |  | 2022-06-27 | 2022-08-05 | 0
2591 | 1.3 | 1.3.4.2.3.5 | C | Firmware support during mDOM FAT | Not Started | 6 | 175d | 2023-01-16 | 2023-09-15 |  | 0% | Parallel to mDOM FAT at DESY and MSU |  |  | 698 |  | 2023-01-16 | 2023-09-15 | 0
2592 | 1.3 | 1.3.4.2.3.6 | C | Firmware support during development of Calibration Devices, Special Devices, system integration, and commissioning | Started | 6 | 1217d | 2021-09-02 | 2026-05-14 | 2617SS | 9% | Activity should run until end-of-project, whenever that is |  |  | 13 |  | 2021-09-02 | 2026-05-14 | 0
2593 | 1.3 | 1.3.4.3 | C | mini-FieldHub ICM Firmware | Complete | 4 | 120d | 2020-08-31 | 2021-02-12 | 2588FF | 100% |  |  |  | 1373 |  | 2020-08-31 | 2021-02-12 | 0
2594 | 1.3 | 1.3.5 | P | Special Devices | Started | 3 | 1733d | 2019-01-01 | 2025-08-29 |  | 9% |  |  |  | 194 |  | 2019-01-01 | 2025-08-29 | 0
2595 | 1.3 | 1.3.5.1 | C | R&D module registration | Complete | 4 | 349d | 2019-01-01 | 2020-05-01 |  | 100% |  |  |  | 1577 |  | 2019-01-01 | 2020-05-01 | 0
2596 | 1.3 | 1.3.5.2 | C | R&D module mission review | Complete | 4 | 1d | 2020-05-04 | 2020-05-04 | 2595 | 100% |  |  |  | 1577 |  | 2020-05-04 | 2020-05-04 | 0
2597 | 1.3 | 1.3.5.3 | C | Allocation of R&D module resources | Complete | 4 | 260d | 2021-01-04 | 2021-12-31 |  | 100% |  |  |  | 1143 |  | 2021-01-04 | 2021-12-31 | 0
2598 | 1.3 | 1.3.5.4 | C | R&D modules deployment readiness review | Complete | 4 | 1d | 2021-12-31 | 2021-12-31 |  | 100% | Has been replaced by reviews for individual devices (WBS 1.3.5.5 to 1.3.5.11) |  |  | 1143 |  | 2021-12-31 | 2021-12-31 | 0
2599 | 1.3 | 1.3.5.5 | P | DM-Ice | Not Started | 4 | 911d | 2022-02-24 | 2025-08-29 |  | 0% |  |  |  | 194 |  | 2022-02-24 | 2025-08-29 | 0
2600 | 1.3 | 1.3.5.5.1 | C | DM-Ice Preliminary Design Review | Not Started | 5 | 0 | 2022-02-24 | 2022-02-24 |  | 0% |  |  |  | 1105 |  | 2022-02-24 | 2022-02-24 | 0
2601 | 1.3 | 1.3.5.5.2 | C | DM-Ice Final Design Review | Not Started | 5 | 0 | 2024-05-01 | 2024-05-01 | 2602SF -195d | 0% |  |  |  | 539 |  | 2024-05-01 | 2024-05-01 | 0
2602 | 1.3 | 1.3.5.5.3 | C | DM-Ice Deployment Readiness Review | Not Started | 5 | 0 | 2025-02-03 | 2025-02-03 | 2603SF -130d | 0% |  |  |  | 344 |  | 2025-02-03 | 2025-02-03 | 0
2603 | 1.3 | 1.3.5.5.4 | C | Ship 2 DM-Ice modules from Yale to Pt. Hueneme | Not Started | 5 | 20d | 2025-08-04 | 2025-08-29 |  | 0% |  |  |  | 194 |  | 2025-08-04 | 2025-08-29 | 0
2604 | 1.3 | 1.3.5.6 | P | Fiber-Optic Module (FOM) | Not Started | 4 | 883d | 2022-04-04 | 2025-08-28 |  | 0% |  |  |  | 195 |  | 2022-04-04 | 2025-08-28 | 0
2605 | 1.3 | 1.3.5.6.1 | C | FOM Preliminary Design Review | Not Started | 5 | 0 | 2022-04-04 | 2022-04-04 |  | 0% |  |  |  | 1078 |  | 2022-04-04 | 2022-04-04 | 0
2606 | 1.3 | 1.3.5.6.2 | C | FOM Final Design Review | Not Started | 5 | 0 | 2023-05-01 | 2023-05-01 | 2607SF -195d | 0% |  |  |  | 798 |  | 2023-05-01 | 2023-05-01 | 0
2607 | 1.3 | 1.3.5.6.3 | C | FOM Deployment Readiness Review | Not Started | 5 | 0 | 2024-02-01 | 2024-02-01 | 2608SF -130d | 0% |  |  |  | 603 |  | 2024-02-01 | 2024-02-01 | 0
2608 | 1.3 | 1.3.5.6.4 | C | Ship 4 FOMs from UW to Pt. Hueneme | Not Started | 5 | 20d | 2024-08-01 | 2024-08-28 | 2544SS | 0% |  |  |  | 453 |  | 2024-08-01 | 2024-08-28 | 0
2609 | 1.3 | 1.3.5.6.5 | C | Ship 5 FOMs from UW to Pt. Hueneme | Not Started | 5 | 20d | 2025-08-01 | 2025-08-28 | 2545SS | 0% |  |  |  | 195 |  | 2025-08-01 | 2025-08-28 | 0
2610 | 1.3 | 1.3.5.7 | P | eLongated Optical Module (LOM) | Should have Started | 4 | 962d | 2021-12-14 | 2025-08-28 |  | 0% |  |  |  | 195 |  | 2021-12-14 | 2025-08-28 | 0
2611 | 1.3 | 1.3.5.7.1 | C | LOM Preliminary Design Review | Complete | 5 | 0 | 2021-12-14 | 2021-12-14 |  | 100% |  |  |  | 1157 |  | 2021-12-14 | 2021-12-14 | 0
2612 | 1.3 | 1.3.5.7.2 | C | LOM Final Design Review | Not Started | 5 | 0 | 2023-05-01 | 2023-05-01 | 2613SF -195d | 0% |  |  |  | 798 |  | 2023-05-01 | 2023-05-01 | 0
2613 | 1.3 | 1.3.5.7.3 | C | LOM Deployment Readiness Review | Not Started | 5 | 0 | 2024-02-01 | 2024-02-01 | 2614SF -130d | 0% |  |  |  | 603 |  | 2024-02-01 | 2024-02-01 | 0
2614 | 1.3 | 1.3.5.7.4 | C | Ship 2 LOMs from UW to Pt. Hueneme | Not Started | 5 | 20d | 2024-08-01 | 2024-08-28 | 2544SS | 0% |  |  |  | 453 |  | 2024-08-01 | 2024-08-28 | 0
2615 | 1.3 | 1.3.5.7.5 | C | Ship 12 LOMs from UW to Pt. Hueneme | Not Started | 5 | 20d | 2025-08-01 | 2025-08-28 | 2545SS | 0% |  |  |  | 195 |  | 2025-08-01 | 2025-08-28 | 0
2616 | 1.3 | 1.3.5.8 | P | Radio Pulser (RP) | Should have Started | 4 | 777d | 2021-09-02 | 2024-08-28 |  | 0% |  |  |  | 453 |  | 2021-09-02 | 2024-08-28 | 0
2617 | 1.3 | 1.3.5.8.1 | C | RP Preliminary Design Review | Complete | 5 | 0 | 2021-09-02 | 2021-09-02 |  | 100% |  |  |  | 13 |  | 2021-09-02 | 2021-09-02 | 0
2618 | 1.3 | 1.3.5.8.2 | C | RP Final Design Review | Not Started | 5 | 0 | 2023-05-01 | 2023-05-01 | 2619SF -195d | 0% |  |  |  | 798 |  | 2023-05-01 | 2023-05-01 | 0
2619 | 1.3 | 1.3.5.8.3 | C | RP Deployment Readiness Review | Not Started | 5 | 0 | 2024-02-01 | 2024-02-01 | 2620SF -130d | 0% |  |  |  | 603 |  | 2024-02-01 | 2024-02-01 | 0
2620 | 1.3 | 1.3.5.8.4 | C | Ship 5 RPs from UW to Pt. Hueneme | Not Started | 5 | 20d | 2024-08-01 | 2024-08-28 | 2544SS | 0% |  |  |  | 453 |  | 2024-08-01 | 2024-08-28 | 0
2621 | 1.3 | 1.3.5.9 | P | Radio Receiver (RR) | Not Started | 4 | 863d | 2022-05-02 | 2025-08-28 |  | 0% |  |  |  | 195 |  | 2022-05-02 | 2025-08-28 | 0
2622 | 1.3 | 1.3.5.9.1 | C | RR Preliminary Design Review | Not Started | 5 | 0 | 2022-05-02 | 2022-05-02 |  | 0% |  |  |  | 1058 |  | 2022-05-02 | 2022-05-02 | 0
2623 | 1.3 | 1.3.5.9.2 | C | RR Final Design Review | Not Started | 5 | 0 | 2023-05-01 | 2023-05-01 | 2624FS -195d | 0% |  |  |  | 798 |  | 2023-05-01 | 2023-05-01 | 0
2624 | 1.3 | 1.3.5.9.3 | C | RR Deployment Readiness Review | Not Started | 5 | 0 | 2024-02-01 | 2024-02-01 | 2625SF -130d | 0% |  |  |  | 603 |  | 2024-02-01 | 2024-02-01 | 0
2625 | 1.3 | 1.3.5.9.4 | C | Ship 2 RRs from UW to Pt. Hueneme | Not Started | 5 | 20d | 2024-08-01 | 2024-08-28 | 2544SS | 0% |  |  |  | 453 |  | 2024-08-01 | 2024-08-28 | 0
2626 | 1.3 | 1.3.5.9.5 | C | Ship 3 RRs from UW to Pt. Hueneme | Not Started | 5 | 20d | 2025-08-01 | 2025-08-28 | 2545SS | 0% |  |  |  | 195 |  | 2025-08-01 | 2025-08-28 | 0
2627 | 1.3 | 1.3.5.10 | P | Very Broadband Seismograph (SMG) | Not Started | 4 | 818d | 2022-07-04 | 2025-08-28 |  | 0% |  |  |  | 195 |  | 2022-07-04 | 2025-08-28 | 0
2628 | 1.3 | 1.3.5.10.1 | C | SMG Preliminary Design Review | Not Started | 5 | 0 | 2022-07-04 | 2022-07-04 |  | 0% |  |  |  | 1013 |  | 2022-07-04 | 2022-07-04 | 0
2629 | 1.3 | 1.3.5.10.2 | C | SMG Final Design Review | Not Started | 5 | 0 | 2024-05-28 | 2024-05-28 | 2630FS -195d | 0% |  |  |  | 520 |  | 2024-05-28 | 2024-05-28 | 0
2630 | 1.3 | 1.3.5.10.3 | C | SMG Deployment Readiness Review | Not Started | 5 | 0 | 2025-02-28 | 2025-02-28 | 2631FS -130d | 0% |  |  |  | 325 |  | 2025-02-28 | 2025-02-28 | 0
2631 | 1.3 | 1.3.5.10.4 | C | Ship SMG from UW to Pt. Hueneme | Not Started | 5 | 20d | 2025-08-01 | 2025-08-28 | 2545SS | 0% |  |  |  | 195 |  | 2025-08-01 | 2025-08-28 | 0
2632 | 1.3 | 1.3.5.11 | P | Wavelength-shifting Optical Module (WOM) | Should have Started | 4 | 726d | 2021-12-10 | 2024-09-25 |  | 0% |  |  |  | 433 |  | 2021-12-10 | 2024-09-25 | 0
2633 | 1.3 | 1.3.5.11.1 | C | WOM Preliminary Design Review | Complete | 5 | 0 | 2021-12-10 | 2021-12-10 |  | 100% |  |  |  | 1159 |  | 2021-12-10 | 2021-12-10 | 0
2634 | 1.3 | 1.3.5.11.2 | C | WOM Final Design Review | Not Started | 5 | 0 | 2023-05-01 | 2023-05-01 | 2635SF -195d | 0% |  |  |  | 798 |  | 2023-05-01 | 2023-05-01 | 0
2635 | 1.3 | 1.3.5.11.3 | C | WOM Deployment Readiness Review | Not Started | 5 | 0 | 2024-02-01 | 2024-02-01 | 2636SF -130d | 0% |  |  |  | 603 |  | 2024-02-01 | 2024-02-01 | 0
2636 | 1.3 | 1.3.5.11.4 | C | Ship 16 WOMs from DESY to CHC | Not Started | 5 | 40d | 2024-08-01 | 2024-09-25 | 2419SS | 0% |  |  |  | 433 |  | 2024-08-01 | 2024-09-25 | 0
2637 | 1.4 | 1.4 | P | CPT | Started | 2 | 1920d | 2018-11-14 | 2026-04-06 |  | 18% |  |  |  | 41 |  | 2018-11-14 | 2026-04-06 | 0
2638 | 1.4 | 1.4.1 | P | Downhole Cables | Started | 3 | 1888d | 2018-11-14 | 2026-02-19 |  | 27% |  |  |  | 73 |  | 2018-11-14 | 2026-02-19 | 0
2639 | 1.4 | 1.4.1.1 | P | Main Cable Assembly | Started | 4 | 1303d | 2018-11-14 | 2023-11-10 |  | 34% |  |  |  | 658 |  | 2018-11-14 | 2023-11-10 | 0
2640 | 1.4 | 1.4.1.1.1 | P | Main Cables | Started | 5 | 1201d | 2018-11-14 | 2023-06-21 |  | 59% |  |  |  | 760 |  | 2018-11-14 | 2023-06-21 | 0
2641 | 1.4 | 1.4.1.1.1.1 | P | Main cable preliminary design phase | Complete | 6 | 860d | 2018-11-14 | 2022-03-01 |  | 100% |  |  |  | 1101 |  | 2018-11-14 | 2022-03-01 | 0
2642 | 1.4 | 1.4.1.1.1.1.1 | C | Main Cable RFI | Complete | 7 | 2d | 2018-11-14 | 2018-11-15 |  | 100% |  |  |  | 1868 |  | 2018-11-14 | 2018-11-15 | 0
2643 | 1.4 | 1.4.1.1.1.1.2 | C | Site visits to potential vendors | Complete | 7 | 91d | 2018-11-16 | 2019-03-22 | 2642 | 100% |  |  |  | 1868 |  | 2018-11-16 | 2019-03-22 | 0
2644 | 1.4 | 1.4.1.1.1.1.3 | C | Procurement of sample quads | Complete | 7 | 216d | 2021-01-01 | 2021-10-29 |  | 100% | Hexatronic triplet received |  |  | 1188 |  | 2021-01-01 | 2021-10-29 | 0
2645 | 1.4 | 1.4.1.1.1.1.4 | C | Evaluation of sample quads | Complete | 7 | 262d | 2021-03-01 | 2022-03-01 |  | 100% | Hexatronic triplet tested |  |  | 1101 |  | 2021-03-01 | 2022-03-01 | 0
2646 | 1.4 | 1.4.1.1.1.2 | P | Main Cable Final Design Phase | Should have Started | 6 | 186d | 2021-11-01 | 2022-07-18 |  | 0% |  |  |  | 1002 |  | 2021-11-01 | 2022-07-18 | 0
2647 | 1.4 | 1.4.1.1.1.2.1 | P | Main cable final design | Should have Started | 7 | 131d | 2021-11-01 | 2022-05-02 | [5 empty] | 1057 |  | 2021-11-01 | 2022-05-02 | 0
2648 | 1.4 | 1.4.1.1.1.2.1.1 | P | Develop electrical properties measurement system | Not Started | 8 | 45d | 2022-03-01 | 2022-05-02 | [5 empty] | 1057 |  | 2022-03-01 | 2022-05-02 | 0
2649 | 1.4 | 1.4.1.1.1.2.1.1.1 | C | Assess crosstalk measurement board requirements | Not Started | 9 | 10d | 2022-03-01 | 2022-03-14 | [5 empty] | 1037 |  | 2022-03-01 | 2022-03-14 | 0
2650 | 1.4 | 1.4.1.1.1.2.1.1.2 | C | Design crosstalk measurement board | Not Started | 9 | 15d | 2022-03-15 | 2022-04-04 | 2649 |  |  |  |  | 1037 |  | 2022-03-15 | 2022-04-04 | 0
2651 | 1.4 | 1.4.1.1.1.2.1.1.3 | C | Order crosstalk measurement board | Not Started | 9 | 15d | 2022-04-05 | 2022-04-25 | 2650 |  |  |  |  | 1037 |  | 2022-04-05 | 2022-04-25 | 0
2652 | 1.4 | 1.4.1.1.1.2.1.1.4 | C | Populate and test crosstalk measurement board | Not Started | 9 | 5d | 2022-04-26 | 2022-05-02 | 2651 |  |  |  |  | 1037 |  | 2022-04-26 | 2022-05-02 | 0
2653 | 1.4 | 1.4.1.1.1.2.1.1.5 | C | Crosstalk measurement board ready for use | Not Started | 9 | 0 | 2022-05-02 | 2022-05-02 | 2652 |  |  |  |  | 1037 |  | 2022-05-02 | 2022-05-02 | 0
2654 | 1.4 | 1.4.1.1.1.2.1.2 | C | Develop mechanical test plan for composite cable | Should have Started | 8 | 80d | 2021-11-01 | 2022-02-18 | [5 empty] | 623 |  | 2021-11-01 | 2022-02-18 | 0
2655 | 1.4 | 1.4.1.1.1.2.2 | P | Hexatronic prototype testing | Should have Started | 7 | 135d | 2021-12-10 | 2022-06-16 |  | 0% |  |  |  | 1024 |  | 2021-12-10 | 2022-06-16 | 0
2656 | 1.4 | 1.4.1.1.1.2.2.1 | C | Hexatronic prototype main cable production | Should have Started | 8 | 58d | 2021-12-10 | 2022-03-01 | [5 empty] | 623 |  | 2021-12-10 | 2022-03-01 | 0
2657 | 1.4 | 1.4.1.1.1.2.2.2 | C | Hexatronic prototype main cable pull test | Not Started | 8 | 22d | 2022-03-02 | 2022-03-31 | 2656, 2654 | 0% |  |  |  | 623 |  | 2022-03-02 | 2022-03-31 | 0
2658 | 1.4 | 1.4.1.1.1.2.2.3 | C | Hexatronic prototype main cable shipping to PSL | Not Started | 8 | 8w | 2022-04-01 | 2022-05-26 | 2657 | 0% |  |  |  | 337 |  | 2022-04-01 | 2022-05-26 | 0
2659 | 1.4 | 1.4.1.1.1.2.2.4 | C | Hexatronic prototype main cable mechanical testing at PSL | Not Started | 8 | 3w | 2022-05-27 | 2022-06-16 | 2658 | 0% |  |  |  | 516 |  | 2022-05-27 | 2022-06-16 | 0
2660 | 1.4 | 1.4.1.1.1.2.2.5 | C | Hexatronic prototype main cable mechanical testing complete | Not Started | 8 | 0 | 2022-06-16 | 2022-06-16 | 2659 |  |  |  |  | 623 |  | 2022-06-16 | 2022-06-16 | 0
2661 | 1.4 | 1.4.1.1.1.2.2.6 | C | Hexatronic prototype main cable shipping to breakout suppliers | Not Started | 8 | 8w | 2022-04-01 | 2022-05-26 | 2657 |  |  |  |  | 631 |  | 2022-04-01 | 2022-05-26 | 0
2662 | 1.4 | 1.4.1.1.1.2.3 | P | Fibron prototype testing | Should have Started | 7 | 146d | 2021-12-20 | 2022-07-11 | [5 empty] | 1007 |  | 2021-12-20 | 2022-07-11 | 0
2663 | 1.4 | 1.4.1.1.1.2.3.1 | C | Fibron prototype main cable production | Should have Started | 8 | 19w | 2021-12-20 | 2022-04-29 | [5 empty] | 1058 |  | 2021-12-20 | 2022-04-29 | 0
2664 | 1.4 | 1.4.1.1.1.2.3.2 | C | Fibron prototype main cable shipping to MSU | Not Started | 8 | 6w | 2022-05-03 | 2022-06-13 | [5 empty] | 1007 |  | 2022-05-03 | 2022-06-13 | 0
2665 | 1.4 | 1.4.1.1.1.2.3.3 | C | Fibron prototype main cable electrical testing | Not Started | 8 | 3w | 2022-06-14 | 2022-07-04 | 2653, 2664 |  |  |  |  | 1007 |  | 2022-06-14 | 2022-07-04 | 0
2666 | 1.4 | 1.4.1.1.1.2.3.4 | C | Fibron prototype main cable communications testing | Not Started | 8 | 1w | 2022-07-05 | 2022-07-11 | 2665 |  |  |  |  | 1007 |  | 2022-07-05 | 2022-07-11 | 0
2667 | 1.4 | 1.4.1.1.1.2.3.5 | C | Fibron prototype main cable testing complete | Not Started | 8 | 0 | 2022-07-11 | 2022-07-11 | 2666 |  |  |  |  | 1007 |  | 2022-07-11 | 2022-07-11 | 0
2668 | 1.4 | 1.4.1.1.1.2.4 | C | Hexatronic main cable final design review / decision | Not Started | 7 | 22d | 2022-06-17 | 2022-07-18 | 2660 |  |  |  |  | 623 |  | 2022-06-17 | 2022-07-18 | 0
2669 | 1.4 | 1.4.1.1.1.2.5 | C | Main cable final design review complete | Not Started | 7 | 0 | 2022-07-18 | 2022-07-18 | 2668 |  |  |  |  | 536 |  | 2022-07-18 | 2022-07-18 | 0
2670 | 1.4 | 1.4.1.1.1.3 | P | Main Cable Production | Started | 6 | 558d | 2021-05-03 | 2023-06-21 |  | 15% |  |  |  | 760 |  | 2021-05-03 | 2023-06-21 | 0
2671 | 1.4 | 1.4.1.1.1.3.1 | C | Main cable procurement | Started | 7 | 346d | 2021-05-03 | 2022-08-29 | 2669FF +30d | 25% |  |  |  | 658 |  | 2021-05-03 | 2022-08-29 | 0
2672 | 1.4 | 1.4.1.1.1.3.2 | P | Production of first article | Not Started | 7 | 120d | 2022-08-30 | 2023-02-13 |  | 0% |  |  |  | 852 |  | 2022-08-30 | 2023-02-13 | 0
2673 | 1.4 | 1.4.1.1.1.3.2.1 | C | Fabrication | Not Started | 8 | 16w | 2022-08-30 | 2022-12-19 | 2671 | 0% |  |  |  | 658 |  | 2022-08-30 | 2022-12-19 | 0
2674 | 1.4 | 1.4.1.1.1.3.2.2 | C | Acceptance testing | Not Started | 8 | 3w | 2022-12-20 | 2023-01-09 | 2673 | 0% |  |  |  | 658 |  | 2022-12-20 | 2023-01-09 | 0
2675 | 1.4 | 1.4.1.1.1.3.2.4 | C | First article shipping to breakout installation facility | Not Started | 8 | 5w | 2023-01-10 | 2023-02-13 | 2674 | 0% |  |  |  | 852 |  | 2023-01-10 | 2023-02-13 | 0
2676 | 1.4 | 1.4.1.1.1.3.3 | C | Production readiness review | Not Started | 7 | 17d | 2023-01-10 | 2023-02-01 | 2674 | 0% |  |  |  | 658 |  | 2023-01-10 | 2023-02-01 | 0
2677 | 1.4 | 1.4.1.1.1.3.3.1 | C | Production readiness review complete | Not Started | 7 | 0 | 2023-02-01 | 2023-02-01 | 2676 |  |  |  |  | 860 |  | 2023-02-01 | 2023-02-01 | 0
2678 | 1.4 | 1.4.1.1.1.3.4 | C | Production of final six main cables | Not Started | 7 | 12w | 2023-02-02 | 2023-04-26 | 2676 | 0% |  |  |  | 658 |  | 2023-02-02 | 2023-04-26 | 0
2679 | 1.4 | 1.4.1.1.1.3.5 | C | Main Cable Production Complete | Not Started | 7 | 0 | 2023-04-26 | 2023-04-26 | 2678 | 0% |  |  |  | 800 |  | 2023-04-26 | 2023-04-26 | 0
2680 | 1.4 | 1.4.1.1.1.3.6 | C | Production main cable shipping to breakout installation facility | Not Started | 7 | 8w | 2023-04-27 | 2023-06-21 | 2678 | 0% |  |  |  | 658 |  | 2023-04-27 | 2023-06-21 | 0
2681 | 1.4 | 1.4.1.1.2 | P | Breakout connections | Started | 5 | 462d | 2021-03-25 | 2022-12-30 |  | 15% |  |  |  | 883 |  | 2021-03-25 | 2022-12-30 | 0
2682 | 1.4 | 1.4.1.1.2.1 | P | Breakout preliminary design phase | Started | 6 | 358d | 2021-03-25 | 2022-08-08 |  | 19% |  |  |  | 987 |  | 2021-03-25 | 2022-08-08 | 0
2683 | 1.4 | 1.4.1.1.2.1.1 | C | Breakout preliminary design | Started | 7 | 336d | 2021-03-25 | 2022-07-07 | 2661FF +4w, 2660FF +3w | 20% |  |  |  | 731 |  | 2021-03-25 | 2022-07-07 | 0
2684 | 1.4 | 1.4.1.1.2.1.2 | C | Breakout preliminary design review | Not Started | 7 | 22d | 2022-07-08 | 2022-08-08 | 2683 | 0% |  |  |  | 731 |  | 2022-07-08 | 2022-08-08 | 0
2685 | 1.4 | 1.4.1.1.2.1.3 | C | Breakout preliminary design review complete | Not Started | 7 | 0 | 2022-08-08 | 2022-08-08 | 2684 |  |  |  |  | 987 |  | 2022-08-08 | 2022-08-08 | 0
2686 | 1.4 | 1.4.1.1.2.2 | P | Breakout final design phase | Not Started | 6 | 104d | 2022-08-09 | 2022-12-30 |  | 0% |  |  |  | 883 |  | 2022-08-09 | 2022-12-30 | 0
2687 | 1.4 | 1.4.1.1.2.2.1 | C | Breakout final design | Not Started | 7 | 10w | 2022-08-09 | 2022-10-17 | 2684 | 0% |  |  |  | 731 |  | 2022-08-09 | 2022-10-17 | 0
2688 | 1.4 | 1.4.1.1.2.2.2 | C | Breakout prototype production | Not Started | 7 | 14w | 2022-08-09 | 2022-11-14 | 2661, 2687SS | 0% |  |  |  | 781 |  | 2022-08-09 | 2022-11-14 | 0
2689 | 1.4 | 1.4.1.1.2.2.3 | C | Breakout prototype testing | Not Started | 7 | 12d | 2022-11-15 | 2022-11-30 | 2688 | 0% |  |  |  | 781 |  | 2022-11-15 | 2022-11-30 | 0
2690 | 1.4 | 1.4.1.1.2.2.4 | C | Breakout final design review | Not Started | 7 | 22d | 2022-12-01 | 2022-12-30 | 2689 | 0% |  |  |  | 781 |  | 2022-12-01 | 2022-12-30 | 0
2691 | 1.4 | 1.4.1.1.2.2.5 | C | Breakout final design review complete | Not Started | 7 | 0 | 2022-12-30 | 2022-12-30 | 2690 |  |  |  |  | 781 |  | 2022-12-30 | 2022-12-30 | 0
2692 | 1.4 | 1.4.1.1.3 | P | Main Cable Assembly production | Not Started | 5 | 102d | 2023-06-22 | 2023-11-10 |  | 0% |  |  |  | 658 |  | 2023-06-22 | 2023-11-10 | 0
2693 | 1.4 | 1.4.1.1.3.2 | C | MCA production | Not Started | 6 | 12w | 2023-06-22 | 2023-09-13 | 2680, 2691, 2753 | 0% |  |  |  | 658 |  | 2023-06-22 | 2023-09-13 | 0
2694 | 1.4 | 1.4.1.1.3.3 | C | Pre-ship review | Not Started | 6 | 2d | 2023-09-14 | 2023-09-15 | 2693 | 0% |  |  |  | 658 |  | 2023-09-14 | 2023-09-15 | 0
2695 | 1.4 | 1.4.1.1.3.4 | C | Main Cable Assembly shipping to PTH (RDD 12/1/23 for FY24 vessel. ROS 12/1/2025) | Not Started | 6 | 8w | 2023-09-18 | 2023-11-10 | 2694 | 0% |  |  |  | 658 |  | 2023-09-18 | 2023-11-10 | 0
2696 | 1.4 | 1.4.1.1.3.5 | C | MCAs shipped to PTH | Not Started | 6 | 0 | 2023-09-18 | 2023-09-18 | 2695SS |  |  |  |  | 698 |  | 2023-09-18 | 2023-09-18 | 0
2697 | 1.4 | 1.4.1.1.4 | C | Main Cable Assembly support | Should have Started | 5 | 551d | 2021-10-01 | 2023-11-10 | [5 empty] | 658 |  | 2021-10-01 | 2023-11-10 | 0
2698 | 1.4 | 1.4.1.2 | P | Breakout Cable Assemblies | Started | 4 | 537d | 2021-10-01 | 2023-10-23 |  | 2% |  |  |  | 672 |  | 2021-10-01 | 2023-10-23 | 0
2699 | 1.4 | 1.4.1.2.1 | P | BCA preliminary design phase | Started | 5 | 249d | 2021-11-01 | 2022-10-13 |  | 10% |  |  |  | 939 |  | 2021-11-01 | 2022-10-13 | 0
2700 | 1.4 | 1.4.1.2.1.1 | C | BCA preliminary design | Started | 6 | 125d | 2021-11-01 | 2022-04-22 |  | 20% |  |  |  | 672 |  | 2021-11-01 | 2022-04-22 | 0
2701 | 1.4 | 1.4.1.2.1.2 | C | BCA preliminary design review | Not Started | 6 | 2d | 2022-04-25 | 2022-04-26 | 2700 | 0% |  |  |  | 672 |  | 2022-04-25 | 2022-04-26 | 0
2702 | 1.4 | 1.4.1.2.1.3 | C | BCA prototype procurement | Not Started | 6 | 6w | 2022-04-27 | 2022-06-07 | 2701 | 0% |  |  |  | 672 |  | 2022-04-27 | 2022-06-07 | 0
2703 | 1.4 | 1.4.1.2.1.4 | C | BCA prototype production | Not Started | 6 | 16w | 2022-06-08 | 2022-09-27 | 2702 | 0% |  |  |  | 672 |  | 2022-06-08 | 2022-09-27 | 0
2704 | 1.4 | 1.4.1.2.1.5 | C | BCA prototype testing | Not Started | 6 | 12d | 2022-09-28 | 2022-10-13 | 2703 | 0% |  |  |  | 672 |  | 2022-09-28 | 2022-10-13 | 0
2705 | 1.4 | 1.4.1.2.1.6 | C | BCA prototype testing complete | Not Started | 6 | 0 | 2022-10-13 | 2022-10-13 | 2704 |  |  |  |  | 939 |  | 2022-10-13 | 2022-10-13 | 0
2706 | 1.4 | 1.4.1.2.2 | P | BCA final design phase | Not Started | 5 | 82d | 2022-10-14 | 2023-02-06 |  | 0% |  |  |  | 857 |  | 2022-10-14 | 2023-02-06 | 0
2707 | 1.4 | 1.4.1.2.2.1 | C | BCA final design | Not Started | 6 | 4w | 2022-10-14 | 2022-11-10 | 2704 | 0% |  |  |  | 672 |  | 2022-10-14 | 2022-11-10 | 0
2708 | 1.4 | 1.4.1.2.2.2 | C | BCA final design review | Not Started | 6 | 22d | 2022-11-11 | 2022-12-12 | 2707 | 0% |  |  |  | 672 |  | 2022-11-11 | 2022-12-12 | 0
2709 | 1.4 | 1.4.1.2.2.3 | C | BCA final design complete | Not Started | 6 | 0 | 2022-12-12 | 2022-12-12 | 2708 | 0% |  |  |  | 672 |  | 2022-12-12 | 2022-12-12 | 0
2710 | 1.4 | 1.4.1.2.2.4 | C | BCA procurement | Not Started | 6 | 8w | 2022-12-13 | 2023-02-06 | 2709 |  |  |  |  | 672 |  | 2022-12-13 | 2023-02-06 | 0
2711 | 1.4 | 1.4.1.2.3 | P | BCA production for first two strings | Not Started | 5 | 116d | 2023-02-07 | 2023-07-18 |  | 0% |  |  |  | 741 |  | 2023-02-07 | 2023-07-18 | 0
2712 | 1.4 | 1.4.1.2.3.1 | C | BCA manufacturing | Not Started | 6 | 20w | 2023-02-07 | 2023-06-26 | 2710 | 0% |  |  |  | 672 |  | 2023-02-07 | 2023-06-26 | 0
2713 | 1.4 | 1.4.1.2.3.2 | C | BCA pre-ship review | Not Started | 6 | 1d | 2023-06-27 | 2023-06-27 | 2712 | 0% |  |  |  | 741 |  | 2023-06-27 | 2023-06-27 | 0
2714 | 1.4 | 1.4.1.2.3.3 | C | Shipping to PTH (FY24 vessel, RDD 12/1/23 - ROS 2/1/25 to pre-position) | Not Started | 6 | 3w | 2023-06-28 | 2023-07-18 | 2713 | 0% |  |  |  | 741 |  | 2023-06-28 | 2023-07-18 | 0
2715 | 1.4 | 1.4.1.2.3.4 | C | BCAs for first two strings shipped | Not Started | 6 | 0 | 2023-07-18 | 2023-07-18 | 2714 |  |  |  |  | 741 |  | 2023-07-18 | 2023-07-18 | 0
2716 | 1.4 | 1.4.1.2.4 | P | BCA production for final five strings | Not Started | 5 | 85d | 2023-06-27 | 2023-10-23 |  | 0% |  |  |  | 672 |  | 2023-06-27 | 2023-10-23 | 0
2717 | 1.4 | 1.4.1.2.4.1 | C | BCA manufacturing - final five strings | Not Started | 6 | 14w | 2023-06-27 | 2023-10-02 | 2712 | 0% |  |  |  | 672 |  | 2023-06-27 | 2023-10-02 | 0
2718 | 1.4 | 1.4.1.2.4.2 | C | Shipping to PTH (FY24 vessel, RDD 12/1/23 - ROS 12/1/25) | Not Started | 6 | 3w | 2023-10-03 | 2023-10-23 | 2717 | 0% |  |  |  | 672 |  | 2023-10-03 | 2023-10-23 | 0
2719 | 1.4 | 1.4.1.2.4.3 | C | BCA manufacturing complete | Not Started | 6 | 0 | 2023-10-02 | 2023-10-02 | 2717 |  |  |  |  | 687 |  | 2023-10-02 | 2023-10-02 | 0
2720 | 1.4 | 1.4.1.2.5 | C | Breakout Cable Assemblies support | Should have Started | 5 | 523d | 2021-10-01 | 2023-10-03 | [5 empty] | 686 |  | 2021-10-01 | 2023-10-03 | 0
2721 | 1.4 | 1.4.1.3 | P | Penetrator Cable Assembly | Started | 4 | 491d | 2021-01-01 | 2022-11-18 |  | 38% |  |  |  | 913 |  | 2021-01-01 | 2022-11-18 | 0
2722 | 1.4 | 1.4.1.3.1 | P | v1 PCAs (Harwin connectors) | Started | 5 | 365d | 2021-01-01 | 2022-05-26 |  | 40% |  |  |  | 1039 |  | 2021-01-01 | 2022-05-26 | 0
2723 | 1.4 | 1.4.1.3.1.1 | C | v1 PCA fabrication | Complete | 6 | 42d | 2021-01-01 | 2021-03-01 |  | 100% |  |  |  | 1322 |  | 2021-01-01 | 2021-03-01 | 0
2724 | 1.4 | 1.4.1.3.1.2 | C | v1 PCA shipping to MMB device production facilities | Started | 6 | 8w | 2022-04-01 | 2022-05-26 | 2723SS, 2725 | 60% |  |  |  | 1039 |  | 2022-04-01 | 2022-05-26 | 0
2725 | 1.4 | 1.4.1.3.1.3 | C | v1 PCA restesting | Started | 6 | 26w | 2021-10-01 | 2022-03-31 |  | 15% |  |  |  | 1039 |  | 2021-10-01 | 2022-03-31 | 0
2726 | 1.4 | 1.4.1.3.1.4 | C | Harwin PCA production complete | Not Started | 6 | 0 | 2022-05-26 | 2022-05-26 | 2724 |  |  |  |  | 1039 |  | 2022-05-26 | 2022-05-26 | 0
2727 | 1.4 | 1.4.1.3.3 | P | PCA mating cables for FAT | Complete | 5 | 52d | 2021-01-01 | 2021-03-15 |  | 100% |  |  |  | 1352 |  | 2021-01-01 | 2021-03-15 | 0
2728 | 1.4 | 1.4.1.3.3.1 | C | PCA mating cable design | Complete | 6 | 21d | 2021-01-01 | 2021-01-29 |  | 100% |  |  |  | 1331 |  | 2021-01-01 | 2021-01-29 | 0
2729 | 1.4 | 1.4.1.3.3.2 | C | PCA mating cable prototyping | Complete | 6 | 32d | 2021-01-01 | 2021-02-15 | 2728SS | 100% |  |  |  | 1352 |  | 2021-01-01 | 2021-02-15 | 0
2730 | 1.4 | 1.4.1.3.3.3 | C | PCA mating cable materials procurement | Complete | 6 | 10d | 2021-02-16 | 2021-03-01 | 2729 | 100% |  |  |  | 1352 |  | 2021-02-16 | 2021-03-01 | 0
2731 | 1.4 | 1.4.1.3.3.4 | C | PCA mating cable materials shipping | Complete | 6 | 10d | 2021-03-02 | 2021-03-15 | 2730 | 100% |  |  |  | 1352 |  | 2021-03-02 | 2021-03-15 | 0
2732 | 1.4 | 1.4.1.3.2 | P | v2 PCAs (Molex connectors) | Started | 5 | 321d | 2021-01-01 | 2022-03-25 |  | 85% |  |  |  | 1083 |  | 2021-01-01 | 2022-03-25 | 0
2733 | 1.4 | 1.4.1.3.2.1 | C | v2 PCA design revisions | Complete | 6 | 64d | 2021-01-01 | 2021-03-31 |  | 100% |  |  |  | 1083 |  | 2021-01-01 | 2021-03-31 | 0
2734 | 1.4 | 1.4.1.3.2.2 | C | v2 PCA fabrication | Started | 6 | 197d | 2021-04-01 | 2021-12-31 | 2733 | 95% |  |  |  | 1083 |  | 2021-04-01 | 2021-12-31 | 0
2735 | 1.4 | 1.4.1.3.2.3 | C | v2 PCA shipping to DOM production facilities | Started | 6 | 12w | 2022-01-03 | 2022-03-25 | 2734 | 35% | holding to ship to Germany in one batch together with MMB PCAs |  |  | 1083 |  | 2022-01-03 | 2022-03-25 | 0
2736 | 1.4 | 1.4.1.3.2.4 | C | mDOM PCA production complete | Not Started | 6 | 0 | 2022-03-25 | 2022-03-25 | 2735 |  |  |  |  | 1083 |  | 2022-03-25 | 2022-03-25 | 0
2737 | 1.4 | 1.4.1.3.4 | P | PCA mating cables for SPAT | Started | 5 | 308d | 2021-09-15 | 2022-11-18 |  | 14% |  |  |  | 913 |  | 2021-09-15 | 2022-11-18 | 0
2738 | 1.4 | 1.4.1.3.4.1 | C | SPAT cable design | Started | 6 | 208d | 2021-09-15 | 2022-07-01 |  | 20% |  |  |  | 913 |  | 2021-09-15 | 2022-07-01 | 0
2739 | 1.4 | 1.4.1.3.4.2 | C | SPAT cable materials procurement | Not Started | 6 | 14w | 2022-07-04 | 2022-10-07 | 2738 | 0% |  |  |  | 913 |  | 2022-07-04 | 2022-10-07 | 0
2740 | 1.4 | 1.4.1.3.4.3 | C | SPAT cable production | Not Started | 6 | 3w | 2022-10-10 | 2022-10-28 | 2739 | 0% |  |  |  | 913 |  | 2022-10-10 | 2022-10-28 | 0
2741 | 1.4 | 1.4.1.3.4.4 | C | SPAT cable shipping to WIPAC | Not Started | 6 | 3w | 2022-10-31 | 2022-11-18 | 2740 | 0% |  |  |  | 913 |  | 2022-10-31 | 2022-11-18 | 0
2742 | 1.4 | 1.4.1.3.4.5 | C | SPAT cable production complete | Not Started | 6 | 0 | 2022-11-18 | 2022-11-18 | 2741 |  |  |  |  | 913 |  | 2022-11-18 | 2022-11-18 | 0
2743 | 1.4 | 1.4.1.3.5 | C | Penetrator Cable Assemblies support | Should have Started | 5 | 296d | 2021-10-01 | 2022-11-18 | [5 empty] | 913 |  | 2021-10-01 | 2022-11-18 | 0
2744 | 1.4 | 1.4.1.4 | P | String Hardware and Support Rope | Started | 4 | 567d | 2021-01-01 | 2023-03-06 |  | 48% |  |  |  | 837 |  | 2021-01-01 | 2023-03-06 | 0
2745 | 1.4 | 1.4.1.4.1 | P | Main cable connections | Started | 5 | 567d | 2021-01-01 | 2023-03-06 |  | 74% |  |  |  | 837 |  | 2021-01-01 | 2023-03-06 | 0
2746 | 1.4 | 1.4.1.4.1.1 | C | Final design | Complete | 6 | 326d | 2021-01-01 | 2022-04-01 |  | 100% |  |  |  | 1078 |  | 2021-01-01 | 2022-04-01 | 0
2747 | 1.4 | 1.4.1.4.1.2 | C | Support rope prototype procurement | Complete | 6 | 82d | 2021-07-08 | 2021-10-29 |  | 100% | Completed for JDR spec cable, finalization depends on MCA final spec |  |  | 1158 |  | 2021-07-08 | 2021-10-29 | 0
2748 | 1.4 | 1.4.1.4.1.3 | C | Support rope prototype testing | Started | 6 | 6w | 2022-02-18 | 2022-03-31 | 2747, 2657FF | 10% |  |  |  | 1079 |  | 2022-02-18 | 2022-03-31 | 0
2749 | 1.4 | 1.4.1.4.1.4 | C | YaleGrip tests with prototype cable | Started | 6 | 6w | 2022-02-18 | 2022-03-31 | 2657FF | 50% |  |  |  | 658 |  | 2022-02-18 | 2022-03-31 | 0
2750 | 1.4 | 1.4.1.4.1.5 | C | String hardware final design review | Not Started | 6 | 1d | 2022-10-17 | 2022-10-17 | 2657, 2749, 2660, 1688 | 0% |  |  |  | 658 |  | 2022-10-17 | 2022-10-17 | 0
2751 | 1.4 | 1.4.1.4.1.6 | C | String hardware procurement (shackles, chains etc) | Not Started | 6 | 12w | 2022-10-18 | 2023-01-09 | 2750 | 0% |  |  |  | 658 |  | 2022-10-18 | 2023-01-09 | 0
2752 | 1.4 | 1.4.1.4.1.7 | C | String hardware production | Not Started | 6 | 8w | 2023-01-10 | 2023-03-06 | 2751 | 0% |  |  |  | 837 |  | 2023-01-10 | 2023-03-06 | 0
2753 | 1.4 | 1.4.1.4.1.8 | C | Cable grip shipping to MCA production facility | Not Started | 6 | 2w | 2023-01-10 | 2023-01-23 | 2751 |  |  |  |  | 765 |  | 2023-01-10 | 2023-01-23 | 0
2754 | 1.4 | 1.4.1.4.1.9 | C | String hardware production complete | Not Started | 6 | 0 | 2023-01-23 | 2023-01-23 | 2753 |  |  |  |  | 867 |  | 2023-01-23 | 2023-01-23 | 0
2755 | 1.4 | 1.4.1.4.2 | C | String hardware support | Should have Started | 5 | 307d | 2021-10-01 | 2022-12-05 | [5 empty] | 902 |  | 2021-10-01 | 2022-12-05 | 0
2756 | 1.4 | 1.4.1.5 | P | Cable emulators | Started | 4 | 393d | 2021-01-01 | 2022-07-05 |  | 6% |  |  |  | 1011 |  | 2021-01-01 | 2022-07-05 | 0
2757 | 1.4 | 1.4.1.5.1 | C | Determine cable emulator requirements | Complete | 5 | 21d | 2021-01-01 | 2021-01-29 |  | 100% |  |  |  | 1383 |  | 2021-01-01 | 2021-01-29 | 0
2758 | 1.4 | 1.4.1.5.2 | C | Cable emulator box design | Started | 5 | 64d | 2021-12-01 | 2022-02-28 |  | 10% |  |  |  | 1102 |  | 2021-12-01 | 2022-02-28 | 0
2759 | 1.4 | 1.4.1.5.3 | C | Cable emulator PCB layout | Should have Started | 5 | 44d | 2021-12-01 | 2022-01-31 |  | 0% |  |  |  | 967 |  | 2021-12-01 | 2022-01-31 | 0
2760 | 1.4 | 1.4.1.5.4 | C | Cable emulator PCB procurement | Not Started | 5 | 4w | 2022-02-01 | 2022-02-28 | 2759 | 0% |  |  |  | 1011 |  | 2022-02-01 | 2022-02-28 | 0
2761 | 1.4 | 1.4.1.5.5 | C | Cable emulator prototype components procurement | Should have Started | 5 | 55d | 2021-12-01 | 2022-02-15 | 2759SS | 0% |  |  |  | 1020 |  | 2021-12-01 | 2022-02-15 | 0
2762 | 1.4 | 1.4.1.5.6 | C | Prototype assembly | Not Started | 5 | 1w | 2022-03-01 | 2022-03-07 | 2761, 2760 | 0% |  |  |  | 1011 |  | 2022-03-01 | 2022-03-07 | 0
2763 | 1.4 | 1.4.1.5.7 | C | Cable emulator testing | Not Started | 5 | 2w | 2022-03-08 | 2022-03-21 | 2762 | 0% |  |  |  | 1011 |  | 2022-03-08 | 2022-03-21 | 0
2764 | 1.4 | 1.4.1.5.8 | C | Cable emulator final design review | Not Started | 5 | 1d | 2022-03-22 | 2022-03-22 | 2763 | 0% |  |  |  | 1011 |  | 2022-03-22 | 2022-03-22 | 0
2765 | 1.4 | 1.4.1.5.9 | C | Procurement of materials for cable emulator production | Not Started | 5 | 8w | 2022-03-23 | 2022-05-17 | 2764 | 0% |  |  |  | 1011 |  | 2022-03-23 | 2022-05-17 | 0
2766 | 1.4 | 1.4.1.5.10 | C | Cable emulator assembly | Not Started | 5 | 3w | 2022-05-18 | 2022-06-07 | 2765 | 0% |  |  |  | 1011 |  | 2022-05-18 | 2022-06-07 | 0
2767 | 1.4 | 1.4.1.5.11 | C | Cable emulator shipping | Not Started | 5 | 4w | 2022-06-08 | 2022-07-05 | 2766 | 0% |  |  |  | 1011 |  | 2022-06-08 | 2022-07-05 | 0
2768 | 1.4 | 1.4.1.5.12 | C | Cable emulator production complete | Not Started | 5 | 0 | 2022-06-07 | 2022-06-07 | 2766 |  |  |  |  | 1031 |  | 2022-06-07 | 2022-06-07 | 0
2769 | 1.4 | 1.4.1.5.13 | C | Cable emulator support | Should have Started | 5 | 198d | 2021-10-01 | 2022-07-05 | [5 empty] | 1011 |  | 2021-10-01 | 2022-07-05 | 0
2770 | 1.4 | 1.4.1.6 | P | On-ice support for string installation | Not Started | 4 | 187d | 2025-06-01 | 2026-02-19 | [5 empty] | 73 |  | 2025-06-01 | 2026-02-19 | 0
2771 | 1.4 | 1.4.1.6.1 | C | Off-ice training Cable SMEs (FS3) | Not Started | 5 | 3d | 2025-08-13 | 2025-08-15 | 777FF |  |  |  |  | 204 |  | 2025-08-13 | 2025-08-15 | 0
2772 | 1.4 | 1.4.1.6.2 | C | Cable SME arrives to support FS3 activities | Not Started | 5 | 0 | 2025-11-20 | 2025-11-20 | [5 empty] | 136 |  | 2025-11-20 | 2025-11-20 | 0
2773 | 1.4 | 1.4.1.6.3 | C | PQ, ECW & Deployment Travel Costs Cable SMEs (FS3) | Not Started | 5 | 187d | 2025-06-01 | 2026-02-19 | [5 empty] | 73 |  | 2025-06-01 | 2026-02-19 | 0
2774 | 1.4 | 1.4.1.6.4 | C | Cable SME support for FS3 activities (slot 1) | Not Started | 5 | 34d | 2025-11-20 | 2026-01-09 | [5 empty] | 102 |  | 2025-11-20 | 2026-01-09 | 0
2775 | 1.4 | 1.4.1.6.5 | C | Cable SME support for FS3 activities (slot 2) | Not Started | 5 | 11d | 2026-01-06 | 2026-01-20 | [5 empty] | 95 |  | 2026-01-06 | 2026-01-20 | 0
2776 | 1.4 | 1.4.2 | P | Surface Cables | Started | 3 | 1359d | 2020-12-01 | 2026-02-26 |  | 10% | Replacement for 1.4.2 IDF via CR2 |  |  | 68 |  | 2020-12-01 | 2026-02-26 | 0
2777 | 1.4 | 1.4.2.1 | P | Surface Cable Assemblies | Started | 4 | 434d | 2020-12-01 | 2022-07-29 |  | 34% |  |  |  | 993 |  | 2020-12-01 | 2022-07-29 | 0
2778 | 1.4 | 1.4.2.1.1 | C | Final design | Complete | 5 | 44d | 2020-12-01 | 2021-01-29 |  | 100% |  |  |  | 1231 |  | 2020-12-01 | 2021-01-29 | 0
2779 | 1.4 | 1.4.2.1.2 | C | Final design review | Complete | 5 | 2d | 2021-02-01 | 2021-02-02 | 2778 | 100% | is this target based on dates carried over from the IDF plan? |  |  | 1231 |  | 2021-02-01 | 2021-02-02 | 0
2780 | 1.4 | 1.4.2.1.3 | C | Procurement | Complete | 5 | 40d | 2021-02-03 | 2021-03-30 | 2779 | 100% |  |  |  | 1231 |  | 2021-02-03 | 2021-03-30 | 0
2781 | 1.4 | 1.4.2.1.4 | C | Cable production | Complete | 5 | 60d | 2021-03-31 | 2021-06-22 | 2780 | 100% |  |  |  | 1231 |  | 2021-03-31 | 2021-06-22 | 0
2782 | 1.4 | 1.4.2.1.5 | C | Shipping to connectorization facility | Complete | 5 | 50d | 2021-06-23 | 2021-08-31 | 2781 | 100% |  |  |  | 1231 |  | 2021-06-23 | 2021-08-31 | 0
2783 | 1.4 | 1.4.2.1.6 | C | Connectorization and testing | Started | 5 | 153d | 2021-12-01 | 2022-07-01 |  | 12% |  |  |  | 993 |  | 2021-12-01 | 2022-07-01 | 0
2784 | 1.4 | 1.4.2.1.7 | C | Pre-ship review | Not Started | 5 | 68d | 2022-02-10 | 2022-05-16 |  | 0% | is this target based on dates carried over from the IDF plan? |  |  | 1027 |  | 2022-02-10 | 2022-05-16 | 0
2785 | 1.4 | 1.4.2.1.8 | C | Shipping to PTH (RDD 12/1/22 for FY23 vessel, ROS 12/1/24) | Not Started | 5 | 4w | 2022-07-04 | 2022-07-29 | 2783, 2784 | 0% |  |  |  | 993 |  | 2022-07-04 | 2022-07-29 | 0
2786 | 1.4 | 1.4.2.1.9 | C | SCAs shipped to PTH | Not Started | 5 | 0 | 2022-07-04 | 2022-07-04 | 2785SS | 0% |  |  |  | 1013 |  | 2022-07-04 | 2022-07-04 | 0
2787 | 1.4 | 1.4.2.1.10 | C | Surface Cable Assembly support | Should have Started | 5 | 201d | 2021-10-01 | 2022-07-08 | [5 empty] | 1008 |  | 2021-10-01 | 2022-07-08 | 0
2788 | 1.4 | 1.4.2.2 | P | Surface Junction Boxes | Started | 4 | 296d | 2021-10-01 | 2022-11-18 |  | 14% |  |  |  | 913 |  | 2021-10-01 | 2022-11-18 | 0
2789 | 1.4 | 1.4.2.2.1 | C | Final design | Started | 5 | 20w | 2022-03-03 | 2022-07-20 | 2669FF +2d | 70% |  |  |  | 913 |  | 2022-03-03 | 2022-07-20 | 0
2790 | 1.4 | 1.4.2.2.2 | C | Final design review | Not Started | 5 | 1d | 2022-07-21 | 2022-07-21 | 2789 | 0% |  |  |  | 913 |  | 2022-07-21 | 2022-07-21 | 0
2791 | 1.4 | 1.4.2.2.3 | C | Procurement | Not Started | 5 | 6w | 2022-07-22 | 2022-09-01 | 2790 | 0% |  |  |  | 913 |  | 2022-07-22 | 2022-09-01 | 0
2792 | 1.4 | 1.4.2.2.4 | C | Fabrication | Not Started | 5 | 6w | 2022-09-02 | 2022-10-13 | 2791 | 0% |  |  |  | 913 |  | 2022-09-02 | 2022-10-13 | 0
2793 | 1.4 | 1.4.2.2.5 | C | SJB production complete | Not Started | 5 | 0 | 2022-10-13 | 2022-10-13 | 2792 | 0% |  |  |  | 939 |  | 2022-10-13 | 2022-10-13 | 0
2794 | 1.4 | 1.4.2.2.6 | C | Pre-ship review | Not Started | 5 | 11d | 2022-10-14 | 2022-10-28 | 2792 | 0% |  |  |  | 913 |  | 2022-10-14 | 2022-10-28 | 0
2795 | 1.4 | 1.4.2.2.7 | C | Shipping to PTH (RDD 12/1/22 for FY23 vessel - ROS 12/1/24) | Not Started | 5 | 3w | 2022-10-31 | 2022-11-18 | 2794 | 0% |  |  |  | 913 |  | 2022-10-31 | 2022-11-18 | 0
2796 | 1.4 | 1.4.2.2.8 | C | Surface Junction Box support | Should have Started | 5 | 296d | 2021-10-01 | 2022-11-18 | [5 empty] | 913 |  | 2021-10-01 | 2022-11-18 | 0
2797 | 1.4 | 1.4.2.3 | P | ICL Upgrade | Started | 4 | 1336d | 2021-01-01 | 2026-02-26 |  | 5% |  |  |  | 68 |  | 2021-01-01 | 2026-02-26 | 0
2798 | 1.4 | 1.4.2.3.1 | C | ASC liaison | Started | 5 | 1336d | 2021-01-01 | 2026-02-26 |  | 8% |  |  |  | 68 |  | 2021-01-01 | 2026-02-26 | 0
2799 | 1.4 | 1.4.2.3.2 | P | Patch panels | Started | 5 | 185d | 2022-04-01 | 2022-12-15 |  | 21% |  |  |  | 894 |  | 2022-04-01 | 2022-12-15 | 0
2800 | 1.4 | 1.4.2.3.2.1 | C | Final design | Started | 6 | 44d | 2022-04-01 | 2022-06-01 |  | 90% |  |  |  | 366 |  | 2022-04-01 | 2022-06-01 | 0
2801 | 1.4 | 1.4.2.3.2.2 | C | Procurement | Not Started | 6 | 16w | 2022-06-02 | 2022-09-21 | 2800 | 0% |  |  |  | 366 |  | 2022-06-02 | 2022-09-21 | 0
2802 | 1.4 | 1.4.2.3.2.3 | C | Fabrication | Not Started | 6 | 6w | 2022-09-22 | 2022-11-02 | 2801 | 0% |  |  |  | 366 |  | 2022-09-22 | 2022-11-02 | 0
2803 | 1.4 | 1.4.2.3.2.4 | C | Pre-ship review | Not Started | 6 | 2w | 2022-11-03 | 2022-11-16 | 2802 | 0% |  |  |  | 365 |  | 2022-11-03 | 2022-11-16 | 0
2804 | 1.4 | 1.4.2.3.2.5 | C | Shipping to PTH (NB: small -- RDD 9/15/23 for ComSur FY25, ROS 12/15/23) | Not Started | 6 | 4w | 2022-11-17 | 2022-12-14 | 2803 | 0% |  |  |  | 366 |  | 2022-11-17 | 2022-12-14 | 0
2805 | 1.4 | 1.4.2.3.2.6 | C | Patch panels shipped to PTH | Not Started | 6 | 0 | 2022-11-17 | 2022-11-17 | 2804SS | 0% |  |  |  | 915 |  | 2022-11-17 | 2022-11-17 | 0
2806 | 1.4 | 1.4.2.3.2.7 | C | Patch panels installation in ICL | Not Started | 6 | 1d | 2022-12-15 | 2022-12-15 | 2804 | 0% |  |  |  | 366 |  | 2022-12-15 | 2022-12-15 | 0
2807 | 1.4 | 1.4.2.3.3 | P | Patch cables | Started | 5 | 687d | 2022-04-12 | 2024-12-03 |  | 4% |  |  |  | 385 |  | 2022-04-12 | 2024-12-03 | 0
2808 | 1.4 | 1.4.2.3.3.1 | C | Final design | Started | 6 | 35w | 2022-06-30 | 2023-03-01 | 2820FF +3w | 10% |  |  |  | 647 |  | 2022-06-30 | 2023-03-01 | 0
2809 | 1.4 | 1.4.2.3.3.2 | C | Prototype production and evaluation | Not Started | 6 | 29w | 2022-04-12 | 2022-10-31 |  | 0% |  |  |  | 734 |  | 2022-04-12 | 2022-10-31 | 0
2810 | 1.4 | 1.4.2.3.3.3 | C | Final design review | Not Started | 6 | 11d | 2023-03-02 | 2023-03-16 | 2808, 2809 | 0% |  |  |  | 647 |  | 2023-03-02 | 2023-03-16 | 0
2811 | 1.4 | 1.4.2.3.3.4 | C | Procurement | Started | 6 | 16w | 2023-03-17 | 2023-07-06 | 2810 | 5% |  |  |  | 647 |  | 2023-03-17 | 2023-07-06 | 0
2812 | 1.4 | 1.4.2.3.3.5 | C | Production | Not Started | 6 | 15w | 2023-07-07 | 2023-10-19 | 2811 | 0% |  |  |  | 647 |  | 2023-07-07 | 2023-10-19 | 0
2813 | 1.4 | 1.4.2.3.3.6 | C | Pre-ship review | Started | 6 | 7d | 2023-10-20 | 2023-10-30 | 2812 | 5% |  |  |  | 647 |  | 2023-10-20 | 2023-10-30 | 0
2814 | 1.4 | 1.4.2.3.3.7 | C | Shipping to PTH (RDD 9/15/24 for FY25 ComSur, ROS 12/1/24) | Not Started | 6 | 4w | 2023-10-31 | 2023-11-28 | 2813 | 0% |  |  |  | 647 |  | 2023-10-31 | 2023-11-28 | 0
2815 | 1.4 | 1.4.2.3.3.8 | C | Patch cables shipped to PTH | Not Started | 6 | 0 | 2023-10-31 | 2023-10-31 | 2814SS | 0% |  |  |  | 667 |  | 2023-10-31 | 2023-10-31 | 0
2816 | 1.4 | 1.4.2.3.3.9 | C | Patch cables installation in ICL | Not Started | 6 | 5d | 2024-11-26 | 2024-12-03 | 2856, 2864, 2889, 2806, 2846, 2893SS | 0% |  |  |  | 366 |  | 2024-11-26 | 2024-12-03 | 0
2817 | 1.4 | 1.4.2.3.3.10 | C | Patch cables and panels installed in ICL | Not Started | 6 | 0 | 2024-12-03 | 2024-12-03 | 2806, 2816 | 0% |  |  |  | 385 |  | 2024-12-03 | 2024-12-03 | 0
2818 | 1.4 | 1.4.2.3.4 | C | ICL Upgrade support | Should have Started | 5 | 1141d | 2021-10-01 | 2026-02-26 | [5 empty] | 68 |  | 2021-10-01 | 2026-02-26 | 0
2819 | 1.4 | 1.4.2.4 | P | On-ice support for surface cable installation | Not Started | 4 | 564d | 2022-12-15 | 2025-02-19 | [5 empty] | 331 |  | 2022-12-15 | 2025-02-19 | 0
2820 | 1.4 | 1.4.2.4.1 | C | Prepare Upgrade electronics rack (M&O) | Not Started | 5 | 40d | 2022-12-15 | 2023-02-08 | [5 empty] | 366 |  | 2022-12-15 | 2023-02-08 | 0
2821 | 1.4 | 1.4.2.4.3 | C | Cable SME arrives to support FS2 activities | Not Started | 5 | 0 | 2024-12-15 | 2024-12-15 | [5 empty] | 347 |  | 2024-12-15 | 2024-12-15 | 0
2822 | 1.4 | 1.4.2.4.4 | C | PQ, ECW, Deployment Travel Costs Cable SMEs (FS2) | Not Started | 5 | 186d | 2024-06-01 | 2025-02-19 | [5 empty] | 331 |  | 2024-06-01 | 2025-02-19 | 0
2823 | 1.4 | 1.4.2.4.5 | C | Cable SME support for FS2 activities (slot 1) | Not Started | 5 | 18d | 2024-12-15 | 2025-01-09 | [5 empty] | 360 |  | 2024-12-15 | 2025-01-09 | 0
2824 | 1.4 | 1.4.2.4.6 | C | Cable SME support for FS2 activities (slot 2) | Not Started | 5 | 24d | 2024-12-15 | 2025-01-17 | [5 empty] | 354 |  | 2024-12-15 | 2025-01-17 | 0
2825 | 1.4 | 1.4.3 | P | FieldHub | Started | 3 | 1009d | 2021-01-01 | 2024-11-18 |  | 28% |  |  |  | 395 |  | 2021-01-01 | 2024-11-18 | 0
2826 | 1.4 | 1.4.3.1 | P | FieldHub Electronics | Started | 4 | 1009d | 2021-01-01 | 2024-11-18 |  | 28% |  |  |  | 395 |  | 2021-01-01 | 2024-11-18 | 0
2827 | 1.4 | 1.4.3.1.1 | P | FieldHub Design | Started | 5 | 632d | 2021-01-01 | 2023-06-05 |  | 44% |  |  |  | 772 |  | 2021-01-01 | 2023-06-05 | 0
2828 | 1.4 | 1.4.3.1.1.1 | C | FieldHub rev1 design | Started | 6 | 346d | 2021-01-01 | 2022-04-29 |  | 80% | including FDOR firmware adapatation |  |  | 606 |  | 2021-01-01 | 2022-04-29 | 0
2829 | 1.4 | 1.4.3.1.1.2 | C | FieldHub rev1 prototype production | Not Started | 6 | 9w | 2022-05-02 | 2022-07-01 | 2828 | 0% |  |  |  | 606 |  | 2022-05-02 | 2022-07-01 | 0
2830 | 1.4 | 1.4.3.1.1.3 | C | FieldHub rev1 testing and installation at NTS | Not Started | 6 | 9w | 2022-07-18 | 2022-09-16 | 2829, 2870SS | 0% |  |  |  | 606 |  | 2022-07-18 | 2022-09-16 | 0
2831 | 1.4 | 1.4.3.1.1.4 | C | FieldHub rev2 design | Not Started | 6 | 11w | 2022-09-19 | 2022-12-02 | 2830 | 0% |  |  |  | 606 |  | 2022-09-19 | 2022-12-02 | 0
2832 | 1.4 | 1.4.3.1.1.5 | C | FieldHub rev2 prototype production | Not Started | 6 | 13w | 2022-12-05 | 2023-03-03 | 2831 | 0% |  |  |  | 606 |  | 2022-12-05 | 2023-03-03 | 0
2833 | 1.4 | 1.4.3.1.1.6 | C | FieldHub rev2 testing and installation at NTS | Not Started | 6 | 9w | 2023-03-06 | 2023-05-05 | 2832, 2884 | 0% |  |  |  | 606 |  | 2023-03-06 | 2023-05-05 | 0
2834 | 1.4 | 1.4.3.1.1.8 | C | FieldHub final design review | Not Started | 6 | 2d | 2023-05-04 | 2023-05-05 | 2833FF | 0% |  |  |  | 606 |  | 2023-05-04 | 2023-05-05 | 0
2835 | 1.4 | 1.4.3.1.1.9 | C | FieldHub rev3 design (if required) | Not Started | 6 | 4w | 2023-05-08 | 2023-06-02 | 2834 | 0% |  |  |  | 606 |  | 2023-05-08 | 2023-06-02 | 0
2836 | 1.4 | 1.4.3.1.1.10 | C | Production readiness review | Not Started | 6 | 1d | 2023-06-05 | 2023-06-05 | 2835 | 0% |  |  |  | 636 |  | 2023-06-05 | 2023-06-05 | 0
2837 | 1.4 | 1.4.3.1.1.11 | C | FieldHub design complete | Not Started | 6 | 0 | 2023-06-05 | 2023-06-05 | 2836 |  |  |  |  | 772 |  | 2023-06-05 | 2023-06-05 | 0
2838 | 1.4 | 1.4.3.1.2 | P | FieldHub Production | Not Started | 5 | 377d | 2023-06-06 | 2024-11-18 |  | 0% |  |  |  | 395 |  | 2023-06-06 | 2024-11-18 | 0
2839 | 1.4 | 1.4.3.1.2.1 | C | Component procurement | Not Started | 6 | 6w | 2023-06-06 | 2023-07-17 | 2836 | 0% |  |  |  | 636 |  | 2023-06-06 | 2023-07-17 | 0
2840 | 1.4 | 1.4.3.1.2.2 | C | PCB fabrication | Not Started | 6 | 6w | 2023-06-06 | 2023-07-17 | 2839SS | 0% |  |  |  | 636 |  | 2023-06-06 | 2023-07-17 | 0
2841 | 1.4 | 1.4.3.1.2.3 | C | FieldHub assembly | Not Started | 6 | 9w | 2023-07-18 | 2023-09-18 | 2839, 2840 | 0% |  |  |  | 636 |  | 2023-07-18 | 2023-09-18 | 0
2842 | 1.4 | 1.4.3.1.2.4 | C | FieldHub acceptance testing | Not Started | 6 | 4w | 2023-09-19 | 2023-10-16 | 2841 | 0% |  |  |  | 636 |  | 2023-09-19 | 2023-10-16 | 0
2843 | 1.4 | 1.4.3.1.2.5 | C | FieldHub production complete | Not Started | 6 | 0 | 2023-10-16 | 2023-10-16 | 2842 | 0% |  |  |  | 677 |  | 2023-10-16 | 2023-10-16 | 0
2844 | 1.4 | 1.4.3.1.2.6 | C | Pre-ship review | Not Started | 6 | 11d | 2023-10-17 | 2023-10-31 | 2842 | 0% |  |  |  | 636 |  | 2023-10-17 | 2023-10-31 | 0
2845 | 1.4 | 1.4.3.1.2.7 | C | Shipping to CHC (Air to Pole, RDD ??, ROS 12/1/24) | Not Started | 6 | 6w | 2023-11-01 | 2023-12-13 | 2844 | 0% |  |  |  | 636 |  | 2023-11-01 | 2023-12-13 | 0
2846 | 1.4 | 1.4.3.1.2.8 | C | FieldHub installation and commissioning in ICL | Not Started | 6 | 5d | 2024-11-12 | 2024-11-18 | 2856, 2889, 3192, 2820 | 0% |  |  |  | 366 |  | 2024-11-12 | 2024-11-18 | 0
2847 | 1.4 | 1.4.3.1.2.9 | C | FieldHubs installed in ICL | Not Started | 6 | 0 | 2024-11-18 | 2024-11-18 | 2846 | 0% |  |  |  | 366 |  | 2024-11-18 | 2024-11-18 | 0
2848 | 1.4 | 1.4.4 | P | CPT Central Infrastructure | Started | 3 | 1310d | 2021-02-01 | 2026-02-19 |  | 15% |  |  |  | 73 |  | 2021-02-01 | 2026-02-19 | 0
2849 | 1.4 | 1.4.4.1 | P | Communications and Timing Systems | Started | 4 | 1041d | 2021-02-01 | 2025-02-04 |  | 22% |  |  |  | 342 |  | 2021-02-01 | 2025-02-04 | 0
2850 | 1.4 | 1.4.4.1.1 | P | Timing distribution system | Started | 5 | 624d | 2021-02-01 | 2023-06-22 |  | 53% |  |  |  | 759 |  | 2021-02-01 | 2023-06-22 | 0
2851 | 1.4 | 1.4.4.1.1.1 | C | Procurement | Started | 6 | 533d | 2021-02-01 | 2023-02-15 |  | 60% |  |  |  | 366 |  | 2021-02-01 | 2023-02-15 | 0
2852 | 1.4 | 1.4.4.1.1.2 | C | Testing | Started | 6 | 8w | 2023-02-16 | 2023-04-12 | 2851 | 25% |  |  |  | 366 |  | 2023-02-16 | 2023-04-12 | 0
2853 | 1.4 | 1.4.4.1.1.3 | C | Pre-ship review | Not Started | 6 | 11d | 2023-04-13 | 2023-04-27 | 2852 | 0% |  |  |  | 366 |  | 2023-04-13 | 2023-04-27 | 0
2854 | 1.4 | 1.4.4.1.1.4 | C | Timing distribution system complete | Not Started | 6 | 0 | 2023-04-27 | 2023-04-27 | 2853 | 0% |  |  |  | 799 |  | 2023-04-27 | 2023-04-27 | 0
2855 | 1.4 | 1.4.4.1.1.5 | C | Shipping to PTH (RDD 9/15/24 for FY25 ComSur - ROS 12/1/24) | Not Started | 6 | 7w | 2023-04-28 | 2023-06-15 | 2853 | 0% |  |  |  | 366 |  | 2023-04-28 | 2023-06-15 | 0
2856 | 1.4 | 1.4.4.1.1.7 | C | Timing distribution system installation in ICL | Not Started | 6 | 5d | 2023-06-16 | 2023-06-22 | 2820, 2855 | 0% |  |  |  | 366 |  | 2023-06-16 | 2023-06-22 | 0
2857 | 1.4 | 1.4.4.1.2 | P | Timing monitoring system | Started | 5 | 764d | 2021-12-19 | 2024-11-25 |  | 22% |  |  |  | 390 |  | 2021-12-19 | 2024-11-25 | 0
2858 | 1.4 | 1.4.4.1.2.1 | C | Final design | Started | 6 | 127w | 2021-12-19 | 2024-05-28 |  | 25% | requires pDAQ software support |  |  | 474 |  | 2021-12-19 | 2024-05-28 | 0
2859 | 1.4 | 1.4.4.1.2.2 | C | Prototype production | Started | 6 | 4w | 2024-04-03 | 2024-04-30 | 2858FS -8w | 10% |  |  |  | 519 |  | 2024-04-03 | 2024-04-30 | 0
2860 | 1.4 | 1.4.4.1.2.3 | C | Installation and testing at NTS/SPTS | Not Started | 6 | 4w | 2024-05-01 | 2024-05-28 | 2859 | 0% |  |  |  | 519 |  | 2024-05-01 | 2024-05-28 | 0
2861 | 1.4 | 1.4.4.1.2.4 | C | Production of ICL system | Not Started | 6 | 6w | 2024-05-29 | 2024-07-09 | 2858 | 0% |  |  |  | 474 |  | 2024-05-29 | 2024-07-09 | 0
2862 | 1.4 | 1.4.4.1.2.5 | C | Timing monitoring system complete | Not Started | 6 | 0 | 2024-07-09 | 2024-07-09 | 2861 | 0% |  |  |  | 489 |  | 2024-07-09 | 2024-07-09 | 0
2863 | 1.4 | 1.4.4.1.2.6 | C | Shipping to PTH (RDD 9/15/24 for FY25 ComSur, ROS 12/1/24) | Not Started | 6 | 3w | 2024-07-10 | 2024-07-30 | 2861 | 0% |  |  |  | 474 |  | 2024-07-10 | 2024-07-30 | 0
2864 | 1.4 | 1.4.4.1.2.8 | C | Timing monitoring system installation in ICL | Not Started | 6 | 5d | 2024-11-19 | 2024-11-25 | 2820, 2847 | 0% |  |  |  | 366 |  | 2024-11-19 | 2024-11-25 | 0
2865 | 1.4 | 1.4.4.1.3 | C | Timing systems support | Should have Started | 5 | 867d | 2021-10-01 | 2025-02-04 | [5 empty] | 342 |  | 2021-10-01 | 2025-02-04 | 0
2866 | 1.4 | 1.4.4.2 | P | Power systems | Started | 4 | 1287d | 2021-03-04 | 2026-02-19 |  | 9% |  |  |  | 73 |  | 2021-03-04 | 2026-02-19 | 0
2867 | 1.4 | 1.4.4.2.1 | P | DOM power supply | Started | 5 | 572d | 2021-03-04 | 2023-05-12 |  | 38% |  |  |  | 788 |  | 2021-03-04 | 2023-05-12 | 0
2868 | 1.4 | 1.4.4.2.1.1 | C | Final design | Started | 6 | 68w | 2021-05-07 | 2022-08-25 | 2870FF | 40% |  |  |  | 974 |  | 2021-05-07 | 2022-08-25 | 0
2869 | 1.4 | 1.4.4.2.1.2 | C | Sample procurement and evaluation | Started | 6 | 412d | 2021-03-04 | 2022-09-30 |  | 50% |  |  |  | 366 |  | 2021-03-04 | 2022-09-30 | 0
2870 | 1.4 | 1.4.4.2.1.3 | C | Sample installation and testing at NTS | Not Started | 6 | 6w | 2022-07-16 | 2022-08-25 | [5 empty] | 606 |  | 2022-07-16 | 2022-08-25 | 0
2871 | 1.4 | 1.4.4.2.1.5 | C | Procurement | Not Started | 6 | 25w | 2022-11-21 | 2023-05-12 | 2885 | 0% |  |  |  | 365 |  | 2022-11-21 | 2023-05-12 | 0
2872 | 1.4 | 1.4.4.2.1.6 | C | Power supply system complete | Not Started | 6 | 0 | 2023-05-12 | 2023-05-12 | 2871 | 0% |  |  |  | 366 |  | 2023-05-12 | 2023-05-12 | 0
2873 | 1.4 | 1.4.4.2.2 | P | DOM power distribution | Started | 5 | 416d | 2021-09-03 | 2023-04-07 |  | 20% |  |  |  | 813 |  | 2021-09-03 | 2023-04-07 | 0
2874 | 1.4 | 1.4.4.2.2.1 | C | Final design | Started | 6 | 296d | 2021-09-03 | 2022-10-21 | 2869FF +3w | 25% |  |  |  | 933 |  | 2021-09-03 | 2022-10-21 | 0
2875 | 1.4 | 1.4.4.2.2.2 | C | Prototype production and evaluation | Started | 6 | 20w | 2022-05-16 | 2022-09-30 | 2869FF | 25% |  |  |  | 366 |  | 2022-05-16 | 2022-09-30 | 0
2876 | 1.4 | 1.4.4.2.2.4 | C | Production | Not Started | 6 | 20w | 2022-11-21 | 2023-04-07 | 2885 | 0% |  |  |  | 365 |  | 2022-11-21 | 2023-04-07 | 0
2877 | 1.4 | 1.4.4.2.2.5 | C | Power distribution system complete | Not Started | 6 | 0 | 2023-04-07 | 2023-04-07 | 2876 | 0% |  |  |  | 366 |  | 2023-04-07 | 2023-04-07 | 0
2878 | 1.4 | 1.4.4.2.3 | P | DOM power control | Should have Started | 5 | 496d | 2021-05-15 | 2023-04-07 |  | 0% |  |  |  | 813 |  | 2021-05-15 | 2023-04-07 | 0
2879 | 1.4 | 1.4.4.2.3.1 | C | Final design | Should have Started | 6 | 286d | 2021-05-15 | 2022-06-17 |  | 0% |  |  |  | 1023 |  | 2021-05-15 | 2022-06-17 | 0
2880 | 1.4 | 1.4.4.2.3.2 | C | Prototype production and evaluation | Not Started | 6 | 20w | 2022-05-16 | 2022-09-30 | 2875FF | 0% |  |  |  | 366 |  | 2022-05-16 | 2022-09-30 | 0
2881 | 1.4 | 1.4.4.2.3.4 | C | Production | Not Started | 6 | 20w | 2022-11-21 | 2023-04-07 | 2885 | 0% |  |  |  | 365 |  | 2022-11-21 | 2023-04-07 | 0
2882 | 1.4 | 1.4.4.2.3.5 | C | Power control system complete | Not Started | 6 | 0 | 2023-04-07 | 2023-04-07 | 2881 | 0% |  |  |  | 366 |  | 2023-04-07 | 2023-04-07 | 0
2883 | 1.4 | 1.4.4.2.4 | P | Power system shipping and installation | Not Started | 5 | 186d | 2022-10-03 | 2023-06-19 |  | 0% |  |  |  | 762 |  | 2022-10-03 | 2023-06-19 | 0
2884 | 1.4 | 1.4.4.2.4.1 | C | Power system installation and testing at NTS | Not Started | 6 | 4w | 2022-10-03 | 2022-10-28 | 2869, 2875, 2880 |  |  |  |  | 366 |  | 2022-10-03 | 2022-10-28 | 0
2885 | 1.4 | 1.4.4.2.4.2 | C | Power system final design review | Not Started | 6 | 3w | 2022-10-31 | 2022-11-18 | 2884 |  |  |  |  | 366 |  | 2022-10-31 | 2022-11-18 | 0
2886 | 1.4 | 1.4.4.2.4.3 | C | Pre-ship review | Not Started | 6 | 1d | 2023-05-15 | 2023-05-15 | 2872, 2877, 2882 | 0% |  |  |  | 366 |  | 2023-05-15 | 2023-05-15 | 0
2887 | 1.4 | 1.4.4.2.4.4 | C | Shipping to PTH (ComSur RDD 9/15/24, ROS 12/1/24) | Not Started | 6 | 4w | 2023-05-16 | 2023-06-12 | 2886 | 0% |  |  |  | 366 |  | 2023-05-16 | 2023-06-12 | 0
2888 | 1.4 | 1.4.4.2.4.5 | C | Power system shipped | Not Started | 6 | 0 | 2023-05-16 | 2023-05-16 | 2887SS | 0% |  |  |  | 787 |  | 2023-05-16 | 2023-05-16 | 0
2889 | 1.4 | 1.4.4.2.4.6 | C | Power system installation in ICL | Not Started | 6 | 5d | 2023-06-13 | 2023-06-19 | 2820, 2887 | 0% | – requires ICL electrical upgrade by ASC |  |  | 366 |  | 2023-06-13 | 2023-06-19 | 0
2890 | 1.4 | 1.4.4.2.5 | C | Power systems support | Should have Started | 5 | 1121d | 2021-10-01 | 2026-01-29 | [5 empty] | 88 |  | 2021-10-01 | 2026-01-29 | 0
2891 | 1.4 | 1.4.4.3 | P | On-ice support for CPT electronics | Not Started | 5 | 549d | 2024-01-07 | 2026-02-19 | [5 empty] | 73 |  | 2024-01-07 | 2026-02-19 | 0
2892 | 1.4 | 1.4.4.3.1 | C | Electronics SME arrives to support FS2 activities | Not Started | 6 | 0 | 2024-01-07 | 2024-01-07 | [5 empty] | 622 |  | 2024-01-07 | 2024-01-07 | 0
2893 | 1.4 | 1.4.4.3.2 | C | PQ, ECW, Deployment Travel Costs FS2 Electronics SMEs (Headcount 2) | Not Started | 6 | 186d | 2024-06-01 | 2025-02-19 | [5 empty] | 326 |  | 2024-06-01 | 2025-02-19 | 0
2894 | 1.4 | 1.4.4.3.3 | C | Electronics SME support for FS2 activities (slot 1) | Not Started | 6 | 19d | 2025-01-07 | 2025-01-31 | [5 empty] | 344 |  | 2025-01-07 | 2025-01-31 | 0
2895 | 1.4 | 1.4.4.3.4 | C | Electronics SME support for FS2 activities (slot 2) | Not Started | 6 | 14d | 2025-01-15 | 2025-02-03 | [5 empty] | 343 |  | 2025-01-15 | 2025-02-03 | 0
2896 | 1.4 | 1.4.4.3.5 | C | Off-ice training Electronics SMEs (FS3) | Not Started | 6 | 21d | 2025-08-01 | 2025-08-29 | [5 empty] | 194 |  | 2025-08-01 | 2025-08-29 | 0
2897 | 1.4 | 1.4.4.3.6 | C | Electronics SME arrives to support FS3 activities | Not Started | 6 | 0 | 2025-11-15 | 2025-11-15 | [5 empty] | 137 |  | 2025-11-15 | 2025-11-15 | 0
2898 | 1.4 | 1.4.4.3.7 | C | PQ, ECW, Deployment Travel Costs FS3 Electronics SMEs (Headcount 2) | Not Started | 6 | 187d | 2025-06-01 | 2026-02-19 | [5 empty] | 73 |  | 2025-06-01 | 2026-02-19 | 0
2899 | 1.4 | 1.4.4.3.8 | C | Electronics SME support for FS3 activities (slot 1) | Not Started | 6 | 21d | 2025-11-15 | 2025-12-15 | [5 empty] | 119 |  | 2025-11-15 | 2025-12-15 | 0
2900 | 1.4 | 1.4.4.3.9 | C | Electronics SME support for FS3 activities (slot 2) | Not Started | 6 | 20d | 2025-12-18 | 2026-01-16 | [5 empty] | 97 |  | 2025-12-18 | 2026-01-16 | 0
2901 | 1.4 | 1.4.5 | P | Northern Test System | Started | 3 | 1363d | 2021-01-01 | 2026-04-06 |  | 25% |  |  |  | 41 |  | 2021-01-01 | 2026-04-06 | 0
2902 | 1.4 | 1.4.5.2 | P | NTS Cables | Should have Started | 4 | 257d | 2021-10-01 | 2022-09-26 |  | 0% |  |  |  | 952 |  | 2021-10-01 | 2022-09-26 | 0
2903 | 1.4 | 1.4.5.2.1 | C | Design of permanent installation scheme | Not Started | 5 | 4w | 2022-07-19 | 2022-08-15 | 2668 | 0% |  |  |  | 952 |  | 2022-07-19 | 2022-08-15 | 0
2904 | 1.4 | 1.4.5.2.2 | C | Facility construction | Not Started | 5 | 5w | 2022-08-16 | 2022-09-19 | 2903 | 0% |  |  |  | 952 |  | 2022-08-16 | 2022-09-19 | 0
2905 | 1.4 | 1.4.5.2.3 | C | Permanent mounting of NTS quads | Not Started | 5 | 1w | 2022-09-20 | 2022-09-26 | 2904 |  |  |  |  | 952 |  | 2022-09-20 | 2022-09-26 | 0
2906 | 1.4 | 1.4.5.2.4 | C | NTS cable permanent installation finished | Not Started | 5 | 0 | 2022-09-26 | 2022-09-26 | 2905 |  |  |  |  | 952 |  | 2022-09-26 | 2022-09-26 | 0
2907 | 1.4 | 1.4.5.2.5 | C | NTS cables support | Should have Started | 5 | 257d | 2021-10-01 | 2022-09-26 | [5 empty] | 952 |  | 2021-10-01 | 2022-09-26 | 0
2908 | 1.4 | 1.4.5.3 | P | NTS dark boxes | Started | 4 | 326d | 2021-01-01 | 2022-04-01 |  | 48% |  |  |  | 1078 |  | 2021-01-01 | 2022-04-01 | 0
2909 | 1.4 | 1.4.5.3.1 | C | Order materials | Complete | 5 | 21d | 2021-01-01 | 2021-01-29 |  | 100% |  |  |  | 1078 |  | 2021-01-01 | 2021-01-29 | 0
2910 | 1.4 | 1.4.5.3.2 | C | Construction | Started | 5 | 61w | 2021-02-01 | 2022-04-01 | 2909 | 65% |  |  |  | 1078 |  | 2021-02-01 | 2022-04-01 | 0
2911 | 1.4 | 1.4.5.3.3 | C | NTS dark boxes ready | Complete | 5 | 1d | 2021-04-15 | 2021-04-15 |  | 100% |  |  |  | 1329 |  | 2021-04-15 | 2021-04-15 | 0
2912 | 1.4 | 1.4.5.3.4 | C | NTS dark boxes support | Should have Started | 5 | 131d | 2021-10-01 | 2022-04-01 | [5 empty] | 1078 |  | 2021-10-01 | 2022-04-01 | 0
2913 | 1.4 | 1.4.5.4 | P | NTS Operations | Started | 4 | 1363d | 2021-01-01 | 2026-04-06 |  | 24% |  |  |  | 41 |  | 2021-01-01 | 2026-04-06 | 0
2914 | 1.4 | 1.4.5.4.1 | C | Commissioning | Complete | 5 | 107d | 2021-01-01 | 2021-05-31 |  | 100% |  |  |  | 41 |  | 2021-01-01 | 2021-05-31 | 0
2915 | 1.4 | 1.4.5.4.2 | C | NTS Fully Operational | Complete | 5 | 1d | 2021-06-01 | 2021-06-01 | 2914 | 100% |  |  |  | 41 |  | 2021-06-01 | 2021-06-01 | 0
2916 | 1.4 | 1.4.5.4.3 | C | NTS Operations | Started | 5 | 1255d | 2021-06-02 | 2026-04-06 | 2915 | 17% |  |  |  | 41 |  | 2021-06-02 | 2026-04-06 | 0
2917 | 1.4 | 1.4.6 | C | CPT Management (PY4 onward) | Should have Started | 3 | 1168d | 2021-10-01 | 2026-04-06 | [5 empty] | 41 |  | 2021-10-01 | 2026-04-06 | 0
2918 | 1.5 | 1.5 | P | Characterization and Calibration System | Started | 2 | 1561d | 2020-04-01 | 2026-04-07 |  | 4% |  |  |  | 40 |  | 2020-04-01 | 2026-04-07 | 0
2919 | 1.5 | 1.5.2 | P | Calibration Assemblies | Started | 3 | 1386d | 2020-04-01 | 2025-08-01 |  | 9% |  |  |  | 215 |  | 2020-04-01 | 2025-08-01 | 0
2920 | 1.5 | 1.5.2.1 | P | On-board LED Flashers | Not Started | 4 | 236d | 2022-04-25 | 2023-03-20 | [5 empty] | 827 |  | 2022-04-25 | 2023-03-20 | 0
2921 | 1.5 | 1.5.2.1.2 | P | mDOM Flashers | Not Started | 5 | 236d | 2022-04-25 | 2023-03-20 | [5 empty] | 827 |  | 2022-04-25 | 2023-03-20 | 0
2922 | 1.5 | 1.5.2.1.2.0 | C | mDOM Flasher DESY Batch 0 Production | Not Started | 6 | 11d | 2022-04-25 | 2022-05-09 | 2309FS +20d |  |  |  |  | 827 |  | 2022-04-25 | 2022-05-09 | 0
2923 | 1.5 | 1.5.2.1.2.1 | C | mDOM Flasher DESY Batch 1 Production | Not Started | 6 | 15d | 2022-05-10 | 2022-05-30 | 2922 |  |  |  |  | 827 |  | 2022-05-10 | 2022-05-30 | 0
2924 | 1.5 | 1.5.2.1.2.2 | C | mDOM Flasher DESY Batch 2 Production | Not Started | 6 | 15d | 2022-05-31 | 2022-06-20 | 2923 |  |  |  |  | 827 |  | 2022-05-31 | 2022-06-20 | 0
2925 | 1.5 | 1.5.2.1.2.3 | C | mDOM Flasher DESY Batch 3 Production | Not Started | 6 | 15d | 2022-06-21 | 2022-07-11 | 2924 |  |  |  |  | 827 |  | 2022-06-21 | 2022-07-11 | 0
2926 | 1.5 | 1.5.2.1.2.4 | C | mDOM Flasher DESY Batch 4 Production | Not Started | 6 | 15d | 2022-07-12 | 2022-08-01 | 2925 |  |  |  |  | 827 |  | 2022-07-12 | 2022-08-01 | 0
2927 | 1.5 | 1.5.2.1.2.5 | C | mDOM Flasher DESY Batch 5 Production | Not Started | 6 | 15d | 2022-08-02 | 2022-08-22 | 2926 |  |  |  |  | 827 |  | 2022-08-02 | 2022-08-22 | 0
2928 | 1.5 | 1.5.2.1.2.6 | C | mDOM Flasher DESY Batch 6 Production | Not Started | 6 | 15d | 2022-08-23 | 2022-09-12 | 2927 |  |  |  |  | 827 |  | 2022-08-23 | 2022-09-12 | 0
2929 | 1.5 | 1.5.2.1.2.7 | C | mDOM Flasher DESY Batch 7 Production | Not Started | 6 | 15d | 2022-09-13 | 2022-10-03 | 2928 |  |  |  |  | 827 |  | 2022-09-13 | 2022-10-03 | 0
2930 | 1.5 | 1.5.2.1.2.8 | C | mDOM Flasher DESY Batch 8 Production | Not Started | 6 | 15d | 2022-10-04 | 2022-10-24 | 2929 |  |  |  |  | 827 |  | 2022-10-04 | 2022-10-24 | 0
2931 | 1.5 | 1.5.2.2.1.4 | C | mDOM Flasher DESY production complete | Not Started | 6 | 0 | 2022-10-24 | 2022-10-24 | 2930 |  |  |  |  | 932 |  | 2022-10-24 | 2022-10-24 | 0
2932 | 1.5 | 1.5.2.1.2.9 | C | mDOM Flasher MSU Batch 1 Production | Not Started | 6 | 15d | 2022-10-25 | 2022-11-14 | 2930 |  |  |  |  | 827 |  | 2022-10-25 | 2022-11-14 | 0
2933 | 1.5 | 1.5.2.1.2.10 | C | mDOM Flasher MSU Batch 2 Production | Not Started | 6 | 15d | 2022-11-15 | 2022-12-05 | 2932 |  |  |  |  | 827 |  | 2022-11-15 | 2022-12-05 | 0
2934 | 1.5 | 1.5.2.1.2.11 | C | mDOM Flasher MSU Batch 3 Production | Not Started | 6 | 15d | 2022-12-06 | 2022-12-26 | 2933 |  |  |  |  | 827 |  | 2022-12-06 | 2022-12-26 | 0
2935 | 1.5 | 1.5.2.1.2.12 | C | mDOM Flasher MSU Batch 4 Production | Not Started | 6 | 15d | 2022-12-27 | 2023-01-16 | 2934 |  |  |  |  | 827 |  | 2022-12-27 | 2023-01-16 | 0
2936 | 1.5 | 1.5.2.1.2.13 | C | mDOM Flasher MSU Batch 5 Production | Not Started | 6 | 15d | 2023-01-17 | 2023-02-06 | 2935 |  |  |  |  | 827 |  | 2023-01-17 | 2023-02-06 | 0
2937 | 1.5 | 1.5.2.1.2.14 | C | mDOM Flasher MSU Batch 6 Production | Not Started | 6 | 15d | 2023-02-07 | 2023-02-27 | 2936 |  |  |  |  | 827 |  | 2023-02-07 | 2023-02-27 | 0
2938 | 1.5 | 1.5.2.1.2.15 | C | mDOM Flasher MSU Batch 7 Production | Not Started | 6 | 15d | 2023-02-28 | 2023-03-20 | 2937 |  |  |  |  | 827 |  | 2023-02-28 | 2023-03-20 | 0
2939 | 1.5 | 1.5.2.2.1.4 | C | mDOM Flasher MSU production complete | Not Started | 6 | 0 | 2023-03-20 | 2023-03-20 | 2938 |  |  |  |  | 827 |  | 2023-03-20 | 2023-03-20 | 0
2940 | 1.5 | 1.5.2.2 | P | Standalone Light Sources | Not Started | 4 | 844d | 2022-05-01 | 2025-08-01 | [5 empty] | 215 |  | 2022-05-01 | 2025-08-01 | 0
2941 | 1.5 | 1.5.2.2.1 | P | POCAM | Not Started | 5 | 844d | 2022-05-01 | 2025-08-01 | [5 empty] | 215 |  | 2022-05-01 | 2025-08-01 | 0
2942 | 1.5 | 1.5.2.2.1.1 | C | POCAM DVT Modules Built | Not Started | 6 | 24d | 2022-05-01 | 2022-06-01 | [5 empty] | -27 |  | 2022-05-01 | 2022-06-01 | 0
2943 | 1.5 | 1.5.2.2.1.2 | C | POCAM Design verification testing | Not Started | 6 | 44d | 2022-06-02 | 2022-08-02 | 2942 |  |  |  |  | -27 |  | 2022-06-02 | 2022-08-02 | 0
2944 | 1.5 | 1.5.2.2.1.3 | C | Update POCAM design | Not Started | 6 | 24d | 2022-08-03 | 2022-09-05 | 2943 |  |  |  |  | -27 |  | 2022-08-03 | 2022-09-05 | 0
2945 | 1.5 | 1.5.2.2.1.4 | C | POCAM Design complete, Final Design Review | Not Started | 6 | 0 | 2022-09-05 | 2022-09-05 | 2944 |  |  |  |  | -27 |  | 2022-09-05 | 2022-09-05 | 0
2946 | 1.5 | 1.5.2.2.1.5 | C | POCAM Batch 1 production (30) | Not Started | 6 | 67d | 2023-01-10 | 2023-04-12 | 2945FS +90d |  |  |  |  | 721 |  | 2023-01-10 | 2023-04-12 | 0
2947 | 1.5 | 1.5.2.2.1.6 | C | POCAM Batch 1 calibration | Not Started | 6 | 66d | 2023-02-07 | 2023-05-09 | 2946SS +20d |  |  |  |  | 768 |  | 2023-02-07 | 2023-05-09 | 0
2948 | 1.5 | 1.5.2.2.1.7 | C | POCAM Batch 1 FAT testing | Not Started | 6 | 23d | 2023-05-10 | 2023-06-09 | 2947 |  |  |  |  | 768 |  | 2023-05-10 | 2023-06-09 | 0
2949 | 1.5 | 1.5.2.2.1.8 | C | POCAM ready to ship | Not Started | 6 | 0 | 2023-06-09 | 2023-06-09 | 2948 |  |  |  |  | 768 |  | 2023-06-09 | 2023-06-09 | 0
2950 | 1.5 | 1.5.2.2.1.9 | C | Deliver 1 POCAM module to NTS | Not Started | 6 | 0 | 2023-12-15 | 2023-12-15 | [5 empty] | 635 |  | 2023-12-15 | 2023-12-15 | 0
2951 | 1.5 | 1.5.2.2.1.10 | C | Deliver Str. 87-88 POCAM Modules to CHC (4) | Not Started | 6 | 0 | 2024-08-01 | 2024-08-01 |  |  | Assume shipping by air from Europe, shipping should occur a few weeks before to make delivery date |  |  | 473 |  | 2024-08-01 | 2024-08-01 | 0
2952 | 1.5 | 1.5.2.2.1.11 | C | Deliver Str. 89-93 POCAM Modules to CHC (17) | Not Started | 6 | 0 | 2025-08-01 | 2025-08-01 | [5 empty] | 215 |  | 2025-08-01 | 2025-08-01 | 0
2953 | 1.5 | 1.5.2.2.2 | P | Pencil Beam ( at UW, Chris Wendt ) | Not Started | 5 | 733d | 2022-10-03 | 2025-08-01 | [5 empty] | 215 |  | 2022-10-03 | 2025-08-01 | 0
2954 | 1.5 | 1.5.2.2.2.0 | C | Pencil Beam Engineering | Not Started | 6 | 476d | 2022-10-07 | 2024-08-07 | 39, 2966FF |  |  |  |  | 468 |  | 2022-10-07 | 2024-08-07 | 0
2955 | 1.5 | 1.5.2.2.2.1 | C | Pencil Beam DVT Module(s) built | Not Started | 6 | 65d | 2022-10-03 | 2022-12-30 | 39 |  |  |  |  | -27 |  | 2022-10-03 | 2022-12-30 | 0
2956 | 1.5 | 1.5.2.2.2.2 | C | Pencil Beam Design verification testing | Not Started | 6 | 78d | 2022-11-14 | 2023-03-01 | 2955SS +30d |  |  |  |  | -27 |  | 2022-11-14 | 2023-03-01 | 0
2957 | 1.5 | 1.5.2.2.2.3 | C | Update Pencil Beam design | Not Started | 6 | 65d | 2022-12-01 | 2023-03-01 | 2956FF |  |  |  |  | -27 |  | 2022-12-01 | 2023-03-01 | 0
2958 | 1.5 | 1.5.2.2.2.4 | C | Pencil Beam Final Design Review | Not Started | 6 | 0 | 2023-03-01 | 2023-03-01 | 2957 |  |  |  |  | -27 |  | 2023-03-01 | 2023-03-01 | 0
2959 | 1.5 | 1.5.2.2.2.5 | C | Pencil Beam Batch 1 production | Not Started | 6 | 43d | 2023-03-02 | 2023-05-01 | 2958 |  |  |  |  | -8 |  | 2023-03-02 | 2023-05-01 | 0
2960 | 1.5 | 1.5.2.2.2.6 | C | Pencil Beam Batch 1 calibration | Not Started | 6 | 67d | 2023-05-02 | 2023-08-02 | 2959 |  |  |  |  | 730 |  | 2023-05-02 | 2023-08-02 | 0
2961 | 1.5 | 1.5.2.2.2.7 | C | Pencil Beam Batch 1 FAT testing | Not Started | 6 | 67d | 2023-05-02 | 2023-08-02 | 2959 |  |  |  |  | -8 |  | 2023-05-02 | 2023-08-02 | 0
2962 | 1.5 | 1.5.2.2.2.8 | C | Pencil Beam Batch 2 production | Not Started | 6 | 108d | 2023-08-03 | 2024-01-04 | 2961 |  |  |  |  | -8 |  | 2023-08-03 | 2024-01-04 | 0
2963 | 1.5 | 1.5.2.2.2.9 | C | Pencil Beam Batch 2 calibration | Not Started | 6 | 154d | 2024-01-05 | 2024-08-07 | 2962 |  | PDR delayed due to lockdowns delaying prototype development |  |  | -8 |  | 2024-01-05 | 2024-08-07 | 0
2964 | 1.5 | 1.5.2.2.2.10 | C | Pencil Beam Batch 2 FAT testing | Not Started | 6 | 154d | 2024-01-05 | 2024-08-07 | 2962 |  | Prototypes delayed due to COVID 19 lockdowns |  |  | -8 |  | 2024-01-05 | 2024-08-07 | 0
2965 | 1.5 | 1.5.2.2.2.11 | C | PencilBeam Batch 1 Ready to Ship | Not Started | 6 | 0 | 2023-08-02 | 2023-08-02 | 2961 |  |  |  |  | 730 |  | 2023-08-02 | 2023-08-02 | 0
2966 | 1.5 | 1.5.2.2.2.12 | C | PencilBeam Batch 2 Ready to Ship | Not Started | 6 | 0 | 2024-08-07 | 2024-08-07 | 2964, 2963 |  |  |  |  | -8 |  | 2024-08-07 | 2024-08-07 | 0
2967 | 1.5 | 1.5.2.2.2.13 | C | Deliver 1 Pencil Beam module to NTS | Not Started | 6 | 0 | 2023-12-15 | 2023-12-15 | [5 empty] | 635 |  | 2023-12-15 | 2023-12-15 | 0
2968 | 1.5 | 1.5.2.2.2.14 | C | Deliver Str. 87-88 Pencil Beam Modules to PTH (4) | Not Started | 6 | 0 | 2024-08-01 | 2024-08-01 | [5 empty] | 473 |  | 2024-08-01 | 2024-08-01 | 0
2969 | 1.5 | 1.5.2.2.2.15 | C | Deliver Str. 89-93 Pencil Beam Modules to PTH (8) | Not Started | 6 | 0 | 2025-08-01 | 2025-08-01 | [5 empty] | 215 |  | 2025-08-01 | 2025-08-01 | 0
2970 | 1.5 | 1.5.2.3 | P | Camera and Light Detection | Started | 4 | 1386d | 2020-04-01 | 2025-08-01 |  | 20% |  |  |  | 215 |  | 2020-04-01 | 2025-08-01 | 0
2971 | 1.5 | 1.5.2.3.1 | P | Cameras in Photosensors | Started | 5 | 735d | 2020-04-01 | 2023-01-24 |  | 39% |  |  |  | 866 |  | 2020-04-01 | 2023-01-24 | 0
2972 | 1.5 | 1.5.2.3.1.2 | P | mDOM Cameras | Started | 6 | 735d | 2020-04-01 | 2023-01-24 |  | 39% |  |  |  | 866 |  | 2020-04-01 | 2023-01-24 | 0
2973 | 1.5 | 1.5.2.3.1.2.1 | C | Camera mDOM batch 1-3 production | Complete | 7 | 69d | 2020-04-01 | 2020-07-06 |  | 100% |  |  |  | 1471 |  | 2020-04-01 | 2020-07-06 | 0
2974 | 1.5 | 1.5.2.3.1.2.2 | C | Camera mDOM batch 4-8 DESY / 1-7 MSU production | Complete | 7 | 65d | 2021-04-01 | 2021-06-30 |  | 100% |  |  |  | 1225 |  | 2021-04-01 | 2021-06-30 | 0
2975 | 1.5 | 1.5.2.3.1.2.3 | C | Camera mDOM DESY batch 1 Calibration (CAT) | Complete | 7 | 15d | 2020-11-30 | 2020-12-18 | 2973FS +104d | 100% |  |  |  | 1367 |  | 2020-11-30 | 2020-12-18 | 0
2976 | 1.5 | 1.5.2.3.1.2.4 | C | Delivery of Camera mDOM batch 1 to DESY | Complete | 7 | 23d | 2020-12-21 | 2021-01-20 | 2975 | 100% |  |  |  | 1367 |  | 2020-12-21 | 2021-01-20 | 0
2977 | 1.5 | 1.5.2.3.1.2.5 | C | Camera mDOM DESY batch 2 Calibration (CAT) | Complete | 7 | 10d | 2021-01-04 | 2021-01-15 |  | 100% |  |  |  | 1370 |  | 2021-01-04 | 2021-01-15 | 0
2978 | 1.5 | 1.5.2.3.1.2.6 | C | Delivery of Camera mDOM batch 2 to DESY | Complete | 7 | 23d | 2021-01-18 | 2021-02-17 | 2977, 2976SS | 100% |  |  |  | 1370 |  | 2021-01-18 | 2021-02-17 | 0
2979 | 1.5 | 1.5.2.3.1.2.7 | C | Camera mDOM DESY batch 3 Calibration (CAT) | Complete | 7 | 10d | 2021-01-18 | 2021-01-29 |  | 100% |  |  |  | 1362 |  | 2021-01-18 | 2021-01-29 | 0
2980 | 1.5 | 1.5.2.3.1.2.8 | C | Delivery of Camera mDOM batch 3 to DESY | Complete | 7 | 21d | 2021-02-01 | 2021-03-01 | 2979 | 100% |  |  |  | 1362 |  | 2021-02-01 | 2021-03-01 | 0
2981 | 1.5 | 1.5.2.3.1.2.9 | C | Camera mDOM DESY batch 4 Calibration (CAT) | Complete | 7 | 10d | 2021-06-10 | 2021-06-23 | 2974FS -15d | 100% |  |  |  | 1240 |  | 2021-06-10 | 2021-06-23 | 0
2982 | 1.5 | 1.5.2.3.1.2.10 | C | Delivery of Camera mDOM batch 4 to DESY | Complete | 7 | 15d | 2021-06-24 | 2021-07-14 | 2981 | 100% |  |  |  | 1240 |  | 2021-06-24 | 2021-07-14 | 0
2983 | 1.5 | 1.5.2.3.1.2.11 | C | Camera mDOM DESY batch 5 Calibration (CAT) | Complete | 7 | 10d | 2021-07-15 | 2021-07-28 | 2982 | 100% |  |  |  | 1240 |  | 2021-07-15 | 2021-07-28 | 0
2984 | 1.5 | 1.5.2.3.1.2.12 | C | Delivery of Camera mDOM batch 5 to DESY | Complete | 7 | 15d | 2021-07-15 | 2021-08-04 | 2983SS | 100% |  |  |  | 1250 |  | 2021-07-15 | 2021-08-04 | 0
2985 | 1.5 | 1.5.2.3.1.2.13 | C | Camera mDOM DESY batch 6 Calibration (CAT) | Not Started | 7 | 20d | 2022-02-01 | 2022-02-28 | [5 empty] | 1056 |  | 2022-02-01 | 2022-02-28 | 0
2986 | 1.5 | 1.5.2.3.1.2.14 | C | Delivery of Camera mDOM batch 6 to DESY | Not Started | 7 | 24d | 2022-03-01 | 2022-04-01 | 2985 |  |  |  |  | 1078 |  | 2022-03-01 | 2022-04-01 | 0
2987 | 1.5 | 1.5.2.3.1.2.15 | C | Camera mDOM DESY batch 7 Calibration (CAT) | Not Started | 7 | 24d | 2022-03-01 | 2022-04-01 | 2985 |  |  |  |  | 1056 |  | 2022-03-01 | 2022-04-01 | 0
2988 | 1.5 | 1.5.2.3.1.2.16 | C | Delivery of Camera mDOM batch 7 to DESY | Not Started | 7 | 22d | 2022-04-04 | 2022-05-03 | 2987 |  |  |  |  | 1056 |  | 2022-04-04 | 2022-05-03 | 0
2989 | 1.5 | 1.5.2.3.1.2.17 | C | Camera mDOM DESY batch 8 Calibration (CAT) | Not Started | 7 | 10d | 2022-03-31 | 2022-04-13 | [5 empty] | 866 |  | 2022-03-31 | 2022-04-13 | 0
2990 | 1.5 | 1.5.2.3.1.2.18 | C | Delivery of Camera mDOM batch 8 to DESY | Not Started | 7 | 25d | 2022-04-14 | 2022-05-18 | 2989 |  |  |  |  | 1045 |  | 2022-04-14 | 2022-05-18 | 0
2991 | 1.5 | 1.5.2.3.1.2.19 | C | Delivery of Camera mDOM to DESY Completed | Not Started | 7 | 0 | 2022-05-18 | 2022-05-18 | 2990, 2988, 2986, 2984, 2980 |  |  |  |  | 1045 |  | 2022-05-18 | 2022-05-18 | 0
2992 | 1.5 | 1.5.2.3.1.2.20 | C | Camera mDOM MSU batch 1 Calibration (CAT) | Not Started | 7 | 22d | 2022-04-14 | 2022-05-13 | 2989 |  |  |  |  | 866 |  | 2022-04-14 | 2022-05-13 | 0
2993 | 1.5 | 1.5.2.3.1.2.21 | C | Delivery of Camera mDOM batch 1 to MSU | Not Started | 7 | 23d | 2022-05-16 | 2022-06-15 | 2992 |  |  |  |  | 866 |  | 2022-05-16 | 2022-06-15 | 0
2994 | 1.5 | 1.5.2.3.1.2.22 | C | Camera mDOM MSU batch 2 Calibration (CAT) | Not Started | 7 | 23d | 2022-06-16 | 2022-07-18 | 2993 |  |  |  |  | 866 |  | 2022-06-16 | 2022-07-18 | 0
2995 | 1.5 | 1.5.2.3.1.2.23 | C | Delivery of Camera mDOM batch 2 to MSU | Not Started | 7 | 23d | 2022-07-19 | 2022-08-18 | 2994 |  |  |  |  | 979 |  | 2022-07-19 | 2022-08-18 | 0
2996 | 1.5 | 1.5.2.3.1.2.24 | C | Camera mDOM MSU batch 3 Calibration (CAT) | Not Started | 7 | 22d | 2022-07-19 | 2022-08-17 | 2994 |  |  |  |  | 866 |  | 2022-07-19 | 2022-08-17 | 0
2997 | 1.5 | 1.5.2.3.1.2.25 | C | Delivery of Camera mDOM batch 3 to MSU | Not Started | 7 | 22d | 2022-08-18 | 2022-09-16 | 2996 |  |  |  |  | 866 |  | 2022-08-18 | 2022-09-16 | 0
2998 | 1.5 | 1.5.2.3.1.2.26 | C | Camera mDOM MSU batch 4 Calibration (CAT) | Not Started | 7 | 21d | 2022-08-18 | 2022-09-15 | 2996 |  |  |  |  | 959 |  | 2022-08-18 | 2022-09-15 | 0
2999 | 1.5 | 1.5.2.3.1.2.27 | C | Delivery of Camera mDOM batch 4 to MSU | Not Started | 7 | 24d | 2022-09-19 | 2022-10-20 | 2997 |  |  |  |  | 866 |  | 2022-09-19 | 2022-10-20 | 0
3000 | 1.5 | 1.5.2.3.1.2.28 | C | Camera mDOM MSU batch 5 Calibration (CAT) | Not Started | 7 | 23d | 2022-09-19 | 2022-10-19 | 2997 |  |  |  |  | 935 |  | 2022-09-19 | 2022-10-19 | 0
3001 | 1.5 | 1.5.2.3.1.2.29 | C | Delivery of Camera mDOM batch 5 to MSU | Not Started | 7 | 23d | 2022-10-21 | 2022-11-22 | 2999 |  |  |  |  | 866 |  | 2022-10-21 | 2022-11-22 | 0
3002 | 1.5 | 1.5.2.3.1.2.30 | C | Camera mDOM MSU batch 6 Calibration (CAT) | Not Started | 7 | 22d | 2022-10-21 | 2022-11-21 | 2999 |  |  |  |  | 912 |  | 2022-10-21 | 2022-11-21 | 0
3003 | 1.5 | 1.5.2.3.1.2.31 | C | Delivery of Camera mDOM batch 6 to MSU | Not Started | 7 | 22d | 2022-11-23 | 2022-12-22 | 3001 |  |  |  |  | 866 |  | 2022-11-23 | 2022-12-22 | 0
3004 | 1.5 | 1.5.2.3.1.2.32 | C | Camera mDOM MSU batch 7 Calibration (CAT) | Not Started | 7 | 22d | 2022-11-23 | 2022-12-22 | 3001 |  |  |  |  | 889 |  | 2022-11-23 | 2022-12-22 | 0
3005 | 1.5 | 1.5.2.3.1.2.33 | C | Delivery of Camera mDOM batch 7 to MSU | Not Started | 7 | 23d | 2022-12-23 | 2023-01-24 | 3003 |  |  |  |  | 866 |  | 2022-12-23 | 2023-01-24 | 0
3006 | 1.5 | 1.5.2.3.1.2.34 | C | Delivery of Camera mDOM to MSU Completed | Not Started | 7 | 0 | 2023-01-24 | 2023-01-24 | 3005, 3003, 3001, 2999, 2997, 2995, 2993 |  |  |  |  | 866 |  | 2023-01-24 | 2023-01-24 | 0
3007 | 1.5 | 1.5.2.3.2 | P | Sweden Camera 2.0 | Not Started | 5 | 733d | 2022-10-03 | 2025-08-01 | [5 empty] | 215 |  | 2022-10-03 | 2025-08-01 | 0
3008 | 1.5 | 1.5.2.3.2.3 | C | Sweden Camera Final Design Review | Not Started | 6 | 0 | 2022-10-03 | 2022-10-03 | [5 empty] | -27 |  | 2022-10-03 | 2022-10-03 | 0
3009 | 1.5 | 1.5.2.3.2.4 | C | Sweden Camera Production | Not Started | 6 | 240d | 2022-10-03 | 2023-09-01 | 3008 |  |  |  |  | 708 |  | 2022-10-03 | 2023-09-01 | 0
3010 | 1.5 | 1.5.2.3.2.5 | C | Sweden Camera Ready to Ship | Not Started | 6 | 0 | 2023-09-01 | 2023-09-01 | 3009 |  |  |  |  | 708 |  | 2023-09-01 | 2023-09-01 | 0
3011 | 1.5 | 1.5.2.3.2.6 | C | Delivery of 1 Sweden Camera Module to NTS | Not Started | 6 | 0 | 2023-10-02 | 2023-10-02 | [5 empty] | 688 |  | 2023-10-02 | 2023-10-02 | 0
3012 | 1.5 | 1.5.2.3.2.7 | C | Delivery of Str. 87-88 Sweden Camera Modules to CHC (2) | Not Started | 6 | 0 | 2024-08-01 | 2024-08-01 |  |  | Assume shipping by air from Europe, shipping should occur a few weeks before to make delivery date |  |  | 473 |  | 2024-08-01 | 2024-08-01 | 0
3013 | 1.5 | 1.5.2.3.2.8 | C | Delivery of Str. 89-93 Sweden Camera Modules to CHC (3) | Not Started | 6 | 0 | 2025-08-01 | 2025-08-01 | [5 empty] | 215 |  | 2025-08-01 | 2025-08-01 | 0
3014 | 1.5 | 1.5.2.4 | P | Acoustic Sensors | Not Started | 4 | 734d | 2022-09-30 | 2025-08-01 | [5 empty] | 215 |  | 2022-09-30 | 2025-08-01 | 0
3015 | 1.5 | 1.5.2.4.4 | C | Acoustic Update design | Not Started | 5 | 0 | 2022-09-30 | 2022-09-30 | [5 empty] | 683 |  | 2022-09-30 | 2022-09-30 | 0
3016 | 1.5 | 1.5.2.4.5 | C | Acoustic Electronic Update and test | Not Started | 5 | 45d | 2022-09-30 | 2022-12-01 | 3015 |  |  |  |  | 683 |  | 2022-09-30 | 2022-12-01 | 0
3017 | 1.5 | 1.5.2.4.6 | C | Acoustic Design complete, Final Design Review | Not Started | 5 | 0 | 2022-12-01 | 2022-12-01 | 3016 |  |  |  |  | 683 |  | 2022-12-01 | 2022-12-01 | 0
3018 | 1.5 | 1.5.2.4.7 | C | Acoustic Batch 1 production | Not Started | 5 | 66d | 2022-12-02 | 2023-03-03 | 3017 |  |  |  |  | 683 |  | 2022-12-02 | 2023-03-03 | 0
3019 | 1.5 | 1.5.2.4.8 | C | Acoustic Batch 1 calibration | Not Started | 5 | 88d | 2023-01-13 | 2023-05-16 | 3018SS +30d |  |  |  |  | 719 |  | 2023-01-13 | 2023-05-16 | 0
3020 | 1.5 | 1.5.2.4.9 | C | Acoustic Batch 1 FAT testing | Not Started | 5 | 67d | 2023-02-24 | 2023-05-29 | 3019SS +30d |  |  |  |  | 777 |  | 2023-02-24 | 2023-05-29 | 0
3021 | 1.5 | 1.5.2.4.10 | C | Acoustic Modules Ready to Ship | Not Started | 5 | 0 | 2023-05-29 | 2023-05-29 | 3020 |  |  |  |  | 777 |  | 2023-05-29 | 2023-05-29 | 0
3022 | 1.5 | 1.5.2.4.11 | C | Acoustic deliver one module to Northern Test System | Not Started | 5 | 0 | 2023-06-27 | 2023-06-27 | 3021FS +21d |  |  |  |  | 756 |  | 2023-06-27 | 2023-06-27 | 0
3023 | 1.5 | 1.5.2.4.12 | C | Delivery of Str. 87-88 Acoustic modules to CHC (4) | Not Started | 5 | 0 | 2024-08-01 | 2024-08-01 |  |  | Assume shipping by air from Europe, shipping should occur a few weeks before to make delivery date |  |  | 473 |  | 2024-08-01 | 2024-08-01 | 0
3024 | 1.5 | 1.5.2.4.13 | C | Delivery of Str. 89-93 Acoustic modules to CHC (8) | Not Started | 5 | 0 | 2025-08-01 | 2025-08-01 | [5 empty] | 215 |  | 2025-08-01 | 2025-08-01 | 0
3025 | 1.5 | 1.5.3 | P | Array Calibration | Not Started | 3 | 908d | 2022-10-03 | 2026-04-07 |  | 0% |  |  |  | 40 |  | 2022-10-03 | 2026-04-07 | 0
3026 | 1.5 | 1.5.3.1 | P | Calibration Benchmarks | Not Started | 4 | 520d | 2024-04-02 | 2026-04-07 |  | 0% |  |  |  | 40 |  | 2024-04-02 | 2026-04-07 | 0
3027 | 1.5 | 1.5.3.1.1 | C | Simulation Studies | Not Started | 5 | 520d | 2024-04-02 | 2026-04-07 | 37FF | 0% |  |  |  | -480 |  | 2024-04-02 | 2026-04-07 | 0
3028 | 1.5 | 1.5.3.1.2 | C | Plan | Not Started | 5 | 175d | 2024-04-02 | 2024-12-03 | 3027SS | 0% |  |  |  | 40 |  | 2024-04-02 | 2024-12-03 | 0
3029 | 1.5 | 1.5.3.1.3 | C | Software Development | Not Started | 5 | 175d | 2024-12-04 | 2025-08-07 | 3028 |  |  |  |  | 40 |  | 2024-12-04 | 2025-08-07 | 0
3030 | 1.5 | 1.5.3.1.4 | C | Execution | Not Started | 5 | 170d | 2025-08-08 | 2026-04-07 | 3029 |  |  |  |  | 40 |  | 2025-08-08 | 2026-04-07 | 0
3031 | 1.5 | 1.5.3.2 | P | Timing Calibration | Not Started | 4 | 908d | 2022-10-03 | 2026-04-07 |  | 0% |  |  |  | 40 |  | 2022-10-03 | 2026-04-07 | 0
3032 | 1.5 | 1.5.3.2.1 | C | Develop Flasher Plan w New Timing System | Not Started | 5 | 250d | 2022-10-03 | 2023-09-15 | 39 | 0% |  |  |  | 78 |  | 2022-10-03 | 2023-09-15 | 0
3033 | 1.5 | 1.5.3.2.2 | C | TEST Flasher in IceCube w New Timing System | Not Started | 5 | 100d | 2023-09-18 | 2024-02-07 | 3032 |  |  |  |  | 78 |  | 2023-09-18 | 2024-02-07 | 0
3034 | 1.5 | 1.5.3.2.3 | C | Development of Timing Calibration Plan | Not Started | 5 | 350d | 2022-10-03 | 2024-02-07 | 39 | 0% |  |  |  | 78 |  | 2022-10-03 | 2024-02-07 | 0
3035 | 1.5 | 1.5.3.2.4 | C | Create Database Structure for Timing Calibration Data | Not Started | 5 | 520d | 2024-04-02 | 2026-04-07 | 37FF, 3033, 3034 |  |  |  |  | 40 |  | 2024-04-02 | 2026-04-07 | 0
3036 | 1.5 | 1.5.3.2.5 | C | Analyze Timing Calibration Data from Deployed Modules | Not Started | 5 | 64d | 2025-12-23 | 2026-03-24 | 1922 |  |  |  |  | 50 |  | 2025-12-23 | 2026-03-24 | 0
3037 | 1.5 | 1.5.3.3 | P | Geometry Calibration | Not Started | 4 | 908d | 2022-10-03 | 2026-04-07 |  | 0% |  |  |  | 40 |  | 2022-10-03 | 2026-04-07 | 0
3038 | 1.5 | 1.5.3.3.1 | C | Develop Geometry Plan | Not Started | 5 | 350d | 2022-10-03 | 2024-02-07 | 39 | 0% |  |  |  | 78 |  | 2022-10-03 | 2024-02-07 | 0
3039 | 1.5 | 1.5.3.3.2 | C | Create Database Structure for Geometry Calibration Data | Not Started | 5 | 520d | 2024-04-02 | 2026-04-07 | 37FF, 3038 |  |  |  |  | 40 |  | 2024-04-02 | 2026-04-07 | 0
3040 | 1.5 | 1.5.3.3.3 | C | Analyze Geometry Calibration Data from Deployed Modules | Not Started | 5 | 64d | 2025-12-23 | 2026-03-24 | 1922 |  |  |  |  | 50 |  | 2025-12-23 | 2026-03-24 | 0
3041 | 1.5 | 1.5.3.3.4 | C | Delivery of Preliminary Timimg and Geometry Calibration | Not Started | 5 | 0 | 2026-03-24 | 2026-03-24 | 3040 |  |  |  |  | 50 |  | 2026-03-24 | 2026-03-24 | 0
3042 | 1.5 | 1.5.3.4 | P | Ice Properties Calibration | Not Started | 4 | 908d | 2022-10-03 | 2026-04-07 | [5 empty] | 40 |  | 2022-10-03 | 2026-04-07 | 0
3043 | 1.5 | 1.5.3.4.1 | C | Plan | Not Started | 5 | 350d | 2022-10-03 | 2024-02-07 | 39 |  |  |  |  | 78 |  | 2022-10-03 | 2024-02-07 | 0
3044 | 1.5 | 1.5.3.4.2 | C | Software Development | Not Started | 5 | 520d | 2024-04-02 | 2026-04-07 | 37FF, 3043 |  |  |  |  | 40 |  | 2024-04-02 | 2026-04-07 | 0
3045 | 1.5 | 1.5.3.4.3 | C | Execution of Array Calibration | Not Started | 5 | 64d | 2025-12-23 | 2026-03-24 | 1922 |  |  |  |  | 50 |  | 2025-12-23 | 2026-03-24 | 0
3046 | 1.5 | 1.5.3.4.4 | C | Preliminary Array Calibration Complete | Not Started | 5 | 0 | 2026-04-07 | 2026-04-07 | 3045, 3030 |  |  |  |  | 40 |  | 2026-04-07 | 2026-04-07 | 0
3047 | 1.5 | 1.5.3.5 | P | Pre-deployment Hole Measurement | Not Started | 4 | 425d | 2024-08-01 | 2026-03-26 | [5 empty] | 48 |  | 2024-08-01 | 2026-03-26 | 0
3048 | 1.5 | 1.5.3.5.1 | C | Testing of dust logger and IDP winch | Not Started | 5 | 22d | 2024-08-01 | 2024-08-30 | [5 empty] | 451 |  | 2024-08-01 | 2024-08-30 | 0
3049 | 1.5 | 1.5.3.5.2 | C | Dust Logger and IDP Winch - Ready to Ship | Not Started | 5 | 0 | 2024-08-30 | 2024-08-30 | 3048 |  |  |  |  | 451 |  | 2024-08-30 | 2024-08-30 | 0
3050 | 1.5 | 1.5.3.5.3 | C | Delivery of logger and winch to PTH | Not Started | 5 | 0 | 2025-09-01 | 2025-09-01 | [5 empty] | 194 |  | 2025-09-01 | 2025-09-01 | 0
3051 | 1.5 | 1.5.3.5.4 | C | Analyze Hole Log Data | Not Started | 5 | 54d | 2026-01-12 | 2026-03-26 | 2008 |  |  |  |  | 48 |  | 2026-01-12 | 2026-03-26 | 0
3052 | 1.5 | 1.5.3.5.5 | C | Preliminary Delivery of Dust Logger Data | Not Started | 5 | 0 | 2026-03-26 | 2026-03-26 | 3051 |  |  |  |  | 48 |  | 2026-03-26 | 2026-03-26 | 0
3053 | 1.5 | 1.5.4 | P | Calibration Management and Organization | Not Started | 3 | 907d | 2022-10-04 | 2026-04-07 | [5 empty] | 40 |  | 2022-10-04 | 2026-04-07 | 0
3054 | 1.5 | 1.5.4.1 | C | Calibration management | Not Started | 4 | 907d | 2022-10-04 | 2026-04-07 | 39, 3308FF |  |  |  |  | 40 |  | 2022-10-04 | 2026-04-07 | 0
3055 | 1.5 | 1.5.4.2 | C | Travel | Not Started | 4 | 907d | 2022-10-04 | 2026-04-07 | 39, 3308FF |  |  |  |  | 40 |  | 2022-10-04 | 2026-04-07 | 0
3056 | 1.6 | 1.6 | P | IceCube Data Systems Integration | Started | 2 | 2052d | 2018-06-01 | 2026-04-24 |  | 34% |  |  |  | 27 |  | 2018-06-01 | 2026-04-24 | 0
3057 | 1.6 | 1.6.0 | C | L2 Task Management | Started | 3 | 1434d | 2020-10-01 | 2026-04-13 |  | 14% |  |  |  | 36 |  | 2020-10-01 | 2026-04-13 | 0
3058 | 1.6 | 1.6.1 | P | Online Systems Software | Started | 3 | 2043d | 2018-06-01 | 2026-04-13 |  | 31% |  |  |  | 36 |  | 2018-06-01 | 2026-04-13 | 0
3059 | 1.6 | 1.6.1.0 | C | L3 Task Management | Started | 4 | 1434d | 2020-10-01 | 2026-04-13 |  | 17% |  |  |  | 36 |  | 2020-10-01 | 2026-04-13 | 0
3060 | 1.6 | 1.6.1.1 | P | DAQ Software | Started | 4 | 1921d | 2018-11-01 | 2026-03-25 |  | 31% |  |  |  | 49 |  | 2018-11-01 | 2026-03-25 | 0
3061 | 1.6 | 1.6.1.1.1 | P | Interface to OM Sensors | Started | 5 | 1872d | 2018-11-01 | 2026-01-15 |  | 47% |  |  |  | 98 |  | 2018-11-01 | 2026-01-15 | 0
3062 | 1.6 | 1.6.1.1.1.1 | C | DAQ-OM Interface Design | Complete | 6 | 146d | 2018-11-01 | 2019-05-23 |  | 100% |  |  |  | 592 |  | 2018-11-01 | 2019-05-23 | 0
3063 | 1.6 | 1.6.1.1.1.2 | C | DAQ-OM Interface Documented | Complete | 6 | 0 | 2019-05-23 | 2019-05-23 | 3062 | 100% |  |  |  | 592 |  | 2019-05-23 | 2019-05-23 | 0
3064 | 1.6 | 1.6.1.1.1.3 | C | Testing minimal DAQ software tools developed for DVT testing | Complete | 6 | 89d | 2019-05-24 | 2019-09-25 | 3063 | 100% |  |  |  | 592 |  | 2019-05-24 | 2019-09-25 | 0
3065 | 1.6 | 1.6.1.1.1.4 | P | Testing minimal DAQ ready for sensor DVT testing | Complete | 6 | 57d | 2019-08-15 | 2019-11-01 |  | 100% |  |  |  | 1708 |  | 2019-08-15 | 2019-11-01 | 0
3066 | 1.6 | 1.6.1.1.1.4.1 | C | Define DAQ interface to FieldHub | Complete | 7 | 57d | 2019-08-15 | 2019-11-01 |  | 100% |  |  |  | 565 |  | 2019-08-15 | 2019-11-01 | 0
3067 | 1.6 | 1.6.1.1.1.5 | C | Testing DAQ software implementation and testing for FATs | Complete | 6 | 131d | 2019-11-04 | 2020-05-04 | 3066, 3064 | 100% |  |  |  | 565 |  | 2019-11-04 | 2020-05-04 | 0
3068 | 1.6 | 1.6.1.1.1.6 | C | Testing DAQ software ready for FAT testing on DEgg | Complete | 6 | 0 | 2020-05-04 | 2020-05-04 | 3067 | 100% |  |  |  | 565 |  | 2020-05-04 | 2020-05-04 | 0
3069 | 1.6 | 1.6.1.1.1.7 | C | Extend DAQ testing software for all OM types (mDOM, pDOM) | Complete | 6 | 229d | 2020-05-05 | 2021-03-19 | 3068 | 100% |  |  |  | 565 |  | 2020-05-05 | 2021-03-19 | 0
3070 | 1.6 | 1.6.1.1.1.8 | C | Support DAQ installation for all sensor testing | Started | 6 | 783d | 2020-09-30 | 2023-09-29 | 3069SS +106d | 62% | new end date for mDOM FAT |  |  | 688 |  | 2020-09-30 | 2023-09-29 | 0
3071 | 1.6 | 1.6.1.1.1.9 | C | Placeholder | Not Started | 6 | 66d | 2022-04-01 | 2022-07-01 |  | 0% |  |  |  | -127 |  | 2022-04-01 | 2022-07-01 | 0
3072 | 1.6 | 1.6.1.1.1.9.1 | C | Prototype and evalulate Upgrade DAQ components within existing IceCube DAQ architecture | Not Started | 6 | 227d | 2022-07-04 | 2023-05-16 | 3071 | 0% | EG. Trigger system rate issues ID'd early - |  |  | -127 |  | 2022-07-04 | 2023-05-16 | 0
3073 | 1.6 | 1.6.1.1.1.10 | C | Review DAQ Operation plans for new modules | Not Started | 6 | 0 | 2023-05-16 | 2023-05-16 | 3072 | 0% | review - major milestone - moved to May 2023 to better fit M&O yearly pole plan |  |  | -34 |  | 2023-05-16 | 2023-05-16 | 0
3074 | 1.6 | 1.6.1.1.1.11 | C | DAQ DataCollector component interface development for Upgrade OM sensors | Not Started | 6 | 160d | 2023-05-17 | 2023-12-28 | 3073 | 0% |  |  |  | -34 |  | 2023-05-17 | 2023-12-28 | 0
3075 | 1.6 | 1.6.1.1.1.11.1 | C | DAQ DataCollector component coding and testing for Upgrade OM sensors | Not Started | 6 | 160d | 2023-12-29 | 2024-08-09 | 3074 | 0% |  |  |  | -34 |  | 2023-12-29 | 2024-08-09 | 0
3076 | 1.6 | 1.6.1.1.1.11.2 | C | IceCube DAQ systems adapted for Upgrade DataCollector intergration | Not Started | 6 | 160d | 2024-08-12 | 2025-03-26 | 3075 | 0% |  |  |  | -34 |  | 2024-08-12 | 2025-03-26 | 0
3077 | 1.6 | 1.6.1.1.1.11.3 | C | IceCube DAQ system level testing at SPTS and NTS | Not Started | 6 | 188d | 2025-03-27 | 2025-12-16 | 3076 | 0% |  |  |  | -34 |  | 2025-03-27 | 2025-12-16 | 0
3078 | 1.6 | 1.6.1.1.1.12 | C | DAQ software ready for deployment including support for all new OMs | Not Started | 6 | 0 | 2025-12-16 | 2025-12-16 | 3077 | 0% |  |  |  | 55 |  | 2025-12-16 | 2025-12-16 | 0
3079 | 1.6 | 1.6.1.1.1.13 | C | DAQ software deployment at SPS | Not Started | 6 | 20d | 2025-12-17 | 2026-01-15 | 3078 | 0% |  |  |  | 55 |  | 2025-12-17 | 2026-01-15 | 0
3080 | 1.6 | 1.6.1.1.2 | P | Interface to Stand Alone calibration devices | Started | 5 | 1400d | 2020-11-01 | 2026-03-25 |  | 9% |  |  |  | 49 |  | 2020-11-01 | 2026-03-25 | 0
3081 | 1.6 | 1.6.1.1.2.1 | C | DAQ-Calibraton device MMB Interface Design | Complete | 6 | 120d | 2020-11-01 | 2021-04-15 |  | 100% |  |  |  | 1329 |  | 2020-11-01 | 2021-04-15 | 0
3082 | 1.6 | 1.6.1.1.2.2 | C | DAQ-Calibration device MMB Interface Documented | Complete | 6 | 1d | 2021-04-16 | 2021-04-16 |  | 100% |  |  |  | 1328 |  | 2021-04-16 | 2021-04-16 | 0
3083 | 1.6 | 1.6.1.1.2.3 | C | DAQ-Calibration MMB software implementation and testing for NTS | Started | 6 | 207d | 2021-11-30 | 2022-09-14 |  | 20% |  |  |  | 317 |  | 2021-11-30 | 2022-09-14 | 0
3084 | 1.6 | 1.6.1.1.2.4 | C | NTS minimal DAQ ready for calibration device testing at NTS | Not Started | 6 | 0 | 2022-09-14 | 2022-09-14 | 3083 | 0% |  |  |  | 317 |  | 2022-09-14 | 2022-09-14 | 0
3085 | 1.6 | 1.6.1.1.2.5 | C | Support DAQ installation for NTS calibration device testing | Not Started | 6 | 643d | 2022-09-15 | 2025-03-11 | 3084 | 0% |  |  |  | 317 |  | 2022-09-15 | 2025-03-11 | 0
3086 | 1.6 | 1.6.1.1.2.5.0 | C | Capture higher level DAQ requirements for Calibration devices | Not Started | 6 | 97d | 2023-04-13 | 2023-08-25 | 3008, 2958FS +30d, 2945 | 0% | moved to match delayed special device schedule |  |  | -85 |  | 2023-04-13 | 2023-08-25 | 0
3087 | 1.6 | 1.6.1.1.2.5.1 | C | Prototype and evaluate DAQ components for Calibration devices | Not Started | 6 | 190d | 2023-08-28 | 2024-05-22 | 3086 | 0% |  |  |  | -85 |  | 2023-08-28 | 2024-05-22 | 0
3088 | 1.6 | 1.6.1.1.2.5.2 | C | Review DAQ/Special devices operations plan for new calibration devices | Not Started | 6 | 0 | 2024-05-22 | 2024-05-22 | 3087 | 0% | review - major milestone |  |  | -85 |  | 2024-05-22 | 2024-05-22 | 0
3089 | 1.6 | 1.6.1.1.2.6 | C | Integrate support for calibration devices into DataCollector component | Not Started | 6 | 150d | 2024-05-23 | 2024-12-19 | 3088 | 0% |  |  |  | -85 |  | 2024-05-23 | 2024-12-19 | 0
3090 | 1.6 | 1.6.1.1.2.6.1 | C | Integrate support for calibration devices into overall DAQ system | Not Started | 6 | 150d | 2024-12-20 | 2025-07-21 | 3089 | 0% |  |  |  | -85 |  | 2024-12-20 | 2025-07-21 | 0
3091 | 1.6 | 1.6.1.1.2.6.2 | C | IceCube DAQ system level testing of calibration devices at SPTS and NTS | Not Started | 6 | 154d | 2025-07-22 | 2026-02-25 | 3090 | 0% |  |  |  | -85 |  | 2025-07-22 | 2026-02-25 | 0
3092 | 1.6 | 1.6.1.1.2.7 | C | DAQ software ready for deployment including support for all new Calibration devices | Not Started | 6 | 0 | 2026-02-25 | 2026-02-25 | 3091 | 0% |  |  |  | 38 |  | 2026-02-25 | 2026-02-25 | 0
3093 | 1.6 | 1.6.1.1.2.8 | C | DAQ for calibration devices software deployment at SPS | Not Started | 6 | 20d | 2026-02-26 | 2026-03-25 | 3092 | 0% |  |  |  | 49 |  | 2026-02-26 | 2026-03-25 | 0
3094 | 1.6 | 1.6.1.2 | P | Experiment Control | Started | 4 | 2042d | 2018-06-01 | 2026-04-10 |  | 24% |  |  |  | 37 |  | 2018-06-01 | 2026-04-10 | 0
3095 | 1.6 | 1.6.1.2.1 | P | Interface to OM sensors | Started | 5 | 1981d | 2018-06-01 | 2026-01-15 |  | 37% |  |  |  | 98 |  | 2018-06-01 | 2026-01-15 | 0
3096 | 1.6 | 1.6.1.2.1.1 | C | Experiment control design for FAT testing | Complete | 6 | 371d | 2018-06-01 | 2019-11-01 |  | 100% |  |  |  | 1707 |  | 2018-06-01 | 2019-11-01 | 0
3097 | 1.6 | 1.6.1.2.1.2 | C | ExpControl- OM Sensor software Interface Documented | Complete | 6 | 1d | 2019-11-04 | 2019-11-04 | 3096 | 100% |  |  |  | 1707 |  | 2019-11-04 | 2019-11-04 | 0
3098 | 1.6 | 1.6.1.2.1.3 | C | Minimal ExpControl for sensor testing development | Complete | 6 | 89d | 2019-06-19 | 2019-10-21 |  | 100% |  |  |  | 1355 |  | 2019-06-19 | 2019-10-21 | 0
3099 | 1.6 | 1.6.1.2.1.4 | C | Minimal ExpControl ready for sensor testing ready | Complete | 6 | 1d | 2019-10-22 | 2019-10-22 | 3098 | 100% |  |  |  | 1355 |  | 2019-10-22 | 2019-10-22 | 0
3100 | 1.6 | 1.6.1.2.1.5 | C | Testing ExpControl software implementation and testing for FATs | Complete | 6 | 131d | 2019-10-23 | 2020-04-22 | 3099 | 100% |  |  |  | 1355 |  | 2019-10-23 | 2020-04-22 | 0
3101 | 1.6 | 1.6.1.2.1.6 | C | Testing ExpControl software ready for FAT testing for DEgg | Complete | 6 | 1d | 2020-04-23 | 2020-04-23 | 3100 | 100% |  |  |  | 1355 |  | 2020-04-23 | 2020-04-23 | 0
3102 | 1.6 | 1.6.1.2.1.7 | C | Extend testing ExpControl software to all OM types (mDOM, pDOM) | Complete | 6 | 229d | 2020-04-24 | 2021-03-10 | 3101 | 100% |  |  |  | 1355 |  | 2020-04-24 | 2021-03-10 | 0
3103 | 1.6 | 1.6.1.2.1.8 | C | Support ExpControl installation for sensor testing | Started | 6 | 782d | 2020-10-01 | 2023-09-29 |  | 17% | new end date for mDOM FAT |  |  | 688 |  | 2020-10-01 | 2023-09-29 | 0
3104 | 1.6 | 1.6.1.2.1.9 | C | Capture requirements for ExpControl - Upgrade OM | Not Started | 6 | 66d | 2022-04-01 | 2022-07-01 |  | 0% |  |  |  | -70 |  | 2022-04-01 | 2022-07-01 | 0
3105 | 1.6 | 1.6.1.2.1.9.1 | C | Prototype and evalulate I3Live extensitons | Not Started | 6 | 227d | 2022-07-04 | 2023-05-16 | 3104 | 0% |  |  |  | 98 |  | 2022-07-04 | 2023-05-16 | 0
3106 | 1.6 | 1.6.1.2.1.10 | C | Review Experiment Control - Upgrade plans for new modules | Not Started | 6 | 0 | 2023-05-16 | 2023-05-16 | 3105 | 0% | review - major milestone |  |  | -70 |  | 2023-05-16 | 2023-05-16 | 0
3107 | 1.6 | 1.6.1.2.1.11 | C | Define ExpControl-Data Collector component interface | Not Started | 6 | 160d | 2023-05-17 | 2023-12-28 | 3106 | 0% |  |  |  | -70 |  | 2023-05-17 | 2023-12-28 | 0
3108 | 1.6 | 1.6.1.2.1.11.1 | C | Implement ExpControl-DataCollector component interfaces | Not Started | 6 | 160d | 2023-12-29 | 2024-08-09 | 3107 | 0% |  |  |  | -70 |  | 2023-12-29 | 2024-08-09 | 0
3109 | 1.6 | 1.6.1.2.1.11.2 | C | Implement ExpControl DB interfaces to support DataCollector component | Not Started | 6 | 160d | 2024-08-12 | 2025-03-26 | 3108 | 0% |  |  |  | -70 |  | 2024-08-12 | 2025-03-26 | 0
3110 | 1.6 | 1.6.1.2.1.11.3 | C | Testing of ExpControl and DAQ operations at SPTS and NTS | Not Started | 6 | 188d | 2025-03-27 | 2025-12-16 | 3109 | 0% |  |  |  | -70 |  | 2025-03-27 | 2025-12-16 | 0
3111 | 1.6 | 1.6.1.2.1.12 | C | ExpCont system for deployment - OM sensors support ready | Not Started | 6 | 0 | 2025-12-16 | 2025-12-16 | 3110 | 0% |  |  |  | 98 |  | 2025-12-16 | 2025-12-16 | 0
3112 | 1.6 | 1.6.1.2.1.13 | C | ExpControl deployment at SPS | Not Started | 6 | 20d | 2025-12-17 | 2026-01-15 | 3111 | 0% |  |  |  | 98 |  | 2025-12-17 | 2026-01-15 | 0
3113 | 1.6 | 1.6.1.2.2 | P | Interface to Stand Alone Calibration Devices | Started | 5 | 1047d | 2022-03-27 | 2026-04-10 |  | 7% |  |  |  | 37 |  | 2022-03-27 | 2026-04-10 | 0
3114 | 1.6 | 1.6.1.2.2.1 | C | Interface Design to Calibration Devices (ExpControl, Config, Calib) | Started | 6 | 120d | 2022-03-27 | 2022-09-08 |  | 50% |  |  |  | 964 |  | 2022-03-27 | 2022-09-08 | 0
3115 | 1.6 | 1.6.1.2.2.2 | C | Capture higher level Exp Control requirements for Calibration devices | Not Started | 6 | 97d | 2023-04-13 | 2023-08-25 | 3008, 2958FS +30d, 2945 | 0% | moved to match delayed special device schedule |  |  | 37 |  | 2023-04-13 | 2023-08-25 | 0
3116 | 1.6 | 1.6.1.2.2.3 | C | Prototype and evaluate Exp Control components for Calibration devices | Not Started | 6 | 190d | 2023-08-28 | 2024-05-22 | 3115 | 0% |  |  |  | 37 |  | 2023-08-28 | 2024-05-22 | 0
3117 | 1.6 | 1.6.1.2.2.4 | C | Review ExpControl/Special devices operations plan for new calibration devices | Not Started | 6 | 0 | 2024-05-22 | 2024-05-22 | 3116 | 0% | review - major milestone |  |  | 37 |  | 2024-05-22 | 2024-05-22 | 0
3118 | 1.6 | 1.6.1.2.2.5 | C | Define and prototype ExpControl - Calibration device special run configuration interface | Not Started | 6 | 140d | 2024-05-23 | 2024-12-05 | 3117 | 0% |  |  |  | 37 |  | 2024-05-23 | 2024-12-05 | 0
3119 | 1.6 | 1.6.1.2.2.5.1 | C | Implement ExpControl - Calibration device special run configuration interface | Not Started | 6 | 140d | 2024-12-06 | 2025-06-23 | 3118 | 0% |  |  |  | 37 |  | 2024-12-06 | 2025-06-23 | 0
3120 | 1.6 | 1.6.1.2.2.5.2 | C | Testing of ExpControl - Calibration device control at SPTS and NTS | Not Started | 6 | 175d | 2025-06-24 | 2026-02-26 | 3119 | 0% |  |  |  | 37 |  | 2025-06-24 | 2026-02-26 | 0
3121 | 1.6 | 1.6.1.2.2.6 | C | ExpControl ready for deployment including support for all new Calibration devices | Not Started | 6 | 0 | 2026-02-26 | 2026-02-26 | 3120, 3092 | 0% |  |  |  | 37 |  | 2026-02-26 | 2026-02-26 | 0
3122 | 1.6 | 1.6.1.2.2.7 | C | ExpControl deployment at SPS | Not Started | 6 | 20d | 2026-02-27 | 2026-03-26 | 3121 | 0% |  |  |  | 37 |  | 2026-02-27 | 2026-03-26 | 0
3123 | 1.6 | 1.6.1.2.2.8 | C | Support ExpControl operations during initial special devices operations | Not Started | 6 | 11d | 2026-03-27 | 2026-04-10 | 3122 | 0% |  |  |  | 37 |  | 2026-03-27 | 2026-04-10 | 0
3124 | 1.6 | 1.6.1.2.3 | C | Extend I3Live and I3Moni system to support run monitoring data from new devices. | Not Started | 5 | 391d | 2024-09-30 | 2026-04-07 | 3075FS +35d | 0% |  |  |  | 40 |  | 2024-09-30 | 2026-04-07 | 0
3125 | 1.6 | 1.6.1.3 | P | Online Filtering | Started | 4 | 766d | 2023-01-02 | 2025-12-17 |  | 2% |  |  |  | 117 |  | 2023-01-02 | 2025-12-17 | 0
3126 | 1.6 | 1.6.1.3.1 | C | Specify Online Filter Req'mts (New sensors / Calib Devices) | Started | 5 | 34d | 2023-01-02 | 2023-02-16 | 3265FS +245d | 15% |  |  |  | 783 |  | 2023-01-02 | 2023-02-16 | 0
3127 | 1.6 | 1.6.1.3.2 | C | Design Filter Sys for unified DAQ readout of ALL sensors& Calib Devices | Not Started | 5 | 65d | 2023-02-17 | 2023-05-18 | 3126 | 0% |  |  |  | 783 |  | 2023-02-17 | 2023-05-18 | 0
3128 | 1.6 | 1.6.1.3.3 | C | Review Online Filtering - Upgrade plans for new modules | Not Started | 5 | 1d | 2023-05-19 | 2023-05-19 | 3127 | 0% | delayed M&O review of Upgrade plans to avoid pole season |  |  | 783 |  | 2023-05-19 | 2023-05-19 | 0
3129 | 1.6 | 1.6.1.3.4 | C | Implement and testing of filtering SW for prod. systems | Not Started | 5 | 196d | 2025-02-18 | 2025-11-18 | 3227FS +65d | 0% | delayed start -> M&O prioritization of PnFNext developement and testing |  |  | 117 |  | 2025-02-18 | 2025-11-18 | 0
3130 | 1.6 | 1.6.1.3.5 | C | New Online Filter Sys for SPS (readout New Sensors& Calib Devices | Not Started | 5 | 0 | 2025-11-18 | 2025-11-18 | 3129 | 0% |  |  |  | 117 |  | 2025-11-18 | 2025-11-18 | 0
3131 | 1.6 | 1.6.1.3.6 | C | New Online Filter Sys Deployment at SPS | Not Started | 5 | 20d | 2025-11-19 | 2025-12-17 | 3130 | 0% | delayed to match 25/26 deployment season |  |  | 117 |  | 2025-11-19 | 2025-12-17 | 0
3132 | 1.6 | 1.6.1.4 | P | OM Software | Started | 4 | 1880d | 2018-12-06 | 2026-03-03 |  | 31% |  |  |  | 65 |  | 2018-12-06 | 2026-03-03 | 0
3133 | 1.6 | 1.6.1.4.1 | C | Develop OM hardware-software high-level design | Complete | 5 | 29d | 2018-12-06 | 2019-01-15 |  | 100% |  |  |  | 1853 |  | 2018-12-06 | 2019-01-15 | 0
3134 | 1.6 | 1.6.1.4.2 | C | Develop OM software development environment allowing cross-compilation on all OM types | Complete | 5 | 63d | 2019-01-16 | 2019-04-12 | 3133 | 100% |  |  |  | 1853 |  | 2019-01-16 | 2019-04-12 | 0
3135 | 1.6 | 1.6.1.4.3 | P | OM testing software app | Started | 5 | 1821d | 2019-01-16 | 2026-01-20 |  | 36% |  |  |  | 95 |  | 2019-01-16 | 2026-01-20 | 0
3136 | 1.6 | 1.6.1.4.3.1 | C | Capture design requirements for OM testing app for DVT testing | Complete | 6 | 34d | 2019-01-16 | 2019-03-04 | 3133 | 100% |  |  |  | 1882 |  | 2019-01-16 | 2019-03-04 | 0
3137 | 1.6 | 1.6.1.4.3.2 | P | Software design and prototyping of OM testing app | Complete | 6 | 92d | 2019-03-04 | 2019-07-09 |  | 100% |  |  |  | 1791 |  | 2019-03-04 | 2019-07-09 | 0
3138 | 1.6 | 1.6.1.4.3.2.1 | C | Specify and implement interfaces from MCU to In-OM devices | Complete | 7 | 92d | 2019-03-04 | 2019-07-09 |  | 100% |  |  |  | 1733 |  | 2019-03-04 | 2019-07-09 | 0
3139 | 1.6 | 1.6.1.4.3.2.2 | C | Specify and implanent interface to from MCU to ICM | Complete | 7 | 58d | 2019-03-04 | 2019-05-22 | 3138SS | 100% |  |  |  | 1825 |  | 2019-03-04 | 2019-05-22 | 0
3140 | 1.6 | 1.6.1.4.3.3 | C | Develop and test OM testing app for DV testing | Complete | 6 | 124d | 2019-05-01 | 2019-10-21 |  | 100% |  |  |  | 111 |  | 2019-05-01 | 2019-10-21 | 0
3141 | 1.6 | 1.6.1.4.3.4 | C | OM testing app for DV testing ready | Complete | 6 | 1d | 2019-10-22 | 2019-10-22 | 3140 | 100% |  |  |  | 111 |  | 2019-10-22 | 2019-10-22 | 0
3142 | 1.6 | 1.6.1.4.3.4.1 | C | Capture design requirements for FAT testing OM software | Complete | 6 | 66d | 2019-10-23 | 2020-01-22 | 3141 | 100% |  |  |  | 111 |  | 2019-10-23 | 2020-01-22 | 0
3143 | 1.6 | 1.6.1.4.3.5 | C | Develop and test OM testing app for FAT testing | Complete | 6 | 111d | 2020-01-23 | 2020-06-25 | 3142 | 100% |  |  |  | 111 |  | 2020-01-23 | 2020-06-25 | 0
3144 | 1.6 | 1.6.1.4.3.6 | C | OM testing app for FAT testing ready | Complete | 6 | 1d | 2020-06-26 | 2020-06-26 | 3143 | 100% |  |  |  | 288 |  | 2020-06-26 | 2020-06-26 | 0
3145 | 1.6 | 1.6.1.4.3.7 | C | Extend OM testing app for mDOM, pDOM devices | Complete | 6 | 110d | 2020-06-29 | 2020-11-27 | 3144 | 100% |  |  |  | 111 |  | 2020-06-29 | 2020-11-27 | 0
3146 | 1.6 | 1.6.1.4.3.8 | C | Support OM testing app thru FAT testing cycles | Started | 6 | 740d | 2020-11-30 | 2023-09-29 | 3145 | 25% | new end date for mDOM FAT |  |  | 688 |  | 2020-11-30 | 2023-09-29 | 0
3147 | 1.6 | 1.6.1.4.3.9 | C | Develop SPAT testing software design and plan | Not Started | 6 | 87d | 2022-01-31 | 2022-05-31 |  | 0% |  |  |  | 1036 |  | 2022-01-31 | 2022-05-31 | 0
3148 | 1.6 | 1.6.1.4.3.9.1 | C | Extend OM testing app to include support for MMB based special devices | Not Started | 6 | 160d | 2022-10-03 | 2023-05-12 | 3145FS +480d | 0% | tie to MMB delivery...DW will provide |  |  | 96 |  | 2022-10-03 | 2023-05-12 | 0
3149 | 1.6 | 1.6.1.4.3.9.2 | C | Support OM testing app thru calibration device DVT and FAT testing | Not Started | 6 | 267d | 2023-05-15 | 2024-05-24 | 3148 | 0% |  |  |  | 521 |  | 2023-05-15 | 2024-05-24 | 0
3150 | 1.6 | 1.6.1.4.3.10 | C | Prototype and test SPAT testing software at NTS | Not Started | 6 | 77d | 2024-01-18 | 2024-05-03 | 3148FS +175d | 0% |  |  |  | 40 |  | 2024-01-18 | 2024-05-03 | 0
3151 | 1.6 | 1.6.1.4.3.10.1 | C | Review SPAT testing plans for Pole | Not Started | 6 | 0 | 2024-06-14 | 2024-06-14 | 3150FS +30d | 0% | Let's review SPAT plan before we start. |  |  | 88 |  | 2024-06-14 | 2024-06-14 | 0
3152 | 1.6 | 1.6.1.4.3.11 | C | Prepare and ship SPAT toolset to Pole | Not Started | 6 | 44d | 2024-04-05 | 2024-06-05 | 3150FS -21d | 0% | basic test equipment/computers, special cable and FH are elsewhere |  |  | 508 |  | 2024-04-05 | 2024-06-05 | 0
3153 | 1.6 | 1.6.1.4.3.12 | C | SPAT personnel arrives at NPX FS2 | Not Started | 6 | 0 | 2024-12-15 | 2024-12-15 |  | 0% |  |  |  | 10 |  | 2024-12-15 | 2024-12-15 | 0
3154 | 1.6 | 1.6.1.4.3.13 | C | SPAT testing preparation and execution at Pole FS2 | Not Started | 6 | 46d | 2024-12-24 | 2025-02-27 | 1809 | 0% |  |  |  | 9 |  | 2024-12-24 | 2025-02-27 | 0
3155 | 1.6 | 1.6.1.4.3.14 | C | SPAT personnel arrives at NPX FS3 | Not Started | 6 | 0 | 2025-11-20 | 2025-11-20 |  | 0% |  |  |  | 95 |  | 2025-11-20 | 2025-11-20 | 0
3156 | 1.6 | 1.6.1.4.3.15 | C | SPAT testing preparation and execution at Pole FS3 | Not Started | 6 | 41d | 2025-11-20 | 2026-01-20 | 3155 | 0% |  |  |  | 95 |  | 2025-11-20 | 2026-01-20 | 0
3157 | 1.6 | 1.6.1.4.4 | P | OM calibration software app | Complete | 5 | 241d | 2020-02-03 | 2021-01-04 |  | 100% |  |  |  | 1402 |  | 2020-02-03 | 2021-01-04 | 0
3158 | 1.6 | 1.6.1.4.4.1 | C | Capture design requirements for OM calibration collection app | Complete | 6 | 30d | 2020-02-03 | 2020-03-13 |  | 100% |  |  |  | 1402 |  | 2020-02-03 | 2020-03-13 | 0
3159 | 1.6 | 1.6.1.4.4.2 | C | Software design and prototyping of OM data calibration app | Complete | 6 | 35d | 2020-03-16 | 2020-05-01 | 3158 | 100% |  |  |  | 1402 |  | 2020-03-16 | 2020-05-01 | 0
3160 | 1.6 | 1.6.1.4.4.3 | C | Develop and test OM data calibration app | Complete | 6 | 175d | 2020-05-04 | 2021-01-01 | 3159 | 100% |  |  |  | 1402 |  | 2020-05-04 | 2021-01-01 | 0
3161 | 1.6 | 1.6.1.4.4.4 | C | OM data calibration app ready for use | Complete | 6 | 1d | 2021-01-04 | 2021-01-04 | 3160 | 100% |  |  |  | 1402 |  | 2021-01-04 | 2021-01-04 | 0
3162 | 1.6 | 1.6.1.4.5 | P | OM data collection app | Started | 5 | 1362d | 2020-12-01 | 2026-03-03 |  | 16% |  |  |  | 65 |  | 2020-12-01 | 2026-03-03 | 0
3163 | 1.6 | 1.6.1.4.5.1 | C | xDOMapp design development | Complete | 6 | 229d | 2020-12-01 | 2021-10-15 |  | 100% |  |  |  | 1143 |  | 2020-12-01 | 2021-10-15 | 0
3164 | 1.6 | 1.6.1.4.5.2 | C | xDOMapp software and firmware design review | Complete | 6 | 0 | 2021-10-28 | 2021-10-28 | 3163FS +9d | 100% |  |  |  | 1134 |  | 2021-10-28 | 2021-10-28 | 0
3165 | 1.6 | 1.6.1.4.5.3 | C | Prototype xDOMapp development and testing at NTS | Complete | 6 | 55d | 2021-10-29 | 2022-01-13 | 3163FS +9d, 3164 | 100% |  |  |  | 1134 |  | 2021-10-29 | 2022-01-13 | 0
3166 | 1.6 | 1.6.1.4.5.4 | C | Verification of OM waveform processing with mDOM and DEgg” | Not Started | 6 | 78d | 2022-06-15 | 2022-09-30 |  | 0% | includes testing of in OM feature extraction and noise rate mitigations |  |  | 466 |  | 2022-06-15 | 2022-09-30 | 0
3167 | 1.6 | 1.6.1.4.5.4.1 | C | Develop and test xDOMapp data collection app | Not Started | 6 | 150d | 2022-10-03 | 2023-04-28 | 3166 | 0% |  |  |  | 466 |  | 2022-10-03 | 2023-04-28 | 0
3168 | 1.6 | 1.6.1.4.5.4.2 | C | Support integration work and testing with DAQ Data Collector component’ | Not Started | 6 | 332d | 2023-05-01 | 2024-08-09 | 3167 | 0% |  |  |  | 466 |  | 2023-05-01 | 2024-08-09 | 0
3169 | 1.6 | 1.6.1.4.5.4.3 | C | Extend xDOMapp to include support for calibration devices in operations | Not Started | 6 | 190d | 2023-08-28 | 2024-05-22 | 3087SS | 0% |  |  |  | 523 |  | 2023-08-28 | 2024-05-22 | 0
3170 | 1.6 | 1.6.1.4.5.4.4 | C | Develop and test xDOMapp support for SPAT testing at NTS | Not Started | 6 | 77d | 2024-01-18 | 2024-05-03 | 3150SS | 0% |  |  |  | 147 |  | 2024-01-18 | 2024-05-03 | 0
3171 | 1.6 | 1.6.1.4.5.4.5 | C | OM data collection app ready for use in SPAT/NTS | Not Started | 6 | 1d | 2024-06-17 | 2024-06-17 | 3170FS +30d |  |  |  |  | 117 |  | 2024-06-17 | 2024-06-17 | 0
3172 | 1.6 | 1.6.1.4.5.4.6 | C | Support full DAQ testing with xDOMapp at NTS/SPTS with OM devices | Not Started | 6 | 188d | 2025-03-27 | 2025-12-16 | 3110SS | 0% |  |  |  | 118 |  | 2025-03-27 | 2025-12-16 | 0
3173 | 1.6 | 1.6.1.4.5.5 | C | Review OM data collection app in detector operations | Not Started | 6 | 0 | 2023-04-28 | 2023-04-28 | 3167 | 0% |  |  |  | 798 |  | 2023-04-28 | 2023-04-28 | 0
3174 | 1.6 | 1.6.1.4.5.6 | C | Support full DAQ testing with xDOMapp at NTS/SPTS with Calibration devices | Not Started | 6 | 154d | 2025-07-22 | 2026-02-25 | 3091SS | 0% |  |  |  | 69 |  | 2025-07-22 | 2026-02-25 | 0
3175 | 1.6 | 1.6.1.4.5.7 | C | OM data collection app ready for use at SPS with full DAQ | Not Started | 6 | 0 | 2025-12-16 | 2025-12-16 | 3172 | 0% |  |  |  | 118 |  | 2025-12-16 | 2025-12-16 | 0
3176 | 1.6 | 1.6.1.4.5.8 | C | Support xDOMapp through SPAT testing and deployment | Not Started | 6 | 316d | 2024-12-10 | 2026-03-03 | 3154SS -10d | 0% |  |  |  | 65 |  | 2024-12-10 | 2026-03-03 | 0
3177 | 1.6 | 1.6.1.4.6 | P | MMB support software | Started | 5 | 1158d | 2021-06-01 | 2025-11-14 |  | 20% |  |  |  | 139 |  | 2021-06-01 | 2025-11-14 | 0
3178 | 1.6 | 1.6.1.4.6.1 | C | Develop and test MMB software package on prototype MMB | Complete | 6 | 109d | 2021-06-01 | 2021-10-29 |  | 100% |  |  |  | 1188 |  | 2021-06-01 | 2021-10-29 | 0
3179 | 1.6 | 1.6.1.4.6.2 | C | Review MMB xDOMapp design | Complete | 6 | 1d | 2021-11-01 | 2021-11-01 |  | 100% |  |  |  | 1187 |  | 2021-11-01 | 2021-11-01 | 0
3180 | 1.6 | 1.6.1.4.6.3 | C | Complete MMB software support package for calibration devices | Not Started | 6 | 88d | 2022-05-13 | 2022-09-13 |  | 0% |  |  |  | 961 |  | 2022-05-13 | 2022-09-13 | 0
3181 | 1.6 | 1.6.1.4.6.4 | C | MMB support software ready for calibration device testing at NTS | Not Started | 6 | 0 | 2022-09-13 | 2022-09-13 |  | 0% |  |  |  | 962 |  | 2022-09-13 | 2022-09-13 | 0
3182 | 1.6 | 1.6.1.4.6.5 | C | Support MMB software for calibration device interface development | Not Started | 6 | 360d | 2024-06-26 | 2025-11-14 | 3087FS +24d | 0% |  |  |  | 139 |  | 2024-06-26 | 2025-11-14 | 0
3183 | 1.6 | 1.6.1.5 | P | FieldHub Software | Started | 4 | 1360d | 2021-01-01 | 2026-04-01 |  | 26% |  |  |  | 44 |  | 2021-01-01 | 2026-04-01 | 0
3184 | 1.6 | 1.6.1.5.1 | C | maintenance of mini-FieldHub server software for FAT | Started | 5 | 716d | 2021-01-01 | 2023-09-29 |  | 60% | new end of FAT testing |  |  | 688 |  | 2021-01-01 | 2023-09-29 | 0
3185 | 1.6 | 1.6.1.5.2 | C | development and testing of FieldHub SBC OS and toolchain | Complete | 5 | 44d | 2021-06-01 | 2021-07-30 |  | 100% |  |  |  | 1253 |  | 2021-06-01 | 2021-07-30 | 0
3186 | 1.6 | 1.6.1.5.2.1 | C | Verification of Field Hub throughput on fully populated strings | Not Started | 5 | 144d | 2022-03-01 | 2022-09-16 |  | 0% | retire FH throughput risks in FH design |  |  | 794 |  | 2022-03-01 | 2022-09-16 | 0
3187 | 1.6 | 1.6.1.5.2.2 | C | FieldHub SBC OS preparation and testing | Not Started | 5 | 70d | 2022-11-01 | 2023-02-06 | 2831FS -24d | 0% |  |  |  | 857 |  | 2022-11-01 | 2023-02-06 | 0
3188 | 1.6 | 1.6.1.5.3 | C | Modification of FieldHub server software to support full FieldHub functionality | Not Started | 5 | 164d | 2022-09-19 | 2023-05-04 | 3186 | 0% |  |  |  | 794 |  | 2022-09-19 | 2023-05-04 | 0
3189 | 1.6 | 1.6.1.5.3.1 | C | Field Hub Software ready for use on FH hardware at NTS | Not Started | 5 | 0 | 2023-05-05 | 2023-05-05 | 3188, 2833 | 0% |  |  |  | 793 |  | 2023-05-05 | 2023-05-05 | 0
3190 | 1.6 | 1.6.1.5.4 | C | Review Field Hub software in Upgrade detector operations | Not Started | 5 | 0 | 2023-05-18 | 2023-05-18 |  | 0% | review - major milestone |  |  | 785 |  | 2023-05-18 | 2023-05-18 | 0
3191 | 1.6 | 1.6.1.5.5 | C | Development of FieldHub monitoring software (IceCube Live interface) | Not Started | 5 | 211d | 2024-01-22 | 2024-11-11 | 3105FS +175d | 0% |  |  |  | 366 |  | 2024-01-22 | 2024-11-11 | 0
3192 | 1.6 | 1.6.1.5.5.1 | C | Software available to support FieldHub installation and testing at Pole | Not Started | 5 | 0 | 2024-11-11 | 2024-11-11 | 3191 | 0% |  |  |  | 366 |  | 2024-11-11 | 2024-11-11 | 0
3193 | 1.6 | 1.6.1.5.6 | C | support of FieldHub / pDAQ Data Collector interface layer with pDAQ development | Not Started | 5 | 290d | 2024-03-25 | 2025-05-07 | 3075SS +60d | 0% |  |  |  | 276 |  | 2024-03-25 | 2025-05-07 | 0
3194 | 1.6 | 1.6.1.5.7 | C | suopport FieldHub and SBC software system thru DAQ deployment and String commissioning | Not Started | 5 | 152d | 2025-08-28 | 2026-04-01 | 3077SS +110d | 0% |  |  |  | 44 |  | 2025-08-28 | 2026-04-01 | 0
3195 | 1.6 | 1.6.1.6 | P | OM Firmware support (PSU) | Started | 4 | 1898d | 2018-12-17 | 2026-04-07 |  | 63% |  |  |  | 40 |  | 2018-12-17 | 2026-04-07 | 0
3196 | 1.6 | 1.6.1.6.1 | P | mDOM DAQ Electronics | Complete | 5 | 729d | 2018-12-17 | 2021-09-30 |  | 100% |  |  |  | 1209 |  | 2018-12-17 | 2021-09-30 | 0
3197 | 1.6 | 1.6.1.6.1.1 | P | Preliminary design phase | Complete | 6 | 70d | 2018-12-17 | 2019-03-22 |  | 100% |  |  |  | 1868 |  | 2018-12-17 | 2019-03-22 | 0
3198 | 1.6 | 1.6.1.6.1.1.1 | C | Build 4 ch. analog-front end (AFE) demonstrator board | Complete | 7 | 50d | 2018-12-17 | 2019-02-22 |  | 100% |  |  |  | 1868 |  | 2018-12-17 | 2019-02-22 | 0
3199 | 1.6 | 1.6.1.6.1.1.2 | C | Characterization of AFE performance | Complete | 7 | 20d | 2019-02-25 | 2019-03-22 | 3198 | 100% |  |  |  | 1868 |  | 2019-02-25 | 2019-03-22 | 0
3200 | 1.6 | 1.6.1.6.1.2 | C | mDOM Mainboard firmware development | Complete | 6 | 456d | 2020-01-02 | 2021-09-30 |  | 100% |  |  |  | 1209 |  | 2020-01-02 | 2021-09-30 | 0
3201 | 1.6 | 1.6.1.6.1.3 | C | Pulsed Laser Test Stand for Design verification | Complete | 6 | 20d | 2021-06-07 | 2021-07-02 |  | 100% |  |  |  | 1273 |  | 2021-06-07 | 2021-07-02 | 0
3202 | 1.6 | 1.6.1.6.1.4 | C | Tender and procurement (series production) | Complete | 6 | 200d | 2020-04-22 | 2021-01-26 |  | 100% |  |  |  | 1386 |  | 2020-04-22 | 2021-01-26 | 0
3203 | 1.6 | 1.6.1.6.1.5 | C | mDOM mainboard firmware support for FAT testing | Complete | 6 | 30d | 2021-07-26 | 2021-09-03 |  | 100% |  |  |  | 1228 |  | 2021-07-26 | 2021-09-03 | 0
3204 | 1.6 | 1.6.1.6.2 | P | D-Egg - PSU | Complete | 5 | 501d | 2019-05-01 | 2021-03-31 |  | 100% |  |  |  | 1340 |  | 2019-05-01 | 2021-03-31 | 0
3205 | 1.6 | 1.6.1.6.2.1 | C | Firmware development | Complete | 6 | 501d | 2019-05-01 | 2021-03-31 |  | 100% |  |  |  | 1340 |  | 2019-05-01 | 2021-03-31 | 0
3206 | 1.6 | 1.6.1.6.2.2 | C | Testing | Complete | 6 | 50d | 2019-12-19 | 2020-02-26 |  | 100% |  |  |  | 1625 |  | 2019-12-19 | 2020-02-26 | 0
3207 | 1.6 | 1.6.1.6.3 | P | Integrated D-Egg - PSU | Complete | 5 | 40d | 2019-11-11 | 2020-01-03 |  | 100% |  |  |  | 1663 |  | 2019-11-11 | 2020-01-03 | 0
3208 | 1.6 | 1.6.1.6.3.1 | C | Design Verification Test | Complete | 6 | 40d | 2019-11-11 | 2020-01-03 |  | 100% |  |  |  | 1663 |  | 2019-11-11 | 2020-01-03 | 0
3209 | 1.6 | 1.6.1.6.3.2 | C | Integrated D-Egg Final Design Review | Complete | 6 | 1d | 2019-11-25 | 2019-11-25 |  | 100% |  |  |  | 1692 |  | 2019-11-25 | 2019-11-25 | 0
3210 | 1.6 | 1.6.1.6.4 | P | PDOM DAQ Electronics - PSU | Started | 5 | 916d | 2019-03-01 | 2022-09-02 |  | 55% |  |  |  | 968 |  | 2019-03-01 | 2022-09-02 | 0
3211 | 1.6 | 1.6.1.6.4.1 | C | Firmware | Complete | 6 | 100d | 2019-03-01 | 2019-07-18 |  | 100% |  |  |  | 1709 |  | 2019-03-01 | 2019-07-18 | 0
3212 | 1.6 | 1.6.1.6.4.2 | C | Testing - Rev2 | Complete | 6 | 75d | 2019-07-19 | 2019-10-31 | 3211 | 100% |  |  |  | 1709 |  | 2019-07-19 | 2019-10-31 | 0
3213 | 1.6 | 1.6.1.6.4.3 | C | Testing - Rev3 | Complete | 6 | 30d | 2021-11-12 | 2021-12-23 |  | 100% |  |  |  | 1149 |  | 2021-11-12 | 2021-12-23 | 0
3214 | 1.6 | 1.6.1.6.4.4 | C | Adapt D-Egg Firmware to PDOM Mainboard and verify design | Started | 6 | 207d | 2021-11-18 | 2022-09-02 |  | 11% |  |  |  | 968 |  | 2021-11-18 | 2022-09-02 | 0
3215 | 1.6 | 1.6.1.6.4.5 | C | PDOM Final Design Review - FW | Not Started | 6 | 0 | 2022-09-02 | 2022-09-02 | 3214 | 0% |  |  |  | 968 |  | 2022-09-02 | 2022-09-02 | 0
3216 | 1.6 | 1.6.1.6.5 | P | Special Devices - PSU | Complete | 5 | 437d | 2020-05-01 | 2022-01-03 |  | 100% |  |  |  | 1142 |  | 2020-05-01 | 2022-01-03 | 0
3217 | 1.6 | 1.6.1.6.5.1 | C | R&D module mission review | Complete | 6 | 1d | 2020-05-01 | 2020-05-01 |  | 100% |  |  |  | 1578 |  | 2020-05-01 | 2020-05-01 | 0
3218 | 1.6 | 1.6.1.6.5.2 | C | R&D modules deployment readiness review | Complete | 6 | 1d | 2022-01-03 | 2022-01-03 |  | 100% |  |  |  | 1142 |  | 2022-01-03 | 2022-01-03 | 0
3219 | 1.6 | 1.6.1.6.6 | C | Firmware device maintenance and support for all OM devices during DAQ Development | Not Started | 5 | 913d | 2022-09-26 | 2026-04-07 | 3072SS +60d |  | Bugfix and feature requests for all device FPGA FW from Tyler (10% FTE 22/3 then 5% ) |  |  | 40 |  | 2022-09-26 | 2026-04-07 | 0
3220 | 1.6 | 1.6.2 | P | Offline Systems | Started | 3 | 1891d | 2019-01-01 | 2026-04-13 |  | 42% |  |  |  | 36 |  | 2019-01-01 | 2026-04-13 | 0
3221 | 1.6 | 1.6.2.0 | C | L3 Task Management | Started | 4 | 1434d | 2020-10-01 | 2026-04-13 |  | 17% | ramp down management effort early... |  |  | 36 |  | 2020-10-01 | 2026-04-13 | 0
3222 | 1.6 | 1.6.2.1 | P | Core Software | Started | 4 | 1274d | 2019-12-24 | 2024-11-13 |  | 82% |  |  |  | 398 |  | 2019-12-24 | 2024-11-13 | 0
3223 | 1.6 | 1.6.2.1.1 | C | Capture Required changes to IceTray software packages | Complete | 5 | 25d | 2019-12-24 | 2020-01-27 |  | 100% |  |  |  | 1188 |  | 2019-12-24 | 2020-01-27 | 0
3224 | 1.6 | 1.6.2.1.2 | C | Design updates to IceTray (support new optical sensor Data/Config/Calib Info) | Complete | 5 | 25d | 2020-01-28 | 2020-03-02 | 3223 | 100% |  |  |  | 1188 |  | 2020-01-28 | 2020-03-02 | 0
3225 | 1.6 | 1.6.2.1.3 | C | Develop and test Updates to IceTray (support new optical sensor Data/Config/Calib Info) | Complete | 5 | 434d | 2020-03-03 | 2021-10-29 | 3224 | 100% |  |  |  | 1188 |  | 2020-03-03 | 2021-10-29 | 0
3226 | 1.6 | 1.6.2.1.4 | C | Core Software Release Supporting Upgrade | Complete | 5 | 0 | 2021-10-29 | 2021-10-29 | 3225 | 100% | expected Dec 2021 |  |  | 1188 |  | 2021-10-29 | 2021-10-29 | 0
3227 | 1.6 | 1.6.2.1.5 | C | Extend Core Software to include support for new hardware readouts | Not Started | 5 | 107d | 2024-06-18 | 2024-11-13 | 3171 | 0% | 1650 |  |  | 182 |  | 2024-06-18 | 2024-11-13 | 0
3228 | 1.6 | 1.6.2.1.6 | C | Core Software Release for hardware readout support ready | Not Started | 5 | 0 | 2024-11-13 | 2024-11-13 | 3227 | 0% |  |  |  | 398 |  | 2024-11-13 | 2024-11-13 | 0
3229 | 1.6 | 1.6.2.2 | P | Reconstruction | Started | 4 | 1530d | 2020-05-12 | 2026-04-03 |  | 54% |  |  |  | 42 |  | 2020-05-12 | 2026-04-03 | 0
3230 | 1.6 | 1.6.2.2.1 | C | Capture Requirements for reconstruction software updates | Complete | 5 | 25d | 2020-05-12 | 2020-06-15 |  | 100% |  |  |  | 1188 |  | 2020-05-12 | 2020-06-15 | 0
3231 | 1.6 | 1.6.2.2.2 | C | Design changes to IceCube Event Reconstruction Algorithms (use data from New Sensors&Calibr Info) | Complete | 5 | 25d | 2020-06-16 | 2020-07-20 | 3230 | 100% |  |  |  | 1188 |  | 2020-06-16 | 2020-07-20 | 0
3232 | 1.6 | 1.6.2.2.3 | C | Develop and test Updates to IceCube Event Reconstruction Algorithms (use data from New Sensors&Calibr Info) | Complete | 5 | 334d | 2020-07-21 | 2021-10-29 | 3231 | 100% |  |  |  | 1188 |  | 2020-07-21 | 2021-10-29 | 0
3233 | 1.6 | 1.6.2.2.4 | C | Reconstruction tools Release Supporting Upgrade | Complete | 5 | 0 | 2021-10-29 | 2021-10-29 | 3232 | 100% |  |  |  | 1188 |  | 2021-10-29 | 2021-10-29 | 0
3234 | 1.6 | 1.6.2.2.5 | C | Offline software support and testing for Upgrade low energy event reconstruction tools | Not Started | 5 | 323d | 2025-01-05 | 2026-04-03 |  |  | General SW support LE reco tools needed ahead of Upgrade data analyses |  |  | 42 |  | 2025-01-05 | 2026-04-03 | 0
3235 | 1.6 | 1.6.2.3 | P | Tools and Infrastructure | Started | 4 | 1891d | 2019-01-01 | 2026-04-13 |  | 24% |  |  |  | 36 |  | 2019-01-01 | 2026-04-13 | 0
3236 | 1.6 | 1.6.2.3.1 | C | Evaluate readiness of Current IceCube SW Development Infrastructure to Support IceCube Upgrade SW Activities&TimeScales | Complete | 5 | 64d | 2019-01-01 | 2019-03-29 |  | 100% |  |  |  | 36 |  | 2019-01-01 | 2019-03-29 | 0
3237 | 1.6 | 1.6.2.3.2 | C | Upgrade IceCube SW Development Infrastructure to support Upgrade activities | Complete | 5 | 87d | 2019-04-01 | 2019-07-30 | 3236 | 100% |  |  |  | 36 |  | 2019-04-01 | 2019-07-30 | 0
3238 | 1.6 | 1.6.2.3.3 | C | Support Upgrade SW Development environment and infrastructure | Started | 5 | 1740d | 2019-07-31 | 2026-04-13 | 3237 | 17% | new end: support through end of project. |  |  | 36 |  | 2019-07-31 | 2026-04-13 | 0
3239 | 1.6 | 1.6.3 | P | Simulation Software | Started | 3 | 1943d | 2018-11-01 | 2026-04-24 |  | 56% |  |  |  | 27 |  | 2018-11-01 | 2026-04-24 | 0
3240 | 1.6 | 1.6.3.0 | C | L3 Task Management | Started | 4 | 1434d | 2020-10-01 | 2026-04-13 |  | 29% |  |  |  | 36 |  | 2020-10-01 | 2026-04-13 | 0
3241 | 1.6 | 1.6.3.1 | P | Electronic readout and optical module simulation | Started | 4 | 1513d | 2020-05-28 | 2026-03-27 |  | 86% |  |  |  | 47 |  | 2020-05-28 | 2026-03-27 | 0
3242 | 1.6 | 1.6.3.1.1 | C | Capture requirements for Optical Sensor Simulation Tools based on Final Designs | Complete | 5 | 25d | 2020-05-28 | 2020-07-01 |  | 100% |  |  |  | 1188 |  | 2020-05-28 | 2020-07-01 | 0
3243 | 1.6 | 1.6.3.1.2 | C | Design Optical Sensor Simulation Tools based on Final Designs | Complete | 5 | 26d | 2020-07-02 | 2020-08-06 | 3242 | 100% |  |  |  | 1188 |  | 2020-07-02 | 2020-08-06 | 0
3244 | 1.6 | 1.6.3.1.3 | P | Version 1 - as designed | Complete | 5 | 321d | 2020-08-07 | 2021-10-29 |  | 100% |  |  |  | 1188 |  | 2020-08-07 | 2021-10-29 | 0
3245 | 1.6 | 1.6.3.1.3.1 | C | Implementation and testing | Complete | 6 | 321d | 2020-08-07 | 2021-10-29 | 3243 | 100% |  |  |  | 1188 |  | 2020-08-07 | 2021-10-29 | 0
3246 | 1.6 | 1.6.3.1.3.2 | C | Release v1 simulation tools | Complete | 6 | 0 | 2021-10-29 | 2021-10-29 | 3245 | 100% |  |  |  | 1188 |  | 2021-10-29 | 2021-10-29 | 0
3247 | 1.6 | 1.6.3.1.4 | P | Version 2 - as built | Not Started | 5 | 63d | 2025-12-30 | 2026-03-27 |  | 0% |  |  |  | 47 |  | 2025-12-30 | 2026-03-27 | 0
3248 | 1.6 | 1.6.3.1.4.1 | C | Capture Improvements of OM device Simulation Tools (w/testing, deployment&initial data collection) | Not Started | 6 | 30d | 2025-12-30 | 2026-02-10 | 3302FS -65d | 0% | delayed as happens "as built"; depends on early input from string comm. |  |  | 4 |  | 2025-12-30 | 2026-02-10 | 0
3249 | 1.6 | 1.6.3.1.4.2 | C | Prepare and handoff needed details for as-built simulation final Implementation and testing | Not Started | 6 | 53d | 2026-01-14 | 2026-03-27 | 3248SS +10d | 0% | delayed as happens "as built" |  |  | 4 |  | 2026-01-14 | 2026-03-27 | 0
3250 | 1.6 | 1.6.3.1.4.3 | C | As built device details delivered to IceCube simulation team for simulation implementation and testing | Not Started | 6 | 0 | 2026-03-27 | 2026-03-27 | 3249 | 0% | delayed as happens "as built" |  |  | 47 |  | 2026-03-27 | 2026-03-27 | 0
3251 | 1.6 | 1.6.3.2 | P | Calibration Device simulation | Not Started | 4 | 800d | 2023-03-02 | 2026-04-07 |  | 0% |  |  |  | 40 |  | 2023-03-02 | 2026-04-07 | 0
3252 | 1.6 | 1.6.3.2.1 | C | Capture requirements for Calibration device Simulation Tools based on Final Designs | Not Started | 5 | 25d | 2023-03-02 | 2023-04-05 | 2945, 2958, 3008 | 0% | pred - special devices FDR |  |  | 661 |  | 2023-03-02 | 2023-04-05 | 0
3253 | 1.6 | 1.6.3.2.2 | C | Design Calibration Device Simulation Tools based on Final Designs | Not Started | 5 | 80d | 2023-04-06 | 2023-07-26 | 3252 | 0% |  |  |  | 661 |  | 2023-04-06 | 2023-07-26 | 0
3254 | 1.6 | 1.6.3.2.3 | P | Version 1 - as designed | Not Started | 5 | 74d | 2023-07-27 | 2023-11-07 |  | 0% |  |  |  | 661 |  | 2023-07-27 | 2023-11-07 | 0
3255 | 1.6 | 1.6.3.2.3.1 | C | Implementation and testing | Not Started | 6 | 74d | 2023-07-27 | 2023-11-07 | 3253 | 0% |  |  |  | 661 |  | 2023-07-27 | 2023-11-07 | 0
3256 | 1.6 | 1.6.3.2.3.2 | C | Release v1 calibration devicesimulation tools | Not Started | 6 | 0 | 2023-11-07 | 2023-11-07 | 3255 | 0% |  |  |  | 661 |  | 2023-11-07 | 2023-11-07 | 0
3257 | 1.6 | 1.6.3.2.4 | P | Version 2 - as built | Not Started | 5 | 45d | 2026-02-04 | 2026-04-07 |  | 0% |  |  |  | 40 |  | 2026-02-04 | 2026-04-07 | 0
3258 | 1.6 | 1.6.3.2.4.1 | C | Capture Improvements of Calibration device Simulation Tools (w/testing, deployment&initial data collection) | Not Started | 6 | 23d | 2026-02-04 | 2026-03-06 | 3308FS -45d | 0% | delayed as happens "as built"; depends on early input from device comm. |  |  | 40 |  | 2026-02-04 | 2026-03-06 | 0
3259 | 1.6 | 1.6.3.2.4.2 | C | Prepare and handoff needed details for as-built simulation final Implementation and testing | Not Started | 6 | 22d | 2026-03-09 | 2026-04-07 | 3258 | 0% | delayed as happens "as built" |  |  | 40 |  | 2026-03-09 | 2026-04-07 | 0
3260 | 1.6 | 1.6.3.2.4.3 | C | As built device details delivered to IceCube simulation team for simulation implementation and testing | Not Started | 6 | 0 | 2026-04-07 | 2026-04-07 | 3259 | 0% | delayed as happens "as built" |  |  | 40 |  | 2026-04-07 | 2026-04-07 | 0
3261 | 1.6 | 1.6.3.3 | P | Simulation production | Started | 4 | 1943d | 2018-11-01 | 2026-04-24 |  | 75% |  |  |  | 27 |  | 2018-11-01 | 2026-04-24 | 0
3262 | 1.6 | 1.6.3.3.1 | C | Initial Production of simulation samples for Design Studies | Complete | 5 | 66d | 2018-11-01 | 2019-01-31 |  | 100% |  |  |  | 1904 |  | 2018-11-01 | 2019-01-31 | 0
3263 | 1.6 | 1.6.3.3.2 | C | Design study simulation sample ready | Complete | 5 | 0 | 2019-01-31 | 2019-01-31 | 3262 | 100% |  |  |  | 1904 |  | 2019-01-31 | 2019-01-31 | 0
3264 | 1.6 | 1.6.3.3.3 | C | Produce"as designed" Simulation Samples (for analysis tool development) | Complete | 5 | 60d | 2021-11-01 | 2022-01-21 |  | 100% |  |  |  | 1028 |  | 2021-11-01 | 2022-01-21 | 0
3265 | 1.6 | 1.6.3.3.4 | C | “As designed” simulation sample ready | Complete | 5 | 0 | 2022-01-21 | 2022-01-21 | 3264 | 100% |  |  |  | 1028 |  | 2022-01-21 | 2022-01-21 | 0
3266 | 1.6 | 1.6.3.3.5 | C | Develop tools for "As -Built"Simulation Samples for Data Quality Verification Studies | Not Started | 5 | 43d | 2026-02-25 | 2026-04-24 | 3249SS +30d | 0% |  |  |  | 27 |  | 2026-02-25 | 2026-04-24 | 0
3267 | 1.6 | 1.6.3.3.6 | C | Tools to provide “As Built” simulation sample ready | Not Started | 5 | 0 | 2026-04-24 | 2026-04-24 | 3266 | 0% |  |  |  | 27 |  | 2026-04-24 | 2026-04-24 | 0
3268 | 1.6 | 1.6.4 | P | Computing Infrastructure | Started | 3 | 1868d | 2019-02-01 | 2026-04-13 |  | 29% |  |  |  | 36 |  | 2019-02-01 | 2026-04-13 | 0
3269 | 1.6 | 1.6.4.0 | C | L3 Task Management | Started | 4 | 1434d | 2020-10-01 | 2026-04-13 |  | 7% |  |  |  | 36 |  | 2020-10-01 | 2026-04-13 | 0
3270 | 1.6 | 1.6.4.1 | P | SPTS/NTS computing needs | Started | 4 | 1868d | 2019-02-01 | 2026-04-13 |  | 36% |  |  |  | 36 |  | 2019-02-01 | 2026-04-13 | 0
3271 | 1.6 | 1.6.4.1.1 | P | NTS | Started | 5 | 1868d | 2019-02-01 | 2026-04-13 |  | 21% |  |  |  | 36 |  | 2019-02-01 | 2026-04-13 | 0
3272 | 1.6 | 1.6.4.1.1.1 | C | Specify Requirements/Design NTS Computing Sys | Complete | 6 | 20d | 2019-02-01 | 2019-02-28 |  | 100% |  |  |  | 1818 |  | 2019-02-01 | 2019-02-28 | 0
3273 | 1.6 | 1.6.4.1.1.2 | C | Procure NTS Computing Hardware | Complete | 6 | 21d | 2019-03-01 | 2019-03-29 | 3272 | 100% |  |  |  | 1818 |  | 2019-03-01 | 2019-03-29 | 0
3274 | 1.6 | 1.6.4.1.1.3 | C | Buildout NTS Computing System | Complete | 6 | 45d | 2019-04-01 | 2019-05-31 | 3273 | 100% |  |  |  | 1818 |  | 2019-04-01 | 2019-05-31 | 0
3275 | 1.6 | 1.6.4.1.1.4 | C | NTS computing system complete | Complete | 6 | 0 | 2019-05-31 | 2019-05-31 | 3274 | 100% |  |  |  | 1818 |  | 2019-05-31 | 2019-05-31 | 0
3276 | 1.6 | 1.6.4.1.1.5 | C | Refresh NTS HW to match SPS | Not Started | 6 | 21d | 2025-03-31 | 2025-04-28 | 3285 | 0% |  |  |  | 283 |  | 2025-03-31 | 2025-04-28 | 0
3277 | 1.6 | 1.6.4.1.1.6 | C | Support NTS System | Started | 6 | 1708d | 2019-09-15 | 2026-04-13 |  | 17% | NTS support thru project |  |  | 36 |  | 2019-09-15 | 2026-04-13 | 0
3278 | 1.6 | 1.6.4.1.2 | P | SPTS | Complete | 5 | 455d | 2020-01-06 | 2021-10-01 |  | 100% |  |  |  | 1208 |  | 2020-01-06 | 2021-10-01 | 0
3279 | 1.6 | 1.6.4.1.2.1 | C | Design/Specify SPTS Ext req'd to support Upgrade Activities | Complete | 6 | 347d | 2020-01-06 | 2021-05-04 |  | 100% |  |  |  | 1208 |  | 2020-01-06 | 2021-05-04 | 0
3280 | 1.6 | 1.6.4.1.2.2 | C | Procure Computing Hardware for SPTS Ext | Complete | 6 | 66d | 2021-05-05 | 2021-08-04 | 3279 | 100% |  |  |  | 1208 |  | 2021-05-05 | 2021-08-04 | 0
3281 | 1.6 | 1.6.4.1.2.3 | C | Buildout SPTS Computing System for Ext(s) | Complete | 6 | 42d | 2021-08-05 | 2021-10-01 | 3280 | 100% |  |  |  | 1208 |  | 2021-08-05 | 2021-10-01 | 0
3282 | 1.6 | 1.6.4.1.2.4 | C | SPTS computing system complete | Complete | 6 | 0 | 2021-10-01 | 2021-10-01 | 3281 | 100% |  |  |  | 1208 |  | 2021-10-01 | 2021-10-01 | 0
3283 | 1.6 | 1.6.4.2 | P | SPS computing needs | Started | 4 | 1745d | 2019-05-01 | 2026-01-19 |  | 22% |  |  |  | 96 |  | 2019-05-01 | 2026-01-19 | 0
3284 | 1.6 | 1.6.4.2.1 | C | Specify space and power needs for IDF design process | Complete | 5 | 43d | 2019-05-01 | 2019-06-28 |  | 100% |  |  |  | 1798 |  | 2019-05-01 | 2019-06-28 | 0
3285 | 1.6 | 1.6.4.2.9 | C | Design/Specify SPS Computing Sys Extensions for Upgrade | Not Started | 5 | 44d | 2025-01-28 | 2025-03-28 | 3088, 3117FS +175d | 0% | deployment delayed |  |  | 216 |  | 2025-01-28 | 2025-03-28 | 0
3286 | 1.6 | 1.6.4.2.10 | C | Procure Computing Sys for SPSExt | Not Started | 5 | 21d | 2025-03-31 | 2025-04-28 | 3285 | 0% | deployment delayed |  |  | 216 |  | 2025-03-31 | 2025-04-28 | 0
3287 | 1.6 | 1.6.4.2.11 | C | Buildout and test SPS systems in North | Not Started | 5 | 45d | 2025-04-29 | 2025-06-30 | 3286 | 0% | deployment delayed |  |  | 216 |  | 2025-04-29 | 2025-06-30 | 0
3288 | 1.6 | 1.6.4.2.12 | C | Ship Computing Sys for SPS Ext to Pole | Not Started | 5 | 22d | 2025-07-01 | 2025-07-30 | 3287 | 0% | deployment delayed |  |  | 216 |  | 2025-07-01 | 2025-07-30 | 0
3289 | 1.6 | 1.6.4.2.13 | C | Computing HW for SPS Ext Arrival at NPX | Not Started | 5 | 0 | 2025-12-13 | 2025-12-13 |  | 0% | deployment delayed |  |  | 97 |  | 2025-12-13 | 2025-12-13 | 0
3290 | 1.6 | 1.6.4.2.14 | C | Installation at Pole | Not Started | 5 | 24d | 2025-12-15 | 2026-01-19 | 3289 | 0% | deployment delayed |  |  | 96 |  | 2025-12-15 | 2026-01-19 | 0
3291 | 1.6 | 1.6.4.2.15 | C | SPS computing system for Upgrade complete at pole | Not Started | 5 | 0 | 2026-01-19 | 2026-01-19 | 3290 | 0% | deployment delayed |  |  | 96 |  | 2026-01-19 | 2026-01-19 | 0
3292 | 1.6 | 1.6.4.3 | P | Distributed computing needs | Started | 4 | 1141d | 2021-11-03 | 2026-03-31 |  | 58% |  |  |  | 45 |  | 2021-11-03 | 2026-03-31 | 0
3293 | 1.6 | 1.6.4.3.1 | C | Support Upgrade Distributed Mass Production - as designed | Complete | 5 | 60d | 2021-11-03 | 2022-01-25 |  | 100% |  |  |  | 1126 |  | 2021-11-03 | 2022-01-25 | 0
3294 | 1.6 | 1.6.4.3.2 | C | Prepare Distributed Mass Production for"As Built" Detector Verification | Not Started | 5 | 43d | 2026-01-30 | 2026-03-31 | 3079FS +10d | 0% | deployment delayed |  |  | 45 |  | 2026-01-30 | 2026-03-31 | 0
3295 | 1.6 | 1.6.5 | P | Upgrade String Commissioning | Not Started | 3 | 327d | 2025-01-01 | 2026-04-07 |  | 0% |  |  |  | 40 |  | 2025-01-01 | 2026-04-07 | 0
3296 | 1.6 | 1.6.5.0 | C | L3 Task Management | Not Started | 4 | 325d | 2025-01-01 | 2026-04-03 |  | 0% | dedicated L3 effort not needed until 2025 activities |  |  | 42 |  | 2025-01-01 | 2026-04-03 | 0
3297 | 1.6 | 1.6.5.1 | P | Upgrade OM module commissioning | Not Started | 4 | 261d | 2025-03-27 | 2026-03-31 |  | 0% |  |  |  | 45 |  | 2025-03-27 | 2026-03-31 | 0
3298 | 1.6 | 1.6.5.1.1 | C | Develop and review OM module commissioning plan | Not Started | 5 | 87d | 2025-03-27 | 2025-07-25 | 3151, 3076 | 0% |  |  |  | 88 |  | 2025-03-27 | 2025-07-25 | 0
3299 | 1.6 | 1.6.5.1.2 | C | Review OM module commissioning plan | Not Started | 5 | 0 | 2025-07-25 | 2025-07-25 | 3298 | 0% |  |  |  | 111 |  | 2025-07-25 | 2025-07-25 | 0
3300 | 1.6 | 1.6.5.1.3 | C | Develop software needed for OM commissioning | Not Started | 5 | 108d | 2025-07-28 | 2025-12-26 | 3299 | 0% |  |  |  | 111 |  | 2025-07-28 | 2025-12-26 | 0
3301 | 1.6 | 1.6.5.1.4 | C | Commission newly deployed OMs following deployment | Not Started | 5 | 83d | 2025-12-03 | 2026-03-31 | 1922SS -14d | 0% | need pred: + string deployment |  |  | -2841 |  | 2025-12-03 | 2026-03-31 | 0
3302 | 1.6 | 1.6.5.1.5 | C | Deliver commissioned OMs to detector operations team for integration | Not Started | 5 | 0 | 2026-03-31 | 2026-03-31 | 3301 | 0% |  |  |  | -2841 |  | 2026-03-31 | 2026-03-31 | 0
3303 | 1.6 | 1.6.5.2 | P | Upgrade calibration device commissioning | Not Started | 4 | 196d | 2025-07-03 | 2026-04-07 |  | 0% |  |  |  | 40 |  | 2025-07-03 | 2026-04-07 | 0
3304 | 1.6 | 1.6.5.2.1 | C | Develop and review calibration device commissioning plan | Not Started | 5 | 46d | 2025-07-03 | 2025-09-04 | 3298SS +70d | 0% |  |  |  | 105 |  | 2025-07-03 | 2025-09-04 | 0
3305 | 1.6 | 1.6.5.2.2 | C | Review calibration device commissioing plan | Not Started | 5 | 0 | 2025-09-04 | 2025-09-04 | 3304 | 0% |  |  |  | 105 |  | 2025-09-04 | 2025-09-04 | 0
3306 | 1.6 | 1.6.5.2.3 | C | Develop software needed for calibration device commissioning | Not Started | 5 | 85d | 2025-09-05 | 2026-01-06 | 3305 | 0% |  |  |  | 105 |  | 2025-09-05 | 2026-01-06 | 0
3307 | 1.6 | 1.6.5.2.4 | C | Commission newly deployed calibration devices following deployment | Not Started | 5 | 77d | 2025-12-18 | 2026-04-07 | 1922SS -3d | 0% | need pred: + string deployment |  |  | 0 | TRUE | 2025-12-18 | 2026-04-07 | 0
3308 | 1.6 | 1.6.5.2.5 | C | Deliver commissioned calibration devices to detector operations team for integration | Not Started | 5 | 0 | 2026-04-07 | 2026-04-07 | 3307 | 0% |  |  |  | 0 | TRUE | 2026-04-07 | 2026-04-07 | 0

## Comments
Row 2 | • Preliminary design review for the D-Egg electronics • Preliminary design reviews of the calibration interface and flasher circuits • Meetings with the photomultiplier tube vendors • A meeting between several Project Office personnel and ASC took place in Denver, CO on June 12. Discussion topics covered support costs for the Upgrade Project for all future seasons. Minutes of the meeting were sent to NSF. • Plan for baseline review for 2019 developed and discussed with Level 2 managers. | Catherine Vakhnina | 07/16/19 4:17 PM
Row 40 | • Drill Personnel: Position Vacancy Listings (PVL's) are in final review with UW-HR • Training: Draft agenda developed for safety/technical training (Aug 5-9) • Property Control: Generator custodianship approved. UNL equipment loan MOU's being discussed. • Support Planning: Detailed Planning Meeting (UW/ASC) held in Denver • Weekly Drill/Install Meetings: On-going • Generator-1: Overhaul Purchase Order with statement of work was submitted • Gen 2&3/PDM: Repair/support coordination meeting is scheduled with ASC and sub-contractor (July 16) in Madison • Test Bed: Water system/pumps set up, AB motor drive testing is continuing, heater is positioned and being integrated • Drill Heads: Calibration testing has begun • Control System: System evaluation and plan development, set-up and testing in test-bed is on-going • Drill Hose: System Engineer met with IVG (hose vendor); schedule, equipment, personnel, and materials confirmed • Independent Firn Drill: System evaluation and testing is underway • Site Plans: Final plans being coordinated with ASC • Installation: Continued coordination of procedures and plans with interfaces (DOM's, Cables, SD's) • DOM Handing Module: Evaluating design options as related to DOM sizes and testing requirements | Catherine Vakhnina | 07/16/19 4:18 PM
Row 174 | 1.2.2.1.2 MHP: Procure - "Heater stacks Furnace stacks y-stainer screens & gaskets, QA, marking, log tags, pack Final flush kit hardware/plumbing for integration Outdoor HEX to dissipate heat of 1x Model75 during test/flush (spec, buy, config) PRV - final determination, spare PRVs w/plumbing, or rebuild kits" | Ian McEwen | 02/23/22 9:37 AM
Row 178 | 1.2.2.1.7 HPU: Compile complete specs Incorporate as backup plan into P&ID Establish list of spare/integrate parts | Ian McEwen | 02/25/22 6:01 PM
Row 180 | 1.2.2.1.7 MHP: HPU plan - "Compile complete specs Incorporate as backup plan into P&ID Establish list of spare/integrate parts" | Ian McEwen | 02/23/22 9:39 AM
Row 183 | 1.2.2.2.1 PHS: Refine PHS plumbing - "Heaters - Review dP switch status Spec PRV Identify plumbing for new Lakos filters Flow balancing - design" | Ian McEwen | 02/23/22 9:40 AM
Row 184 | 1.2.2.2.2 PHS: Identify components - "Heaters - Rebuild outlet flow assemblies Heaters - Replace needle valves with larger Heaters - dP switches, replace as needed Procure, configure PRV Procure plumbing for new Lakos filters Flow balancing - procure, assemble, test" | Ian McEwen | 02/23/22 9:41 AM
Row 185 | 1.2.2.2.3 Control Boxes: Gray box status determine - may require FS1 field evaluation Reconfigure gray boxes, temp displays, DGHs, TS->Solo, etc. | Ian McEwen | 02/25/22 6:02 PM
Row 187 | 1.2.2.2.3 PHS: Control box upgrade - "Gray box status determine - may require FS1 field evaluation. Reconfigure gray boxes, temp displays, DGHs, TS->Solo, etc." | Ian McEwen | 02/23/22 9:42 AM
Row 190 | 1.2.2.3.2 Fuel Storage/Delivery - "Full listing of hoses, compare with inventory Hose and fittings restock MDS fuel solenoids, spares Come to agreement with ASC on 5k -> daytank fuel hoses and connections" | Ian McEwen | 02/23/22 9:43 AM
Row 204 | 1.2.3.1.3 Crescent & Belt Refurb: "Final fabrication work on crescent cable rollers Collect/assess//replace load cell hardware (phenolic blocks, etc)" | Ian McEwen | 02/25/22 6:03 PM
Row 212 | 1.2.3.1.8 TOS/Tower - Procure "Driller Tape" | Ian McEwen | 02/25/22 5:55 PM
Row 213 | 1.2.3.1.9 TOS/Tower - Procure "Driller Tape". Crescent refurb parts after eval in FS1 | Ian McEwen | 02/25/22 5:55 PM
Row 214 | 1.2.3.1.10 TOS/Tower: Procure "Driller Tape" | Ian McEwen | 02/25/22 5:56 PM
Row 234 | 1.2.3.3.7.1 Load Sharing: Create test plan, IV&T, layout study reference material reel motion control PCN mini-review" | Ian McEwen | 02/25/22 5:49 PM
Row 235 | 1.2.3.3.7.2 Load Sharing: System modeling PLC programming, HMI utility, SCADA configure drive and motor test carts | Ian McEwen | 02/25/22 5:50 PM
Row 236 | 1.2.3.3.7.3 Load Sharing: Reposition PSL crescent; install tower hoist, load cell, encoder remove wooden platform, install hose transition rig Sherman sheave with load cell and encoder PO10: swap motor, install encoder PO5: refurb, new motor, encoder Cabling: power, motor encoders, load cells, payout encoders Weight stack, victaulic adapters, yale grips, special rigging Position reels, 2x 40' hose sections, rope, cable configure: drives, plc calibrate load cells | Ian McEwen | 02/25/22 5:51 PM
Row 237 | 1.2.3.3.7.4 Load Sharing: Diameter correction test/tune load sharing | Ian McEwen | 02/25/22 5:52 PM
Row 238 | 1.2.3.3.7.5 Load Sharing: Test/tune load sharing | Ian McEwen | 02/25/22 5:53 PM
Row 240 | 1.2.3.3.9 Reels & Winches: MDCR sliprings (2x) - incl cold test RWCR sliprings (2x) | Ian McEwen | 02/25/22 6:09 PM
Row 241 | 1.2.3.3.10 Reels & Winches: Determine slip ring requirements and specs with install/xDOM teams Procure slip rings Configure and test slip rings | Ian McEwen | 02/25/22 6:10 PM
Row 242 | 1.2.3.3.11 Reels & Winches: Backup hand drill chucks and drill (RWCR & RWHR) TU20 brake controller rebuild/replace Capstan winches, assess and replace | Ian McEwen | 02/25/22 6:11 PM
Row 301 | 1.2.4.2.2 Sensors: "Legacy sensors - configure, test (40,40,0) Spec, (trial), procure, configure, test: Pressure sensors (16,0,21000) Venturi flow sensors(16,0,7500) Temp sensors (0,0,0) WT level sensors (60,0,2500) WT temp sensors (32,0,2000) Downhole level sensors (24,0,7500) Downhole temp sensors (24,0,7500) Overtemp switches (8,0,2500) Pressure switches (8,0,1000) Environmental sensors (32,0,3750) Payout encoders (PY4 1.2.4.3.2.2) Load cells (PY4 1.2.3.1.5) Turbine flow meters (0,0,0) dP heater switches (16,0,4000)" | Ian McEwen | 03/03/22 7:08 PM
Row 325 | 1.2.4.2.11.5 CS HW Production Main PLC: Redundant (2x) core PLC and chassis Local I/O Network switch Redundant UPS and Power Supplies mounted in box or rack mountable panel | Ian McEwen | 03/03/22 7:23 PM
Row 326 | 1.2.4.2.11.6 CS HW Build Mobile DCC: PLC chassis w/ small number of multipurpose I/O blocks Power supply Network switch RasPi for simple plotting/archiving functionality DIN-mounted in portable protective enclosure with connections Laptop to run HMI emulator screens Gateway? | Ian McEwen | 03/03/22 7:24 PM
Row 338 | 1.2.4.3.5 SCADA Monitoring Software - Configure hardware Collection of simple HMI test screens for each subsystem Sensor/variable mapping for test screen functionality | Ian McEwen | 03/04/22 5:57 PM
Row 340 | 1.2.4.3.7 CS SW Configure Mobile DCC Test System: Configure hardware Collection of simple HMI test screens for each subsystem. Sensor/variable mapping for test screen functionality. | Ian McEwen | 03/02/22 9:43 AM
Row 462 | 1.2.4.8.2.1.1 CS PHS HW: One drive needed | Ian McEwen | 02/23/22 9:06 AM
Row 469 | 1.2.4.8.2.3.1 CS PHS HW3: 8-port unmanaged switch | Ian McEwen | 02/23/22 9:07 AM
Row 471 | 1.2.4.8.2.3.3 CS PHS HW3: Network box uses AB Remote I/O instead of DGHs | Ian McEwen | 02/23/22 9:08 AM
Row 477 | 1.2.4.8.2.6.1 CS PHS HW6: One ultrasonic level sensor has been procured for testing | Ian McEwen | 02/23/22 9:10 AM
Row 499 | 1.2.4.8.4.1.1 CS TOS HW1: Additional drives, I/O cards required (no spares were ordered previously, some were installed in the test bed) | Ian McEwen | 02/23/22 9:12 AM
Row 500 | 1.2.4.8.4.1.2 CS TOS & Reels: AC power and control signal pigtail materials | Ian McEwen | 02/23/22 9:13 AM
Row 502 | 1.2.4.8.4.1.4 CS TOS & Reels: hardware needed for VFD installation | Ian McEwen | 02/23/22 9:14 AM
Row 505 | 1.2.4.8.4.2.1 CS TOS HW2: E-stop - Gen 1 drawings have mistakes, lack functional descriptions in many areas. Many updates required. Extensive review of proposed changes required | Ian McEwen | 02/23/22 9:16 AM
Row 506 | 1.2.4.8.4.2.2 CS TOS HW2: E-stop - Stop/Enable signal connections in Gen 1 broke electrical isolation between drives. To correct, new relays must be selected, connectorized pigtails must be designed and built | Ian McEwen | 02/23/22 9:17 AM
Row 507 | 1.2.4.8.4.2.3 CS TOS HW2: E-stop - Interconnecting cables must be found or rebuilt. Functional tests with the motor drive cart ensure that safety functions work as intended. | Ian McEwen | 02/23/22 9:18 AM
Row 509 | 1.2.4.8.4.2.5 CS TOS HW2: E-stop - Old E-stop controllers are unusable. New PCB design, new control switch configurations, new operating procedures. Mat'l: Circuit boards, industrial switches, MS connectors, enclosures | Ian McEwen | 02/23/22 9:19 AM
Row 512 | 1.2.4.8.4.3.1 CS TOS HW3: Network/PLC - 24V supplies in the network boxes power the E-stop system. Old power supplies not acceptable | Ian McEwen | 02/23/22 9:20 AM
Row 514 | 1.2.4.8.4.3.3 CS TOS HW3: E-stop - Industrial Ethernet cables, connectors | Ian McEwen | 02/23/22 9:21 AM
Row 515 | 1.2.4.8.4.3.4 CS TOS HW3: E-stop - Select PLC and I/O hardware, lay out enclosure design in CAD, generate BOM, develop a signal routing plan including I/O modules, cables, attached sensors | Ian McEwen | 02/23/22 9:22 AM
Row 516 | 1.2.4.8.4.3.4 CS TOS HW4: I/O Box - Consumable supplies | Ian McEwen | 02/23/22 9:24 AM
Row 528 | 1.2.4.8.4.7 CS TOS HW7: Tower payout - VFD Line filters were removed for SALSA, replace | Ian McEwen | 02/23/22 9:27 AM
Row 529 | 1.2.4.8.4.8 CS TOS HW7: Tower Payout - Tower hoist and control wiring were removed for SALSA | Ian McEwen | 02/23/22 9:28 AM
Row 574 | 1.2.4.8.7.1.1 CS HPP HW1: Motor Drives - One additional 50 HP drive needed | Ian McEwen | 02/23/22 9:30 AM
Row 575 | 1.2.4.8.7.1.2 CS HPP HW1: Motor Drives - Determine external inputs, design and signal pigtails. | Ian McEwen | 02/23/22 9:30 AM
Row 576 | 1.2.4.8.7.1.3 CS HPP HW1: Motor drive - Examine HPP photos, select conduit, wires, fittings, markers, tools; build connection prototypes, document procedures | Ian McEwen | 02/23/22 9:32 AM
Row 592 | 1.2.4.8.7.5.1 CS HPP HW5: Sensor box - gateway, box, power supply, terminals | Ian McEwen | 02/23/22 9:34 AM
Row 603 | 1.2.4.8.7.8.4 CS HPP HW8: Network box - 16 port unmanaged switch | Ian McEwen | 02/23/22 9:35 AM
Row 677 | 1.2.6.1.2 Procure WT Parts: "Vacuum breaker valves for submersible pumps (6x + spares) Penetration plumbing" | Ian McEwen | 02/26/22 11:54 AM
Row 678 | 1.2.6.1.3 Procure WT Parts (PY6): "WT1 return manifold: reconfigure and reassemble Submersible pump riser hose refit" | Ian McEwen | 02/26/22 11:55 AM
Row 682 | 1.2.6.2.3 Configure Pumps/Plumbing: "Transfer pumps: splice, plumbing, elec tests, pack Charge pumps: splice, plumbing, shrouds, elec tests, pack" | Ian McEwen | 02/26/22 11:56 AM
Row 685 | 1.2.6.2.5 Procure Pump Repair Components: "Procure materials for WT pump extension cables and connectors HPP cylinder linings and tooling" | Ian McEwen | 02/26/22 11:57 AM
Row 691 | 1.2.6.3.5 Procure Filtration Upgrades: Review bag filter inventory, supplement as needed | Ian McEwen | 02/27/22 10:35 AM
Row 693 | 1.2.6.3.7 Design Condensate System: Design baseline plan - dispose from inside PHS to empty ice well Condensate backup bulk storage/transport plan | Ian McEwen | 02/27/22 10:34 AM
Row 694 | 1.2.6.3.8 Procure Condensate System Components: Tank pump disposal hose reel disposal hose, disposal downhole assembly, disposal mechanical (load frame, plumbing, hardware, insulation, etc) disposal electrical (heat trace, hose reel motor control, etc) | Ian McEwen | 02/27/22 10:34 AM
Row 698 | 1.2.6.4.2 Identify/spec Interconnect Replacements: Finalize lengths and uses in P&ID | Ian McEwen | 02/27/22 10:32 AM
Row 699 | 1.2.6.4.3 Interconnect Procurements: Marwin ball valve repair kits Copper JIC gaskets | Ian McEwen | 02/27/22 10:31 AM
Row 700 | 1.2.6.4.4 Procure Heated Hose Materials | Ian McEwen | 02/27/22 10:30 AM
Row 702 | 1.2.6.4.6 Finalize Gen Water Loop Design: Evaluate and select flow control scheme (gensets and ARA) and components determine final design and components | Ian McEwen | 02/27/22 10:27 AM
Row 703 | 1.2.6.4.7 Gen Water Loop Procure/Assemble: Flowmeter, auto-proportion valve cabling filter config and bypass assemble and test, test control from CS | Ian McEwen | 02/27/22 10:26 AM
Row 704 | 1.2.6.4.8 Procure Hose Insulation: Procure camp and surface hose insulation (PY6) heated hose transformer skid, reconfigure/upgrade as needed - after FS1 eval | Ian McEwen | 02/27/22 10:25 AM
Row 712 | 1.2.6.6.1 Overall ARA System Redesign: Determine if 225m x 1"" hose is sufficient Determine if 225m x 12 AWG is ok for 10 HP Review pump circuit and elec distribution Review hose bundle situation Capture Stinger heater component specs and inventory - start with T3 Design and plan for main system tie-in Rodwell and condensate bulb strategy plans How to utilize ARA water tank and Water Buffalo at hole start, contingency water | Ian McEwen | 02/27/22 11:18 AM
Row 715 | 1.2.6.6.4 Specify Sensors: Spec downhole sensors (PT and TT) Spec surface sensors (flow) | Ian McEwen | 02/27/22 11:21 AM
Row 744 | 1.2.7.1.7 IFD Follow-up: IFD followup tasks (PY5): Locate water carrots for backup plan Build brake cable Assemble remaining DNF, etc. for shipment Prepare field documentation. | Ian McEwen | 02/27/22 6:55 PM
Row 915 | 1.2.8.5.4.4 Season kick-off tasking (FS1): Cleaning, configuring, and prepping for use. | Ian McEwen | 02/12/22 5:48 PM
Row 950 | 1.2.8.5.6.3.3.1. MHP 1 Refit (FS1): Flush heaters w epump to clean out debris, pressure test heaters with proof pump. | Ian McEwen | 02/12/22 5:58 PM
Row 951 | 1.2.8.5.6.3.3.1 MHP 1 Refit (FS1): Replace missing/damaged water hoses, re-install high temp cutoff switches, install condensate collection plumbing/tanks/pumps, install y-strainer flowmeter assemblies, replace MHP pressure relief valves, return supply and return hoses to drilling configuration | Ian McEwen | 02/12/22 5:59 PM
Row 952 | 1.2.8.5.6.3.3.1 MHP 1 Refit (FS1): Replace polycarb fuel tube MHP#1, replace missing fuel hoses, inspect and test fuel solenoid valves. | Ian McEwen | 02/12/22 5:59 PM
Row 953 | 1.2.8.5.6.3.3.1. MHP 1 Refit (FS1): Install furnace exhaust stack, install heater & exhaust stacks. | Ian McEwen | 02/12/22 5:59 PM
Row 967 | 1.2.8.5.6.3.4.1. MHP2 Refit (FS1): Flush heaters w epump to clean out debris, pressure test heaters with proof pump. | Ian McEwen | 02/12/22 6:00 PM
Row 968 | 1.2.8.5.6.3.4.1. MHP2 Refit (FS1): Replace missing/damaged water hoses, re-install high temp cutoff switches, install condensate collection plumbing/tanks/pumps, install y-strainer flowmeter assemblies, replace MHP pressure relief valves, return supply and return hoses to drilling configuration | Ian McEwen | 02/12/22 6:00 PM
Row 969 | 1.2.8.5.6.3.4.1. MHP2 Refit (FS1): Replace polycarb fuel tube MHP#1, replace missing fuel hoses, inspect and test fuel solenoid valves. | Ian McEwen | 02/12/22 6:07 PM
Row 970 | 1.2.8.5.6.3.4.1. MHP2 Refit (FS1): Install furnace exhaust stack & install heater exhaust stacks. | Ian McEwen | 02/12/22 6:00 PM
Row 973 | 1.8.5.6.3.3.2 MHP2 Controls -Add Serial-to-Ethernet gateway to existing network box -Refurbish all heater control assemblies at PSL -Minimal testing is expected for refurbished controls -Minimal testing is expected for refurbished sensors | Ian McEwen | 01/31/22 2:11 PM
Row 983 | 1.2.8.5.6.3.4.5.1 MHP3 Refit (FS1): Flush heaters w epump to clean out debris, pressure test heaters with proof pump. | Ian McEwen | 02/12/22 6:03 PM
Row 984 | 1.2.8.5.6.3.5.1 MHP3 Refit (FS1): Replace missing/damaged water hoses, re-install high temp cutoff switches, install condensate collection plumbing/tanks/pumps, install y-strainer flowmeter assemblies, replace MHP pressure relief valves, return supply and return hoses to drilling configuration | Ian McEwen | 02/12/22 6:03 PM
Row 985 | 1.2.8.5.6.3.5.1 MHP3 Refit (FS1): Replace polycarb fuel tube MHP#1, replace missing fuel hoses, inspect and test fuel solenoid valves. | Ian McEwen | 02/12/22 6:04 PM
Row 986 | 1.2.8.5.6.3.5.1 MHP3 Refit (FS1): Install furnace exhaust stack, install heater & exhaust stacks. | Ian McEwen | 02/12/22 6:09 PM
Row 989 | 1.2.8.5.6.3.5.2 MHP3 Controls: -Add Serial-to-Ethernet gateway to existing network box -Refurbish all heater control assemblies at PSL -Minimal testing is expected for refurbished controls -Minimal testing is expected for refurbished sensors | Ian McEwen | 01/31/22 2:14 PM
Row 999 | 1.2.8.5.6.3.6.1. MHP4 Refit (FS1): Flush heaters w epump to clean out debris, pressure test heaters with proof pump. | Ian McEwen | 02/12/22 6:06 PM
Row 1000 | 1.2.8.5.6.3.6.1 MHP4 Refit (FS1): Replace missing/damaged water hoses, re-install high temp cutoff switches, install condensate collection plumbing/tanks/pumps, install y-strainer flowmeter assemblies, replace MHP pressure relief valves, return supply and return hoses to drilling configuration | Ian McEwen | 02/12/22 6:06 PM
Row 1005 | 1.2.8.5.6.3.6.2 MHP4 Refit (FS1) - Controls: -Add Serial-to-Ethernet gateway to existing network box -Refurbish all heater control assemblies at PSL -Minimal testing is expected for refurbished controls -Minimal testing is expected for refurbished sensors | Ian McEwen | 01/31/22 2:15 PM
Row 1017 | 1.2.8.5.6.4.3.1. PHS Refit (FS1): Flush heaters w epump to clean out debris, pressure test heaters with proof pump. | Ian McEwen | 02/12/22 6:35 PM
Row 1018 | 1.2.8.5.6.4.3.1. PHS Refit (FS1): Evaluate and rebuild plumbing loop from Water Tank. | Ian McEwen | 02/12/22 6:35 PM
Row 1019 | 1.2.8.5.6.4.3.1. PHS Refit (FS1): Inspect and test fuel solenoid and fuel system. | Ian McEwen | 02/12/22 6:35 PM
Row 1020 | 1.2.8.5.6.4.3.1. PHS Refit (FS1): Install furnace exhaust stack, install heater & exhaust stack. | Ian McEwen | 02/12/22 6:36 PM
Row 1021 | 1.2.8.5.6.4.3.1. PHS Refit (FS1): Install condensate collection and disposal system. | Ian McEwen | 02/12/22 6:37 PM
Row 1022 | 1.2.8.5.6.4.3.1. PHS Refit (FS1): Install filtration system and plumbing. | Ian McEwen | 02/12/22 6:37 PM
Row 1025 | 1.2.8.5.6.4.2 PHS Refit Controls: -Motor drives run 3 external and 1 internal pump -Mechanical relay(s) will replace old SSR and diode array -Network box not serviceable, rebuild at PSL. -Heater DGH replacement torn off -Heaters must be tested with new controls -Test and document all new hardware and electrical functions -Tank sensors are missing or not functioning reliably | Ian McEwen | 01/31/22 2:07 PM
Row 1040 | 1.2.8.5.6.5.3.1. HPP Refit (FS1): Replace damaged/missing hoses, install pressure relief valves. | Ian McEwen | 02/12/22 6:37 PM
Row 1041 | 1.2.8.5.6.5.3.1. HPP Refit (FS1): Inspect and test fuel fuel solenoid and fuel system. | Ian McEwen | 02/12/22 6:38 PM
Row 1042 | 1.2.8.5.6.5.3.1. HPP Refit (FS1): Install furnace exhaust stack. | Ian McEwen | 02/12/22 6:39 PM
Row 1043 | 1.2.8.5.6.5.3.1. HPP Refit (FS1): Install and align belts, fill HPP oil. | Ian McEwen | 02/12/22 6:38 PM
Row 1046 | 1.2.8.5.6.5.3.1. HPP Refit (FS1) - Controls: -All motor drives being replaced -Drives in HPP can pre-configured to accept old sensor connections -New box required for local PLC and I/O module, ethernet switch -New soft-starts or drives compatible with PLC control -Sensor boxes stored years in ICL, is untested, may need work -DGH box has been upgraded with Modbus DGH modules -Gen-1 SSR and diode array need replacement HPP network box is not servicable, will be rebuilt at PSL -Test and document all new hardware and electrical functions | Ian McEwen | 01/31/22 2:05 PM
Row 1063 | 1.2.8.5.6.6.2.1.Water Tank Refit (FS1): Water Tank Modifications (Railings, Ladders, & Doghouses). | Ian McEwen | 02/12/22 6:37 PM
Row 1079 | 1.2.8.5.6.7.2.5 TOS Refit (FS1): Install furnace exhaust stack, inspect and test fuel fuel solenoid and fuel system, run furnace. | Ian McEwen | 02/12/22 6:39 PM
Row 1080 | 1.2.8.5.6.7.2.5 TOS Refit (FS1): Install furnace exhaust stack, inspect and test fuel fuel solenoid and fuel system, run furnace. | Ian McEwen | 02/12/22 6:40 PM
Row 1084 | 1.2.8.5.6.7.1.2 TOS1 Controls -New mechanical supports. Re-wire inputs and outputs. -Some changes to E-stop boxes anticipated. -Analysis needed to verify & update documentation. -Serial network to environmental sensors will be unchanged, others not used. -Grayhill I/O blocks are obsolete. Replace with units compatible with A-B drives and PLCs. -New wiring -SHR = Supply Hose Reel -Drill Cable Reel (DCR) will not be available this season to test DCR drives -8th motor drive, possibly new pendant (no I/O box? -I/O Box and pendant involved -Requires a motor and sensors connected through the RTW cable reel -New motor drive, use old pendants -Test and document all new hardware and electrical functions -New electronic hardware and wiring | Ian McEwen | 02/01/22 12:42 PM
Row 1127 | 1.2.8.5.6.8.2 RWHR (FS1): Install rebuilt Mico Disc Brake, change oil in brake and gearbox, heat trace and insulate plumbing. | Ian McEwen | 02/12/22 6:40 PM
Row 1129 | 1.2.8.5.6.8.2 RWHR (FS1): Replace Electric Drive Motor. | Ian McEwen | 02/12/22 6:41 PM
Row 1130 | 1.2.8.5.6.8.2 RWHR (FS1): Test operation with AB motor drive (not done during 19/20 season). | Ian McEwen | 02/12/22 6:41 PM
Row 1144 | 1.2.8.5.6.9.2 TU20 (FS1): TU20s - Install slip ring on #1, install new hydraulic hand pump on #2, upgrade hydraulic plumbing both, heat trace and insulate hydraulic plumbing both. | Ian McEwen | 02/12/22 6:41 PM
Row 1145 | 1.2.8.5.6.9.2 TU15 (FS1): Install new hydraulic hand pump, heat trace and insulate hydraulic plumbing, test operation with AB motor drive (not done during 19/20 season) | Ian McEwen | 02/12/22 6:41 PM
Row 1175 | 1.2.8.5.6.11.2.1 ARA Sled2: ePump and accessories (accumulator, gauges, local flow meter display, etc.) | Ian McEwen | 03/01/22 8:12 AM
Row 1176 | 1.2.8.5.6.11.2.3 ARA Sled 2: Checkout ePump and control, oil, belt tension, electrical connections, motor rotation, Top off glycol drum, Test and power up heat trace. | Ian McEwen | 03/01/22 8:14 AM
Row 1178 | 1.2.8.5.6.11.4.1 ARA Sled 3 Precommission: Warm up and inspect, reel, heaters, fuel system, mech and elec, MGO boards, DCC shelter. Install heater stacks, remove tape, install fire extinguisher. Install beam clamp and hoist. Top off fuel tank Test/repair hose reel brake, top off fluid. Insulate and heat trace additional as needed | Ian McEwen | 03/01/22 8:16 AM
Row 1179 | 1.2.8.5.6.11.4.2 ARA Sled 3 Precommission: Install new plumbing integation components onto heater skids Install new Hot Box hose reel plumbing manifold. Repair/replace hydraulic rotary union. | Ian McEwen | 03/01/22 8:18 AM
Row 1180 | 1.2.8.5.6.11.4.3 ARA Sled 3 Precommission: Install new readout components for CS tie-in into DCC (on bench) Reinstall DCC (DNF - requires power) | Ian McEwen | 03/01/22 8:19 AM
Row 1181 | 1.2.8.5.6.11.4.4 ARA Sled 3 Precommission: Remove used 225m hose bundle with TU15, evaluate first 120m off, make decision on retermination Install new 225m hose bundle or reterminated 120m hose bundle, pressure and electrical tests. | Ian McEwen | 03/01/22 8:21 AM
Row 1183 | 1.2.8.5.6.11.5.1 ARA Rodwell Drillhead Commissioning: Locate drillhead heating blankets Locate 5m extension hose. Drillhead inspection and prep on bench, sensor test | Ian McEwen | 03/01/22 8:22 AM
Row 1184 | 1.2.8.5.6.11.5.2 ARA Rodwell Drill Head Commissioning: Chain test both drillheads through reel, slipring, DCC. Verify motor direction Hang drillhead from bundle (fit test) | Ian McEwen | 03/01/22 8:23 AM
Row 1186 | 1.2.8.5.6.11.6.1 ARA System Commissioning: Decouple Sled 1 from Train Install test well More glycol, more fuel if needed Power up and readout tests, local Test all e-stop switch function, local | Ian McEwen | 03/01/22 8:36 AM
Row 1187 | 1.2.8.5.6.11.6.2 ARA System Commissioning: Verify brake release on motor power up, brake set on motor power down, estop, reel stop Verify correct rotation of both motors Test run of all motors Functionality test of drive modes and load share target Calibrate and verify load cells Calbirate and verify payout Test safeties (pendant disable, e-stop, local reel stop, load cell limit, rate limits Test all pendants | Ian McEwen | 03/01/22 8:37 AM
Row 1188 | 1.2.8.5.6.11.6.3 ARA System Commissioning: Glycol Validate charge pump rotation Circ 0 = ePump - return Circ 1 = ePump - Htrs - Hose reel - return Circ 2 = ePump - Htrs - Hose reel - bundle - return Look for leaks, fix e-stop test verify instrumentation (flows, pressures, etc) | Ian McEwen | 03/01/22 8:38 AM
Row 1189 | 1.2.8.5.6.11.6.4 ARA System Commissioning: WARM heaters check that stacks are clear Dry run to check power up and steady fuel pressure e-stop test wet run check safeties (flow, temp-DCC, temp-localTS) verify water tank temp sensor working clean y-strainers test tank level sensor (in glycol barrel) | Ian McEwen | 03/01/22 8:40 AM
Row 1190 | 1.2.8.5.6.11.6.5 ARA System Commissioning: use Mobile DCC as global system stand-in | Ian McEwen | 03/01/22 8:43 AM
Row 1191 | 1.2.8.5.6.11.6.6 System Testing in Test Well: Circulation with drillhead in contained closed-loop test well | Ian McEwen | 03/01/22 8:46 AM
Row 1205 | 1.2.8.5.7 SES Set-up: Build out SES as MDS work is completed at Cryo. Evaluate interconnects, mount cable trays | Ian McEwen | 02/12/22 6:42 PM
Row 1317 | Funds added to 1.2.8.5.3 1.2.8.5.3.17.1 $ 16,640 1.2.8.5.3.17.2 $ 16,640 1.2.8.5.3.17.3 $ 3,328 | Jim Lowe | 06/24/19 10:08 AM
Row 1535 | 1.2.8.7.8.2 Develop and Establish Rodwell (8gpm)(52hr ave drill duration) = 25k gal per hole makeup (25k)(7) = 175000 gal tot makeup (175k)/(0.6) = 292k gal after 40% permeation losses (292k)(2) = 583k hot H2O delivered vs. melted (583k)/(30gpm) = 13.5d when developing using 30 gpm through MHPs 13.5 -> 14 days | Ian McEwen | 02/13/22 11:17 AM
Row 2058 | • mDOM test-mainboard first articles delivered • mDOM DAQ chain test setup (PMT + high-voltage uBase + analog front-end test board incl. ADC) set up and started system characterization • mDOM PMT specifications submitted to and discussed with potential vendors • D-Egg Rev. 2 mainboard first articles delivered • D-Egg Rev. 4 high-voltage subsystem passed discharge tests | Catherine Vakhnina | 07/16/19 4:18 PM
Row 2637 | • Purchase order issued for Hexatronic main cable test assembly, production is scheduled for later this summer. Continued engagement with alternate main cable vendors. • Main cable length change request processed. • Purchase orders for penetrator cable assembly prototypes all issued, delivery schedule finalized. Discussion of international procurement process for production units well advanced. • Planning for surface cable option well advanced. Cargo requirements for surface cable deployment in 21/22 season established and communicated to ASC/AIL. Options for routing into ICL, in order of preference, agreed with ASC and reconnaissance of ICL east tower and 2nd floor rack space availability planned for 19/20 Pole season. Locations of surface junction boxes agreed, main cable and (pending reconnaissance) surface cable lengths determined. Discussion of surface cable and surface junction box engineering requirements begun. • Development of power supply distribution/control node underway. White Rabbit timing synchronization system development prototypes ordered. • NTS floor layout determined, required upgrades to power outlets (208 V) determined. GPS antenna unit received for testing. | Catherine Vakhnina | 07/16/19 4:18 PM
Row 2639 | Funds added to 1.4.1.1 1.4.1.1.5 $ 4,174 | Jim Lowe | 06/24/19 10:16 AM
Row 2641 | Funds added to 1.4.1.1.1 1.4.1.1.1.5 $ 5,115 1.4.1.1.1.6 $ 6,138 1.4.1.1.1.7 $ 6,138 1.4.1.1.1.8 $ 2,046 | Jim Lowe | 06/24/19 10:12 AM
Row 2902 | Funds added to 1.4.5.2 1.4.5.2.5 $ 1,023 1.4.5.2.6 $ 3,069 | Jim Lowe | 06/24/19 10:17 AM
Row 2918 | March 2020 report for 1.5 Multiple camera issues found and fixed for D-egg installation on March 6 (trial 1) and March 16 (trial 2) and March 23 (trial 3). 10 camera ring are in Chiba. Camera project is now fully funded. Purchasing plan in place to purchase as much hardware as possible as soon as possible to mitigate delays from COVID 19. 8 out of 9 cameras passed detailed FVT, the ninth was believed to have been damaged due to extensive shipping and handling. Test included functionality after long cold soak at -40C. No evidence of light leak from camera illumination LED. A solution has been determined for the issue where all the cameras must be enabled to communicate with any: current plan would be to disable 5V when switching camera in a camera run. Of the 50 D-eggs (100 D-egg halves) which have been produced, 12 have camera rings installed. A flasher testing plan and rig have been designed for mDOMs in Mainz, being adapted for D-eggs in Japan. Due to COVID-19 lockdowns, work on prototypes for acoustic and pencil beams has been delayed and these items will probably not be ready for preliminary design review until fall 2020. We should have a firm deadline for the FDR of the PencilBeam in March 2021 so that we can ship the first modules at the end of August 2021. Acoustic should be on a similar schedule. | Dawn Williams | 03/30/20 7:29 PM
Row 2918 | January 2020 report for 1.5 FAT planning workshop scheduled for Feb. 25 before the PAP meeting A production calibration database has been made and test scripts have been successfully run outside of Madison. Flashers: some tests have been done, the time profile and controllability of brightness near threshold are problems. Would be fixed by uniform layout. Awaiting results of other tests. Flashers can now be controlled with a Rev3 mainboard using the jumper. Cameras: three issues seen in testing. Mechanical: Holding ring failed shock test, and cables got disconnected during shock test. Electrical: all cameras must all be enabled in order to access any. All of these are under investigation Mini-mainboard: A schematic has been uploaded and is under discussion. Mainboard-mounted (slow control) calibration devices: I2C transactions occasionally time out on DEgg rev2 and rev3 boards. The magnetometer is the biggest offender with dozens of timeouts, the pressure sensor has a handful of timeouts, and the accelerometer has no timeouts to date. Mitigation measures are under discussion. | Dawn Williams | 01/31/20 7:36 PM
Row 2918 | Dec. 2019 report for 1.5: Flashers: 600 LEDs have been ordered and received at Chiba for D-egg mass production #1. DVT procedures for flasher boards were developed and are scheduled to be complete by early January. Since the flashers cannot be triggered by the ICM yet since the ICM is not available, a jumper has been implemented on the mainboard to switch between the ICM and the FPGA as the calibration trigger source. FPGA control is supported now through our entire software stack, will be tested at Madison soon. Cameras: Cameras were successfully integrated into D-egg on Dec. 18. DVT procedures for the camera were developed and the camera DVT is planned for January 9. An image was successfully captured from the camera through the calibration interface. PencilBeam and Acoustics: the review schedules for these devices will be finalized in February 2020. | Dawn Williams | 01/06/20 3:01 PM
Row 2918 | Nov. 2019 report for 1.5: Flashers: it was discovered that the LED order for mass production was not placed at Madison, but we have sufficient LEDs for D-egg DVT and are ordering LEDs for mass production. The Mainz group has agreed to oversee production of flasher boards for the mDOM. DVT procedures are being developed for the D-egg flasher board. Standalone devices: - POCAM team has followed up on action items from the October design review. These items involved finalizing some aspects of POCAM design and proposing an operational profile for the POCAM. - Common mini-mainboard for standalone calibration devices: Schematics have been finalized and a schedule for layout and prototype production is under discussion; it is currently expected that prototypes will be available for the POCAM, PencilBeam and Acoustic teams to test by the end of February 2020. Cameras: - The camera holding structure design has been revised based on the requests from NME following the visit of SKKU postdoc Christoph Toennis. - An order for the new camera holding structure design for the DVT has been placed and it is expected to be ready and delivered to NME before Dec 16th for the high pressure DVT - An order for 150 cameras has been placed with Arducam. The cameras are expected to arrive in early January. The main dedication of this order is for D-Egg Batch #1 mass production. - A batch of 30 cameras previously received from Arducam in September has completed basic testing at SKKU. - 3 cameras were shipped to UW Madison for electrical integration testing | Dawn Williams | 12/04/19 3:18 PM
Row 2918 | Oct. 2019 report for 1.5 -- Camera mounting solution was finalized for the D-egg. The camera will be mounted below the mainboard. -- Adhesive for D-egg LEDs has been tested at room temperature and -40 C. -- POCAM was successfully reviewed. Procurement of pressure vessels has begun. -- Work continues on mini-mainboard which will be used by standalone calibration devices. | Dawn Williams | 11/04/19 8:09 PM
Row 2918 | • 1.5.2.1 On-board LED Flashers: The Kapustinsky circuit has been selected as the common flasher circuit for all DOMs. The circuit has been laid out in the ring-shaped PCB for the D-egg. • 1.5.2.3 Camera and Light Detection: The camera and illumination board have been tested in a swimming pool. • 1.5.2.4 Acoustic Sensors: The options for acoustic sensors have been narrowed down to two: three acoustic sensors per mDOM, or acoustic sensors co-located with acoustic pingers. Final decision to be made by end of July. | Catherine Vakhnina | 07/16/19 4:19 PM
Row 3056 | *OCT 2021 update* ON PROJECT - Continued device software support for FAT and DVT testing of DEgg, mDOM and pDOM hardware, including: - initial support for pDOM devices - on-board camera interface debugging and improvements OFF PROJECT - Continued testing infrastructure support for FAT and DVT testing of DEgg, mDOM and pDOM hardware. - FieldHub software developement with SBC prototypes - continued development and testing for "As-designed" simulation data samples | Erik Blaufuss | 11/05/21 10:26 AM
Row 3056 | April 2020 Status update: - Continued progress on DEgg mainboard software for FAT testing - Refinement of FAT and DVT test database and display tools | Erik Blaufuss | 05/04/20 4:10 PM
Row 3056 | Mar 2020 Status Update - Continued DVT testing support for Rev4 DEgg mainboard at Chiba - DVT/FAT testing results DB and visualization tools prototype now in use - Continued development of software tools for FAT testing of DEggs | Erik Blaufuss | 04/03/20 2:44 PM
Row 3056 | Feb 2020 status update: - Supported DVT testing software for DEgg test modules through final design review -- Held DEgg FAT workshop - pushed FAT plan toward maturity. - Developing IceTray software framework extensions for IceCube Upgrade support. | Erik Blaufuss | 03/03/20 3:44 PM
Row 3056 | Jan 2019 status updates: - STF testing framework complete and in use for ongoing DVT D-Egg testing - Providing software support for DVT acitivities fpr D-Egg sensors. - Ongoing planning for D-Egg FAT activities and needed software | Erik Blaufuss | 02/04/20 1:28 PM
Row 3056 | Dec 2019 Status updates: - STF testing framework for DVT testing nearing completion for use in testing programs - Integration of Rev3 DEgg main boards into testing systems. - Support for all DEgg Mainboard components within MB software package. | Erik Blaufuss | 01/05/20 8:09 PM
Row 3056 | Nov 2019 Status updates: - Integration work of D-Egg Component devices with Mainboard control and readout software progressing well. Expect to have support for all on-board devices ready for testing suites by end of year - Preparations continue on DVT D-Egg software testing suite for Rev3 D-Egg mainboard and full device testing. | Erik Blaufuss | 12/03/19 1:37 PM
Row 3056 | Oct 2019 Status updates: - NTS computing environment setup and integration with the SPTS system at U-Wisconsin complete - D-Egg mainboard software development progressing with focus on integrating all D-Egg system components - Preparing integrated software testing suite for rev3 and production D-Egg mainboard design verification and testing | Erik Blaufuss | 11/04/19 12:43 PM
Row 3056 | • Developing software testing environment for first item DEgg mainboards • Developing optical module testing and verification plans for design verification and final acceptance testing phases • Evaluating IceCube analysis and simulation software for readiness to handle Upgrade sensors and calibration devices • We have first versions of the OM-DAQ interfaces that will reside within the OM on-board software and more advanced design work is underway to implement and test these with the first article DEgg electronic mainboards. | Catherine Vakhnina | 07/16/19 4:19 PM
Sheet | WBS 1.5 Update for October 2021 On project: WBS 1.5 L2 manager Dawn Williams began discussions on gathering calibration constants from mDOM and D-egg PMTs Off project: Cameras on mDOMs had a readout issue due to slow ramp-up of a voltage regulator. A software fix has been identified for this so that the camera firmware will not need to be reprogrammed. Mini-mainboard requirements discussions continue. | Dawn Williams | 11/05/21 6:40 PM
Sheet | May 2020 Updated 1.6: - Development of DEgg FAT testing software progressing, including: data collection software, database storage of results, and visualization tools in preparation for start of DEgg FAT testing this summer. - First version of interface definition between MCU and ICM software available. | Erik Blaufuss | 06/03/20 10:02 AM
Sheet | May 2020 report for 1.5 There is an issue with one of the flasher parts for the mDOM: the NTE2403 5 GHz wideband PNP transistor is a Critical component for flasher performance. The part is not currently available in Europe, cost is 3.10 USD / pc. in the US. Possible drop-in replacement is BFT92,215. This is a discontinued part, but 186,000 pcs. in stock at AVNET Europe at a cost of 0.158 EUR / pc. Would save 15 kEUR to the project but rely on a discontinued part and mean the electronics are not identical for D-egg and mDOM flashers since the NTE2403 is already procured for the D-egg. To evaluate the new part, the mDOM DVT PCB panel features 220 flashers but only 120 are needed for DVT mDOMs (incl. spares). We will populate the other 100 flashers on the panel assuming the BFT92 can be used as a direct drop-in-replacement for the NTE2403. These will then be tested in comparison to the default boards. Flasherboard testing (FLAT) electronics are assembled in a custom / easily accessible dark box. Cabling, software still being prepared. Electronics are being adapted for D-egg flasher testing. Integrating cameras into the batch 1 D-eggs before sealing is a potential issue since this was going to rely on people traveling from SKKU to Chiba, but there are still travel restrictions due to COVID 19 for the foreseeable future. We expect to have prototype of the mini-mainboard out in a couple of weeks for the POCAM, PencilBeam and Acoustic teams to evaluate. After that we will begin planning the Acoustic module review. The acoustic combined receiver/pinger module is being developed: acoustic sensors with variable gain between 50 dB and 70 dB at bandwidths up to 38 kHz. The positioning of the acoustic sensors was validated with a trilateration measurement in a swimming pool with an average deviation of 5 cm from the expected positions; acoustic positioning improves with chirp signal. For the POCAM, testing of all 8 Housings and ordering the remaining 22 housings is expected in June. By the end of the year, all boards should be ready, the first complete module should be ready, and the calibration setup will be ready for underwater isotropy measurement. A POCAM paper has been submitted to JINST. The Swedish camera was added to project geometry as part of updating the upgrade string design. Scope is currently at 5 cameras in the physics region of the detector. | Dawn Williams | 06/02/20 7:07 PM
Sheet | May 2020 status update for 1.4: * first iteration of ICM / MCU / SoC software/firmware interface defined with preliminary documentation available * initial version of power control interface software complete, can query and report status on power supply modules * schematic entry for the power control board, implemented as a BeagleBone Black single-board computer, underway | Tyce DeYoung | 06/01/20 3:09 PM
Sheet | February 2020 report for 1.5 FAT planning workshop : result of calibration discussion was that only basic functionality (on/off) can be tested in FAT, we need to do more detailed characterization on individual boards and a subset of fully characterized "golden" DOMs. Flashers: after further checks, the flashers appear to have the same intensity vs. DAC setting behavior when threshold corrected. A meeting is planned for the week of March 9 to discuss mDOM production plans for flashers and testing and charcaterization. Cameras: D-egg camera mount fixed and tested in Madison. Due to delay in camera mount testing and shipping of materials between US, South Korea and Japan, 30 D-eggs in production batch 1 will have cameras, 20 will not. Cameras may be backfilled when D-eggs are sealed in April or May. | Dawn Williams | 03/03/20 10:40 PM
Sheet | Oct. 2019 report for 1.5 -- Camera mounting solution was finalized for the D-egg. The camera will be mounted below the mainboard. -- Adhesive for D-egg LEDs has been tested at room temperature and -40 C. -- POCAM was successfully reviewed. Procurement of pressure vessels has begun. -- Work continues on mini-mainboard which will be used by standalone calibration devices. | Dawn Williams | 11/04/19 8:06 PM