## LogisticsReview11_2021
Last update 4/07/2022
ID | Recommendation | Responsible | Status | Estimated Date for closing | Notes
LR1 | Project team should perform their own schedule analysis using the 10 Best Practices for a high-quality and reliable schedule discussed in the GAO Schedule Assessment Guide (GAO-16-89G) for guidance and deliver their self-assessment to NSF at their next project review | Vivian O'Dell / Jim Lowe | closed | 2022-03-01 | Schedule cleanup performed to implement GAO best practice. | Schedule cleanup performed to implement GAO best practice.
LR2 | Produce graphic that shows all planning tools being used and how they feed and/or link with each other. Additionally, identify who is the single point of contact and/or manager for each planning tool and its roll-up destination. | Vivian O'Dell / Jim Lowe | closed | 2022-04-07 | Produced document that has all of this information | Produced document that has all of this information
LR3 | Consider mechanization of cable pulling operations up the ICL towers to reduce labor and potential for injury. | John Kelley/Delia Tosi | open |  | John and Delia will work with ASC for this. Needs to be resolved in time for year before deep drilling. (in principle year 2 in a 3 FS project | John and delia will work with ASC for this. Needs to be resolved in time for year before deep drilling. (in principle year 2 in a 3 FS project
LR4 | Research potential advantages of heating the cables in the area where they enter the ICL towers to make snaking them from the snow trench into ICL easier. | John Kelley | open |  | See above. Need a comprehensive plan for cable pulling with ASC. | See above. Need a comprehensive plan for cable pulling with ASC.
LR5 | Give serious consideration to splitting shipments of the two Conex vans of D-eggs into two carriers to reduce potential impacts of an accident with one. | Aya Ishihara, Ian McEwen | open |  | Will look into shipping separately | Will look into shipping separately
LR6 | Extend tolerance or recommended alternate location for GPR scan of proposed nine firn holes and cable trenches to CRREL and define the level of fidelity needed. | Delia Tosi | open | 2022-11-01 | Will provide plan to CRREL and survey crew by August 2022 That includes extended tolerance of hole placement and recommendations for alternate sites. | Will provide plan to CRREL and survey crew by August 2022 That includes extended tolerance of hole placement and recommendations for alternate sites.
LR7 | Planning should identity the schedule float that exists between the earliest and latest dates when deliverables must be ready to enter the USAP logistics system. Add a float column with conditional formatting (red, yellow, green; based on number of days) in the cargo spreadsheet. | Vivian O'Dell /Ian McEwen/Delia Tosi | closed | 2022-04-01 | Will be done in the IMS as well during IMS cleanup. | Float calculations are now included in the Cargo Master as Shipment Float & South Pole Float. Total time between Shipment and need by date at South Pole is calculated additionally.
LR8 | Include recording accelerometer in sample packaging for first available South Pole Traverse to get a sense of the potential for shock and vibration damage during shipment using the traverse. | Terry Benson | In progress | 2022-10-01 | Developing plans to include on a package for shipment in FY23 | Develed plans to include data loggers on 2 traverses (SPOT1 & SPOT2). Package shipments are in the FY23 cargo plan. Research into commercially available accelerometer loggers is underway.
LR9 | Activities planned for the same construction season should be prioritized before the start of the season to ensure resources are applied to the most critical activities should delays begin to be experienced. | Dar Gibson, Ian McEwen | Closed | 2022-01-20 | Field seasons activities have been prioritized and planned in detail for all three field seasons. They will be reviewed and further optimized prior to each field season. | Field seasons activities have been prioritized and planned in detail for all three field seasons. They will be reviewed and further optimized prior to each field season.
LR10 | Drilling activities in the schedule should be broken down into smaller duration activities to allow for better visibility of the entire drilling process and to allow planned efficiency when staff are expected to move from one hole to the next. | Dar Gibson, Terry Benson | Closed | 2022-01-20 | Drilling activites have been broken down. Relocation from hole to hole has also been inserted in the schedule | Drilling activites have been broken down into greater level of granularity. Relocation from hole to hole has also been inserted in the schedule
LR11 | Drilling activities should include some buffer time to allow for inefficiencies experienced at shift changes and mid-day breaks. | Dar Gibson, Terry Benson | Closed | 2022-01-20 | Buffer time has been built into the schedule by adding time between end of predecessor activity to start of successor activity | Buffer time has been built into the schedule by adding time between end of predecessor activity to start of successor activity
LR12 | The Excel spreadsheet that was provided as an output from Smartsheet showed that generic resources are applied for tasks occurring in the same time period. EN and TE are the two most common resource types. With multiple activities occurring during the same time frame that use EN and TE resources it is not possible to determine if the planned staffing is over or under allocated. This can be solved by creating unique resource names (SHFT1_ENG, SHFT1_DRL, SHFT1_HOS, SHFT2_ENG, SHFT2_DRL, etc.). This may provide for a better analysis of the resource loading and population planning. | Ian McEwen, Jim Lowe, Terry Benson, Dar Gibson | closed | 2022-04-01 | Will be done during schedule cleanup. | Resource tags have been expanded to allow for better visibility and analysis. Electrical Engineer (EN-EE), Mechancial Engineer (EN-ME), and Safety Engineer (EN-S) are now sorted in Smartsheet hours reports.
LR13 | The risk register should include both technical risks and programmatic risks. An analysis of the risk register should include looking for pairs of risks that are correlated (i.e., if Risk A happens, then the probability of Risk B increases). | Vivian O'Dell/Farshid Feyzi/Mike Duvernois/Mike Zernick | closed | 2021-03-07 | Risk Register includes both technical and programmatic risks. Risk workshop conducted with all L2s in January. Looking into correlated risks. | Risk Register includes both technical and programmatic risks. Risk workshop conducted with all L2s in January. Correlated risks have been identified and analyzed
NSFLR1 | Improve documentation overall; and including documentation pertaining to (1) on-site personnel needs and (2) spares especially in the context of risk assessment | Vivian O'Dell/Farshid Feyzi/Ian McEwen/Delia Tosi | In progress |  |  | Document updated are in progress. Safety and quality plans and risk mitigation plans are being revised. New documents for project management have been developed.
NSFLR2 | Consider risk mitigating scenarios within forthcoming logistical support guidance. Shallow drilling with the FS2 team, reducing the number of strings, or reducing the number of DOMs per string have been mentioned. | Mike DuVernois, Farshid Feyzi, Ian McEwen | closed | 2022-02-25 | Have studied the effects of reducing the number of strings in a scoping document. Have also worked with AIL on the logistics needs and availability. | Have studied the effects of reducing the number of strings in a scoping document. Have also worked with AIL on the logistics needs and availability.
NSFLR3 | Develop the software toolset to meet the requirements of an integrated master schedule including linkages and dependencies | Jim Lowe | closed | 2022-03-10 | Have made a new bottom up estimate of cost and schedule, including dependencies and linkages. | Have made a new bottom up estimate of cost and schedule, including dependencies and linkages.
NSFLR4 | Provide better visualization such as float associated with tasks and cargo | Jim Lowe, Ian McEwen, Delia Tosi | In progress | 2022-03-10 | Working on a good way to show this. | Float calculations are now included in the Cargo Master as Shipment Float & South Pole Float. Total time between Shipment and need by date at South Pole is calculated additionally.
NSFLR5 | Further develop the on-ice safety plan considering a safety lead at each drilling location | Mike Zernick | closed | 2022-03-02 | The plan has been developed, and will be presented during the reviews by MAZ. | The plan has been developed, and will be presented during the reviews by MAZ.
NSFLR6 | Refine quality control / assurance processes for packing/shipping | Ian McEwen, Delia Tosi, Mike Zernick | closed | 2022-04-01 | The IceCube Upgrade Logistics-Cargo Estimation and Planning procedure has been reivised to include Quality parameters for shipments. Further, a Pre-Shipping Quality Checklist has been developed. | Quality assurance process for packing and shipping are being updated and incorporated in the logistics plans.

## Sheet1
Status List
In progress
open
closed