## 1.2.5 Electrical Generation
Upgrade Cost Estimate
Name: | 1.2.5 Electrical Generation
Parent WBS: | 1.2 Implementation |  | MATERIALS ESTIMATE | [14 empty] | LABOR ESTIMATE | [6 empty] | TOTAL | SCHEDULE INPUT
Description of Scope:
Initials/Date: | BMB/3.4.2022 |  | Quantities | [6 empty] | Basis of Estimate (Select One, See Table Below) | [7 empty] | HOURS | [8 empty] | SCHEDULE LOGIC
WBS (if known) | Project Year (0-10) | Description | QTY | Spare | Total | Fabricate or Procure? | Procurement Details Manufacturer, Model, P/N, Vendor | Unit Price | Total Expected Price | C1 LOE Tasks | C2 Advanced | C3 Preliminary | C4 Conceptual | C5 Pre- Conceptual | C6 Rough Estimate | Cost Estimating Technique (See Table Below) | Materials Comments/Notes (procurement lead time, shipping restrictions, etc) | ENGR ($115/hr) | CAD ($81/hr) | SHOP ($77/hr) | STUDENT ($15/hr) | Total Hours | Total Hours Cost | Labor Comments/Schedule Inputs (eg. "March" or "After Microturbine running", etc) |  | Duration (Weeks) | Predecessors | Successors | Milestone | % of total | orig mat'l | orig labor | orig tot | delta | -436
1.2.5.1 |  | Generator 1 - COMPLETE | [27 empty] | 0
1.2.5.2 |  | Generators 2, 3, and PDM | [27 empty] | 0
1.2.5.2.6 | 5 | GEN-1, 2, 3 - Procure Batteries | 6 |  | 6 | P | CAT 9X9730 | 333.3333 | 2000 |  | x |  |  |  |  | C | https://parts.cat.com/en/fabick/9X-9730 | 8 |  |  |  | 8 | 920 |  | 2920 |  |  |  |  | 4.6173
1.2.5.2.7 | 5 | Generator 2 Subcontract Repairs in New Zealand | 1 |  | 1 | P |  | 14804 | 14804 |  | x |  |  |  |  | C | Round trip trucking (Bascik Transport) from USAP site to Terra Cat $345 NZD plus GST- $275 USD estimated. Terra Cat quoted repair of injection pump governor shaft and electronic controller - $5229.03 USD. Estimated $6500.00 USD for diagnosis/repair/testing of alternator output issue and $2800 for structural repair of the 20' ISO shipping container that houses the power plant. Terra Cat was not willing to quote without diagnosis of alternator/structural issues. Total $14,804.03 USD. | [7 empty] | 14804 |  |  |  |  | 23.4092 | 13700 | 0 | 13700 | 1104
1.2.5.2.8 | 5 | PDM - Procure Batteries | 2 |  | 2 | P | Interstate 34M-AGM | 300 | 600 |  | x |  |  |  |  | C | https://www.interstatebatteries.com/products/34m-agm | [7 empty] | 600 |  |  |  |  | 0.94877
1.2.5.2.9 | 6 | Develop SOW for South Pole Power Generation Technical Support Subcontract & Communicate with Vendor | [9 empty] | x |  |  |  | D |  | 40 |  |  |  | 40 | 4600 | expert opinion - work with subcontractor to get generator tech on drill team | 4600 |  |  |  |  | 7.2739
1.2.5.2.10 | 5/6 | Predeployment Coordination with Power Generation Technical Support Subcontract Vendor | [10 empty] | x |  |  | D |  | 80 |  |  |  | 80 | 9200 | expert opinion - initiate with subcontractor to get generator tech on drill team | 9200 |  |  |  |  | 14.5478
1.2.5.4 |  | System Electrical Distribution | [27 empty] | 0
1.2.5.4.3 | 5 | System Elec Dist: Design & Procure | [6 empty] | 5460 |  |  |  | x |  |  | D | appleton connectors. Use ACP1034 as basis of estimate. qty=12 x $455/ea = $5460. This link points to Appleton quote. | 20 |  |  |  | 20 | 2300 | procure, receive and organize | 7760 |  |  |  |  | 12.2707 | 7000 | 2300 | 9300 | -1540
1.2.5.4.5 | 5 | System Elec Dist: Build and Test Subcomponents | [10 empty] | x |  |  | D |  | 36 |  |  |  | 36 | 4140 | labor to connectorize 480 power cables in North | 4140 |  |  |  |  | 6.5465
1.2.5.4.8 | 6 | System Electrical Resupply (PY6) | [6 empty] | 5000 |  |  |  | x |  |  | D | annual resupply estimate for plugs, cabling, breakers, GFI outlets, lights, space heaters | 24 |  | 24 |  | 48 | 4608 | expert opinion | 9608 |  |  |  |  | 15.1929
1.2.5.4.10 | 7 | System Electrical Resupply (PY7) | [6 empty] | 5000 |  |  |  | x |  |  | D | annual resupply estimate for plugs, cabling, breakers, GFI outlets, lights, space heaters | 24 |  | 24 |  | 48 | 4608 | expert opinion | 9608 |  |  |  |  | 15.1929
0
0
[9 empty] | 32864 | Total Expected Materials Cost | [7 empty] | 232 | 0 | 48 | 0 | 280 | 30376 | Total Hours Cost | 63240
Schedule Logic Terms that can be used:
FS = Finish-to-Start
SS = Start-Start
FF = Finish-Finsh
SF = Start-to-Finish