## ChangeLog
Rev | Date | Author(s) | Comments | Cost Impact | Total Base Cost | Total Contingency Cost | Total Base + Contingency |  | base cost
- | 2022-05-24 | VO | Initial version from Smartsheet |  | 14731624.3968 | 3696326.4802 | 18427950.8771
1 | 2022-05-24 | VO |  | 0 | 14831624.4071 | 3596326.47 | 18427950.8771
2 | 2022-06-23 | VO |  | 0 | 14731624.3968 | 3696326.4802 | 18427950.8771
3 | 2022-07-11 | KH | Significant reformat of Master Database for readability and programmatic manipulation; Change budget: Finance -> L. Mercier; Remove PMCS; Add Dash360; Escalate M&S, Travel, Equipment; Add this ChangeLog; Update discrete risk 80%CL amount. | 1749144.391 | 16478393.776 | 3698701.492 | 20177095.268 | ??
4 | 2022-07-15 | KH | Dash360 indirect; correct salaries; update discrete risk 80%CL. | 1749144.391 | 16478393.776 | 3698701.492 | 20177095.268
4.1 | 2022-07-18 | KH | Fix discrete risk 80% CL and round to 2 sig figures | -34128.87 | 16478393.776 | 3664572.622 | 20142966.398
4.2 | 2022-07-21 | KH | Change discrete risk to 90% CL based on NSF comments; update BCA costs based on PDR 7/18/22; update PDOM FAT generic labor -> Wendt; update IDP winch generic labor -> Tosi | 798161.903 | 16719945.7192 | 4221182.5819 | 20941128.3011
4.3 | 2022-07-22 | KH | Risk CL is 80% to agree with final risk evaluation document as submitted and frozen for ICER | 540000 | 16719945.7192 | 4761182.5819 | 21481128.3011
4.4 | 2022-07-24 | VO | Rebalance risk across FY's | 0 | 16719945.7192 | 4761182.5819 | 21481128.3011
4.5 | 2022-08-03 | VO | Add in differences and explanations between versions | 0 | 16719945.7192 | 4761182.5819 | 21481128.3011
4.6 | 2022-08-23 | KH | Added all subaward 1030 long forms; Hanson --> Karle | -120688.5864 | 16604846.0986 | 4755593.616 | 21360439.7147
4.7 | 2022-08-29 | VO | Adjusted UMd rates according to Sullivan | -3633.2493 | 16601512.8424 | 4755293.623 | 21356806.4653
4.8 | 2022-09-14 | KH | Rectify MSU / PSU elements to reflect updated 1030s | 38.8459 | 16601510.8563 | 4755334.4549 | 21356845.3112
|  |  |  | Overall change | 1869886.4595 | 1059007.9747
Base Cost Changes
|  |  |  | Item |  | Base Cost
|  |  |  | PCMS Consulting |  | 2016298.26 |  | Add consulting company for enterprise tools
|  |  |  | PCMS Personnel |  | -417146.1322 |  | remove dedicated IceCube personnel
|  |  |  | Escalation on CapEx, M&S, Travel |  | 105123 |  | Added escalation of 2.15% starting in FY23 for all items, not just labor
|  |  |  | Additional f/w engineering |  | 163056 |  | Additional firmware engineering for xDOM / calibration work.
|  |  |  | BCA adjustment |  | 86110 |  | Re-evalulation of Breakout Cable Assembly CapEx costs
|  |  |  | BCA shipping adjustment |  | 22475 |  | Re-evalulation of Breakout Cable Assembly shipping costs
|  |  |  | named salary adjustments |  | 12405 |  | salary adjustments based on named personnel, general cleanup
|  |  |  | Total base Change |  | 1988321.1278

## Contingencies
Code | RangeL | RangeH | Midpoint
C1 | 3% | 15% | 9%
C2 | 5% | 20% | 12.5%
C3 | 10% | 30% | 20%
C4 | 20% | 50% | 35%
C5 | 40% | 60% | 50%
C6 | 60% | 80% | 70%

## BJ worksheet
End of PY4 | 18394122.3817
Total PY5-PY8 Base funds | 16601510.8563
Total PY5-PY8 Contingency | 4755334.4549
Total Award | 39750967.693
Original Cost (PY1-PY5) | 22983529
Delta | 16767438.693
(A) Senior Personnel | PY5 | PY6 | PY7 | PY8 | Total
A. Karle, PI : | 12907.674 | 13185.189 | 13468.6706 | 0 | 39561.5335
1.8 cal. Months total
F. Feyzi, PM | 178868.736 | 96432.6073 | 75175.5616 | 45015.904 | 395493.8089
25.99 cal. Months total
V. O’Dell, PD | 82520.856 | 70245.8787 | 63384.6125 | 29319.569 | 245471.9162
13.93 cal. Months total
Total Senior Personnel | 274297.266 | 179863.675 | 152029.8447 | 74336.473 | 680527.2587 | 680527.2587
(B) Other Personnel | PY5 | PY6 | PY7 | PY8 | Total
WBS 1.1 Personnel | 260445.9712 | 238872.9573 | 221434.7075 | 51514.8683 | 772268.5043
WBS 1.2 Personnel | 146327.4234 | 167459.914 | 180793.3032 | 129716.2824 | 624296.923
WBS 1.3 Personnel | 34812.2093 | 30014.1482 | 30659.4523 | 18269.2012 | 113755.0109
WBS 1.4 Personnel | 44420.949 | 27225.5996 | 0 | 10444.4432 | 82090.9918
WBS 1.5 Personnel | 29878.875 | 35863.0671 | 0 | 0 | 65741.9421
WBS 1.6 Personnel | 103882.8726 | 117306.0261 | 74005.2071 | 45450.3406 | 340644.4464
Total Other Personnel | 619768.3004 | 616741.7124 | 506892.6702 | 255395.1355 | 1998797.8185 | 1998797.8185
Total # of calendar months per year | 67.92 | 66.91 | 55.58 | 29.6 | 220.01
(C) Fringe Benefits | PY5 | PY6 | PY7 | PY8 | Total
(A+B) Total Salaries and Wages | 894065.5664 | 796605.3873 | 658921.5148 | 329730.6086 | 2679323.0772
(C ) Fringe Benefits | 312922.9482 | 278811.8856 | 230622.5302 | 115405.713 | 937763.077
(A+B+C) Total /w/ Fringe | 1206988.5147 | 1075417.2729 | 889544.045 | 445136.3216 | 3617086.1542 | 3617086.1542
(D) Capital Equipment | PY5 | PY6 | PY7 | PY8 | Total
Capital Equipment | 556542.8235 | 266989.6424 | 115321.4945 | 2177.6269 | 941031.5874
PSL Capitalized Labor | 1262830.3965 | 1224134.2604 | 1487959.8001 | 1392095.1997 | 5367019.6567
Total Capital Equipment | 1819373.22 | 1491123.9028 | 1603281.2946 | 1394272.8266 | 6308051.244 | 6308051.244
(E) Travel | PY5 | PY6 | PY7 | PY8 | Total
Domestic | 52709.4 | 59477.3483 | 74186.4095 | 1959.8642 | 188333.022
International | 42085.8 | 53842.6521 | 90174.8598 | 3919.7285 | 190023.0404
Total | 94795.2 | 113320.0004 | 164361.2693 | 5879.5927 | 378356.0624 | 378356.0624
| PY5 | PY6 | PY7 | PY8 | Total
Materials and Supplies | 120452.2155 | 68100.5203 | 78947.77 | 9037.1518 | 276537.6576
| PY5 | PY6 | PY7 | PY8 | Total
PMCS Services | 334896 | 343467 | 359152 | 280327 | 1317842
| PY5 | PY6 | PY7 | PY8 | Total
Michigan State University | 593417.0181 | 125361.874 | 110929.2608 | 63844.2109 | 893552.3637
Penn State University | 42311.617 | 30809.6577 | 31471.8296 | 18964.613 | 123557.7173
University of Alabama | 31519.5184 | 119511.6933 | 216037.52 | 98896.584 | 465965.3158
University of Maryland | 70728.4298 | 69347.2225 | 79735.093 | 38146.0027 | 257956.7481
Total | 737976.5832 | 345030.4476 | 438173.7034 | 219851.4105 | 1741032.1448 | 1741032.1448
| PY5 | PY6 | PY7 | PY8 | Total
Contingency - direct | 686374.294 | 1475537.3259 | 1482030.8962 | 248402.019 | 3892344.5352
I-Indirect | PY5 | PY6 | PY7 | PY8 | Total
Base - indirect | 931279.923 | 848161.5406 | 790762.6947 | 392401.435 | 2962605.5933
Contingency - indirect | 133258.0406 | 340353.1264 | 345186.2308 | 44192.5219 | 862989.9197
| PY5 | PY6 | PY7 | PY8 | Total
Total all | 6065393.991 | 6100511.1368 | 6151439.9042 | 3039500.2792 | 21356845.3112

## MSN203763 Info & Financials
Award Title | IceCube Upgrade_ EODEV
Reference Nbr | 1719277 - PHY
Sponsor | NATIONAL SCIENCE FOUNDATION
Flow-through Sponsor | 0
Award Type | Cooperative Agreement
Award Amount | 18318253
Start Date | 2018-10-01
End Date | 2023-09-30
Dept | 349300 ICECUBE RESEARCH*WIPAC
Solicitation RFP
CFDA | 47.049
RTC? | N
Status | Accepted
Primary PI | HANSON, KAEL D
Co-Investigator(s)
Description | IceCube Upgrade: An IceCube Extension for Precision Neutrino Physics and Astrophysics
Period: Inception - Aug 2022
Summary Level: 4
Account | Budget | MTD | Actuals | Encumbrances | Balance
EXPENSES
Expenses
Direct Expenses
Salaries | 0 | 61275.15 | 2845132.43 | 114509.15 | -3564903.92
Fringe Benefits | 0 | 22426.71 | 977636.03 | 41910.365 | -1241072.4
Equipment | 0 | 208232.87 | 7853530.79 | 781325.42 | -8116605.21
Supplies | 0 | 3388.26 | 276869.57 | 13373.59 | -290243.16
Domestic Travel | 0 | 2322.44 | 41513.4 | 0 | -41513.4
Foreign Travel | 0 | 0 | 114418.13 | 0 | -114418.13
Tuition and Fees | 0 | 0 | 3333.33 | 0 | -3333.33
Subagreements | 0 | 97331 | 2151246.12 | 505346.88 | -2591593
Other Expenditures | 0 | 3463.2 | 335524.4 | 94258.87 | -429783.27
[ZDIRECT] All Direct Costs Projbud | 16745480 | 0 | 0 | 0 | 16745480
Sales Credits
[9051] Sales Credits-External | 0 | 0 | -18983.41 | 0 | 18983.41
SUBTOTAL DIRECT AVAILABLE BALANCE | 16745480 | 398439.63 | 14580220.79 | 1550724.275 | 370997.59
TOTAL INDIRECT COSTS (F&A) | 1572773 | 48807.03 | 2123229.77 | 139947.5468 | -690404.3167 | 264051.975
TOTAL INCLUDING F&A | 18318253 | 447246.66 | 16703450.56 | 1690671.8217 | -75869.3818
Revenue (Non Sales Credit) |  |  | 16701216.28
LESS: Unbilled Accounts Receivable |  |  | 359108.53
LESS: Accounts Receivable |  |  | 0
TOTAL CALCULATED CASH RECEIVED |  |  | 16342107.75
314000
122550.3

## Info
Escalation Table | [5 empty] | Contingency Table
Type | PY4 | PY5 | PY6 | PY7 | PY8 | Contingency Category | PY5 | PY6 | PY7 | PY8 | Total
Labor Hours | 100% | 102.2% | 104.3% | 106.6% | 108.9% | EU Direct | 623102.7649 | 431836.8547 | 378953.4409 | 248402.019 | 1682295.0794
Travel | 100% | 102.2% | 104.3% | 106.6% | 108.9% | EU Indirect | 120974.0141 | 99609.1532 | 88263.6862 | 44192.5219 | 353039.3755
M & S | 100% | 102.2% | 104.3% | 106.6% | 108.9% | EU Direct % | 83.74% | 81.26% | 81.11% | 84.9%
CapEx | 100% | 102.2% | 104.3% | 106.6% | 108.9% | EU Indirect % | 16.26% | 18.74% | 18.89% | 15.1% |  | Total Discrete
Services | 100% | 100% | 100% | 100% | 100% | Discrete Risk Total | 75555.5556 | 1284444.4444 | 1360000 |  | 2720000 | 2720000
[6 empty] | Discrete Risk Direct | 63271.5291 | 1043700.4713 | 1103077.4554 | 0 | 2210049.4557
[6 empty] | Discrete Risk Indirect | 12284.0265 | 240743.9732 | 256922.5446 | 0 | 509950.5443
[6 empty] | Contingency Direct | 686374.294 | 1475537.3259 | 1482030.8962 | 248402.019 | 3892344.5352
[6 empty] | Contingency Indirect | 133258.0406 | 340353.1264 | 345186.2308 | 44192.5219 | 862989.9197 |  | 4755334.4549
Project Cost Overview
[7 empty] | PY5 | PY6 | PY7 | PY8 | TOTAL
[6 empty] | Base | 5245761.6564 | 4284620.6845 | 4324222.7772 | 2746905.7383 | 16601510.8563
[6 empty] | Base + Contingency | 6065393.991 | 6100511.1368 | 6151439.9042 | 3039500.2792 | 21356845.3112
[6 empty] | EU Fraction | 14.18% | 12.4% | 10.8% | 10.65% | 12.26%
[6 empty] | Discrete Fraction | 1.44% | 29.98% | 31.45% | 0% | 16.38%
[6 empty] | Total Contingency Fraction | 15.62% | 42.38% | 42.26% | 10.65% | 28.64%

## ByWBS
WBS |  | TOTAL |  |  |  | UW |  |  |  | MSU |  |  |  | PSU |  |  |  | UA |  |  |  | UMD
L2 | L3 | PY5 | PY6 | PY7 | PY8 | PY5 | PY6 | PY7 | PY8 | PY5 | PY6 | PY7 | PY8 | PY5 | PY6 | PY7 | PY8 | PY5 | PY6 | PY7 | PY8 | PY5 | PY6 | PY7 | PY8
1.1 | 1.1.1 | 681797.2136 | 489309.0597 | 434348.9315 | 189457.7261 | 649863.3064 | 456601.7236 | 400938.3877 | 169532.4118 | 0 | 0 | 0 | 0 | 16019.0482 | 16450.3076 | 16803.9892 | 11443.5166 | 0 | 0 | 0 | 0 | 15914.859 | 16257.0284 | 16606.5546 | 8481.7977
1.1 | 1.1.2 | 579901.1923 | 594466.294 | 619947.0224 | 476872.9889 | 579901.1923 | 594466.294 | 619947.0224 | 476872.9889 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1 | 1.1.3 | 173636.2498 | 139567.2426 | 142567.9383 | 30846.3839 | 173636.2498 | 139567.2426 | 142567.9383 | 30846.3839 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1 | 1.1.4 | 35874.348 | 18322.8232 | 14453.501 | 2867.8762 | 35874.348 | 18322.8232 | 14453.501 | 2867.8762 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1 | 1.1.5 | 260930.2434 | 266540.2436 | 229907.4867 | 24717.0214 | 260930.2434 | 266540.2436 | 229907.4867 | 24717.0214 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1 Total |  | 1732139.247 | 1508205.6631 | 1441224.8798 | 724761.9965 | 1700205.3399 | 1475498.327 | 1407814.3361 | 704836.6821 | 0 | 0 | 0 | 0 | 16019.0482 | 16450.3076 | 16803.9892 | 11443.5166 | 0 | 0 | 0 | 0 | 15914.859 | 16257.0284 | 16606.5546 | 8481.7977
1.2 | 1.2.1 | 771098.8651 | 648719.7898 | 660174.3443 | 280370.0595 | 771098.8651 | 648719.7898 | 660174.3443 | 280370.0595 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2 | 1.2.2 | 18074.421 | 78878.4419 | 0 | 0 | 18074.421 | 78878.4419 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2 | 1.2.3 | 60290.973 | 42846.6469 | 28429.5965 | 0 | 60290.973 | 42846.6469 | 28429.5965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2 | 1.2.4 | 869385.3705 | 152886.0019 | 90439.2022 | 4006.8336 | 869385.3705 | 152886.0019 | 90439.2022 | 4006.8336 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2 | 1.2.5 | 35572.716 | 19625.438 | 10241.1354 | 0 | 35572.716 | 19625.438 | 10241.1354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2 | 1.2.6 | 11440.8 | 47702.9202 | 0 | 0 | 11440.8 | 47702.9202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2 | 1.2.7 | 73443.807 | 43898.4569 | 38127.1245 | 10539.7144 | 73443.807 | 43898.4569 | 38127.1245 | 10539.7144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2 | 1.2.8 | 144474.831 | 806809.9875 | 1333605.9701 | 1323375.869 | 144474.831 | 806809.9875 | 1333605.9701 | 1323375.869 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2 | 1.2.9 | 148072.554 | 133846.9897 | 0 | 0 | 148072.554 | 133846.9897 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2 | 1.2.10 | 0 | 1516.6724 | 58627.6761 | 46907.9237 | 0 | 1516.6724 | 58627.6761 | 46907.9237 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2 Total |  | 2131854.3376 | 1976731.3452 | 2219645.0492 | 1665200.4002 | 2131854.3376 | 1976731.3452 | 2219645.0492 | 1665200.4002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3 | 1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3 | 1.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3 | 1.3.3 | 156912.9687 | 1596.4972 | 0 | 0 | 156912.9687 | 1596.4972 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3 | 1.3.4 | 54144.4655 | 61994.223 | 63327.0988 | 37735.035 | 54144.4655 | 61994.223 | 63327.0988 | 37735.035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3 | 1.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3 Total |  | 211057.4342 | 63590.7203 | 63327.0988 | 37735.035 | 211057.4342 | 63590.7203 | 63327.0988 | 37735.035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.4 | 1.4.1 | 511308.9137 | 69749.3472 | 8288.7857 | 57346.7165 | 0 | 0 | 0 | 0 | 511308.9137 | 69749.3472 | 8288.7857 | 57346.7165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.4 | 1.4.2 | 108993.7649 | 13807.9579 | 36385.9823 | 416.4712 | 70695.2579 | 6021.9557 | 815.411 | 416.4712 | 38298.507 | 7786.0023 | 35570.5713 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.4 | 1.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.4 | 1.4.4 | 111279.9444 | 70030.9467 | 23280.4628 | 28025.8504 | 111279.9444 | 67266.8674 | 2568.5445 | 24988.0608 | 0 | 2764.0793 | 20711.9183 | 3037.7896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.4 | 1.4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.4 | 1.4.6 | 43809.5973 | 45062.4452 | 46357.9854 | 3459.7048 | 0 | 0 | 0 | 0 | 43809.5973 | 45062.4452 | 46357.9854 | 3459.7048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.4 Total |  | 775392.2203 | 198650.6971 | 114313.2163 | 89248.7429 | 181975.2023 | 73288.8231 | 3383.9555 | 25404.532 | 593417.0181 | 125361.874 | 110929.2608 | 63844.2109 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.5 | 1.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.5 | 1.5.2 | 61714.8163 | 57788.2111 | 0 | 0 | 61714.8163 | 57788.2111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.5 | 1.5.3 | 0 | 116592.5643 | 194435.9384 | 95976.3863 | 0 | 24613.7827 | 6523.2877 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91978.7815 | 187912.6506 | 95976.3863 | 0 | 0 | 0 | 0
1.5 | 1.5.4 | 31519.5184 | 27532.9118 | 28124.8694 | 2920.1977 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31519.5184 | 27532.9118 | 28124.8694 | 2920.1977 | 0 | 0 | 0 | 0
1.5 Total |  | 93234.3347 | 201913.6872 | 222560.8078 | 98896.584 | 61714.8163 | 82401.9939 | 6523.2877 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31519.5184 | 119511.6933 | 216037.52 | 98896.584 | 0 | 0 | 0 | 0
1.6 | 1.6.0 | 54813.5708 | 57480.5615 | 60280.8634 | 24670.8164 | 0 | 4390.3674 | 4484.7603 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54813.5708 | 53090.1941 | 55796.1031 | 24670.8164
1.6 | 1.6.1 | 246489.0642 | 277249.7615 | 166821.0806 | 94921.8154 | 220196.4954 | 262890.4114 | 152153.2401 | 87400.7191 | 0 | 0 | 0 | 0 | 26292.5688 | 14359.3501 | 14667.8404 | 7521.0964 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.6 | 1.6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.6 | 1.6.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.6 | 1.6.4 | 781.4475 | 798.2486 | 28717.3459 | 6476.9593 | 781.4475 | 798.2486 | 28717.3459 | 6476.9593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.6 | 1.6.5 | 0 | 0 | 7332.4354 | 4993.3885 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7332.4354 | 4993.3885
1.6 Total |  | 302084.0825 | 335528.5717 | 263151.7253 | 131062.9797 | 220977.9429 | 268079.0275 | 185355.3464 | 93877.6784 | 0 | 0 | 0 | 0 | 26292.5688 | 14359.3501 | 14667.8404 | 7521.0964 | 0 | 0 | 0 | 0 | 54813.5708 | 53090.1941 | 63128.5385 | 29664.2049
Total Base |  | 5245761.6564 | 4284620.6845 | 4324222.7772 | 2746905.7383 | 4507785.0731 | 3939590.2369 | 3886049.0737 | 2527054.3277 | 593417.0181 | 125361.874 | 110929.2608 | 63844.2109 | 42311.617 | 30809.6577 | 31471.8296 | 18964.613 | 31519.5184 | 119511.6933 | 216037.52 | 98896.584 | 70728.4298 | 69347.2225 | 79735.093 | 38146.0027
Contingency |  | 819632.3346 | 1815890.4523 | 1827217.127 | 292594.5409
Total NSF |  | 6065393.991 | 6100511.1368 | 6151439.9042 | 3039500.2792 | 21356845.3112
Rev2 Budget
|  | PY5 | PY6 | PY7 | PY8
Total Base |  | 4806290.6414 | 3876967.0134 | 3792745.9104 | 2355620.8419 | 14831624.4071
Contingency |  | 1300997.64 | 1000079.3 | 1038378.83 | 256870.7 | 3596326.47
Total NSF |  | 6107288.2814 | 4877046.3134 | 4831124.7404 | 2612491.5419 | 18427950.8771
Δ
|  | PY5 | PY6 | PY7 | PY8
Total Base |  | 439471.015 | 407653.6711 | 531476.8668 | 391284.8964 |  | 16601510.8563
Contingency |  | -481365.3054 | 815811.1523 | 788838.297 | 35723.8409 |  | 4755334.4549
Total NSF |  | -41894.2904 | 1223464.8235 | 1320315.1638 | 427008.7373 | 2928894.4342
[6 empty] | 21356845.3112 | 21356845.3112 |  |  | 21376005.5047 |  | -19160.1935

## CostDatabase
WBS | L2 | L3 | Inst | Center | Schedule Task Name | Cost Activity | Resource Name | Type | Subtype | Resource ID | Estimating Technique | Labor Rate |  | Fringe | Indirect | On/Off Ice | ContCode | Estimate Uncertainty (EU) |  |  | Notes | PY5 | [30 empty] | PY6 | [30 empty] | PY7 | [30 empty] | PY8 | [30 empty] | Complete Total PY5-PY8
[12 empty] | Actual | Table |  |  |  |  | % | Amount | Indirect |  | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | PY5HR | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | PY5 Direct | PY5 Fringe | PY5 Indirect | PY5 Total | PY5 EU Direct | PY5 EU Indirect | 2023-10-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | 2024-07-01 | 2024-08-01 | 2024-09-01 | PY6HR | 2023-10-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | 2024-07-01 | 2024-08-01 | 2024-09-01 | PY6 Direct | PY6 Fringe | PY6 Indirect | PY6 Total | PY6 EU Direct | PY6 EU Indirect | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | PY7HR | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | PY7 Direct | PY7 Fringe | PY7 Indirect | PY7 Total | PY7 EU Direct | PY7 EU Indirect | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | PY8HR | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | PY8 Direct | PY8 Fringe | PY8 Indirect | PY8 Total | PY8 EU Direct | PY8 EU Indirect
1.1.1.1 | 1.1 | 1.1.1 | UW | WIPAC | Project Administration (B) | Project admin - principal investigator | Karle | Labor Hours | Labor - LoE | KE | A - Analogy | 140.4 | 121 | 35% | 53% | Off Ice | C1 | 9% | 7354.2913 | 2547.565 | [9 empty] | 45 | 45 |  |  | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6318 | 6318 | 0 | 0 | 12907.674 | 4517.6859 | 9235.4407 | 26660.8006 | 1568.2824 | 831.1897 | [8 empty] | 45 | 45 |  |  | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6318 | 6318 | 0 | 0 | 13185.189 | 4614.8161 | 9434.0027 | 27234.0079 | 1602.0005 | 849.0602 | [8 empty] | 45 | 45 |  |  | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6318 | 6318 | 0 | 0 | 13468.6706 | 4714.0347 | 9636.8338 | 27819.539 | 1636.4435 | 867.315 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81714.3475
1.1.1.1 | 1.1 | 1.1.1 | PSU |  | Project Administration (B) | Project admin - Doug Cowen | Cowen | Labor Hours | Labor - LoE | KE | A - Analogy | 120.005 | 116 | 36% | 59.86% | Off Ice | C1 | 9% | 1079.3728 | 404.174 |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 |  |  |  | 45 | 600.025 | 600.025 | 600.025 | 600.025 | 600.025 | 600.025 | 600.025 | 600.025 | 600.025 | 0 | 0 | 0 | 5516.3298 | 1985.8787 | 4490.8221 | 11993.0306 | 675.1988 | 404.174 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11993.0306
1.1.1.1 | 1.1 | 1.1.1 | PSU |  | Project Administration (B) | Project admin - Doug Cowen | Cowen | Labor Hours | Labor - LoE | KE | A - Analogy | 120 | 116 | 36% | 61% | Off Ice | C1 | 9% | 4385.1448 | 1661.4524 | [10 empty] | 5 | 5 | 5 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600 | 600 | 600 | 1838.7 | 661.932 | 1525.3855 | 4026.0175 | 225.0569 | 137.2847 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 60 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 7512.9282 | 2704.6542 | 6232.7252 | 16450.3076 | 919.5824 | 560.9453 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 60 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 7674.4562 | 2762.8042 | 6366.7288 | 16803.9892 | 939.3534 | 573.0056 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 |  |  |  |  | 40 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 0 | 0 | 0 | 0 | 5226.3046 | 1881.4697 | 4335.7423 | 11443.5166 | 639.6997 | 390.2168 | 48723.831
1.1.1.1 | 1.1 | 1.1.1 | UMD |  | Project Administration (B) | Project admin - Greg Sullivan | Sullivan | Labor Hours | Labor - LoE | KE | A - Analogy | 172.51 | 116 | 29.9% | 54.5% | Off Ice | C1 | 9% | 5153.4216 | 1817.8736 | Added by Erik B from UMD | 3.75 | 3.75 | 3.75 | 3.75 | 3.75 | 3.75 | 3.75 | 3.75 | 3.75 | 3.75 | 3.75 | 3.75 | 45 | 646.9125 | 646.9125 | 646.9125 | 646.9125 | 646.9125 | 646.9125 | 646.9125 | 646.9125 | 646.9125 | 646.9125 | 646.9125 | 646.9125 | 7929.8534 | 2371.0262 | 5613.9794 | 15914.859 | 927.0792 | 505.2581 | 3.75 | 3.75 | 3.75 | 3.75 | 3.75 | 3.75 | 3.75 | 3.75 | 3.75 | 3.75 | 3.75 | 3.75 | 45 | 646.9125 | 646.9125 | 646.9125 | 646.9125 | 646.9125 | 646.9125 | 646.9125 | 646.9125 | 646.9125 | 646.9125 | 646.9125 | 646.9125 | 8100.3453 | 2422.0032 | 5734.6799 | 16257.0284 | 947.0114 | 516.1212 | 3.75 | 3.75 | 3.75 | 3.75 | 3.75 | 3.75 | 3.75 | 3.75 | 3.75 | 3.75 | 3.75 | 3.75 | 45 | 646.9125 | 646.9125 | 646.9125 | 646.9125 | 646.9125 | 646.9125 | 646.9125 | 646.9125 | 646.9125 | 646.9125 | 646.9125 | 646.9125 | 8274.5027 | 2474.0763 | 5857.9756 | 16606.5546 | 967.3721 | 527.2178 | 3.75 | 3.75 | 3.75 | 3.75 | 3.75 | 3.75 | [6 empty] | 22.5 | 646.9125 | 646.9125 | 646.9125 | 646.9125 | 646.9125 | 646.9125 | 0 | 0 | 0 | 0 | 0 | 0 | 4226.2023 | 1263.6345 | 2991.961 | 8481.7977 | 494.0853 | 269.2765 | 57260.2397
1.1.1.1 | 1.1 | 1.1.1 | UW | WIPAC | Project Administration (B) | Project Director-ODell | ODell | Labor Hours | Labor - LoE | KE | A - Analogy | 112.2 | 121 | 35% | 53% | Off Ice | C1 | 9% | 45631.816 | 15807.0996 |  | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 720 | 6732 | 6732 | 6732 | 6732 | 6732 | 6732 | 6732 | 6732 | 6732 | 6732 | 6732 | 6732 | 82520.856 | 28882.2996 | 59043.6725 | 170446.8281 | 10026.284 | 5313.9305 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 600 | 5610 | 5610 | 5610 | 5610 | 5610 | 5610 | 5610 | 5610 | 5610 | 5610 | 5610 | 5610 | 70245.8787 | 24586.0575 | 50260.9262 | 145092.8624 | 8534.8743 | 4523.4834 | 50 | 50 | 50 | 50 | 50 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 530 | 5610 | 5610 | 5610 | 5610 | 5610 | 4488 | 4488 | 4488 | 4488 | 4488 | 4488 | 4488 | 63384.6125 | 22184.6144 | 45351.6902 | 130920.9171 | 7701.2304 | 4081.6521 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 |  |  |  |  | 240 | 3366 | 3366 | 3366 | 3366 | 3366 | 3366 | 3366 | 3366 | 0 | 0 | 0 | 0 | 29319.569 | 10261.8492 | 20978.1517 | 60559.5699 | 3562.3276 | 1888.0336 | 507020.1774
1.1.1.1 | 1.1 | 1.1.1 | UW | WIPAC | Project Administration (B) | Project manager-Feyzi | Feyzi | Labor Hours | Labor - LoE | KE | A - Analogy | 97.28 | 121 | 35% | 53% | Off Ice | C1 | 9% | 73520.1357 | 25467.7594 |  | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 1800 | 14592 | 14592 | 14592 | 14592 | 14592 | 14592 | 14592 | 14592 | 14592 | 14592 | 14592 | 14592 | 178868.736 | 62604.0576 | 127980.5806 | 369453.3742 | 21732.5514 | 11518.2523 | 100 | 100 | 0 | 0 | 50 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 950 | 9728 | 9728 | 0 | 0 | 4864 | 9728 | 9728 | 9728 | 9728 | 9728 | 9728 | 9728 | 96432.6073 | 33751.4126 | 68997.5305 | 199181.5504 | 11716.5618 | 6209.7777 | 75 | 75 | 0 | 0 | 50 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 725 | 7296 | 7296 | 0 | 0 | 4864 | 7296 | 7296 | 7296 | 7296 | 7296 | 7296 | 7296 | 75175.5616 | 26311.4466 | 53788.1144 | 155275.1226 | 9133.8307 | 4840.9303 | 75 | 75 | 0 | 0 | 50 | 75 | 75 | 75 |  |  |  |  | 425 | 7296 | 7296 | 0 | 0 | 4864 | 7296 | 7296 | 7296 | 0 | 0 | 0 | 0 | 45015.904 | 15755.5664 | 32208.8793 | 92980.3497 | 5469.4323 | 2898.7991 | 816890.3968
1.1.1.1 | 1.1 | 1.1.1 | UW | WIPAC | Project Administration (B) | Project Office M&S |  | M & S | M & S |  | E - Extrapolation from Actuals |  | 1 | 0% | 53% | Off Ice | C1 | 9% | 7851.7998 | 2719.9045 |  | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1200 | 0 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1200 | 15833.25 | 0 | 8391.6225 | 24224.8725 | 1424.9925 | 755.246 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1200 | 0 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1200 | 16173.6649 | 0 | 8572.0424 | 24745.7073 | 1455.6298 | 771.4838 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1200 | 0 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1200 | 16521.3987 | 0 | 8756.3413 | 25277.74 | 1486.9259 | 788.0707 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 0 | 0 |  |  |  |  | 0 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 0 | 0 | 0 | 0 | 0 | 0 | 8492.745 | 0 | 4501.1549 | 12993.8999 | 764.3471 | 405.1039 | 87242.2196
1.1.1.1 | 1.1 | 1.1.1 | UW | WIPAC | Project Administration (B) | Project Advisory Panel Reviews - Panel Members Compensation | Domestic | Travel | Travel |  | E - Extrapolation from Actuals |  | 1 | 0% | 53% | Off Ice | C1 | 9% | 5949.446 | 2060.9192 | 6-panel members (domestic travel), 3 require some form of payment ~$1,000 each |  |  |  |  | 13800 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 13800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14096.7 | 0 | 7471.251 | 21567.951 | 1268.703 | 672.4126 |  |  |  |  | 13800 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 13800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14399.7791 | 0 | 7631.8829 | 22031.6619 | 1295.9801 | 686.8695 | [5 empty] | 13800 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 13800 | 0 | 0 | 0 | 0 | 0 | 0 | 14709.3743 | 0 | 7795.9684 | 22505.3427 | 1323.8437 | 701.6372 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66104.9556
1.1.1.1 | 1.1 | 1.1.1 | UW | WIPAC | Project Administration (B) | PO-Travel | Domestic | Travel | Travel |  | E - Extrapolation from Actuals |  | 1 | 0% | 53% | Off Ice | C1 | 9% | 6477.9909 | 2244.0099 | [8 empty] | 14400 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14400 | 0 | 0 | 0 | 0 | 14709.6 | 0 | 7796.088 | 22505.688 | 1323.864 | 701.6479 | [7 empty] | 14400 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14400 | 0 | 0 | 0 | 0 | 15025.8564 | 0 | 7963.7039 | 22989.5603 | 1352.3271 | 716.7334 | [7 empty] | 14400 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14400 | 0 | 0 | 0 | 0 | 15348.9123 | 0 | 8134.9235 | 23483.8358 | 1381.4021 | 732.1431 | 1800 | [11 empty] | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1959.8642 | 0 | 1038.728 | 2998.5923 | 176.3878 | 93.4855 | 71977.6764
1.1.1.1 | 1.1 | 1.1.1 | UW | WIPAC | Project Administration (B) | PO-Travel | Foreign | Travel | Travel |  | E - Extrapolation from Actuals |  | 1 | 0% | 53% | Off Ice | C1 | 9% | 4138.745 | 1433.6829 | [8 empty] | 9600 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9600 | 0 | 0 | 0 | 0 | 9806.4 | 0 | 5197.392 | 15003.792 | 882.576 | 467.7653 | [7 empty] | 9600 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9600 | 0 | 0 | 0 | 0 | 10017.2376 | 0 | 5309.1359 | 15326.3735 | 901.5514 | 477.8222 | [7 empty] | 9600 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9600 | 0 | 0 | 0 | 0 | 10232.6082 | 0 | 5423.2824 | 15655.8906 | 920.9347 | 488.0954 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45986.0561
1.1.2.1 | 1.1 | 1.1.2 | UW | WIPAC | Project Controls and Finance (B) | Financial management - L. Mercier | Mercier | Labor Hours | Labor - LoE | MA | A - Analogy | 44.44 | 46 | 35% | 53% | Off Ice | C1 | 9% | 22940.0314 | 7946.5468 |  | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 720 | 2666.4 | 2666.4 | 2666.4 | 2666.4 | 2666.4 | 2666.4 | 2666.4 | 2666.4 | 2666.4 | 2666.4 | 2666.4 | 2666.4 | 32684.7312 | 11439.6559 | 23385.9252 | 67510.3123 | 3971.1948 | 2104.7333 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 720 | 2666.4 | 2666.4 | 2666.4 | 2666.4 | 2666.4 | 2666.4 | 2666.4 | 2666.4 | 2666.4 | 2666.4 | 2666.4 | 2666.4 | 33387.4529 | 11685.6085 | 23888.7226 | 68961.784 | 4056.5755 | 2149.985 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 720 | 2666.4 | 2666.4 | 2666.4 | 2666.4 | 2666.4 | 2666.4 | 2666.4 | 2666.4 | 2666.4 | 2666.4 | 2666.4 | 2666.4 | 34105.2832 | 11936.8491 | 24402.3301 | 70444.4624 | 4143.7919 | 2196.2097 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 |  |  |  |  | 480 | 2666.4 | 2666.4 | 2666.4 | 2666.4 | 2666.4 | 2666.4 | 2666.4 | 2666.4 | 0 | 0 | 0 | 0 | 23225.6978 | 8128.9942 | 16617.9868 | 47972.6789 | 2821.9223 | 1495.6188 | 254889.2375
1.1.2.1 | 1.1 | 1.1.2 | UW | WIPAC | Project Controls and Finance (B) | Project Controls - Dash360 consultants | PMCS Consulting | Services | Services |  | E - Extrapolation from Actuals |  | 1 | 0% | 53% | Off Ice | C1 | 9% | 181466.8434 | 62861.0634 | Dash360 service agreement (quotation McVeigh 6/23/2022) | 27908 | 27908 | 27908 | 27908 | 27908 | 27908 | 27908 | 27908 | 27908 | 27908 | 27908 | 27908 | 0 | 27908 | 27908 | 27908 | 27908 | 27908 | 27908 | 27908 | 27908 | 27908 | 27908 | 27908 | 27908 | 334896 | 0 | 177494.88 | 512390.88 | 30140.64 | 15974.5392 | 28622.25 | 28622.25 | 28622.25 | 28622.25 | 28622.25 | 28622.25 | 28622.25 | 28622.25 | 28622.25 | 28622.25 | 28622.25 | 28622.25 | 0 | 28622.25 | 28622.25 | 28622.25 | 28622.25 | 28622.25 | 28622.25 | 28622.25 | 28622.25 | 28622.25 | 28622.25 | 28622.25 | 28622.25 | 343467 | 0 | 182037.51 | 525504.51 | 30912.03 | 16383.3759 | 29929.3333 | 29929.3333 | 29929.3333 | 29929.3333 | 29929.3333 | 29929.3333 | 29929.3333 | 29929.3333 | 29929.3333 | 29929.3333 | 29929.3333 | 29929.3333 | 0 | 29929.3333 | 29929.3333 | 29929.3333 | 29929.3333 | 29929.3333 | 29929.3333 | 29929.3333 | 29929.3333 | 29929.3333 | 29929.3333 | 29929.3333 | 29929.3333 | 359152 | 0 | 190350.56 | 549502.56 | 32323.68 | 17131.5504 | 40046.7143 | 40046.7143 | 40046.7143 | 40046.7143 | 40046.7143 | 40046.7143 | 40046.7143 | [5 empty] | 0 | 40046.7143 | 40046.7143 | 40046.7143 | 40046.7143 | 40046.7143 | 40046.7143 | 40046.7143 | 0 | 0 | 0 | 0 | 0 | 280327 | 0 | 148573.31 | 428900.31 | 25229.43 | 13371.5979 | 2016298.26
1.1.3.1 | 1.1 | 1.1.3 | UW | WIPAC | Quality, Safety Management, Document Control Systems (B) | Q&A / Safety - Zernick | Zernick | Labor Hours | Labor - LoE | MA | A - Analogy | 60.69 | 46 | 35% | 53% | Off Ice | C1 | 9% | 43795.6033 | 15171.026 |  | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 1356 | 6857.97 | 6857.97 | 6857.97 | 6857.97 | 6857.97 | 6857.97 | 6857.97 | 6857.97 | 6857.97 | 6857.97 | 6857.97 | 6857.97 | 84064.9963 | 29422.7487 | 60148.5048 | 173636.2498 | 10213.897 | 5413.3654 | 113 | 113 | 0 | 0 | 50 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 1067 | 6857.97 | 6857.97 | 0 | 0 | 3034.5 | 6857.97 | 6857.97 | 6857.97 | 6857.97 | 6857.97 | 6857.97 | 6857.97 | 67570.6815 | 23649.7385 | 48346.8226 | 139567.2426 | 8209.8378 | 4351.214 | 113 | 113 | 0 | 0 | 50 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 1067 | 6857.97 | 6857.97 | 0 | 0 | 3034.5 | 6857.97 | 6857.97 | 6857.97 | 6857.97 | 6857.97 | 6857.97 | 6857.97 | 69023.4511 | 24158.2079 | 49386.2793 | 142567.9383 | 8386.3493 | 4444.7651 | 113 | 113 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 226 | 6857.97 | 6857.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14934.1002 | 5226.9351 | 10685.3487 | 30846.3839 | 1814.4932 | 961.6814 | 486617.8145
1.1.4.1 | 1.1 | 1.1.4 | UW | WIPAC | Logistics (B) | Logistics-Tosi | Tosi | Labor Hours | Labor - LoE | SC | A - Analogy | 47.23 | 52 | 35% | 53% | Off Ice | C1 | 9% | 6436.6694 | 2229.6959 | Tosi - 25% | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 360 | 1416.9 | 1416.9 | 1416.9 | 1416.9 | 1416.9 | 1416.9 | 1416.9 | 1416.9 | 1416.9 | 1416.9 | 1416.9 | 1416.9 | 17368.3602 | 6078.9261 | 12427.0617 | 35874.348 | 2110.2558 | 1118.4356 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 180 | 708.45 | 708.45 | 708.45 | 708.45 | 708.45 | 708.45 | 708.45 | 708.45 | 708.45 | 708.45 | 708.45 | 708.45 | 8870.89 | 3104.8115 | 6347.1218 | 18322.8232 | 1077.8131 | 571.241 | 14 | 14 | 5 | 0 | 8 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 139 | 661.22 | 661.22 | 236.15 | 0 | 377.84 | 661.22 | 661.22 | 661.22 | 661.22 | 661.22 | 661.22 | 661.22 | 6997.5798 | 2449.1529 | 5006.7683 | 14453.501 | 850.2059 | 450.6092 | 9 | 9 | 0 | 0 | 0 | 9 | 0 | 0 |  |  |  |  | 27 | 425.07 | 425.07 | 0 | 0 | 0 | 425.07 | 0 | 0 | 0 | 0 | 0 | 0 | 1388.4658 | 485.963 | 993.4473 | 2867.8762 | 168.6986 | 89.4103 | 71518.5484
1.1.5.1 | 1.1 | 1.1.5 | UW | WIPAC | Systems Engineering (B) | System Engineering-Sandstrom | Sandstrom | Labor Hours | Labor - LoE | SE | A - Analogy | 64.14 | 55 | 35% | 53% | Off Ice | C1 | 9% | 29784.4648 | 10317.4943 |  | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 900 | 4810.5 | 4810.5 | 4810.5 | 4810.5 | 4810.5 | 4810.5 | 4810.5 | 4810.5 | 4810.5 | 4810.5 | 4810.5 | 4810.5 | 58967.109 | 20638.4882 | 42190.9665 | 121796.5636 | 7164.5037 | 3797.187 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 900 | 4810.5 | 4810.5 | 4810.5 | 4810.5 | 4810.5 | 4810.5 | 4810.5 | 4810.5 | 4810.5 | 4810.5 | 4810.5 | 4810.5 | 60234.9018 | 21082.2156 | 43098.0723 | 124415.1898 | 7318.5406 | 3878.8265 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 600 | 3207 | 3207 | 3207 | 3207 | 3207 | 3207 | 3207 | 3207 | 3207 | 3207 | 3207 | 3207 | 41019.9682 | 14356.9889 | 29349.7872 | 84726.7442 | 4983.9261 | 2641.4808 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 330938.4976
1.1.5.1 | 1.1 | 1.1.5 | UW | WIPAC | Systems Engineering (B) | Technical Coordination-DuVernois | DuVernois | Labor Hours | Labor - LoE | SS | A - Analogy | 73.27 | 66 | 35% | 53% | Off Ice | C1 | 9% | 40604.0848 | 14065.4673 |  | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 900 | 5495.25 | 5495.25 | 5495.25 | 5495.25 | 5495.25 | 5495.25 | 5495.25 | 5495.25 | 5495.25 | 5495.25 | 5495.25 | 5495.25 | 67360.7745 | 23576.2711 | 48196.6342 | 139133.6797 | 8184.3341 | 4337.6971 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 900 | 5495.25 | 5495.25 | 5495.25 | 5495.25 | 5495.25 | 5495.25 | 5495.25 | 5495.25 | 5495.25 | 5495.25 | 5495.25 | 5495.25 | 68809.0312 | 24083.1609 | 49232.8618 | 142125.0538 | 8360.2973 | 4430.9576 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 900 | 5495.25 | 5495.25 | 5495.25 | 5495.25 | 5495.25 | 5495.25 | 5495.25 | 5495.25 | 5495.25 | 5495.25 | 5495.25 | 5495.25 | 70288.4253 | 24600.9489 | 50291.3683 | 145180.7425 | 8540.0437 | 4526.2231 | 75 | 75 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 150 | 5495.25 | 5495.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11966.6044 | 4188.3115 | 8562.1055 | 24717.0214 | 1453.9424 | 770.5895 | 451156.4975
1.2.1.1 | 1.2 | 1.2.1 | UW | WIPAC | Implementation Management and Controls | EHWD Project Management and Controls (WIPAC_Implementation_Manager) | McEwen | Labor Hours | Labor - LoE | SE | D - Expert Opinion | 60.69 | 55 | 35% | 53% | Off Ice | C1 | 9% | 76478.2042 | 26492.4498 |  | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 1800 | 9103.5 | 9103.5 | 9103.5 | 9103.5 | 9103.5 | 9103.5 | 9103.5 | 9103.5 | 9103.5 | 9103.5 | 9103.5 | 9103.5 | 111590.703 | 39056.7461 | 79843.148 | 230490.597 | 13558.2704 | 7185.8833 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 1800 | 9103.5 | 9103.5 | 9103.5 | 9103.5 | 9103.5 | 9103.5 | 9103.5 | 9103.5 | 9103.5 | 9103.5 | 9103.5 | 9103.5 | 113989.9031 | 39896.4661 | 81559.7757 | 235446.1449 | 13849.7732 | 7340.3798 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 1800 | 9103.5 | 9103.5 | 9103.5 | 9103.5 | 9103.5 | 9103.5 | 9103.5 | 9103.5 | 9103.5 | 9103.5 | 9103.5 | 9103.5 | 116440.686 | 40754.2401 | 83313.3109 | 240508.237 | 14147.5434 | 7498.198 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | [5 empty] | 1050 | 9103.5 | 9103.5 | 9103.5 | 9103.5 | 9103.5 | 9103.5 | 9103.5 | 0 | 0 | 0 | 0 | 0 | 69384.0938 | 24284.4328 | 49644.3191 | 143312.8457 | 8430.1674 | 4467.9887 | 849757.8246
1.2.1.2.5.1 | 1.2 | 1.2.1 | UW | PSL | 2022-23 Management & Systems Engineering | 2022-23 Systems Engineering (Terry Benson) | Benson | Labor Hours | Labor - Task | EN-ME | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C1 | 9% | 9515.2725 | 0 | Engineering oversight and systems development - coordination and planning, season planning, ASC interface, SIP, logistics coordination, drill procedures, EVMS, seasonal reports | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 900 | 8625 | 8625 | 8625 | 8625 | 8625 | 8625 | 8625 | 8625 | 8625 | 8625 | 8625 | 8625 | 105725.25 | 0 | 0 | 105725.25 | 9515.2725 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105725.25
1.2.1.2.5.1 | 1.2 | 1.2.1 | UW | PSL | 2022-23 Management & Systems Engineering | 2022-23 Management | Gibson | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C1 | 9% | 15224.436 | 0 | Drill Manager LOE: 0.8 FTE = 1440 hr/yr | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 1440 | 13800 | 13800 | 13800 | 13800 | 13800 | 13800 | 13800 | 13800 | 13800 | 13800 | 13800 | 13800 | 169160.4 | 0 | 0 | 169160.4 | 15224.436 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 169160.4
1.2.1.2.5.1 | 1.2 | 1.2.1 | UW | PSL | 2022-23 Management & Systems Engineering | 2022-23 Systems Engineering Support |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C1 | 9% | 4859.1325 | 0 | Team meetings - weekly status, reviews, collaboration mtgs, ASC weekly and annual Weekly status mtgs: 35 wks * 1 hr * 12 people = 420 hr ASC coord: 18 wks * 1 hr * 3 people = 78 hr Total = 558 hr | 38.3 | 38.3 | 38.3 | 38.3 | 38.3 | 38.3 | 38.3 | 38.3 | 38.3 | 38.3 | 38.3 | 38.3 | 459.6 | 4404.5 | 4404.5 | 4404.5 | 4404.5 | 4404.5 | 4404.5 | 4404.5 | 4404.5 | 4404.5 | 4404.5 | 4404.5 | 4404.5 | 53990.361 | 0 | 0 | 53990.361 | 4859.1325 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53990.361
1.2.1.2.5.2 | 1.2 | 1.2.1 | UW | PSL | Drill Procedure Review | Drill Procedure Review |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C2 | 12.5% | 4111.5375 | 0 | 1 hr session/wk * 35 wks each year 8 people = 280 hr/yr | [6 empty] | 46 | 47 | 47 | 47 | 47 | 46 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 5290 | 5405 | 5405 | 5405 | 5405 | 5290 | 32892.3 | 0 | 0 | 32892.3 | 4111.5375 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32892.3
1.2.1.2.5.3 | 1.2 | 1.2.1 | UW | PSL | Drill Hole Modeling | Drill Hole Modeling |  | Labor Hours | Labor - Task | EN-ME | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C2 | 12.5% | 1174.725 | 0 | Hole modeling = 120 hr/yr | [8 empty] | 40 | 40 |  |  | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4600 | 4600 | 0 | 0 | 9397.8 | 0 | 0 | 9397.8 | 1174.725 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9397.8
1.2.1.2.6.1 | 1.2 | 1.2.1 | UW | PSL | 2023-24 Management & Systems Engineering | 2023-24 Management & Systems Engineering | Benson | Labor Hours | Labor - Task | EN-ME | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C1 | 9% | 6473.4207 | 0 | Engineering oversight and systems development | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66.6 |  |  |  | 66.6 | 66.6 | 66.6 | 66.6 | 66.6 | 66.6 | 66.6 | 66.6 | 599.4 | 7659 | 0 | 0 | 0 | 7659 | 7659 | 7659 | 7659 | 7659 | 7659 | 7659 | 7659 | 71926.8964 | 0 | 0 | 71926.8964 | 6473.4207 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71926.8964
1.2.1.2.6.1 | 1.2 | 1.2.1 | UW | PSL | 2023-24 Management & Systems Engineering | 2023-24 Management | Gibson | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C1 | 9% | 10361.361 | 0 | Drill Manager LOE: 0.8 FTE = 1440 hr/yr | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106.6 |  |  |  | 106.6 | 106.6 | 106.6 | 106.6 | 106.6 | 106.6 | 106.6 | 106.6 | 959.4 | 12259 | 0 | 0 | 0 | 12259 | 12259 | 12259 | 12259 | 12259 | 12259 | 12259 | 12259 | 115126.2335 | 0 | 0 | 115126.2335 | 10361.361 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115126.2335
1.2.1.2.6.1 | 1.2 | 1.2.1 | UW | PSL | 2023-24 Management & Systems Engineering | 2023-24 Systems Engineering Support |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C1 | 9% | 3974.339 | 0 | Team meetings - weekly status, reviews, collaboration mtgs, ASC weekly and annual Weekly status mtgs: 35 wks * 1 hr * 12 people = 420 hr ASC coord: 18 wks * 1 hr * 3 people = 54 hr Total = 1914 hr | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 |  |  |  | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 368 | 4600 | 0 | 0 | 0 | 4715 | 4715 | 4715 | 4715 | 4715 | 4715 | 4715 | 4715 | 44159.3224 | 0 | 0 | 44159.3224 | 3974.339 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44159.3224
1.2.1.2.6.2 | 1.2 | 1.2.1 | UW | PSL | PY6 Season Debrief | PY6 Season Debrief |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C2 | 12.5% | 1799.9724 | 0 | Season Debrief - 30 people, hybrid, 4 hr = 120 hr | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 120 | [6 empty] | 120 | 0 | 0 | 0 | 0 | 0 | 13800 | 0 | 0 | 0 | 0 | 0 | 0 | 14399.7791 | 0 | 0 | 14399.7791 | 1799.9724 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14399.7791
1.2.1.2.6.3 | 1.2 | 1.2.1 | UW | PSL | Drill Procedure Review | Drill Procedure Review |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C2 | 12.5% | 3359.9484 | 0 | 1 hr session/wk * 35 wks each year 8 people = 280 hr/yr | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 37 | 37 | 38 | 38 | 37 | 37 | 224 | 0 | 0 | 0 | 0 | 0 | 0 | 4255 | 4255 | 4370 | 4370 | 4255 | 4255 | 26879.5876 | 0 | 0 | 26879.5876 | 3359.9484 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26879.5876
1.2.1.2.6.5 | 1.2 | 1.2.1 | UW | PSL | Drill Hole Modeling | Drill Hole Modeling |  | Labor Hours | Labor - Task | EN-ME | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C2 | 12.5% | 1199.9816 | 0 | Hole modeling = 120 hr/yr | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 40 | 40 |  |  | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4600 | 4600 | 0 | 0 | 9599.8527 | 0 | 0 | 9599.8527 | 1199.9816 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9599.8527
1.2.1.2.7.1 | 1.2 | 1.2.1 | UW | PSL | 2024-25 Management & Systems Engineering | 2024-25 Management & Systems Engineering | Benson | Labor Hours | Labor - Task | EN-ME | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C1 | 9% | 6612.5992 | 0 | System engineering oversight and systems development | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66.6 |  |  |  | 66.6 | 66.6 | 66.6 | 66.6 | 66.6 | 66.6 | 66.6 | 66.6 | 599.4 | 7659 | 0 | 0 | 0 | 7659 | 7659 | 7659 | 7659 | 7659 | 7659 | 7659 | 7659 | 73473.3246 | 0 | 0 | 73473.3246 | 6612.5992 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73473.3246
1.2.1.2.7.1 | 1.2 | 1.2.1 | UW | PSL | 2024-25 Management & Systems Engineering | 2024-25 Management | Gibson | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C1 | 9% | 10584.1303 | 0 | Drill Manager LOE: 0.8 FTE = 1440 hr/yr | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106.6 |  |  |  | 106.6 | 106.6 | 106.6 | 106.6 | 106.6 | 106.6 | 106.6 | 106.6 | 959.4 | 12259 | 0 | 0 | 0 | 12259 | 12259 | 12259 | 12259 | 12259 | 12259 | 12259 | 12259 | 117601.4475 | 0 | 0 | 117601.4475 | 10584.1303 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 117601.4475
1.2.1.2.7.1 | 1.2 | 1.2.1 | UW | PSL | 2024-25 Management & Systems Engineering | 2024-25 Systems Engineering Support |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C1 | 9% | 4059.7873 | 0 | Team meetings - weekly status, reviews, collaboration mtgs, ASC weekly and annual Weekly status mtgs: 35 wks * 1 hr * 12 people = 420 hr ASC coord: 18 wks * 1 hr * 3 people = 54 hr Total = 1914 hr | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 |  |  |  | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 368 | 4600 | 0 | 0 | 0 | 4715 | 4715 | 4715 | 4715 | 4715 | 4715 | 4715 | 4715 | 45108.7479 | 0 | 0 | 45108.7479 | 4059.7873 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45108.7479
1.2.1.2.7.2 | 1.2 | 1.2.1 | UW | PSL | PY7 Season Debrief | PY7 Season Debrief |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C2 | 12.5% | 1838.6718 | 0 | Season Debrief - 30 people, hybrid, 4 hr = 120 hr | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 120 | [6 empty] | 120 | 0 | 0 | 0 | 0 | 0 | 13800 | 0 | 0 | 0 | 0 | 0 | 0 | 14709.3743 | 0 | 0 | 14709.3743 | 1838.6718 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14709.3743
1.2.1.2.7.3 | 1.2 | 1.2.1 | UW | PSL | Drill Procedure Review | Drill Procedure Review |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C2 | 12.5% | 3432.1873 | 0 | 1 hr session/wk * 35 wks each year 8 people = 280 hr/yr | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 37 | 37 | 38 | 38 | 37 | 37 | 224 | 0 | 0 | 0 | 0 | 0 | 0 | 4255 | 4255 | 4370 | 4370 | 4255 | 4255 | 27457.4987 | 0 | 0 | 27457.4987 | 3432.1873 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27457.4987
1.2.1.2.7.5 | 1.2 | 1.2.1 | UW | PSL | Drill Hole Modeling | Drill Hole Modeling |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C2 | 12.5% | 1225.7812 | 0 | Hole modeling = 120 hr/yr | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 40 | 40 |  |  | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4600 | 4600 | 0 | 0 | 9806.2495 | 0 | 0 | 9806.2495 | 1225.7812 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9806.2495
1.2.1.2.7.6 | 1.2 | 1.2.1 | UW | PSL | Drill Readiness Review (PSL) | Drill Readiness Review (PSL) |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C2 | 12.5% | 2941.8749 | 0 | 12 Engineers 2 days @ 8 hrs = 192 hr | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 192 |  |  | 192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22080 | 0 | 0 | 23534.9989 | 0 | 0 | 23534.9989 | 2941.8749 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23534.9989
1.2.1.2.8.1 | 1.2 | 1.2.1 | UW | PSL | 2025-26 Management & Systems Engineering | 2025-26 Systems Engineering | Benson | Labor Hours | Labor - Task | EN-ME | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C1 | 9% | 3042.6892 | 0 | System Engineer - Oct (pre-deployment) & March/April for closeout. On-ice hours captured in Field Seasons. | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67.5 |  |  |  | 67.5 | 67.5 | 67.5 | [5 empty] | 270 | 7762.5 | 0 | 0 | 0 | 7762.5 | 7762.5 | 7762.5 | 0 | 0 | 0 | 0 | 0 | 33807.6582 | 0 | 0 | 33807.6582 | 3042.6892 | 0 | 33807.6582
1.2.1.2.8.1 | 1.2 | 1.2.1 | UW | PSL | 2025-26 Management & Systems Engineering | 2025-26 Management | Gibson | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C1 | 9% | 4056.919 | 0 | Drill Manager LOE: Oct (pre-deployment) & March/April for closeout. On-ice hours captured in Field Seasons. | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 |  |  |  |  | 120 | 120 | [5 empty] | 360 | 13800 | 0 | 0 | 0 | 0 | 13800 | 13800 | 0 | 0 | 0 | 0 | 0 | 45076.8775 | 0 | 0 | 45076.8775 | 4056.919 | 0 | 45076.8775
1.2.1.2.8.1 | 1.2 | 1.2.1 | UW | PSL | 2025-26 Management & Systems Engineering | 2025-26 Systems Engineering Support |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C1 | 9% | 2704.6127 | 0 | Engineering support hours for weekly status meeting & off-ice engineering support | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 |  |  |  |  | 100 | 100 | [5 empty] | 240 | 4600 | 0 | 0 | 0 | 0 | 11500 | 11500 | 0 | 0 | 0 | 0 | 0 | 30051.2517 | 0 | 0 | 30051.2517 | 2704.6127 | 0 | 30051.2517
1.2.1.2.8.2 | 1.2 | 1.2.1 | UW | PSL | PY8 Season Debrief | PY8 Season Debrief |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C2 | 12.5% | 1878.2032 | 0 | Season Debrief - 30 people, hybrid, 4 hr = 120 hr | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 120 | [6 empty] | 120 | 0 | 0 | 0 | 0 | 0 | 13800 | 0 | 0 | 0 | 0 | 0 | 0 | 15025.6258 | 0 | 0 | 15025.6258 | 1878.2032 | 0 | 15025.6258
1.2.1.3.2.1 | 1.2 | 1.2.1 | UW | WIPAC | String Management and Controls (2022-2023) | String Management and Controls (2022-2023) | Tosi | Labor Hours | Labor - LoE | SC | D - Expert Opinion | 47.23 | 52 | 35% | 53% | Off Ice | C1 | 9% | 2421.5185 | 838.8267 | Tosi - 15% | 22 | 22 | 22 | 22 | 23 | 23 | 23 | 23 | 22 | 22 | 23 | 23 | 270 | 1039.06 | 1039.06 | 1039.06 | 1039.06 | 1086.29 | 1086.29 | 1086.29 | 1086.29 | 1039.06 | 1039.06 | 1086.29 | 1086.29 | 13026.2702 | 4559.1946 | 9320.2963 | 26905.761 | 1582.6918 | 838.8267 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26905.761
1.2.1.3.2.2 | 1.2 | 1.2.1 | UW | WIPAC | Installation Engineering (2022-2023) | Installation Engineering (2022-2023) | Tosi | Labor Hours | Labor - LoE | SC | D - Expert Opinion | 47.23 | 52 | 35% | 53% | Off Ice | C1 | 9% | 4035.8641 | 1398.0444 | Tosi - 25% | 38 | 38 | 38 | 38 | 38 | 36 | 36 | 36 | 38 | 38 | 38 | 38 | 450 | 1794.74 | 1794.74 | 1794.74 | 1794.74 | 1794.74 | 1700.28 | 1700.28 | 1700.28 | 1794.74 | 1794.74 | 1794.74 | 1794.74 | 21710.4503 | 7598.6576 | 15533.8272 | 44842.935 | 2637.8197 | 1398.0444 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44842.935
1.2.1.3.2.3 | 1.2 | 1.2.1 | UW | PSL | Installation Engineering Support (2022-2023) | Installation Engineering Support (2022-2023) |  | Labor Hours | Labor - LoE | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C2 | 12.5% | 704.835 | 0 |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 48 | 460 | 460 | 460 | 460 | 460 | 460 | 460 | 460 | 460 | 460 | 460 | 460 | 5638.68 | 0 | 0 | 5638.68 | 704.835 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5638.68
1.2.1.3.3.1 | 1.2 | 1.2.1 | UW | WIPAC | String Management and Controls (2023-2024) | String Management and Controls (2023-2024) | Tosi | Labor Hours | Labor - LoE | SC | D - Expert Opinion | 47.23 | 52 | 35% | 53% | Off Ice | C1 | 9% | 1649.0541 | 571.241 | Tosi - 10% | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 180 | 708.45 | 708.45 | 708.45 | 708.45 | 708.45 | 708.45 | 708.45 | 708.45 | 708.45 | 708.45 | 708.45 | 708.45 | 8870.89 | 3104.8115 | 6347.1218 | 18322.8232 | 1077.8131 | 571.241 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18322.8232
1.2.1.3.3.2 | 1.2 | 1.2.1 | UW | WIPAC | Installation Engineering (2023-2024) | Installation Engineering (2023-2024) | Tosi | Labor Hours | Labor - LoE | SC | D - Expert Opinion | 47.23 | 52 | 35% | 53% | Off Ice | C1 | 9% | 4947.1623 | 1713.7229 | Tosi - 30% | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 540 | 2125.35 | 2125.35 | 2125.35 | 2125.35 | 2125.35 | 2125.35 | 2125.35 | 2125.35 | 2125.35 | 2125.35 | 2125.35 | 2125.35 | 26612.6699 | 9314.4345 | 19041.3653 | 54968.4697 | 3233.4394 | 1713.7229 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54968.4697
1.2.1.3.3.3 | 1.2 | 1.2.1 | UW | PSL | Installation Engineering Support (2023-2024) | Installation Engineering Support (2023-2024) |  | Labor Hours | Labor - LoE | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C2 | 12.5% | 719.989 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 48 | 460 | 460 | 460 | 460 | 460 | 460 | 460 | 460 | 460 | 460 | 460 | 460 | 5759.9116 | 0 | 0 | 5759.9116 | 719.989 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5759.9116
1.2.1.3.4.1 | 1.2 | 1.2.1 | UW | WIPAC | String Management and Controls (2024-2025) | String Management and Controls (2024-2025) | Tosi | Labor Hours | Labor - LoE | SC | D - Expert Opinion | 47.23 | 52 | 35% | 53% | Off Ice | C1 | 9% | 842.2544 | 291.7613 | Tosi - 5% | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 8 | 9 | 9 | 9 | 9 | 10 | 10 | 10 | 90 | 377.84 | 377.84 | 0 | 0 | 377.84 | 425.07 | 425.07 | 425.07 | 425.07 | 472.3 | 472.3 | 472.3 | 4530.8071 | 1585.7825 | 3241.7924 | 9358.382 | 550.4931 | 291.7613 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9358.382
1.2.1.3.4.2 | 1.2 | 1.2.1 | UW | WIPAC | Installation Engineering (2024-2025) | Installation Engineering (2024-2025) | Tosi | Labor Hours | Labor - LoE | SC | D - Expert Opinion | 47.23 | 52 | 35% | 53% | Off Ice | C1 | 9% | 4211.2719 | 1458.8066 | Tosi - 25% | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 0 | 0 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 450 | 2125.35 | 2125.35 | 0 | 0 | 2125.35 | 2125.35 | 2125.35 | 2125.35 | 2125.35 | 2125.35 | 2125.35 | 2125.35 | 22654.0353 | 7928.9123 | 16208.9622 | 46791.9098 | 2752.4653 | 1458.8066 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46791.9098
1.2.1.3.4.3 | 1.2 | 1.2.1 | UW | PSL | Installation Engineering Support (2024-2025) | Installation Engineering Support (2024-2025) |  | Labor Hours | Labor - LoE | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C2 | 12.5% | 674.1797 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 0 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 44 | 460 | 460 | 460 | 0 | 460 | 460 | 460 | 460 | 460 | 460 | 460 | 460 | 5393.4372 | 0 | 0 | 5393.4372 | 674.1797 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5393.4372
1.2.1.3.5.1 | 1.2 | 1.2.1 | UW | WIPAC | String Management and Controls (2025-2026) | String Management and Controls (2025-2026) | Tosi | Labor Hours | Labor - LoE | SC | D - Expert Opinion | 47.23 | 52 | 35% | 53% | Off Ice | C1 | 9% | 172.0726 | 59.6068 | Tosi - 5% | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 |  |  |  | 12 | [7 empty] | 18 | 283.38 | 0 | 0 | 0 | 566.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 925.6439 | 323.9754 | 662.2982 | 1911.9174 | 112.4657 | 59.6068 | 1911.9174
1.2.1.3.5.2 | 1.2 | 1.2.1 | UW | WIPAC | Installation Engineering (2025-2026) | Installation Engineering (2025-2026) | Tosi | Labor Hours | Labor - LoE | SC | D - Expert Opinion | 47.23 | 52 | 35% | 53% | Off Ice | C1 | 9% | 736.0882 | 254.9848 | Tosi - 20% | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 |  |  |  | 30 | 16 | 16 | [5 empty] | 77 | 708.45 | 0 | 0 | 0 | 1416.9 | 755.68 | 755.68 | 0 | 0 | 0 | 0 | 0 | 3959.6988 | 1385.8946 | 2833.1645 | 8178.7579 | 481.1034 | 254.9848 | 8178.7579
1.2.1.4.5 | 1.2 | 1.2.1 | UW | PSL | 2022-23 Quality & Safety | 2022-23 Quality & Safety HA Review |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C2 | 12.5% | 2114.505 | 0 | 12 sessions * 2 hr/session each year 6 people = 144 hr/yr | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 144 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 16916.04 | 0 | 0 | 16916.04 | 2114.505 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16916.04
1.2.1.4.6 | 1.2 | 1.2.1 | UW | PSL | 2023-24 Quality & Safety | 2023-24 Quality & Safety HA Review |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C2 | 12.5% | 2159.9669 | 0 | 12 sessions * 2 hr/session each year 6 people = 144 hr/yr | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 144 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 17279.7349 | 0 | 0 | 17279.7349 | 2159.9669 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17279.7349
1.2.1.4.7 | 1.2 | 1.2.1 | UW | PSL | 2024-25 Quality & Safety | 2025-25 Quality & Safety HA Review |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C2 | 12.5% | 2206.4061 | 0 | 12 sessions * 2 hr/session each year 6 people = 144 hr/yr | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 144 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 1380 | 17651.2492 | 0 | 0 | 17651.2492 | 2206.4061 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17651.2492
1.2.1.4.8 | 1.2 | 1.2.1 | UW | PSL | 2025-26 Quality & Safety | 2025-26 Quality & Safety HA Review |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C2 | 12.5% | 375.6406 | 0 | 2 sessions * 2 hr/session each year 6 people = 24 hr/yr October & November | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 12 | [10 empty] | 24 | 1380 | 1380 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3005.1252 | 0 | 0 | 3005.1252 | 375.6406 | 0 | 3005.1252
1.2.1.5.5 | 1.2 | 1.2.1 | UW | PSL | 2022-23 Travel (non-deployment) | 2022-23 Travel (non-deployment) | Domestic | Travel | Travel |  | E - Extrapolation from Actuals |  | 1 | 0% | 53% | Off Ice | C1 | 9% | 1772.3229 | 613.9419 | Collab Mtg (international): 1x $3600 ASC/Denver (domestic): 5x $1800 = $9k Total = 3.6k+9k = 12.6k | [5 empty] | 9000 | 3600 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 9000 | 3600 | 0 | 0 | 0 | 0 | 0 | 12870.9 | 0 | 6821.577 | 19692.477 | 1158.381 | 613.9419 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19692.477
1.2.1.5.6 | 1.2 | 1.2.1 | UW | PSL | 2023-24 Travel (non-deployment) | 2023-24 Travel (non-deployment) | Domestic | Travel | Travel |  | E - Extrapolation from Actuals |  | 1 | 0% | 53% | Off Ice | C1 | 9% | 1810.4279 | 627.1417 | Collab Mtg (international): 1x $3600 ASC/Denver (domestic): 5x $1800 = $9k Total = 3.6k+9k = 12.6k | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 9000 | 3600 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 9000 | 3600 | 0 | 0 | 0 | 0 | 0 | 13147.6244 | 0 | 6968.2409 | 20115.8653 | 1183.2862 | 627.1417 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20115.8653
1.2.1.5.7 | 1.2 | 1.2.1 | UW | PSL | 2024-25 Travel (non-deployment) | 2024-25 Travel (non-deployment) | Domestic | Travel | Travel |  | E - Extrapolation from Actuals |  | 1 | 0% | 53% | Off Ice | C1 | 9% | 1849.3521 | 640.6252 | Collab Mtg (international): 1x $3600 ASC/Denver (domestic): 5x $1800 = $9k Total = 3.6k+9k = 12.6k | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 9000 | 3600 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 9000 | 3600 | 0 | 0 | 0 | 0 | 0 | 13430.2983 | 0 | 7118.0581 | 20548.3564 | 1208.7268 | 640.6252 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20548.3564
1.2.1.6.2.11 | 1.2 | 1.2.1 | UW | PSL | Crate Control Systems Components Shipment 1 - DNF (Vessel) | Crate Control Systems Components Shipment 1 - DNF (Vessel) |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C2 | 12.5% | 234.945 | 0 |  | 16 | [11 empty] | 16 | 1840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 0 | 0 | 1879.56 | 234.945 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56
1.2.1.6.2.11 | 1.2 | 1.2.1 | UW | PSL | Crate Control Systems Components Shipment 1 - DNF (Vessel) | Crate Control Systems Components Shipment 1 - DNF (Vessel) |  | M & S | M & S |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C2 | 12.5% | 163.7133 | 56.7111 | Collapsible Bulk Container, Black, 48 inH x 45 inL x 41 inW, 1EA w/ lid $838 W.W. Grainger Item #36XE25 & #1XGG9 | 838 | [11 empty] | 0 | 838 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 856.017 | 0 | 453.689 | 1309.706 | 107.0021 | 56.7111 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1309.706
1.2.1.6.2.20 | 1.2 | 1.2.1 | UW | PSL | Load Container C (Main/Combo Cables, Bull Wheel, Hose Heating Components, ARA Drill Components - Crate 2) (Vessel) | Load Container C (Main/Combo Cables, Bull Wheel, Hose Heating Components, ARA Drill Components - Crate 2) (Vessel) |  | Labor Hours | Labor - Task | TE | D - Expert Opinion | 77 | 77 | 0% | 0% | Off Ice | C2 | 12.5% | 294.9581 | 0 |  | 30 | [11 empty] | 30 | 2310 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2359.665 | 0 | 0 | 2359.665 | 294.9581 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2359.665
1.2.1.6.2.20 | 1.2 | 1.2.1 | UW | PSL | Load Container C (Main/Combo Cables, Bull Wheel, Hose Heating Components, ARA Drill Components - Crate 2) (Vessel) | Load Container C (Main/Combo Cables, Bull Wheel, Hose Heating Components, ARA Drill Components - Crate 2) (Vessel) |  | M & S | M & S |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C2 | 12.5% | 1172.1713 | 406.0463 | $6000 estimated for 20' container purchase with delivery. PY3 container procurement was 6k. | 6000 | [11 empty] | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6129 | 0 | 3248.37 | 9377.37 | 766.125 | 406.0463 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9377.37
1.2.1.6.2.21 | 1.2 | 1.2.1 | UW | PSL | Crate Drill Heads, Spare Parts to PTH (Vessel) Store in ICL - DNF | Crate Drill Heads, Spare Parts to PTH (Vessel) Store in ICL - DNF |  | Labor Hours | Labor - Task | TE | D - Expert Opinion | 77 | 77 | 0% | 0% | Off Ice | C2 | 12.5% | 0 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.1.6.2.22 | 1.2 | 1.2.1 | UW | PSL | Crate Control Systems Components Shipment 2 - DNF (Comsur) | Crate Control Systems Components Shipment 2 - DNF (Comsur) |  | Labor Hours | Labor - Task | TE | D - Expert Opinion | 77 | 77 | 0% | 0% | Off Ice | C2 | 12.5% | 235.9665 | 0 | [9 empty] | 24 |  |  |  | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1848 | 0 | 0 | 0 | 1887.732 | 0 | 0 | 1887.732 | 235.9665 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1887.732
1.2.1.6.2.22 | 1.2 | 1.2.1 | UW | PSL | Crate Control Systems Components Shipment 2 - DNF (Comsur) | Crate Control Systems Components Shipment 2 - DNF (Comsur) |  | M & S | M & S |  | C - Engineering Buildup |  | 1 | 0% | 53% | Off Ice | C2 | 12.5% | 327.4265 | 113.4223 | Collapsible Bulk Container, Black, 48 inH x 45 inL x 41 inW, 1EA w/ lid $838 W.W. Grainger Item #36XE25 & #1XGG9 | [8 empty] | 1676 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1676 | 0 | 0 | 0 | 1712.034 | 0 | 907.378 | 2619.412 | 214.0043 | 113.4223 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2619.412
1.2.1.6.2.23 | 1.2 | 1.2.1 | UW | PSL | Crate Elect. Distribution System Components (ComSur) | Crate Elect. Distribution System Components (ComSur) |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C2 | 12.5% | 117.4725 | 0 | [10 empty] | 4 | 4 |  | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 460 | 460 | 0 | 939.78 | 0 | 0 | 939.78 | 117.4725 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78
1.2.1.6.2.24 | 1.2 | 1.2.1 | UW | PSL | Crate MDS Internal Hoses & Spares Resupply (FS2 Resupply Container - Comsur) | Crate MDS Internal Hoses & Spares Resupply (FS2 Resupply Container - Comsur) |  | Labor Hours | Labor - Task | TE | D - Expert Opinion | 77 | 77 | 0% | 0% | Off Ice | C2 | 12.5% | 80.3466 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 8 |  |  |  | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 616 | 0 | 0 | 0 | 642.7727 | 0 | 0 | 642.7727 | 80.3466 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 642.7727
1.2.1.6.2.25 | 1.2 | 1.2.1 | UW | PSL | Crate Drill Filtration Resupply (FS2 Resupply Container - Comsur) | Crate Drill Filtration Resupply (FS2 Resupply Container - Comsur) |  | Labor Hours | Labor - Task | TE | D - Expert Opinion | 77 | 77 | 0% | 0% | Off Ice | C2 | 12.5% | 80.3466 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 8 |  |  |  | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 616 | 0 | 0 | 0 | 642.7727 | 0 | 0 | 642.7727 | 80.3466 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 642.7727
1.2.1.6.2.26 | 1.2 | 1.2.1 | UW | PSL | Crate FS2 SES Interconnect Resupply (FS2 Resupply Container - Comsur) | Crate FS2 SES Interconnect Resupply (FS2 Resupply Container - Comsur) |  | Labor Hours | Labor - Task | TE | D - Expert Opinion | 77 | 77 | 0% | 0% | Off Ice | C2 | 12.5% | 80.3466 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 8 |  |  |  | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 616 | 0 | 0 | 0 | 642.7727 | 0 | 0 | 642.7727 | 80.3466 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 642.7727
1.2.1.6.2.28 | 1.2 | 1.2.1 | UW | PSL | Load FS2 Resupply Container (FS2 Comsur) | Load FS2 Resupply Container (Comsur) |  | Labor Hours | Labor - Task | TE | D - Expert Opinion | 77 | 77 | 0% | 0% | Off Ice | C2 | 12.5% | 160.6932 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 16 |  |  | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1232 | 0 | 0 | 1285.5455 | 0 | 0 | 1285.5455 | 160.6932 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1285.5455
1.2.1.6.2.29 | 1.2 | 1.2.1 | UW | PSL | Crate Repair/Replacement Components Resupply (FS2 Resupply Container - Comsur) | Crate Repair/Replacement Components Resupply (FS2 Resupply Container - Comsur) |  | Labor Hours | Labor - Task | TE | D - Expert Opinion | 77 | 77 | 0% | 0% | Off Ice | C2 | 12.5% | 80.3466 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 8 |  |  | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 616 | 0 | 0 | 642.7727 | 0 | 0 | 642.7727 | 80.3466 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 642.7727
1.2.1.6.2.30 | 1.2 | 1.2.1 | UW | PSL | Crate Control Systems Components Shipment 3 - DNF (Comsur) | Crate Control Systems Components Shipment 3 - DNF (Vessel) |  | Labor Hours | Labor - Task | TE | D - Expert Opinion | 77 | 77 | 0% | 0% | Off Ice | C2 | 12.5% | 164.1481 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 16 |  |  | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1232 | 0 | 0 | 1313.1847 | 0 | 0 | 1313.1847 | 164.1481 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1313.1847
1.2.1.6.3.1 | 1.2 | 1.2.1 | UW | PSL | FS0 - Ship Control Systems Components Shipment 1, ARA System DNF, Drill Heads, & Container C (Vessel) | FS0 - Ship Control Systems Components Shipment 1, ARA System Parts, Drill Heads, & Container C (Vessel) |  | M & S | M & S |  | E - Extrapolation from Actuals |  | 1 | 0% | 53% | Off Ice | C2 | 12.5% | 781.4475 | 270.6975 | Estimated based on November 2021 trucking invoice (SEKO) - October '22 is a full 53' trailer load | 4000 | [11 empty] | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4086 | 0 | 2165.58 | 6251.58 | 510.75 | 270.6975 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6251.58
1.2.1.6.3.1 | 1.2 | 1.2.1 | UW | PSL | FS0 - Ship Control Systems Components Shipment 1, ARA System DNF, Drill Heads, & Container C (Vessel) | FS0 - Ship Control Systems Components Shipment 1, ARA System Parts, Drill Heads, & Container C (Vessel) |  | M & S | M & S |  | E - Extrapolation from Actuals |  | 1 | 0% | 53% | Off Ice | C2 | 12.5% | 195.3619 | 67.6744 | Estimated based on 2021 Reynolds & Reynolds loading support invoice | 1000 | [11 empty] | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1021.5 | 0 | 541.395 | 1562.895 | 127.6875 | 67.6744 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1562.895
1.2.1.6.3.2 | 1.2 | 1.2.1 | UW | PSL | FS1 - Ship Control Systems Components Shipment 2 - DNF (Comsur) | FS1 - Ship Control Systems Components Shipment 2 - DNF (Comsur) |  | M & S | M & S |  | E - Extrapolation from Actuals |  | 1 | 0% | 53% | Off Ice | C2 | 12.5% | 683.7666 | 236.8603 | Estimated based on November 2021 trucking invoice (SEKO) - August '23 is a partial truck load | [10 empty] | 3500 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3500 | 0 | 3575.25 | 0 | 1894.8825 | 5470.1325 | 446.9063 | 236.8603 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5470.1325
1.2.1.6.3.3 | 1.2 | 1.2.1 | UW | PSL | FS2 - Ship Control Systems Components Shipment 3, Refit Resupply Container (Comsur) | FS2 - Ship Control Systems Components Shipment 3, Resupply Container (Comsur) |  | M & S | M & S |  | E - Extrapolation from Actuals |  | 1 | 0% | 53% | Off Ice | C2 | 12.5% | 498.9054 | 172.8234 | Estimated based on November 2021 trucking invoice (SEKO) - August '24 is a quarter truck load | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 2500 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 0 | 2608.6556 | 0 | 1382.5875 | 3991.2431 | 326.082 | 172.8234 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3991.2431
1.2.1.6.3.4 | 1.2 | 1.2.1 | UW | PSL | FS3 - Ship Resupply Container (Comsur) | FS3 - Ship Resupply Container (Comsur) |  | M & S | M & S |  | E - Extrapolation from Actuals |  | 1 | 0% | 53% | Off Ice | C2 | 12.5% | 509.6319 | 176.5391 | Estimated based on November 2021 trucking invoice (SEKO) - August '25 is a quarter truck load | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 2500 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 0 | 2664.7417 | 0 | 1412.3131 | 4077.0548 | 333.0927 | 176.5391 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4077.0548
1.2.1.6.4.1 | 1.2 | 1.2.1 | UW | PSL | Crate Sensor Handling Structure | Crate (Installation): Sensor Handling Structure (Vessel) |  | M & S | M & S |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C2 | 12.5% | 586.0856 | 203.0231 |  | 3000 | [11 empty] | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3064.5 | 0 | 1624.185 | 4688.685 | 383.0625 | 203.0231 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4688.685
1.2.1.6.4.2 | 1.2 | 1.2.1 | UW | PSL | Crate Installation Kits | Crate (Installation): Installation Kits (Vessel) |  | Labor Hours | Labor - Task | TE | D - Expert Opinion | 77 | 77 | 0% | 0% | Off Ice | C2 | 12.5% | 314.622 | 0 | [9 empty] | 16 | 16 |  |  | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1232 | 1232 | 0 | 0 | 2516.976 | 0 | 0 | 2516.976 | 314.622 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2516.976
1.2.1.6.4.2 | 1.2 | 1.2.1 | UW | PSL | Crate Installation Kits | Crate (Installation): Installation Kits (Vessel) |  | M & S | M & S |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C2 | 12.5% | 956.101 | 331.1984 | 7x 34"H x 48"L x 40"Wx 7crates at $699/each Grainger 1XGG6 | [8 empty] | 2447 | 2447 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2447 | 2447 | 0 | 0 | 4999.221 | 0 | 2649.5871 | 7648.8081 | 624.9026 | 331.1984 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7648.8081
1.2.1.6.4.3 | 1.2 | 1.2.1 | UW | PSL | Crate String Weights | Crate (Installation): String Weights (Vessel) |  | Labor Hours | Labor - Task | TE | D - Expert Opinion | 77 | 77 | 0% | 0% | Off Ice | C2 | 12.5% | 78.6555 | 0 | 2x $517/each Collapsible Bulk Container, Black, 34 inH x 48 inL x 45 inW, 1EA Item # 39H823 |  |  |  | 8 | [8 empty] | 8 | 0 | 0 | 0 | 616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 629.244 | 0 | 0 | 629.244 | 78.6555 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 629.244
1.2.1.6.4.3 | 1.2 | 1.2.1 | UW | PSL | Crate String Weights | Crate (Installation): String Weights (Vessel) |  | M & S | M & S |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C2 | 12.5% | 202.0042 | 69.9753 | $1317 estimated for three 40" x 48" x 25" bulk containers with lids to package hardware for shipping |  |  |  | 1034 | [8 empty] | 0 | 0 | 0 | 0 | 1034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1056.231 | 0 | 559.8024 | 1616.0334 | 132.0289 | 69.9753 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1616.0334
1.2.1.6.4.4 | 1.2 | 1.2.1 | UW | PSL | Crate Science Equipment FS2 (SPAT, IME, Pressure Sensors, Laser Rangers) | Crate (Installation): Science Equipment FS2 (SPAT, IME, Laser Rangers, Pressure Sensors)(Comsur) |  | M & S | M & S |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C2 | 12.5% | 148.0751 | 51.294 | $371/each estimated for two 45" x 48" x 44" bulk containers with lids to package hardware for shipping | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 742 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 742 | 0 | 0 | 0 | 774.249 | 0 | 410.352 | 1184.601 | 96.7811 | 51.294 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1184.601
1.2.1.6.4.5 | 1.2 | 1.2.1 | UW | PSL | Crate Science Equipment FS3 | Crate (Installation): Science Equipment FS3 (Comsur) |  | M & S | M & S |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C2 | 12.5% | 151.2587 | 52.3968 | $371/each estimated for two 45" x 48" x 44" bulk containers with lids to package hardware for shipping | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 742 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 742 | 0 | 0 | 790.8953 | 0 | 419.1745 | 1210.0699 | 98.8619 | 52.3968 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1210.0699
1.2.1.6.5.1 | 1.2 | 1.2.1 | UW | PSL | Ship Sensor Handling Structure | Ship (Installation): Sensor Handling Structure (Vessel) |  | M & S | M & S |  | E - Extrapolation from Actuals |  | 1 | 0% | 53% | Off Ice | C2 | 12.5% | 586.0856 | 203.0231 | DHF ships on truck with Container C | 3000 | [11 empty] | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3064.5 | 0 | 1624.185 | 4688.685 | 383.0625 | 203.0231 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4688.685
1.2.1.6.5.2 | 1.2 | 1.2.1 | UW | PSL | Ship Installation Kits | Ship (Installation): Installation Kits (Vessel) |  | M & S | M & S |  | E - Extrapolation from Actuals |  | 1 | 0% | 53% | Off Ice | C2 | 12.5% | 409.5015 | 141.8535 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2052 | [11 empty] | 0 | 2052 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2141.1845 | 0 | 1134.8278 | 3276.0123 | 267.6481 | 141.8535 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3276.0123
1.2.1.6.5.3 | 1.2 | 1.2.1 | UW | PSL | Ship String Weights | Ship (Installation): String Weights (Vessel) |  | M & S | M & S |  | E - Extrapolation from Actuals |  | 1 | 0% | 53% | Off Ice | C2 | 12.5% | 103.7723 | 35.9473 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 520 | [11 empty] | 0 | 520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 542.6004 | 0 | 287.5782 | 830.1786 | 67.825 | 35.9473 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 830.1786
1.2.1.6.5.4 | 1.2 | 1.2.1 | UW | PSL | Ship Science Crate FS2 (SPAT, IME, Pressure Sensors, Laser Rangers) | Ship (Installation): Science Equipment FS2 (SPAT, IME, Laser Rangers, Pressure Sensors) (Comsur) |  | M & S | M & S |  | E - Extrapolation from Actuals |  | 1 | 0% | 53% | Off Ice | C2 | 12.5% | 199.5622 | 69.1294 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 1000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 1043.4623 | 0 | 553.035 | 1596.4972 | 130.4328 | 69.1294 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1596.4972
1.2.1.6.5.5 | 1.2 | 1.2.1 | UW | PSL | Ship Science Crate FS3 | Ship (Installation): Science Equipment FS3 (Comsur) |  | M & S | M & S |  | E - Extrapolation from Actuals |  | 1 | 0% | 53% | Off Ice | C2 | 12.5% | 203.8527 | 70.6157 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 1000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 1065.8967 | 0 | 564.9252 | 1630.8219 | 133.2371 | 70.6157 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1630.8219
1.2.2.1.6 | 1.2 | 1.2.2 | UW | PSL | Procure MHP Upgrade, Sub-Components, Spares (PY5) | MHP: Procure MHP Upgrade, Sub-Components, Spares (PY5) | Gibson | Labor Hours | Labor - Task | EN-ME | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 563.868 | 0 | [7 empty] | 12 | 12 |  |  |  |  | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 1380 | 1380 | 0 | 0 | 0 | 0 | 2819.34 | 0 | 0 | 2819.34 | 563.868 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2819.34
1.2.2.1.6 | 1.2 | 1.2.2 | UW | PSL | Procure MHP Upgrade, Sub-Components, Spares (PY5) | MHP: Procure MHP Upgrade, Sub-Components, Spares (PY5) |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 0% | Off Ice | C3 | 20% | 1021.5 | 0 | [7 empty] | 2500 | 2500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 2500 | 0 | 0 | 0 | 0 | 5107.5 | 0 | 0 | 5107.5 | 1021.5 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5107.5
1.2.2.1.7 | 1.2 | 1.2.2 | UW | PSL | Develop HPU2 Integrate Plan | MHP: Develop HPU2 Integrate Plan |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C4 | 35% | 2099.9678 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 25 | 25 |  |  |  | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2875 | 2875 | 0 | 0 | 0 | 5999.9079 | 0 | 0 | 5999.9079 | 2099.9678 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5999.9079
1.2.2.1.8 | 1.2 | 1.2.2 | UW | PSL | Procure and Assemble HPU2 Integration Components | MHP: Procure and Assemble HPU2 Integration Components |  | Labor Hours | Labor - Task | EN-ME | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 959.9853 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 20 | 20 |  |  | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2300 | 2300 | 0 | 0 | 4799.9264 | 0 | 0 | 4799.9264 | 959.9853 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4799.9264
1.2.2.1.8 | 1.2 | 1.2.2 | UW | PSL | Procure and Assemble HPU2 Integration Components | MHP: Procure and Assemble HPU2 Integration Components |  | Labor Hours | Labor - Task | TE | D - Expert Opinion | 77 | 77 | 0% | 0% | Off Ice | C3 | 20% | 642.7727 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 20 | 20 |  |  | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1540 | 1540 | 0 | 0 | 3213.8637 | 0 | 0 | 3213.8637 | 642.7727 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3213.8637
1.2.2.1.8 | 1.2 | 1.2.2 | UW | PSL | Procure and Assemble HPU2 Integration Components | MHP: Procure and Assemble HPU2 Integration Components |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 0% | Off Ice | C3 | 20% | 2086.9245 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 5000 | 5000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 5000 | 0 | 0 | 10434.6225 | 0 | 0 | 10434.6225 | 2086.9245 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10434.6225
1.2.2.1.10 | 1.2 | 1.2.2 | UW | PSL | Procure MHP Upgrade, Sub-Components, Spares (PY6) | MHP: Procure Upgrade, Sub-Components, Spares (PY6) |  | Labor Hours | Labor - Task | EN-ME | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 575.9912 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 12 | 12 |  |  |  |  | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 1380 | 1380 | 0 | 0 | 0 | 0 | 2879.9558 | 0 | 0 | 2879.9558 | 575.9912 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2879.9558
1.2.2.1.10 | 1.2 | 1.2.2 | UW | PSL | Procure MHP Upgrade, Sub-Components, Spares (PY6) | MHP: Procure Upgrade, Sub-Components, Spares (PY6) |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 0% | Off Ice | C3 | 20% | 1043.4623 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2500 | 2500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 2500 | 0 | 0 | 0 | 0 | 5217.3113 | 0 | 0 | 5217.3113 | 1043.4623 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5217.3113
1.2.2.2.4 | 1.2 | 1.2.2 | UW | PSL | Procure and Upgrade Control Boxes (PY6) | PHS: Procure and Upgrade Control Boxes (PY6) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 1919.9705 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 40 | 40 | [5 empty] | 80 | 0 | 0 | 0 | 0 | 0 | 4600 | 4600 | 0 | 0 | 0 | 0 | 0 | 9599.8527 | 0 | 0 | 9599.8527 | 1919.9705 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9599.8527
1.2.2.2.4 | 1.2 | 1.2.2 | UW | PSL | Procure and Upgrade Control Boxes (PY6) | PHS: Procure and Upgrade Control Boxes (PY6) |  | Labor Hours | Labor - Task | TE | D - Expert Opinion | 77 | 77 | 0% | 0% | Off Ice | C3 | 20% | 1285.5455 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 40 | 40 | [5 empty] | 80 | 0 | 0 | 0 | 0 | 0 | 3080 | 3080 | 0 | 0 | 0 | 0 | 0 | 6427.7275 | 0 | 0 | 6427.7275 | 1285.5455 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6427.7275
1.2.2.2.4 | 1.2 | 1.2.2 | UW | PSL | Procure and Upgrade Control Boxes (PY6) | PHS: Procure and Upgrade Control Boxes (PY6) |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 0% | Off Ice | C3 | 20% | 834.7698 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 2000 | 2000 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 2000 | 0 | 0 | 0 | 0 | 0 | 4173.849 | 0 | 0 | 4173.849 | 834.7698 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4173.849
1.2.2.2.5 | 1.2 | 1.2.2 | UW | PSL | Procure Upgrade, Sub-Components, Spares (PY6) | PHS: Procure Upgrade, Sub-Components, Spares (PY6) |  | Labor Hours | Labor Hours | EN-ME | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 575.9912 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 12 | 12 |  |  |  |  | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 1380 | 1380 | 0 | 0 | 0 | 0 | 2879.9558 | 0 | 0 | 2879.9558 | 575.9912 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2879.9558
1.2.2.2.5 | 1.2 | 1.2.2 | UW | PSL | Procure Upgrade, Sub-Components, Spares (PY6) | PHS: Procure Upgrade, Sub-Components, Spares (PY6) |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 0% | Off Ice | C3 | 20% | 1043.4623 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2500 | 2500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 2500 | 0 | 0 | 0 | 0 | 5217.3113 | 0 | 0 | 5217.3113 | 1043.4623 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5217.3113
1.2.2.3.8 | 1.2 | 1.2.2 | UW | PSL | Procure ARA Fueling Hose & Nozzle (PY5) | Fuel Tower: Procure ARA Fueling Hose & Nozzle (PY5) |  | Labor Hours | Labor - Task | EN-ME | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 187.956 | 0 | [6 empty] | 8 | [6 empty] | 8 | 0 | 0 | 0 | 0 | 0 | 920 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78 | 0 | 0 | 939.78 | 187.956 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78
1.2.2.3.8 | 1.2 | 1.2.2 | UW | PSL | Procure ARA Fueling Hose & Nozzle (PY5) | Fuel Tower: Procure ARA Fueling Hose & Nozzle (PY5) |  | CapEx | CapEx |  | C - Engineering Buildup |  | 1 | 0% | 0% | Off Ice | C3 | 20% | 907.5006 | 0 | [6 empty] | 4442 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 4442 | 0 | 0 | 0 | 0 | 0 | 0 | 4537.503 | 0 | 0 | 4537.503 | 907.5006 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4537.503
1.2.2.3.9 | 1.2 | 1.2.2 | UW | PSL | Procure Racor Fuel Filter Elements and Gauges Replacements (PY5) | Fuel Tower: Procure Racor Fuel Filter Elements and Gauges Replacements (PY5) |  | Labor Hours | Labor - Task | EN-ME | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 375.912 | 0 | [6 empty] | 16 | [6 empty] | 16 | 0 | 0 | 0 | 0 | 0 | 1840 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 0 | 0 | 1879.56 | 375.912 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56
1.2.2.3.9 | 1.2 | 1.2.2 | UW | PSL | Procure Racor Fuel Filter Elements and Gauges Replacements (PY5) | Fuel Tower: Procure Racor Fuel Filter Elements and Gauges Replacements (PY5) |  | Labor Hours | Labor - Task | TE | D - Expert Opinion | 77 | 77 | 0% | 0% | Off Ice | C3 | 20% | 251.6976 | 0 | [6 empty] | 16 | [6 empty] | 16 | 0 | 0 | 0 | 0 | 0 | 1232 | 0 | 0 | 0 | 0 | 0 | 0 | 1258.488 | 0 | 0 | 1258.488 | 251.6976 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1258.488
1.2.2.3.9 | 1.2 | 1.2.2 | UW | PSL | Procure Racor Fuel Filter Elements and Gauges Replacements (PY5) | Fuel Tower: Procure Racor Fuel Filter Elements and Gauges Replacements (PY5) |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 0% | Off Ice | C3 | 20% | 306.45 | 0 | [6 empty] | 1500 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 1532.25 | 0 | 0 | 1532.25 | 306.45 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1532.25
1.2.2.3.10 | 1.2 | 1.2.2 | UW | PSL | Procure Fuel system Upgrade/Maintenance Subcomponents (PY6) | Fuel Tower: Procure Fuel system Upgrade/Maintenance Subcomponents (PY6) |  | Labor Hours | Labor - Task | EN-ME | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 575.9912 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 12 | 12 | [5 empty] | 24 | 0 | 0 | 0 | 0 | 0 | 1380 | 1380 | 0 | 0 | 0 | 0 | 0 | 2879.9558 | 0 | 0 | 2879.9558 | 575.9912 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2879.9558
1.2.2.3.10 | 1.2 | 1.2.2 | UW | PSL | Procure Fuel system Upgrade/Maintenance Subcomponents (PY6) | Fuel Tower: Procure Fuel system Upgrade/Maintenance Subcomponents (PY6) |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 0% | Off Ice | C3 | 20% | 500.8619 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 1200 | 1200 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 1200 | 0 | 0 | 0 | 0 | 0 | 2504.3094 | 0 | 0 | 2504.3094 | 500.8619 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2504.3094
1.2.2.3.11 | 1.2 | 1.2.2 | UW | PSL | Procure MHP Fuel Heat Exchangers Replacements (PY6) | Fuel Tower: Procure MHP Fuel Heat Exchangers Replacements (PY6) |  | Labor Hours | Labor - Task | EN-ME | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 383.9941 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 16 | [5 empty] | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 1840 | 0 | 0 | 0 | 0 | 0 | 1919.9705 | 0 | 0 | 1919.9705 | 383.9941 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1919.9705
1.2.2.3.11 | 1.2 | 1.2.2 | UW | PSL | Procure MHP Fuel Heat Exchangers Replacements (PY6) | Fuel Tower: Procure MHP Fuel Heat Exchangers Replacements (PY6) |  | CapEx | CapEx |  | C - Engineering Buildup |  | 1 | 0% | 0% | Off Ice | C3 | 20% | 2145.9845 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 10283 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10283 | 0 | 0 | 0 | 0 | 0 | 10729.9223 | 0 | 0 | 10729.9223 | 2145.9845 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10729.9223
1.2.3.1.5 | 1.2 | 1.2.3 | UW | PSL | Crescent Emergency Repair Kit Assembly (PY6) | Tower Ops: Crescent Emergency Repair Kit Assembly | Lemery | Labor Hours | Labor - Task | EN-ME | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 959.9853 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 40 | [7 empty] | 40 | 0 | 0 | 0 | 0 | 4600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4799.9264 | 0 | 0 | 4799.9264 | 959.9853 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4799.9264
1.2.3.1.5 | 1.2 | 1.2.3 | UW | PSL | Crescent Emergency Repair Kit Assembly (PY6) | Tower Ops: Crescent Emergency Repair Kit Assembly | Lemry | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 0% | Off Ice | C3 | 20% | 521.7311 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2500 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2608.6556 | 0 | 0 | 2608.6556 | 521.7311 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2608.6556
1.2.3.1.6 | 1.2 | 1.2.3 | UW | PSL | Examine Interface between Dust Logger and Tower & Address as Needed | Tower Ops: Examine Interface between Dust Logger and Tower & Address as Needed |  | Labor Hours | Labor - Task | EN-ME | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C4 | 35% | 1644.615 | 0 | [10 empty] | 20 | 20 |  | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2300 | 2300 | 0 | 4698.9 | 0 | 0 | 4698.9 | 1644.615 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9
1.2.3.1.6 | 1.2 | 1.2.3 | UW | PSL | Examine Interface between Dust Logger and Tower & Address as Needed | Tower Ops: Examine Interface between Dust Logger and Tower & Address as Needed |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 0% | Off Ice | C4 | 35% | 858.06 | 0 | [10 empty] | 1200 | 1200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 1200 | 0 | 2451.6 | 0 | 0 | 2451.6 | 858.06 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2451.6
1.2.3.1.7.2 | 1.2 | 1.2.3 | UW | PSL | Calibration Load Cell | Tower Ops: Load Cell Calibration |  | Labor Hours | Labor - Task | EN-ME | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C2 | 12.5% | 117.4725 | 0 | [5 empty] | 8 | [7 empty] | 8 | 0 | 0 | 0 | 0 | 920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78 | 0 | 0 | 939.78 | 117.4725 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78
1.2.3.1.7.2 | 1.2 | 1.2.3 | UW | PSL | Calibration Load Cell | Tower Ops: Load Cell Calibration |  | CapEx | CapEx |  | C - Engineering Buildup |  | 1 | 0% | 0% | Off Ice | C2 | 12.5% | 228.4329 | 0 | [5 empty] | 1789 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 1789 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1827.4635 | 0 | 0 | 1827.4635 | 228.4329 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1827.4635
1.2.3.1.7.3 | 1.2 | 1.2.3 | UW | PSL | Calibration Load Cell Rigging | Tower Ops: Identify/Procure: Load Cell Rigging Calibration |  | Labor Hours | Labor - Task | EN-ME | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C2 | 12.5% | 117.4725 | 0 | [6 empty] | 8 | [6 empty] | 8 | 0 | 0 | 0 | 0 | 0 | 920 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78 | 0 | 0 | 939.78 | 117.4725 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78
1.2.3.1.7.3 | 1.2 | 1.2.3 | UW | PSL | Calibration Load Cell Rigging | Tower Ops: Identify/Procure: Load Cell Rigging Calibration |  | CapEx | CapEx |  | C - Engineering Buildup |  | 1 | 0% | 0% | Off Ice | C2 | 12.5% | 155.7788 | 0 | [6 empty] | 1220 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1220 | 0 | 0 | 0 | 0 | 0 | 0 | 1246.23 | 0 | 0 | 1246.23 | 155.7788 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1246.23
1.2.3.1.8 | 1.2 | 1.2.3 | UW | PSL | Identify/Procure: TOS & Tower Hardware, Repair Parts (PY5) | Tower Ops: Identify/Procure: TOS & Tower Hardware, Repair Parts (PY5) |  | Labor Hours | Labor - Task | EN-ME | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 375.912 | 0 | [9 empty] | 16 |  |  |  | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1840 | 0 | 0 | 0 | 1879.56 | 0 | 0 | 1879.56 | 375.912 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56
1.2.3.1.8 | 1.2 | 1.2.3 | UW | PSL | Identify/Procure: TOS & Tower Hardware, Repair Parts (PY5) | Tower Ops: Identify/Procure: TOS & Tower Hardware, Repair Parts (PY5) |  | Labor Hours | Labor - Task | EN-ME | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 375.912 | 0 | [9 empty] | 8 |  | 8 |  | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 920 | 0 | 920 | 0 | 1879.56 | 0 | 0 | 1879.56 | 375.912 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56
1.2.3.1.8 | 1.2 | 1.2.3 | UW | PSL | Identify/Procure: TOS & Tower Hardware, Repair Parts (PY5) | Tower Ops: Identify/Procure: TOS & Tower Hardware, Repair Parts (PY5) |  | CapEx | CapEx |  | C - Engineering Buildup |  | 1 | 0% | 0% | Off Ice | C3 | 20% | 2090.3976 | 0 | Driller tape: 4 cases @ 30 rolls/case = 120 rolls $50/roll -> $6k | [8 empty] | 5232 |  | 5000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5232 | 0 | 5000 | 0 | 10451.988 | 0 | 0 | 10451.988 | 2090.3976 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10451.988
1.2.3.1.9 | 1.2 | 1.2.3 | UW | PSL | Identify/Procure: TOS & Tower Hardware, Repair Parts (PY6) | Tower Ops: Identify/Procure: TOS & Tower Hardware, Repair Parts (PY6) |  | Labor Hours | Labor - Task | EN-ME | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 383.9941 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 16 |  |  |  | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1840 | 0 | 0 | 0 | 1919.9705 | 0 | 0 | 1919.9705 | 383.9941 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1919.9705
1.2.3.1.9 | 1.2 | 1.2.3 | UW | PSL | Identify/Procure: TOS & Tower Hardware, Repair Parts (PY6) | Tower Ops: Identify/Procure: TOS & Tower Hardware, Repair Parts (PY6) |  | Labor Hours | Labor Hours | EN-ME | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 383.9941 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 16 |  |  | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1840 | 0 | 0 | 1919.9705 | 0 | 0 | 1919.9705 | 383.9941 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1919.9705
1.2.3.1.9 | 1.2 | 1.2.3 | UW | PSL | Identify/Procure: TOS & Tower Hardware, Repair Parts (PY6) | Tower Ops: Identify/Procure: TOS & Tower Hardware, Repair Parts (PY6) |  | CapEx | CapEx |  | C - Engineering Buildup |  | 1 | 0% | 0% | Off Ice | C3 | 20% | 1926.6487 | 0 | Driller tape: 4 cases @ 30 rolls/case = 120 rolls $50/roll -> $6k | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 5232 | 4000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5232 | 4000 | 0 | 0 | 9633.2435 | 0 | 0 | 9633.2435 | 1926.6487 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9633.2435
1.2.3.1.10 | 1.2 | 1.2.3 | UW | PSL | Identify/Procure: TOS & Tower Hardware, Repair Parts (PY7) | Tower Ops: Identify/Procure: TOS & Tower Hardware, Repair Parts (PY7) |  | Labor Hours | Labor - Task | EN-ME | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 392.25 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 16 |  |  |  |  | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1840 | 0 | 0 | 0 | 0 | 1961.2499 | 0 | 0 | 1961.2499 | 392.25 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1961.2499
1.2.3.1.10 | 1.2 | 1.2.3 | UW | PSL | Identify/Procure: TOS & Tower Hardware, Repair Parts (PY7) | Tower Ops: Identify/Procure: TOS & Tower Hardware, Repair Parts (PY7) |  | Labor Hours | Labor - Task | EN-ME | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 392.25 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 16 |  |  |  | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1840 | 0 | 0 | 0 | 1961.2499 | 0 | 0 | 1961.2499 | 392.25 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1961.2499
1.2.3.1.10 | 1.2 | 1.2.3 | UW | PSL | Identify/Procure: TOS & Tower Hardware, Repair Parts (PY7) | Tower Ops: Identify/Procure: TOS & Tower Hardware, Repair Parts (PY7) |  | CapEx | CapEx |  | C - Engineering Buildup |  | 1 | 0% | 0% | Off Ice | C3 | 20% | 4901.4193 | 0 | Driller tape: 50 rolls/hole x 7 holes = 350 rolls Plus 3 cases @ 30 rolls/case = 440 rolls $50/roll -> $22k | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 20492 | 2500 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20492 | 2500 | 0 | 0 | 0 | 24507.0967 | 0 | 0 | 24507.0967 | 4901.4193 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24507.0967
1.2.3.2.10 | 1.2 | 1.2.3 | UW | PSL | Drillheads: Prepare Crates, Spares, Tools, & Docs x3 | Drillheads: Prepare Crates, Spares, Tools, & Docs x3 |  | Labor Hours | Labor - Task | EN-ME | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 563.868 | 0 |  | 24 | [11 empty] | 24 | 2760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2819.34 | 0 | 0 | 2819.34 | 563.868 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2819.34
1.2.3.2.10 | 1.2 | 1.2.3 | UW | PSL | Drillheads: Prepare Crates, Spares, Tools, & Docs x3 | Drillheads: Prepare Crates, Spares, Tools, & Docs x3 |  | Labor Hours | Labor - Task | TE | D - Expert Opinion | 77 | 77 | 0% | 0% | Off Ice | C3 | 20% | 377.5464 | 0 |  | 24 | [11 empty] | 24 | 1848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1887.732 | 0 | 0 | 1887.732 | 377.5464 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1887.732
1.2.3.3.9 | 1.2 | 1.2.3 | UW | PSL | Reels & Winches: Drill Reels Sliprings - Final Testing & Prep | Reels & Winches: Drill Reels Sliprings - final testing and prep |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 375.912 | 0 | [9 empty] | 16 |  |  |  | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1840 | 0 | 0 | 0 | 1879.56 | 0 | 0 | 1879.56 | 375.912 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56
1.2.3.3.10 | 1.2 | 1.2.3 | UW | PSL | Reels & Winches: TU20 Sliprings - Spec, Procure, Test | Reels & Winches: TU20 Sliprings - spec, procure, test |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 3759.12 | 0 | [6 empty] | 80 | 80 | [5 empty] | 160 | 0 | 0 | 0 | 0 | 0 | 9200 | 9200 | 0 | 0 | 0 | 0 | 0 | 18795.6 | 0 | 0 | 18795.6 | 3759.12 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18795.6
1.2.3.3.10 | 1.2 | 1.2.3 | UW | PSL | Reels & Winches: TU20 Sliprings - Spec, Procure, Test | Reels & Winches: TU20 Sliprings - spec, procure, test |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 0% | Off Ice | C3 | 20% | 1718.7759 | 0 | [6 empty] | 8413 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 8413 | 0 | 0 | 0 | 0 | 0 | 0 | 8593.8795 | 0 | 0 | 8593.8795 | 1718.7759 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8593.8795
1.2.3.3.11 | 1.2 | 1.2.3 | UW | PSL | Reels & Winches: Reel Components & Spares (PY6). TU20 brakes | Reels & Winches: Reel Components & Spares (PY6). TU20 brakes) |  | Labor Hours | Labor - Task | EN-ME | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 1919.9705 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 80 | [6 empty] | 80 | 0 | 0 | 0 | 0 | 0 | 9200 | 0 | 0 | 0 | 0 | 0 | 0 | 9599.8527 | 0 | 0 | 9599.8527 | 1919.9705 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9599.8527
1.2.3.3.11 | 1.2 | 1.2.3 | UW | PSL | Reels & Winches: Reel Components & Spares (PY6). TU20 brakes | Reels & Winches: Reel Components & Spares (PY6). TU20 brakes) |  | Labor Hours | Labor - Task | TE | D - Expert Opinion | 77 | 77 | 0% | 0% | Off Ice | C3 | 20% | 642.7727 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 40 | [6 empty] | 40 | 0 | 0 | 0 | 0 | 0 | 3080 | 0 | 0 | 0 | 0 | 0 | 0 | 3213.8637 | 0 | 0 | 3213.8637 | 642.7727 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3213.8637
1.2.3.3.11 | 1.2 | 1.2.3 | UW | PSL | Reels & Winches: Reel Components & Spares (PY6). TU20 brakes | Reels & Winches: Reel Components & Spares (PY6). TU20 brakes) |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 0% | Off Ice | C3 | 20% | 1830.2328 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 8770 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 8770 | 0 | 0 | 0 | 0 | 0 | 0 | 9151.1639 | 0 | 0 | 9151.1639 | 1830.2328 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9151.1639
1.2.4.1.8 | 1.2 | 1.2.4 | UW | PSL | Coordination with USAP IT (PY5) | Architecture: Coordination with USAP IT (PY5) (station connectivity, internet, phone) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 469.89 | 0 | [9 empty] | 20 |  |  |  | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2300 | 0 | 0 | 0 | 2349.45 | 0 | 0 | 2349.45 | 469.89 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2349.45
1.2.4.1.9 | 1.2 | 1.2.4 | UW | PSL | CS Drawings & Documentation (PY5) | Architecture: CS Drawings & Documentation (PY5) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 751.824 | 0 | [10 empty] | 8 | 16 | 8 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 920 | 1840 | 920 | 3759.12 | 0 | 0 | 3759.12 | 751.824 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3759.12
1.2.4.1.10 | 1.2 | 1.2.4 | UW | PSL | CS Drawings & Documentation (PY6) | Architecture: CS Drawings & Documentation (PY6) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 767.9882 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 16 | 16 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1840 | 1840 | 3839.9411 | 0 | 0 | 3839.9411 | 767.9882 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3839.9411
1.2.4.1.11 | 1.2 | 1.2.4 | UW | PSL | CS Drawings & Documentation (PY7) | Architecture: CS Drawings & Documentation (PY7) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 784.5 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 16 | 16 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1840 | 1840 | 3922.4998 | 0 | 0 | 3922.4998 | 784.5 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3922.4998
1.2.4.1.12 | 1.2 | 1.2.4 | UW | PSL | CS Drawings & Documentation (PY8) | Architecture: CS Drawings & Documentation (PY8) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 801.3667 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 32 | [6 empty] | 32 | 0 | 0 | 0 | 0 | 0 | 3680 | 0 | 0 | 0 | 0 | 0 | 0 | 4006.8336 | 0 | 0 | 4006.8336 | 801.3667 | 0 | 4006.8336
1.2.4.2.2.5 | 1.2 | 1.2.4 | UW | PSL | Procure System Sensors (PY5) | Controls Hardware: Procure System Sensors (PY5) |  | Labor Hours | Labor Hours | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 751.824 | 0 |  | 32 | [11 empty] | 32 | 3680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3759.12 | 0 | 0 | 3759.12 | 751.824 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3759.12
1.2.4.2.2.5 | 1.2 | 1.2.4 | UW | PSL | Procure System Sensors (PY5) | Controls Hardware: Procure System Sensors (PY5) |  | CapEx | CapEx |  | C - Engineering Buildup |  | 1 | 0% | 0% | Off Ice | C2 | 12.5% | 3546.648 | 0 |  | 27776 | [11 empty] | 0 | 27776 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28373.184 | 0 | 0 | 28373.184 | 3546.648 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28373.184
1.2.4.2.11.1 | 1.2 | 1.2.4 | UW | PSL | CS HW Production Ignition Servers (3x: DCC, TOS1, TOS2) | Network Controllers: CS HW Production Ignition Servers (3x: DCC, TOS1, TOS2) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 234.945 | 0 | [5 empty] | 2 | 4 | 4 | [5 empty] | 10 | 0 | 0 | 0 | 0 | 230 | 460 | 460 | 0 | 0 | 0 | 0 | 0 | 1174.725 | 0 | 0 | 1174.725 | 234.945 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1174.725
1.2.4.2.11.1 | 1.2 | 1.2.4 | UW | PSL | CS HW Production Ignition Servers (3x: DCC, TOS1, TOS2) | Network Controllers: CS HW Production Ignition Servers (3x: DCC, TOS1, TOS2) |  | CapEx | CapEx |  | C - Engineering Buildup |  | 1 | 0% | 0% | Off Ice | C2 | 12.5% | 596.4283 | 0 | [5 empty] | 4671 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 4671 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4771.4265 | 0 | 0 | 4771.4265 | 596.4283 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4771.4265
1.2.4.2.11.2 | 1.2 | 1.2.4 | UW | PSL | CS HW Production Database Server (1x: DCC) | Network Controllers: CS HW Production Database Server (1x: DCC) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 234.945 | 0 | [5 empty] | 2 | 4 | 4 | [5 empty] | 10 | 0 | 0 | 0 | 0 | 230 | 460 | 460 | 0 | 0 | 0 | 0 | 0 | 1174.725 | 0 | 0 | 1174.725 | 234.945 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1174.725
1.2.4.2.11.2 | 1.2 | 1.2.4 | UW | PSL | CS HW Production Database Server (1x: DCC) | Network Controllers: CS HW Production Database Server (1x: DCC) |  | CapEx | CapEx |  | C - Engineering Buildup |  | 1 | 0% | 0% | Off Ice | C2 | 12.5% | 371.0599 | 0 | [5 empty] | 2906 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 2906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2968.479 | 0 | 0 | 2968.479 | 371.0599 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2968.479
1.2.4.2.11.3 | 1.2 | 1.2.4 | UW | PSL | CS HW Production Peripherals (3x sets: DCC, TOS1, TOS2) | Network Controllers: CS HW Production Peripherals (3x sets: DCC, TOS1, TOS2) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 375.912 | 0 | [6 empty] | 16 | [6 empty] | 16 | 0 | 0 | 0 | 0 | 0 | 1840 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 0 | 0 | 1879.56 | 375.912 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56
1.2.4.2.11.3 | 1.2 | 1.2.4 | UW | PSL | CS HW Production Peripherals (3x sets: DCC, TOS1, TOS2) | Network Controllers: CS HW Production Peripherals (3x sets: DCC, TOS1, TOS2) |  | CapEx | CapEx |  | C - Engineering Buildup |  | 1 | 0% | 0% | Off Ice | C2 | 12.5% | 2237.085 | 0 | [6 empty] | 17520 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 17520 | 0 | 0 | 0 | 0 | 0 | 0 | 17896.68 | 0 | 0 | 17896.68 | 2237.085 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17896.68
1.2.4.2.11.4 | 1.2 | 1.2.4 | UW | PSL | CS HW DCC Core Switch & Security Appliance | Network Controllers: CS HW DCC Core Switch & Security Appliance |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 187.956 | 0 | [6 empty] | 8 | [6 empty] | 8 | 0 | 0 | 0 | 0 | 0 | 920 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78 | 0 | 0 | 939.78 | 187.956 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78
1.2.4.2.11.4 | 1.2 | 1.2.4 | UW | PSL | CS HW DCC Core Switch & Security Appliance | Network Controllers: CS HW DCC Core Switch & Security Appliance |  | CapEx | CapEx |  | C - Engineering Buildup |  | 1 | 0% | 0% | Off Ice | C2 | 12.5% | 2528.5956 | 0 | [6 empty] | 19803 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 19803 | 0 | 0 | 0 | 0 | 0 | 0 | 20228.7645 | 0 | 0 | 20228.7645 | 2528.5956 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20228.7645
1.2.4.2.11.5 | 1.2 | 1.2.4 | UW | PSL | CS HW Production Main PLC - PLC (redundant), I/O, network, UPS, in a box (3x: DCC, TOS1, TOS2) | Network Controllers: CS HW Production Main PLC - PLC (redundant), I/O, network, UPS, in a box (3x: DCC, TOS1, TOS2) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 845.802 | 0 | [7 empty] | 16 | 10 | 10 |  |  |  | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 1840 | 1150 | 1150 | 0 | 0 | 0 | 4229.01 | 0 | 0 | 4229.01 | 845.802 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4229.01
1.2.4.2.11.5 | 1.2 | 1.2.4 | UW | PSL | CS HW Production Main PLC - PLC (redundant), I/O, network, UPS, in a box (3x: DCC, TOS1, TOS2) | Network Controllers: CS HW Production Main PLC - PLC (redundant), I/O, network, UPS, in a box (3x: DCC, TOS1, TOS2) |  | CapEx | CapEx |  | C - Engineering Buildup |  | 1 | 0% | 0% | Off Ice | C2 | 12.5% | 3813.6426 | 0 | [7 empty] | 29867 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29867 | 0 | 0 | 0 | 0 | 0 | 30509.1405 | 0 | 0 | 30509.1405 | 3813.6426 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30509.1405
1.2.4.2.13 | 1.2 | 1.2.4 | UW | PSL | CS HW PY6 Resupply | Network Controllers: CS HW PY6 Resupply |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C4 | 35% | 3359.9484 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 40 | 40 | [5 empty] | 80 | 0 | 0 | 0 | 0 | 0 | 4600 | 4600 | 0 | 0 | 0 | 0 | 0 | 9599.8527 | 0 | 0 | 9599.8527 | 3359.9484 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9599.8527
1.2.4.2.13 | 1.2 | 1.2.4 | UW | PSL | CS HW PY6 Resupply | Network Controllers: CS HW PY6 Resupply |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 0% | Off Ice | C4 | 35% | 1460.8472 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 2000 | 2000 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 2000 | 0 | 0 | 0 | 0 | 0 | 4173.849 | 0 | 0 | 4173.849 | 1460.8472 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4173.849
1.2.4.2.14 | 1.2 | 1.2.4 | UW | PSL | CS HW PY7 Resupply | Network Controllers: CS HW PY7 Resupply |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C4 | 35% | 3432.1873 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 40 | 40 | [5 empty] | 80 | 0 | 0 | 0 | 0 | 0 | 4600 | 4600 | 0 | 0 | 0 | 0 | 0 | 9806.2495 | 0 | 0 | 9806.2495 | 3432.1873 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9806.2495
1.2.4.2.14 | 1.2 | 1.2.4 | UW | PSL | CS HW PY7 Resupply | Network Controllers: CS HW PY7 Resupply |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 0% | Off Ice | C4 | 35% | 1492.2554 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 2000 | 2000 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 2000 | 0 | 0 | 0 | 0 | 0 | 4263.5868 | 0 | 0 | 4263.5868 | 1492.2554 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4263.5868
1.2.4.3.4 | 1.2 | 1.2.4 | UW | PSL | PLC & Software Development (w/sub-tasks) | Controls Software: PLC & Software Development (w/sub-tasks) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 2849.6479 | 0 |  | 10 |  | 10 |  | 10 |  | 10 |  | 10 |  | 10 |  | 60 | 1150 | 0 | 1150 | 0 | 1150 | 0 | 1150 | 0 | 1150 | 0 | 1150 | 0 | 7048.35 | 0 | 0 | 7048.35 | 1409.67 | 0 | 10 |  | 10 |  | 10 |  | 10 |  | 10 |  | 10 |  | 60 | 1150 | 0 | 1150 | 0 | 1150 | 0 | 1150 | 0 | 1150 | 0 | 1150 | 0 | 7199.8895 | 0 | 0 | 7199.8895 | 1439.9779 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14248.2395
1.2.4.3.5 | 1.2 | 1.2.4 | UW | PSL | SCADA Monitoring Software and Server Procurement | Controls Software: SCADA Monitoring Software Procurement - Server |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C2 | 12.5% | 293.6813 | 0 |  | 20 | [11 empty] | 20 | 2300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2349.45 | 0 | 0 | 2349.45 | 293.6813 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2349.45
1.2.4.3.5 | 1.2 | 1.2.4 | UW | PSL | SCADA Monitoring Software and Server Procurement | Controls Software: SCADA Monitoring Software - Server |  | CapEx | CapEx |  | C - Engineering Buildup |  | 1 | 0% | 0% | Off Ice | C2 | 12.5% | 293.2982 | 0 |  | 2297 | [11 empty] | 0 | 2297 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2346.3855 | 0 | 0 | 2346.3855 | 293.2982 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2346.3855
1.2.4.3.9.1.1 | 1.2 | 1.2.4 | UW | PSL | Local-Panel MDS-specific HMI (PY5) | Operator Screen MHP: Local-Panel MDS-specific HMI (PY5) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 469.89 | 0 | [7 empty] | 20 | [5 empty] | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 2300 | 0 | 0 | 0 | 0 | 0 | 2349.45 | 0 | 0 | 2349.45 | 469.89 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2349.45
1.2.4.3.9.1.2 | 1.2 | 1.2.4 | UW | PSL | Local-Panel MDS-specific HMI (PY6) | Operator Screen MHP: Local-Panel MDS-specific HMI (PY6) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 479.9926 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 20 | [5 empty] | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 2300 | 0 | 0 | 0 | 0 | 0 | 2399.9632 | 0 | 0 | 2399.9632 | 479.9926 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2399.9632
1.2.4.3.9.1.3 | 1.2 | 1.2.4 | UW | PSL | DCC-based SCADA UI (PY5) | Operator Screen MHP: DCC-based SCADA UI (PY5) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 1879.56 | 0 | [7 empty] | 80 | [5 empty] | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 9200 | 0 | 0 | 0 | 0 | 0 | 9397.8 | 0 | 0 | 9397.8 | 1879.56 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9397.8
1.2.4.3.9.1.4 | 1.2 | 1.2.4 | UW | PSL | DCC-based SCADA UI (PY6) | Operator Screen MHP: DCC-based SCADA UI (PY6) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 1919.9705 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 80 | [5 empty] | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 9200 | 0 | 0 | 0 | 0 | 0 | 9599.8527 | 0 | 0 | 9599.8527 | 1919.9705 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9599.8527
1.2.4.3.9.2.1 | 1.2 | 1.2.4 | UW | PSL | Local-Panel MDS-specific HMI (PY5) | Operator Screen Fuel System: Local-Panel MDS-specific HMI (PY5) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 187.956 | 0 | [8 empty] | 8 |  |  |  |  | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 920 | 0 | 0 | 0 | 0 | 939.78 | 0 | 0 | 939.78 | 187.956 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78
1.2.4.3.9.2.2 | 1.2 | 1.2.4 | UW | PSL | Local-Panel MDS-specific HMI (PY6) | Operator Screen Fuel System: Local-Panel MDS-specific HMI (PY6) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 191.9971 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 8 |  |  |  |  | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 920 | 0 | 0 | 0 | 0 | 959.9853 | 0 | 0 | 959.9853 | 191.9971 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 959.9853
1.2.4.3.9.2.3 | 1.2 | 1.2.4 | UW | PSL | DCC-based SCADA (PY5) | Operator Screen Fuel System: DCC-based SCADA (PY5) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 187.956 | 0 | [8 empty] | 8 |  |  |  |  | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 920 | 0 | 0 | 0 | 0 | 939.78 | 0 | 0 | 939.78 | 187.956 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78
1.2.4.3.9.2.4 | 1.2 | 1.2.4 | UW | PSL | DCC-based SCADA (PY6) | Operator Screen Fuel System: DCC-based SCADA (PY6) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 191.9971 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 8 |  |  |  |  | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 920 | 0 | 0 | 0 | 0 | 959.9853 | 0 | 0 | 959.9853 | 191.9971 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 959.9853
1.2.4.3.9.3.1 | 1.2 | 1.2.4 | UW | PSL | Local-Panel MDS-specific HMI (PY5) | Operator Screen Gensets: Local-Panel MDS-specific HMI (PY5) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 187.956 | 0 | [9 empty] | 8 |  |  |  | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 920 | 0 | 0 | 0 | 939.78 | 0 | 0 | 939.78 | 187.956 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78
1.2.4.3.9.3.2 | 1.2 | 1.2.4 | UW | PSL | Local-Panel MDS-specific HMI (PY6) | Operator Screen Gensets: Local-Panel MDS-specific HMI (PY6) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 191.9971 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 8 |  |  |  | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 920 | 0 | 0 | 0 | 959.9853 | 0 | 0 | 959.9853 | 191.9971 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 959.9853
1.2.4.3.9.3.3 | 1.2 | 1.2.4 | UW | PSL | DCC-based SCADA (PY5) | Operator Screen Gensets: DCC-based SCADA (PY5) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 281.934 | 0 | [9 empty] | 12 |  |  |  | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1380 | 0 | 0 | 0 | 1409.67 | 0 | 0 | 1409.67 | 281.934 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1409.67
1.2.4.3.9.3.4 | 1.2 | 1.2.4 | UW | PSL | DCC-based SCADA (PY6) | Operator Screen Gensets: DCC-based SCADA (PY6) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 287.9956 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 12 |  |  |  | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1380 | 0 | 0 | 0 | 1439.9779 | 0 | 0 | 1439.9779 | 287.9956 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1439.9779
1.2.4.3.9.4.3 | 1.2 | 1.2.4 | UW | PSL | DCC-based SCADA (PY5) | Operator Screen Rodwell: DCC-based SCADA (PY5) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 939.78 | 0 | [10 empty] | 40 |  |  | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4600 | 0 | 0 | 4698.9 | 0 | 0 | 4698.9 | 939.78 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9
1.2.4.3.9.4.4 | 1.2 | 1.2.4 | UW | PSL | DCC-based SCADA (PY6) | Operator Screen Rodwell: DCC-based SCADA (PY6) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 959.9853 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 40 |  |  | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4600 | 0 | 0 | 4799.9264 | 0 | 0 | 4799.9264 | 959.9853 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4799.9264
1.2.4.3.9.5.1 | 1.2 | 1.2.4 | UW | PSL | Local-Panel MDS-specific HMI (PY5) | Operator Screen HPP: Local-Panel MDS-specific HMI (PY5) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 422.901 | 0 | [11 empty] | 18 |  | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2070 | 0 | 2114.505 | 0 | 0 | 2114.505 | 422.901 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2114.505
1.2.4.3.9.5.2 | 1.2 | 1.2.4 | UW | PSL | Local-Panel MDS-specific HMI (PY6) | Operator Screen HPP: Local-Panel MDS-specific HMI (PY6) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 431.9934 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 18 |  | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2070 | 0 | 2159.9669 | 0 | 0 | 2159.9669 | 431.9934 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2159.9669
1.2.4.3.9.5.3 | 1.2 | 1.2.4 | UW | PSL | DCC-based SCADA (PY5) | Operator Screen HPP: DCC-based SCADA (PY5) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 939.78 | 0 | [11 empty] | 40 |  | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4600 | 0 | 4698.9 | 0 | 0 | 4698.9 | 939.78 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9
1.2.4.3.9.5.4 | 1.2 | 1.2.4 | UW | PSL | DCC-based SCADA (PY6) | Operator Screen HPP: DCC-based SCADA (PY6) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 959.9853 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 40 |  | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4600 | 0 | 4799.9264 | 0 | 0 | 4799.9264 | 959.9853 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4799.9264
1.2.4.3.9.6.1 | 1.2 | 1.2.4 | UW | PSL | Local-Panel MDS-specific HMI (PY5) | Operator Screen PHS: Local-Panel MDS-specific HMI (PY5) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 375.912 | 0 | [12 empty] | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1840 | 1879.56 | 0 | 0 | 1879.56 | 375.912 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56
1.2.4.3.9.6.2 | 1.2 | 1.2.4 | UW | PSL | Local-Panel MDS-specific HMI (PY6) | Operator Screen PHS: Local-Panel MDS-specific HMI (PY6) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 383.9941 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1840 | 1919.9705 | 0 | 0 | 1919.9705 | 383.9941 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1919.9705
1.2.4.3.9.6.3 | 1.2 | 1.2.4 | UW | PSL | DCC-based SCADA (PY5) | Operator Screen PHS: DCC-based SCADA (PY5) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 939.78 | 0 | [12 empty] | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4600 | 4698.9 | 0 | 0 | 4698.9 | 939.78 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9
1.2.4.3.9.6.4 | 1.2 | 1.2.4 | UW | PSL | DCC-based SCADA (PY6) | Operator Screen PHS: DCC-based SCADA (PY6) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 959.9853 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4600 | 4799.9264 | 0 | 0 | 4799.9264 | 959.9853 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4799.9264
1.2.4.3.10.1 | 1.2 | 1.2.4 | UW | PSL | SCADA - DrillHead (PY5) | TOS Operator Screen: SCADA - DrillHead (PY5) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 187.956 | 0 | [8 empty] | 8 |  |  |  |  | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 920 | 0 | 0 | 0 | 0 | 939.78 | 0 | 0 | 939.78 | 187.956 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78
1.2.4.3.10.2 | 1.2 | 1.2.4 | UW | PSL | SCADA - DrillHead (PY6) | TOS Operator Screen: SCADA - DrillHead (PY6) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 191.9971 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 8 |  |  |  |  | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 920 | 0 | 0 | 0 | 0 | 959.9853 | 0 | 0 | 959.9853 | 191.9971 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 959.9853
1.2.4.3.10.3 | 1.2 | 1.2.4 | UW | PSL | SCADA - Drill_Settings (PY5) | TOS Operator Screen: SCADA - Drill_Settings (PY5) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 187.956 | 0 | [8 empty] | 8 |  |  |  |  | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 920 | 0 | 0 | 0 | 0 | 939.78 | 0 | 0 | 939.78 | 187.956 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78
1.2.4.3.10.4 | 1.2 | 1.2.4 | UW | PSL | SCADA - Drill_Settings (PY6) | TOS Operator Screen: SCADA - Drill_Settings (PY6) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 191.9971 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 8 |  |  |  |  | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 920 | 0 | 0 | 0 | 0 | 959.9853 | 0 | 0 | 959.9853 | 191.9971 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 959.9853
1.2.4.3.10.5 | 1.2 | 1.2.4 | UW | PSL | SCADA - Drilling_Drill Control (PY5) | TOS Operator Screen: SCADA - SCADA - Drilling_Drill Control (PY5) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 281.934 | 0 | [9 empty] | 12 |  |  |  | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1380 | 0 | 0 | 0 | 1409.67 | 0 | 0 | 1409.67 | 281.934 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1409.67
1.2.4.3.10.6 | 1.2 | 1.2.4 | UW | PSL | SCADA - Drilling_Drill Control (PY6) | TOS Operator Screen: SCADA - Drilling_Drill Control (PY6) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 287.9956 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 12 |  |  |  | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1380 | 0 | 0 | 0 | 1439.9779 | 0 | 0 | 1439.9779 | 287.9956 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1439.9779
1.2.4.3.10.7 | 1.2 | 1.2.4 | UW | PSL | SCADA - Drilling_Cable Level Wind (PY5) | TOS Operator Screen: SCADA - SCADA - Drilling_Cable Level Wind (PY5) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 281.934 | 0 | [10 empty] | 12 |  |  | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1380 | 0 | 0 | 1409.67 | 0 | 0 | 1409.67 | 281.934 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1409.67
1.2.4.3.10.8 | 1.2 | 1.2.4 | UW | PSL | SCADA - Drilling_Cable Level Wind (PY6) | TOS Operator Screen: SCADA - Drilling_Cable Level Wind (PY6) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 287.9956 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 12 |  |  | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1380 | 0 | 0 | 1439.9779 | 0 | 0 | 1439.9779 | 287.9956 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1439.9779
1.2.4.3.10.9 | 1.2 | 1.2.4 | UW | PSL | SCADA - Drilling_Hose Level Wind (PY5) | TOS Operator Screen: SCADA - Drilling_Hose Level Wind (PY5) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 281.934 | 0 | [10 empty] | 12 |  |  | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1380 | 0 | 0 | 1409.67 | 0 | 0 | 1409.67 | 281.934 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1409.67
1.2.4.3.10.10 | 1.2 | 1.2.4 | UW | PSL | SCADA - Drilling_Hose Level Wind (PY6) | TOS Operator Screen: SCADA - Drilling_Hose Level Wind (PY6) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 287.9956 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 12 |  |  | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1380 | 0 | 0 | 1439.9779 | 0 | 0 | 1439.9779 | 287.9956 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1439.9779
1.2.4.3.10.11 | 1.2 | 1.2.4 | UW | PSL | SCADA - Return Water Pump (PY5) | TOS Operator Screen: SCADA - Return Water Pump (PY5) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 187.956 | 0 | [11 empty] | 8 |  | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 920 | 0 | 939.78 | 0 | 0 | 939.78 | 187.956 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78
1.2.4.3.10.12 | 1.2 | 1.2.4 | UW | PSL | SCADA - Return Water Pump (PY6) | TOS Operator Screen: SCADA - Return Water Pump (PY6) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 191.9971 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 8 |  | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 920 | 0 | 959.9853 | 0 | 0 | 959.9853 | 191.9971 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 959.9853
1.2.4.3.10.13 | 1.2 | 1.2.4 | UW | PSL | SCADA - Deployment - Cable (PY5) | TOS Operator Screen: SCADA - Deployment - Cable (PY5) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 187.956 | 0 | [12 empty] | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 920 | 939.78 | 0 | 0 | 939.78 | 187.956 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78
1.2.4.3.10.14 | 1.2 | 1.2.4 | UW | PSL | SCADA - Deployment - Cable (PY6) | TOS Operator Screen: SCADA - Deployment - Cable (PY6) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 191.9971 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 920 | 959.9853 | 0 | 0 | 959.9853 | 191.9971 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 959.9853
1.2.4.3.10.15 | 1.2 | 1.2.4 | UW | PSL | SCADA - Deployment Settings (PY5) | TOS Operator Screen: SCADA - Deployment Settings (PY5) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 234.945 | 0 | [12 empty] | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1150 | 1174.725 | 0 | 0 | 1174.725 | 234.945 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1174.725
1.2.4.3.10.16 | 1.2 | 1.2.4 | UW | PSL | SCADA - Deployment Settings (PY6) | TOS Operator Screen: SCADA - Deployment Settings (PY6) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 239.9963 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1150 | 1199.9816 | 0 | 0 | 1199.9816 | 239.9963 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1199.9816
1.2.4.3.11.1 | 1.2 | 1.2.4 | UW | PSL | Build DCC dB schema (PY5) | TOS Operator Screen: Build DCC dB schema (PY5) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 1879.56 | 0 | [7 empty] | 40 | 40 |  |  |  |  | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 4600 | 4600 | 0 | 0 | 0 | 0 | 9397.8 | 0 | 0 | 9397.8 | 1879.56 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9397.8
1.2.4.3.11.2 | 1.2 | 1.2.4 | UW | PSL | Build DCC dB schema (PY6) | TOS Operator Screen: Build DCC dB schema (PY6) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 1919.9705 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 80 | [5 empty] | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 9200 | 0 | 0 | 0 | 0 | 0 | 9599.8527 | 0 | 0 | 9599.8527 | 1919.9705 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9599.8527
1.2.4.3.11.3 | 1.2 | 1.2.4 | UW | PSL | Build Drill dB schema (PY5) | TOS Operator Screen: Build Drill dB schema (PY5) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 939.78 | 0 | [8 empty] | 40 |  |  |  |  | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4600 | 0 | 0 | 0 | 0 | 4698.9 | 0 | 0 | 4698.9 | 939.78 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9
1.2.4.3.11.4 | 1.2 | 1.2.4 | UW | PSL | Build Drill dB schema (PY6) | TOS Operator Screen: Build Drill dB schema (PY6) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 959.9853 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 40 |  |  |  |  | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4600 | 0 | 0 | 0 | 0 | 4799.9264 | 0 | 0 | 4799.9264 | 959.9853 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4799.9264
1.2.4.3.11.5 | 1.2 | 1.2.4 | UW | PSL | Build Deploy dB schema (PY5) | TOS Operator Screen: Build Deploy dB schema (PY5) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 704.835 | 0 | [9 empty] | 30 |  |  |  | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3450 | 0 | 0 | 0 | 3524.175 | 0 | 0 | 3524.175 | 704.835 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3524.175
1.2.4.3.11.6 | 1.2 | 1.2.4 | UW | PSL | Build Deploy dB schema (PY6) | TOS Operator Screen: Build Deploy dB schema (PY6) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 719.989 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 30 |  |  |  | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3450 | 0 | 0 | 0 | 3599.9448 | 0 | 0 | 3599.9448 | 719.989 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3599.9448
1.2.4.3.12 | 1.2 | 1.2.4 | UW | PSL | CS SW Standup Production Computing Hardware, Configure, Verify before Shipment (3x systems) (PY6) | Controls Software: CS SW Standup Production Computing Hardware, Configure, Verify before Shipment (3x systems) (PY6) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C4 | 35% | 5879.9098 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 20 | 30 | 30 | 30 | 30 |  |  | 140 | 0 | 0 | 0 | 0 | 0 | 2300 | 3450 | 3450 | 3450 | 3450 | 0 | 0 | 16799.7422 | 0 | 0 | 16799.7422 | 5879.9098 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16799.7422
1.2.4.3.13 | 1.2 | 1.2.4 | UW | PSL | CS SW MDS-specific HMI Refinement (PY7) | Controls Software: CS SW MDS-specific HMI Refinement (PY7) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C4 | 35% | 3432.1873 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 20 | 20 | 20 | 20 |  |  | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 2300 | 2300 | 2300 | 2300 | 0 | 0 | 9806.2495 | 0 | 0 | 9806.2495 | 3432.1873 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9806.2495
1.2.4.3.14 | 1.2 | 1.2.4 | UW | PSL | CS SW DCC-based SCADA Refinement (PY7) | Controls Software: CS SW DCC-based SCADA Refinement (PY7) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C4 | 35% | 5148.281 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 30 | 30 | 30 | 30 |  |  | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 3450 | 3450 | 3450 | 3450 | 0 | 0 | 14709.3743 | 0 | 0 | 14709.3743 | 5148.281 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14709.3743
1.2.4.3.15 | 1.2 | 1.2.4 | UW | PSL | CS SW TOS-based SCADA Refinement (PY7) | Controls Software: CS SW TOS-based SCADA Refinement (PY7) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C4 | 35% | 5148.281 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 30 | 30 | 30 | 30 |  |  | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 3450 | 3450 | 3450 | 3450 | 0 | 0 | 14709.3743 | 0 | 0 | 14709.3743 | 5148.281 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14709.3743
1.2.4.3.16 | 1.2 | 1.2.4 | UW | PSL | CS SW dB Refinement (PY7) | Controls Software: CS SW dB Refinement (PY7) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C4 | 35% | 5148.281 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 30 | 30 | 30 | 30 |  |  | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 3450 | 3450 | 3450 | 3450 | 0 | 0 | 14709.3743 | 0 | 0 | 14709.3743 | 5148.281 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14709.3743
1.2.4.4.4 | 1.2 | 1.2.4 | UW | PSL | Programming and Testing at PSL | Motor Drives: Programming and Testing at PSL (PSL_Engineer) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 3171.7575 | 0 | [6 empty] | 35 | 35 |  | 35 |  | 30 |  | 135 | 0 | 0 | 0 | 0 | 0 | 4025 | 4025 | 0 | 4025 | 0 | 3450 | 0 | 15858.7875 | 0 | 0 | 15858.7875 | 3171.7575 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15858.7875
1.2.4.5.6 | 1.2 | 1.2.4 | UW | PSL | E-Stop Resupply (PY6) | E-stop: Estop PY6 Resupply |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C4 | 35% | 1007.9845 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 24 |  |  |  |  | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2760 | 0 | 0 | 0 | 0 | 2879.9558 | 0 | 0 | 2879.9558 | 1007.9845 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2879.9558
1.2.4.5.6 | 1.2 | 1.2.4 | UW | PSL | E-Stop Resupply (PY6) | E-stop: Estop PY6 Resupply |  | Labor Hours | Labor - Task | TE | D - Expert Opinion | 77 | 77 | 0% | 0% | Off Ice | C4 | 35% | 674.9114 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 24 |  |  |  |  | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1848 | 0 | 0 | 0 | 0 | 1928.3182 | 0 | 0 | 1928.3182 | 674.9114 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1928.3182
1.2.4.5.6 | 1.2 | 1.2.4 | UW | PSL | E-Stop Resupply (PY6) | E-stop: Estop PY6 Resupply |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 0% | Off Ice | C4 | 35% | 1826.0589 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 5000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 5217.3113 | 0 | 0 | 5217.3113 | 1826.0589 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5217.3113
1.2.4.5.7 | 1.2 | 1.2.4 | UW | PSL | E-Stop Resupply (PY7) | E-stop: Estop PY7 Resupply |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C4 | 35% | 1029.6562 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 24 |  |  |  |  | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2760 | 0 | 0 | 0 | 0 | 2941.8749 | 0 | 0 | 2941.8749 | 1029.6562 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2941.8749
1.2.4.5.7 | 1.2 | 1.2.4 | UW | PSL | E-Stop Resupply (PY7) | E-stop: Estop PY7 Resupply |  | Labor Hours | Labor - Task | TE | D - Expert Opinion | 77 | 77 | 0% | 0% | Off Ice | C4 | 35% | 689.422 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 24 |  |  |  |  | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1848 | 0 | 0 | 0 | 0 | 1969.7771 | 0 | 0 | 1969.7771 | 689.422 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1969.7771
1.2.4.5.7 | 1.2 | 1.2.4 | UW | PSL | E-Stop Resupply (PY7) | E-stop: Estop PY7 Resupply |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 0% | Off Ice | C4 | 35% | 1865.3192 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 5000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 5329.4834 | 0 | 0 | 5329.4834 | 1865.3192 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5329.4834
1.2.4.6.3 | 1.2 | 1.2.4 | UW | PSL | Update Workspace (desk, chairs), Procure Printer & Accessories | DCC: Update Workspace (desk, chairs), Procure Printer & Accessories |  | Labor Hours | Labor Hours | EN-EE | C - Engineering Buildup | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 751.824 | 0 | [5 empty] | 8 | 24 | [6 empty] | 32 | 0 | 0 | 0 | 0 | 920 | 2760 | 0 | 0 | 0 | 0 | 0 | 0 | 3759.12 | 0 | 0 | 3759.12 | 751.824 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3759.12
1.2.4.6.3 | 1.2 | 1.2.4 | UW | PSL | Update Workspace (desk, chairs), Procure Printer & Accessories | DCC: Update Workspace (desk, chairs), Procure Printer & Accessories |  | CapEx | CapEx |  | C - Engineering Buildup |  | 1 | 0% | 0% | Off Ice | C2 | 12.5% | 1375.1944 | 0 | [5 empty] | 10770 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 10770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11001.555 | 0 | 0 | 11001.555 | 1375.1944 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11001.555
1.2.4.7.3 | 1.2 | 1.2.4 | UW | PSL | Fabricate and Test SES & SES to TOS Cables - Signal | Outdoor Cables: Fabricate and Test SES & SES to TOS Cables - Signal |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 939.78 | 0 | [7 empty] | 10 | 10 | 10 | 10 |  |  | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 1150 | 1150 | 1150 | 1150 | 0 | 0 | 4698.9 | 0 | 0 | 4698.9 | 939.78 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9
1.2.4.7.4 | 1.2 | 1.2.4 | UW | PSL | CS Cabling Resupply (PY6) | Outdoor Cables: CS Cabling Resupply (PY6) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C4 | 35% | 1007.9845 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 12 | 12 | [5 empty] | 24 | 0 | 0 | 0 | 0 | 0 | 1380 | 1380 | 0 | 0 | 0 | 0 | 0 | 2879.9558 | 0 | 0 | 2879.9558 | 1007.9845 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2879.9558
1.2.4.7.4 | 1.2 | 1.2.4 | UW | PSL | CS Cabling Resupply (PY6) | Outdoor Cables: CS Cabling Resupply (PY6) |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 0% | Off Ice | C4 | 35% | 1826.0589 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 2500 | 2500 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 2500 | 0 | 0 | 0 | 0 | 0 | 5217.3113 | 0 | 0 | 5217.3113 | 1826.0589 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5217.3113
1.2.4.7.5 | 1.2 | 1.2.4 | UW | PSL | CS Cabling Resupply (PY7) | Outdoor Cables: CS Cabling Resupply (PY7) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C4 | 35% | 1029.6562 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 12 | 12 | [5 empty] | 24 | 0 | 0 | 0 | 0 | 0 | 1380 | 1380 | 0 | 0 | 0 | 0 | 0 | 2941.8749 | 0 | 0 | 2941.8749 | 1029.6562 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2941.8749
1.2.4.7.5 | 1.2 | 1.2.4 | UW | PSL | CS Cabling Resupply (PY7) | Outdoor Cables: CS Cabling Resupply (PY7) |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 0% | Off Ice | C4 | 35% | 1865.3192 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 2500 | 2500 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 2500 | 0 | 0 | 0 | 0 | 0 | 5329.4834 | 0 | 0 | 5329.4834 | 1865.3192 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5329.4834
1.2.4.8.1.2.1 | 1.2 | 1.2.4 | UW | PSL | Procure sample temperature display and digital thermostat, install in test bed heater, test | CS: Procure sample temperature display and digital thermostat, install in test bed heater, test |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 187.956 | 0 |  | 8 | [11 empty] | 8 | 920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78 | 0 | 0 | 939.78 | 187.956 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78
1.2.4.8.1.2.1 | 1.2 | 1.2.4 | UW | PSL | Procure sample temperature display and digital thermostat, install in test bed heater, test | CS: Procure sample temperature display and digital thermostat, install in test bed heater, test |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 0% | Off Ice | C2 | 12.5% | 38.3063 | 0 |  | 300 | [11 empty] | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 306.45 | 0 | 0 | 306.45 | 38.3063 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 306.45
1.2.4.8.1.2.2 | 1.2 | 1.2.4 | UW | PSL | Select and procure temperature display units for heater controls, conversion hardware | CS: Select and procure temperature display units for heater controls, conversion hardware |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 187.956 | 0 |  |  | 8 | [10 empty] | 8 | 0 | 920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78 | 0 | 0 | 939.78 | 187.956 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78
1.2.4.8.1.2.2 | 1.2 | 1.2.4 | UW | PSL | Select and procure temperature display units for heater controls, conversion hardware | CS: Select and procure temperature display units for heater controls, conversion hardware |  | CapEx | CapEx |  | C - Engineering Buildup |  | 1 | 0% | 0% | Off Ice | C2 | 12.5% | 574.5938 | 0 |  |  | 4500 | [10 empty] | 0 | 0 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4596.75 | 0 | 0 | 4596.75 | 574.5938 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4596.75
1.2.4.8.1.2.3 | 1.2 | 1.2.4 | UW | PSL | Replace temperature display units, remove RTD DGHs, transfer net connections, test | CS: Replace temperature display units, remove RTD DGHs, transfer net connections, test |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 563.868 | 0 |  |  |  | 24 | [9 empty] | 24 | 0 | 0 | 2760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2819.34 | 0 | 0 | 2819.34 | 563.868 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2819.34
1.2.4.8.1.2.3 | 1.2 | 1.2.4 | UW | PSL | Replace temperature display units, remove RTD DGHs, transfer net connections, test | CS: Replace temperature display units, remove RTD DGHs, transfer net connections, test |  | Labor Hours | Labor - Task | TE | D - Expert Opinion | 77 | 77 | 0% | 0% | Off Ice | C3 | 20% | 1573.11 | 0 |  |  |  | 100 | [9 empty] | 100 | 0 | 0 | 7700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7865.55 | 0 | 0 | 7865.55 | 1573.11 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7865.55
1.2.4.8.1.2.4 | 1.2 | 1.2.4 | UW | PSL | Select and procure digital thermostats for heater controls, conversion hardware | CS: Select and procure digital thermostats for heater controls, conversion hardware |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 187.956 | 0 | [5 empty] | 8 | [7 empty] | 8 | 0 | 0 | 0 | 0 | 920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78 | 0 | 0 | 939.78 | 187.956 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78
1.2.4.8.1.2.4 | 1.2 | 1.2.4 | UW | PSL | Select and procure digital thermostats for heater controls, conversion hardware | CS: Select and procure digital thermostats for heater controls, conversion hardware |  | CapEx | CapEx |  | C - Engineering Buildup |  | 1 | 0% | 0% | Off Ice | C2 | 12.5% | 633.5854 | 0 | [5 empty] | 4962 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 4962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5068.683 | 0 | 0 | 5068.683 | 633.5854 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5068.683
1.2.4.8.1.2.5 | 1.2 | 1.2.4 | UW | PSL | Write thermostat field replacement procedure | CS: Write thermostat field replacement procedure |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 563.868 | 0 | [7 empty] | 24 | [5 empty] | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 2760 | 0 | 0 | 0 | 0 | 0 | 2819.34 | 0 | 0 | 2819.34 | 563.868 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2819.34
1.2.4.8.1.3.1 | 1.2 | 1.2.4 | UW | PSL | Write rewiring and test instructions for MHP E-stop boxes (fixes switch contact selections made in Gen 1) | CS: Write rewiring and test instructions for MHP E-stop boxes (fixes switch contact selections made in Gen 1) |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 563.868 | 0 |  |  | 24 | [10 empty] | 24 | 0 | 2760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2819.34 | 0 | 0 | 2819.34 | 563.868 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2819.34
1.2.4.8.1.3.2 | 1.2 | 1.2.4 | UW | PSL | Write test procedures for dry heater tests | CS: Write test procedures for dry heater tests |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 751.824 | 0 |  |  | 16 | 16 | [9 empty] | 32 | 0 | 1840 | 1840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3759.12 | 0 | 0 | 3759.12 | 751.824 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3759.12
1.2.4.8.1.3.3 | 1.2 | 1.2.4 | UW | PSL | Assemble equipment to test flow meters (excitation coil and portable pulse generator) | CS: Assemble equipment to test flow meters (excitation coil and portable pulse generator) |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 563.868 | 0 |  |  |  | 12 | 12 | [8 empty] | 24 | 0 | 0 | 1380 | 1380 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2819.34 | 0 | 0 | 2819.34 | 563.868 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2819.34
1.2.4.8.1.3.3 | 1.2 | 1.2.4 | UW | PSL | Assemble equipment to test flow meters (excitation coil and portable pulse generator) | CS: Assemble equipment to test flow meters (excitation coil and portable pulse generator) |  | CapEx | CapEx |  | C - Engineering Buildup |  | 1 | 0% | 0% | Off Ice | C3 | 20% | 155.0637 | 0 |  |  |  | 759 | [9 empty] | 0 | 0 | 0 | 759 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 775.3185 | 0 | 0 | 775.3185 | 155.0637 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 775.3185
1.2.4.8.1.3.4 | 1.2 | 1.2.4 | UW | PSL | Write flow meter test procedure and assemble test kit | CS: Write flow meter test procedure and assemble test kit |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 563.868 | 0 |  |  |  |  | 12 | 12 | [7 empty] | 24 | 0 | 0 | 0 | 1380 | 1380 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2819.34 | 0 | 0 | 2819.34 | 563.868 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2819.34
1.2.4.8.1.5.1 | 1.2 | 1.2.4 | UW | PSL | Develop heater-based sensor readout; (heater temp/flow manifold pressures | CS: Develop heater-based sensor readout; (heater temp/flow manifold pressures |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 2819.34 | 0 |  |  |  |  | 120 | [8 empty] | 120 | 0 | 0 | 0 | 13800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14096.7 | 0 | 0 | 14096.7 | 2819.34 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14096.7
1.2.4.8.1.5.2 | 1.2 | 1.2.4 | UW | PSL | Develop environmental sensor readout; (bldg temps, smoke, e-stop) | CS: Develop environmental sensor readout; (bldg temps, smoke, e-stop) |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 845.802 | 0 |  |  |  |  | 36 | [8 empty] | 36 | 0 | 0 | 0 | 4140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4229.01 | 0 | 0 | 4229.01 | 845.802 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4229.01
1.2.4.8.1.5.3 | 1.2 | 1.2.4 | UW | PSL | Develop heater control; (ON/OFF, Thermostat setpoint) | CS: Develop heater control; (ON/OFF, Thermostat setpoint) |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 939.78 | 0 | [5 empty] | 20 | 20 | [6 empty] | 40 | 0 | 0 | 0 | 0 | 2300 | 2300 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 0 | 0 | 4698.9 | 939.78 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9
1.2.4.8.1.5.7 | 1.2 | 1.2.4 | UW | PSL | Implement interlocks | CS: Implement interlocks |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 469.89 | 0 | [6 empty] | 20 | [6 empty] | 20 | 0 | 0 | 0 | 0 | 0 | 2300 | 0 | 0 | 0 | 0 | 0 | 0 | 2349.45 | 0 | 0 | 2349.45 | 469.89 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2349.45
1.2.4.8.1.5.8 | 1.2 | 1.2.4 | UW | PSL | Document Subsystem | CS: Document Subsystem |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C1 | 9% | 211.4505 | 0 | [7 empty] | 20 | [5 empty] | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 2300 | 0 | 0 | 0 | 0 | 0 | 2349.45 | 0 | 0 | 2349.45 | 211.4505 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2349.45
1.2.4.8.2.1.3 | 1.2 | 1.2.4 | UW | PSL | Develop VFD installation strategy & document, procure materials | CS: Develop VFD installation strategy & document, procure materials |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 939.78 | 0 |  | 40 | [11 empty] | 40 | 4600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 0 | 0 | 4698.9 | 939.78 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9
1.2.4.8.2.1.3 | 1.2 | 1.2.4 | UW | PSL | Develop VFD installation strategy & document, procure materials | CS: Develop VFD installation strategy & document, procure materials |  | Labor Hours | Labor - Task | TE | D - Expert Opinion | 77 | 77 | 0% | 0% | Off Ice | C3 | 20% | 251.6976 | 0 |  | 16 | [11 empty] | 16 | 1232 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1258.488 | 0 | 0 | 1258.488 | 251.6976 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1258.488
1.2.4.8.2.3.2 | 1.2 | 1.2.4 | UW | PSL | Select and procure new power supplies for the network box, procure one RS-485 gateway | CS: Select and procure new power supplies for the network box, procure one RS-485 gateway |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 375.912 | 0 |  | 16 | [11 empty] | 16 | 1840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 0 | 0 | 1879.56 | 375.912 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56
1.2.4.8.2.3.2 | 1.2 | 1.2.4 | UW | PSL | Select and procure new power supplies for the network box, procure one RS-485 gateway | CS: Select and procure new power supplies for the network box, procure one RS-485 gateway |  | CapEx | CapEx |  | C - Engineering Buildup |  | 1 | 0% | 0% | Off Ice | C2 | 12.5% | 118.1109 | 0 |  | 925 | [11 empty] | 0 | 925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 944.8875 | 0 | 0 | 944.8875 | 118.1109 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 944.8875
1.2.4.8.2.3.3 | 1.2 | 1.2.4 | UW | PSL | Redesign and rebuild PHS network box with new I/O, document as-built configuration | CS: Redesign and rebuild PHS network box with new I/O, document as-built configuration |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 3383.208 | 0 |  | 44 | 100 | [10 empty] | 144 | 5060 | 11500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16916.04 | 0 | 0 | 16916.04 | 3383.208 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16916.04
1.2.4.8.2.3.3 | 1.2 | 1.2.4 | UW | PSL | Redesign and rebuild PHS network box with new I/O, document as-built configuration | CS: Redesign and rebuild PHS network box with new I/O, document as-built configuration |  | Labor Hours | Labor - Task | TE | D - Expert Opinion | 77 | 77 | 0% | 0% | Off Ice | C3 | 20% | 629.244 | 0 |  | 20 | 20 | [10 empty] | 40 | 1540 | 1540 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3146.22 | 0 | 0 | 3146.22 | 629.244 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3146.22
1.2.4.8.2.3.3 | 1.2 | 1.2.4 | UW | PSL | Redesign and rebuild PHS network box with new I/O, document as-built configuration | CS: Redesign and rebuild PHS network box with new I/O, document as-built configuration |  | CapEx | CapEx |  | C - Engineering Buildup |  | 1 | 0% | 0% | Off Ice | C3 | 20% | 786.555 | 0 |  | 3850 | [11 empty] | 0 | 3850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3932.775 | 0 | 0 | 3932.775 | 786.555 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3932.775
1.2.4.8.2.3.4 | 1.2 | 1.2.4 | UW | PSL | Indicate where approximately 20 sensor and network cables terminate in PHS and document config. plans | CS: Indicate where approximately 20 sensor and network cables terminate in PHS and document config. plans |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 2537.406 | 0 |  |  | 50 | 58 | [9 empty] | 108 | 0 | 5750 | 6670 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12687.03 | 0 | 0 | 12687.03 | 2537.406 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12687.03
1.2.4.8.2.3.5 | 1.2 | 1.2.4 | UW | PSL | Configure heater-mounted DGH modules, develop and document DGH installation and test plans | CS: Configure heater-mounted DGH modules, develop and document DGH installation and test plans |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 563.868 | 0 |  |  |  | 12 | 12 | [8 empty] | 24 | 0 | 0 | 1380 | 1380 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2819.34 | 0 | 0 | 2819.34 | 563.868 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2819.34
1.2.4.8.2.3.5 | 1.2 | 1.2.4 | UW | PSL | Configure heater-mounted DGH modules, develop and document DGH installation and test plans | CS: Configure heater-mounted DGH modules, develop and document DGH installation and test plans |  | Labor Hours | Labor - Task | TE | D - Expert Opinion | 77 | 77 | 0% | 0% | Off Ice | C3 | 20% | 251.6976 | 0 |  |  |  |  | 16 | [8 empty] | 16 | 0 | 0 | 0 | 1232 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1258.488 | 0 | 0 | 1258.488 | 251.6976 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1258.488
1.2.4.8.2.4 | 1.2 | 1.2.4 | UW | PSL | CS PHS HW4: New E-stop Slap Switch & Box for Outdoor Location | CS PHS HW4: New estop slap switch and box for outdoor location |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 187.956 | 0 |  |  |  |  | 8 | [8 empty] | 8 | 0 | 0 | 0 | 920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78 | 0 | 0 | 939.78 | 187.956 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78
1.2.4.8.2.4 | 1.2 | 1.2.4 | UW | PSL | CS PHS HW4: New E-stop Slap Switch & Box for Outdoor Location | CS PHS HW4: New estop slap switch and box for outdoor location |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 0% | Off Ice | C3 | 20% | 40.86 | 0 |  |  |  |  | 200 | [8 empty] | 0 | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 204.3 | 0 | 0 | 204.3 | 40.86 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 204.3
1.2.4.8.2.5 | 1.2 | 1.2.4 | UW | PSL | CS PHS HW5: Develop heater test procedures, configure test tools, document test plans | CS PHS HW5: Develop heater test procedures, configure test tools, document test plans |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 845.802 | 0 | [5 empty] | 18 | 18 | [6 empty] | 36 | 0 | 0 | 0 | 0 | 2070 | 2070 | 0 | 0 | 0 | 0 | 0 | 0 | 4229.01 | 0 | 0 | 4229.01 | 845.802 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4229.01
1.2.4.8.2.7.1 | 1.2 | 1.2.4 | UW | PSL | Develop and document test plans for all PHS system components | CS: Develop and document test plans for all PHS system components |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 845.802 | 0 | [7 empty] | 18 | 18 |  |  |  |  | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 2070 | 2070 | 0 | 0 | 0 | 0 | 4229.01 | 0 | 0 | 4229.01 | 845.802 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4229.01
1.2.4.8.2.7.2 | 1.2 | 1.2.4 | UW | PSL | Review Gen-1 docs, identify where sensor connections terminated, plan for reconnection and test | CS: Develop and document test plans for all PHS system components |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 845.802 | 0 | [8 empty] | 18 | 18 |  |  |  | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2070 | 2070 | 0 | 0 | 0 | 4229.01 | 0 | 0 | 4229.01 | 845.802 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4229.01
1.2.4.8.2.8.1 | 1.2 | 1.2.4 | UW | PSL | Develop heater-based sensor readout; (heater temp/flow manifold pressures) | CS: Develop heater-based sensor readout; (heater temp/flow manifold pressures) |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 563.868 | 0 |  |  |  |  | 24 | [8 empty] | 24 | 0 | 0 | 0 | 2760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2819.34 | 0 | 0 | 2819.34 | 563.868 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2819.34
1.2.4.8.2.8.2 | 1.2 | 1.2.4 | UW | PSL | Develop environmental sensor readout; (bldg temps, smoke, e-stop) | CS: Develop environmental sensor readout; (bldg temps, smoke, e-stop) |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 375.912 | 0 |  |  |  |  | 16 | [8 empty] | 16 | 0 | 0 | 0 | 1840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 0 | 0 | 1879.56 | 375.912 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56
1.2.4.8.2.8.3 | 1.2 | 1.2.4 | UW | PSL | Develop water tank sensors readout | CS: Develop water tank sensors readout |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 563.868 | 0 | [5 empty] | 12 | 12 | [6 empty] | 24 | 0 | 0 | 0 | 0 | 1380 | 1380 | 0 | 0 | 0 | 0 | 0 | 0 | 2819.34 | 0 | 0 | 2819.34 | 563.868 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2819.34
1.2.4.8.2.8.4 | 1.2 | 1.2.4 | UW | PSL | Develop heater control; (ON/OFF, Thermostat setpoint) | CS: Develop heater control; (ON/OFF, Thermostat setpoint) |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 375.912 | 0 | [6 empty] | 16 | [6 empty] | 16 | 0 | 0 | 0 | 0 | 0 | 1840 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 0 | 0 | 1879.56 | 375.912 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56
1.2.4.8.2.8.5 | 1.2 | 1.2.4 | UW | PSL | Develop AB drive/pump control; (variable speed velocity drives) | CS: Develop AB drive/pump control; (variable speed velocity drives) |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 939.78 | 0 | [6 empty] | 20 | 20 | [5 empty] | 40 | 0 | 0 | 0 | 0 | 0 | 2300 | 2300 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 0 | 0 | 4698.9 | 939.78 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9
1.2.4.8.2.8.10 | 1.2 | 1.2.4 | UW | PSL | Implement interlocks | CS: Implement interlocks |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 469.89 | 0 | [7 empty] | 20 | [5 empty] | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 2300 | 0 | 0 | 0 | 0 | 0 | 2349.45 | 0 | 0 | 2349.45 | 469.89 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2349.45
1.2.4.8.2.8.11 | 1.2 | 1.2.4 | UW | PSL | Document Subsystem | CS: Implement interlocks |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 939.78 | 0 | [8 empty] | 40 |  |  |  |  | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4600 | 0 | 0 | 0 | 0 | 4698.9 | 0 | 0 | 4698.9 | 939.78 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9
1.2.4.8.3.1.3 | 1.2 | 1.2.4 | UW | PSL | Configure VFDs with accessories, connection pigtails, document | CS: Configure VFDs with accessories, connection pigtails, document |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 563.868 | 0 |  | 24 | [11 empty] | 24 | 2760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2819.34 | 0 | 0 | 2819.34 | 563.868 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2819.34
1.2.4.8.3.1.3 | 1.2 | 1.2.4 | UW | PSL | Configure VFDs with accessories, connection pigtails, document | CS: Configure VFDs with accessories, connection pigtails, document |  | Labor Hours | Labor - Task | TE | D - Expert Opinion | 77 | 77 | 0% | 0% | Off Ice | C3 | 20% | 629.244 | 0 |  | 20 | 20 | [10 empty] | 40 | 1540 | 1540 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3146.22 | 0 | 0 | 3146.22 | 629.244 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3146.22
1.2.4.8.3.1.3 | 1.2 | 1.2.4 | UW | PSL | Configure VFDs with accessories, connection pigtails, document | CS: Configure VFDs with accessories, connection pigtails, document |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 0% | Off Ice | C3 | 20% | 1021.5 | 0 |  | 5000 | [11 empty] | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5107.5 | 0 | 0 | 5107.5 | 1021.5 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5107.5
1.2.4.8.3.1.4 | 1.2 | 1.2.4 | UW | PSL | Develop VFD mechanical and electrical installation strategies & document, procure materials | CS: Develop VFD mechanical and electrical installation strategies & document, procure materials |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 939.78 | 0 |  |  |  | 40 | [9 empty] | 40 | 0 | 0 | 4600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 0 | 0 | 4698.9 | 939.78 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9
1.2.4.8.3.1.4 | 1.2 | 1.2.4 | UW | PSL | Develop VFD mechanical and electrical installation strategies & document, procure materials | CS: Develop VFD mechanical and electrical installation strategies & document, procure materials |  | Labor Hours | Labor - Task | TE | D - Expert Opinion | 77 | 77 | 0% | 0% | Off Ice | C3 | 20% | 1258.488 | 0 |  |  |  | 80 | [9 empty] | 80 | 0 | 0 | 6160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6292.44 | 0 | 0 | 6292.44 | 1258.488 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6292.44
1.2.4.8.3.1.4 | 1.2 | 1.2.4 | UW | PSL | Develop VFD mechanical and electrical installation strategies & document, procure materials | CS: Develop VFD mechanical and electrical installation strategies & document, procure materials |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 0% | Off Ice | C3 | 20% | 408.6 | 0 |  |  |  | 2000 | [9 empty] | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2043 | 0 | 0 | 2043 | 408.6 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2043
1.2.4.8.3.1.5 | 1.2 | 1.2.4 | UW | PSL | SW configuration and autotuning, make plan - MDCR/LW, DSHR/LW, RWHR, RWCR, Tower Hoist | CS: SW configuration and autotuning, make plan - MDCR/LW, DSHR/LW, RWHR, RWCR, Tower Hoist |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 1879.56 | 0 |  |  |  |  | 80 | [8 empty] | 80 | 0 | 0 | 0 | 9200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9397.8 | 0 | 0 | 9397.8 | 1879.56 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9397.8
1.2.4.8.3.2.2 | 1.2 | 1.2.4 | UW | PSL | Document changes to E-stop and Reel stop interfaces to motor drives, procure materials, implement | CS: Document changes to E-stop and Reel stop interfaces to motor drives, procure materials, implement |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 2819.34 | 0 |  | 120 | [11 empty] | 120 | 13800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14096.7 | 0 | 0 | 14096.7 | 2819.34 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14096.7
1.2.4.8.3.2.2 | 1.2 | 1.2.4 | UW | PSL | Document changes to E-stop and Reel stop interfaces to motor drives, procure materials, implement | CS: Document changes to E-stop and Reel stop interfaces to motor drives, procure materials, implement |  | Labor Hours | Labor - Task | TE | D - Expert Opinion | 77 | 77 | 0% | 0% | Off Ice | C3 | 20% | 629.244 | 0 |  | 40 | [11 empty] | 40 | 3080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3146.22 | 0 | 0 | 3146.22 | 629.244 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3146.22
1.2.4.8.3.2.2 | 1.2 | 1.2.4 | UW | PSL | Document changes to E-stop and Reel stop interfaces to motor drives, procure materials, implement | CS: Document changes to E-stop and Reel stop interfaces to motor drives, procure materials, implement |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 0% | Off Ice | C3 | 20% | 817.2 | 0 |  | 4000 | [11 empty] | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4086 | 0 | 0 | 4086 | 817.2 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4086
1.2.4.8.3.2.3 | 1.2 | 1.2.4 | UW | PSL | Test refurbished E-stop panels with reel safety junction boxes, I/O boxes, network boxes, drives | CS: Test refurbished E-stop panels with reel safety junction boxes, I/O boxes, network boxes, drives |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 4698.9 | 0 |  |  | 200 | [10 empty] | 200 | 0 | 23000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23494.5 | 0 | 0 | 23494.5 | 4698.9 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23494.5
1.2.4.8.3.2.3 | 1.2 | 1.2.4 | UW | PSL | Test refurbished E-stop panels with reel safety junction boxes, I/O boxes, network boxes, drives | CS: Test refurbished E-stop panels with reel safety junction boxes, I/O boxes, network boxes, drives |  | Labor Hours | Labor - Task | TE | D - Expert Opinion | 77 | 77 | 0% | 0% | Off Ice | C3 | 20% | 1258.488 | 0 |  |  | 80 | [10 empty] | 80 | 0 | 6160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6292.44 | 0 | 0 | 6292.44 | 1258.488 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6292.44
1.2.4.8.3.2.3 | 1.2 | 1.2.4 | UW | PSL | Test refurbished E-stop panels with reel safety junction boxes, I/O boxes, network boxes, drives | CS: Test refurbished E-stop panels with reel safety junction boxes, I/O boxes, network boxes, drives |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 0% | Off Ice | C3 | 20% | 51.075 | 0 |  |  | 250 | [10 empty] | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 255.375 | 0 | 0 | 255.375 | 51.075 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 255.375
1.2.4.8.3.2.6 | 1.2 | 1.2.4 | UW | PSL | Design new E-stop controllers for TOS, build and test boxes | CS: Design new E-stop controllers for TOS, build and test boxes |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 2819.34 | 0 | [6 empty] | 30 | 30 | 30 | 30 |  |  |  | 120 | 0 | 0 | 0 | 0 | 0 | 3450 | 3450 | 3450 | 3450 | 0 | 0 | 0 | 14096.7 | 0 | 0 | 14096.7 | 2819.34 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14096.7
1.2.4.8.3.2.6 | 1.2 | 1.2.4 | UW | PSL | Design new E-stop controllers for TOS, build and test boxes | CS: Design new E-stop controllers for TOS, build and test boxes |  | Labor Hours | Labor - Task | TE | D - Expert Opinion | 77 | 77 | 0% | 0% | Off Ice | C3 | 20% | 1258.488 | 0 | [6 empty] | 20 | 20 | 20 | 20 |  |  |  | 80 | 0 | 0 | 0 | 0 | 0 | 1540 | 1540 | 1540 | 1540 | 0 | 0 | 0 | 6292.44 | 0 | 0 | 6292.44 | 1258.488 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6292.44
1.2.4.8.3.2.6 | 1.2 | 1.2.4 | UW | PSL | Design new E-stop controllers for TOS, build and test boxes | CS: Design new E-stop controllers for TOS, build and test boxes |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 0% | Off Ice | C3 | 20% | 612.9 | 0 | [7 empty] | 1500 | 1500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 1500 | 0 | 0 | 0 | 0 | 3064.5 | 0 | 0 | 3064.5 | 612.9 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3064.5
1.2.4.8.3.3.1 | 1.2 | 1.2.4 | UW | PSL | Spec and procure new power supplies for TOS network boxes, procure DGH gateway, document changes | CS: Spec and procure new power supplies for TOS network boxes, procure DGH gateway, document changes |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 563.868 | 0 |  |  |  | 24 | [9 empty] | 24 | 0 | 0 | 2760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2819.34 | 0 | 0 | 2819.34 | 563.868 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2819.34
1.2.4.8.3.3.1 | 1.2 | 1.2.4 | UW | PSL | Spec and procure new power supplies for TOS network boxes, procure DGH gateway, document changes | CS: Spec and procure new power supplies for TOS network boxes, procure DGH gateway, document changes |  | CapEx | CapEx |  | C - Engineering Buildup |  | 1 | 0% | 0% | Off Ice | C2 | 12.5% | 210.6844 | 0 |  |  |  | 1650 | [9 empty] | 0 | 0 | 0 | 1650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1685.475 | 0 | 0 | 1685.475 | 210.6844 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1685.475
1.2.4.8.3.3.2 | 1.2 | 1.2.4 | UW | PSL | Document plans for TOS network box upgrades, specify and procure tools and materials | CS: Document plans for TOS network box upgrades, specify and procure tools and materials |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 563.868 | 0 |  |  |  |  | 12 | 12 | [7 empty] | 24 | 0 | 0 | 0 | 1380 | 1380 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2819.34 | 0 | 0 | 2819.34 | 563.868 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2819.34
1.2.4.8.3.3.2 | 1.2 | 1.2.4 | UW | PSL | Document plans for TOS network box upgrades, specify and procure tools and materials | CS: Document plans for TOS network box upgrades, specify and procure tools and materials |  | Labor Hours | Labor - Task | TE | D - Expert Opinion | 77 | 77 | 0% | 0% | Off Ice | C3 | 20% | 251.6976 | 0 | [5 empty] | 16 | [7 empty] | 16 | 0 | 0 | 0 | 0 | 1232 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1258.488 | 0 | 0 | 1258.488 | 251.6976 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1258.488
1.2.4.8.3.3.2 | 1.2 | 1.2.4 | UW | PSL | Document plans for TOS network box upgrades, specify and procure tools and materials | CS: Document plans for TOS network box upgrades, specify and procure tools and materials |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 0% | Off Ice | C3 | 20% | 81.72 | 0 | [5 empty] | 400 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 408.6 | 0 | 0 | 408.6 | 81.72 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 408.6
1.2.4.8.3.3.3 | 1.2 | 1.2.4 | UW | PSL | Spec TOS network switch location, spec cables to drives, I/O boxes, network box, DCC modem, PC, PLC, e-stop controller | CS: Spec TOS nework switch location, spec cables to drives, I/O boxes, network box, DCC modem, PC, PLC, e-stop controller |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 1409.67 | 0 | [5 empty] | 30 | 30 | [6 empty] | 60 | 0 | 0 | 0 | 0 | 3450 | 3450 | 0 | 0 | 0 | 0 | 0 | 0 | 7048.35 | 0 | 0 | 7048.35 | 1409.67 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7048.35
1.2.4.8.3.3.3 | 1.2 | 1.2.4 | UW | PSL | Spec TOS network switch location, spec cables to drives, I/O boxes, network box, DCC modem, PC, PLC, e-stop controller | CS: Spec TOS nework switch location, spec cables to drives, I/O boxes, network box, DCC modem, PC, PLC, e-stop controller |  | Labor Hours | Labor - Task | TE | D - Expert Opinion | 77 | 77 | 0% | 0% | Off Ice | C3 | 20% | 503.3952 | 0 | [5 empty] | 16 | 16 | [6 empty] | 32 | 0 | 0 | 0 | 0 | 1232 | 1232 | 0 | 0 | 0 | 0 | 0 | 0 | 2516.976 | 0 | 0 | 2516.976 | 503.3952 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2516.976
1.2.4.8.3.3.3 | 1.2 | 1.2.4 | UW | PSL | Spec TOS network switch location, spec cables to drives, I/O boxes, network box, DCC modem, PC, PLC, e-stop controller | CS: Spec TOS nework switch location, spec cables to drives, I/O boxes, network box, DCC modem, PC, PLC, e-stop controller |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 0% | Off Ice | C3 | 20% | 204.3 | 0 | [6 empty] | 1000 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 1021.5 | 0 | 0 | 1021.5 | 204.3 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1021.5
1.2.4.8.3.3.4 | 1.2 | 1.2.4 | UW | PSL | Design enclosures for TOS PLCs and attached I/O used for payout encoders, load cells; procure parts | CS: Design enclosures for TOS PLCs and attached I/O used for payout encoders, load cells; procure parts |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 1879.56 | 0 | [6 empty] | 20 | 30 | 30 |  |  |  |  | 80 | 0 | 0 | 0 | 0 | 0 | 2300 | 3450 | 3450 | 0 | 0 | 0 | 0 | 9397.8 | 0 | 0 | 9397.8 | 1879.56 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9397.8
1.2.4.8.3.3.4 | 1.2 | 1.2.4 | UW | PSL | Design enclosures for TOS PLCs and attached I/O used for payout encoders, load cells; procure parts | CS: Design enclosures for TOS PLCs and attached I/O used for payout encoders, load cells; procure parts |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 0% | Off Ice | C3 | 20% | 408.6 | 0 | [7 empty] | 2000 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 2043 | 0 | 0 | 2043 | 408.6 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2043
1.2.4.8.3.3.5 | 1.2 | 1.2.4 | UW | PSL | Construct enclosures for TOS PLCs and attached I/O , test | CS: Construct enclosures for TOS PLCs and attached I/O , test |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 1409.67 | 0 | [8 empty] | 20 | 20 | 20 |  |  | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2300 | 2300 | 2300 | 0 | 0 | 7048.35 | 0 | 0 | 7048.35 | 1409.67 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7048.35
1.2.4.8.3.3.5 | 1.2 | 1.2.4 | UW | PSL | Construct enclosures for TOS PLCs and attached I/O , test | CS: Construct enclosures for TOS PLCs and attached I/O , test |  | Labor Hours | Labor - Task | TE | D - Expert Opinion | 77 | 77 | 0% | 0% | Off Ice | C3 | 20% | 1132.6392 | 0 | [8 empty] | 20 | 32 | 20 |  |  | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1540 | 2464 | 1540 | 0 | 0 | 5663.196 | 0 | 0 | 5663.196 | 1132.6392 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5663.196
1.2.4.8.3.3.5 | 1.2 | 1.2.4 | UW | PSL | Construct enclosures for TOS PLCs and attached I/O , test | CS: Construct enclosures for TOS PLCs and attached I/O , test |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 0% | Off Ice | C3 | 20% | 40.86 | 0 | [8 empty] | 200 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 204.3 | 0 | 0 | 204.3 | 40.86 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 204.3
1.2.4.8.3.5.1 | 1.2 | 1.2.4 | UW | PSL | Develop and document on-ice test plans for E-stop, Reel-Stop, and Fault Detection hardware | CS: Develop and document on-ice test plans for E-stop, Reel-Stop, and Fault Detection hardware |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 939.78 | 0 |  |  |  |  | 40 | [8 empty] | 40 | 0 | 0 | 0 | 4600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 0 | 0 | 4698.9 | 939.78 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9
1.2.4.8.3.5.2 | 1.2 | 1.2.4 | UW | PSL | Develop and document on-ice test plans for integrated hardware | CS: Develop and document on-ice test plans for integrated hardware |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 2819.34 | 0 |  |  |  |  | 60 | 60 | [7 empty] | 120 | 0 | 0 | 0 | 6900 | 6900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14096.7 | 0 | 0 | 14096.7 | 2819.34 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14096.7
1.2.4.8.3.6.2 | 1.2 | 1.2.4 | UW | PSL | Test load cells and payout encoders with PLC, verify functionality required for payout control, load sharing | CS: Test load cells and payout encoders with PLC, verify functionality required for payout control, load sharing |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 4698.9 | 0 |  |  | 100 | 100 | [9 empty] | 200 | 0 | 11500 | 11500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23494.5 | 0 | 0 | 23494.5 | 4698.9 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23494.5
1.2.4.8.3.8 | 1.2 | 1.2.4 | UW | PSL | CS TOS HW9: Tower Hoist Reconnect Materials TOS2, Identify and Procure | CS TOS HW9: Tower hoist reconnect materials TOS2, identify and procure |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 939.78 | 0 | [5 empty] | 20 | 20 | [6 empty] | 40 | 0 | 0 | 0 | 0 | 2300 | 2300 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 0 | 0 | 4698.9 | 939.78 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9
1.2.4.8.3.8 | 1.2 | 1.2.4 | UW | PSL | CS TOS HW9: Tower Hoist Reconnect Materials TOS2, Identify and Procure | CS TOS HW9: Tower hoist reconnect materials TOS2, identify and procure |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 0% | Off Ice | C3 | 20% | 204.3 | 0 | [5 empty] | 1000 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1021.5 | 0 | 0 | 1021.5 | 204.3 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1021.5
1.2.4.8.3.9 | 1.2 | 1.2.4 | UW | PSL | CS TOS HW10: Review deployment plans and HW, integrate with drill | CS TOS HW10: Review deployment plans and HW, integrate with drill |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 2819.34 | 0 | [6 empty] | 30 | 30 | 30 | 30 |  |  |  | 120 | 0 | 0 | 0 | 0 | 0 | 3450 | 3450 | 3450 | 3450 | 0 | 0 | 0 | 14096.7 | 0 | 0 | 14096.7 | 2819.34 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14096.7
1.2.4.8.3.10.1 | 1.2 | 1.2.4 | UW | PSL | Develop general control/monitoring software | CS: Develop general control/monitoring software |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 2819.34 | 0 |  |  |  |  | 40 | 40 | 40 | [6 empty] | 120 | 0 | 0 | 0 | 4600 | 4600 | 4600 | 0 | 0 | 0 | 0 | 0 | 0 | 14096.7 | 0 | 0 | 14096.7 | 2819.34 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14096.7
1.2.4.8.3.10.2 | 1.2 | 1.2.4 | UW | PSL | Develop reel control software(MCR/LW, DSHR/LW, RWHR, RWCR, Tower Winch) | CS: Develop reel control software(MCR/LW, DSHR/LW, RWHR, RWCR, Tower Winch) |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 1879.56 | 0 | [6 empty] | 40 | 40 | [5 empty] | 80 | 0 | 0 | 0 | 0 | 0 | 4600 | 4600 | 0 | 0 | 0 | 0 | 0 | 9397.8 | 0 | 0 | 9397.8 | 1879.56 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9397.8
1.2.4.8.3.10.3 | 1.2 | 1.2.4 | UW | PSL | Develop tension-sharing algorithm software (MCR/LW, DSHR/LW) | CS: Develop tension-sharing algorithm software (MCR/LW, DSHR/LW) |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 2819.34 | 0 | [7 empty] | 30 | 30 | 30 | 30 |  |  | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 3450 | 3450 | 3450 | 3450 | 0 | 0 | 14096.7 | 0 | 0 | 14096.7 | 2819.34 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14096.7
1.2.4.8.3.10.4 | 1.2 | 1.2.4 | UW | PSL | Develop drillhead data monitoring interface) | CS: Develop drillhead data monitoring interface) |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 563.868 | 0 | [10 empty] | 24 |  |  | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2760 | 0 | 0 | 2819.34 | 0 | 0 | 2819.34 | 563.868 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2819.34
1.2.4.8.3.10.8 | 1.2 | 1.2.4 | UW | PSL | Implement interlocks | CS: Implement interlocks |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 939.78 | 0 | [11 empty] | 20 | 20 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2300 | 2300 | 4698.9 | 0 | 0 | 4698.9 | 939.78 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9
1.2.4.8.3.10.9 | 1.2 | 1.2.4 | UW | PSL | Document Subsystem | CS: Document Subsystem |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 939.78 | 0 | [12 empty] | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4600 | 4698.9 | 0 | 0 | 4698.9 | 939.78 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9
1.2.4.8.4.1 | 1.2 | 1.2.4 | UW | PSL | CS HW Drillhead sofware/hardware production version | CS HW Drillhead sofware/hardware production version |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 1409.67 | 0 | [8 empty] | 30 | 30 |  |  |  | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3450 | 3450 | 0 | 0 | 0 | 7048.35 | 0 | 0 | 7048.35 | 1409.67 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7048.35
1.2.4.8.4.1 | 1.2 | 1.2.4 | UW | PSL | CS HW Drillhead sofware/hardware production version | CS HW Drillhead sofware/hardware production version |  | CapEx | CapEx |  | C - Engineering Buildup |  | 1 | 0% | 0% | Off Ice | C2 | 12.5% | 320.4956 | 0 | [8 empty] | 2510 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2510 | 0 | 0 | 0 | 0 | 2563.965 | 0 | 0 | 2563.965 | 320.4956 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2563.965
1.2.4.8.4.2.1 | 1.2 | 1.2.4 | UW | PSL | Port C-Lang ingest process to rPI platform & test | CS: Port C-Lang ingest process to rPI platform & test |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 751.824 | 0 | [9 empty] | 16 | 16 |  |  | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1840 | 1840 | 0 | 0 | 3759.12 | 0 | 0 | 3759.12 | 751.824 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3759.12
1.2.4.8.4.2.2 | 1.2 | 1.2.4 | UW | PSL | Integrate rPI platform into PLC infrastructure | CS: Integrate rPI platform into PLC infrastructure |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 939.78 | 0 | [11 empty] | 20 | 20 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2300 | 2300 | 4698.9 | 0 | 0 | 4698.9 | 939.78 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9
1.2.4.8.4.2.3 | 1.2 | 1.2.4 | UW | PSL | Document Subsystem | CS: Document Subsystem |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 939.78 | 0 | [12 empty] | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4600 | 4698.9 | 0 | 0 | 4698.9 | 939.78 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9
1.2.4.8.5.1 | 1.2 | 1.2.4 | UW | PSL | Design, construct and test master E-stop controller, produce documentation and user instructions | CS: Design, construct and test master E-stop controller, produce documentation and user instructions |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 3759.12 | 0 |  |  |  |  | 40 | 40 | 40 | 40 | [5 empty] | 160 | 0 | 0 | 0 | 4600 | 4600 | 4600 | 4600 | 0 | 0 | 0 | 0 | 0 | 18795.6 | 0 | 0 | 18795.6 | 3759.12 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18795.6
1.2.4.8.5.1 | 1.2 | 1.2.4 | UW | PSL | Design, construct and test master E-stop controller, produce documentation and user instructions | CS: Design, construct and test master E-stop controller, produce documentation and user instructions |  | Labor Hours | Labor - Task | TE | D - Expert Opinion | 77 | 77 | 0% | 0% | Off Ice | C3 | 20% | 629.244 | 0 |  |  |  |  | 10 | 10 | 10 | 10 | [5 empty] | 40 | 0 | 0 | 0 | 770 | 770 | 770 | 770 | 0 | 0 | 0 | 0 | 0 | 3146.22 | 0 | 0 | 3146.22 | 629.244 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3146.22
1.2.4.8.5.1 | 1.2 | 1.2.4 | UW | PSL | Design, construct and test master E-stop controller, produce documentation and user instructions | CS: Design, construct and test master E-stop controller, produce documentation and user instructions |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 0% | Off Ice | C3 | 20% | 612.9 | 0 | [5 empty] | 1500 | 1500 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 1500 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 3064.5 | 0 | 0 | 3064.5 | 612.9 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3064.5
1.2.4.8.5.2 | 1.2 | 1.2.4 | UW | PSL | Design and construct general-purpose I/O box for fuel sled, gather required component stock to install | CS: Design and construct general-purpose I/O box for fuel sled, gather required component stock to install |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 1879.56 | 0 | [7 empty] | 20 | 40 | 20 |  |  |  | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 2300 | 4600 | 2300 | 0 | 0 | 0 | 9397.8 | 0 | 0 | 9397.8 | 1879.56 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9397.8
1.2.4.8.5.2 | 1.2 | 1.2.4 | UW | PSL | Design and construct general-purpose I/O box for fuel sled, gather required component stock to install | CS: Design and construct general-purpose I/O box for fuel sled, gather required component stock to install |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 0% | Off Ice | C3 | 20% | 786.555 | 0 | [8 empty] | 3850 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3850 | 0 | 0 | 0 | 0 | 3932.775 | 0 | 0 | 3932.775 | 786.555 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3932.775
1.2.4.8.5.3 | 1.2 | 1.2.4 | UW | PSL | Procure 20 kW three-phase heater for DCC and 208V breakers | CS: Procure 20 kW three-phase heater for DCC and 208V breakers |  | Labor Hours | Labor - Task | TE | D - Expert Opinion | 77 | 77 | 0% | 0% | Off Ice | C3 | 20% | 251.6976 | 0 | [9 empty] | 16 |  |  |  | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1232 | 0 | 0 | 0 | 1258.488 | 0 | 0 | 1258.488 | 251.6976 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1258.488
1.2.4.8.5.3 | 1.2 | 1.2.4 | UW | PSL | Procure 20 kW three-phase heater for DCC and 208V breakers | Procure 20 kW three-phase heater for DCC and 208V breakers |  | CapEx | CapEx |  | C - Engineering Buildup |  | 1 | 0% | 0% | Off Ice | C2 | 12.5% | 402.471 | 0 | [9 empty] | 3152 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3152 | 0 | 0 | 0 | 3219.768 | 0 | 0 | 3219.768 | 402.471 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3219.768
1.2.4.8.5.4 | 1.2 | 1.2.4 | UW | PSL | WT1 VT pump drives: procure, configure, rewire plan | CS: WT1 VT pump drives: procure, configure, rewire plan |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 375.912 | 0 | [9 empty] | 16 |  |  |  | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1840 | 0 | 0 | 0 | 1879.56 | 0 | 0 | 1879.56 | 375.912 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56
1.2.4.8.5.4 | 1.2 | 1.2.4 | UW | PSL | WT1 VT pump drives: procure, configure, rewire plan | CS: WT1 VT pump drives: procure, configure, rewire plan |  | CapEx | CapEx |  | C - Engineering Buildup |  | 1 | 0% | 0% | Off Ice | C2 | 12.5% | 649.0356 | 0 | [9 empty] | 5083 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5083 | 0 | 0 | 0 | 5192.2845 | 0 | 0 | 5192.2845 | 649.0356 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5192.2845
1.2.4.8.5.5 | 1.2 | 1.2.4 | UW | PSL | WT1 VT pump drives: final configure | CS: WT1 VT pump drives: final configure |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 1409.67 | 0 | [11 empty] | 30 | 30 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3450 | 3450 | 7048.35 | 0 | 0 | 7048.35 | 1409.67 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7048.35
1.2.4.8.5.6 | 1.2 | 1.2.4 | UW | PSL | WT1 VT pump drives: install plan and kit | CS: WT1 VT pump drives: install plan and kit |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 1409.67 | 0 | [12 empty] | 60 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6900 | 7048.35 | 0 | 0 | 7048.35 | 1409.67 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7048.35
1.2.4.8.5.6 | 1.2 | 1.2.4 | UW | PSL | WT1 VT pump drives: install plan and kit | CS: WT1 VT pump drives: install plan and kit |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 0% | Off Ice | C3 | 20% | 306.45 | 0 | [12 empty] | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 1532.25 | 0 | 0 | 1532.25 | 306.45 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1532.25
1.2.4.8.5.7.1 | 1.2 | 1.2.4 | UW | PSL | Develop fuel system sensor readout ; (multi-level tank status, control relay status ) | CS: Develop fuel system sensor readout ; (multi-level tank status, control relay status ) |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 845.802 | 0 | [9 empty] | 18 | 18 |  |  | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2070 | 2070 | 0 | 0 | 4229.01 | 0 | 0 | 4229.01 | 845.802 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4229.01
1.2.4.8.5.7.2 | 1.2 | 1.2.4 | UW | PSL | Configure/document Point I/O Block | CS: Configure/document Point I/O Block |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 375.912 | 0 | [10 empty] | 8 | 8 |  | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 920 | 920 | 0 | 1879.56 | 0 | 0 | 1879.56 | 375.912 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56
1.2.4.8.5.7.3 | 1.2 | 1.2.4 | UW | PSL | Document Subsystem | CS: Document Subsystem |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 845.802 | 0 | [11 empty] | 36 |  | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4140 | 0 | 4229.01 | 0 | 0 | 4229.01 | 845.802 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4229.01
1.2.4.8.5.7.4 | 1.2 | 1.2.4 | UW | PSL | Implement interlocks | CS: Implement interlocks |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 469.89 | 0 | [11 empty] | 20 |  | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2300 | 0 | 2349.45 | 0 | 0 | 2349.45 | 469.89 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2349.45
1.2.4.8.6.1 | 1.2 | 1.2.4 | UW | PSL | CS Gensets HW - identify, procure, assemble | CS: CS Gensets HW - identify, procure, assemble |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 959.9853 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 20 | 20 | [5 empty] | 40 | 0 | 0 | 0 | 0 | 0 | 2300 | 2300 | 0 | 0 | 0 | 0 | 0 | 4799.9264 | 0 | 0 | 4799.9264 | 959.9853 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4799.9264
1.2.4.8.6.1 | 1.2 | 1.2.4 | UW | PSL | CS Gensets HW - identify, procure, assemble | CS: CS Gensets HW - identify, procure, assemble |  | Labor Hours | Labor - Task | TE | D - Expert Opinion | 77 | 77 | 0% | 0% | Off Ice | C3 | 20% | 642.7727 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 20 | 20 | [5 empty] | 40 | 0 | 0 | 0 | 0 | 0 | 1540 | 1540 | 0 | 0 | 0 | 0 | 0 | 3213.8637 | 0 | 0 | 3213.8637 | 642.7727 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3213.8637
1.2.4.8.6.1 | 1.2 | 1.2.4 | UW | PSL | CS Gensets HW - identify, procure, assemble | CS: CS Gensets HW - identify, procure, assemble |  | CapEx | CapEx |  | C - Engineering Buildup |  | 1 | 0% | 0% | Off Ice | C3 | 20% | 803.4659 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 3850 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 3850 | 0 | 0 | 0 | 0 | 0 | 0 | 4017.3297 | 0 | 0 | 4017.3297 | 803.4659 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4017.3297
1.2.4.8.6.2.1 | 1.2 | 1.2.4 | UW | PSL | Develop sensor readout; (bldg temps, fuel temps, supply/return water temps) | CS: Develop sensor readout; (bldg temps, fuel temps, supply/return water temps) |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 959.9853 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 20 | 20 |  |  |  |  | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 2300 | 2300 | 0 | 0 | 0 | 0 | 4799.9264 | 0 | 0 | 4799.9264 | 959.9853 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4799.9264
1.2.4.8.6.2.2 | 1.2 | 1.2.4 | UW | PSL | Develop sensor readout; (engine jacket temps, exhaust temps, drip pan status) | CS: Develop sensor readout; (engine jacket temps, exhaust temps, drip pan status) |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 959.9853 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 20 | 20 |  |  |  | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2300 | 2300 | 0 | 0 | 0 | 4799.9264 | 0 | 0 | 4799.9264 | 959.9853 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4799.9264
1.2.4.8.6.2.3 | 1.2 | 1.2.4 | UW | PSL | Configure/document network switch | CS: Configure/document network switch |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 191.9971 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 8 |  |  |  | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 920 | 0 | 0 | 0 | 959.9853 | 0 | 0 | 959.9853 | 191.9971 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 959.9853
1.2.4.8.6.2.4 | 1.2 | 1.2.4 | UW | PSL | Configure/document RTA gateway to M-DGH interface | CS: Configure/document RTA gateway to M-DGH interface |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 239.9963 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 10 |  |  |  | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1150 | 0 | 0 | 0 | 1199.9816 | 0 | 0 | 1199.9816 | 239.9963 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1199.9816
1.2.4.8.6.2.5 | 1.2 | 1.2.4 | UW | PSL | Configure/document M-DGHs | CS: Configure/document M-DGHs |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 479.9926 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 20 |  |  | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2300 | 0 | 0 | 2399.9632 | 0 | 0 | 2399.9632 | 479.9926 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2399.9632
1.2.4.8.6.2.6 | 1.2 | 1.2.4 | UW | PSL | Document Subsystem | CS: Document Subsystem |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 959.9853 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 20 | 20 |  | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2300 | 2300 | 0 | 4799.9264 | 0 | 0 | 4799.9264 | 959.9853 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4799.9264
1.2.4.8.7.1.3 | 1.2 | 1.2.4 | UW | PSL | Develop VFD mechanical and electrical installation strategies & document, procure materials | CS: Develop VFD mechanical and electrical installation strategies & document, procure materials |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 1691.604 | 0 |  |  |  | 36 | 36 | [8 empty] | 72 | 0 | 0 | 4140 | 4140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8458.02 | 0 | 0 | 8458.02 | 1691.604 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8458.02
1.2.4.8.7.1.3 | 1.2 | 1.2.4 | UW | PSL | Develop VFD mechanical and electrical installation strategies & document, procure materials | CS: Develop VFD mechanical and electrical installation strategies & document, procure materials |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 0% | Off Ice | C3 | 20% | 204.3 | 0 |  |  |  | 1000 | [9 empty] | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1021.5 | 0 | 0 | 1021.5 | 204.3 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1021.5
1.2.4.8.7.2.1 | 1.2 | 1.2.4 | UW | PSL | Define requirements and procedures for reading signals applied to HPP motor drives | CS: Define requirements and procedures for reading signals applied to HPP motor drives |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 375.912 | 0 |  | 16 | [11 empty] | 16 | 1840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 0 | 0 | 1879.56 | 375.912 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56
1.2.4.8.7.2.2 | 1.2 | 1.2.4 | UW | PSL | Define method of verifying sensor readout accuracy (reading vs stimulus) | CS: Define method of verifying sensor readout accuracy (reading vs stimulus) |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 375.912 | 0 |  |  | 16 | [10 empty] | 16 | 0 | 1840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 0 | 0 | 1879.56 | 375.912 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56
1.2.4.8.7.2.3 | 1.2 | 1.2.4 | UW | PSL | Develop and document test procedures for on-ice personnel | CS: Develop and document test procedures for on-ice personnel |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 375.912 | 0 |  |  |  | 16 | [9 empty] | 16 | 0 | 0 | 1840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 0 | 0 | 1879.56 | 375.912 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56
1.2.4.8.7.3.1 | 1.2 | 1.2.4 | UW | PSL | Define core HPP PLC functions and requirements, define needed I/O connections | CS: Define core HPP PLC functions and requirements, define needed I/O connections |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 939.78 | 0 |  |  | 20 | 20 | [9 empty] | 40 | 0 | 2300 | 2300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 0 | 0 | 4698.9 | 939.78 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9
1.2.4.8.7.3.2 | 1.2 | 1.2.4 | UW | PSL | Select PLC, Enclosure, Power supplies, I/O expansion cards, power distribution, connectors and cables | CS: Select PLC, Enclosure, Power supplies, I/O expansion cards, power distribution, connectors and cables |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 939.78 | 0 |  |  |  | 20 | 20 | [8 empty] | 40 | 0 | 0 | 2300 | 2300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 0 | 0 | 4698.9 | 939.78 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9
1.2.4.8.7.3.3 | 1.2 | 1.2.4 | UW | PSL | Design and Construct PLC enclosure | CS: Design and Construct PLC enclosure |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 751.824 | 0 |  |  |  |  | 32 | [8 empty] | 32 | 0 | 0 | 0 | 3680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3759.12 | 0 | 0 | 3759.12 | 751.824 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3759.12
1.2.4.8.7.3.3 | 1.2 | 1.2.4 | UW | PSL | Design and Construct PLC enclosure | CS: Design and Construct PLC enclosure |  | Labor Hours | Labor - Task | TE | D - Expert Opinion | 77 | 77 | 0% | 0% | Off Ice | C3 | 20% | 629.244 | 0 |  |  |  |  | 20 | 20 | [7 empty] | 40 | 0 | 0 | 0 | 1540 | 1540 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3146.22 | 0 | 0 | 3146.22 | 629.244 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3146.22
1.2.4.8.7.3.3 | 1.2 | 1.2.4 | UW | PSL | Design and Construct PLC enclosure | CS: Design and Construct PLC enclosure |  | CapEx | CapEx |  | C - Engineering Buildup |  | 1 | 0% | 0% | Off Ice | C3 | 20% | 1440.315 | 0 | [5 empty] | 7050 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 7050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7201.575 | 0 | 0 | 7201.575 | 1440.315 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7201.575
1.2.4.8.7.3.4 | 1.2 | 1.2.4 | UW | PSL | Test HPP PLC enclosure with HPP Network box | CS: Test HPP PLC enclosure with HPP Network box |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 563.868 | 0 | [6 empty] | 24 | [6 empty] | 24 | 0 | 0 | 0 | 0 | 0 | 2760 | 0 | 0 | 0 | 0 | 0 | 0 | 2819.34 | 0 | 0 | 2819.34 | 563.868 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2819.34
1.2.4.8.7.4.2 | 1.2 | 1.2.4 | UW | PSL | Procure additional drives for charge pumps (4), AC and network pigtail materials | CS: Procure additional drives for charge pumps (4), AC and network pigtail materials |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 375.912 | 0 |  |  |  |  | 16 | [8 empty] | 16 | 0 | 0 | 0 | 1840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 0 | 0 | 1879.56 | 375.912 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56
1.2.4.8.7.4.2 | 1.2 | 1.2.4 | UW | PSL | Procure additional drives for charge pumps (4), AC and network pigtail materials | CS: Procure additional drives for charge pumps (4), AC and network pigtail materials |  | CapEx | CapEx |  | C - Engineering Buildup |  | 1 | 0% | 0% | Off Ice | C2 | 12.5% | 1852.1072 | 0 |  |  |  |  | 14505 | [8 empty] | 0 | 0 | 0 | 0 | 14505 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14816.8575 | 0 | 0 | 14816.8575 | 1852.1072 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14816.8575
1.2.4.8.7.4.3 | 1.2 | 1.2.4 | UW | PSL | Connectorize four drives with power and network pigtails, test each in test bed | CS: Connectorize four drives with power and network pigtails, test each in test bed |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 563.868 | 0 | [7 empty] | 24 | [5 empty] | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 2760 | 0 | 0 | 0 | 0 | 0 | 2819.34 | 0 | 0 | 2819.34 | 563.868 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2819.34
1.2.4.8.7.4.3 | 1.2 | 1.2.4 | UW | PSL | Connectorize four drives with power and network pigtails, test each in test bed | CS: Connectorize four drives with power and network pigtails, test each in test bed |  | Labor Hours | Labor - Task | TE | D - Expert Opinion | 77 | 77 | 0% | 0% | Off Ice | C3 | 20% | 629.244 | 0 | [7 empty] | 20 | 20 |  |  |  |  | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 1540 | 1540 | 0 | 0 | 0 | 0 | 3146.22 | 0 | 0 | 3146.22 | 629.244 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3146.22
1.2.4.8.7.4.3 | 1.2 | 1.2.4 | UW | PSL | Connectorize four drives with power and network pigtails, test each in test bed | CS: Connectorize four drives with power and network pigtails, test each in test bed |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 0% | Off Ice | C3 | 20% | 204.3 | 0 | [7 empty] | 1000 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 1021.5 | 0 | 0 | 1021.5 | 204.3 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1021.5
1.2.4.8.7.7.1 | 1.2 | 1.2.4 | UW | PSL | Select and procure E-stop relays for pump VFD Enable signals | CS: Select and procure E-stop relays for pump VFD Enable signals |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 187.956 | 0 | [7 empty] | 8 | [5 empty] | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 920 | 0 | 0 | 0 | 0 | 0 | 939.78 | 0 | 0 | 939.78 | 187.956 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78
1.2.4.8.7.7.1 | 1.2 | 1.2.4 | UW | PSL | Select and procure E-stop relays for pump VFD Enable signals | CS: Select and procure E-stop relays for pump VFD Enable signals |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 0% | Off Ice | C3 | 20% | 40.86 | 0 | [7 empty] | 200 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 204.3 | 0 | 0 | 204.3 | 40.86 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 204.3
1.2.4.8.7.7.2 | 1.2 | 1.2.4 | UW | PSL | Develop and document rewiring instructions for HPP E-stop box | CS: Develop and document rewiring instructions for HPP E-stop box |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 375.912 | 0 | [8 empty] | 16 |  |  |  |  | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1840 | 0 | 0 | 0 | 0 | 1879.56 | 0 | 0 | 1879.56 | 375.912 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56
1.2.4.8.7.9.1 | 1.2 | 1.2.4 | UW | PSL | Develop and document test plans for all HPP system components | CS: Develop and document test plans for all HPP system components |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 845.802 | 0 | [9 empty] | 36 |  |  |  | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4140 | 0 | 0 | 0 | 4229.01 | 0 | 0 | 4229.01 | 845.802 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4229.01
1.2.4.8.7.9.2 | 1.2 | 1.2.4 | UW | PSL | Review Gen-1 docs, identify where sensor connections terminated, plan for field integration and test | CS: Review Gen-1 docs, identify where sensor connections terminated, plan for field integration and test |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 751.824 | 0 | [9 empty] | 32 |  |  |  | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3680 | 0 | 0 | 0 | 3759.12 | 0 | 0 | 3759.12 | 751.824 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3759.12
1.2.4.8.7.10.1 | 1.2 | 1.2.4 | UW | PSL | Develop water path sensor readout; (pressure, temp, flow) | CS: Develop water path sensor readout; (pressure, temp, flow) |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 939.78 | 0 |  |  |  |  | 40 | [8 empty] | 40 | 0 | 0 | 0 | 4600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 0 | 0 | 4698.9 | 939.78 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9
1.2.4.8.7.10.2 | 1.2 | 1.2.4 | UW | PSL | Develop environmental sensor readout; (bldg temps, smoke, e-stop) | CS: Develop environmental sensor readout; (bldg temps, smoke, e-stop) |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 939.78 | 0 |  |  |  |  | 40 | [8 empty] | 40 | 0 | 0 | 0 | 4600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 0 | 0 | 4698.9 | 939.78 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9
1.2.4.8.7.10.9 | 1.2 | 1.2.4 | UW | PSL | Implement interlocks | CS: Implement interlocks |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 469.89 | 0 | [9 empty] | 20 |  |  |  | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2300 | 0 | 0 | 0 | 2349.45 | 0 | 0 | 2349.45 | 469.89 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2349.45
1.2.4.8.7.10.10 | 1.2 | 1.2.4 | UW | PSL | Document Subsystem | CS: Document Subsystem |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 939.78 | 0 | [9 empty] | 40 |  |  |  | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4600 | 0 | 0 | 0 | 4698.9 | 0 | 0 | 4698.9 | 939.78 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9
1.2.4.8.8.2.1 | 1.2 | 1.2.4 | UW | PSL | Develop ARA-drill sensor readout; (heater flows, head press, tank level) | CS: Develop ARA-drill sensor readout; (heater flows, head press, tank level) |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 1879.56 | 0 |  |  | 80 | [10 empty] | 80 | 0 | 9200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9397.8 | 0 | 0 | 9397.8 | 1879.56 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9397.8
1.2.4.8.8.2.2 | 1.2 | 1.2.4 | UW | PSL | Develop AB drive/pump control; (variable speed velocity drives) | CS: Develop AB drive/pump control; (variable speed velocity drives) |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 939.78 | 0 |  |  |  | 20 | 20 | [8 empty] | 40 | 0 | 0 | 2300 | 2300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 0 | 0 | 4698.9 | 939.78 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9
1.2.4.8.8.2.3 | 1.2 | 1.2.4 | UW | PSL | Configure/document Point I/O Block | CS: Configure/document Point I/O Block |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 375.912 | 0 |  |  |  |  | 16 | [8 empty] | 16 | 0 | 0 | 0 | 1840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 0 | 0 | 1879.56 | 375.912 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56
1.2.4.8.8.2.4 | 1.2 | 1.2.4 | UW | PSL | Configure/document network switch | CS: Configure/document network switch |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 187.956 | 0 | [5 empty] | 8 | [7 empty] | 8 | 0 | 0 | 0 | 0 | 920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78 | 0 | 0 | 939.78 | 187.956 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78
1.2.4.8.8.2.5 | 1.2 | 1.2.4 | UW | PSL | Configure/document RTA gateway to M-DGH interface | CS: Configure/document RTA gateway to M-DGH interface |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 375.912 | 0 | [5 empty] | 16 | [7 empty] | 16 | 0 | 0 | 0 | 0 | 1840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 0 | 0 | 1879.56 | 375.912 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56
1.2.4.8.8.2.6 | 1.2 | 1.2.4 | UW | PSL | Configure/document M-DGHs | CS: Configure/document M-DGHs |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 469.89 | 0 | [6 empty] | 20 | [6 empty] | 20 | 0 | 0 | 0 | 0 | 0 | 2300 | 0 | 0 | 0 | 0 | 0 | 0 | 2349.45 | 0 | 0 | 2349.45 | 469.89 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2349.45
1.2.4.8.8.2.7 | 1.2 | 1.2.4 | UW | PSL | Implement interlocks | CS: Implement interlocks |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 469.89 | 0 | [6 empty] | 20 | [6 empty] | 20 | 0 | 0 | 0 | 0 | 0 | 2300 | 0 | 0 | 0 | 0 | 0 | 0 | 2349.45 | 0 | 0 | 2349.45 | 469.89 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2349.45
1.2.4.8.8.2.8 | 1.2 | 1.2.4 | UW | PSL | Document Subsystem | CS: Document Subsystem |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 939.78 | 0 | [7 empty] | 40 | [5 empty] | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 4600 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 0 | 0 | 4698.9 | 939.78 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9
1.2.5.2.6 | 1.2 | 1.2.5 | UW | PSL | GEN-1, 2, 3 - Procure Batteries | GEN-2, 3, PDM - Procure Batteries |  | Labor Hours | Labor Hours | EN-ME | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C2 | 12.5% | 117.4725 | 0 |  | 8 | [11 empty] | 8 | 920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78 | 0 | 0 | 939.78 | 117.4725 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78
1.2.5.2.6 | 1.2 | 1.2.5 | UW | PSL | GEN-1, 2, 3 - Procure Batteries | GEN-2, 3, PDM - Procure Batteries |  | CapEx | CapEx |  | C - Engineering Buildup |  | 1 | 0% | 0% | Off Ice | C2 | 12.5% | 255.375 | 0 |  | 2000 | [11 empty] | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2043 | 0 | 0 | 2043 | 255.375 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2043
1.2.5.2.7 | 1.2 | 1.2.5 | UW | PSL | Generator 2 Subcontract Repairs in New Zealand | GEN-2, 3, PDM - Generator 2 Subcontract Repairs in New Zealand |  | CapEx | CapEx |  | C - Engineering Buildup |  | 1 | 0% | 0% | Off Ice | C2 | 12.5% | 1890.2858 | 0 | Round trip trucking (Bascik Transport) from USAP site to Terra Cat $345 NZD plus GST- $275 USD estimated. Terra Cat quoted repair of injection pump governor shaft and electronic controller - $5229.03 USD. Estimated $6500.00 USD for diagnosis/repair/testing of alternator output issue and $2800 for structural repair of the 20' ISO shipping container that houses the power plant. Terra Cat was not willing to quote without diagnosis of alternator/structural issues. Total $14,804.03 USD |  | 7402 | 7402 | [9 empty] | 0 | 0 | 7402 | 7402 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15122.286 | 0 | 0 | 15122.286 | 1890.2858 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15122.286
1.2.5.2.8 | 1.2 | 1.2.5 | UW | PSL | PDM - Procure Batteries | PDM - Procure Batteries |  | CapEx | CapEx |  | C - Engineering Buildup |  | 1 | 0% | 0% | Off Ice | C2 | 12.5% | 76.6125 | 0 | [10 empty] | 600 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600 | 0 | 0 | 612.9 | 0 | 0 | 612.9 | 76.6125 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 612.9
1.2.5.2.9 | 1.2 | 1.2.5 | UW | PSL | Develop SOW for South Pole Power Generation Technical Support Subcontract & Communicate with Vendor (PY6) | GEN-2, 3, PDM - Develop SOW for South Pole Power Generation Technical Support Subcontract & Communicate with Vendor |  | Labor Hours | Labor Hours | EN-ME | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 959.9853 | 0 | South Pole Contractor cost captured in FS2 (2023-24). | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | [10 empty] | 40 | 2300 | 2300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4799.9264 | 0 | 0 | 4799.9264 | 959.9853 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4799.9264
1.2.5.2.10 | 1.2 | 1.2.5 | UW | PSL | Predeployment Coordination with Power Generation Technical Support Subcontract Vendor (PY6) | GEN-2, 3, PDM - Predeployment Coordination with Power Generation Technical Support Subcontract Vendor (PY6) |  | Labor Hours | Labor Hours | EN-ME | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C4 | 35% | 3324.5892 | 0 | [11 empty] | 20 | 20 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2300 | 2300 | 4698.9 | 0 | 0 | 4698.9 | 1644.615 | 0 | 20 | 20 | [10 empty] | 40 | 2300 | 2300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4799.9264 | 0 | 0 | 4799.9264 | 1679.9742 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9498.8264
1.2.5.4.3 | 1.2 | 1.2.5 | UW | PSL | System Elec Dist: Design & Procure | Elec Dist. System: Design & Procure |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C4 | 35% | 822.3075 | 0 |  | 20 | [11 empty] | 20 | 2300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2349.45 | 0 | 0 | 2349.45 | 822.3075 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2349.45
1.2.5.4.3 | 1.2 | 1.2.5 | UW | PSL | System Elec Dist: Design & Procure | Elec Dist. System: Design & Procure |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 0% | Off Ice | C4 | 35% | 1952.0865 | 0 |  | 5460 | [11 empty] | 0 | 5460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5577.39 | 0 | 0 | 5577.39 | 1952.0865 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5577.39
1.2.5.4.5 | 1.2 | 1.2.5 | UW | PSL | System Elec Dist: Build and Test Subcomponents | Elec Dist. System: Build and Test Subcomponents |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C4 | 35% | 1480.1535 | 0 | [5 empty] | 18 |  | 18 | [5 empty] | 36 | 0 | 0 | 0 | 0 | 2070 | 0 | 2070 | 0 | 0 | 0 | 0 | 0 | 4229.01 | 0 | 0 | 4229.01 | 1480.1535 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4229.01
1.2.5.4.8 | 1.2 | 1.2.5 | UW | PSL | System Electrical Resupply (PY6) | Elec Dist. System: System Electrical Resupply (PY6) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C4 | 35% | 1007.9845 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 24 | [5 empty] | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 2760 | 0 | 0 | 0 | 0 | 0 | 2879.9558 | 0 | 0 | 2879.9558 | 1007.9845 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2879.9558
1.2.5.4.8 | 1.2 | 1.2.5 | UW | PSL | System Electrical Resupply (PY6) | Elec Dist. System: System Electrical Resupply (PY6) |  | Labor Hours | Labor - Task | TE | D - Expert Opinion | 77 | 77 | 0% | 0% | Off Ice | C4 | 35% | 674.9114 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 24 | [5 empty] | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 1848 | 0 | 0 | 0 | 0 | 0 | 1928.3182 | 0 | 0 | 1928.3182 | 674.9114 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1928.3182
1.2.5.4.8 | 1.2 | 1.2.5 | UW | PSL | System Electrical Resupply (PY6) | Elec Dist. System: System Electrical Resupply (PY6) |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 0% | Off Ice | C4 | 35% | 1826.0589 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 5000 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 5217.3113 | 0 | 0 | 5217.3113 | 1826.0589 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5217.3113
1.2.5.4.10 | 1.2 | 1.2.5 | UW | PSL | System Electrical Resupply (PY7) | Elec Dist. System: System Electrical Resupply (PY7) |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C4 | 35% | 1029.6562 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 24 | [5 empty] | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 2760 | 0 | 0 | 0 | 0 | 0 | 2941.8749 | 0 | 0 | 2941.8749 | 1029.6562 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2941.8749
1.2.5.4.10 | 1.2 | 1.2.5 | UW | PSL | System Electrical Resupply (PY7) | Elec Dist. System: System Electrical Resupply (PY7) |  | Labor Hours | Labor - Task | TE | D - Expert Opinion | 77 | 77 | 0% | 0% | Off Ice | C4 | 35% | 689.422 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 24 | [5 empty] | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 1848 | 0 | 0 | 0 | 0 | 0 | 1969.7771 | 0 | 0 | 1969.7771 | 689.422 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1969.7771
1.2.5.4.10 | 1.2 | 1.2.5 | UW | PSL | System Electrical Resupply (PY7) | Elec Dist. System: System Electrical Resupply (PY7) |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 0% | Off Ice | C4 | 35% | 1865.3192 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 5000 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 5329.4834 | 0 | 0 | 5329.4834 | 1865.3192 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5329.4834
1.2.6.1.3 | 1.2 | 1.2.6 | UW | PSL | Procure Repair Parts, Replacements (PY6) | Water Tanks: Procure Repair Parts, Replacements (PY6) |  | Labor Hours | Labor - Task | EN-ME | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C4 | 35% | 1007.9845 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 24 | [5 empty] | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 2760 | 0 | 0 | 0 | 0 | 0 | 2879.9558 | 0 | 0 | 2879.9558 | 1007.9845 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2879.9558
1.2.6.1.3 | 1.2 | 1.2.6 | UW | PSL | Procure Repair Parts, Replacements (PY6) | Water Tanks: Procure Repair Parts, Replacements (PY6) |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 0% | Off Ice | C4 | 35% | 1826.0589 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 5000 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 5217.3113 | 0 | 0 | 5217.3113 | 1826.0589 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5217.3113
1.2.6.2.5 | 1.2 | 1.2.6 | UW | PSL | Procure Repair/Replacement Components (PY5) | Pumps: Procure Repair/Replacement Components (PY5) |  | Labor Hours | Labor - Task | EN-ME | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C4 | 35% | 1644.615 | 0 | [7 empty] | 40 | [5 empty] | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 4600 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 0 | 0 | 4698.9 | 1644.615 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9
1.2.6.2.5 | 1.2 | 1.2.6 | UW | PSL | Procure Repair/Replacement Components (PY5) | Pumps: Procure Repair/Replacement Components (PY5)) |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 0% | Off Ice | C4 | 35% | 2359.665 | 0 | [7 empty] | 6600 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6600 | 0 | 0 | 0 | 0 | 0 | 6741.9 | 0 | 0 | 6741.9 | 2359.665 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6741.9
1.2.6.2.6 | 1.2 | 1.2.6 | UW | PSL | Procure Repair/Replacement Components (PY6) | Pumps: Procure Repair/Replacement Components (PY6) |  | Labor Hours | Labor - Task | EN-ME | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C4 | 35% | 1007.9845 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 24 | [5 empty] | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 2760 | 0 | 0 | 0 | 0 | 0 | 2879.9558 | 0 | 0 | 2879.9558 | 1007.9845 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2879.9558
1.2.6.2.6 | 1.2 | 1.2.6 | UW | PSL | Procure Repair/Replacement Components (PY6) | Pumps: Procure Repair/Replacement Components (PY6) |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 0% | Off Ice | C4 | 35% | 1826.0589 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 5000 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 5217.3113 | 0 | 0 | 5217.3113 | 1826.0589 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5217.3113
1.2.6.4.9 | 1.2 | 1.2.6 | UW | PSL | Procure External Interconnect Materials (PY6) | Interconnect: Procure External Interconnect materials (PY6) |  | Labor Hours | Labor - Task | EN-ME | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C4 | 35% | 1679.9742 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 40 |  |  |  |  | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4600 | 0 | 0 | 0 | 0 | 4799.9264 | 0 | 0 | 4799.9264 | 1679.9742 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4799.9264
1.2.6.4.9 | 1.2 | 1.2.6 | UW | PSL | Procure External Interconnect Materials (PY6) | Interconnect: Procure External Interconnect materials (PY6) |  | CapEx | CapEx |  | C - Engineering Buildup |  | 1 | 0% | 0% | Off Ice | C4 | 35% | 3853.3496 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 10551 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10551 | 0 | 0 | 0 | 0 | 11009.5702 | 0 | 0 | 11009.5702 | 3853.3496 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11009.5702
1.2.6.5.1 | 1.2 | 1.2.6 | UW | PSL | Identify Replacement Water Hoses (1-1/2", 3/4", and 1/2" Hose) | MDS: Evaluate Water Hoses (1-1/2", 3/4", and 1/2" Hose) |  | Labor Hours | Labor - Task | EN-ME | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C4 | 35% | 335.9948 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 8 | [5 empty] | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 920 | 0 | 0 | 0 | 0 | 0 | 959.9853 | 0 | 0 | 959.9853 | 335.9948 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 959.9853
1.2.6.5.2 | 1.2 | 1.2.6 | UW | PSL | Identify Replacement Fuel Hoses | MDS: Evaluate Fuel Hoses |  | Labor Hours | Labor - Task | EN-ME | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C4 | 35% | 335.9948 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 8 | [5 empty] | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 920 | 0 | 0 | 0 | 0 | 0 | 959.9853 | 0 | 0 | 959.9853 | 335.9948 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 959.9853
1.2.6.5.3 | 1.2 | 1.2.6 | UW | PSL | Procure Replacements and Spares | MDS: Procure Replacements Internal Hoses and Spares |  | Labor Hours | Labor - Task | EN-ME | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C4 | 35% | 671.9897 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 8 | 8 |  |  |  |  | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 920 | 920 | 0 | 0 | 0 | 0 | 1919.9705 | 0 | 0 | 1919.9705 | 671.9897 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1919.9705
1.2.6.5.3 | 1.2 | 1.2.6 | UW | PSL | Procure Replacements and Spares | MDS: Procure Replacements Internal Hoses and Spares |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 0% | Off Ice | C4 | 35% | 4150.632 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 11365 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11365 | 0 | 0 | 0 | 0 | 0 | 11858.9485 | 0 | 0 | 11858.9485 | 4150.632 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11858.9485
1.2.7.1.7 | 1.2 | 1.2.7 | UW | PSL | IFD Follow-up Tasks (PY5) | Support Equipment: IFD Follow-up Tasks (PY5) |  | Labor Hours | Labor - Task | EN-ME | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 939.78 | 0 |  | 40 | [11 empty] | 40 | 4600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 0 | 0 | 4698.9 | 939.78 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9
1.2.7.1.7 | 1.2 | 1.2.7 | UW | PSL | IFD Follow-up Tasks (PY5) | Support Equipment: IFD Follow-up Tasks (PY5) |  | Labor Hours | Labor - Task | TE | D - Expert Opinion | 77 | 77 | 0% | 0% | Off Ice | C3 | 20% | 377.5464 | 0 |  | 24 | [11 empty] | 24 | 1848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1887.732 | 0 | 0 | 1887.732 | 377.5464 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1887.732
1.2.7.1.7 | 1.2 | 1.2.7 | UW | PSL | IFD Follow-up Tasks (PY5) | Support Equipment: IFD Follow-up Tasks (PY5) |  | CapEx | CapEx |  | C - Engineering Buildup |  | 1 | 0% | 0% | Off Ice | C3 | 20% | 408.6 | 0 |  | 2000 | [11 empty] | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2043 | 0 | 0 | 2043 | 408.6 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2043
1.2.7.2.1 | 1.2 | 1.2.7 | UW | PSL | Identify Spares and Replacements | Support Equipment: Identify Spares and Replacements |  | Labor Hours | Labor - Task | EN-ME | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C4 | 35% | 986.769 | 0 |  | 8 |  | 8 | 8 | [8 empty] | 24 | 920 | 0 | 920 | 920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2819.34 | 0 | 0 | 2819.34 | 986.769 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2819.34
1.2.7.2.2 | 1.2 | 1.2.7 | UW | PSL | Procure Spares and Replacements | Support Equipment: Procure Spares and Replacements |  | Labor Hours | Labor - Task | EN-ME | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C4 | 35% | 1662.2946 | 0 | [9 empty] | 8 | 12 |  |  | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 920 | 1380 | 0 | 0 | 2349.45 | 0 | 0 | 2349.45 | 822.3075 | 0 | 8 | [6 empty] | 6 | 6 |  |  |  | 20 | 920 | 0 | 0 | 0 | 0 | 0 | 0 | 690 | 690 | 0 | 0 | 0 | 2399.9632 | 0 | 0 | 2399.9632 | 839.9871 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4749.4132
1.2.7.2.2 | 1.2 | 1.2.7 | UW | PSL | Procure Spares and Replacements | Support Equipment: Procure Spares and Replacements |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 0% | Off Ice | C4 | 35% | 2890.9471 | 0 | [10 empty] | 4000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 0 | 0 | 4086 | 0 | 0 | 4086 | 1430.1 | 0 | 1000 | [6 empty] | 1000 | 2000 |  |  |  | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 2000 | 0 | 0 | 0 | 4173.849 | 0 | 0 | 4173.849 | 1460.8472 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8259.849
1.2.7.2.4 | 1.2 | 1.2.7 | UW | PSL | Procure Hose Stock and Fittings (FY5) | Support Equipment: Procure Hose Stock and Fittings |  | Labor Hours | Labor - Task | EN-ME | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C4 | 35% | 986.769 | 0 | [8 empty] | 8 | 16 |  |  |  | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 920 | 1840 | 0 | 0 | 0 | 2819.34 | 0 | 0 | 2819.34 | 986.769 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2819.34
1.2.7.2.4 | 1.2 | 1.2.7 | UW | PSL | Procure Hose Stock and Fittings (FY5) | Support Equipment: Procure Hose Stock and Fittings |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 0% | Off Ice | C4 | 35% | 1787.625 | 0 | [9 empty] | 5000 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 5107.5 | 0 | 0 | 5107.5 | 1787.625 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5107.5
1.2.7.2.5 | 1.2 | 1.2.7 | UW | PSL | Spare Parts Inventory and Catalog - Electrical/Controls | Support Equipment: Spare Parts Inventory and Catalog - Electrical/Controls |  | Labor Hours | Labor - Task | EN-ME | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C4 | 35% | 657.846 | 0 | [9 empty] | 8 | 8 |  |  | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 920 | 920 | 0 | 0 | 1879.56 | 0 | 0 | 1879.56 | 657.846 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56
1.2.7.3.1 | 1.2 | 1.2.7 | UW | PSL | Identify Upgrade-Replacements, Spares | Shops: Identify Upgrade-Replacements, Spares |  | Labor Hours | Labor - Task | EN-ME | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C4 | 35% | 657.846 | 0 | [7 empty] | 8 | 8 |  |  |  |  | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 920 | 920 | 0 | 0 | 0 | 0 | 1879.56 | 0 | 0 | 1879.56 | 657.846 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56
1.2.7.3.2 | 1.2 | 1.2.7 | UW | PSL | Procure Upgrade-Replacements, Spares | Shops: Procure Upgrade-Replacements, Spares |  | Labor Hours | Labor - Task | EN-ME | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C4 | 35% | 1315.692 | 0 | [8 empty] | 16 | 8 | 8 |  |  | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1840 | 920 | 920 | 0 | 0 | 3759.12 | 0 | 0 | 3759.12 | 1315.692 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3759.12
1.2.7.3.2 | 1.2 | 1.2.7 | UW | PSL | Procure Upgrade-Replacements, Spares | Shops: Procure Upgrade-Replacements, Spares |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 0% | Off Ice | C4 | 35% | 1251.3375 | 0 | [8 empty] | 1500 | 1000 | 1000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 1000 | 1000 | 0 | 0 | 3575.25 | 0 | 0 | 3575.25 | 1251.3375 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3575.25
1.2.7.4.7 | 1.2 | 1.2.7 | UW | PSL | Commission/Maintenance/Decommission (PY5) | Testbed: Commission/Maintenance/Decommission (PY5) |  | Labor Hours | Labor - Task | TE | D - Expert Opinion | 77 | 77 | 0% | 0% | Off Ice | C4 | 35% | 2202.354 | 0 | [5 empty] | 20 | 20 | 20 | 20 |  |  |  |  | 80 | 0 | 0 | 0 | 0 | 1540 | 1540 | 1540 | 1540 | 0 | 0 | 0 | 0 | 6292.44 | 0 | 0 | 6292.44 | 2202.354 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6292.44
1.2.7.4.7 | 1.2 | 1.2.7 | UW | PSL | Commission/Maintenance/Decommission (PY5) | Testbed: Commission/Maintenance/Decommission (PY5) |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C4 | 35% | 3289.23 | 0 | [5 empty] | 20 | 20 | 20 | 20 |  |  |  |  | 80 | 0 | 0 | 0 | 0 | 2300 | 2300 | 2300 | 2300 | 0 | 0 | 0 | 0 | 9397.8 | 0 | 0 | 9397.8 | 3289.23 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9397.8
1.2.7.4.7 | 1.2 | 1.2.7 | UW | PSL | Commission/Maintenance/Decommission (PY5) | Testbed: Commission/Maintenance/Decommission (PY5) |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 0% | Off Ice | C4 | 35% | 3575.25 | 0 | [5 empty] | 2500 | 2500 | 2500 | 2500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2500 | 2500 | 2500 | 2500 | 0 | 0 | 0 | 0 | 10215 | 0 | 0 | 10215 | 3575.25 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10215
1.2.7.4.8 | 1.2 | 1.2.7 | UW | PSL | Commission/Maintenance/Decommission (PY6) | Testbed: Commission/Maintenance/Decommission (PY6) |  | Labor Hours | Labor - Task | TE | D - Expert Opinion | 77 | 77 | 0% | 0% | Off Ice | C4 | 35% | 2249.7046 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 20 | 20 | 20 | 20 |  |  |  |  | 80 | 0 | 0 | 0 | 0 | 1540 | 1540 | 1540 | 1540 | 0 | 0 | 0 | 0 | 6427.7275 | 0 | 0 | 6427.7275 | 2249.7046 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6427.7275
1.2.7.4.8 | 1.2 | 1.2.7 | UW | PSL | Commission/Maintenance/Decommission (PY6) | Testbed: Commission/Maintenance/Decommission (PY6) |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C4 | 35% | 3359.9484 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 20 | 20 | 20 | 20 |  |  |  |  | 80 | 0 | 0 | 0 | 0 | 2300 | 2300 | 2300 | 2300 | 0 | 0 | 0 | 0 | 9599.8527 | 0 | 0 | 9599.8527 | 3359.9484 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9599.8527
1.2.7.4.8 | 1.2 | 1.2.7 | UW | PSL | Commission/Maintenance/Decommission (PY6) | Testbed: Commission/Maintenance/Decommission (PY6) |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 0% | Off Ice | C4 | 35% | 3652.1179 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2500 | 2500 | 2500 | 2500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2500 | 2500 | 2500 | 2500 | 0 | 0 | 0 | 0 | 10434.6225 | 0 | 0 | 10434.6225 | 3652.1179 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10434.6225
1.2.7.4.9 | 1.2 | 1.2.7 | UW | PSL | Commission/Maintenance/Decommission (PY7) | Testbed: Commission/Maintenance/Decommission (PY7) |  | Labor Hours | Labor - Task | TE | D - Expert Opinion | 77 | 77 | 0% | 0% | Off Ice | C4 | 35% | 2298.0733 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 20 | 20 | 20 | 20 |  |  |  |  | 80 | 0 | 0 | 0 | 0 | 1540 | 1540 | 1540 | 1540 | 0 | 0 | 0 | 0 | 6565.9236 | 0 | 0 | 6565.9236 | 2298.0733 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6565.9236
1.2.7.4.9 | 1.2 | 1.2.7 | UW | PSL | Commission/Maintenance/Decommission (PY7) | Testbed: Commission/Maintenance/Decommission (PY7) |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C4 | 35% | 3432.1873 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 20 | 20 | 20 | 20 |  |  |  |  | 80 | 0 | 0 | 0 | 0 | 2300 | 2300 | 2300 | 2300 | 0 | 0 | 0 | 0 | 9806.2495 | 0 | 0 | 9806.2495 | 3432.1873 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9806.2495
1.2.7.4.9 | 1.2 | 1.2.7 | UW | PSL | Commission/Maintenance/Decommission (PY7) | Testbed: Commission/Maintenance/Decommission (PY7) |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 0% | Off Ice | C4 | 35% | 3730.6384 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2500 | 2500 | 2500 | 2500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2500 | 2500 | 2500 | 2500 | 0 | 0 | 0 | 0 | 10658.9669 | 0 | 0 | 10658.9669 | 3730.6384 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10658.9669
1.2.7.4.10 | 1.2 | 1.2.7 | UW | PSL | Commission/Maintenance/Decommission (PY8) | Testbed: Commission/Maintenance/Decommission (PY8) |  | Labor Hours | Labor - Task | TE | D - Expert Opinion | 77 | 77 | 0% | 0% | Off Ice | C4 | 35% | 1173.7409 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | [10 empty] | 40 | 1540 | 1540 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3353.5455 | 0 | 0 | 3353.5455 | 1173.7409 | 0 | 3353.5455
1.2.7.4.10 | 1.2 | 1.2.7 | UW | PSL | Commission/Maintenance/Decommission (PY8) | Testbed: Commission/Maintenance/Decommission (PY8) |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C4 | 35% | 1752.9897 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | [10 empty] | 40 | 2300 | 2300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5008.5419 | 0 | 0 | 5008.5419 | 1752.9897 | 0 | 5008.5419
1.2.7.4.10 | 1.2 | 1.2.7 | UW | PSL | Commission/Maintenance/Decommission (PY8) | Testbed: Commission/Maintenance/Decommission (PY8) |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 0% | Off Ice | C4 | 35% | 762.1694 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 1000 | [10 empty] | 0 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2177.6269 | 0 | 0 | 2177.6269 | 762.1694 | 0 | 2177.6269
1.2.7.5.5 | 1.2 | 1.2.7 | UW | PSL | Procure Tools & Equipment, & Consumables | Tools & Equipment: Procure Tools & Consumables |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C4 | 35% | 3024.4097 | 0 | [9 empty] | 8 | 8 | 8 |  | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 920 | 920 | 920 | 0 | 2819.34 | 0 | 0 | 2819.34 | 986.769 | 0 | [8 empty] | 8 | 8 | 8 |  | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 920 | 920 | 920 | 0 | 2879.9558 | 0 | 0 | 2879.9558 | 1007.9845 | 0 | [7 empty] | 8 | 8 | 8 |  |  | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 920 | 920 | 920 | 0 | 0 | 2941.8749 | 0 | 0 | 2941.8749 | 1029.6562 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8641.1707
1.2.7.5.5 | 1.2 | 1.2.7 | UW | PSL | Procure Tools & Equipment, & Consumables | Tools & Equipment: Procure Tools & Consumables |  | M & S | M & S |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C4 | 35% | 8382.8748 | 2903.8717 | [10 empty] | 2500 | 2500 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 2500 | 0 | 5107.5 | 0 | 2706.975 | 7814.475 | 1787.625 | 947.4412 | [9 empty] | 2500 | 2500 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 2500 | 0 | 5217.3113 | 0 | 2765.175 | 7982.4862 | 1826.0589 | 967.8112 | [8 empty] | 2500 | 2500 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 2500 | 0 | 0 | 5329.4834 | 0 | 2824.6262 | 8154.1097 | 1865.3192 | 988.6192 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23951.0709
1.2.8.1.2 | 1.2 | 1.2.8 | UW | PSL | FS1 Off-Ice Safety Training & PPE Procurement - 10 FTE Drillers (10-primary 2-alternates) & 1 Safety Officer | FS1 - Off-Ice EHWD & Safety Training - 5 Drillers (w/ 2 alternates) (Driller_PSL_DirectHire) |  | Labor Hours | Labor - Task | TE | D - Expert Opinion | 77 | 77 | 0% | 0% | Off Ice | C1 | 9% | 1982.1186 | 0 | Contract staff training/travel labor - 3 Direct Hire + 2 alternates - assuming 7 days @ 8 hours per | [10 empty] | 280 |  | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21560 | 0 | 22023.54 | 0 | 0 | 22023.54 | 1982.1186 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22023.54
1.2.8.1.2 | 1.2 | 1.2.8 | UW | PSL | FS1 Off-Ice Safety Training & PPE Procurement - 10 FTE Drillers (10-primary 2-alternates) & 1 Safety Officer | FS1 - Off-Ice EHWD & Safety Training - 10 PSL (Driller Lead/Engineers) |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C1 | 9% | 3171.7575 | 0 | PSL staff training labor - Assuming 30 hours per PSL team member for training x 10 PSL Engineers | [10 empty] | 300 |  | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34500 | 0 | 35241.75 | 0 | 0 | 35241.75 | 3171.7575 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35241.75
1.2.8.1.2 | 1.2 | 1.2.8 | UW | PSL | FS1 Off-Ice Safety Training & PPE Procurement - 10 FTE Drillers (10-primary 2-alternates) & 1 Safety Officer | FS1 - Off-Ice EHWD & Safety Training - Safety Training Materials/Vendors |  | M & S | M & S |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C1 | 9% | 703.3028 | 243.6278 | SafeStart, rigging, and Red Cross training - additional training materials added in coordination with USAP contractor | [10 empty] | 5000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 5107.5 | 0 | 2706.975 | 7814.475 | 459.675 | 243.6277 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7814.475
1.2.8.1.2 | 1.2 | 1.2.8 | UW | PSL | FS1 Off-Ice Safety Training & PPE Procurement - 10 FTE Drillers (10-primary 2-alternates) & 1 Safety Officer | FS1 - Off-Ice EHWD & Safety Training - Safety Equipment/Consumables |  | M & S | M & S |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C1 | 9% | 309.4532 | 107.1962 | Procurement of replacement smoke detector batteries, smoke detectors, toe warmers, hand warmers, oxygen, CO, H2S, monitors, first aid kit, work gloves, knee pads, goggles, and N95 masks | [7 empty] | 1000 | 1000 | 200 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 1000 | 200 | 0 | 0 | 2247.3 | 0 | 1191.069 | 3438.369 | 202.257 | 107.1962 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3438.369
1.2.8.1.2 | 1.2 | 1.2.8 | UW | PSL | FS1 Off-Ice Safety Training & PPE Procurement - 10 FTE Drillers (10-primary 2-alternates) & 1 Safety Officer | FS1 - Off-Ice EHWD & Safety Training - 5 DH Drillers (w/ 2 alternates) - (Direct Hire Travel -1 Domestic, 2 International, 2 Local) | Foreign | Travel | Travel |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C1 | 9% | 900.2275 | 311.8435 | Contract staff training Foreign Travel - 3 Direct Hire w/ 2 alternates - 5 Total (estimating 2 local, 1 domestic, 2 intl). Duration 7 days. $8200 total travel cost 2 Local - No travel costs 1 Domestic - $1800 2 International - $6400 | [10 empty] | 6400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6400 | 0 | 6537.6 | 0 | 3464.928 | 10002.528 | 588.384 | 311.8435 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10002.528
1.2.8.1.2 | 1.2 | 1.2.8 | UW | PSL | FS1 Off-Ice Safety Training & PPE Procurement - 10 FTE Drillers (10-primary 2-alternates) & 1 Safety Officer | FS1 - Off-Ice EHWD & Safety Training - 5 DH Drillers (w/ 2 alternates) - (Direct Hire Travel -1 Domestic, 2 International, 2 Local) | Domestic | Travel | Travel |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C1 | 9% | 253.189 | 87.706 | Contract staff training Domestic Travel - 3 Direct Hire w/ 2 alternates - 5 Total (estimating 2 local, 1 domestic, 2 intl). Duration 7 days. $8200 total travel cost 2 Local - No travel costs 1 Domestic - $1800 2 International - $6400 | [10 empty] | 1800 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 1838.7 | 0 | 974.511 | 2813.211 | 165.483 | 87.706 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2813.211
1.2.8.1.3 | 1.2 | 1.2.8 | UW | PSL | FS2 Off-Ice Safety Training & PPE Procurement - 16 Drillers (14 - Primary 2 - alternates) & 1 Safety Officer | FS2 - Off-Ice EHWD & Safety Training - 8 Drillers (2 alternates) (Driller_PSL_DirectHire) |  | Labor Hours | Labor - Task | TE | D - Expert Opinion | 77 | 77 | 0% | 0% | Off Ice | C1 | 9% | 3239.5746 | 0 | Contract staff training/travel labor - 8 Direct Hire (w/ 2 alternates) - assuming 7 days @ 8 hours per (448 hours total) | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 224 | 224 |  | 448 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17248 | 17248 | 0 | 35995.2738 | 0 | 0 | 35995.2738 | 3239.5746 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35995.2738
1.2.8.1.3 | 1.2 | 1.2.8 | UW | PSL | FS2 Off-Ice Safety Training & PPE Procurement - 16 Drillers (14 - Primary 2 - alternates) & 1 Safety Officer | FS2 - 10 PSL (Driller_Lead/Engineer) |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C1 | 9% | 3239.9503 | 0 | PSL staff training labor - Assuming 30 hours per PSL team member for training x 10 PSL Engineers | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 150 | 150 |  | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17250 | 17250 | 0 | 35999.4476 | 0 | 0 | 35999.4476 | 3239.9503 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35999.4476
1.2.8.1.3 | 1.2 | 1.2.8 | UW | PSL | FS2 Off-Ice Safety Training & PPE Procurement - 16 Drillers (14 - Primary 2 - alternates) & 1 Safety Officer | FS2 - Off-Ice EHWD & Safety Training - Safety Training Materials/Vendors |  | M & S | M & S |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C1 | 9% | 359.2119 | 124.4329 | Red Cross and job specific training TBD - additional training materials added in coordination with USAP contractor | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 2608.6556 | 0 | 1382.5875 | 3991.2431 | 234.779 | 124.4329 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3991.2431
1.2.8.1.3 | 1.2 | 1.2.8 | UW | PSL | FS2 Off-Ice Safety Training & PPE Procurement - 16 Drillers (14 - Primary 2 - alternates) & 1 Safety Officer | FS2 - Off-Ice EHWD & Safety Training - Safety Equipment/Consumables |  | M & S | M & S |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C1 | 9% | 359.2119 | 124.4329 | Procurement of replacement smoke detector batteries, smoke detectors, toe warmers, hand warmers, absorbent pads, N95 masks, smoke and CO monitors | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 1000 | 1000 | 500 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 1000 | 500 | 0 | 0 | 2608.6556 | 0 | 1382.5875 | 3991.2431 | 234.779 | 124.4329 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3991.2431
1.2.8.1.3 | 1.2 | 1.2.8 | UW | PSL | FS2 Off-Ice Safety Training & PPE Procurement - 16 Drillers (14 - Primary 2 - alternates) & 1 Safety Officer | FS2 - Off-Ice EHWD & Safety Training - 8 DH Drillers w/ 2 alternates - (Direct Hire Travel -1 Domestic 2 International) | Foreign | Travel | Travel |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C1 | 9% | 1379.3736 | 477.8222 | Contract staff training International Travel - 8 Direct Hire w/ 2 alternates Duration 7 days. 2 Local - No travel costs 3 Domestic - $5400 3 International - $9600 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 4800 | 4800 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4800 | 4800 | 0 | 10017.2376 | 0 | 5309.1359 | 15326.3735 | 901.5514 | 477.8222 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15326.3735
1.2.8.1.3 | 1.2 | 1.2.8 | UW | PSL | FS2 Off-Ice Safety Training & PPE Procurement - 16 Drillers (14 - Primary 2 - alternates) & 1 Safety Officer | FS2 - Off-Ice EHWD & Safety Training - 6 DH Drillers w/ 2 alternates - (Direct Hire Travel -1 Domestic 2 International) | Domestic | Travel | Travel |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C1 | 9% | 775.8977 | 268.775 | Contract staff training Domestic Travel - 8 Direct Hire w/ 2 alternates Duration 7 days. 2 Local - No travel costs 3 Domestic - $5400 3 International - $9600 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 2700 | 2700 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2700 | 2700 | 0 | 5634.6962 | 0 | 2986.389 | 8621.0851 | 507.1227 | 268.775 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8621.0851
1.2.8.1.4 | 1.2 | 1.2.8 | UW | PSL | FS3 Off-Ice Safety Training & PPE Procurement - 32 Drillers (28 - primary 4 - alternates) & 1 Safety Officer | FS3 - Off-Ice EHWD & Safety Training - 22 Drillers (w/ 4 alternates) (Driller_PSL_DirectHire) |  | Labor Hours | Labor - Task | TE | D - Expert Opinion | 77 | 77 | 0% | 0% | Off Ice | C1 | 9% | 19855.353 | 0 | Contract staff training/travel labor - 24 Direct Hire - 20 deploy w/ 4 alternates. Duration 14 - 8 hour days with travel. | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 1344 | 1344 |  | 2688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 103488 | 103488 | 0 | 220615.033 | 0 | 0 | 220615.033 | 19855.353 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220615.033
1.2.8.1.4 | 1.2 | 1.2.8 | UW | PSL | FS3 Off-Ice Safety Training & PPE Procurement - 32 Drillers (28 - primary 4 - alternates) & 1 Safety Officer | FS3 - Off-Ice EHWD & Safety Training - 10 PSL Staff - 2 Rotators (Engineer/Driller PSL_Lead) |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C1 | 9% | 6619.2184 | 0 | PSL staff training labor - Assuming 60 hours per PSL team member for training x 10 PSL Engineers | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 300 | 300 |  | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34500 | 34500 | 0 | 73546.8715 | 0 | 0 | 73546.8715 | 6619.2184 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73546.8715
1.2.8.1.4 | 1.2 | 1.2.8 | UW | PSL | FS3 Off-Ice Safety Training & PPE Procurement - 32 Drillers (28 - primary 4 - alternates) & 1 Safety Officer | FS3 - Off-Ice EHWD & Safety Training - Safety Training Materials/Vendors |  | M & S | M & S |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C1 | 9% | 733.8699 | 254.2164 | SafeStart, rigging, job specific training (TBD) and Red Cross training - additional training materials added in coordination with USAP contractor | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2000 | 3000 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 3000 | 0 | 0 | 0 | 5329.4834 | 0 | 2824.6262 | 8154.1097 | 479.6535 | 254.2164 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8154.1097
1.2.8.1.4 | 1.2 | 1.2.8 | UW | PSL | FS3 Off-Ice Safety Training & PPE Procurement - 32 Drillers (28 - primary 4 - alternates) & 1 Safety Officer | FS3 - Off-Ice EHWD & Safety Training - Safety Equipment/Consumables |  | M & S | M & S |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C1 | 9% | 660.4829 | 228.7947 | Procurement of replacement smoke detector batteries, smoke detectors, toe warmers, hand warmers, absorbent pads, N95 masks, smoke and CO monitors | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2000 | 2000 | 500 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 2000 | 500 | 0 | 0 | 4796.5351 | 0 | 2542.1636 | 7338.6987 | 431.6882 | 228.7947 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7338.6987
1.2.8.1.4 | 1.2 | 1.2.8 | UW | PSL | FS3 Off-Ice Safety Training & PPE Procurement - 32 Drillers (28 - primary 4 - alternates) & 1 Safety Officer | FS3 - Off-Ice EHWD & Safety Training - 24 Drillers (Direct Hire Travel) | Foreign | Travel | Travel |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C1 | 9% | 2818.0603 | 976.1908 | Contract staff - Training Foreign Travel - 24 Direct Hire - 20 deploy w/ 4 alternates Duration 14 days with travel. 6 Local - No travel costs 12 Domestic - $21600 6 International - $19200 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 9600 | 9600 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9600 | 9600 | 0 | 20465.2164 | 0 | 10846.5647 | 31311.7811 | 1841.8695 | 976.1908 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31311.7811
1.2.8.1.4 | 1.2 | 1.2.8 | UW | PSL | FS3 Off-Ice Safety Training & PPE Procurement - 32 Drillers (28 - primary 4 - alternates) & 1 Safety Officer | FS3 - Off-Ice EHWD & Safety Training - 24 Drillers (Direct Hire Travel) | Domestic | Travel | Travel |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C1 | 9% | 3170.3178 | 1098.2147 | Contract staff -Training Domestic Travel - 24 Direct Hire - 20 deploy w/ 4 alternates Duration 14 days with travel. 6 Local - No travel costs 12 Domestic - $21600 6 International - $19200 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 10800 | 10800 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10800 | 10800 | 0 | 23023.3685 | 0 | 12202.3853 | 35225.7538 | 2072.1032 | 1098.2147 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35225.7538
1.2.8.1.5 | 1.2 | 1.2.8 | UW | PSL | FS3 Off-Ice Logging Winch Training with IDP (3 Drillers 1 day) | FS3 - Off-Ice Logging Winch Training - 3 Drillers 1 day |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C1 | 9% | 264.7687 | 0 | Logging Winch Training - 3 Drillers 1 day training with IDP support (IDP cost in Calibration WBS) | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 24 |  |  | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2760 | 0 | 0 | 2941.8749 | 0 | 0 | 2941.8749 | 264.7687 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2941.8749
1.2.8.5.2 | 1.2 | 1.2.8 | UW | PSL | PQ, ECW & Deployment Travel Costs (FS1) | Deployment Travel & PQ Costs (FS1) (Driller_PSL_Manager) |  | Labor Hours | Labor - Task | EN | E - Extrapolation from Actuals | 115 | 115 | 0% | 0% | Off Ice | C1 | 9% | 1397.2394 | 0 | 1 Drill Manager, 5 days deployment travel 3 days redeployment | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 40 |  |  | 24 | [7 empty] | 64 | 0 | 4600 | 0 | 0 | 2760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7679.8822 | 0 | 0 | 7679.8822 | 691.1894 | 0 |  | 40 |  |  | 24 | [7 empty] | 64 | 0 | 4600 | 0 | 0 | 2760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7844.9996 | 0 | 0 | 7844.9996 | 706.05 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15524.8818
1.2.8.5.2 | 1.2 | 1.2.8 | UW | WIPAC | PQ, ECW & Deployment Travel Costs (FS1) | Deployment Travel & PQ Costs (FS1) (Safety Engineer) | Zernick | Labor Hours | Labor - Task | EN-S | E - Extrapolation from Actuals | 60.69 | 46 | 35% | 53% | Off Ice | C1 | 9% | 753.4277 | 260.9913 | 1 Safety Engineer, 5 days deployment travel 3 days redeployment | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 40 |  |  | 24 | [7 empty] | 64 | 0 | 2427.6 | 0 | 0 | 1456.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4052.9743 | 1418.541 | 2899.9031 | 8371.4185 | 492.4364 | 260.9913 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8371.4185
1.2.8.5.2 | 1.2 | 1.2.8 | UW | PSL | PQ, ECW & Deployment Travel Costs (FS1) | Deployment Travel & PQ Costs (FS1) (Driller_PSL_DirectHire) x 3 |  | Labor Hours | Labor - Task | TE | E - Extrapolation from Actuals | 77 | 77 | 0% | 0% | Off Ice | C1 | 9% | 1388.3891 | 0 | 3 Seasonal drillers, 5 days deployment travel 3 days redeployment (No Contributed drillers) | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 120 |  |  | 72 | [7 empty] | 192 | 0 | 9240 | 0 | 0 | 5544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15426.5459 | 0 | 0 | 15426.5459 | 1388.3891 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15426.5459
1.2.8.5.2 | 1.2 | 1.2.8 | UW | PSL | PQ, ECW & Deployment Travel Costs (FS1) | Deployment Travel & PQ Costs (FS1) (PSL_Engineer) x 9 |  | Labor Hours | Labor - Task | EN | E - Extrapolation from Actuals | 115 | 115 | 0% | 0% | Off Ice | C1 | 9% | 6220.7045 | 0 | 9 PSL Engineers (2 Rotators), 5 days deployment travel 3 days redeployment | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 280 | 128 |  | 168 | [7 empty] | 576 | 0 | 32200 | 14720 | 0 | 19320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69118.9394 | 0 | 0 | 69118.9394 | 6220.7045 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69118.9394
1.2.8.5.2 | 1.2 | 1.2.8 | UW | PSL | PQ, ECW & Deployment Travel Costs (FS1) | Deployment Travel & PQ Costs (FS1) (Drill Team) |  | M & S | M & S |  | E - Extrapolation from Actuals |  | 1 | 0% | 53% | Off Ice | C1 | 9% | 2138.0404 | 740.6284 | 16 - PQ's 1 Drill Lead, 1 Safety Engineer, 5 Direct Hire (2 alternate) & 9 PSL Engineers @ $950/each (anticipated cost) | [8 empty] | 7600 |  | 7600 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7600 | 0 | 7600 | 0 | 15526.8 | 0 | 8229.204 | 23756.004 | 1397.412 | 740.6284 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23756.004
1.2.8.5.2 | 1.2 | 1.2.8 | UW | PSL | PQ, ECW & Deployment Travel Costs (FS1) | Deployment Travel & PQ Costs (FS1) (Drill Team) | Foreign | Travel | Travel |  | E - Extrapolation from Actuals |  | 1 | 0% | 53% | Off Ice | C1 | 9% | 3544.6459 | 1227.8839 | 14 - Deployment Travel @ $1800 each | [9 empty] | 12600 | 12600 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12600 | 12600 | 0 | 25741.8 | 0 | 13643.154 | 39384.954 | 2316.762 | 1227.8839 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39384.954
1.2.8.5.11 | 1.2 | 1.2.8 | UW | PSL | On-Ice Labor (FS1) | On-Ice Labor (FS1) (PSL Engineers) |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 85.1852 | 115 | 0% | 0% | On Ice | C2 | 12.5% | 50999.2175 | 0 | EE/ME Engineer Labor Totals from Population file. Assumes 2 days in McMurdo southbound and 0 days northbound. | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1044 | 1818 | 1728 | [8 empty] | 4590 | 0 | 88933.3333 | 154866.6667 | 147200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 407993.7398 | 0 | 0 | 407993.7398 | 50999.2175 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 407993.7398
1.2.8.5.11 | 1.2 | 1.2.8 | UW | PSL | On-Ice Labor (FS1) | On-Ice Labor (FS1) (PSL Contract Drillers) |  | Labor Hours | Labor - Task | TE | D - Expert Opinion | 57.037 | 77 | 0% | 0% | On Ice | C2 | 12.5% | 10980.7011 | 0 | Technician Labor Totals from Population file. Assumes 2 days in McMurdo southbound and 0 days northbound. | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 279 | 549 | 648 | [8 empty] | 1476 | 0 | 15913.3333 | 31313.3333 | 36960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87845.6086 | 0 | 0 | 87845.6086 | 10980.7011 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87845.6086
1.2.8.5.11 | 1.2 | 1.2.8 | UW | WIPAC | On-Ice Labor (FS1) | On-Ice Labor (FS1) (Safety Engineer) | Zernick | Labor Hours | Labor - Task | EN-S | D - Expert Opinion | 44.96 | 46 | 35% | 53% | On Ice | C1 | 9% | 2590.1636 | 897.2462 | Safety Engineer Labor Totals from Population file. Assumes 2 days in McMurdo southbound and 0 days northbound. | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 162 | 135 | [9 empty] | 297 | 0 | 7283.52 | 6069.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13933.4766 | 4876.7168 | 9969.4025 | 28779.596 | 1692.9174 | 897.2462 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28779.596
1.2.8.6.2 | 1.2 | 1.2.8 | UW | PSL | PQ, ECW & Deployment Travel Costs (FS2) Team | Deployment Travel & PQ Costs (FS2) (Driller_PSL_Manager) |  | Labor Hours | Labor - Task | EN | E - Extrapolation from Actuals | 115 | 115 | 0% | 0% | Off Ice | C1 | 9% | 706.05 | 0 | 1 Drill Manager, 5 days deployment travel 3 days redeployment | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 40 |  |  | 24 | [7 empty] | 64 | 0 | 4600 | 0 | 0 | 2760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7844.9996 | 0 | 0 | 7844.9996 | 706.05 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7844.9996
1.2.8.6.2 | 1.2 | 1.2.8 | UW | WIPAC | PQ, ECW & Deployment Travel Costs (FS2) Team | Deployment Travel & PQ Costs (FS2) (Safety_Engineer) | Zernick | Labor Hours | Labor - Task | EN-S | E - Extrapolation from Actuals | 60.69 | 46 | 35% | 53% | Off Ice | C1 | 9% | 769.6264 | 266.6026 | 1 Safety Engineer, 5 days deployment travel 3 days redeployment | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 40 |  |  | 24 | [7 empty] | 64 | 0 | 2427.6 | 0 | 0 | 1456.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4140.1133 | 1449.0396 | 2962.2511 | 8551.404 | 503.0238 | 266.6026 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8551.404
1.2.8.6.2 | 1.2 | 1.2.8 | UW | PSL | PQ, ECW & Deployment Travel Costs (FS2) Team | Deployment Travel & PQ Costs (FS2) (PSL_Direct_Hire) |  | Labor Hours | Labor - Task | TE | E - Extrapolation from Actuals | 77 | 77 | 0% | 0% | Off Ice | C1 | 9% | 2836.479 | 0 | 6 PSL Direct Hire, 5 days deployment travel 3 days redeployment | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 240 |  |  | 144 | [7 empty] | 384 | 0 | 18480 | 0 | 0 | 11088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31516.4333 | 0 | 0 | 31516.4333 | 2836.479 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31516.4333
1.2.8.6.2 | 1.2 | 1.2.8 | UW | PSL | PQ, ECW & Deployment Travel Costs (FS2) Team | Deployment Travel & PQ Costs (FS2) (PSL_Engineer) |  | Labor Hours | Labor - Task | EN | E - Extrapolation from Actuals | 115 | 115 | 0% | 0% | Off Ice | C1 | 9% | 6354.4497 | 0 | 9 PSL Engineers w/ 2 Rotators, 5 days deployment travel 3 days redeployment | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 280 | 128 |  | 168 | [7 empty] | 576 | 0 | 32200 | 14720 | 0 | 19320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70604.9966 | 0 | 0 | 70604.9966 | 6354.4497 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70604.9966
1.2.8.6.2 | 1.2 | 1.2.8 | UW | PSL | PQ, ECW & Deployment Travel Costs (FS2) Team | Deployment Travel & PQ Costs (FS2) (Drill Team) |  | M & S | M & S |  | E - Extrapolation from Actuals |  | 1 | 0% | 53% | Off Ice | C1 | 9% | 2593.5098 | 898.4053 | 19 - PQ's @ $950/each (anticipated cost) - 2 Alternates and 17 Primaries | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 9025 | 9025 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9025 | 9025 | 0 | 18834.4936 | 0 | 9982.2816 | 28816.7752 | 1695.1044 | 898.4053 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28816.7752
1.2.8.6.2 | 1.2 | 1.2.8 | UW | PSL | PQ, ECW & Deployment Travel Costs (FS2) Team | Deployment Travel & PQ Costs (FS2) (Drill Team) | Foreign | Travel | Travel |  | E - Extrapolation from Actuals |  | 1 | 0% | 53% | Off Ice | C1 | 9% | 4396.7534 | 1523.0584 | 17 - Deploy travel costs w/ 2 PSL rotator @ $1800 each | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 15300 | 15300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15300 | 15300 | 31929.9449 | 0 | 16922.8708 | 48852.8156 | 2873.695 | 1523.0584 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48852.8156
1.2.8.6.6.9 | 1.2 | 1.2.8 | UW | PSL | Parallel Gens through PDM Bays (Driller & Contract Gen Tech) | Generators/PDM: Parallel Gens through PDM Bays (Contract Gen Tech) |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 0% | On Ice | C3 | 20% | 2963.1928 | 0 | Estimated 18 days of contractor cost @ $250 per hour 9 hour days plus travel & PQ allowance of $1200 for a total of $41,700 or $5957 for each of the 7 days of work at the Pole. | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 13900 | [10 empty] | 0 | 0 | 13900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14815.964 | 0 | 0 | 14815.964 | 2963.1928 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14815.964
1.2.8.6.6.10 | 1.2 | 1.2.8 | UW | PSL | Load Test using Resistance Heaters (Driller & Contract Gen Tech) | Generators/PDM: Load Test using Resistance Heaters (Contract Gen Tech) |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 0% | On Ice | C3 | 20% | 2963.1928 | 0 | Estimated 18 days of contractor cost @ $250 per hour 9 hour days plus travel & PQ allowance of $1200 for a total of $41,700 or $5957 for each of the 7 days of work at the Pole. | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 13900 | [10 empty] | 0 | 0 | 13900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14815.964 | 0 | 0 | 14815.964 | 2963.1928 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14815.964
1.2.8.6.6.11 | 1.2 | 1.2.8 | UW | PSL | Test Safety Shut-downs (Driller & Contract Gen Tech) | Generators/PDM: Test Safety Shut-downs (Contract Gen Tech) |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 0% | On Ice | C3 | 20% | 2963.1928 | 0 | Estimated 18 days of contractor cost @ $250 per hour 9 hour days plus travel & PQ allowance of $1200 for a total of $41,700 or $5957 for each of the 7 days of work at the Pole. | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 13900 | [9 empty] | 0 | 0 | 0 | 13900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14815.964 | 0 | 0 | 14815.964 | 2963.1928 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14815.964
1.2.8.6.15 | 1.2 | 1.2.8 | UW | PSL | On-ice Labor FS2 | On-Ice Labor (FS2) (PSL Engineers) |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 85.1852 | 115 | 0% | 0% | On Ice | C2 | 12.5% | 50563.4742 | 0 | EE/ME Engineer Labor Totals from Population file. Assumes 2 days in McMurdo southbound and 1 day northbound. | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 990 | 1818 | 1647 | [8 empty] | 4455 | 0 | 84333.3333 | 154866.6667 | 140300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 404507.7932 | 0 | 0 | 404507.7932 | 50563.4742 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 404507.7932
1.2.8.6.15 | 1.2 | 1.2.8 | UW | PSL | On-ice Labor FS2 | On-Ice Labor (FS2) (PSL Drillers) |  | Labor Hours | Labor - Task | TE | D - Expert Opinion | 57.037 | 77 | 0% | 0% | On Ice | C2 | 12.5% | 25648.1391 | 0 | Technician Labor Totals from Population file. Assumes 2 days in McMurdo southbound and 1 day northbound. | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 819 | 1197 | 1359 | [8 empty] | 3375 | 0 | 46713.3333 | 68273.3333 | 77513.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 205185.1125 | 0 | 0 | 205185.1125 | 25648.1391 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 205185.1125
1.2.8.6.15 | 1.2 | 1.2.8 | UW | WIPAC | On-ice Labor FS2 | On-Ice Labor (FS2) (Safety Engineer) | Zernick | Labor Hours | Labor - Task | EN-S | D - Expert Opinion | 44.96 | 46 | 35% | 53% | On Ice | C2 | 12.5% | 4714.1305 | 1632.9995 | Safety Engineer Labor Totals from Population file. Assumes 2 days in McMurdo southbound and 1 day northbound. | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 48 | 225 | 108 | [8 empty] | 381 | 0 | 2158.08 | 10116 | 4855.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18258.5545 | 6390.4941 | 13063.9957 | 37713.0442 | 3081.1311 | 1632.9995 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37713.0442
1.2.8.7.2 | 1.2 | 1.2.8 | UW | PSL | PQ, ECW & Deployment Travel Costs (FS3) | Deployment Travel & PQ Costs (FS3) (Driller_Manager) |  | Labor Hours | Labor - Task | EN | E - Extrapolation from Actuals | 115 | 115 | 0% | 0% | Off Ice | C1 | 9% | 721.23 | 0 | 1 (Drill Manager), 5 days deployment travel 3 days redeployment | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 40 |  |  | 24 | [7 empty] | 64 | 0 | 4600 | 0 | 0 | 2760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8013.6671 | 0 | 0 | 8013.6671 | 721.23 | 0 | 8013.6671
1.2.8.7.2 | 1.2 | 1.2.8 | UW | WIPAC | PQ, ECW & Deployment Travel Costs (FS3) | Deployment Travel & PQ Costs (FS3) (Safety_Engineer) | Zernick | Labor Hours | Labor - Task | EN-S | E - Extrapolation from Actuals | 60.69 | 46 | 35% | 53% | Off Ice | C1 | 9% | 786.1733 | 272.3346 | 1 (Safety Engineer), 5 days deployment travel 3 days redeployment | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 40 |  | 24 | [8 empty] | 64 | 0 | 2427.6 | 0 | 1456.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4229.1257 | 1480.194 | 3025.9395 | 8735.2592 | 513.8388 | 272.3346 | 8735.2592
1.2.8.7.2 | 1.2 | 1.2.8 | UW | PSL | PQ, ECW & Deployment Travel Costs (FS3) | Deployment Travel & PQ Costs (FS3) (Driller_PSL_Direct_Hire) |  | Labor Hours | Labor - Task | EN | E - Extrapolation from Actuals | 115 | 115 | 0% | 0% | Off Ice | C1 | 9% | 14424.6008 | 0 | 20 (PSL Direct Hire), 5 days deployment travel 3 days redeployment | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 800 |  | 480 | [8 empty] | 1280 | 0 | 92000 | 0 | 55200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160273.3424 | 0 | 0 | 160273.3424 | 14424.6008 | 0 | 160273.3424
1.2.8.7.2 | 1.2 | 1.2.8 | UW | PSL | PQ, ECW & Deployment Travel Costs (FS3) | Deployment Travel & PQ Costs (FS3) (Engineer_PSL) |  | Labor Hours | Labor - Task | EN | E - Extrapolation from Actuals | 115 | 115 | 0% | 0% | Off Ice | C1 | 9% | 5769.8403 | 0 | 8 (PSL Engineers), 5 days deployment travel 3 days redeployment | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 320 |  | 192 | [8 empty] | 512 | 0 | 36800 | 0 | 22080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64109.3369 | 0 | 0 | 64109.3369 | 5769.8403 | 0 | 64109.3369
1.2.8.7.2 | 1.2 | 1.2.8 | UW | PSL | PQ, ECW & Deployment Travel Costs (FS3) | PQ Costs (FS3) (Drill Team) |  | M & S | M & S |  | E - Extrapolation from Actuals |  | 1 | 0% | 53% | Off Ice | C1 | 9% | 4601.3641 | 1593.9366 | 33 - PQ's @ $950/each (anticipated cost) 28 Drillers, Safety Engineer & 4 Alternates | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 15675 | 15675 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15675 | 15675 | 0 | 0 | 33415.8612 | 0 | 17710.4064 | 51126.2676 | 3007.4275 | 1593.9366 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51126.2676
1.2.8.7.2 | 1.2 | 1.2.8 | UW | PSL | PQ, ECW & Deployment Travel Costs (FS3) | Travel (FS3) (Drill Team) | Foreign | Travel | Travel |  | E - Extrapolation from Actuals |  | 1 | 0% | 53% | Off Ice | C1 | 9% | 7661.6014 | 2654.0188 | 29 - Deploy travel costs 29 (28 Drillers & 1 Safety Engineer) @ $1800 each | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 26100 | 26100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26100 | 26100 | 55639.8071 | 0 | 29489.0978 | 85128.9049 | 5007.5826 | 2654.0188 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85128.9049
1.2.8.7.13 | 1.2 | 1.2.8 | UW | PSL | On-Ice Labor (FS3) | On-Ice Labor (FS3) (PSL Engineers) |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 85.1852 | 115 | 0% | 0% | On Ice | C2 | 12.5% | 46850.7361 | 0 | EE/ME Engineer Labor Totals from Population file. Assumes 2 days in McMurdo southbound and 1 day northbound. | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 702 | 1872 | 1467 | [8 empty] | 4041 | 0 | 59800 | 159466.6667 | 124966.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 374805.8892 | 0 | 0 | 374805.8892 | 46850.7361 | 0 | 374805.8892
1.2.8.7.13 | 1.2 | 1.2.8 | UW | PSL | On-Ice Labor (FS3) | On-Ice Labor (FS3) (PSL Contract Drillers) |  | Labor Hours | Labor - Task | TE | D - Expert Opinion | 57.037 | 77 | 0% | 0% | On Ice | C2 | 12.5% | 80694.6881 | 0 | Technician Labor Totals from Population file. Assumes 2 days in McMurdo southbound and 1 day northbound. | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1890 | 4680 | 3825 | [8 empty] | 10395 | 0 | 107800 | 266933.3333 | 218166.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 645557.5047 | 0 | 0 | 645557.5047 | 80694.6881 | 0 | 645557.5047
1.2.8.7.13 | 1.2 | 1.2.8 | UW | WIPAC | On-Ice Labor (FS3) | On-Ice Labor (FS3) (Safety Engineer) | Zernick | Labor Hours | Labor - Task | EN-S | D - Expert Opinion | 44.96 | 46 | 35% | 53% | On Ice | C2 | 12.5% | 7735.1087 | 2679.4821 | Safety Engineer Labor Totals from Population file. Assumes 2 days in McMurdo southbound and 1 day northbound. | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 144 | 234 | 234 | [8 empty] | 612 | 0 | 6474.24 | 10520.64 | 10520.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29959.2687 | 10485.7441 | 21435.8568 | 61880.8696 | 5055.6266 | 2679.4821 | 61880.8696
1.2.9.1.3.2 | 1.2 | 1.2.9 | UW | WIPAC | Procure Sensor Handling Equipment | Off-Ice Install: Procure Sensor Handling Equipment |  | CapEx | CapEx |  | C - Engineering Buildup |  | 1 | 0% | 0% | Off Ice | C3 | 20% | 1726.9479 | 0 |  | 8453 | [11 empty] | 0 | 8453 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8634.7395 | 0 | 0 | 8634.7395 | 1726.9479 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8634.7395
1.2.9.1.3.3 | 1.2 | 1.2.9 | UW | WIPAC | Procure ESD Mitigation Equipment | Off-Ice Install: Procure ESD Sensor Handling Equipment |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 0% | Off Ice | C4 | 35% | 1983.9062 | 0 | Lab coats, ESDgloves, ESD runners | 5549 | [11 empty] | 0 | 5549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5668.3035 | 0 | 0 | 5668.3035 | 1983.9062 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5668.3035
1.2.9.2.8 | 1.2 | 1.2.9 | UW | WIPAC | Procure Installation Hardware | Off-Ice Install: Procure Installation Hardware |  | CapEx | CapEx |  | C - Engineering Buildup |  | 1 | 0% | 0% | Off Ice | C3 | 20% | 22064.4 | 0 |  |  | 36000 | 36000 | 36000 | [8 empty] | 0 | 0 | 36000 | 36000 | 36000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110322 | 0 | 0 | 110322 | 22064.4 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110322
1.2.9.2.9 | 1.2 | 1.2.9 | UW | WIPAC | Procure Installation Weights | Off-Ice Install: Procure Installation Weights |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 0% | Off Ice | C4 | 35% | 3539.4975 | 0 |  |  | 3300 | 3300 | 3300 | [8 empty] | 0 | 0 | 3300 | 3300 | 3300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10112.85 | 0 | 0 | 10112.85 | 3539.4975 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10112.85
1.2.9.3.2.1 | 1.2 | 1.2.9 | UW | WIPAC | IME ICL Quad Connectivity Tester Design, Prototype, Production (2023-24) | Off-ice Install: IME ICL Quad Connectivity Tester Design, Prototype & Production (2023-24) |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 0% | Off Ice | C4 | 35% | 1753.0166 | 0 | IME ICL QCT | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 600 | 600 | 600 |  | 2000 | 1000 |  |  |  |  | 0 | 0 | 0 | 600 | 600 | 600 | 0 | 2000 | 1000 | 0 | 0 | 0 | 0 | 5008.6188 | 0 | 0 | 5008.6188 | 1753.0166 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5008.6188
1.2.9.3.2.1 | 1.2 | 1.2.9 | UW | WIPAC | IME ICL Quad Connectivity Tester Design, Prototype, Production (2023-24) | Off-ice Install: IME ICL Quad Connectivity Tester Design, Prototype & Production (2023-24) | Domestic | Travel | Travel |  | E - Extrapolation from Actuals |  | 1 | 0% | 53% | Off Ice | C1 | 9% | 258.6326 | 89.5917 | IME ICL QCT 1 domestic travel to NTS at MSU | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 900 | 900 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 900 | 900 | 0 | 0 | 0 | 1878.2321 | 0 | 995.463 | 2873.695 | 169.0409 | 89.5917 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2873.695
1.2.9.3.3.2 | 1.2 | 1.2.9 | UW | PSL | IME Depth Readout Development and System Integration (2022-23) | Off-ice Install: IME Depth Readout Development and System Integration (2022-23) | Wisniewski | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 1409.67 | 0 | Duplicate system (1/TOS plus spares) | [7 empty] | 10 | 20 | 20 | 10 |  | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1150 | 2300 | 2300 | 1150 | 0 | 7048.35 | 0 | 0 | 7048.35 | 1409.67 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7048.35
1.2.9.3.3.2 | 1.2 | 1.2.9 | UW | PSL | IME Depth Readout Development and System Integration (2022-23) | Off-ice Install: IME Depth Readout Development and System Integration (2022-23) | Domestic | Travel | Travel |  | E - Extrapolation from Actuals |  | 1 | 0% | 53% | Off Ice | C1 | 9% | 253.189 | 87.706 | 1 domestic trip ($1800/person) to MSU for testing with full length quad | [7 empty] | 450 | 450 | 450 | 450 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450 | 450 | 450 | 450 | 0 | 1838.7 | 0 | 974.511 | 2813.211 | 165.483 | 87.706 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2813.211
1.2.9.3.3.2 | 1.2 | 1.2.9 | UW | WIPAC | IME Depth Readout Development and System Integration (2022-23) | Off-ice Install: IME Depth Readout Development and System Integration (2022-23) |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 0% | Off Ice | C4 | 35% | 1215.585 | 0 | Purchasing 2x materials for spares | [7 empty] | 1700 |  | 1700 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1700 | 0 | 1700 | 0 | 0 | 3473.1 | 0 | 0 | 3473.1 | 1215.585 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3473.1
1.2.9.3.3.3 | 1.2 | 1.2.9 | UW | PSL | IME Depth Readout System Final Integration (2023-24) | Off-Ice Install: IME Depth Readout System Final Integration (2023-24) | Wisniewski | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 959.9853 | 0 | Test of all Paro Sensors | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 20 | 20 |  |  |  | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2300 | 2300 | 0 | 0 | 0 | 4799.9264 | 0 | 0 | 4799.9264 | 959.9853 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4799.9264
1.2.9.3.3.7 | 1.2 | 1.2.9 | UW | WIPAC | Procure Pressure Sensors | Off-Ice Install: Procure Pressure Sensors |  | CapEx | CapEx |  | C - Engineering Buildup |  | 1 | 0% | 0% | Off Ice | C2 | 12.5% | 13668.8337 | 0 | May delay pressure sensor procurement if calibration shelf life duration in question. Vendor quote for 2022 is 11800/each, with increment of 3-5% / year | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 34932 | 34932 | 34932 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 34932 | 34932 | 34932 | 0 | 0 | 0 | 0 | 0 | 109350.67 | 0 | 0 | 109350.67 | 13668.8337 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109350.67
1.2.9.4.2.3 | 1.2 | 1.2.9 | UW | WIPAC | Procure Logbook Tablets | Off-Ice Install: Procure Tablets for Logbook |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 0% | Off Ice | C4 | 35% | 2179.2187 | 0 | two rugged tablets for logbook keeping | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 1989 | 1989 | 1989 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1989 | 1989 | 1989 | 0 | 0 | 0 | 6226.3392 | 0 | 0 | 6226.3392 | 2179.2187 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6226.3392
1.2.9.4.2.5 | 1.2 | 1.2.9 | UW | WIPAC | Procure Laser Rangers, Tape Measures, Shop Lights, Helmets for Installation | Off-Ice Install: Procure Laser Rangers & various Installation Supplies |  | CapEx | CapEx |  | E - Extrapolation from Actuals |  | 1 | 0% | 0% | Off Ice | C3 | 20% | 1117.5481 | 0 | Laser ranges to measure well depth and distance between DOMs (2) | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 1339 | 1339 | 1339 | 669 | 669 |  |  |  | 0 | 0 | 0 | 0 | 0 | 1339 | 1339 | 1339 | 669 | 669 | 0 | 0 | 0 | 5587.7403 | 0 | 0 | 5587.7403 | 1117.5481 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5587.7403
1.2.10.1.3 | 1.2 | 1.2.10 | UW | PSL | FS3 Off-Ice Installation Training (Drillers, Installers, Management, including alternates) | Install FS3: FS3 Off-Ice Installation Training: Drillers | PSL Driller | Labor Hours | Labor - Task | TE | D - Expert Opinion | 77 | 77 | 0% | 0% | Off Ice | C1 | 9% | 2127.3592 | 0 | 3x8 hours installation training (sensor handling, practice at the tower). Need (3+1 spare)x3=12 drillers | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 288 |  | 288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22176 | 0 | 23637.325 | 0 | 0 | 23637.325 | 2127.3592 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23637.325
1.2.10.4.2 | 1.2 | 1.2.10 | UW | WIPAC | PQ, ECW, Deployment Travel Costs Installation Team FS2 (Headcount 1) | Install FS2: Install Team FS2 PQ Costs (Headcount 1) |  | M & S | M & S |  | E - Extrapolation from Actuals |  | 1 | 0% | 53% | On Ice | C1 | 9% | 100.5793 | 34.8412 | 1 - PQ @ $700/each (anticipated cost) | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 350 | 350 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350 | 350 | 0 | 0 | 730.4236 | 0 | 387.1245 | 1117.5481 | 65.7381 | 34.8412 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1117.5481
1.2.10.4.2 | 1.2 | 1.2.10 | UW | WIPAC | PQ, ECW, Deployment Travel Costs Installation Team FS2 (Headcount 1) | Install FS2: Install Team FS2 ECW Costs (Headcount 1) |  | M & S | M & S |  | E - Extrapolation from Actuals |  | 1 | 0% | 53% | On Ice | C1 | 9% | 35.9212 | 12.4433 | 1 - ECW allowance @ $250/each | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 125 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125 | 125 | 260.8656 | 0 | 138.2587 | 399.1243 | 23.4779 | 12.4433 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 399.1243
1.2.10.4.2 | 1.2 | 1.2.10 | UW | WIPAC | PQ, ECW, Deployment Travel Costs Installation Team FS2 (Headcount 1) | Install FS2: Install Team FS2 Deployment Travel Costs (Headcount 1) | Foreign | Travel | Travel |  | E - Extrapolation from Actuals |  | 1 | 0% | 53% | On Ice | C1 | 9% | 264.1932 | 91.5179 | 1 - International Travel (3 nights southbound, 2 nights northbound, plus per diem) @ $1800/each | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1080 |  |  | 720 | [7 empty] | 0 | 0 | 1080 | 0 | 0 | 720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1918.614 | 0 | 1016.8654 | 2935.4795 | 172.6753 | 91.5179 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2935.4795
1.2.10.4.10 | 1.2 | 1.2.10 | UW | WIPAC | Installation: On-Ice Labor (FS2) | Installation: On-Ice Labor (FS2) (Installation Lead) | Tosi | Labor Hours | Labor - LoE | SC | D - Expert Opinion | 34.99 | 52 | 35% | 53% | On Ice | C1 | 9% | 2745.5032 | 951.0567 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 162 | 234 | [8 empty] | 396 | 0 | 0 | 5668.38 | 8187.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14769.1071 | 5169.1875 | 10567.2962 | 30505.5908 | 1794.4465 | 951.0567 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30505.5908
1.2.10.5.2 | 1.2 | 1.2.10 | UW | WIPAC | PQ, ECW, Deployment Travel Costs Install FS2 Installation Team | Install FS3: Install Team FS3 PQ Costs (Headcount 1) |  | M & S | M & S |  | E - Extrapolation from Actuals |  | 1 | 0% | 53% | On Ice | C1 | 9% | 102.7418 | 35.5903 | 1 - PQ @ $700/each (anticipated cost) | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 350 | 350 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350 | 350 | 0 | 0 | 746.1277 | 0 | 395.4477 | 1141.5754 | 67.1515 | 35.5903 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1141.5754
1.2.10.5.2 | 1.2 | 1.2.10 | UW | WIPAC | PQ, ECW, Deployment Travel Costs Install FS2 Installation Team | Install FS3: Install Team FS3 ECW Costs (Headcount 1) |  | M & S | M & S |  | E - Extrapolation from Actuals |  | 1 | 0% | 53% | On Ice | C1 | 9% | 36.6935 | 12.7108 | 1 - ECW allowance @ $250/each | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 125 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125 | 125 | 266.4742 | 0 | 141.2313 | 407.7055 | 23.9827 | 12.7108 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 407.7055
1.2.10.5.2 | 1.2 | 1.2.10 | UW | WIPAC | PQ, ECW, Deployment Travel Costs Install FS2 Installation Team | Install FS3: Install Team FS3 Deployment Costs (Headcount 1 + 9 in-kind) | Foreign | Travel | Travel |  | E - Extrapolation from Actuals |  | 1 | 0% | 53% | On Ice | C1 | 9% | 269.8733 | 93.4855 | 1 - International Travel (3 nights southbound, 2 nights northbound, plus per diem) @ $1800/each | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1080 |  |  | 720 | [7 empty] | 0 | 0 | 1080 | 0 | 0 | 720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1959.8642 | 0 | 1038.728 | 2998.5923 | 176.3878 | 93.4855 | 2998.5923
1.2.10.5.8 | 1.2 | 1.2.10 | UW | WIPAC | Installation: On-Ice Labor (FS3) | Installation: On-Ice Labor (FS3) (Installation Lead) | Tosi | Labor Hours | Labor - Task | SC | D - Expert Opinion | 34.99 | 52 | 35% | 53% | On Ice | C1 | 9% | 3951.8398 | 1368.938 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 108 | 234 | 216 | [8 empty] | 558 | 0 | 3778.92 | 8187.66 | 7557.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21258.4514 | 7440.458 | 15210.422 | 43909.3314 | 2582.9018 | 1368.938 | 43909.3314
1.3.3.1.2.5 | 1.3 | 1.3.3 | UW | WIPAC | PDOM Rev3 Mainboard production (Qty. 27) | Domestic trip to PCA manufacturer | Domestic | Travel | Travel |  | E - Extrapolation from Actuals |  | 1 | 0% | 53% | Off Ice | C1 | 9% | 253.189 | 87.706 |  | 1800 | [11 empty] | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1838.7 | 0 | 974.511 | 2813.211 | 165.483 | 87.706 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2813.211
1.3.3.1.2.5 | 1.3 | 1.3.3 | UW | WIPAC | PDOM Rev3 Mainboard production (Qty. 27) | 27 Rev3 PDOM Mainboards |  | CapEx | CapEx |  | E - Extrapolation from Actuals |  | 1 | 0% | 0% | Off Ice | C2 | 12.5% | 5464.3866 | 0 |  | 42795 | [11 empty] | 0 | 42795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43715.0925 | 0 | 0 | 43715.0925 | 5464.3866 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43715.0925
1.3.3.1.2.5 | 1.3 | 1.3.3 | UW | WIPAC | PDOM Rev3 Mainboard production (Qty. 27) | 27 PDOM Calibration Boards |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 0% | Off Ice | C3 | 20% | 3585.465 | 0 |  | 17550 | [11 empty] | 0 | 17550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17927.325 | 0 | 0 | 17927.325 | 3585.465 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17927.325
1.3.3.2.2.5 | 1.3 | 1.3.3 | UW | WIPAC | PDOM HV system production (Qty. 27) | 27 PDOM HV subsystems (HV supply PCA) |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 0% | Off Ice | C3 | 20% | 1930.635 | 0 |  | 9450 | [11 empty] | 0 | 9450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9653.175 | 0 | 0 | 9653.175 | 1930.635 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9653.175
1.3.3.4.1 | 1.3 | 1.3.3 | UW | WIPAC | Refurbish 10 IceCube DOMs | 35 Penetrator Cable Assemblies and attachment hardware |  | CapEx | CapEx |  | E - Extrapolation from Actuals |  | 1 | 0% | 0% | Off Ice | C1 | 9% | 1962.8122 | 0 |  |  |  | 21350 | [9 empty] | 0 | 0 | 0 | 21350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21809.025 | 0 | 0 | 21809.025 | 1962.8122 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21809.025
1.3.3.4.5.1 | 1.3 | 1.3.3 | UW | PSL | Refurbishment Batch #1 (Qty. 20) | Refurbishment Batch #1 (Qty. 20) | N.N. | Labor Hours | Labor - Task | TE | A - Analogy | 89 | 77 | 0% | 0% | Off Ice | C3 | 20% | 4363.848 | 0 |  | 120 | 120 | [10 empty] | 240 | 10680 | 10680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21819.24 | 0 | 0 | 21819.24 | 4363.848 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21819.24
1.3.3.4.5.1 | 1.3 | 1.3.3 | UW | WIPAC | Refurbishment Batch #1 (Qty. 20) | Refurbishment Batch #1 (Qty. 20) |  | M & S | M & S |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C3 | 20% | 1875.474 | 649.674 |  | 3000 | 3000 | [10 empty] | 0 | 3000 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6129 | 0 | 3248.37 | 9377.37 | 1225.8 | 649.674 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9377.37
1.3.3.4.5.2 | 1.3 | 1.3.3 | UW | WIPAC | FAT Batch #1 | FAT Batch #1 | Wendt | Labor Hours | Labor - Task | SC | A - Analogy | 64.75 | 52 | 35% | 53% | Off Ice | C3 | 20% | 3552.0305 | 1230.442 |  |  | 10 | 100 | 20 | [8 empty] | 130 | 0 | 647.5 | 6475 | 1295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8598.4763 | 3009.4667 | 6152.2098 | 17760.1527 | 2321.5886 | 1230.442 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17760.1527
1.3.3.4.5.2 | 1.3 | 1.3.3 | UW | WIPAC | FAT Batch #1 | FAT Batch #1 |  | M & S | M & S |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C3 | 20% | 1562.895 | 541.395 |  |  | 5000 | [10 empty] | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5107.5 | 0 | 2706.975 | 7814.475 | 1021.5 | 541.395 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7814.475
1.3.3.4.5.3 | 1.3 | 1.3.3 | UW | PSL | Packing Batch #1 | Packing Batch #1 | N.N. | Labor Hours | Labor - Task | TE | A - Analogy | 46 | 77 | 0% | 0% | Off Ice | C3 | 20% | 375.912 | 0 |  |  |  |  | 40 | [8 empty] | 40 | 0 | 0 | 0 | 1840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 0 | 0 | 1879.56 | 375.912 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56
1.3.3.4.5.3 | 1.3 | 1.3.3 | UW | WIPAC | Packing Batch #1 | Packing Batch #1 |  | M & S | M & S |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C3 | 20% | 312.579 | 108.279 |  |  |  |  | 1000 | [8 empty] | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1021.5 | 0 | 541.395 | 1562.895 | 204.3 | 108.279 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1562.895
1.3.3.4.6 | 1.3 | 1.3.3 | UW | WIPAC | Ship 2 + 1 spare PDOMs for Strings 87-88 to Pt. Hueneme | Ship to Pt. Hueneme |  | M & S | M & S |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C3 | 20% | 156.2895 | 54.1395 | [11 empty] | 500 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 510.75 | 0 | 270.6975 | 781.4475 | 102.15 | 54.1395 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 781.4475
1.3.3.4.7 | 1.3 | 1.3.3 | UW | WIPAC | Ship 12 + 1 spare PDOMs for Strings 89-93 to Pt. Hueneme | Ship to Pt. Hueneme |  | M & S | M & S |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C3 | 20% | 319.2994 | 110.607 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 1000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 1043.4623 | 0 | 553.035 | 1596.4972 | 208.6925 | 110.607 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1596.4972
1.3.4.2.3.3 | 1.3 | 1.3.4 | UW | WIPAC | Firmware support D-Egg | Firmware support during D-Egg FAT | S. Griffin | Labor Hours | Labor - LoE | EN | D - Expert Opinion | 47 | 49 | 35% | 53% | Off Ice | C1 | 9% | 8686.6 | 3009.0837 |  | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 264 | 1034 | 1034 | 1034 | 1034 | 1034 | 1034 | 1034 | 1034 | 1034 | 1034 | 1034 | 1034 | 12674.772 | 4436.1702 | 9068.7994 | 26179.7416 | 1539.9848 | 816.1919 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 264 | 1034 | 1034 | 1034 | 1034 | 1034 | 1034 | 1034 | 1034 | 1034 | 1034 | 1034 | 1034 | 12947.2796 | 4531.5479 | 9263.7786 | 26742.606 | 1573.0945 | 833.7401 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 264 | 1034 | 1034 | 1034 | 1034 | 1034 | 1034 | 1034 | 1034 | 1034 | 1034 | 1034 | 1034 | 13225.6461 | 4628.9761 | 9462.9498 | 27317.572 | 1606.916 | 851.6655 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | [5 empty] | 154 | 1034 | 1034 | 1034 | 1034 | 1034 | 1034 | 1034 | 0 | 0 | 0 | 0 | 0 | 7880.8319 | 2758.2912 | 5638.7352 | 16277.8582 | 957.5211 | 507.4862 | 96517.7779
1.3.4.2.3.5 | 1.3 | 1.3.4 | UW | WIPAC | Firmware support mDOM | Firmware support during mDOM FAT | S. Griffin | Labor Hours | Labor - LoE | EN | D - Expert Opinion | 47 | 49 | 35% | 53% | Off Ice | C1 | 9% | 8097.5558 | 2805.0357 |  |  |  |  | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 198 | 0 | 0 | 0 | 1034 | 1034 | 1034 | 1034 | 1034 | 1034 | 1034 | 1034 | 1034 | 9506.079 | 3327.1277 | 6801.5995 | 19634.8062 | 1154.9886 | 612.144 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 264 | 1034 | 1034 | 1034 | 1034 | 1034 | 1034 | 1034 | 1034 | 1034 | 1034 | 1034 | 1034 | 12947.2796 | 4531.5479 | 9263.7786 | 26742.606 | 1573.0945 | 833.7401 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 264 | 1034 | 1034 | 1034 | 1034 | 1034 | 1034 | 1034 | 1034 | 1034 | 1034 | 1034 | 1034 | 13225.6461 | 4628.9761 | 9462.9498 | 27317.572 | 1606.916 | 851.6655 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | [5 empty] | 154 | 1034 | 1034 | 1034 | 1034 | 1034 | 1034 | 1034 | 0 | 0 | 0 | 0 | 0 | 7880.8319 | 2758.2912 | 5638.7352 | 16277.8582 | 957.5211 | 507.4862 | 89972.8425
1.3.4.2.3.6 | 1.3 | 1.3.4 | UW | WIPAC | Firmware support during development of Calibration Devices, Special Devices, system integration, and commissioning | Firmware support during development of Calibration Devices, Special Devices, system integration, and commissioning | S. Griffin | Labor Hours | Labor - LoE | EN | D - Expert Opinion | 47 | 49 | 35% | 53% | Off Ice | C1 | 9% | 2763.9182 | 957.4357 |  | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 84 | 329 | 329 | 329 | 329 | 329 | 329 | 329 | 329 | 329 | 329 | 329 | 329 | 4032.882 | 1411.5087 | 2885.5271 | 8329.9178 | 489.9952 | 259.6974 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 84 | 329 | 329 | 329 | 329 | 329 | 329 | 329 | 329 | 329 | 329 | 329 | 329 | 4119.589 | 1441.8561 | 2947.5659 | 8509.011 | 500.5301 | 265.2809 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 84 | 329 | 329 | 329 | 329 | 329 | 329 | 329 | 329 | 329 | 329 | 329 | 329 | 4208.1601 | 1472.856 | 3010.9386 | 8691.9547 | 511.2915 | 270.9845 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | [5 empty] | 49 | 329 | 329 | 329 | 329 | 329 | 329 | 329 | 0 | 0 | 0 | 0 | 0 | 2507.5374 | 877.6381 | 1794.143 | 5179.3185 | 304.6658 | 161.4729 | 30710.202
1.4.1.1.1.3.2.1 | 1.4 | 1.4.1 | MSU |  | Fabrication | First article cable fabrication | Ng | Labor Hours | Labor - LoE - Consultant | EN-ME | A - Analogy | 62 | 62 | 0% | 55% | Off Ice | C1 | 9% | 424.0778 | 150.4792 |  | 16 | 16 | 16 | [9 empty] | 48 | 992 | 992 | 992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3039.984 | 0 | 1671.9912 | 4711.9752 | 273.5986 | 150.4792 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4711.9752
1.4.1.1.1.3.2.2 | 1.4 | 1.4.1 | MSU |  | Acceptance testing | First article acceptance testing | Ng | Labor Hours | Labor - Task - Consultant | EN-ME | D - Expert Opinion | 62 | 62 | 0% | 55% | Off Ice | C4 | 35% | 1099.4609 | 390.1313 |  |  |  |  | 32 | [8 empty] | 32 | 0 | 0 | 0 | 1984 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026.656 | 0 | 1114.6608 | 3141.3168 | 709.3296 | 390.1313 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3141.3168
1.4.1.1.1.3.2.2 | 1.4 | 1.4.1 | MSU |  | Acceptance testing | First article acceptance testing | Wilkins | Labor Hours | Labor - Task - Consultant | TE | D - Expert Opinion | 47 | 46.67 | 0% | 55% | Off Ice | C4 | 35% | 833.4623 | 295.7447 |  |  |  |  | 32 | [8 empty] | 32 | 0 | 0 | 0 | 1504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1536.336 | 0 | 844.9848 | 2381.3208 | 537.7176 | 295.7447 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2381.3208
1.4.1.1.1.3.2.4 | 1.4 | 1.4.1 | MSU |  | First article shipping to breakout installation facility | First article shipping to breakout installation facility | Ng | Labor Hours | Labor - Task - Consultant | EN-ME | A - Analogy | 62 | 62 | 0% | 55% | Off Ice | C3 | 20% | 628.2634 | 222.9322 |  |  |  |  | 16 | 16 | [7 empty] | 32 | 0 | 0 | 0 | 992 | 992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026.656 | 0 | 1114.6608 | 3141.3168 | 405.3312 | 222.9322 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3141.3168
1.4.1.1.1.3.3 | 1.4 | 1.4.1 | MSU |  | Production readiness review | Production readiness review | Ng | Labor Hours | Labor - Task - Consultant | EN-ME | A - Analogy | 62 | 62 | 0% | 55% | Off Ice | C2 | 12.5% | 687.1631 | 243.8321 | [5 empty] | 56 | [7 empty] | 56 | 0 | 0 | 0 | 0 | 3472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3546.648 | 0 | 1950.6564 | 5497.3044 | 443.331 | 243.8321 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5497.3044
1.4.1.1.1.3.3 | 1.4 | 1.4.1 | MSU |  | Production readiness review | Production readiness review | Wilkins | Labor Hours | Labor - Task - Consultant | TE | A - Analogy | 47 | 46.67 | 0% | 55% | Off Ice | C2 | 12.5% | 520.9139 | 184.8404 | [5 empty] | 56 | [7 empty] | 56 | 0 | 0 | 0 | 0 | 2632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2688.588 | 0 | 1478.7234 | 4167.3114 | 336.0735 | 184.8404 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4167.3114
1.4.1.1.1.3.4 | 1.4 | 1.4.1 | MSU |  | Production of final six main cables | Production of final six main cables | Ng | Labor Hours | Labor - LoE - Consultant | EN-ME | A - Analogy | 62 | 62 | 0% | 55% | Off Ice | C1 | 9% | 424.0778 | 150.4792 | [5 empty] | 16 | 16 | 16 | [5 empty] | 48 | 0 | 0 | 0 | 0 | 992 | 992 | 992 | 0 | 0 | 0 | 0 | 0 | 3039.984 | 0 | 1671.9912 | 4711.9752 | 273.5986 | 150.4792 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4711.9752
1.4.1.1.1.3.6 | 1.4 | 1.4.1 | MSU |  | Production main cable shipping to breakout installation facility | Production cable shipping to breakout installation facility | Ng | Labor Hours | Labor - Task - Consultant | EN-ME | A - Analogy | 62 | 62 | 0% | 55% | Off Ice | C3 | 20% | 628.2634 | 222.9322 | [7 empty] | 8 | 8 | 16 |  |  |  | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 496 | 496 | 992 | 0 | 0 | 0 | 2026.656 | 0 | 1114.6608 | 3141.3168 | 405.3312 | 222.9322 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3141.3168
1.4.1.1.2.2.1 | 1.4 | 1.4.1 | MSU |  | Breakout final design | Breakout final design | Wilkins | Labor Hours | Labor - Task - Consultant | TE | D - Expert Opinion | 47 | 46.67 | 0% | 55% | Off Ice | C5 | 50% | 297.6651 | 105.6231 |  | 8 | [11 empty] | 8 | 376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 384.084 | 0 | 211.2462 | 595.3302 | 192.042 | 105.6231 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 595.3302
1.4.1.1.2.2.1 | 1.4 | 1.4.1 | MSU |  | Breakout final design | Breakout final design | Ng | Labor Hours | Labor - Task - Consultant | EN-ME | D - Expert Opinion | 62 | 62 | 0% | 55% | Off Ice | C5 | 50% | 1963.323 | 696.663 |  | 40 | [11 empty] | 40 | 2480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2533.32 | 0 | 1393.326 | 3926.646 | 1266.66 | 696.663 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3926.646
1.4.1.1.2.2.2 | 1.4 | 1.4.1 | MSU |  | Breakout prototype production | Breakout prototype production | Ng | Labor Hours | Labor - LoE - Consultant | EN-ME | A - Analogy | 62 | 62 | 0% | 55% | Off Ice | C1 | 9% | 282.7185 | 100.3195 |  | 16 | 16 | [10 empty] | 32 | 992 | 992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026.656 | 0 | 1114.6608 | 3141.3168 | 182.399 | 100.3195 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3141.3168
1.4.1.1.2.2.3 | 1.4 | 1.4.1 | MSU |  | Breakout prototype testing | Breakout prototype testing | Ng | Labor Hours | Labor - Task - Consultant | EN-ME | A - Analogy | 62 | 62 | 0% | 55% | Off Ice | C2 | 12.5% | 490.8308 | 174.1658 |  |  | 40 | [10 empty] | 40 | 0 | 2480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2533.32 | 0 | 1393.326 | 3926.646 | 316.665 | 174.1658 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3926.646
1.4.1.1.2.2.3 | 1.4 | 1.4.1 | MSU |  | Breakout prototype testing | Breakout prototype testing | Wilkins | Labor Hours | Labor - Task - Consultant | TE | A - Analogy | 47 | 46.67 | 0% | 55% | Off Ice | C2 | 12.5% | 372.0814 | 132.0289 |  |  | 40 | [10 empty] | 40 | 0 | 1880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1920.42 | 0 | 1056.231 | 2976.651 | 240.0525 | 132.0289 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2976.651
1.4.1.1.2.2.3 | 1.4 | 1.4.1 | MSU |  | Breakout prototype testing | Breakout prototype testing | Foreign | Travel | Travel |  | E - Extrapolation from Actuals |  | 1 | 0% | 55% | Off Ice | C1 | 9% | 1367.9928 | 485.4168 |  |  | 9600 | [10 empty] | 0 | 0 | 9600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9806.4 | 0 | 5393.52 | 15199.92 | 882.576 | 485.4168 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15199.92
1.4.1.1.2.2.4 | 1.4 | 1.4.1 | MSU |  | Breakout final design review | Breakout final design review | Wilkins | Labor Hours | Labor - Task - Consultant | TE | A - Analogy | 47 | 46.67 | 0% | 55% | Off Ice | C3 | 20% | 1428.7925 | 506.9909 |  |  |  | 96 | [9 empty] | 96 | 0 | 0 | 4512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4609.008 | 0 | 2534.9544 | 7143.9624 | 921.8016 | 506.9909 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7143.9624
1.4.1.1.2.2.4 | 1.4 | 1.4.1 | MSU |  | Breakout final design review | Breakout final design review | Ng | Labor Hours | Labor - Task - Consultant | EN-ME | A - Analogy | 62 | 62 | 0% | 55% | Off Ice | C3 | 20% | 1884.7901 | 668.7965 |  |  |  | 96 | [9 empty] | 96 | 0 | 0 | 5952 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6079.968 | 0 | 3343.9824 | 9423.9504 | 1215.9936 | 668.7965 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9423.9504
1.4.1.1.2.2.4 | 1.4 | 1.4.1 | MSU |  | Breakout final design review | Breakout final design review | Domestic | Travel | Travel |  | E - Extrapolation from Actuals |  | 1 | 0% | 55% | Off Ice | C1 | 9% | 769.496 | 273.047 |  |  |  | 5400 | [9 empty] | 0 | 0 | 0 | 5400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5516.1 | 0 | 3033.855 | 8549.955 | 496.449 | 273.047 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8549.955
1.4.1.1.3.2 | 1.4 | 1.4.1 | MSU |  | MCA production | MCA production | Foreign | Travel | Travel |  | E - Extrapolation from Actuals |  | 1 | 0% | 55% | Off Ice | C1 | 9% | 911.9952 | 323.6112 | [9 empty] | 6400 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6400 | 0 | 0 | 0 | 6537.6 | 0 | 3595.68 | 10133.28 | 588.384 | 323.6112 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10133.28
1.4.1.1.3.2 | 1.4 | 1.4.1 | MSU |  | MCA production | MCA production | Ng | Labor Hours | Labor - LoE - Consultant | EN-ME | A - Analogy | 62 | 62 | 0% | 55% | Off Ice | C1 | 9% | 494.7574 | 175.5591 | [9 empty] | 16 | 16 | 16 | 8 | 56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 992 | 992 | 992 | 496 | 3546.648 | 0 | 1950.6564 | 5497.3044 | 319.1983 | 175.5591 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5497.3044
1.4.1.1.3.3 | 1.4 | 1.4.1 | MSU |  | Pre-ship review | Pre-ship review | Wilkins | Labor Hours | Labor - Task - Consultant | TE | A - Analogy | 47 | 46.67 | 0% | 55% | Off Ice | C3 | 20% | 833.4623 | 295.7447 | [12 empty] | 56 | 56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2632 | 2688.588 | 0 | 1478.7234 | 4167.3114 | 537.7176 | 295.7447 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4167.3114
1.4.1.1.3.3 | 1.4 | 1.4.1 | MSU |  | Pre-ship review | Pre-ship review | Ng | Labor Hours | Labor - Task - Consultant | EN-ME | A - Analogy | 62 | 62 | 0% | 55% | Off Ice | C3 | 20% | 1099.4609 | 390.1313 | [12 empty] | 56 | 56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3472 | 3546.648 | 0 | 1950.6564 | 5497.3044 | 709.3296 | 390.1313 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5497.3044
1.4.1.1.3.4 | 1.4 | 1.4.1 | MSU |  | Main Cable Assembly shipping to PTH (RDD 12/1/23 for FY24 vessel. ROS 12/1/2025) | Main Cable Assembly shipping to PTH | Ng | Labor Hours | Labor - Task - Consultant | EN-ME | A - Analogy | 62 | 62 | 0% | 55% | Off Ice | C3 | 20% | 635.0172 | 225.3287 | [12 empty] | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 992 | 1013.328 | 0 | 557.3304 | 1570.6584 | 202.6656 | 111.4661 | 8 | 8 | [10 empty] | 16 | 496 | 496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1035.1146 | 0 | 569.313 | 1604.4276 | 207.0229 | 113.8626 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3175.086
1.4.1.2.1.5 | 1.4 | 1.4.1 | MSU |  | BCA prototype testing | BCA prototype evaluation | Ng | Labor Hours | Labor - Task - Consultant | EN-ME | A - Analogy | 62 | 62 | 0% | 55% | Off Ice | C4 | 35% | 1030.7446 | 365.7481 |  | 30 | [11 empty] | 30 | 1860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1899.99 | 0 | 1044.9945 | 2944.9845 | 664.9965 | 365.7481 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2944.9845
1.4.1.2.1.5 | 1.4 | 1.4.1 | MSU |  | BCA prototype testing | BCA prototype evaluation | Wilkins | Labor Hours | Labor - Task - Consultant | TE | A - Analogy | 47 | 46.67 | 0% | 55% | Off Ice | C4 | 35% | 781.3709 | 277.2606 |  | 30 | [11 empty] | 30 | 1410 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440.315 | 0 | 792.1733 | 2232.4883 | 504.1103 | 277.2606 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2232.4883
1.4.1.2.1.5 | 1.4 | 1.4.1 | MSU |  | BCA prototype testing | BCA prototype evaluation | Foreign | Travel | Travel |  | E - Extrapolation from Actuals |  | 1 | 0% | 55% | Off Ice | C1 | 9% | 1367.9928 | 485.4168 |  | 9600 | [11 empty] | 0 | 9600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9806.4 | 0 | 5393.52 | 15199.92 | 882.576 | 485.4168 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15199.92
1.4.1.2.2.1 | 1.4 | 1.4.1 | MSU |  | BCA final design | BCA final design | Ng | Labor Hours | Labor - Task - Consultant | EN-ME | D - Expert Opinion | 62 | 62 | 0% | 55% | Off Ice | C4 | 35% | 4810.1414 | 1706.8244 |  | 80 | 60 | [10 empty] | 140 | 4960 | 3720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8866.62 | 0 | 4876.641 | 13743.261 | 3103.317 | 1706.8244 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13743.261
1.4.1.2.2.1 | 1.4 | 1.4.1 | MSU |  | BCA final design | BCA final design | Wilkins | Labor Hours | Labor - Task - Consultant | TE | D - Expert Opinion | 47 | 46.67 | 0% | 55% | Off Ice | C4 | 35% | 2083.6557 | 739.3617 |  | 40 | 40 | [10 empty] | 80 | 1880 | 1880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3840.84 | 0 | 2112.462 | 5953.302 | 1344.294 | 739.3617 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5953.302
1.4.1.2.2.2 | 1.4 | 1.4.1 | MSU |  | BCA final design review | BCA final design review | Ng | Labor Hours | Labor - Task - Consultant | EN-ME | A - Analogy | 62 | 62 | 0% | 55% | Off Ice | C2 | 12.5% | 1177.9938 | 417.9978 |  |  | 20 | 76 | [9 empty] | 96 | 0 | 1240 | 4712 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6079.968 | 0 | 3343.9824 | 9423.9504 | 759.996 | 417.9978 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9423.9504
1.4.1.2.2.2 | 1.4 | 1.4.1 | MSU |  | BCA final design review | BCA final design review | Wilkins | Labor Hours | Labor - Task - Consultant | TE | A - Analogy | 47 | 46.67 | 0% | 55% | Off Ice | C2 | 12.5% | 892.9953 | 316.8693 |  |  | 20 | 76 | [9 empty] | 96 | 0 | 940 | 3572 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4609.008 | 0 | 2534.9544 | 7143.9624 | 576.126 | 316.8693 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7143.9624
1.4.1.2.2.2 | 1.4 | 1.4.1 | MSU |  | BCA final design review | BCA final design review | Domestic | Travel | Travel |  | E - Extrapolation from Actuals |  | 1 | 0% | 55% | Off Ice | C1 | 9% | 769.496 | 273.047 |  |  |  | 5400 | [9 empty] | 0 | 0 | 0 | 5400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5516.1 | 0 | 3033.855 | 8549.955 | 496.449 | 273.047 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8549.955
1.4.1.2.2.4 | 1.4 | 1.4.1 | MSU |  | BCA procurement | BCA procurement | Ng | Labor Hours | Labor - Task - Consultant | EN-ME | D - Expert Opinion | 62 | 62 | 0% | 55% | Off Ice | C4 | 35% | 2748.6522 | 975.3282 |  |  |  | 40 | 32 | 8 | [7 empty] | 80 | 0 | 0 | 2480 | 1984 | 496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5066.64 | 0 | 2786.652 | 7853.292 | 1773.324 | 975.3282 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7853.292
1.4.1.2.3.1 | 1.4 | 1.4.1 | MSU |  | BCA manufacturing | BCA manufacturing - first two strings | Ng | Labor Hours | Labor - LoE - Consultant | EN-ME | A - Analogy | 62 | 62 | 0% | 55% | Off Ice | C1 | 9% | 706.7963 | 250.7987 | [5 empty] | 16 | 16 | 16 | 16 | 16 |  |  |  | 80 | 0 | 0 | 0 | 0 | 992 | 992 | 992 | 992 | 992 | 0 | 0 | 0 | 5066.64 | 0 | 2786.652 | 7853.292 | 455.9976 | 250.7987 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7853.292
1.4.1.2.3.1 | 1.4 | 1.4.1 | MSU |  | BCA manufacturing | BCA manufacturing - first two strings | Foreign | Travel | Travel |  | E - Extrapolation from Actuals |  | 1 | 0% | 55% | Off Ice | C1 | 9% | 911.9952 | 323.6112 | [6 empty] | 6400 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 6400 | 0 | 0 | 0 | 0 | 0 | 0 | 6537.6 | 0 | 3595.68 | 10133.28 | 588.384 | 323.6112 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10133.28
1.4.1.2.3.1 | 1.4 | 1.4.1 | MSU |  | BCA manufacturing | BCA connectors - first two strings, MCA side (62 connectors) |  | CapEx | CapEx |  | A - Analogy |  | 1 | 0% | 0% | Off Ice | C3 | 20% | 4433.31 | 0 | PCA side connectors already purchased |  |  |  |  | 21700 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 21700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22166.55 | 0 | 0 | 22166.55 | 4433.31 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22166.55
1.4.1.2.3.1 | 1.4 | 1.4.1 | MSU |  | BCA manufacturing | BCA cable - first two strings (3,000 m) |  | CapEx | CapEx |  | A - Analogy |  | 1 | 0% | 0% | Off Ice | C4 | 35% | 18233.775 | 0 | 2,000 m of cable for first two strings and spares, $15/m based on SB 45027 |  |  |  |  | 51000 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 51000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52096.5 | 0 | 0 | 52096.5 | 18233.775 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52096.5
1.4.1.2.3.1 | 1.4 | 1.4.1 | MSU |  | BCA manufacturing | BCA fabrication costs - first two strings |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 0% | Off Ice | C4 | 35% | 8938.125 | 0 | [9 empty] | 25000 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 25537.5 | 0 | 0 | 25537.5 | 8938.125 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25537.5
1.4.1.2.3.2 | 1.4 | 1.4.1 | MSU |  | BCA pre-ship review | BCA pre-ship review | Ng | Labor Hours | Labor - Task - Consultant | EN-ME | A - Analogy | 62 | 62 | 0% | 55% | Off Ice | C3 | 20% | 1099.4609 | 390.1313 | [9 empty] | 56 |  |  |  | 56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3472 | 0 | 0 | 0 | 3546.648 | 0 | 1950.6564 | 5497.3044 | 709.3296 | 390.1313 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5497.3044
1.4.1.2.3.3 | 1.4 | 1.4.1 | MSU |  | Shipping to PTH (FY24 vessel, RDD 12/1/23 - ROS 2/1/25 to pre-position) | Shipping to PTH | Ng | Labor Hours | Labor - Task - Consultant | EN-ME | A - Analogy | 62 | 62 | 0% | 55% | Off Ice | C3 | 20% | 628.2634 | 222.9322 | [9 empty] | 16 | 16 |  |  | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 992 | 992 | 0 | 0 | 2026.656 | 0 | 1114.6608 | 3141.3168 | 405.3312 | 222.9322 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3141.3168
1.4.1.2.3.3 | 1.4 | 1.4.1 | MSU |  | Shipping to PTH (FY24 vessel, RDD 12/1/23 - ROS 2/1/25 to pre-position) | BCA shipping costs to PTH (1st two strings) |  | M & S | M & S |  | D - Expert Opinion |  | 1 | 0% | 55% | Off Ice | C4 | 35% | 4433.31 | 1573.11 | [9 empty] | 8000 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8000 | 0 | 0 | 0 | 8172 | 0 | 4494.6 | 12666.6 | 2860.2 | 1573.11 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12666.6
1.4.1.2.4.1 | 1.4 | 1.4.1 | MSU |  | BCA manufacturing - final five strings | BCA manufacturing | Ng | Labor Hours | Labor - LoE - Consultant | EN-ME | A - Analogy | 62 | 62 | 0% | 55% | Off Ice | C1 | 9% | 568.4762 | 201.7174 | [10 empty] | 16 | 16 | 16 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 992 | 992 | 992 | 3039.984 | 0 | 1671.9912 | 4711.9752 | 273.5986 | 150.4792 | 16 | [11 empty] | 16 | 992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1035.1146 | 0 | 569.313 | 1604.4276 | 93.1603 | 51.2382 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6316.4028
1.4.1.2.4.1 | 1.4 | 1.4.1 | MSU |  | BCA manufacturing - final five strings | BCA manufacturing | Foreign | Travel | Travel |  | E - Extrapolation from Actuals |  | 1 | 0% | 55% | Off Ice | C1 | 9% | 911.9952 | 323.6112 | [12 empty] | 6400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6400 | 6537.6 | 0 | 3595.68 | 10133.28 | 588.384 | 323.6112 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10133.28
1.4.1.2.4.1 | 1.4 | 1.4.1 | MSU |  | BCA manufacturing - final five strings | BCA connectors - last five strings, MCA side (110 connectors) |  | CapEx | CapEx |  | A - Analogy |  | 1 | 0% | 0% | Off Ice | C3 | 20% | 7865.55 | 0 | [5 empty] | 38500 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 38500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39327.75 | 0 | 0 | 39327.75 | 7865.55 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39327.75
1.4.1.2.4.1 | 1.4 | 1.4.1 | MSU |  | BCA manufacturing - final five strings | BCA cable - last five strings (6,830 m) |  | CapEx | CapEx |  | A - Analogy |  | 1 | 0% | 0% | Off Ice | C4 | 35% | 41512.2277 | 0 | 4,556 m of cable for remaining five strings, $15/m based on SB 45027 |  |  |  |  | 116110 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 116110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118606.365 | 0 | 0 | 118606.365 | 41512.2277 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118606.365
1.4.1.2.4.1 | 1.4 | 1.4.1 | MSU |  | BCA manufacturing - final five strings | BCA fabrication costs - last five strings |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 0% | Off Ice | C4 | 35% | 16434.5304 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | [11 empty] | 0 | 45000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46955.8013 | 0 | 0 | 46955.8013 | 16434.5304 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46955.8013
1.4.1.2.4.2 | 1.4 | 1.4.1 | MSU |  | Shipping to PTH (FY24 vessel, RDD 12/1/23 - ROS 12/1/25) | Shipping to PTH | Ng | Labor Hours | Labor - Task - Consultant | EN-ME | A - Analogy | 62 | 62 | 0% | 55% | Off Ice | C2 | 12.5% | 401.1069 | 142.3283 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | [11 empty] | 32 | 1984 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2070.2291 | 0 | 1138.626 | 3208.8551 | 258.7786 | 142.3283 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3208.8551
1.4.1.2.4.2 | 1.4 | 1.4.1 | MSU |  | Shipping to PTH (FY24 vessel, RDD 12/1/23 - ROS 12/1/25) | BCA shipping costs to PTH (remaining strings) |  | M & S | M & S |  | D - Expert Opinion |  | 1 | 0% | 55% | Off Ice | C4 | 35% | 5660.7827 | 2008.6648 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | [11 empty] | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10434.6225 | 0 | 5739.0424 | 16173.6649 | 3652.1179 | 2008.6648 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16173.6649
1.4.1.2.5 | 1.4 | 1.4.1 | MSU |  | Breakout Cable Assemblies support | Breakout Cable Assembly miscellaneous supplies |  | M & S | M & S |  | F - Parametric |  | 1 | 0% | 55% | Off Ice | C1 | 9% | 89.445 | 31.7385 |  | 125 |  |  | 125 |  |  | 125 |  |  | 125 |  |  | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 510.75 | 0 | 280.9125 | 791.6625 | 45.9675 | 25.2821 | 125 | [11 empty] | 0 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130.4328 | 0 | 71.738 | 202.1708 | 11.739 | 6.4564 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 993.8333
1.4.1.3.4.2 | 1.4 | 1.4.1 | MSU |  | SPAT cable materials procurement | SPAT cable materials |  | M & S | M & S |  | C - Engineering Buildup |  | 1 | 0% | 55% | Off Ice | C2 | 12.5% | 189.999 | 67.419 |  | 960 | [11 empty] | 0 | 960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 980.64 | 0 | 539.352 | 1519.992 | 122.58 | 67.419 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1519.992
1.4.1.3.4.3 | 1.4 | 1.4.1 | MSU |  | SPAT cable production | SPAT cable production | Wilkins | Labor Hours | Labor - Task - Consultant | TE | A - Analogy | 47 | 46.67 | 0% | 55% | Off Ice | C3 | 20% | 595.3302 | 211.2462 |  | 40 | [11 empty] | 40 | 1880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1920.42 | 0 | 1056.231 | 2976.651 | 384.084 | 211.2462 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2976.651
1.4.1.3.4.4 | 1.4 | 1.4.1 | MSU |  | SPAT cable shipping to WIPAC | SPAT cable shipping | Wilkins | Labor Hours | Labor - Task - Consultant | TE | A - Analogy | 47 | 46.67 | 0% | 55% | Off Ice | C2 | 12.5% | 74.4163 | 26.4058 |  |  | 8 | [10 empty] | 8 | 0 | 376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 384.084 | 0 | 211.2462 | 595.3302 | 48.0105 | 26.4058 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 595.3302
1.4.1.3.5 | 1.4 | 1.4.1 | MSU |  | Penetrator Cable Assemblies support | Penetrator Cable Assembly Miscellaneous supplies |  | M & S | M & S |  | F - Parametric |  | 1 | 0% | 55% | Off Ice | C1 | 9% | 17.8124 | 6.3205 |  | 125 | [11 empty] | 0 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 127.6875 | 0 | 70.2281 | 197.9156 | 11.4919 | 6.3205 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 197.9156
1.4.1.4.1.5 | 1.4 | 1.4.1 | MSU |  | String hardware final design review | String hardware final design review | Domestic | Travel | Travel |  | E - Extrapolation from Actuals |  | 1 | 0% | 55% | Off Ice | C1 | 9% | 512.9973 | 182.0313 |  | 3600 | [11 empty] | 0 | 3600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3677.4 | 0 | 2022.57 | 5699.97 | 330.966 | 182.0313 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5699.97
1.4.1.4.1.7 | 1.4 | 1.4.1 | MSU |  | String hardware production | String hardware shipping to MCA production facility | Ng | Labor Hours | Labor - Task - Consultant | EN-ME | A - Analogy | 62 | 62 | 0% | 55% | Off Ice | C3 | 20% | 314.1317 | 111.4661 |  | 8 | 8 | [10 empty] | 16 | 496 | 496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1013.328 | 0 | 557.3304 | 1570.6584 | 202.6656 | 111.4661 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1570.6584
1.4.1.4.2 | 1.4 | 1.4.1 | MSU |  | String hardware support | String hardware miscellaneous supplies |  | M & S | M & S |  | F - Parametric |  | 1 | 0% | 55% | Off Ice | C1 | 9% | 35.6248 | 12.6411 |  | 125 |  |  | 125 | [8 empty] | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 255.375 | 0 | 140.4563 | 395.8313 | 22.9838 | 12.6411 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 395.8313
1.4.1.6.1 | 1.4 | 1.4.1 | MSU |  | Off-ice training Cable SMEs (FS3) | Off-Ice Safety Training FS3 Cable SMEs (Headcount 2) | Domestic | Travel | Travel |  | E - Extrapolation from Actuals |  | 1 | 0% | 55% | On Ice | C1 | 9% | 535.2933 | 189.9428 | standard domestic trip $1800 (x2) | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 3600 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3600 | 0 | 3837.2281 | 0 | 2110.4754 | 5947.7035 | 345.3505 | 189.9428 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5947.7035
1.4.1.6.3 | 1.4 | 1.4.1 | MSU |  | PQ, ECW & Deployment Travel Costs Cable SMEs (FS3) | Cable SME FS3 PQ costs (Headcount 2) |  | M & S | M & S |  | C - Engineering Buildup |  | 1 | 0% | 55% | On Ice | C2 | 12.5% | 206.5175 | 73.2804 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 500 | 500 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 500 | 0 | 0 | 1065.8967 | 0 | 586.2432 | 1652.1399 | 133.2371 | 73.2804 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1652.1399
1.4.1.6.3 | 1.4 | 1.4.1 | MSU |  | PQ, ECW & Deployment Travel Costs Cable SMEs (FS3) | Cable SME FS3 ECW costs (Headcount 2) |  | M & S | M & S |  | C - Engineering Buildup |  | 1 | 0% | 55% | On Ice | C2 | 12.5% | 86.1178 | 30.5579 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 208 | 209 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 208 | 209 | 444.4789 | 0 | 244.4634 | 688.9423 | 55.5599 | 30.5579 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 688.9423
1.4.1.6.3 | 1.4 | 1.4.1 | MSU |  | PQ, ECW & Deployment Travel Costs Cable SMEs (FS3) | Cable SME FS3 Deployment travel (Headcount 2) | Foreign | Travel | Travel |  | E - Extrapolation from Actuals |  | 1 | 0% | 55% | On Ice | C1 | 9% | 546.8021 | 194.0266 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2160 |  |  | 1440 | [7 empty] | 0 | 0 | 2160 | 0 | 0 | 1440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3919.7285 | 0 | 2155.8507 | 6075.5791 | 352.7756 | 194.0266 | 6075.5791
1.4.1.6.4 | 1.4 | 1.4.1 | MSU |  | Cable SME support for FS3 activities (slot 1) | On-Ice Cable SME support for FS3 activities (slot 1) | Ng | Labor Hours | Labor - LoE - Consultant | EN-ME | C - Engineering Buildup | 62 | 62 | 0% | 55% | On Ice | C1 | 9% | 2825.1443 | 1002.4706 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 75 | 150 | 75 | [8 empty] | 300 | 0 | 4650 | 9300 | 4650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20251.9305 | 0 | 11138.5618 | 31390.4923 | 1822.6737 | 1002.4706 | 31390.4923
1.4.1.6.5 | 1.4 | 1.4.1 | MSU |  | Cable SME support for FS3 activities (slot 2) | On-Ice Cable SME support for FS3 activities (slot 2) | TBD | Labor Hours | Labor - LoE - Consultant | EN-ME | C - Engineering Buildup | 62 | 62 | 0% | 55% | On Ice | C1 | 9% | 1789.2581 | 634.898 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 40 | 150 | [8 empty] | 190 | 0 | 0 | 2480 | 9300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12826.2226 | 0 | 7054.4225 | 19880.6451 | 1154.36 | 634.898 | 19880.6451
1.4.2.2.4 | 1.4 | 1.4.2 | MSU |  | Fabrication | Fabrication | Ng | Labor Hours | Labor - Task - Consultant | EN-ME | D - Expert Opinion | 62 | 62 | 0% | 55% | Off Ice | C4 | 35% | 274.8652 | 97.5328 |  | 8 | [11 empty] | 8 | 496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 506.664 | 0 | 278.6652 | 785.3292 | 177.3324 | 97.5328 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 785.3292
1.4.2.2.4 | 1.4 | 1.4.2 | MSU |  | Fabrication | SJBs |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 0% | Off Ice | C4 | 35% | 5005.35 | 0 |  | 14000 | [11 empty] | 0 | 14000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14301 | 0 | 0 | 14301 | 5005.35 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14301
1.4.2.2.6 | 1.4 | 1.4.2 | MSU |  | Pre-ship review | Pre-ship review | Wilkins | Labor Hours | Labor - Task - Consultant | TE | A - Analogy | 47 | 46.67 | 0% | 55% | Off Ice | C2 | 12.5% | 223.2488 | 79.2173 |  | 24 | [11 empty] | 24 | 1128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1152.252 | 0 | 633.7386 | 1785.9906 | 144.0315 | 79.2173 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1785.9906
1.4.2.2.6 | 1.4 | 1.4.2 | MSU |  | Pre-ship review | Pre-ship review | Ng | Labor Hours | Labor - Task - Consultant | EN-ME | A - Analogy | 62 | 62 | 0% | 55% | Off Ice | C2 | 12.5% | 294.4985 | 104.4995 |  | 24 | [11 empty] | 24 | 1488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1519.992 | 0 | 835.9956 | 2355.9876 | 189.999 | 104.4995 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2355.9876
1.4.2.2.6 | 1.4 | 1.4.2 | UW | WIPAC | Pre-ship review | Pre-ship review | Kelley | Labor Hours | Labor - Task | SS | A - Analogy | 63.95 | 66 | 35% | 53% | Off Ice | C2 | 12.5% | 404.7859 | 140.22 |  | 24 | [11 empty] | 24 | 1534.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1567.7982 | 548.7294 | 1121.7596 | 3238.2872 | 264.5659 | 140.22 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3238.2872
1.4.2.2.6 | 1.4 | 1.4.2 | MSU |  | Pre-ship review | Shipping to PTH | Ng | Labor Hours | Labor - Task - Consultant | EN-ME | D - Expert Opinion | 62 | 62 | 0% | 55% | Off Ice | C3 | 20% | 471.1975 | 167.1991 |  | 24 | [11 empty] | 24 | 1488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1519.992 | 0 | 835.9956 | 2355.9876 | 303.9984 | 167.1991 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2355.9876
1.4.2.2.6 | 1.4 | 1.4.2 | MSU |  | Pre-ship review | Shipping costs to PTH |  | M & S | M & S |  | D - Expert Opinion |  | 1 | 0% | 55% | Off Ice | C4 | 35% | 831.2456 | 294.9581 |  | 1500 | [11 empty] | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1532.25 | 0 | 842.7375 | 2374.9875 | 536.2875 | 294.9581 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2374.9875
1.4.2.2.8 | 1.4 | 1.4.2 | MSU |  | Surface Junction Box support | Surface Junction Box miscellaneous supplies |  | M & S | M & S |  | F - Parametric |  | 1 | 0% | 55% | Off Ice | C1 | 9% | 18.0119 | 6.3913 |  |  | 125 | [10 empty] | 0 | 0 | 126.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 129.1176 | 0 | 71.0147 | 200.1323 | 11.6206 | 6.3913 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200.1323
1.4.2.3.2.3 | 1.4 | 1.4.2 | UW | WIPAC | Fabrication | Fabrication | Kelley | Labor Hours | Labor - Task | SS | D - Expert Opinion | 63.95 | 66 | 35% | 53% | Off Ice | C4 | 35% | 944.5004 | 327.1799 |  | 20 | [11 empty] | 20 | 1279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1306.4985 | 457.2745 | 934.7997 | 2698.5727 | 617.3205 | 327.1799 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2698.5727
1.4.2.3.2.4 | 1.4 | 1.4.2 | UW | WIPAC | Pre-ship review | Pre-ship review | Kelley | Labor Hours | Labor - Task | SS | A - Analogy | 63.95 | 66 | 35% | 53% | Off Ice | C2 | 12.5% | 134.9286 | 46.74 |  |  | 8 | [10 empty] | 8 | 0 | 511.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 522.5994 | 182.9098 | 373.9199 | 1079.4291 | 88.1886 | 46.74 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1079.4291
1.4.2.3.2.5 | 1.4 | 1.4.2 | UW | WIPAC | Shipping to PTH (NB: small -- RDD 9/15/23 for ComSur FY25, ROS 12/15/23) | Shipping to PTH (NB: small) | Kelley | Labor Hours | Labor - Task | SS | D - Expert Opinion | 63.95 | 66 | 35% | 53% | Off Ice | C3 | 20% | 431.7716 | 149.5679 |  |  | 8 | 8 | [9 empty] | 16 | 0 | 511.6 | 511.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1045.1988 | 365.8196 | 747.8397 | 2158.8581 | 282.2037 | 149.5679 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2158.8581
1.4.2.3.2.5 | 1.4 | 1.4.2 | UW | WIPAC | Shipping to PTH (NB: small -- RDD 9/15/23 for ComSur FY25, ROS 12/15/23) | Shipping costs |  | M & S | M & S |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C4 | 35% | 547.0133 | 189.4883 |  |  | 1000 | [10 empty] | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1021.5 | 0 | 541.395 | 1562.895 | 357.525 | 189.4883 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1562.895
1.4.2.3.3.1 | 1.4 | 1.4.2 | UW | WIPAC | Final design | Final design | Kelley | Labor Hours | Labor - Task | SS | D - Expert Opinion | 63.95 | 66 | 35% | 53% | Off Ice | C4 | 35% | 1133.4005 | 392.6159 | [5 empty] | 24 | [7 empty] | 24 | 0 | 0 | 0 | 0 | 1534.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1567.7982 | 548.7294 | 1121.7596 | 3238.2872 | 740.7846 | 392.6159 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3238.2872
1.4.2.3.3.3 | 1.4 | 1.4.2 | UW | WIPAC | Final design review | Final design review | Kelley | Labor Hours | Labor - Task | SS | A - Analogy | 63.95 | 66 | 35% | 53% | Off Ice | C2 | 12.5% | 944.5004 | 327.1799 | [6 empty] | 56 | [6 empty] | 56 | 0 | 0 | 0 | 0 | 0 | 3581.2 | 0 | 0 | 0 | 0 | 0 | 0 | 3658.1958 | 1280.3685 | 2617.4391 | 7556.0034 | 617.3205 | 327.1799 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7556.0034
1.4.2.3.3.4 | 1.4 | 1.4.2 | UW | WIPAC | Procurement | Procurement | Kelley | Labor Hours | Labor - Task | SS | D - Expert Opinion | 63.95 | 66 | 35% | 53% | Off Ice | C3 | 20% | 431.7716 | 149.5679 | [6 empty] | 8 | 8 | [5 empty] | 16 | 0 | 0 | 0 | 0 | 0 | 511.6 | 511.6 | 0 | 0 | 0 | 0 | 0 | 1045.1988 | 365.8196 | 747.8397 | 2158.8581 | 282.2037 | 149.5679 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2158.8581
1.4.2.3.3.4 | 1.4 | 1.4.2 | MSU |  | Procurement | Procurement | Wilkins | Labor Hours | Labor - LoE - Consultant | TE | A - Analogy | 47 | 46.67 | 0% | 55% | Off Ice | C1 | 9% | 267.8986 | 95.0608 | [6 empty] | 8 | 8 | 8 | 8 | 8 |  |  | 40 | 0 | 0 | 0 | 0 | 0 | 376 | 376 | 376 | 376 | 376 | 0 | 0 | 1920.42 | 0 | 1056.231 | 2976.651 | 172.8378 | 95.0608 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2976.651
1.4.2.3.3.4 | 1.4 | 1.4.2 | UW | WIPAC | Procurement | Patch cables (169) |  | M & S | M & S |  | C - Engineering Buildup |  | 1 | 0% | 53% | Off Ice | C2 | 12.5% | 5777.8275 | 2001.4696 | [8 empty] | 29575 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29575 | 0 | 0 | 0 | 0 | 30210.8625 | 0 | 16011.7571 | 46222.6196 | 3776.3578 | 2001.4696 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46222.6196
1.4.2.3.3.5 | 1.4 | 1.4.2 | MSU |  | Production | Production | Wilkins | Labor Hours | Labor - Task - Consultant | TE | D - Expert Opinion | 47 | 46.67 | 0% | 55% | Off Ice | C3 | 20% | 2688.5856 | 954.0142 | [10 empty] | 50 | 50 | 50 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2350 | 2350 | 2350 | 7201.575 | 0 | 3960.8663 | 11162.4413 | 1440.315 | 792.1733 | 30 | [11 empty] | 30 | 1410 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1471.2818 | 0 | 809.205 | 2280.4867 | 294.2564 | 161.841 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13442.928
1.4.2.3.3.6 | 1.4 | 1.4.2 | UW | WIPAC | Pre-ship review | Pre-ship review | Kelley | Labor Hours | Labor - Task | SS | A - Analogy | 63.95 | 66 | 35% | 53% | Off Ice | C2 | 12.5% | 413.4888 | 143.2347 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | [11 empty] | 24 | 1534.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1601.5059 | 560.5271 | 1145.8774 | 3307.9104 | 270.2541 | 143.2347 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3307.9104
1.4.2.3.3.7 | 1.4 | 1.4.2 | MSU |  | Shipping to PTH (RDD 9/15/24 for FY25 ComSur, ROS 12/1/24) | Shipping to PTH | Wilkins | Labor Hours | Labor - Task - Consultant | TE | D - Expert Opinion | 47 | 46.67 | 0% | 55% | Off Ice | C3 | 20% | 486.5038 | 172.6304 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 8 | [10 empty] | 32 | 1128 | 376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1569.3672 | 0 | 863.152 | 2432.5192 | 313.8734 | 172.6304 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2432.5192
1.4.2.3.3.7 | 1.4 | 1.4.2 | UW | WIPAC | Shipping to PTH (RDD 9/15/24 for FY25 ComSur, ROS 12/1/24) | Patch cable shipping costs |  | M & S | M & S |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C4 | 35% | 670.5288 | 232.2747 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1200 | [10 empty] | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1252.1547 | 0 | 663.642 | 1915.7967 | 438.2541 | 232.2747 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1915.7967
1.4.2.3.4 | 1.4 | 1.4.2 | UW | WIPAC | ICL Upgrade support | ICL Upgrade Support miscellaneous supplies |  | M & S | M & S |  | F - Parametric |  | 1 | 0% | 53% | Off Ice | C1 | 9% | 253.042 | 87.6551 |  | 125 |  |  | 125 |  |  | 125 |  |  | 125 |  |  | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 510.75 | 0 | 270.6975 | 781.4475 | 45.9675 | 24.3628 | 125 |  |  | 125 |  |  | 125 |  |  | 125 |  |  | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 521.7311 | 0 | 276.5175 | 798.2486 | 46.9558 | 24.8866 | 125 |  |  | 125 |  |  | 125 |  |  | 125 |  |  | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 532.9483 | 0 | 282.4626 | 815.411 | 47.9654 | 25.4216 | 125 |  |  | 125 | [8 empty] | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 272.2034 | 0 | 144.2678 | 416.4712 | 24.4983 | 12.9841 | 2811.5782
1.4.2.4.4 | 1.4 | 1.4.2 | MSU |  | PQ, ECW, Deployment Travel Costs Cable SMEs (FS2) | Cable SME FS2 PQ costs (Headcount 2) |  | M & S | M & S |  | C - Engineering Buildup |  | 1 | 0% | 55% | On Ice | C2 | 12.5% | 283.0391 | 100.4332 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 700 | 700 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 700 | 700 | 0 | 0 | 1460.8472 | 0 | 803.4659 | 2264.3131 | 182.6059 | 100.4332 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2264.3131
1.4.2.4.4 | 1.4 | 1.4.2 | MSU |  | PQ, ECW, Deployment Travel Costs Cable SMEs (FS2) | Cable SME FS2 ECW costs (Headcount 2) |  | M & S | M & S |  | C - Engineering Buildup |  | 1 | 0% | 55% | On Ice | C2 | 12.5% | 101.0854 | 35.869 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 250 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 250 | 521.7311 | 0 | 286.9521 | 808.6832 | 65.2164 | 35.869 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 808.6832
1.4.2.4.4 | 1.4 | 1.4.2 | MSU |  | PQ, ECW, Deployment Travel Costs Cable SMEs (FS2) | Cable SME FS2 Deployment travel (Headcount 2) | Foreign | Travel | Travel |  | E - Extrapolation from Actuals |  | 1 | 0% | 55% | On Ice | C1 | 9% | 535.2933 | 189.9428 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2160 |  |  | 1440 | [7 empty] | 0 | 0 | 2160 | 0 | 0 | 1440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3837.2281 | 0 | 2110.4754 | 5947.7035 | 345.3505 | 189.9428 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5947.7035
1.4.2.4.5 | 1.4 | 1.4.2 | MSU |  | Cable SME support for FS2 activities (slot 1) | Cable SME support for FS2 activities (slot 1) | Ng | Labor Hours | Labor - LoE - Consultant | EN-ME | C - Engineering Buildup | 62 | 62 | 0% | 55% | On Ice | C1 | 9% | 1060.1782 | 376.1922 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 75 | 40 | [8 empty] | 115 | 0 | 0 | 4650 | 2480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7599.8434 | 0 | 4179.9139 | 11779.7573 | 683.9859 | 376.1922 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11779.7573
1.4.2.4.6 | 1.4 | 1.4.2 | MSU |  | Cable SME support for FS2 activities (slot 2) | Cable SME support for FS2 activities (slot 2) | Shooltz | Labor Hours | Labor - LoE - Consultant | EN-EE | C - Engineering Buildup | 72 | 72 | 0% | 55% | On Ice | C1 | 9% | 1605.88 | 569.8284 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 75 | 75 | [8 empty] | 150 | 0 | 0 | 5400 | 5400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11511.6842 | 0 | 6331.4263 | 17843.1106 | 1036.0516 | 569.8284 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17843.1106
1.4.4.1.1.1 | 1.4 | 1.4.4 | UW | WIPAC | Procurement | Procurement | Kelley | Labor Hours | Labor - LoE | SS | A - Analogy | 63.95 | 66 | 35% | 53% | Off Ice | C1 | 9% | 485.7431 | 168.2639 |  | 8 | 8 | 8 | 8 | 8 | [7 empty] | 40 | 511.6 | 511.6 | 511.6 | 511.6 | 511.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2612.997 | 914.5489 | 1869.5994 | 5397.1453 | 317.4791 | 168.2639 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5397.1453
1.4.4.1.1.1 | 1.4 | 1.4.4 | UW | WIPAC | Procurement | White Rabbit OEM nodes for NTS and SPTS (10 total, 6 to be purchased) |  | CapEx | CapEx |  | C - Engineering Buildup |  | 1 | 0% | 0% | Off Ice | C2 | 12.5% | 826.7766 | 0 | 4 already purchased by NvE, 6 more planned | 6475 | [11 empty] | 0 | 6475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6614.2125 | 0 | 0 | 6614.2125 | 826.7766 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6614.2125
1.4.4.1.1.1 | 1.4 | 1.4.4 | UW | WIPAC | Procurement | White Rabbit OEM nodes for ICL (10) |  | CapEx | CapEx |  | C - Engineering Buildup |  | 1 | 0% | 0% | Off Ice | C2 | 12.5% | 1377.8758 | 0 |  | 10791 | [11 empty] | 0 | 10791 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11023.0065 | 0 | 0 | 11023.0065 | 1377.8758 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11023.0065
1.4.4.1.1.1 | 1.4 | 1.4.4 | UW | WIPAC | Procurement | Fiber patch cables for ICL (10) |  | M & S | M & S |  | C - Engineering Buildup |  | 1 | 0% | 53% | Off Ice | C2 | 12.5% | 39.0724 | 13.5349 | [5 empty] | 200 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 204.3 | 0 | 108.279 | 312.579 | 25.5375 | 13.5349 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 312.579
1.4.4.1.1.5 | 1.4 | 1.4.4 | UW | WIPAC | Shipping to PTH (RDD 9/15/24 for FY25 ComSur - ROS 12/1/24) | Shipping to PTH | Kelley | Labor Hours | Labor - Task | SS | D - Expert Opinion | 63.95 | 66 | 35% | 53% | Off Ice | C3 | 20% | 647.6574 | 224.3519 | [7 empty] | 8 | 8 | 8 |  |  |  | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 511.6 | 511.6 | 511.6 | 0 | 0 | 0 | 1567.7982 | 548.7294 | 1121.7596 | 3238.2872 | 423.3055 | 224.3519 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3238.2872
1.4.4.1.1.5 | 1.4 | 1.4.4 | UW | WIPAC | Shipping to PTH (RDD 9/15/24 for FY25 ComSur - ROS 12/1/24) | Shipping costs |  | M & S | M & S |  | A - Analogy |  | 1 | 0% | 53% | Off Ice | C4 | 35% | 164.104 | 56.8465 | [7 empty] | 300 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 306.45 | 0 | 162.4185 | 468.8685 | 107.2575 | 56.8465 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 468.8685
1.4.4.1.2.1 | 1.4 | 1.4.4 | UW | WIPAC | Final design | Final design | Kelley | Labor Hours | Labor - Task | SS | D - Expert Opinion | 63.95 | 66 | 35% | 53% | Off Ice | C4 | 35% | 6753.6503 | 2339.4998 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 40 | 60 | 20 | 20 |  |  |  |  | 140 | 0 | 0 | 0 | 0 | 2558 | 3837 | 1279 | 1279 | 0 | 0 | 0 | 0 | 9342.1175 | 3269.7411 | 6684.2851 | 19296.1437 | 4414.1505 | 2339.4998 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19296.1437
1.4.4.1.2.2 | 1.4 | 1.4.4 | UW | WIPAC | Prototype production | Prototype production | Kelley | Labor Hours | Labor - Task | SS | D - Expert Opinion | 63.95 | 66 | 35% | 53% | Off Ice | C3 | 20% | 2205.2736 | 763.9183 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 80 | [5 empty] | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 5116 | 0 | 0 | 0 | 0 | 0 | 5338.3529 | 1868.4235 | 3819.5915 | 11026.3679 | 1441.3553 | 763.9183 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11026.3679
1.4.4.1.2.2 | 1.4 | 1.4.4 | UW | WIPAC | Prototype production | Timing monitoring prototype |  | CapEx | CapEx |  | A - Analogy |  | 1 | 0% | 0% | Off Ice | C3 | 20% | 626.0774 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 3000 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 3130.3868 | 0 | 0 | 3130.3868 | 626.0774 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3130.3868
1.4.4.1.2.3 | 1.4 | 1.4.4 | UW | WIPAC | Installation and testing at NTS/SPTS | Installation and testing at NTS/SPTS | Kelley | Labor Hours | Labor - Task | SS | D - Expert Opinion | 63.95 | 66 | 35% | 53% | Off Ice | C3 | 20% | 1653.9552 | 572.9387 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 60 |  |  |  |  | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3837 | 0 | 0 | 0 | 0 | 4003.7647 | 1401.3176 | 2864.6936 | 8269.7759 | 1081.0165 | 572.9387 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8269.7759
1.4.4.1.2.3 | 1.4 | 1.4.4 | UW | WIPAC | Installation and testing at NTS/SPTS | Installation and testing at NTS/SPTS | Domestic | Travel | Travel |  | E - Extrapolation from Actuals |  | 1 | 0% | 53% | Off Ice | C1 | 9% | 258.6326 | 89.5917 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 1800 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 1878.2321 | 0 | 995.463 | 2873.695 | 169.0409 | 89.5917 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2873.695
1.4.4.1.2.4 | 1.4 | 1.4.4 | UW | WIPAC | Production of ICL system | Production of ICL system | Kelley | Labor Hours | Labor - Task | SS | D - Expert Opinion | 63.95 | 66 | 35% | 53% | Off Ice | C3 | 20% | 2205.2736 | 763.9183 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 20 | 40 | 20 |  |  | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1279 | 2558 | 1279 | 0 | 0 | 5338.3529 | 1868.4235 | 3819.5915 | 11026.3679 | 1441.3553 | 763.9183 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11026.3679
1.4.4.1.2.4 | 1.4 | 1.4.4 | UW | WIPAC | Production of ICL system | Timing monitoring system for ICL |  | CapEx | CapEx |  | A - Analogy |  | 1 | 0% | 0% | Off Ice | C3 | 20% | 1252.1547 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 6000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 0 | 0 | 6260.7735 | 0 | 0 | 6260.7735 | 1252.1547 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6260.7735
1.4.4.1.2.6 | 1.4 | 1.4.4 | UW | WIPAC | Shipping to PTH (RDD 9/15/24 for FY25 ComSur, ROS 12/1/24) | Shipping to PTH | Kelley | Labor Hours | Labor - Task | SS | D - Expert Opinion | 63.95 | 66 | 35% | 53% | Off Ice | C3 | 20% | 661.5821 | 229.1755 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 24 |  |  | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1534.8 | 0 | 0 | 1601.5059 | 560.5271 | 1145.8774 | 3307.9104 | 432.4066 | 229.1755 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3307.9104
1.4.4.1.2.6 | 1.4 | 1.4.4 | UW | WIPAC | Shipping to PTH (RDD 9/15/24 for FY25 ComSur, ROS 12/1/24) | Shipping costs |  | M & S | M & S |  | A - Analogy |  | 1 | 0% | 53% | Off Ice | C4 | 35% | 167.6322 | 58.0687 | assumes joint shipment with 1.4.4.1.1 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 300 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 313.0387 | 0 | 165.9105 | 478.9492 | 109.5635 | 58.0687 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 478.9492
1.4.4.1.3 | 1.4 | 1.4.4 | UW | WIPAC | Timing systems support | Timing systems miscellaneous supplies |  | M & S | M & S |  | F - Parametric |  | 1 | 0% | 53% | Off Ice | C1 | 9% | 160.5194 | 55.6048 |  |  | 125 |  |  | 125 |  |  | 125 |  |  | 125 |  | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 510.75 | 0 | 270.6975 | 781.4475 | 45.9675 | 24.3628 |  | 125 |  |  | 125 |  |  | 125 |  |  | 125 |  | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 521.7311 | 0 | 276.5175 | 798.2486 | 46.9558 | 24.8866 |  | 125 | [10 empty] | 0 | 0 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 133.2371 | 0 | 70.6157 | 203.8527 | 11.9913 | 6.3554 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1783.5489
1.4.4.2.1.5 | 1.4 | 1.4.4 | UW | WIPAC | Procurement | Procurement | Kelley | Labor Hours | Labor - LoE | SS | A - Analogy | 63.95 | 66 | 35% | 53% | Off Ice | C1 | 9% | 680.0403 | 235.5695 |  |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 |  |  |  |  | 56 | 0 | 511.6 | 511.6 | 511.6 | 511.6 | 511.6 | 511.6 | 511.6 | 0 | 0 | 0 | 0 | 3658.1958 | 1280.3685 | 2617.4391 | 7556.0034 | 444.4708 | 235.5695 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7556.0034
1.4.4.2.1.5 | 1.4 | 1.4.4 | UW | WIPAC | Procurement | DC power supply chassis for ICL (3) |  | CapEx | CapEx |  | C - Engineering Buildup |  | 1 | 0% | 0% | Off Ice | C2 | 12.5% | 254.7366 | 0 | [8 empty] | 1995 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1995 | 0 | 0 | 0 | 0 | 2037.8925 | 0 | 0 | 2037.8925 | 254.7366 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2037.8925
1.4.4.2.1.5 | 1.4 | 1.4.4 | UW | WIPAC | Procurement | 48V DC power supply modules for ICL (15) |  | CapEx | CapEx |  | C - Engineering Buildup |  | 1 | 0% | 0% | Off Ice | C2 | 12.5% | 923.1806 | 0 | [8 empty] | 7230 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7230 | 0 | 0 | 0 | 0 | 7385.445 | 0 | 0 | 7385.445 | 923.1806 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7385.445
1.4.4.2.2.1 | 1.4 | 1.4.4 | UW | WIPAC | Final design | Final design | Kelley | Labor Hours | Labor - Task | SS | D - Expert Opinion | 63.95 | 66 | 35% | 53% | Off Ice | C4 | 35% | 755.6003 | 261.7439 |  | 16 | [11 empty] | 16 | 1023.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1045.1988 | 365.8196 | 747.8397 | 2158.8581 | 493.8564 | 261.7439 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2158.8581
1.4.4.2.2.4 | 1.4 | 1.4.4 | UW | WIPAC | Production | Production | Kelley | Labor Hours | Labor - LoE | SS | A - Analogy | 63.95 | 66 | 35% | 53% | Off Ice | C1 | 9% | 728.6146 | 252.3959 |  |  | 10 | 10 | 10 | 10 | 10 | 10 | [5 empty] | 60 | 0 | 639.5 | 639.5 | 639.5 | 639.5 | 639.5 | 639.5 | 0 | 0 | 0 | 0 | 0 | 3919.4955 | 1371.8234 | 2804.399 | 8095.718 | 476.2187 | 252.3959 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8095.718
1.4.4.2.2.4 | 1.4 | 1.4.4 | UW | WIPAC | Production | Custom power fanout unit for NTS |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 0% | Off Ice | C3 | 20% | 260.4825 | 0 | [5 empty] | 1275 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 1275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1302.4125 | 0 | 0 | 1302.4125 | 260.4825 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1302.4125
1.4.4.2.2.4 | 1.4 | 1.4.4 | UW | WIPAC | Production | Power fanout cables for NTS (5) |  | CapEx | CapEx |  | C - Engineering Buildup |  | 1 | 0% | 0% | Off Ice | C2 | 12.5% | 102.15 | 0 | [5 empty] | 800 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 817.2 | 0 | 0 | 817.2 | 102.15 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 817.2
1.4.4.2.2.4 | 1.4 | 1.4.4 | UW | WIPAC | Production | Custom power fanout units for ICL (2) |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 0% | Off Ice | C3 | 20% | 520.965 | 0 | [7 empty] | 2550 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2550 | 0 | 0 | 0 | 0 | 0 | 2604.825 | 0 | 0 | 2604.825 | 520.965 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2604.825
1.4.4.2.2.4 | 1.4 | 1.4.4 | UW | WIPAC | Production | Power fanout cables for ICL (10) |  | CapEx | CapEx |  | C - Engineering Buildup |  | 1 | 0% | 0% | Off Ice | C2 | 12.5% | 204.3 | 0 | [7 empty] | 1600 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1600 | 0 | 0 | 0 | 0 | 0 | 1634.4 | 0 | 0 | 1634.4 | 204.3 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1634.4
1.4.4.2.3.4 | 1.4 | 1.4.4 | UW | WIPAC | Production | Production | Kelley | Labor Hours | Labor - LoE | SS | A - Analogy | 63.95 | 66 | 35% | 53% | Off Ice | C1 | 9% | 1457.2292 | 504.7918 |  |  | 24 | 24 | 24 | 24 | 24 | [6 empty] | 120 | 0 | 1534.8 | 1534.8 | 1534.8 | 1534.8 | 1534.8 | 0 | 0 | 0 | 0 | 0 | 0 | 7838.991 | 2743.6469 | 5608.7981 | 16191.4359 | 952.4374 | 504.7918 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16191.4359
1.4.4.2.3.4 | 1.4 | 1.4.4 | UW | WIPAC | Production | Power control unit for NTS |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 0% | Off Ice | C3 | 20% | 153.225 | 0 |  |  |  |  | 750 | [8 empty] | 0 | 0 | 0 | 0 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 766.125 | 0 | 0 | 766.125 | 153.225 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 766.125
1.4.4.2.3.4 | 1.4 | 1.4.4 | UW | WIPAC | Production | Power control units for ICL (2) |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 0% | Off Ice | C3 | 20% | 306.45 | 0 | [6 empty] | 1500 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 1532.25 | 0 | 0 | 1532.25 | 306.45 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1532.25
1.4.4.2.4.1 | 1.4 | 1.4.4 | UW | WIPAC | Power system installation and testing at NTS | Installation and testing at NTS | Kelley | Labor Hours | Labor - Task | SS | D - Expert Opinion | 63.95 | 66 | 35% | 53% | Off Ice | C3 | 20% | 1079.4291 | 373.9199 |  | 40 | [11 empty] | 40 | 2558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2612.997 | 914.5489 | 1869.5994 | 5397.1453 | 705.5092 | 373.9199 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5397.1453
1.4.4.2.4.1 | 1.4 | 1.4.4 | UW | WIPAC | Power system installation and testing at NTS | Installation and testing at NTS | Domestic | Travel | Travel |  | E - Extrapolation from Actuals |  | 1 | 0% | 53% | Off Ice | C1 | 9% | 253.189 | 87.706 |  | 1800 | [11 empty] | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1838.7 | 0 | 974.511 | 2813.211 | 165.483 | 87.706 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2813.211
1.4.4.2.4.2 | 1.4 | 1.4.4 | UW | WIPAC | Power system final design review | Power system final design review | Kelley | Labor Hours | Labor - Task | SS | A - Analogy | 63.95 | 66 | 35% | 53% | Off Ice | C3 | 20% | 2590.6297 | 897.4077 |  | 40 | 56 | [10 empty] | 96 | 2558 | 3581.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6271.1928 | 2194.9175 | 4487.0384 | 12953.1487 | 1693.2221 | 897.4077 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12953.1487
1.4.4.2.4.3 | 1.4 | 1.4.4 | UW | WIPAC | Pre-ship review | Pre-ship review | Kelley | Labor Hours | Labor - Task | SS | A - Analogy | 63.95 | 66 | 35% | 53% | Off Ice | C3 | 20% | 1079.4291 | 373.9199 | [8 empty] | 40 |  |  |  |  | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2558 | 0 | 0 | 0 | 0 | 2612.997 | 914.5489 | 1869.5994 | 5397.1453 | 705.5092 | 373.9199 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5397.1453
1.4.4.2.4.4 | 1.4 | 1.4.4 | UW | WIPAC | Shipping to PTH (ComSur RDD 9/15/24, ROS 12/1/24) | Shipping to PTH | Kelley | Labor Hours | Labor - Task | SS | A - Analogy | 63.95 | 66 | 35% | 53% | Off Ice | C2 | 12.5% | 404.7859 | 140.22 | [8 empty] | 8 | 16 |  |  |  | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 511.6 | 1023.2 | 0 | 0 | 0 | 1567.7982 | 548.7294 | 1121.7596 | 3238.2872 | 264.5659 | 140.22 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3238.2872
1.4.4.2.4.4 | 1.4 | 1.4.4 | UW | WIPAC | Shipping to PTH (ComSur RDD 9/15/24, ROS 12/1/24) | Shipping costs |  | M & S | M & S |  | A - Analogy |  | 1 | 0% | 53% | Off Ice | C4 | 35% | 273.5066 | 94.7441 | [9 empty] | 500 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 510.75 | 0 | 270.6975 | 781.4475 | 178.7625 | 94.7441 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 781.4475
1.4.4.2.5 | 1.4 | 1.4.4 | UW | WIPAC | Power systems support | Power systems miscellaneous supplies |  | M & S | M & S |  | F - Parametric |  | 1 | 0% | 53% | Off Ice | C1 | 9% | 253.042 | 87.6551 |  | 125 |  |  | 125 |  |  | 125 |  |  | 125 |  |  | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 510.75 | 0 | 270.6975 | 781.4475 | 45.9675 | 24.3628 | 125 |  |  | 125 |  |  | 125 |  |  | 125 |  |  | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 521.7311 | 0 | 276.5175 | 798.2486 | 46.9558 | 24.8866 | 125 |  |  | 125 |  |  | 125 |  |  | 125 |  |  | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 532.9483 | 0 | 282.4626 | 815.411 | 47.9654 | 25.4216 | 125 |  |  | 125 | [8 empty] | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 272.2034 | 0 | 144.2678 | 416.4712 | 24.4983 | 12.9841 | 2811.5782
1.4.4.3.2 | 1.4 | 1.4.4 | MSU |  | PQ, ECW, Deployment Travel Costs FS2 Electronics SMEs (Headcount 2) | Electronics SME FS2 PQ costs (slot 1) |  | M & S | M & S |  | C - Engineering Buildup |  | 1 | 0% | 55% | On Ice | C2 | 12.5% | 101.0854 | 35.869 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 350 | 350 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 250 | 0 | 0 | 521.7311 | 0 | 286.9521 | 808.6832 | 65.2164 | 35.869 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 808.6832
1.4.4.3.2 | 1.4 | 1.4.4 | MSU |  | PQ, ECW, Deployment Travel Costs FS2 Electronics SMEs (Headcount 2) | Electronics SME FS2 ECW costs (slot 1) |  | M & S | M & S |  | C - Engineering Buildup |  | 1 | 0% | 55% | On Ice | C2 | 12.5% | 52.5644 | 18.6519 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 125 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130 | 130 | 271.3002 | 0 | 149.2151 | 420.5153 | 33.9125 | 18.6519 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 420.5153
1.4.4.3.2 | 1.4 | 1.4.4 | MSU |  | PQ, ECW, Deployment Travel Costs FS2 Electronics SMEs (Headcount 2) | Electronics SME FS2 Deployment travel (slot 1) | Foreign | Travel | Travel |  | E - Extrapolation from Actuals |  | 1 | 0% | 55% | On Ice | C1 | 9% | 267.6467 | 94.9714 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1080 |  |  | 720 | [7 empty] | 0 | 0 | 1080 | 0 | 0 | 720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1918.614 | 0 | 1055.2377 | 2973.8518 | 172.6753 | 94.9714 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2973.8518
1.4.4.3.2 | 1.4 | 1.4.4 | MSU |  | PQ, ECW, Deployment Travel Costs FS2 Electronics SMEs (Headcount 2) | Electronics SME FS2 PQ costs (slot 2) |  | M & S | M & S |  | C - Engineering Buildup |  | 1 | 0% | 55% | On Ice | C2 | 12.5% | 141.5196 | 50.2166 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 350 | 350 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350 | 350 | 0 | 0 | 730.4236 | 0 | 401.733 | 1132.1565 | 91.3029 | 50.2166 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1132.1565
1.4.4.3.2 | 1.4 | 1.4.4 | MSU |  | PQ, ECW, Deployment Travel Costs FS2 Electronics SMEs (Headcount 2) | Electronics SME FS2 ECW costs (slot 2) |  | M & S | M & S |  | C - Engineering Buildup |  | 1 | 0% | 55% | On Ice | C2 | 12.5% | 50.3405 | 17.8628 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 125 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124 | 125 | 259.8221 | 0 | 142.9022 | 402.7243 | 32.4778 | 17.8628 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 402.7243
1.4.4.3.2 | 1.4 | 1.4.4 | MSU |  | PQ, ECW, Deployment Travel Costs FS2 Electronics SMEs (Headcount 2) | Electronics SME FS2 Deployment travel (slot 2) | Foreign | Travel | Travel |  | E - Extrapolation from Actuals |  | 1 | 0% | 55% | On Ice | C1 | 9% | 267.6467 | 94.9714 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1080 |  |  | 720 | [7 empty] | 0 | 0 | 1080 | 0 | 0 | 720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1918.614 | 0 | 1055.2377 | 2973.8518 | 172.6753 | 94.9714 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2973.8518
1.4.4.3.3 | 1.4 | 1.4.4 | MSU |  | Electronics SME support for FS2 activities (slot 1) | Electronics SME support for FS2 activities | Halliday | Labor Hours | Labor - LoE - Consultant | PO | D - Expert Opinion | 30.815 | 31 | 33.84% | 55% | On Ice | C1 | 9% | 919.8747 | 326.4072 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 150 | [8 empty] | 150 | 0 | 0 | 0 | 4622.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4926.841 | 1667.243 | 3626.7462 | 10220.8301 | 593.4676 | 326.4072 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10220.8301
1.4.4.3.8 | 1.4 | 1.4.4 | UW | WIPAC | Electronics SME support for FS3 activities (slot 1) | Electronics SME support for FS3 activities (slot 1) | Kelley | Labor Hours | Labor - LoE | SS | D - Expert Opinion | 63.95 | 66 | 35% | 53% | On Ice | C1 | 9% | 1941.5698 | 672.5699 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 75 | 75 | [9 empty] | 150 | 0 | 4796.25 | 4796.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10444.4432 | 3655.5551 | 7472.9991 | 21572.9974 | 1268.9998 | 672.5699 | 21572.9974
1.4.4.3.5 | 1.4 | 1.4.4 | MSU |  | Off-ice training Electronics SMEs (FS3) | Off-ice safety training FS3 Electronics SMEs | Domestic | Travel | Travel |  | E - Extrapolation from Actuals |  | 1 | 0% | 55% | On Ice | C1 | 9% | 267.6467 | 94.9714 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 1800 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 1918.614 | 0 | 1055.2377 | 2973.8518 | 172.6753 | 94.9714 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2973.8518
1.4.4.3.7 | 1.4 | 1.4.4 | UW | WIPAC | PQ, ECW, Deployment Travel Costs FS3 Electronics SMEs (Headcount 2) | Electronics SME FS3 PQ costs (slot 1) |  | M & S | M & S |  | C - Engineering Buildup |  | 1 | 0% | 53% | On Ice | C2 | 12.5% | 142.6969 | 49.431 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 350 | 350 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350 | 350 | 0 | 0 | 746.1277 | 0 | 395.4477 | 1141.5754 | 93.266 | 49.431 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1141.5754
1.4.4.3.7 | 1.4 | 1.4.4 | UW | WIPAC | PQ, ECW, Deployment Travel Costs FS3 Electronics SMEs (Headcount 2) | Electronics SME FS3 ECW costs (slot 1) |  | M & S | M & S |  | C - Engineering Buildup |  | 1 | 0% | 53% | On Ice | C2 | 12.5% | 50.9632 | 17.6539 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 125 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125 | 125 | 266.4742 | 0 | 141.2313 | 407.7055 | 33.3093 | 17.6539 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 407.7055
1.4.4.3.7 | 1.4 | 1.4.4 | UW | WIPAC | PQ, ECW, Deployment Travel Costs FS3 Electronics SMEs (Headcount 2) | Electronics SME FS3 Deployment travel (slot 1) | Foreign | Travel | Travel |  | E - Extrapolation from Actuals |  | 1 | 0% | 53% | On Ice | C1 | 9% | 269.8733 | 93.4855 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1080 |  |  | 720 | [7 empty] | 0 | 0 | 1080 | 0 | 0 | 720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1959.8642 | 0 | 1038.728 | 2998.5923 | 176.3878 | 93.4855 | 2998.5923
1.4.4.3.7 | 1.4 | 1.4.4 | MSU |  | PQ, ECW, Deployment Travel Costs FS3 Electronics SMEs (Headcount 2) | Electronics SME FS3 PQ costs (slot 2) |  | M & S | M & S |  | C - Engineering Buildup |  | 1 | 0% | 55% | On Ice | C2 | 12.5% | 144.5622 | 51.2963 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 350 | 350 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350 | 350 | 0 | 0 | 746.1277 | 0 | 410.3702 | 1156.4979 | 93.266 | 51.2963 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1156.4979
1.4.4.3.7 | 1.4 | 1.4.4 | MSU |  | PQ, ECW, Deployment Travel Costs FS3 Electronics SMEs (Headcount 2) | Electronics SME FS3 ECW costs (slot 2) |  | M & S | M & S |  | C - Engineering Buildup |  | 1 | 0% | 55% | On Ice | C2 | 12.5% | 51.6294 | 18.3201 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 125 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125 | 125 | 266.4742 | 0 | 146.5608 | 413.035 | 33.3093 | 18.3201 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 413.035
1.4.4.3.7 | 1.4 | 1.4.4 | MSU |  | PQ, ECW, Deployment Travel Costs FS3 Electronics SMEs (Headcount 2) | Electronics SME FS3 Deployment travel (slot 2) | Foreign | Travel | Travel |  | E - Extrapolation from Actuals |  | 1 | 0% | 55% | On Ice | C1 | 9% | 273.4011 | 97.0133 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1080 |  |  | 720 | [7 empty] | 0 | 0 | 1080 | 0 | 0 | 720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1959.8642 | 0 | 1077.9253 | 3037.7896 | 176.3878 | 97.0133 | 3037.7896
1.4.6 | 1.4 | 1.4.6 | MSU |  | CPT Management (PY4 onward) | CPT Management - Ty DeYoung | DeYoung | Labor Hours | Labor - LoE | KE | E - Extrapolation from Actuals | 97 | 97 | 7.652% | 55% | Off Ice | C1 | 9% | 10379.4378 | 3683.0263 | [8 empty] | 37 | 75 | 75 | 38 |  | 225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3589 | 7275 | 7275 | 3686 | 0 | 22361.022 | 1710.9983 | 13239.6112 | 37311.6315 | 2166.4818 | 1191.565 | [7 empty] | 37 | 75 | 75 | 38 |  | 225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3589 | 7275 | 7275 | 3686 | 0 | 23032.0098 | 1762.3403 | 13636.8926 | 38431.2426 | 2231.4915 | 1227.3203 | [7 empty] | 37 | 75 | 75 | 38 |  | 225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3589 | 7275 | 7275 | 3686 | 0 | 23722.9893 | 1815.212 | 14046.0107 | 39584.212 | 2298.4381 | 1264.141 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115327.0861
1.4.6 | 1.4 | 1.4.6 | MSU |  | CPT Management (PY4 onward) | CPT Management miscellaneous Supplies |  | M & S | M & S |  | F - Parametric |  | 1 | 0% | 55% | Off Ice | C1 | 9% | 256.9198 | 91.1651 |  | 125 |  |  | 125 |  |  | 125 |  |  | 125 |  |  | 0 | 126 | 0 | 0 | 126 | 0 | 0 | 126 | 0 | 0 | 126 | 0 | 0 | 514.836 | 0 | 283.1598 | 797.9958 | 46.3352 | 25.4844 | 125 |  |  | 125 |  |  | 125 |  |  | 125 |  |  | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 521.7311 | 0 | 286.9521 | 808.6832 | 46.9558 | 25.8257 | 125 |  |  | 125 |  |  | 125 |  |  | 125 |  |  | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 532.9483 | 0 | 293.1216 | 826.0699 | 47.9654 | 26.3809 | 125 |  |  | 125 | [8 empty] | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 272.2034 | 0 | 149.7119 | 421.9152 | 24.4983 | 13.4741 | 2854.6642
1.4.6 | 1.4 | 1.4.6 | MSU |  | CPT Management (PY4 onward) | Reviews and Project Planning Meetings | Domestic | Travel | Travel |  | E - Extrapolation from Actuals |  | 1 | 0% | 55% | Off Ice | C1 | 9% | 1845.7184 | 654.9323 |  | 1800 | [5 empty] | 1800 | [5 empty] | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 3677.4 | 0 | 2022.57 | 5699.97 | 330.966 | 182.0313 | 1800 | [5 empty] | 1800 | [5 empty] | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 3756.4641 | 0 | 2066.0553 | 5822.5194 | 338.0818 | 185.945 | 1800 | [5 empty] | 1800 | [5 empty] | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 3837.2281 | 0 | 2110.4754 | 5947.7035 | 345.3505 | 189.9428 | 1800 | [11 empty] | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1959.8642 | 0 | 1077.9253 | 3037.7896 | 176.3878 | 97.0133 | 20507.9824
1.5.2.2.2.0 | 1.5 | 1.5.2 | UW | WIPAC | Pencil Beam Engineering | Overall coordination for Pencil Beam | Wendt | Labor Hours | Labor - LoE | SS | D - Expert Opinion | 65 | 66 | 35% | 53% |  | C1 | 9% | 10755.2725 | 3725.6826 |  | 37.5 | 37.5 | 37.5 | 37.5 | 37.5 | 37.5 | 37.5 | 37.5 | 37.5 | 37.5 | 37.5 | 37.5 | 450 | 2437.5 | 2437.5 | 2437.5 | 2437.5 | 2437.5 | 2437.5 | 2437.5 | 2437.5 | 2437.5 | 2437.5 | 2437.5 | 2437.5 | 29878.875 | 10457.6063 | 21378.3351 | 61714.8163 | 3630.2833 | 1924.0502 | 37.5 | 37.5 | 37.5 | 37.5 | 37.5 | 37.5 | 37.5 | 37.5 | 37.5 | 37.5 | 37.5 |  | 412.5 | 2437.5 | 2437.5 | 2437.5 | 2437.5 | 2437.5 | 2437.5 | 2437.5 | 2437.5 | 2437.5 | 2437.5 | 2437.5 | 0 | 27977.8316 | 9792.2411 | 20018.1385 | 57788.2111 | 3399.3065 | 1801.6325 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 119503.0274
1.5.3.1.1 | 1.5 | 1.5.3 | UA |  | Simulation Studies | Simulation Studies | PostDoc | Labor Hours | Labor - Task | PO | D - Expert Opinion | 28 | 35 | 17.38% | 49% | Off Ice | C1 | 9% | 6297.5572 | 2071.0088 | zeroed postdoc, needed later years when we have schedule approved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75 | 75 | 75 | 75 | 75 | 75 | 450 | 0 | 0 | 0 | 0 | 0 | 0 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 13147.6244 | 2285.0571 | 7562.0139 | 22994.6954 | 1388.9413 | 680.5813 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 900 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 26860.5965 | 4668.3717 | 15449.1944 | 46978.1627 | 2837.6071 | 1390.4275 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69972.858
1.5.3.2.4 | 1.5 | 1.5.3 | UA |  | Create Database Structure for Timing Calibration Data | Create Database Structure for Timing Calibration Data | PostDoc | Labor Hours | Labor - Task | PO | D - Expert Opinion | 28 | 35 | 17.38% | 49% | Off Ice | C1 | 9% | 7377.2916 | 2426.0892 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 75 | 75 | 75 | 75 | 75 | 75 | 450 | 0 | 0 | 0 | 0 | 0 | 0 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 13147.6244 | 2285.0571 | 7562.0139 | 22994.6954 | 1388.9413 | 680.5813 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 900 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 26860.5965 | 4668.3717 | 15449.1944 | 46978.1627 | 2837.6071 | 1390.4275 | 75 | 75 | 75 | [9 empty] | 225 | 2100 | 2100 | 2100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6859.5248 | 1192.1854 | 3945.338 | 11997.0483 | 724.6539 | 355.0804 | 81969.9063
1.5.3.2.5 | 1.5 | 1.5.3 | UA |  | Analyze Timing Calibration Data from Deployed Modules | Analyze Timing Calibration Data from Deployed Modules | PostDoc | Labor Hours | Labor - Task | PO | D - Expert Opinion | 28 | 35 | 17.38% | 49% | Off Ice | C1 | 9% | 1079.7343 | 355.0804 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 75 | 75 | 75 | [6 empty] | 225 | 0 | 0 | 0 | 2100 | 2100 | 2100 | 0 | 0 | 0 | 0 | 0 | 0 | 6859.5248 | 1192.1854 | 3945.338 | 11997.0483 | 724.6539 | 355.0804 | 11997.0483
1.5.3.3.2 | 1.5 | 1.5.3 | UA |  | Create Database Structure for Geometry Calibration Data | Create Database Structure for Geometry Calibration Data | PostDoc | Labor Hours | Labor - Task | PO | D - Expert Opinion | 28 | 35 | 17.38% | 49% | Off Ice | C1 | 9% | 7377.2916 | 2426.0892 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 75 | 75 | 75 | 75 | 75 | 75 | 450 | 0 | 0 | 0 | 0 | 0 | 0 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 13147.6244 | 2285.0571 | 7562.0139 | 22994.6954 | 1388.9413 | 680.5813 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 900 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 26860.5965 | 4668.3717 | 15449.1944 | 46978.1627 | 2837.6071 | 1390.4275 | 75 | 75 | 75 | [9 empty] | 225 | 2100 | 2100 | 2100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6859.5248 | 1192.1854 | 3945.338 | 11997.0483 | 724.6539 | 355.0804 | 81969.9063
1.5.3.3.3 | 1.5 | 1.5.3 | UA |  | Analyze Geometry Calibration Data from Deployed Modules | Analyze Geometry Calibration Data from Deployed Modules | PostDoc | Labor Hours | Labor - Task | PO | D - Expert Opinion | 28 | 35 | 17.38% | 49% | Off Ice | C1 | 9% | 1079.7343 | 355.0804 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 75 | 75 | 75 | [6 empty] | 225 | 0 | 0 | 0 | 2100 | 2100 | 2100 | 0 | 0 | 0 | 0 | 0 | 0 | 6859.5248 | 1192.1854 | 3945.338 | 11997.0483 | 724.6539 | 355.0804 | 11997.0483
1.5.3.4.2 | 1.5 | 1.5.3 | UA |  | Software Development | Software Development | PostDoc | Labor Hours | Labor - Task | PO | D - Expert Opinion | 28 | 35 | 17.38% | 49% | Off Ice | C1 | 9% | 8457.0259 | 2781.1696 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 75 | 75 | 75 | 75 | 75 | 75 | 450 | 0 | 0 | 0 | 0 | 0 | 0 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 13147.6244 | 2285.0571 | 7562.0139 | 22994.6954 | 1388.9413 | 680.5813 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 900 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 26860.5965 | 4668.3717 | 15449.1944 | 46978.1627 | 2837.6071 | 1390.4275 | 150 | 150 | 150 | [9 empty] | 450 | 4200 | 4200 | 4200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13719.0497 | 2384.3708 | 7890.6761 | 23994.0966 | 1449.3078 | 710.1608 | 93966.9546
1.5.3.4.3 | 1.5 | 1.5.3 | UA |  | Execution of Array Calibration | Execution | PostDoc | Labor Hours | Labor - Task | PO | D - Expert Opinion | 28 | 35 | 17.38% | 49% | Off Ice | C1 | 9% | 2159.4687 | 710.1608 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 150 | 150 | 150 | [6 empty] | 450 | 0 | 0 | 0 | 4200 | 4200 | 4200 | 0 | 0 | 0 | 0 | 0 | 0 | 13719.0497 | 2384.3708 | 7890.6761 | 23994.0966 | 1449.3078 | 710.1608 | 23994.0966
1.5.3.5.1 | 1.5 | 1.5.3 | UW | WIPAC | Testing of dust logger and IDP winch | Dust logger shipping UCB to UW/PSL |  | M & S | M & S |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C1 | 9% | 143.6848 | 49.7731 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 1000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 1043.4623 | 0 | 553.035 | 1596.4972 | 93.9116 | 49.7731 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1596.4972
1.5.3.5.1 | 1.5 | 1.5.3 | UW | PSL | Testing of dust logger and IDP winch | PSL Engineering support for summer 2024 testing |  | Labor Hours | Labor - Task | TE | D - Expert Opinion | 77 | 77 | 0% | 0% | Off Ice | C1 | 9% | 347.0973 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 48 |  | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3696 | 0 | 3856.6365 | 0 | 0 | 3856.6365 | 347.0973 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3856.6365
1.5.3.5.1 | 1.5 | 1.5.3 | UW | WIPAC | Testing of dust logger and IDP winch | Research Scientist to test dust logger | Tosi | Labor Hours | Labor - Task | SS | D - Expert Opinion | 47.23 | 66 | 35% | 53% | Off Ice | C1 | 9% | 1465.8259 | 507.7697 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 160 |  | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7556.8 | 0 | 7885.2355 | 2759.8324 | 5641.886 | 16286.954 | 958.0561 | 507.7697 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16286.954
1.5.3.5.1 | 1.5 | 1.5.3 | UW | WIPAC | Testing of dust logger and IDP winch | Travel to test dust logger | Domestic | Travel | Travel |  | E - Extrapolation from Actuals |  | 1 | 0% | 53% | Off Ice | C1 | 9% | 258.6326 | 89.5917 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 1800 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 1878.2321 | 0 | 995.463 | 2873.695 | 169.0409 | 89.5917 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2873.695
1.5.3.5.3 | 1.5 | 1.5.3 | UW | WIPAC | Delivery of logger and winch to PTH | Shipping of logger and winch to PTH |  | M & S | M & S |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C1 | 9% | 587.0959 | 203.3731 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 4263.5868 | 0 | 2259.701 | 6523.2877 | 383.7228 | 203.3731 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6523.2877
1.5.4.1 | 1.5 | 1.5.4 | UA |  | Calibration management | Calibration Management | Williams | Labor Hours | Labor - LoE | KE | D - Expert Opinion | 73 | 116 | 32% | 49% | Off Ice | C1 | 9% | 3236.5257 | 1064.3608 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5840 | 0 | 0 | 5965.56 | 1908.9792 | 3858.5242 | 11733.0634 | 708.7085 | 347.2672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5840 | 0 | 0 | 6093.8195 | 1950.0223 | 3941.4825 | 11985.3243 | 723.9458 | 354.7334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5840 | 0 | 0 | 6224.8367 | 1991.9477 | 4026.2244 | 12243.0087 | 739.5106 | 362.3602 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35961.3964
1.5.4.1 | 1.5 | 1.5.4 | UA |  | Calibration management | Miscellaneous supplies for calibration and outreach activities |  | M & S | M & S |  | D - Expert Opinion |  | 1 | 0% | 49% | Off Ice | C1 | 9% | 410.9494 | 135.1444 |  | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 0 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 3064.5 | 0 | 1501.605 | 4566.105 | 275.805 | 135.1445 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4566.105
1.5.4.2 | 1.5 | 1.5.4 | UA |  | Travel | Travel to reviews and working meetings - Domestic | Domestic | Travel | Travel |  | E - Extrapolation from Actuals |  | 1 | 0% | 49% | Off Ice | C1 | 9% | 1774.2713 | 583.4852 | [5 empty] | 1800 |  |  |  |  | 1800 |  |  | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 3677.4 | 0 | 1801.926 | 5479.326 | 330.966 | 162.1733 |  |  |  |  | 1800 |  |  |  |  | 1800 |  |  | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 3756.4641 | 0 | 1840.6674 | 5597.1315 | 338.0818 | 165.6601 |  |  |  |  | 1800 |  |  |  |  | 1800 |  |  | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 3837.2281 | 0 | 1880.2418 | 5717.4698 | 345.3505 | 169.2218 |  |  |  |  | 1800 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1959.8642 | 0 | 960.3335 | 2920.1977 | 176.3878 | 86.43 | 19714.1251
1.5.4.2 | 1.5 | 1.5.4 | UA |  | Travel | Travel to reviews and working meetings - International | Foreign | Travel | Travel |  | E - Extrapolation from Actuals |  | 1 | 0% | 49% | Off Ice | C1 | 9% | 2687.0284 | 883.6536 | [8 empty] | 3200 |  |  | 3200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3200 | 0 | 0 | 3200 | 0 | 6537.6 | 0 | 3203.424 | 9741.024 | 588.384 | 288.3082 | [7 empty] | 3200 |  |  | 3200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3200 | 0 | 0 | 3200 | 0 | 6678.1584 | 0 | 3272.2976 | 9950.456 | 601.0343 | 294.5068 | [7 empty] | 3200 |  |  | 3200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3200 | 0 | 0 | 3200 | 0 | 6821.7388 | 0 | 3342.652 | 10164.3908 | 613.9565 | 300.8387 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29855.8708
1.6.0 | 1.6 | 1.6.0 | UMD |  | L2 Task Management | L2 Task management - Erik Blaufuss | Blaufuss | Labor Hours | Labor - LoE | SS | E - Extrapolation from Actuals | 85.53 | 66 | 29.9% | 54.5% | Off Ice | C1 | 9% | 14989.6427 | 5287.6086 | 20% effort for management - EKB | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 264 | 1881.66 | 1881.66 | 1881.66 | 1881.66 | 1881.66 | 1881.66 | 1881.66 | 1881.66 | 1881.66 | 1881.66 | 1881.66 | 1881.66 | 23065.3883 | 6896.5511 | 16329.257 | 46291.1963 | 2696.5745 | 1469.6331 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 264 | 1881.66 | 1881.66 | 1881.66 | 1881.66 | 1881.66 | 1881.66 | 1881.66 | 1881.66 | 1881.66 | 1881.66 | 1881.66 | 1881.66 | 23561.2941 | 7044.8269 | 16680.336 | 47286.4571 | 2754.5509 | 1501.2302 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 264 | 1881.66 | 1881.66 | 1881.66 | 1881.66 | 1881.66 | 1881.66 | 1881.66 | 1881.66 | 1881.66 | 1881.66 | 1881.66 | 1881.66 | 24067.862 | 7196.2907 | 17038.9632 | 48303.1159 | 2813.7737 | 1533.5067 | 22 | 22 | 22 | 22 | 22 | 22 | [6 empty] | 132 | 1881.66 | 1881.66 | 1881.66 | 1881.66 | 1881.66 | 1881.66 | 0 | 0 | 0 | 0 | 0 | 0 | 12292.6605 | 3675.5055 | 8702.6505 | 24670.8164 | 1437.1349 | 783.2385 | 166551.5857
1.6.0 | 1.6 | 1.6.0 | UMD |  | L2 Task Management | Travel to annual project reviews | Domestic | Travel | Travel |  | E - Extrapolation from Actuals |  | 1 | 0% | 54.5% | Off Ice | C1 | 9% | 1300.4621 | 458.7391 | [7 empty] | 1800 |  |  |  |  | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 1800 | 3677.4 | 0 | 2004.183 | 5681.583 | 330.966 | 180.3765 | [6 empty] | 1800 |  |  |  |  | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 1800 | 3756.4641 | 0 | 2047.2729 | 5803.737 | 338.0818 | 184.2546 | [6 empty] | 1800 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 1918.614 | 0 | 1045.6447 | 2964.2587 | 172.6753 | 94.108 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14449.5787
1.6.0 | 1.6 | 1.6.0 | UMD |  | L2 Task Management | Travel to project planning workshops and meetings | Domestic | Travel | Travel |  | E - Extrapolation from Actuals |  | 1 | 0% | 54.5% | Off Ice | C1 | 9% | 255.6712 | 90.1882 | [7 empty] | 1800 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 1838.7 | 0 | 1002.0915 | 2840.7915 | 165.483 | 90.1882 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2840.7915
1.6.0 | 1.6 | 1.6.0 | UW | WIPAC | L2 Task Management | PQ process - all L3 areas |  | M & S | M & S |  | E - Extrapolation from Actuals |  | 1 | 0% | 53% | On Ice | C1 | 9% | 275.9358 | 95.5856 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 950 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 950 | 0 | 0 | 0 | 0 | 0 | 0 | 991.2891 | 0 | 525.3832 | 1516.6724 | 89.216 | 47.2845 | [5 empty] | 950 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 950 | 0 | 0 | 0 | 0 | 0 | 0 | 1012.6019 | 0 | 536.679 | 1549.2808 | 91.1342 | 48.3011 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3065.9532
1.6.0 | 1.6 | 1.6.0 | UW | WIPAC | L2 Task Management | Deployment to Pole - all L3 areas | Foreign | Travel | Travel |  | E - Extrapolation from Actuals |  | 1 | 0% | 53% | On Ice | C1 | 9% | 522.8257 | 181.1096 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 1878.2321 | 0 | 995.463 | 2873.695 | 169.0409 | 89.5917 | [11 empty] | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 1918.614 | 0 | 1016.8654 | 2935.4795 | 172.6753 | 91.5179 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5809.1745
1.6.0 | 1.6 | 1.6.0 | UMD |  | L2 Task Management | PQ process - all L3 areas |  | M & S | M & S |  | E - Extrapolation from Actuals |  | 1 | 0% | 54.5% | On Ice | C1 | 9% | 140.8023 | 49.6681 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 950 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 950 | 0 | 0 | 0 | 0 | 0 | 0 | 1012.6019 | 0 | 551.868 | 1564.4699 | 91.1342 | 49.6681 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1564.4699
1.6.0 | 1.6 | 1.6.0 | UMD |  | L2 Task Management | Deployment to Pole - all L3 areas | Foreign | Travel | Travel |  | E - Extrapolation from Actuals |  | 1 | 0% | 54.5% | On Ice | C1 | 9% | 266.7833 | 94.108 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 1918.614 | 0 | 1045.6447 | 2964.2587 | 172.6753 | 94.108 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2964.2587
1.6.1.0 | 1.6 | 1.6.1 | UW | WIPAC | L3 Task Management | L3 Task Management - Jim Braun | Braun | Labor Hours | Labor Hours | SC | E - Extrapolation from Actuals | 54 | 52 | 35% | 53% | Off Ice | C1 | 9% | 3541.7788 | 1226.8907 |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 96 | 432 | 432 | 432 | 432 | 432 | 432 | 432 | 432 | 432 | 432 | 432 | 432 | 5295.456 | 1853.4096 | 3788.8988 | 10937.7644 | 643.3979 | 341.0009 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 96 | 432 | 432 | 432 | 432 | 432 | 432 | 432 | 432 | 432 | 432 | 432 | 432 | 5409.3083 | 1893.2579 | 3870.3601 | 11172.9263 | 657.231 | 348.3324 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 96 | 432 | 432 | 432 | 432 | 432 | 432 | 432 | 432 | 432 | 432 | 432 | 432 | 5525.6084 | 1933.963 | 3953.5728 | 11413.1442 | 671.3614 | 355.8216 | 8 | 8 | 8 | 8 | 8 | 8 | [6 empty] | 48 | 432 | 432 | 432 | 432 | 432 | 432 | 0 | 0 | 0 | 0 | 0 | 0 | 2822.2045 | 987.7716 | 2019.2873 | 5829.2634 | 342.8978 | 181.7359 | 39353.0983
1.6.1.0 | 1.6 | 1.6.1 | UW | WIPAC | L3 Task Management | Travel to project planning workshops and meetings | Domestic | Travel | Travel |  | E - Extrapolation from Actuals |  | 1 | 0% | 53% | Off Ice | C1 | 9% | 776.0147 | 268.8155 | [7 empty] | 1800 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 1838.7 | 0 | 974.511 | 2813.211 | 165.483 | 87.706 | [6 empty] | 1800 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 1878.2321 | 0 | 995.463 | 2873.695 | 169.0409 | 89.5917 | [6 empty] | 1800 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 1918.614 | 0 | 1016.8654 | 2935.4795 | 172.6753 | 91.5179 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8622.3855
1.6.1.0 | 1.6 | 1.6.1 | UW | WIPAC | L3 Task Management | Travel to NTS for new OM integration work | Domestic | Travel | Travel |  | E - Extrapolation from Actuals |  | 1 | 0% | 53% | Off Ice | C1 | 9% | 253.189 | 87.706 | [7 empty] | 1800 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 1838.7 | 0 | 974.511 | 2813.211 | 165.483 | 87.706 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2813.211
1.6.1.0 | 1.6 | 1.6.1 | UW | WIPAC | L3 Task Management | Travel to NTS for new calibration device integration work | Domestic | Travel | Travel |  | E - Extrapolation from Actuals |  | 1 | 0% | 53% | Off Ice | C1 | 9% | 522.8257 | 181.1096 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 1800 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 1878.2321 | 0 | 995.463 | 2873.695 | 169.0409 | 89.5917 | [6 empty] | 1800 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 1918.614 | 0 | 1016.8654 | 2935.4795 | 172.6753 | 91.5179 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5809.1745
1.6.1.0 | 1.6 | 1.6.1 | UW | WIPAC | L3 Task Management | Travel to NTS for OM integration work | Domestic | Travel | Travel |  | E - Extrapolation from Actuals |  | 1 | 0% | 53% | Off Ice | C1 | 9% | 522.8257 | 181.1096 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 1800 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 1878.2321 | 0 | 995.463 | 2873.695 | 169.0409 | 89.5917 | [6 empty] | 1800 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 1918.614 | 0 | 1016.8654 | 2935.4795 | 172.6753 | 91.5179 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5809.1745
1.6.1.4.3.8 | 1.6 | 1.6.1 | UW | WIPAC | Support OM testing app thru FAT testing cycles | Support OM testing app thru FAT testing cycles | Weber | Labor Hours | Labor - Task | SE | D - Expert Opinion | 63.08 | 55 | 35% | 53% | Off Ice | C1 | 9% | 6468.3204 | 2240.66 |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 540 | 2838.6 | 2838.6 | 2838.6 | 2838.6 | 2838.6 | 2838.6 | 2838.6 | 2838.6 | 2838.6 | 2838.6 | 2838.6 | 2838.6 | 34795.5588 | 12178.4456 | 24896.2223 | 71870.2267 | 4227.6604 | 2240.66 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71870.2267
1.6.1.4.3.9.1 | 1.6 | 1.6.1 | UW | WIPAC | Extend OM testing app to include support for MMB based special devices | Extend OM testing app to include support for MMB based special devices | Weber | Labor Hours | Labor - Task | SE | D - Expert Opinion | 63.08 | 55 | 35% | 53% | Off Ice | C4 | 35% | 20496.3239 | 7100.0338 |  | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 20 |  |  |  |  | 440 | 3784.8 | 3784.8 | 3784.8 | 3784.8 | 3784.8 | 3784.8 | 3784.8 | 1261.6 | 0 | 0 | 0 | 0 | 28351.9368 | 9923.1779 | 20285.8108 | 58560.9255 | 13396.2901 | 7100.0338 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58560.9255
1.6.1.4.3.9.2 | 1.6 | 1.6.1 | UW | WIPAC | Support OM testing app thru calibration device DVT and FAT testing | Support OM testing app thru calibration device DVT and FAT testing | Weber | Labor Hours | Labor - Task | SE | D - Expert Opinion | 63.08 | 55 | 35% | 53% | Off Ice | C2 | 12.5% | 12305.6967 | 4262.7577 | [8 empty] | 40 | 60 | 60 | 60 | 60 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2523.2 | 3784.8 | 3784.8 | 3784.8 | 3784.8 | 18042.1416 | 6314.7496 | 12909.1523 | 37266.0435 | 3044.6114 | 1613.644 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 30 |  |  |  |  | 450 | 3784.8 | 3784.8 | 3784.8 | 3784.8 | 3784.8 | 3784.8 | 3784.8 | 1892.4 | 0 | 0 | 0 | 0 | 29619.7194 | 10366.9018 | 21192.9093 | 61179.5305 | 4998.3277 | 2649.1137 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98445.574
1.6.1.4.3.10 | 1.6 | 1.6.1 | UW | WIPAC | Prototype and test SPAT testing software at NTS | Prototype and test SPAT testing software at NTS | Weber | Labor Hours | Labor - Task | SE | D - Expert Opinion | 63.08 | 55 | 35% | 53% | Off Ice | C3 | 20% | 6525.8166 | 2260.577 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 60 | 60 | 60 | 60 | [5 empty] | 240 | 0 | 0 | 0 | 3784.8 | 3784.8 | 3784.8 | 3784.8 | 0 | 0 | 0 | 0 | 0 | 15797.1837 | 5529.0143 | 11302.8849 | 32629.0829 | 4265.2396 | 2260.577 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32629.0829
1.6.1.4.3.11 | 1.6 | 1.6.1 | UW | WIPAC | Prepare and ship SPAT toolset to Pole | Prepare and ship SPAT toolset to Pole | Weber | Labor Hours | Labor - Task | SE | D - Expert Opinion | 63.08 | 55 | 35% | 53% | Off Ice | C2 | 12.5% | 2294.2324 | 794.7341 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 45 | 45 | 45 |  |  | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2838.6 | 2838.6 | 2838.6 | 0 | 0 | 8885.9158 | 3110.0705 | 6357.8728 | 18353.8591 | 1499.4983 | 794.7341 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18353.8591
1.6.1.4.3.11 | 1.6 | 1.6.1 | UW | WIPAC | Prepare and ship SPAT toolset to Pole | Prepare and ship SPAT toolset to Pole |  | M & S | M & S |  | D - Expert Opinion |  | 1 | 0% | 53% |  | C2 | 12.5% | 1496.7162 | 518.4703 | tools and computers for SPAT | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 7500 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | 0 | 0 | 0 | 7825.9669 | 0 | 4147.7624 | 11973.7293 | 978.2459 | 518.4703 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11973.7293
1.6.1.4.3.13 | 1.6 | 1.6.1 | UW | WIPAC | SPAT testing preparation and execution at Pole FS2 | SPAT testing preparation and execution at Pole FS2 | Weber | Labor Hours | Labor - Task | SE | D - Expert Opinion | 63.08 | 55 | 35% | 53% | On Ice | C2 | 12.5% | 7811.8613 | 2706.0696 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 150 | 150 | 150 | [7 empty] | 450 | 0 | 0 | 9462 | 9462 | 9462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30256.5434 | 10589.7902 | 21648.5568 | 62494.8904 | 5105.7917 | 2706.0696 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62494.8904
1.6.1.4.3.15 | 1.6 | 1.6.1 | UW | WIPAC | SPAT testing preparation and execution at Pole FS3 | SPAT testing preparation and execution at Pole FS3 | Weber | Labor Hours | Labor - Task | SE | D - Expert Opinion | 63.08 | 55 | 35% | 53% | On Ice | C2 | 12.5% | 7979.8163 | 2764.2501 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 150 | 150 | 150 | [8 empty] | 450 | 0 | 9462 | 9462 | 9462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30907.0591 | 10817.4707 | 22114.0008 | 63838.5305 | 5215.5662 | 2764.2501 | 63838.5305
1.6.1.4.5.4.3 | 1.6 | 1.6.1 | UW | WIPAC | Extend xDOMapp to include support for calibration devices in operations | Extend xDOMapp to include support for calibration devices in operations | Weber | Labor Hours | Labor - Task | SE | D - Expert Opinion | 63.08 | 55 | 35% | 53% | Off Ice | C4 | 35% | 20133.0964 | 6974.2099 | [11 empty] | 45 | 45 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2838.6 | 2838.6 | 5799.2598 | 2029.7409 | 4149.3704 | 11978.3711 | 2740.1503 | 1452.2796 | 45 | 45 | 45 | 30 | 30 | 30 | 30 | 30 | 30 | 20 |  |  | 335 | 2838.6 | 2838.6 | 2838.6 | 1892.4 | 1892.4 | 1892.4 | 1892.4 | 1892.4 | 1892.4 | 1261.6 | 0 | 0 | 22050.2356 | 7717.5825 | 15776.9436 | 45544.7616 | 10418.7363 | 5521.9302 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57523.1327
1.6.1.4.5.6 | 1.6 | 1.6.1 | UW | WIPAC | Support full DAQ testing with xDOMapp at NTS/SPTS with Calibration devices | Support full DAQ testing with xDOMapp at NTS/SPTS with Calibration devices | Weber | Labor Hours | Labor - Task | SE | D - Expert Opinion | 63.08 | 55 | 35% | 53% | Off Ice | C2 | 12.5% | 3062.2062 | 1060.7642 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 20 | 45 | 45 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1261.6 | 2838.6 | 2838.6 | 7396.0439 | 2588.6154 | 5291.8694 | 15276.5288 | 1248.0824 | 661.4837 | 45 |  |  |  | 20 | [7 empty] | 65 | 2838.6 | 0 | 0 | 0 | 1261.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4464.353 | 1562.5235 | 3194.2446 | 9221.1211 | 753.3596 | 399.2806 | 24497.6498
1.6.1.4.5.8 | 1.6 | 1.6.1 | UW | WIPAC | Support xDOMapp through SPAT testing and deployment | Support xDOMapp through SPAT testing and deployment | Weber | Labor Hours | Labor - Task | SE | D - Expert Opinion | 63.08 | 55 | 35% | 53% | Off Ice | C2 | 12.5% | 6271.883 | 2172.6131 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 300 | 0 | 0 | 1892.4 | 1892.4 | 1892.4 | 1892.4 | 1892.4 | 1892.4 | 1892.4 | 1892.4 | 1892.4 | 1892.4 | 20171.0289 | 7059.8601 | 14432.3712 | 41663.2603 | 3403.8611 | 1804.0464 | 30 |  |  |  | 30 | [7 empty] | 60 | 1892.4 | 0 | 0 | 0 | 1892.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4120.9412 | 1442.3294 | 2948.5334 | 8511.8041 | 695.4088 | 368.5667 | 50175.0643
1.6.1.4.6.5 | 1.6 | 1.6.1 | UW | WIPAC | Support MMB software for calibration device interface development | Support MMB-xDOMapp software for calibration devices | Weber | Labor Hours | Labor - Task | SE | D - Expert Opinion | 63.08 | 55 | 35% | 53% | Off Ice | C2 | 12.5% | 13733.8946 | 4757.4929 | [7 empty] | 45 | 45 | 45 | 45 |  |  | 180 | 0 | 0 | 0 | 0 | 0 | 0 | 2838.6 | 2838.6 | 2838.6 | 2838.6 | 0 | 0 | 11598.5196 | 4059.4819 | 8298.7408 | 23956.7422 | 1957.2502 | 1037.3426 | 45 | 45 | 45 |  |  |  |  | 45 | 90 | 90 | 90 | 90 | 540 | 2838.6 | 2838.6 | 2838.6 | 0 | 0 | 0 | 0 | 2838.6 | 5677.2 | 5677.2 | 5677.2 | 5677.2 | 35543.6633 | 12440.2822 | 25431.4911 | 73415.4366 | 5997.9932 | 3178.9364 | 45 | 45 | [10 empty] | 90 | 2838.6 | 2838.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6051.3087 | 2117.958 | 4329.7114 | 12498.9781 | 1021.1583 | 541.2139 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109871.1569
1.6.1.6.6 | 1.6 | 1.6.1 | PSU |  | Firmware device maintenance and support for all OM devices during DAQ Development | Firmware device maintenance and support for all OM devices during DAQ Development | Anderson | Labor Hours | Labor - Task | SE | D - Expert Opinion | 50.5024 | 64 | 36% | 59.86% | Off Ice | C3 | 20% | 3903.0879 | 1461.5216 |  | 14 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 |  |  |  | 174 | 707.0336 | 1010.048 | 1010.048 | 1010.048 | 1010.048 | 1010.048 | 1010.048 | 1010.048 | 1010.048 | 0 | 0 | 0 | 8976.3466 | 3231.4848 | 7307.6079 | 19515.4393 | 2441.5663 | 1461.5216 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19515.4393
1.6.1.6.6 | 1.6 | 1.6.1 | PSU |  | Firmware device maintenance and support for all OM devices during DAQ Development | Firmware device maintenance and support for all OM devices during DAQ Development | Anderson | Labor Hours | Labor - Task | SE | D - Expert Opinion | 50.5 | 64 | 36% | 61% | Off Ice | C3 | 20% | 8665.0833 | 3283.044 | [10 empty] | 20 | 20 | 20 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1010 | 1010 | 1010 | 3095.145 | 1114.2522 | 2567.7323 | 6777.1295 | 841.8794 | 513.5465 | 10 | 12 | 11.25 | 11.202 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 124.452 | 505 | 606 | 568.125 | 565.701 | 505 | 505 | 505 | 505 | 505 | 505 | 505 | 505 | 6557.9787 | 2360.8723 | 5440.4991 | 14359.3501 | 1783.7702 | 1088.0998 | 10 | 12 | 11.45 | 11 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 124.45 | 505 | 606 | 578.225 | 555.5 | 505 | 505 | 505 | 505 | 505 | 505 | 505 | 505 | 6698.8676 | 2411.5923 | 5557.3805 | 14667.8404 | 1822.092 | 1111.4761 | 10 | 11 | 10.73 | 10.74 | 10 | 10 | [6 empty] | 62.47 | 505 | 555.5 | 541.865 | 542.37 | 505 | 505 | 0 | 0 | 0 | 0 | 0 | 0 | 3434.918 | 1236.5705 | 2849.6079 | 7521.0964 | 934.2977 | 569.9216 | 43325.4164
1.6.4.0 | 1.6 | 1.6.4 | UW | WIPAC | L3 Task Management | L3 Task management - Ralf Auer | Auer | Labor Hours | Labor - LoE | EN | E - Extrapolation from Actuals | 60 | 49 | 35% | 53% | Off Ice | C1 | 9% | 1438.9122 | 498.4467 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 72 | 0 | 0 | 0 | 480 | 480 | 480 | 480 | 480 | 480 | 480 | 480 | 480 | 4604.6737 | 1611.6358 | 3294.644 | 9510.9535 | 559.4679 | 296.518 | 8 | 8 | 8 | 8 | 8 | 8 | [6 empty] | 48 | 480 | 480 | 480 | 480 | 480 | 480 | 0 | 0 | 0 | 0 | 0 | 0 | 3135.7828 | 1097.524 | 2243.6526 | 6476.9593 | 380.9976 | 201.9287 | 15987.9129
1.6.4.0 | 1.6 | 1.6.4 | UW | WIPAC | L3 Task Management | Miscellaneous supplies |  | M & S | M & S |  | E - Extrapolation from Actuals |  | 1 | 0% | 53% | Off Ice | C1 | 9% | 142.1727 | 49.2493 | [7 empty] | 500 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 510.75 | 0 | 270.6975 | 781.4475 | 45.9675 | 24.3628 | [6 empty] | 500 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 521.7311 | 0 | 276.5175 | 798.2486 | 46.9558 | 24.8866 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1579.6961
1.6.4.0 | 1.6 | 1.6.4 | UW | WIPAC | L3 Task Management | Trip to MSU to install NTS equipment | Domestic | Travel | Travel |  | E - Extrapolation from Actuals |  | 1 | 0% | 53% | Off Ice | C1 | 9% | 264.1932 | 91.5179 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 1800 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 1918.614 | 0 | 1016.8654 | 2935.4795 | 172.6753 | 91.5179 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2935.4795
1.6.4.0 | 1.6 | 1.6.4 | UW | WIPAC | L3 Task Management | NTS computing system purchase |  | CapEx | CapEx |  | E - Extrapolation from Actuals |  | 1 | 0% | 0% | Off Ice | C3 | 20% | 532.9483 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 2500 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 2664.7417 | 0 | 0 | 2664.7417 | 532.9483 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2664.7417
1.6.4.0 | 1.6 | 1.6.4 | UW | WIPAC | L3 Task Management | Miscellaneous supplies |  | M & S | M & S |  | E - Extrapolation from Actuals |  | 1 | 0% | 53% | Off Ice | C1 | 9% | 73.387 | 25.4216 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 500 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 532.9483 | 0 | 282.4626 | 815.411 | 47.9654 | 25.4216 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 815.411
1.6.4.0 | 1.6 | 1.6.4 | UW | WIPAC | L3 Task Management | SPS computing system additions |  | CapEx | CapEx |  | E - Extrapolation from Actuals |  | 1 | 0% | 0% | Off Ice | C3 | 20% | 2558.1521 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 12000 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 | 0 | 0 | 0 | 12790.7603 | 0 | 0 | 12790.7603 | 2558.1521 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12790.7603
1.6.5.0 | 1.6 | 1.6.5 | UMD |  | L3 Task Management | L3 Task Management | TBD | Labor Hours | Labor - Task | SC | E - Extrapolation from Actuals | 52.12 | 52 | 35.6% | 54.5% | Off Ice | C1 | 9% | 1109.3241 | 391.315 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.25 | 5.25 | 5.25 | 5.25 | 5.25 | 5.25 | 5.25 | 5.25 | 5.25 | 5.25 | 5.25 | 5.25 | 63 | 273.63 | 273.63 | 273.63 | 273.63 | 273.63 | 273.63 | 273.63 | 273.63 | 273.63 | 273.63 | 273.63 | 273.63 | 3499.9357 | 1245.9771 | 2586.5225 | 7332.4354 | 427.1322 | 232.787 | 7 | 7 | 7 | 7 | 7 | 7 | [6 empty] | 42 | 364.84 | 364.84 | 364.84 | 364.84 | 364.84 | 364.84 | 0 | 0 | 0 | 0 | 0 | 0 | 2383.4562 | 848.5104 | 1761.4218 | 4993.3885 | 290.877 | 158.528 | 12325.8238
[50 empty] | 5245761.6564 | [95 empty] | 16601510.8563
Formulas:
PY5 = DATE(2017+INT(RIGHT([PY5, row above],1)),10,1)
PY6 = DATE(2017+INT(RIGHT([PY6, row above],1)),10,1)
PY7 = DATE(2017+INT(RIGHT([PY7, row above],1)),10,1)
PY8 = DATE(2017+INT(RIGHT([PY8, row above],1)),10,1)

## PY5 1030 - UW
Project Year | PY5 |  |  | 1.1.1 | 1.1.2 | 1.1.3 | 1.1.4 | 1.1.5 | 1.2.1 | 1.2.2 | 1.2.3 | 1.2.4 | 1.2.5 | 1.2.6 | 1.2.7 | 1.2.8 | 1.2.9 | 1.2.10 | 1.3.1 | 1.3.2 | 1.3.3 | 1.3.4 | 1.3.5 | 1.4.1 | 1.4.2 | 1.4.3 | 1.4.4 | 1.4.5 | 1.4.6 | 1.5.1 | 1.5.2 | 1.5.3 | 1.5.4 | 1.6.0 | 1.6.1 | 1.6.2 | 1.6.3 | 1.6.4 | 1.6.5
Institution | UW |  |  | 1.1.1: 1.1 Project Office; 1.2.1: 1.2 Drilling and Installation; 1.3.1: 1.3 Deep Ice Sensor Modules; 1.4.1: 1.4 Comm/Power/Timing; 1.5.1: 1.5 Characterization and Calibration System; 1.6.0: 1.6 IceCube Data Systems Integration
|  |  |  | 1.1.1 Project Management | 1.1.2 Project Controls | 1.1.3 Quality and Safety | 1.1.4 Polar Operations | 1.1.5 Project Engineering | 1.2.1 Implementation Management & Systems Engineering | 1.2.2 Thermal Plant - Off-ice | 1.2.3 Tower Operations Site (TOS) - Off-ice | 1.2.4 Computing and Control System - Off-ice | 1.2.5 Power Generation & Distribution | 1.2.6 Water Handling Systems - Off-ice | 1.2.7 Support Equipment - Off-ice | 1.2.8 Drill Field Seasons - Antarctica | 1.2.9 Installation - Off-ice | 1.2.10 Installation Field Seasons - Antarctica | 1.3.1 mDOM | 1.3.2 D-Egg | 1.3.3 PDOM | 1.3.4 Ice Comms Module | 1.3.5 Special Devices | 1.4.1 Downhole Cables | 1.4.2 Surface Cables | 1.4.3 FieldHub | 1.4.4 CPT Central Infrastructure | 1.4.5 Northern Test System | 1.4.6 CPT Management (PY4 onward) | 1.5.1 Module Calibration | 1.5.2 Calibration Assemblies | 1.5.3 Array Calibration | 1.5.4 Calibration Management and Organization | 1.6.0 L2 Task Management | 1.6.1 Online Systems Software | 1.6.2 Offline Systems | 1.6.3 Simulation Software | 1.6.4 Computing Infrastructure | 1.6.5 Upgrade String Commissioning
Expense Description |  |  | Total Yr 5
Senior Personnel
Title | Last Name | Cal. Mo.
Principal Investigator | Karle | 0.6 | 12907.674 | 12907.674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project Manager | Feyzi | 12 | 178868.736 | 178868.736 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project Director | ODell | 4.8 | 82520.856 | 82520.856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other Personnel |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Financial Manager | Mercier | 4.8 | 32684.7312 | 0 | 32684.7312 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project Controls Analyst | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Quality and Safety | Zernick | 9.04 | 84064.9963 | 0 | 0 | 84064.9963 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Technical Coordinator | DuVernois | 6 | 67360.7745 | 0 | 0 | 0 | 0 | 67360.7745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project Engineer | Sandstrom | 6 | 58967.109 | 0 | 0 | 0 | 0 | 58967.109 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Logistics Manager | Tosi | 7.2 | 52105.0806 | 0 | 0 | 0 | 17368.3602 | 0 | 34736.7204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Implementation Manager | McEwen | 12 | 111590.703 | 0 | 0 | 0 | 0 | 0 | 111590.703 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Scientist | Wendt | 3.8667 | 38477.3513 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8598.4763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29878.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Engineer / Technician | Weber | 10.2 | 98587.4166 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98587.4166 | 0 | 0 | 0 | 0
Engineer | Kelley | 4.5333 | 44420.949 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10713.2877 | 0 | 33707.6613 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Engineer | Braun | 0.64 | 5295.456 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5295.456 | 0 | 0 | 0 | 0
Engineer | Auer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Senior Scientist | Senior Scientist | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Scientist | Scientist | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Engineer | S. Griffin | 3.64 | 26213.733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26213.733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Salaries and Wages
|  |  | 894065.5664 | 274297.266 | 32684.7312 | 84064.9963 | 17368.3602 | 126327.8835 | 146327.4234 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8598.4763 | 26213.733 | 0 | 0 | 10713.2877 | 0 | 33707.6613 | 0 | 0 | 0 | 29878.875 | 0 | 0 | 0 | 103882.8726 | 0 | 0 | 0 | 0
Fringe Benefits
|  |  | 312922.9482 | 96004.0431 | 11439.6559 | 29422.7487 | 6078.9261 | 44214.7592 | 51214.5982 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3009.4667 | 9174.8065 | 0 | 0 | 3749.6507 | 0 | 11797.6815 | 0 | 0 | 0 | 10457.6063 | 0 | 0 | 0 | 36359.0054 | 0 | 0 | 0 | 0
Equipment
Descrip. | Qty | Unit Cost
Capital Equipment | 1 | 1 | 556542.8235 | 0 | 0 | 0 | 0 | 0 | 0 | 11177.253 | 24571.161 | 198636.804 | 23355.576 | 6741.9 | 25026.75 | 0 | 138210.993 | 0 | 0 | 0 | 93104.6175 | 0 | 0 | 0 | 0 | 0 | 35717.769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Capitalized Labor | 1 | 1 | 1262830.3965 | 0 | 0 | 0 | 0 | 0 | 403933.788 | 6897.168 | 35719.812 | 670748.5665 | 12217.14 | 4698.9 | 40602.582 | 57265.29 | 7048.35 | 0 | 0 | 0 | 23698.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Eqpt
|  |  | 1819373.22 | 0 | 0 | 0 | 0 | 0 | 403933.788 | 18074.421 | 60290.973 | 869385.3705 | 35572.716 | 11440.8 | 65629.332 | 57265.29 | 145259.343 | 0 | 0 | 0 | 116803.4175 | 0 | 0 | 0 | 0 | 0 | 35717.769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Travel
Domestic |  |  | 52709.4 | 28806.3 | 0 | 0 | 0 | 0 | 12870.9 | 0 | 0 | 0 | 0 | 0 | 0 | 1838.7 | 1838.7 | 0 | 0 | 0 | 1838.7 | 0 | 0 | 0 | 0 | 0 | 1838.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3677.4 | 0 | 0 | 0 | 0
Foreign |  |  | 42085.8 | 9806.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32279.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Travel
|  |  | 94795.2 | 38612.7 | 0 | 0 | 0 | 0 | 12870.9 | 0 | 0 | 0 | 0 | 0 | 0 | 34118.1 | 1838.7 | 0 | 0 | 0 | 1838.7 | 0 | 0 | 0 | 0 | 0 | 1838.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3677.4 | 0 | 0 | 0 | 0
Participant Support Costs
Descr | # participants |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Part. Supp.
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other Direct Costs
Materials and Supplies |  |  | 120452.2155 | 15833.25 | 0 | 0 | 0 | 0 | 29564.253 | 0 | 0 | 0 | 0 | 0 | 5107.5 | 22881.6 | 0 | 0 | 0 | 0 | 12768.75 | 0 | 0 | 0 | 31743.1125 | 0 | 2043 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 510.75 | 0
Computers/Office |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Software/licenses |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other categories |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
And other cats… |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Materials and Supplies
|  |  | 120452.2155 | 15833.25 | 0 | 0 | 0 | 0 | 29564.253 | 0 | 0 | 0 | 0 | 0 | 5107.5 | 22881.6 | 0 | 0 | 0 | 0 | 12768.75 | 0 | 0 | 0 | 31743.1125 | 0 | 2043 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 510.75 | 0
Publication Costs/Documentation/Dissemination
Consultant Services Description |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Software/Programming |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Database consultant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PMCS Service | PMCS Consulting |  | 334896 | 0 | 334896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Etc. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Consultant/Prof Services
|  |  | 334896 | 0 | 334896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Computer Services |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subotal Computer Services
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subawards
MSU |  |  | 593417.0181 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 511308.9137 | 38298.507 | 0 | 0 | 0 | 43809.5973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PSU |  |  | 42311.617 | 16019.0482 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26292.5688 | 0 | 0 | 0 | 0
UA |  |  | 31519.5184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31519.5184 | 0 | 0 | 0 | 0 | 0 | 0
UMD |  |  | 70728.4298 | 15914.859 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54813.5708 | 0 | 0 | 0 | 0 | 0
Subtotal - Subawards
|  |  | 737976.5832 | 31933.9071 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 511308.9137 | 38298.507 | 0 | 0 | 0 | 43809.5973 | 0 | 0 | 0 | 31519.5184 | 54813.5708 | 26292.5688 | 0 | 0 | 0 | 0
Other - Contingency |  |  | 686374.294 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Leases |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Maint/Repair |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Shipping/Postage |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Other
|  |  | 686374.294 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total - Direct Costs
|  | 4314481.7334 | 5000856.0274 | 456681.1662 | 379020.3871 | 113487.745 | 23447.2863 | 170542.6427 | 643910.9626 | 18074.421 | 60290.973 | 869385.3705 | 35572.716 | 11440.8 | 70736.832 | 114264.99 | 147098.043 | 0 | 0 | 0 | 143018.8104 | 35388.5396 | 0 | 511308.9137 | 84504.5579 | 0 | 85104.8118 | 0 | 43809.5973 | 0 | 40336.4813 | 0 | 31519.5184 | 54813.5708 | 170211.8468 | 0 | 0 | 510.75 | 0
Indirect Costs
Indirect |  | 5245761.6564 | 931279.923 | 225116.0473 | 200880.8052 | 60148.5048 | 12427.0617 | 90387.6006 | 127187.9025 | 0 | 0 | 0 | 0 | 0 | 2706.975 | 30209.841 | 974.511 | 0 | 0 | 0 | 13894.1583 | 18755.926 | 0 | 0 | 24489.207 | 0 | 26175.1327 | 0 | 0 | 0 | 21378.3351 | 0 | 0 | 0 | 76277.2173 | 0 | 0 | 270.6975 | 0
Other - Contingency Indirect |  | 819632.3346 | 133258.0406 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Indirect Costs |  |  | 1064537.9636 | 225116.0473 | 200880.8052 | 60148.5048 | 12427.0617 | 90387.6006 | 127187.9025 | 0 | 0 | 0 | 0 | 0 | 2706.975 | 30209.841 | 974.511 | 0 | 0 | 0 | 13894.1583 | 18755.926 | 0 | 0 | 24489.207 | 0 | 26175.1327 | 0 | 0 | 0 | 21378.3351 | 0 | 0 | 0 | 76277.2173 | 0 | 0 | 270.6975 | 0
0
Total - Direct and Indirect
|  |  | 6065393.991 | 681797.2136 | 579901.1923 | 173636.2498 | 35874.348 | 260930.2434 | 771098.8651 | 18074.421 | 60290.973 | 869385.3705 | 35572.716 | 11440.8 | 73443.807 | 144474.831 | 148072.554 | 0 | 0 | 0 | 156912.9687 | 54144.4655 | 0 | 511308.9137 | 108993.7649 | 0 | 111279.9444 | 0 | 43809.5973 | 0 | 61714.8163 | 0 | 31519.5184 | 54813.5708 | 246489.0642 | 0 | 0 | 781.4475 | 0
Base funds total | 16601510.8563
Contingence funds total | 4755334.4549

## PY6 1030 - UW
Project Year | PY6 |  |  | 1.1.1 | 1.1.2 | 1.1.3 | 1.1.4 | 1.1.5 | 1.2.1 | 1.2.2 | 1.2.3 | 1.2.4 | 1.2.5 | 1.2.6 | 1.2.7 | 1.2.8 | 1.2.9 | 1.2.10 | 1.3.1 | 1.3.2 | 1.3.3 | 1.3.4 | 1.3.5 | 1.4.1 | 1.4.2 | 1.4.3 | 1.4.4 | 1.4.5 | 1.4.6 | 1.5.1 | 1.5.2 | 1.5.3 | 1.5.4 | 1.6.0 | 1.6.1 | 1.6.2 | 1.6.3 | 1.6.4 | 1.6.5
Institution | UW |  |  | 1.1.1: 1.1 Project Office; 1.2.1: 1.2 Drilling and Installation; 1.3.1: 1.3 Deep Ice Sensor Modules; 1.4.1: 1.4 Comm/Power/Timing; 1.5.1: 1.5 Characterization and Calibration System; 1.6.0: 1.6 IceCube Data Systems Integration
|  |  |  | 1.1.1 Project Management | 1.1.2 Project Controls | 1.1.3 Quality and Safety | 1.1.4 Polar Operations | 1.1.5 Project Engineering | 1.2.1 Implementation Management & Systems Engineering | 1.2.2 Thermal Plant - Off-ice | 1.2.3 Tower Operations Site (TOS) - Off-ice | 1.2.4 Computing and Control System - Off-ice | 1.2.5 Power Generation & Distribution | 1.2.6 Water Handling Systems - Off-ice | 1.2.7 Support Equipment - Off-ice | 1.2.8 Drill Field Seasons - Antarctica | 1.2.9 Installation - Off-ice | 1.2.10 Installation Field Seasons - Antarctica | 1.3.1 mDOM | 1.3.2 D-Egg | 1.3.3 PDOM | 1.3.4 Ice Comms Module | 1.3.5 Special Devices | 1.4.1 Downhole Cables | 1.4.2 Surface Cables | 1.4.3 FieldHub | 1.4.4 CPT Central Infrastructure | 1.4.5 Northern Test System | 1.4.6 CPT Management (PY4 onward) | 1.5.1 Module Calibration | 1.5.2 Calibration Assemblies | 1.5.3 Array Calibration | 1.5.4 Calibration Management and Organization | 1.6.0 L2 Task Management | 1.6.1 Online Systems Software | 1.6.2 Offline Systems | 1.6.3 Simulation Software | 1.6.4 Computing Infrastructure | 1.6.5 Upgrade String Commissioning
Expense Description |  |  | Total Yr 5
Senior Personnel
Title | Last Name | Cal. Mo.
Principal Investigator | Karle | 0.6 | 13185.189 | 13185.189 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project Manager | Feyzi | 6.3333 | 96432.6073 | 96432.6073 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project Director | ODell | 4 | 70245.8787 | 70245.8787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other Personnel |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Financial Manager | Mercier | 4.8 | 33387.4529 | 0 | 33387.4529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project Controls Analyst | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Quality and Safety | Zernick | 9.52 | 85557.1324 | 0 | 0 | 67570.6815 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17986.451 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Technical Coordinator | DuVernois | 6 | 68809.0312 | 0 | 0 | 0 | 0 | 68809.0312 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project Engineer | Sandstrom | 6 | 60234.9018 | 0 | 0 | 0 | 0 | 60234.9018 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Logistics Manager | Tosi | 7.0667 | 52239.6854 | 0 | 0 | 0 | 8870.89 | 0 | 35483.5599 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7885.2355 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Implementation Manager | McEwen | 12 | 113989.9031 | 0 | 0 | 0 | 0 | 0 | 113989.9031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Scientist | Wendt | 2.75 | 27977.8316 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27977.8316 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Engineer / Technician | Weber | 11.3333 | 111896.7178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 111896.7178 | 0 | 0 | 0 | 0
Engineer | Kelley | 2.72 | 27225.5996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1601.5059 | 0 | 25624.0938 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Engineer | Braun | 0.64 | 5409.3083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5409.3083 | 0 | 0 | 0 | 0
Engineer | Auer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Senior Scientist | Senior Scientist | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Scientist | Scientist | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Engineer | S. Griffin | 4.08 | 30014.1482 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30014.1482 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Salaries and Wages
|  |  | 796605.3873 | 179863.675 | 33387.4529 | 67570.6815 | 8870.89 | 129043.933 | 149473.463 | 0 | 0 | 0 | 0 | 0 | 0 | 17986.451 | 0 | 0 | 0 | 0 | 0 | 30014.1482 | 0 | 0 | 1601.5059 | 0 | 25624.0938 | 0 | 0 | 0 | 27977.8316 | 7885.2355 | 0 | 0 | 117306.0261 | 0 | 0 | 0 | 0
Fringe Benefits
|  |  | 278811.8856 | 62952.2862 | 11685.6085 | 23649.7385 | 3104.8115 | 45165.3765 | 52315.7121 | 0 | 0 | 0 | 0 | 0 | 0 | 6295.2578 | 0 | 0 | 0 | 0 | 0 | 10504.9519 | 0 | 0 | 560.5271 | 0 | 8968.4328 | 0 | 0 | 0 | 9792.2411 | 2759.8324 | 0 | 0 | 41057.1092 | 0 | 0 | 0 | 0
Equipment
Descrip. | Qty | Unit Cost
Capital Equipment | 1 | 1 | 266989.6424 | 0 | 0 | 0 | 0 | 0 | 0 | 38277.3257 | 21393.063 | 18625.8012 | 5217.3113 | 33303.1412 | 14608.4715 | 0 | 126173.3683 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9391.1603 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Capitalized Labor | 1 | 1 | 1224134.2604 | 0 | 0 | 0 | 0 | 0 | 308987.9545 | 40601.1161 | 21453.5839 | 134260.2008 | 14408.1267 | 14399.7791 | 21307.4991 | 660059.4373 | 4799.9264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3856.6365 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Eqpt
|  |  | 1491123.9028 | 0 | 0 | 0 | 0 | 0 | 308987.9545 | 78878.4419 | 42846.6469 | 152886.0019 | 19625.438 | 47702.9202 | 35915.9706 | 660059.4373 | 130973.2947 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9391.1603 | 0 | 0 | 0 | 0 | 3856.6365 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Travel
Domestic |  |  | 59477.3483 | 29425.6355 | 0 | 0 | 0 | 0 | 13147.6244 | 0 | 0 | 0 | 0 | 0 | 0 | 5634.6962 | 1878.2321 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1878.2321 | 0 | 0 | 0 | 0 | 1878.2321 | 0 | 0 | 5634.6962 | 0 | 0 | 0 | 0
Foreign |  |  | 53842.6521 | 10017.2376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41947.1825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1878.2321 | 0 | 0 | 0 | 0 | 0
Subtotal - Travel
|  |  | 113320.0004 | 39442.8731 | 0 | 0 | 0 | 0 | 13147.6244 | 0 | 0 | 0 | 0 | 0 | 0 | 47581.8786 | 1878.2321 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1878.2321 | 0 | 0 | 0 | 0 | 1878.2321 | 0 | 1878.2321 | 5634.6962 | 0 | 0 | 0 | 0
Participant Support Costs
Descr | # participants |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Part. Supp.
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other Direct Costs
Materials and Supplies |  |  | 68100.5203 | 16173.6649 | 0 | 0 | 0 | 0 | 7110.1518 | 0 | 0 | 0 | 0 | 0 | 5217.3113 | 24051.8049 | 0 | 991.2891 | 0 | 0 | 1043.4623 | 0 | 0 | 0 | 1773.8858 | 0 | 1356.5009 | 0 | 0 | 0 | 0 | 1043.4623 | 0 | 991.2891 | 7825.9669 | 0 | 0 | 521.7311 | 0
Computers/Office |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Software/licenses |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other categories |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
And other cats… |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Materials and Supplies
|  |  | 68100.5203 | 16173.6649 | 0 | 0 | 0 | 0 | 7110.1518 | 0 | 0 | 0 | 0 | 0 | 5217.3113 | 24051.8049 | 0 | 991.2891 | 0 | 0 | 1043.4623 | 0 | 0 | 0 | 1773.8858 | 0 | 1356.5009 | 0 | 0 | 0 | 0 | 1043.4623 | 0 | 991.2891 | 7825.9669 | 0 | 0 | 521.7311 | 0
Publication Costs/Documentation/Dissemination
Consultant Services Description |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Software/Programming |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Database consultant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PMCS Service | PMCS Consulting |  | 343467 | 0 | 343467 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Etc. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Consultant/Prof Services
|  |  | 343467 | 0 | 343467 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Computer Services |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subotal Computer Services
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subawards
MSU |  |  | 125361.874 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69749.3472 | 7786.0023 | 0 | 2764.0793 | 0 | 45062.4452 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PSU |  |  | 30809.6577 | 16450.3076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14359.3501 | 0 | 0 | 0 | 0
UA |  |  | 119511.6933 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91978.7815 | 27532.9118 | 0 | 0 | 0 | 0 | 0 | 0
UMD |  |  | 69347.2225 | 16257.0284 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53090.1941 | 0 | 0 | 0 | 0 | 0
Subtotal - Subawards
|  |  | 345030.4476 | 32707.336 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69749.3472 | 7786.0023 | 0 | 2764.0793 | 0 | 45062.4452 | 0 | 0 | 91978.7815 | 27532.9118 | 53090.1941 | 14359.3501 | 0 | 0 | 0 | 0
Other - Contingency |  |  | 1475537.3259 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Leases |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Maint/Repair |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Shipping/Postage |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Other
|  |  | 1475537.3259 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total - Direct Costs
| 3436459.1439 |  | 4911996.4699 | 331139.8352 | 388540.0614 | 91220.42 | 11975.7015 | 174209.3095 | 531034.9057 | 78878.4419 | 42846.6469 | 152886.0019 | 19625.438 | 47702.9202 | 41133.2819 | 755974.8296 | 132851.5267 | 991.2891 | 0 | 0 | 1043.4623 | 40519.1 | 0 | 69749.3472 | 11721.921 | 0 | 49982.4992 | 0 | 45062.4452 | 0 | 37770.0726 | 109402.1803 | 27532.9118 | 55959.7153 | 186183.1484 | 0 | 0 | 521.7311 | 0
Indirect Costs
Indirect | 4284620.6845 |  | 848161.5406 | 158169.2245 | 205926.2326 | 48346.8226 | 6347.1218 | 92330.9341 | 117684.8841 | 0 | 0 | 0 | 0 | 0 | 2765.175 | 50835.1579 | 995.463 | 525.3832 | 0 | 0 | 553.035 | 21475.123 | 0 | 0 | 2086.0369 | 0 | 20048.4476 | 0 | 0 | 0 | 20018.1385 | 7190.384 | 0 | 1520.8462 | 91066.6131 | 0 | 0 | 276.5175 | 0
Other - Contingency Indirect | 1815890.4523 |  | 340353.1264 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Indirect Costs |  |  | 1188514.667 | 158169.2245 | 205926.2326 | 48346.8226 | 6347.1218 | 92330.9341 | 117684.8841 | 0 | 0 | 0 | 0 | 0 | 2765.175 | 50835.1579 | 995.463 | 525.3832 | 0 | 0 | 553.035 | 21475.123 | 0 | 0 | 2086.0369 | 0 | 20048.4476 | 0 | 0 | 0 | 20018.1385 | 7190.384 | 0 | 1520.8462 | 91066.6131 | 0 | 0 | 276.5175 | 0
0 | bar: 1.2.1 to 1.6.5
Total - Direct and Indirect
|  |  | 6100511.1368 | 489309.0597 | 594466.294 | 139567.2426 | 18322.8232 | 266540.2436 | 648719.7898 | 78878.4419 | 42846.6469 | 152886.0019 | 19625.438 | 47702.9202 | 43898.4569 | 806809.9875 | 133846.9897 | 1516.6724 | 0 | 0 | 1596.4972 | 61994.223 | 0 | 69749.3472 | 13807.9579 | 0 | 70030.9467 | 0 | 45062.4452 | 0 | 57788.2111 | 116592.5643 | 27532.9118 | 57480.5615 | 277249.7615 | 0 | 0 | 798.2486 | 0

## PY7 1030 - UW
Project Year | PY7 |  |  | 1.1.1 | 1.1.2 | 1.1.3 | 1.1.4 | 1.1.5 | 1.2.1 | 1.2.2 | 1.2.3 | 1.2.4 | 1.2.5 | 1.2.6 | 1.2.7 | 1.2.8 | 1.2.9 | 1.2.10 | 1.3.1 | 1.3.2 | 1.3.3 | 1.3.4 | 1.3.5 | 1.4.1 | 1.4.2 | 1.4.3 | 1.4.4 | 1.4.5 | 1.4.6 | 1.5.1 | 1.5.2 | 1.5.3 | 1.5.4 | 1.6.0 | 1.6.1 | 1.6.2 | 1.6.3 | 1.6.4 | 1.6.5
Institution | UW |  |  | 1.1.1: 1.1 Project Office; 1.2.1: 1.2 Drilling and Installation; 1.3.1: 1.3 Deep Ice Sensor Modules; 1.4.1: 1.4 Comm/Power/Timing; 1.5.1: 1.5 Characterization and Calibration System; 1.6.0: 1.6 IceCube Data Systems Integration
|  |  |  | 1.1.1 Project Management | 1.1.2 Project Controls | 1.1.3 Quality and Safety | 1.1.4 Polar Operations | 1.1.5 Project Engineering | 1.2.1 Implementation Management & Systems Engineering | 1.2.2 Thermal Plant - Off-ice | 1.2.3 Tower Operations Site (TOS) - Off-ice | 1.2.4 Computing and Control System - Off-ice | 1.2.5 Power Generation & Distribution | 1.2.6 Water Handling Systems - Off-ice | 1.2.7 Support Equipment - Off-ice | 1.2.8 Drill Field Seasons - Antarctica | 1.2.9 Installation - Off-ice | 1.2.10 Installation Field Seasons - Antarctica | 1.3.1 mDOM | 1.3.2 D-Egg | 1.3.3 PDOM | 1.3.4 Ice Comms Module | 1.3.5 Special Devices | 1.4.1 Downhole Cables | 1.4.2 Surface Cables | 1.4.3 FieldHub | 1.4.4 CPT Central Infrastructure | 1.4.5 Northern Test System | 1.4.6 CPT Management (PY4 onward) | 1.5.1 Module Calibration | 1.5.2 Calibration Assemblies | 1.5.3 Array Calibration | 1.5.4 Calibration Management and Organization | 1.6.0 L2 Task Management | 1.6.1 Online Systems Software | 1.6.2 Offline Systems | 1.6.3 Simulation Software | 1.6.4 Computing Infrastructure | 1.6.5 Upgrade String Commissioning
Expense Description |  |  | Total Yr 5
Senior Personnel
Title | Last Name | Cal. Mo.
Principal Investigator | Karle | 0.6 | 13468.6706 | 13468.6706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project Manager | Feyzi | 4.8333 | 75175.5616 | 75175.5616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project Director | ODell | 3.5333 | 63384.6125 | 63384.6125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other Personnel |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Financial Manager | Mercier | 4.8 | 34105.2832 | 0 | 34105.2832 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project Controls Analyst | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Quality and Safety | Zernick | 10.08 | 91422.1188 | 0 | 0 | 69023.4511 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22398.6677 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Technical Coordinator | DuVernois | 6 | 70288.4253 | 0 | 0 | 0 | 0 | 70288.4253 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project Engineer | Sandstrom | 4 | 41019.9682 | 0 | 0 | 0 | 0 | 41019.9682 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Logistics Manager | Tosi | 7.1667 | 48951.5293 | 0 | 0 | 0 | 6997.5798 | 0 | 27184.8423 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14769.1071 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Implementation Manager | McEwen | 12 | 116440.686 | 0 | 0 | 0 | 0 | 0 | 116440.686 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Scientist | Wendt | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Engineer / Technician | Weber | 6.3333 | 63874.9249 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63874.9249 | 0 | 0 | 0 | 0
Engineer | Kelley | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Engineer | Braun | 0.64 | 5525.6084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5525.6084 | 0 | 0 | 0 | 0
Engineer | Auer | 0.48 | 4604.6737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4604.6737 | 0
Senior Scientist | Senior Scientist | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Scientist | Scientist | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Engineer | S. Griffin | 4.08 | 30659.4523 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30659.4523 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Salaries and Wages
|  |  | 658921.5148 | 152028.8447 | 34105.2832 | 69023.4511 | 6997.5798 | 111308.3935 | 143625.5284 | 0 | 0 | 0 | 0 | 0 | 0 | 22398.6677 | 0 | 14769.1071 | 0 | 0 | 0 | 30659.4523 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69400.5334 | 0 | 0 | 4604.6737 | 0
Fringe Benefits
|  |  | 230622.5302 | 53210.0956 | 11936.8491 | 24158.2079 | 2449.1529 | 38957.9377 | 50268.9349 | 0 | 0 | 0 | 0 | 0 | 0 | 7839.5337 | 0 | 5169.1875 | 0 | 0 | 0 | 10730.8083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24290.1867 | 0 | 0 | 1611.6358 | 0
Equipment
Descrip. | Qty | Unit Cost
Capital Equipment | 1 | 1 | 115321.4945 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24507.0967 | 14922.5536 | 5329.4834 | 0 | 10658.9669 | 44447.8919 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15455.502 | 0
Capitalized Labor | 1 | 1 | 1487959.8001 | 0 | 0 | 0 | 0 | 0 | 336049.5125 | 0 | 3922.4998 | 75516.6486 | 4911.6519 | 0 | 19314.048 | 1024608.1143 | 0 | 23637.325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Eqpt
|  |  | 1603281.2946 | 0 | 0 | 0 | 0 | 0 | 336049.5125 | 0 | 28429.5965 | 90439.2022 | 10241.1354 | 0 | 29973.0149 | 1069056.0062 | 0 | 23637.325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15455.502 | 0
Travel
Domestic |  |  | 74186.4095 | 30058.2866 | 0 | 0 | 0 | 0 | 13430.2983 | 0 | 0 | 0 | 0 | 0 | 0 | 23023.3685 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5755.8421 | 0 | 0 | 1918.614 | 0
Foreign |  |  | 90174.8598 | 10232.6082 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76105.0235 | 0 | 1918.614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1918.614 | 0 | 0 | 0 | 0 | 0
Subtotal - Travel
|  |  | 164361.2693 | 40290.8948 | 0 | 0 | 0 | 0 | 13430.2983 | 0 | 0 | 0 | 0 | 0 | 0 | 99128.392 | 0 | 1918.614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1918.614 | 5755.8421 | 0 | 0 | 1918.614 | 0
Participant Support Costs
Descr | # participants |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Part. Supp.
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other Direct Costs
Materials and Supplies |  |  | 78947.77 | 16521.3987 | 0 | 0 | 0 | 0 | 4521.5338 | 0 | 0 | 0 | 0 | 0 | 5329.4834 | 43541.8797 | 0 | 1012.6019 | 0 | 0 | 0 | 0 | 0 | 0 | 532.9483 | 0 | 1678.7873 | 0 | 0 | 0 | 0 | 4263.5868 | 0 | 1012.6019 | 0 | 0 | 0 | 532.9483 | 0
Computers/Office |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Software/licenses |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other categories |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
And other cats… |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Materials and Supplies
|  |  | 78947.77 | 16521.3987 | 0 | 0 | 0 | 0 | 4521.5338 | 0 | 0 | 0 | 0 | 0 | 5329.4834 | 43541.8797 | 0 | 1012.6019 | 0 | 0 | 0 | 0 | 0 | 0 | 532.9483 | 0 | 1678.7873 | 0 | 0 | 0 | 0 | 4263.5868 | 0 | 1012.6019 | 0 | 0 | 0 | 532.9483 | 0
Publication Costs/Documentation/Dissemination
Consultant Services Description |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Software/Programming |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Database consultant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PMCS Service | PMCS Consulting |  | 359152 | 0 | 359152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Etc. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Consultant/Prof Services
|  |  | 359152 | 0 | 359152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Computer Services |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subotal Computer Services
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subawards
MSU |  |  | 110929.2608 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8288.7857 | 35570.5713 | 0 | 20711.9183 | 0 | 46357.9854 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PSU |  |  | 31471.8296 | 16803.9892 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14667.8404 | 0 | 0 | 0 | 0
UA |  |  | 216037.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 187912.6506 | 28124.8694 | 0 | 0 | 0 | 0 | 0 | 0
UMD |  |  | 79735.093 | 16606.5546 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55796.1031 | 0 | 0 | 0 | 0 | 7332.4354
Subtotal - Subawards
|  |  | 438173.7034 | 33410.5438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8288.7857 | 35570.5713 | 0 | 20711.9183 | 0 | 46357.9854 | 0 | 0 | 187912.6506 | 28124.8694 | 55796.1031 | 14667.8404 | 0 | 0 | 0 | 7332.4354
Other - Contingency |  |  | 1482030.8962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Leases |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Maint/Repair |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Shipping/Postage |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Other
|  |  | 1482030.8962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total - Direct Costs
| 3533460.0824 |  | 5015490.9787 | 295461.7775 | 405194.1323 | 93181.659 | 9446.7327 | 150266.3312 | 547895.8078 | 0 | 28429.5965 | 90439.2022 | 10241.1354 | 0 | 35302.4983 | 1241964.4793 | 0 | 46506.8355 | 0 | 0 | 0 | 41390.2607 | 0 | 8288.7857 | 36103.5197 | 0 | 22390.7056 | 0 | 46357.9854 | 0 | 0 | 192176.2374 | 28124.8694 | 58727.319 | 114114.4026 | 0 | 0 | 24123.3739 | 7332.4354
Indirect Costs
Indirect | 4324222.7772 |  | 790762.6947 | 138887.1539 | 214752.8901 | 49386.2793 | 5006.7683 | 79641.1555 | 112278.5365 | 0 | 0 | 0 | 0 | 0 | 2824.6262 | 91641.4908 | 0 | 12120.8406 | 0 | 0 | 0 | 21936.8382 | 0 | 0 | 282.4626 | 0 | 889.7573 | 0 | 0 | 0 | 0 | 2259.701 | 0 | 1553.5444 | 52706.678 | 0 | 0 | 4593.9721 | 0
Other - Contingency Indirect | 1827217.127 |  | 345186.2308 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Indirect Costs |  |  | 1135948.9255 | 138887.1539 | 214752.8901 | 49386.2793 | 5006.7683 | 79641.1555 | 112278.5365 | 0 | 0 | 0 | 0 | 0 | 2824.6262 | 91641.4908 | 0 | 12120.8406 | 0 | 0 | 0 | 21936.8382 | 0 | 0 | 282.4626 | 0 | 889.7573 | 0 | 0 | 0 | 0 | 2259.701 | 0 | 1553.5444 | 52706.678 | 0 | 0 | 4593.9721 | 0
0 | bar: 1.2.1 to 1.6.5
Total - Direct and Indirect
|  |  | 6151439.9042 | 434348.9315 | 619947.0224 | 142567.9383 | 14453.501 | 229907.4867 | 660174.3443 | 0 | 28429.5965 | 90439.2022 | 10241.1354 | 0 | 38127.1245 | 1333605.9701 | 0 | 58627.6761 | 0 | 0 | 0 | 63327.0988 | 0 | 8288.7857 | 36385.9823 | 0 | 23280.4628 | 0 | 46357.9854 | 0 | 0 | 194435.9384 | 28124.8694 | 60280.8634 | 166821.0806 | 0 | 0 | 28717.3459 | 7332.4354
651294.7751

## PY8 1030 - UW
Project Year | PY8 |  |  | 1.1.1 | 1.1.2 | 1.1.3 | 1.1.4 | 1.1.5 | 1.2.1 | 1.2.2 | 1.2.3 | 1.2.4 | 1.2.5 | 1.2.6 | 1.2.7 | 1.2.8 | 1.2.9 | 1.2.10 | 1.3.1 | 1.3.2 | 1.3.3 | 1.3.4 | 1.3.5 | 1.4.1 | 1.4.2 | 1.4.3 | 1.4.4 | 1.4.5 | 1.4.6 | 1.5.1 | 1.5.2 | 1.5.3 | 1.5.4 | 1.6.0 | 1.6.1 | 1.6.2 | 1.6.3 | 1.6.4 | 1.6.5
Institution | UW |  |  | 1.1.1: 1.1 Project Office; 1.2.1: 1.2 Drilling and Installation; 1.3.1: 1.3 Deep Ice Sensor Modules; 1.4.1: 1.4 Comm/Power/Timing; 1.5.1: 1.5 Characterization and Calibration System; 1.6.0: 1.6 IceCube Data Systems Integration
|  |  |  | 1.1.1 Project Management | 1.1.2 Project Controls | 1.1.3 Quality and Safety | 1.1.4 Polar Operations | 1.1.5 Project Engineering | 1.2.1 Implementation Management & Systems Engineering | 1.2.2 Thermal Plant - Off-ice | 1.2.3 Tower Operations Site (TOS) - Off-ice | 1.2.4 Computing and Control System - Off-ice | 1.2.5 Power Generation & Distribution | 1.2.6 Water Handling Systems - Off-ice | 1.2.7 Support Equipment - Off-ice | 1.2.8 Drill Field Seasons - Antarctica | 1.2.9 Installation - Off-ice | 1.2.10 Installation Field Seasons - Antarctica | 1.3.1 mDOM | 1.3.2 D-Egg | 1.3.3 PDOM | 1.3.4 Ice Comms Module | 1.3.5 Special Devices | 1.4.1 Downhole Cables | 1.4.2 Surface Cables | 1.4.3 FieldHub | 1.4.4 CPT Central Infrastructure | 1.4.5 Northern Test System | 1.4.6 CPT Management (PY4 onward) | 1.5.1 Module Calibration | 1.5.2 Calibration Assemblies | 1.5.3 Array Calibration | 1.5.4 Calibration Management and Organization | 1.6.0 L2 Task Management | 1.6.1 Online Systems Software | 1.6.2 Offline Systems | 1.6.3 Simulation Software | 1.6.4 Computing Infrastructure | 1.6.5 Upgrade String Commissioning
Expense Description |  |  | Total Yr 5
Senior Personnel
Title | Last Name | Cal. Mo.
Principal Investigator | Karle | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project Manager | Feyzi | 2.8333 | 45015.904 | 45015.904 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project Director | ODell | 1.6 | 29319.569 | 29319.569 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other Personnel |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Financial Manager | Mercier | 3.2 | 23225.6978 | 0 | 23225.6978 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project Controls Analyst | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Quality and Safety | Zernick | 6.0133 | 49122.4946 | 0 | 0 | 14934.1002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34188.3944 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Technical Coordinator | DuVernois | 1 | 11966.6044 | 0 | 0 | 0 | 0 | 11966.6044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project Engineer | Sandstrom | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Logistics Manager | Tosi | 4.5333 | 27532.26 | 0 | 0 | 0 | 1388.4658 | 0 | 4885.3427 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21258.4514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Implementation Manager | McEwen | 7 | 69384.0938 | 0 | 0 | 0 | 0 | 0 | 69384.0938 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Scientist | Wendt | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Engineer / Technician | Weber | 3.8333 | 39492.3533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39492.3533 | 0 | 0 | 0 | 0
Engineer | Kelley | 1 | 10444.4432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10444.4432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Engineer | Braun | 0.32 | 2822.2045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2822.2045 | 0 | 0 | 0 | 0
Engineer | Auer | 0.32 | 3135.7828 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3135.7828 | 0
Senior Scientist | Senior Scientist | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Scientist | Scientist | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Engineer | S. Griffin | 2.38 | 18269.2012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18269.2012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Salaries and Wages
|  |  | 329730.6086 | 74335.473 | 23225.6978 | 14934.1002 | 1388.4658 | 11966.6044 | 74269.4365 | 0 | 0 | 0 | 0 | 0 | 0 | 34188.3944 | 0 | 21258.4514 | 0 | 0 | 0 | 18269.2012 | 0 | 0 | 0 | 0 | 10444.4432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42314.5578 | 0 | 0 | 3135.7828 | 0
Fringe Benefits
|  |  | 115405.713 | 26017.4156 | 8128.9942 | 5226.9351 | 485.963 | 4188.3115 | 25994.3028 | 0 | 0 | 0 | 0 | 0 | 0 | 11965.9381 | 0 | 7440.458 | 0 | 0 | 0 | 6394.2204 | 0 | 0 | 0 | 0 | 3655.5551 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14810.0952 | 0 | 0 | 1097.524 | 0
Equipment
Descrip. | Qty | Unit Cost
Capital Equipment | 1 | 1 | 2177.6269 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2177.6269 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Capitalized Labor | 1 | 1 | 1392095.1997 | 0 | 0 | 0 | 0 | 0 | 126966.5384 | 0 | 0 | 4006.8336 | 0 | 0 | 8362.0874 | 1252759.7403 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Eqpt
|  |  | 1394272.8266 | 0 | 0 | 0 | 0 | 0 | 126966.5384 | 0 | 0 | 4006.8336 | 0 | 0 | 10539.7144 | 1252759.7403 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Travel
Domestic |  |  | 1959.8642 | 1959.8642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Foreign |  |  | 3919.7285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1959.8642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1959.8642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Travel
|  |  | 5879.5927 | 1959.8642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1959.8642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1959.8642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Participant Support Costs
Descr | # participants |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Part. Supp.
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other Direct Costs
Materials and Supplies |  |  | 9037.1518 | 8492.745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 272.2034 | 0 | 272.2034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Computers/Office |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Software/licenses |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other categories |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
And other cats… |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Materials and Supplies
|  |  | 9037.1518 | 8492.745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 272.2034 | 0 | 272.2034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Publication Costs/Documentation/Dissemination
Consultant Services Description |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Software/Programming |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Database consultant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PMCS Service | PMCS Consulting |  | 280327 | 0 | 280327 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Etc. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Consultant/Prof Services
|  |  | 280327 | 0 | 280327 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Computer Services |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subotal Computer Services
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subawards
MSU |  |  | 63844.2109 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57346.7165 | 0 | 0 | 3037.7896 | 0 | 3459.7048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PSU |  |  | 18964.613 | 11443.5166 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7521.0964 | 0 | 0 | 0 | 0
UA |  |  | 98896.584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95976.3863 | 2920.1977 | 0 | 0 | 0 | 0 | 0 | 0
UMD |  |  | 38146.0027 | 8481.7977 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24670.8164 | 0 | 0 | 0 | 0 | 4993.3885
Subtotal - Subawards
|  |  | 219851.4105 | 19925.3144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57346.7165 | 0 | 0 | 3037.7896 | 0 | 3459.7048 | 0 | 0 | 95976.3863 | 2920.1977 | 24670.8164 | 7521.0964 | 0 | 0 | 0 | 4993.3885
Other - Contingency |  |  | 248402.019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Leases |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Maint/Repair |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Shipping/Postage |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Other
|  |  | 248402.019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total - Direct Costs
| 2354504.3033 |  | 2602906.3222 | 130730.8123 | 311681.6921 | 20161.0353 | 1874.4289 | 16154.916 | 227230.2777 | 0 | 0 | 4006.8336 | 0 | 0 | 10539.7144 | 1298914.0728 | 0 | 30658.7737 | 0 | 0 | 0 | 24663.4216 | 0 | 57346.7165 | 272.2034 | 0 | 19369.8555 | 0 | 3459.7048 | 0 | 0 | 95976.3863 | 2920.1977 | 24670.8164 | 64645.7493 | 0 | 0 | 4233.3068 | 4993.3885
Indirect Costs
Indirect | 2746905.7383 |  | 392401.435 | 58726.9139 | 165191.2968 | 10685.3487 | 993.4473 | 8562.1055 | 53139.7818 | 0 | 0 | 0 | 0 | 0 | 0 | 24461.7962 | 0 | 16249.15 | 0 | 0 | 0 | 13071.6134 | 0 | 0 | 144.2678 | 0 | 8655.9949 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30276.0661 | 0 | 0 | 2243.6526 | 0
Other - Contingency Indirect | 292594.5409 |  | 44192.5219 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Indirect Costs |  |  | 436593.957 | 58726.9139 | 165191.2968 | 10685.3487 | 993.4473 | 8562.1055 | 53139.7818 | 0 | 0 | 0 | 0 | 0 | 0 | 24461.7962 | 0 | 16249.15 | 0 | 0 | 0 | 13071.6134 | 0 | 0 | 144.2678 | 0 | 8655.9949 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30276.0661 | 0 | 0 | 2243.6526 | 0
0 | bar: 1.2.1 to 1.6.5
Total - Direct and Indirect
|  |  | 3039500.2792 | 189457.7261 | 476872.9889 | 30846.3839 | 2867.8762 | 24717.0214 | 280370.0595 | 0 | 0 | 4006.8336 | 0 | 0 | 10539.7144 | 1323375.869 | 0 | 46907.9237 | 0 | 0 | 0 | 37735.035 | 0 | 57346.7165 | 416.4712 | 0 | 28025.8504 | 0 | 3459.7048 | 0 | 0 | 95976.3863 | 2920.1977 | 24670.8164 | 94921.8154 | 0 | 0 | 6476.9593 | 4993.3885
83382.1169

## PY5 1030 - MSU
Project Year | PY5 |  |  | 1.1.1 | 1.1.2 | 1.1.3 | 1.1.4 | 1.1.5 | 1.2.1 | 1.2.2 | 1.2.3 | 1.2.4 | 1.2.5 | 1.2.6 | 1.2.7 | 1.2.8 | 1.2.9 | 1.2.10 | 1.3.1 | 1.3.2 | 1.3.3 | 1.3.4 | 1.3.5 | 1.4.1 | 1.4.2 | 1.4.3 | 1.4.4 | 1.4.5 | 1.4.6 | 1.5.1 | 1.5.2 | 1.5.3 | 1.5.4 | 1.6.0 | 1.6.1 | 1.6.2 | 1.6.3 | 1.6.4 | 1.6.5
Institution | MSU |  |  | 1.1.1: 1.1 Project Office; 1.2.1: 1.2 Drilling and Installation; 1.3.1: 1.3 Deep Ice Sensor Modules; 1.4.1: 1.4 Comm/Power/Timing; 1.5.1: 1.5 Characterization and Calibration System; 1.6.0: 1.6 IceCube Data Systems Integration
|  |  |  | 1.1.1 Project Management | 1.1.2 Project Controls | 1.1.3 Quality and Safety | 1.1.4 Polar Operations | 1.1.5 Project Engineering | 1.2.1 Implementation Management & Systems Engineering | 1.2.2 Thermal Plant - Off-ice | 1.2.3 Tower Operations Site (TOS) - Off-ice | 1.2.4 Computing and Control System - Off-ice | 1.2.5 Power Generation & Distribution | 1.2.6 Water Handling Systems - Off-ice | 1.2.7 Support Equipment - Off-ice | 1.2.8 Drill Field Seasons - Antarctica | 1.2.9 Installation - Off-ice | 1.2.10 Installation Field Seasons - Antarctica | 1.3.1 mDOM | 1.3.2 D-Egg | 1.3.3 PDOM | 1.3.4 Ice Comms Module | 1.3.5 Special Devices | 1.4.1 Downhole Cables | 1.4.2 Surface Cables | 1.4.3 FieldHub | 1.4.4 CPT Central Infrastructure | 1.4.5 Northern Test System | 1.4.6 CPT Management (PY4 onward) | 1.5.1 Module Calibration | 1.5.2 Calibration Assemblies | 1.5.3 Array Calibration | 1.5.4 Calibration Management and Organization | 1.6.0 L2 Task Management | 1.6.1 Online Systems Software | 1.6.2 Offline Systems | 1.6.3 Simulation Software | 1.6.4 Computing Infrastructure | 1.6.5 Upgrade String Commissioning
Expense Description |  |  | Total Yr 5
Senior Personnel
Title | Last Name | Cal. Mo.
Principal Investigator | DeYoung | 1.5 | 22361.022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22361.022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other Personnel |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PostDoctoral Researcher | Halliday | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Salaries and Wages
|  |  | 22361.022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22361.022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fringe Benefits
|  |  | 1710.9983 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1710.9983 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Equipment
Descrip. | Qty | Unit Cost
Capital Equipment | 1 | 1 | 272035.665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 257734.665 | 14301 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Capitalized Labor | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Eqpt
|  |  | 272035.665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 257734.665 | 14301 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Travel
Domestic |  |  | 18387 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14709.6 | 0 | 0 | 0 | 0 | 3677.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Foreign |  |  | 39225.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39225.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Travel
|  |  | 57612.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53935.2 | 0 | 0 | 0 | 0 | 3677.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Participant Support Costs
Descr | # participants |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Part. Supp.
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other Direct Costs
Materials and Supplies |  |  | 12222.6561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10046.4525 | 1661.3676 | 0 | 0 | 0 | 514.836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Computers/Office |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Software/licenses |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other categories |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
And other cats… |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Materials and Supplies
|  |  | 12222.6561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10046.4525 | 1661.3676 | 0 | 0 | 0 | 514.836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Publication Costs/Documentation/Dissemination
Consultant Services | Ng |  | 77139.594 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73592.946 | 3546.648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Consultant Services | Shooltz |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Consultant Services | TBD |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Consultant Services | Wilkins |  | 36295.938 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26021.691 | 10274.247 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Software/Programming |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Database consultant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PMCS Service | PMCS Consulting |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Etc. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Consultant/Prof Services
|  |  | 113435.532 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99614.637 | 13820.895 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Computer Services |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subotal Computer Services
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subawards
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Subawards
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Leases |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Maint/Repair |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Shipping/Postage |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Other
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total - Direct Costs
|  |  | 479378.4734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 421330.9545 | 29783.2626 | 0 | 0 | 0 | 28264.2563 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Indirect Costs
Indirect |  |  | 114038.5446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89977.9592 | 8515.2444 | 0 | 0 | 0 | 15545.341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other |  |  |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Indirect Costs |  |  | 114038.5446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89977.9592 | 8515.2444 | 0 | 0 | 0 | 15545.341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
Total - Direct and Indirect
|  |  | 593417.0181 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 511308.9137 | 38298.507 | 0 | 0 | 0 | 43809.5973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## PY6 1030 - MSU
Project Year | PY6 |  |  | 1.1.1 | 1.1.2 | 1.1.3 | 1.1.4 | 1.1.5 | 1.2.1 | 1.2.2 | 1.2.3 | 1.2.4 | 1.2.5 | 1.2.6 | 1.2.7 | 1.2.8 | 1.2.9 | 1.2.10 | 1.3.1 | 1.3.2 | 1.3.3 | 1.3.4 | 1.3.5 | 1.4.1 | 1.4.2 | 1.4.3 | 1.4.4 | 1.4.5 | 1.4.6 | 1.5.1 | 1.5.2 | 1.5.3 | 1.5.4 | 1.6.0 | 1.6.1 | 1.6.2 | 1.6.3 | 1.6.4 | 1.6.5
Institution | MSU |  |  | 1.1.1: 1.1 Project Office; 1.2.1: 1.2 Drilling and Installation; 1.3.1: 1.3 Deep Ice Sensor Modules; 1.4.1: 1.4 Comm/Power/Timing; 1.5.1: 1.5 Characterization and Calibration System; 1.6.0: 1.6 IceCube Data Systems Integration
|  |  |  | 1.1.1 Project Management | 1.1.2 Project Controls | 1.1.3 Quality and Safety | 1.1.4 Polar Operations | 1.1.5 Project Engineering | 1.2.1 Implementation Management & Systems Engineering | 1.2.2 Thermal Plant - Off-ice | 1.2.3 Tower Operations Site (TOS) - Off-ice | 1.2.4 Computing and Control System - Off-ice | 1.2.5 Power Generation & Distribution | 1.2.6 Water Handling Systems - Off-ice | 1.2.7 Support Equipment - Off-ice | 1.2.8 Drill Field Seasons - Antarctica | 1.2.9 Installation - Off-ice | 1.2.10 Installation Field Seasons - Antarctica | 1.3.1 mDOM | 1.3.2 D-Egg | 1.3.3 PDOM | 1.3.4 Ice Comms Module | 1.3.5 Special Devices | 1.4.1 Downhole Cables | 1.4.2 Surface Cables | 1.4.3 FieldHub | 1.4.4 CPT Central Infrastructure | 1.4.5 Northern Test System | 1.4.6 CPT Management (PY4 onward) | 1.5.1 Module Calibration | 1.5.2 Calibration Assemblies | 1.5.3 Array Calibration | 1.5.4 Calibration Management and Organization | 1.6.0 L2 Task Management | 1.6.1 Online Systems Software | 1.6.2 Offline Systems | 1.6.3 Simulation Software | 1.6.4 Computing Infrastructure | 1.6.5 Upgrade String Commissioning
Expense Description |  |  | Total Yr 5
Senior Personnel
Title | Last Name | Cal. Mo.
Principal Investigator | DeYoung | 1.5 | 23032.0098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23032.0098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other Personnel |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PostDoctoral Researcher | Halliday | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Salaries and Wages
|  |  | 23032.0098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23032.0098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fringe Benefits
|  |  | 1762.3403 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1762.3403 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Equipment
Descrip. | Qty | Unit Cost
Capital Equipment | 1 | 1 | 46955.8013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46955.8013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Capitalized Labor | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Eqpt
|  |  | 46955.8013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46955.8013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Travel
Domestic |  |  | 3756.4641 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3756.4641 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Foreign |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Travel
|  |  | 3756.4641 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3756.4641 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Participant Support Costs
Descr | # participants |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Part. Supp.
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other Direct Costs
Materials and Supplies |  |  | 14852.6417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10565.0553 | 1982.5783 | 0 | 1783.277 | 0 | 521.7311 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Computers/Office |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Software/licenses |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other categories |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
And other cats… |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Materials and Supplies
|  |  | 14852.6417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10565.0553 | 1982.5783 | 0 | 1783.277 | 0 | 521.7311 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Publication Costs/Documentation/Dissemination
Consultant Services | Ng |  | 4140.4582 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4140.4582 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Consultant Services | Shooltz |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Consultant Services | TBD |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Consultant Services | Wilkins |  | 3040.649 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3040.649 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Software/Programming |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Database consultant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PMCS Service | PMCS Consulting |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Etc. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Consultant/Prof Services
|  |  | 7181.1072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4140.4582 | 3040.649 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Computer Services |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subotal Computer Services
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subawards
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Subawards
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Leases |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Maint/Repair |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Shipping/Postage |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Other
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total - Direct Costs
|  |  | 97540.3643 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61661.3147 | 5023.2273 | 0 | 1783.277 | 0 | 29072.5453 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Indirect Costs
Indirect |  |  | 27821.5097 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8088.0324 | 2762.775 | 0 | 980.8023 | 0 | 15989.8999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other |  |  |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Indirect Costs |  |  | 27821.5097 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8088.0324 | 2762.775 | 0 | 980.8023 | 0 | 15989.8999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
Total - Direct and Indirect
|  |  | 125361.874 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69749.3472 | 7786.0023 | 0 | 2764.0793 | 0 | 45062.4452 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## PY7 1030 - MSU
Project Year | PY7 |  |  | 1.1.1 | 1.1.2 | 1.1.3 | 1.1.4 | 1.1.5 | 1.2.1 | 1.2.2 | 1.2.3 | 1.2.4 | 1.2.5 | 1.2.6 | 1.2.7 | 1.2.8 | 1.2.9 | 1.2.10 | 1.3.1 | 1.3.2 | 1.3.3 | 1.3.4 | 1.3.5 | 1.4.1 | 1.4.2 | 1.4.3 | 1.4.4 | 1.4.5 | 1.4.6 | 1.5.1 | 1.5.2 | 1.5.3 | 1.5.4 | 1.6.0 | 1.6.1 | 1.6.2 | 1.6.3 | 1.6.4 | 1.6.5
Institution | MSU |  |  | 1.1.1: 1.1 Project Office; 1.2.1: 1.2 Drilling and Installation; 1.3.1: 1.3 Deep Ice Sensor Modules; 1.4.1: 1.4 Comm/Power/Timing; 1.5.1: 1.5 Characterization and Calibration System; 1.6.0: 1.6 IceCube Data Systems Integration
|  |  |  | 1.1.1 Project Management | 1.1.2 Project Controls | 1.1.3 Quality and Safety | 1.1.4 Polar Operations | 1.1.5 Project Engineering | 1.2.1 Implementation Management & Systems Engineering | 1.2.2 Thermal Plant - Off-ice | 1.2.3 Tower Operations Site (TOS) - Off-ice | 1.2.4 Computing and Control System - Off-ice | 1.2.5 Power Generation & Distribution | 1.2.6 Water Handling Systems - Off-ice | 1.2.7 Support Equipment - Off-ice | 1.2.8 Drill Field Seasons - Antarctica | 1.2.9 Installation - Off-ice | 1.2.10 Installation Field Seasons - Antarctica | 1.3.1 mDOM | 1.3.2 D-Egg | 1.3.3 PDOM | 1.3.4 Ice Comms Module | 1.3.5 Special Devices | 1.4.1 Downhole Cables | 1.4.2 Surface Cables | 1.4.3 FieldHub | 1.4.4 CPT Central Infrastructure | 1.4.5 Northern Test System | 1.4.6 CPT Management (PY4 onward) | 1.5.1 Module Calibration | 1.5.2 Calibration Assemblies | 1.5.3 Array Calibration | 1.5.4 Calibration Management and Organization | 1.6.0 L2 Task Management | 1.6.1 Online Systems Software | 1.6.2 Offline Systems | 1.6.3 Simulation Software | 1.6.4 Computing Infrastructure | 1.6.5 Upgrade String Commissioning
Expense Description |  |  | Total Yr 5
Senior Personnel
Title | Last Name | Cal. Mo.
Principal Investigator | DeYoung | 1.5 | 23722.9893 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23722.9893 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other Personnel |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PostDoctoral Researcher | Halliday | 1 | 4926.841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4926.841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Salaries and Wages
|  |  | 28649.8303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4926.841 | 0 | 23722.9893 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fringe Benefits
|  |  | 3482.455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1667.243 | 0 | 1815.212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Equipment
Descrip. | Qty | Unit Cost
Capital Equipment | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Capitalized Labor | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Eqpt
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Travel
Domestic |  |  | 9593.0702 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3837.2281 | 0 | 0 | 1918.614 | 0 | 3837.2281 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Foreign |  |  | 7674.4562 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3837.2281 | 0 | 3837.2281 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Travel
|  |  | 17267.5264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3837.2281 | 3837.2281 | 0 | 5755.8421 | 0 | 3837.2281 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Participant Support Costs
Descr | # participants |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Part. Supp.
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other Direct Costs
Materials and Supplies |  |  | 3055.9258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1510.3756 | 0 | 0 | 1012.6019 | 0 | 532.9483 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Computers/Office |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Software/licenses |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other categories |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
And other cats… |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Materials and Supplies
|  |  | 3055.9258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1510.3756 | 0 | 0 | 1012.6019 | 0 | 532.9483 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Publication Costs/Documentation/Dissemination
Consultant Services | Ng |  | 7599.8434 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7599.8434 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Consultant Services | Shooltz |  | 11511.6842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11511.6842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Consultant Services | TBD |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Consultant Services | Wilkins |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Software/Programming |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Database consultant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PMCS Service | PMCS Consulting |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Etc. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Consultant/Prof Services
|  |  | 19111.5276 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19111.5276 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Computer Services |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subotal Computer Services
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subawards
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Subawards
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Leases |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Maint/Repair |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Shipping/Postage |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Other
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total - Direct Costs
|  |  | 71567.265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5347.6037 | 22948.7557 | 0 | 13362.5279 | 0 | 29908.3777 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Indirect Costs
Indirect |  |  | 39361.9958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2941.182 | 12621.8156 | 0 | 7349.3904 | 0 | 16449.6077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other |  |  |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Indirect Costs |  |  | 39361.9958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2941.182 | 12621.8156 | 0 | 7349.3904 | 0 | 16449.6077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
Total - Direct and Indirect
|  |  | 110929.2608 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8288.7857 | 35570.5713 | 0 | 20711.9183 | 0 | 46357.9854 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## PY8 1030 - MSU
Project Year | PY8 |  |  | 1.1.1 | 1.1.2 | 1.1.3 | 1.1.4 | 1.1.5 | 1.2.1 | 1.2.2 | 1.2.3 | 1.2.4 | 1.2.5 | 1.2.6 | 1.2.7 | 1.2.8 | 1.2.9 | 1.2.10 | 1.3.1 | 1.3.2 | 1.3.3 | 1.3.4 | 1.3.5 | 1.4.1 | 1.4.2 | 1.4.3 | 1.4.4 | 1.4.5 | 1.4.6 | 1.5.1 | 1.5.2 | 1.5.3 | 1.5.4 | 1.6.0 | 1.6.1 | 1.6.2 | 1.6.3 | 1.6.4 | 1.6.5
Institution | MSU |  |  | 1.1.1: 1.1 Project Office; 1.2.1: 1.2 Drilling and Installation; 1.3.1: 1.3 Deep Ice Sensor Modules; 1.4.1: 1.4 Comm/Power/Timing; 1.5.1: 1.5 Characterization and Calibration System; 1.6.0: 1.6 IceCube Data Systems Integration
|  |  |  | 1.1.1 Project Management | 1.1.2 Project Controls | 1.1.3 Quality and Safety | 1.1.4 Polar Operations | 1.1.5 Project Engineering | 1.2.1 Implementation Management & Systems Engineering | 1.2.2 Thermal Plant - Off-ice | 1.2.3 Tower Operations Site (TOS) - Off-ice | 1.2.4 Computing and Control System - Off-ice | 1.2.5 Power Generation & Distribution | 1.2.6 Water Handling Systems - Off-ice | 1.2.7 Support Equipment - Off-ice | 1.2.8 Drill Field Seasons - Antarctica | 1.2.9 Installation - Off-ice | 1.2.10 Installation Field Seasons - Antarctica | 1.3.1 mDOM | 1.3.2 D-Egg | 1.3.3 PDOM | 1.3.4 Ice Comms Module | 1.3.5 Special Devices | 1.4.1 Downhole Cables | 1.4.2 Surface Cables | 1.4.3 FieldHub | 1.4.4 CPT Central Infrastructure | 1.4.5 Northern Test System | 1.4.6 CPT Management (PY4 onward) | 1.5.1 Module Calibration | 1.5.2 Calibration Assemblies | 1.5.3 Array Calibration | 1.5.4 Calibration Management and Organization | 1.6.0 L2 Task Management | 1.6.1 Online Systems Software | 1.6.2 Offline Systems | 1.6.3 Simulation Software | 1.6.4 Computing Infrastructure | 1.6.5 Upgrade String Commissioning
Expense Description |  |  | Total Yr 5
Senior Personnel
Title | Last Name | Cal. Mo.
Principal Investigator | DeYoung | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other Personnel |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PostDoctoral Researcher | Halliday | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Salaries and Wages
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fringe Benefits
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Equipment
Descrip. | Qty | Unit Cost
Capital Equipment | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Capitalized Labor | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Eqpt
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Travel
Domestic |  |  | 1959.8642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1959.8642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Foreign |  |  | 5879.5927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3919.7285 | 0 | 0 | 1959.8642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Travel
|  |  | 7839.457 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3919.7285 | 0 | 0 | 1959.8642 | 0 | 1959.8642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Participant Support Costs
Descr | # participants |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Part. Supp.
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other Direct Costs
Materials and Supplies |  |  | 272.2034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 272.2034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Computers/Office |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Software/licenses |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other categories |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
And other cats… |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Materials and Supplies
|  |  | 272.2034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 272.2034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Publication Costs/Documentation/Dissemination
Consultant Services | Ng |  | 20251.9305 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20251.9305 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Consultant Services | Shooltz |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Consultant Services | TBD |  | 12826.2226 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12826.2226 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Consultant Services | Wilkins |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Software/Programming |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Database consultant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PMCS Service | PMCS Consulting |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Etc. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Consultant/Prof Services
|  |  | 33078.1531 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33078.1531 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Computer Services |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subotal Computer Services
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subawards
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Subawards
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Leases |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Maint/Repair |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Shipping/Postage |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Other
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total - Direct Costs
|  |  | 41189.8135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36997.8816 | 0 | 0 | 1959.8642 | 0 | 2232.0676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Indirect Costs
Indirect |  |  | 22654.3974 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20348.8349 | 0 | 0 | 1077.9253 | 0 | 1227.6372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other |  |  |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Indirect Costs |  |  | 22654.3974 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20348.8349 | 0 | 0 | 1077.9253 | 0 | 1227.6372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
Total - Direct and Indirect
|  |  | 63844.2109 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57346.7165 | 0 | 0 | 3037.7896 | 0 | 3459.7048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## PY5 1030 - PSU
Project Year | PY5 |  |  | 1.1.1 | 1.1.2 | 1.1.3 | 1.1.4 | 1.1.5 | 1.2.1 | 1.2.2 | 1.2.3 | 1.2.4 | 1.2.5 | 1.2.6 | 1.2.7 | 1.2.8 | 1.2.9 | 1.2.10 | 1.3.1 | 1.3.2 | 1.3.3 | 1.3.4 | 1.3.5 | 1.4.1 | 1.4.2 | 1.4.3 | 1.4.4 | 1.4.5 | 1.4.6 | 1.5.1 | 1.5.2 | 1.5.3 | 1.5.4 | 1.6.0 | 1.6.1 | 1.6.2 | 1.6.3 | 1.6.4 | 1.6.5
Institution | PSU |  |  | 1.1.1: 1.1 Project Office; 1.2.1: 1.2 Drilling and Installation; 1.3.1: 1.3 Deep Ice Sensor Modules; 1.4.1: 1.4 Comm/Power/Timing; 1.5.1: 1.5 Characterization and Calibration System; 1.6.0: 1.6 IceCube Data Systems Integration
|  |  |  | 1.1.1 Project Management | 1.1.2 Project Controls | 1.1.3 Quality and Safety | 1.1.4 Polar Operations | 1.1.5 Project Engineering | 1.2.1 Implementation Management & Systems Engineering | 1.2.2 Thermal Plant - Off-ice | 1.2.3 Tower Operations Site (TOS) - Off-ice | 1.2.4 Computing and Control System - Off-ice | 1.2.5 Power Generation & Distribution | 1.2.6 Water Handling Systems - Off-ice | 1.2.7 Support Equipment - Off-ice | 1.2.8 Drill Field Seasons - Antarctica | 1.2.9 Installation - Off-ice | 1.2.10 Installation Field Seasons - Antarctica | 1.3.1 mDOM | 1.3.2 D-Egg | 1.3.3 PDOM | 1.3.4 Ice Comms Module | 1.3.5 Special Devices | 1.4.1 Downhole Cables | 1.4.2 Surface Cables | 1.4.3 FieldHub | 1.4.4 CPT Central Infrastructure | 1.4.5 Northern Test System | 1.4.6 CPT Management (PY4 onward) | 1.5.1 Module Calibration | 1.5.2 Calibration Assemblies | 1.5.3 Array Calibration | 1.5.4 Calibration Management and Organization | 1.6.0 L2 Task Management | 1.6.1 Online Systems Software | 1.6.2 Offline Systems | 1.6.3 Simulation Software | 1.6.4 Computing Infrastructure | 1.6.5 Upgrade String Commissioning
Expense Description |  |  | Total Yr 5
Senior Personnel
Title | Last Name | Cal. Mo.
Principal Investigator | Cowen | 0.4 | 7355.0298 | 7355.0298 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other Personnel |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Firmware Engineer | Anderson | 1.56 | 12071.4916 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12071.4916 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Salaries and Wages
|  |  | 19426.5215 | 7355.0298 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12071.4916 | 0 | 0 | 0 | 0
Fringe Benefits
|  |  | 6993.5477 | 2647.8107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4345.737 | 0 | 0 | 0 | 0
Equipment
Descrip. | Qty | Unit Cost
Capital Equipment | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Capitalized Labor | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Eqpt
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Travel
Domestic |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Foreign |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Travel
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Participant Support Costs
Descr | # participants |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Part. Supp.
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other Direct Costs
Materials and Supplies |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Computers/Office |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Software/licenses |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other categories |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
And other cats… |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Materials and Supplies
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Publication Costs/Documentation/Dissemination
Consultant Services Description |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Software/Programming |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Database consultant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Etc. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Consultant/Prof Services
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Computer Services |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subotal Computer Services
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subawards
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Subawards
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Leases |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Maint/Repair |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Shipping/Postage |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Other
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total - Direct Costs
|  |  | 26420.0692 | 10002.8406 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16417.2286 | 0 | 0 | 0 | 0
Indirect Costs
Indirect |  |  | 15891.5478 | 6016.2076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9875.3402 | 0 | 0 | 0 | 0
Other |  |  |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Indirect Costs |  |  | 15891.5478 | 6016.2076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9875.3402 | 0 | 0 | 0 | 0
0
Total - Direct and Indirect
|  |  | 42311.617 | 16019.0482 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26292.5688 | 0 | 0 | 0 | 0

## PY6 1030 - PSU
Project Year | PY6 |  |  | 1.1.1 | 1.1.2 | 1.1.3 | 1.1.4 | 1.1.5 | 1.2.1 | 1.2.2 | 1.2.3 | 1.2.4 | 1.2.5 | 1.2.6 | 1.2.7 | 1.2.8 | 1.2.9 | 1.2.10 | 1.3.1 | 1.3.2 | 1.3.3 | 1.3.4 | 1.3.5 | 1.4.1 | 1.4.2 | 1.4.3 | 1.4.4 | 1.4.5 | 1.4.6 | 1.5.1 | 1.5.2 | 1.5.3 | 1.5.4 | 1.6.0 | 1.6.1 | 1.6.2 | 1.6.3 | 1.6.4 | 1.6.5
Institution | PSU |  |  | 1.1.1: 1.1 Project Office; 1.2.1: 1.2 Drilling and Installation; 1.3.1: 1.3 Deep Ice Sensor Modules; 1.4.1: 1.4 Comm/Power/Timing; 1.5.1: 1.5 Characterization and Calibration System; 1.6.0: 1.6 IceCube Data Systems Integration
|  |  |  | 1.1.1 Project Management | 1.1.2 Project Controls | 1.1.3 Quality and Safety | 1.1.4 Polar Operations | 1.1.5 Project Engineering | 1.2.1 Implementation Management & Systems Engineering | 1.2.2 Thermal Plant - Off-ice | 1.2.3 Tower Operations Site (TOS) - Off-ice | 1.2.4 Computing and Control System - Off-ice | 1.2.5 Power Generation & Distribution | 1.2.6 Water Handling Systems - Off-ice | 1.2.7 Support Equipment - Off-ice | 1.2.8 Drill Field Seasons - Antarctica | 1.2.9 Installation - Off-ice | 1.2.10 Installation Field Seasons - Antarctica | 1.3.1 mDOM | 1.3.2 D-Egg | 1.3.3 PDOM | 1.3.4 Ice Comms Module | 1.3.5 Special Devices | 1.4.1 Downhole Cables | 1.4.2 Surface Cables | 1.4.3 FieldHub | 1.4.4 CPT Central Infrastructure | 1.4.5 Northern Test System | 1.4.6 CPT Management (PY4 onward) | 1.5.1 Module Calibration | 1.5.2 Calibration Assemblies | 1.5.3 Array Calibration | 1.5.4 Calibration Management and Organization | 1.6.0 L2 Task Management | 1.6.1 Online Systems Software | 1.6.2 Offline Systems | 1.6.3 Simulation Software | 1.6.4 Computing Infrastructure | 1.6.5 Upgrade String Commissioning
Expense Description |  |  | Total Yr 5
Senior Personnel
Title | Last Name | Cal. Mo.
Principal Investigator | Cowen | 0.4 | 7512.9282 | 7512.9282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other Personnel |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Firmware Engineer | Anderson | 0.82968 | 6557.9787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6557.9787 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Salaries and Wages
|  |  | 14070.9069 | 7512.9282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6557.9787 | 0 | 0 | 0 | 0
Fringe Benefits
|  |  | 5065.5265 | 2704.6542 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2360.8723 | 0 | 0 | 0 | 0
Equipment
Descrip. | Qty | Unit Cost
Capital Equipment | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Capitalized Labor | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Eqpt
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Travel
Domestic |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Foreign |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Travel
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Participant Support Costs
Descr | # participants |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Part. Supp.
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other Direct Costs
Materials and Supplies |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Computers/Office |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Software/licenses |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other categories |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
And other cats… |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Materials and Supplies
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Publication Costs/Documentation/Dissemination
Consultant Services Description |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Software/Programming |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Database consultant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Etc. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Consultant/Prof Services
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Computer Services |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subotal Computer Services
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subawards
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Subawards
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Leases |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Maint/Repair |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Shipping/Postage |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Other
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total - Direct Costs
|  |  | 19136.4334 | 10217.5824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8918.851 | 0 | 0 | 0 | 0
Indirect Costs
Indirect |  |  | 11673.2243 | 6232.7252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5440.4991 | 0 | 0 | 0 | 0
Other |  |  |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Indirect Costs |  |  | 11673.2243 | 6232.7252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5440.4991 | 0 | 0 | 0 | 0
0
Total - Direct and Indirect
|  |  | 30809.6577 | 16450.3076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14359.3501 | 0 | 0 | 0 | 0

## PY7 1030 - PSU
Project Year | PY7 |  |  | 1.1.1 | 1.1.2 | 1.1.3 | 1.1.4 | 1.1.5 | 1.2.1 | 1.2.2 | 1.2.3 | 1.2.4 | 1.2.5 | 1.2.6 | 1.2.7 | 1.2.8 | 1.2.9 | 1.2.10 | 1.3.1 | 1.3.2 | 1.3.3 | 1.3.4 | 1.3.5 | 1.4.1 | 1.4.2 | 1.4.3 | 1.4.4 | 1.4.5 | 1.4.6 | 1.5.1 | 1.5.2 | 1.5.3 | 1.5.4 | 1.6.0 | 1.6.1 | 1.6.2 | 1.6.3 | 1.6.4 | 1.6.5
Institution | PSU |  |  | 1.1.1: 1.1 Project Office; 1.2.1: 1.2 Drilling and Installation; 1.3.1: 1.3 Deep Ice Sensor Modules; 1.4.1: 1.4 Comm/Power/Timing; 1.5.1: 1.5 Characterization and Calibration System; 1.6.0: 1.6 IceCube Data Systems Integration
|  |  |  | 1.1.1 Project Management | 1.1.2 Project Controls | 1.1.3 Quality and Safety | 1.1.4 Polar Operations | 1.1.5 Project Engineering | 1.2.1 Implementation Management & Systems Engineering | 1.2.2 Thermal Plant - Off-ice | 1.2.3 Tower Operations Site (TOS) - Off-ice | 1.2.4 Computing and Control System - Off-ice | 1.2.5 Power Generation & Distribution | 1.2.6 Water Handling Systems - Off-ice | 1.2.7 Support Equipment - Off-ice | 1.2.8 Drill Field Seasons - Antarctica | 1.2.9 Installation - Off-ice | 1.2.10 Installation Field Seasons - Antarctica | 1.3.1 mDOM | 1.3.2 D-Egg | 1.3.3 PDOM | 1.3.4 Ice Comms Module | 1.3.5 Special Devices | 1.4.1 Downhole Cables | 1.4.2 Surface Cables | 1.4.3 FieldHub | 1.4.4 CPT Central Infrastructure | 1.4.5 Northern Test System | 1.4.6 CPT Management (PY4 onward) | 1.5.1 Module Calibration | 1.5.2 Calibration Assemblies | 1.5.3 Array Calibration | 1.5.4 Calibration Management and Organization | 1.6.0 L2 Task Management | 1.6.1 Online Systems Software | 1.6.2 Offline Systems | 1.6.3 Simulation Software | 1.6.4 Computing Infrastructure | 1.6.5 Upgrade String Commissioning
Expense Description |  |  | Total Yr 5
Senior Personnel
Title | Last Name | Cal. Mo.
Principal Investigator | Cowen | 0.4 | 7674.4562 | 7674.4562 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other Personnel |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Firmware Engineer | Anderson | 0.82967 | 6698.8676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6698.8676 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Salaries and Wages
|  |  | 14373.3237 | 7674.4562 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6698.8676 | 0 | 0 | 0 | 0
Fringe Benefits
|  |  | 5174.3965 | 2762.8042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2411.5923 | 0 | 0 | 0 | 0
Equipment
Descrip. | Qty | Unit Cost
Capital Equipment | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Capitalized Labor | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Eqpt
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Travel
Domestic |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Foreign |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Travel
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Participant Support Costs
Descr | # participants |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Part. Supp.
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other Direct Costs
Materials and Supplies |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Computers/Office |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Software/licenses |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other categories |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
And other cats… |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Materials and Supplies
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Publication Costs/Documentation/Dissemination
Consultant Services Description |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Software/Programming |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Database consultant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Etc. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Consultant/Prof Services
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Computer Services |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subotal Computer Services
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subawards
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Subawards
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Leases |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Maint/Repair |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Shipping/Postage |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Other
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total - Direct Costs
|  |  | 19547.7203 | 10437.2604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9110.4599 | 0 | 0 | 0 | 0
Indirect Costs
Indirect |  |  | 11924.1094 | 6366.7288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5557.3805 | 0 | 0 | 0 | 0
Other |  |  |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Indirect Costs |  |  | 11924.1094 | 6366.7288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5557.3805 | 0 | 0 | 0 | 0
0
Total - Direct and Indirect
|  |  | 31471.8296 | 16803.9892 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14667.8404 | 0 | 0 | 0 | 0

## PY8 1030 - PSU
Project Year | PY8 |  |  | 1.1.1 | 1.1.2 | 1.1.3 | 1.1.4 | 1.1.5 | 1.2.1 | 1.2.2 | 1.2.3 | 1.2.4 | 1.2.5 | 1.2.6 | 1.2.7 | 1.2.8 | 1.2.9 | 1.2.10 | 1.3.1 | 1.3.2 | 1.3.3 | 1.3.4 | 1.3.5 | 1.4.1 | 1.4.2 | 1.4.3 | 1.4.4 | 1.4.5 | 1.4.6 | 1.5.1 | 1.5.2 | 1.5.3 | 1.5.4 | 1.6.0 | 1.6.1 | 1.6.2 | 1.6.3 | 1.6.4 | 1.6.5
Institution | PSU |  |  | 1.1.1: 1.1 Project Office; 1.2.1: 1.2 Drilling and Installation; 1.3.1: 1.3 Deep Ice Sensor Modules; 1.4.1: 1.4 Comm/Power/Timing; 1.5.1: 1.5 Characterization and Calibration System; 1.6.0: 1.6 IceCube Data Systems Integration
|  |  |  | 1.1.1 Project Management | 1.1.2 Project Controls | 1.1.3 Quality and Safety | 1.1.4 Polar Operations | 1.1.5 Project Engineering | 1.2.1 Implementation Management & Systems Engineering | 1.2.2 Thermal Plant - Off-ice | 1.2.3 Tower Operations Site (TOS) - Off-ice | 1.2.4 Computing and Control System - Off-ice | 1.2.5 Power Generation & Distribution | 1.2.6 Water Handling Systems - Off-ice | 1.2.7 Support Equipment - Off-ice | 1.2.8 Drill Field Seasons - Antarctica | 1.2.9 Installation - Off-ice | 1.2.10 Installation Field Seasons - Antarctica | 1.3.1 mDOM | 1.3.2 D-Egg | 1.3.3 PDOM | 1.3.4 Ice Comms Module | 1.3.5 Special Devices | 1.4.1 Downhole Cables | 1.4.2 Surface Cables | 1.4.3 FieldHub | 1.4.4 CPT Central Infrastructure | 1.4.5 Northern Test System | 1.4.6 CPT Management (PY4 onward) | 1.5.1 Module Calibration | 1.5.2 Calibration Assemblies | 1.5.3 Array Calibration | 1.5.4 Calibration Management and Organization | 1.6.0 L2 Task Management | 1.6.1 Online Systems Software | 1.6.2 Offline Systems | 1.6.3 Simulation Software | 1.6.4 Computing Infrastructure | 1.6.5 Upgrade String Commissioning
Expense Description |  |  | Total Yr 5
Senior Personnel
Title | Last Name | Cal. Mo.
Principal Investigator | Cowen | 0.26667 | 5226.3046 | 5226.3046 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other Personnel |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Firmware Engineer | Anderson | 0.41647 | 3434.918 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3434.918 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Salaries and Wages
|  |  | 8661.2226 | 5226.3046 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3434.918 | 0 | 0 | 0 | 0
Fringe Benefits
|  |  | 3118.0401 | 1881.4697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1236.5705 | 0 | 0 | 0 | 0
Equipment
Descrip. | Qty | Unit Cost
Capital Equipment | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Capitalized Labor | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Eqpt
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Travel
Domestic |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Foreign |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Travel
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Participant Support Costs
Descr | # participants |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Part. Supp.
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other Direct Costs
Materials and Supplies |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Computers/Office |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Software/licenses |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other categories |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
And other cats… |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Materials and Supplies
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Publication Costs/Documentation/Dissemination
Consultant Services Description |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Software/Programming |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Database consultant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Etc. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Consultant/Prof Services
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Computer Services |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subotal Computer Services
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subawards
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Subawards
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Leases |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Maint/Repair |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Shipping/Postage |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Other
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total - Direct Costs
|  |  | 11779.2627 | 7107.7743 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4671.4884 | 0 | 0 | 0 | 0
Indirect Costs
Indirect |  |  | 7185.3503 | 4335.7423 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2849.6079 | 0 | 0 | 0 | 0
Other |  |  |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Indirect Costs |  |  | 7185.3503 | 4335.7423 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2849.6079 | 0 | 0 | 0 | 0
0
Total - Direct and Indirect
|  |  | 18964.613 | 11443.5166 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7521.0964 | 0 | 0 | 0 | 0

## PY5 1030 - UA
Project Year | PY5 |  |  | 1.1.1 | 1.1.2 | 1.1.3 | 1.1.4 | 1.1.5 | 1.2.1 | 1.2.2 | 1.2.3 | 1.2.4 | 1.2.5 | 1.2.6 | 1.2.7 | 1.2.8 | 1.2.9 | 1.2.10 | 1.3.1 | 1.3.2 | 1.3.3 | 1.3.4 | 1.3.5 | 1.4.1 | 1.4.2 | 1.4.3 | 1.4.4 | 1.4.5 | 1.4.6 | 1.5.1 | 1.5.2 | 1.5.3 | 1.5.4 | 1.6.0 | 1.6.1 | 1.6.2 | 1.6.3 | 1.6.4 | 1.6.5
Institution | UA |  |  | 1.1.1: 1.1 Project Office; 1.2.1: 1.2 Drilling and Installation; 1.3.1: 1.3 Deep Ice Sensor Modules; 1.4.1: 1.4 Comm/Power/Timing; 1.5.1: 1.5 Characterization and Calibration System; 1.6.0: 1.6 IceCube Data Systems Integration
|  |  |  | 1.1.1 Project Management | 1.1.2 Project Controls | 1.1.3 Quality and Safety | 1.1.4 Polar Operations | 1.1.5 Project Engineering | 1.2.1 Implementation Management & Systems Engineering | 1.2.2 Thermal Plant - Off-ice | 1.2.3 Tower Operations Site (TOS) - Off-ice | 1.2.4 Computing and Control System - Off-ice | 1.2.5 Power Generation & Distribution | 1.2.6 Water Handling Systems - Off-ice | 1.2.7 Support Equipment - Off-ice | 1.2.8 Drill Field Seasons - Antarctica | 1.2.9 Installation - Off-ice | 1.2.10 Installation Field Seasons - Antarctica | 1.3.1 mDOM | 1.3.2 D-Egg | 1.3.3 PDOM | 1.3.4 Ice Comms Module | 1.3.5 Special Devices | 1.4.1 Downhole Cables | 1.4.2 Surface Cables | 1.4.3 FieldHub | 1.4.4 CPT Central Infrastructure | 1.4.5 Northern Test System | 1.4.6 CPT Management (PY4 onward) | 1.5.1 Module Calibration | 1.5.2 Calibration Assemblies | 1.5.3 Array Calibration | 1.5.4 Calibration Management and Organization | 1.6.0 L2 Task Management | 1.6.1 Online Systems Software | 1.6.2 Offline Systems | 1.6.3 Simulation Software | 1.6.4 Computing Infrastructure | 1.6.5 Upgrade String Commissioning
Expense Description |  |  | Total Yr 5
Senior Personnel
Title | Last Name | Cal. Mo.
Principal Investigator | Williams | 0.53333 | 5965.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5965.56 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other Personnel |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PostDoc | PostDoc | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Salaries and Wages
|  |  | 5965.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5965.56 | 0 | 0 | 0 | 0 | 0 | 0
Fringe Benefits
|  |  | 1908.9792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1908.9792 | 0 | 0 | 0 | 0 | 0 | 0
Equipment
Descrip. | Qty | Unit Cost
Capital Equipment | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Capitalized Labor | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Eqpt
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Travel
Domestic |  |  | 3677.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3677.4 | 0 | 0 | 0 | 0 | 0 | 0
Foreign |  |  | 6537.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6537.6 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Travel
|  |  | 10215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10215 | 0 | 0 | 0 | 0 | 0 | 0
Participant Support Costs
Descr | # participants |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Part. Supp.
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other Direct Costs
Materials and Supplies |  |  | 3064.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3064.5 | 0 | 0 | 0 | 0 | 0 | 0
Computers/Office |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Software/licenses |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other categories |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
And other cats… |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Materials and Supplies
|  |  | 3064.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3064.5 | 0 | 0 | 0 | 0 | 0 | 0
Publication Costs/Documentation/Dissemination
Consultant Services Description |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Software/Programming |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Database consultant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Etc. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Consultant/Prof Services
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Computer Services |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subotal Computer Services
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subawards
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Subawards
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Leases |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Maint/Repair |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Shipping/Postage |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Other
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total - Direct Costs
|  |  | 21154.0392 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21154.0392 | 0 | 0 | 0 | 0 | 0 | 0
Indirect Costs
Indirect |  |  | 10365.4792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10365.4792 | 0 | 0 | 0 | 0 | 0 | 0
Other |  |  |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Indirect Costs |  |  | 10365.4792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10365.4792 | 0 | 0 | 0 | 0 | 0 | 0
0
Total - Direct and Indirect
|  |  | 31519.5184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31519.5184 | 0 | 0 | 0 | 0 | 0 | 0

## PY6 1030 - UA
Project Year | PY6 |  |  | 1.1.1 | 1.1.2 | 1.1.3 | 1.1.4 | 1.1.5 | 1.2.1 | 1.2.2 | 1.2.3 | 1.2.4 | 1.2.5 | 1.2.6 | 1.2.7 | 1.2.8 | 1.2.9 | 1.2.10 | 1.3.1 | 1.3.2 | 1.3.3 | 1.3.4 | 1.3.5 | 1.4.1 | 1.4.2 | 1.4.3 | 1.4.4 | 1.4.5 | 1.4.6 | 1.5.1 | 1.5.2 | 1.5.3 | 1.5.4 | 1.6.0 | 1.6.1 | 1.6.2 | 1.6.3 | 1.6.4 | 1.6.5
Institution | UA |  |  | 1.1.1: 1.1 Project Office; 1.2.1: 1.2 Drilling and Installation; 1.3.1: 1.3 Deep Ice Sensor Modules; 1.4.1: 1.4 Comm/Power/Timing; 1.5.1: 1.5 Characterization and Calibration System; 1.6.0: 1.6 IceCube Data Systems Integration
|  |  |  | 1.1.1 Project Management | 1.1.2 Project Controls | 1.1.3 Quality and Safety | 1.1.4 Polar Operations | 1.1.5 Project Engineering | 1.2.1 Implementation Management & Systems Engineering | 1.2.2 Thermal Plant - Off-ice | 1.2.3 Tower Operations Site (TOS) - Off-ice | 1.2.4 Computing and Control System - Off-ice | 1.2.5 Power Generation & Distribution | 1.2.6 Water Handling Systems - Off-ice | 1.2.7 Support Equipment - Off-ice | 1.2.8 Drill Field Seasons - Antarctica | 1.2.9 Installation - Off-ice | 1.2.10 Installation Field Seasons - Antarctica | 1.3.1 mDOM | 1.3.2 D-Egg | 1.3.3 PDOM | 1.3.4 Ice Comms Module | 1.3.5 Special Devices | 1.4.1 Downhole Cables | 1.4.2 Surface Cables | 1.4.3 FieldHub | 1.4.4 CPT Central Infrastructure | 1.4.5 Northern Test System | 1.4.6 CPT Management (PY4 onward) | 1.5.1 Module Calibration | 1.5.2 Calibration Assemblies | 1.5.3 Array Calibration | 1.5.4 Calibration Management and Organization | 1.6.0 L2 Task Management | 1.6.1 Online Systems Software | 1.6.2 Offline Systems | 1.6.3 Simulation Software | 1.6.4 Computing Infrastructure | 1.6.5 Upgrade String Commissioning
Expense Description |  |  | Total Yr 5
Senior Personnel
Title | Last Name | Cal. Mo.
Principal Investigator | Williams | 0.53333 | 6093.8195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6093.8195 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other Personnel |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PostDoc | PostDoc | 12 | 52590.4974 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52590.4974 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Salaries and Wages
|  |  | 58684.3169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52590.4974 | 6093.8195 | 0 | 0 | 0 | 0 | 0 | 0
Fringe Benefits
|  |  | 11090.2507 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9140.2284 | 1950.0223 | 0 | 0 | 0 | 0 | 0 | 0
Equipment
Descrip. | Qty | Unit Cost
Capital Equipment | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Capitalized Labor | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Eqpt
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Travel
Domestic |  |  | 3756.4641 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3756.4641 | 0 | 0 | 0 | 0 | 0 | 0
Foreign |  |  | 6678.1584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6678.1584 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Travel
|  |  | 10434.6225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10434.6225 | 0 | 0 | 0 | 0 | 0 | 0
Participant Support Costs
Descr | # participants |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Part. Supp.
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other Direct Costs
Materials and Supplies |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Computers/Office |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Software/licenses |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other categories |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
And other cats… |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Materials and Supplies
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Publication Costs/Documentation/Dissemination
Consultant Services Description |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Software/Programming |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Database consultant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Etc. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Consultant/Prof Services
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Computer Services |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subotal Computer Services
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subawards
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Subawards
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Leases |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Maint/Repair |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Shipping/Postage |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Other
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total - Direct Costs
|  |  | 80209.1901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61730.7258 | 18478.4643 | 0 | 0 | 0 | 0 | 0 | 0
Indirect Costs
Indirect |  |  | 39302.5032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30248.0557 | 9054.4475 | 0 | 0 | 0 | 0 | 0 | 0
Other |  |  |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Indirect Costs |  |  | 39302.5032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30248.0557 | 9054.4475 | 0 | 0 | 0 | 0 | 0 | 0
0
Total - Direct and Indirect
|  |  | 119511.6933 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91978.7815 | 27532.9118 | 0 | 0 | 0 | 0 | 0 | 0

## PY7 1030 - UA
Project Year | PY7 |  |  | 1.1.1 | 1.1.2 | 1.1.3 | 1.1.4 | 1.1.5 | 1.2.1 | 1.2.2 | 1.2.3 | 1.2.4 | 1.2.5 | 1.2.6 | 1.2.7 | 1.2.8 | 1.2.9 | 1.2.10 | 1.3.1 | 1.3.2 | 1.3.3 | 1.3.4 | 1.3.5 | 1.4.1 | 1.4.2 | 1.4.3 | 1.4.4 | 1.4.5 | 1.4.6 | 1.5.1 | 1.5.2 | 1.5.3 | 1.5.4 | 1.6.0 | 1.6.1 | 1.6.2 | 1.6.3 | 1.6.4 | 1.6.5
Institution | UA |  |  | 1.1.1: 1.1 Project Office; 1.2.1: 1.2 Drilling and Installation; 1.3.1: 1.3 Deep Ice Sensor Modules; 1.4.1: 1.4 Comm/Power/Timing; 1.5.1: 1.5 Characterization and Calibration System; 1.6.0: 1.6 IceCube Data Systems Integration
|  |  |  | 1.1.1 Project Management | 1.1.2 Project Controls | 1.1.3 Quality and Safety | 1.1.4 Polar Operations | 1.1.5 Project Engineering | 1.2.1 Implementation Management & Systems Engineering | 1.2.2 Thermal Plant - Off-ice | 1.2.3 Tower Operations Site (TOS) - Off-ice | 1.2.4 Computing and Control System - Off-ice | 1.2.5 Power Generation & Distribution | 1.2.6 Water Handling Systems - Off-ice | 1.2.7 Support Equipment - Off-ice | 1.2.8 Drill Field Seasons - Antarctica | 1.2.9 Installation - Off-ice | 1.2.10 Installation Field Seasons - Antarctica | 1.3.1 mDOM | 1.3.2 D-Egg | 1.3.3 PDOM | 1.3.4 Ice Comms Module | 1.3.5 Special Devices | 1.4.1 Downhole Cables | 1.4.2 Surface Cables | 1.4.3 FieldHub | 1.4.4 CPT Central Infrastructure | 1.4.5 Northern Test System | 1.4.6 CPT Management (PY4 onward) | 1.5.1 Module Calibration | 1.5.2 Calibration Assemblies | 1.5.3 Array Calibration | 1.5.4 Calibration Management and Organization | 1.6.0 L2 Task Management | 1.6.1 Online Systems Software | 1.6.2 Offline Systems | 1.6.3 Simulation Software | 1.6.4 Computing Infrastructure | 1.6.5 Upgrade String Commissioning
Expense Description |  |  | Total Yr 5
Senior Personnel
Title | Last Name | Cal. Mo.
Principal Investigator | Williams | 0.53333 | 6224.8367 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6224.8367 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other Personnel |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PostDoc | PostDoc | 24 | 107442.3862 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 107442.3862 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Salaries and Wages
|  |  | 113667.2228 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 107442.3862 | 6224.8367 | 0 | 0 | 0 | 0 | 0 | 0
Fringe Benefits
|  |  | 20665.4345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18673.4867 | 1991.9477 | 0 | 0 | 0 | 0 | 0 | 0
Equipment
Descrip. | Qty | Unit Cost
Capital Equipment | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Capitalized Labor | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Eqpt
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Travel
Domestic |  |  | 3837.2281 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3837.2281 | 0 | 0 | 0 | 0 | 0 | 0
Foreign |  |  | 6821.7388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6821.7388 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Travel
|  |  | 10658.9669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10658.9669 | 0 | 0 | 0 | 0 | 0 | 0
Participant Support Costs
Descr | # participants |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Part. Supp.
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other Direct Costs
Materials and Supplies |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Computers/Office |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Software/licenses |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other categories |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
And other cats… |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Materials and Supplies
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Publication Costs/Documentation/Dissemination
Consultant Services Description |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Software/Programming |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Database consultant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Etc. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Consultant/Prof Services
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Computer Services |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subotal Computer Services
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subawards
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Subawards
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Leases |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Maint/Repair |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Shipping/Postage |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Other
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total - Direct Costs
|  |  | 144991.6242 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 126115.8729 | 18875.7513 | 0 | 0 | 0 | 0 | 0 | 0
Indirect Costs
Indirect |  |  | 71045.8958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61796.7777 | 9249.1181 | 0 | 0 | 0 | 0 | 0 | 0
Other |  |  |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Indirect Costs |  |  | 71045.8958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61796.7777 | 9249.1181 | 0 | 0 | 0 | 0 | 0 | 0
0
Total - Direct and Indirect
|  |  | 216037.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 187912.6506 | 28124.8694 | 0 | 0 | 0 | 0 | 0 | 0

## PY8 1030 - UA
Project Year | PY8 |  |  | 1.1.1 | 1.1.2 | 1.1.3 | 1.1.4 | 1.1.5 | 1.2.1 | 1.2.2 | 1.2.3 | 1.2.4 | 1.2.5 | 1.2.6 | 1.2.7 | 1.2.8 | 1.2.9 | 1.2.10 | 1.3.1 | 1.3.2 | 1.3.3 | 1.3.4 | 1.3.5 | 1.4.1 | 1.4.2 | 1.4.3 | 1.4.4 | 1.4.5 | 1.4.6 | 1.5.1 | 1.5.2 | 1.5.3 | 1.5.4 | 1.6.0 | 1.6.1 | 1.6.2 | 1.6.3 | 1.6.4 | 1.6.5
Institution | UA |  |  | 1.1.1: 1.1 Project Office; 1.2.1: 1.2 Drilling and Installation; 1.3.1: 1.3 Deep Ice Sensor Modules; 1.4.1: 1.4 Comm/Power/Timing; 1.5.1: 1.5 Characterization and Calibration System; 1.6.0: 1.6 IceCube Data Systems Integration
|  |  |  | 1.1.1 Project Management | 1.1.2 Project Controls | 1.1.3 Quality and Safety | 1.1.4 Polar Operations | 1.1.5 Project Engineering | 1.2.1 Implementation Management & Systems Engineering | 1.2.2 Thermal Plant - Off-ice | 1.2.3 Tower Operations Site (TOS) - Off-ice | 1.2.4 Computing and Control System - Off-ice | 1.2.5 Power Generation & Distribution | 1.2.6 Water Handling Systems - Off-ice | 1.2.7 Support Equipment - Off-ice | 1.2.8 Drill Field Seasons - Antarctica | 1.2.9 Installation - Off-ice | 1.2.10 Installation Field Seasons - Antarctica | 1.3.1 mDOM | 1.3.2 D-Egg | 1.3.3 PDOM | 1.3.4 Ice Comms Module | 1.3.5 Special Devices | 1.4.1 Downhole Cables | 1.4.2 Surface Cables | 1.4.3 FieldHub | 1.4.4 CPT Central Infrastructure | 1.4.5 Northern Test System | 1.4.6 CPT Management (PY4 onward) | 1.5.1 Module Calibration | 1.5.2 Calibration Assemblies | 1.5.3 Array Calibration | 1.5.4 Calibration Management and Organization | 1.6.0 L2 Task Management | 1.6.1 Online Systems Software | 1.6.2 Offline Systems | 1.6.3 Simulation Software | 1.6.4 Computing Infrastructure | 1.6.5 Upgrade String Commissioning
Expense Description |  |  | Total Yr 5
Senior Personnel
Title | Last Name | Cal. Mo.
Principal Investigator | Williams | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other Personnel |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PostDoc | PostDoc | 12 | 54876.1987 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54876.1987 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Salaries and Wages
|  |  | 54876.1987 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54876.1987 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fringe Benefits
|  |  | 9537.4833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9537.4833 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Equipment
Descrip. | Qty | Unit Cost
Capital Equipment | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Capitalized Labor | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Eqpt
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Travel
Domestic |  |  | 1959.8642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1959.8642 | 0 | 0 | 0 | 0 | 0 | 0
Foreign |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Travel
|  |  | 1959.8642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1959.8642 | 0 | 0 | 0 | 0 | 0 | 0
Participant Support Costs
Descr | # participants |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Part. Supp.
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other Direct Costs
Materials and Supplies |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Computers/Office |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Software/licenses |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other categories |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
And other cats… |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Materials and Supplies
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Publication Costs/Documentation/Dissemination
Consultant Services Description |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Software/Programming |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Database consultant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Etc. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Consultant/Prof Services
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Computer Services |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subotal Computer Services
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subawards
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Subawards
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Leases |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Maint/Repair |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Shipping/Postage |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Other
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total - Direct Costs
|  |  | 66373.5463 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64413.6821 | 1959.8642 | 0 | 0 | 0 | 0 | 0 | 0
Indirect Costs
Indirect |  |  | 32523.0377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31562.7042 | 960.3335 | 0 | 0 | 0 | 0 | 0 | 0
Other |  |  |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Indirect Costs |  |  | 32523.0377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31562.7042 | 960.3335 | 0 | 0 | 0 | 0 | 0 | 0
0
Total - Direct and Indirect
|  |  | 98896.584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95976.3863 | 2920.1977 | 0 | 0 | 0 | 0 | 0 | 0

## PY5 1030 - UMD
Project Year | PY5 |  |  | 1.1.1 | 1.1.2 | 1.1.3 | 1.1.4 | 1.1.5 | 1.2.1 | 1.2.2 | 1.2.3 | 1.2.4 | 1.2.5 | 1.2.6 | 1.2.7 | 1.2.8 | 1.2.9 | 1.2.10 | 1.3.1 | 1.3.2 | 1.3.3 | 1.3.4 | 1.3.5 | 1.4.1 | 1.4.2 | 1.4.3 | 1.4.4 | 1.4.5 | 1.4.6 | 1.5.1 | 1.5.2 | 1.5.3 | 1.5.4 | 1.6.0 | 1.6.1 | 1.6.2 | 1.6.3 | 1.6.4 | 1.6.5
Institution | UMD |  |  | 1.1.1: 1.1 Project Office; 1.2.1: 1.2 Drilling and Installation; 1.3.1: 1.3 Deep Ice Sensor Modules; 1.4.1: 1.4 Comm/Power/Timing; 1.5.1: 1.5 Characterization and Calibration System; 1.6.0: 1.6 IceCube Data Systems Integration
|  |  |  | 1.1.1 Project Management | 1.1.2 Project Controls | 1.1.3 Quality and Safety | 1.1.4 Polar Operations | 1.1.5 Project Engineering | 1.2.1 Implementation Management & Systems Engineering | 1.2.2 Thermal Plant - Off-ice | 1.2.3 Tower Operations Site (TOS) - Off-ice | 1.2.4 Computing and Control System - Off-ice | 1.2.5 Power Generation & Distribution | 1.2.6 Water Handling Systems - Off-ice | 1.2.7 Support Equipment - Off-ice | 1.2.8 Drill Field Seasons - Antarctica | 1.2.9 Installation - Off-ice | 1.2.10 Installation Field Seasons - Antarctica | 1.3.1 mDOM | 1.3.2 D-Egg | 1.3.3 PDOM | 1.3.4 Ice Comms Module | 1.3.5 Special Devices | 1.4.1 Downhole Cables | 1.4.2 Surface Cables | 1.4.3 FieldHub | 1.4.4 CPT Central Infrastructure | 1.4.5 Northern Test System | 1.4.6 CPT Management (PY4 onward) | 1.5.1 Module Calibration | 1.5.2 Calibration Assemblies | 1.5.3 Array Calibration | 1.5.4 Calibration Management and Organization | 1.6.0 L2 Task Management | 1.6.1 Online Systems Software | 1.6.2 Offline Systems | 1.6.3 Simulation Software | 1.6.4 Computing Infrastructure | 1.6.5 Upgrade String Commissioning
Expense Description |  |  | Total Yr 5
Senior Personnel
Title | Last Name | Cal. Mo.
Principal Investigator | Sullivan | 0.3 | 7929.8534 | 7929.8534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Data Systems L2 | Blaufuss | 1.76 | 23065.3883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23065.3883 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other Personnel |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Scientist | TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Salaries and Wages
|  |  | 30995.2417 | 7929.8534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23065.3883 | 0 | 0 | 0 | 0 | 0
Fringe Benefits
|  |  | 9267.5773 | 2371.0262 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6896.5511 | 0 | 0 | 0 | 0 | 0
Equipment
Descrip. | Qty | Unit Cost
Capital Equipment | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Capitalized Labor | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Eqpt
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Travel
Domestic |  |  | 5516.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5516.1 | 0 | 0 | 0 | 0 | 0
Foreign |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Travel
|  |  | 5516.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5516.1 | 0 | 0 | 0 | 0 | 0
Participant Support Costs
Descr | # participants |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Part. Supp.
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other Direct Costs
Materials and Supplies |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Computers/Office |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Software/licenses |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other categories |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
And other cats… |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Materials and Supplies
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Publication Costs/Documentation/Dissemination
Consultant Services Description |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Software/Programming |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Database consultant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Etc. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Consultant/Prof Services
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Computer Services |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subotal Computer Services
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subawards
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Subawards
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Leases |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Maint/Repair |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Shipping/Postage |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Other
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total - Direct Costs
|  |  | 45778.919 | 10300.8796 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35478.0394 | 0 | 0 | 0 | 0 | 0
Indirect Costs
Indirect |  |  | 24949.5108 | 5613.9794 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19335.5315 | 0 | 0 | 0 | 0 | 0
Other |  |  |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Indirect Costs |  |  | 24949.5108 | 5613.9794 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19335.5315 | 0 | 0 | 0 | 0 | 0
0
Total - Direct and Indirect
|  |  | 70728.4298 | 15914.859 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54813.5708 | 0 | 0 | 0 | 0 | 0

## PY6 1030 - UMD
Project Year | PY6 |  |  | 1.1.1 | 1.1.2 | 1.1.3 | 1.1.4 | 1.1.5 | 1.2.1 | 1.2.2 | 1.2.3 | 1.2.4 | 1.2.5 | 1.2.6 | 1.2.7 | 1.2.8 | 1.2.9 | 1.2.10 | 1.3.1 | 1.3.2 | 1.3.3 | 1.3.4 | 1.3.5 | 1.4.1 | 1.4.2 | 1.4.3 | 1.4.4 | 1.4.5 | 1.4.6 | 1.5.1 | 1.5.2 | 1.5.3 | 1.5.4 | 1.6.0 | 1.6.1 | 1.6.2 | 1.6.3 | 1.6.4 | 1.6.5
Institution | UMD |  |  | 1.1.1: 1.1 Project Office; 1.2.1: 1.2 Drilling and Installation; 1.3.1: 1.3 Deep Ice Sensor Modules; 1.4.1: 1.4 Comm/Power/Timing; 1.5.1: 1.5 Characterization and Calibration System; 1.6.0: 1.6 IceCube Data Systems Integration
|  |  |  | 1.1.1 Project Management | 1.1.2 Project Controls | 1.1.3 Quality and Safety | 1.1.4 Polar Operations | 1.1.5 Project Engineering | 1.2.1 Implementation Management & Systems Engineering | 1.2.2 Thermal Plant - Off-ice | 1.2.3 Tower Operations Site (TOS) - Off-ice | 1.2.4 Computing and Control System - Off-ice | 1.2.5 Power Generation & Distribution | 1.2.6 Water Handling Systems - Off-ice | 1.2.7 Support Equipment - Off-ice | 1.2.8 Drill Field Seasons - Antarctica | 1.2.9 Installation - Off-ice | 1.2.10 Installation Field Seasons - Antarctica | 1.3.1 mDOM | 1.3.2 D-Egg | 1.3.3 PDOM | 1.3.4 Ice Comms Module | 1.3.5 Special Devices | 1.4.1 Downhole Cables | 1.4.2 Surface Cables | 1.4.3 FieldHub | 1.4.4 CPT Central Infrastructure | 1.4.5 Northern Test System | 1.4.6 CPT Management (PY4 onward) | 1.5.1 Module Calibration | 1.5.2 Calibration Assemblies | 1.5.3 Array Calibration | 1.5.4 Calibration Management and Organization | 1.6.0 L2 Task Management | 1.6.1 Online Systems Software | 1.6.2 Offline Systems | 1.6.3 Simulation Software | 1.6.4 Computing Infrastructure | 1.6.5 Upgrade String Commissioning
Expense Description |  |  | Total Yr 5
Senior Personnel
Title | Last Name | Cal. Mo.
Principal Investigator | Sullivan | 0.3 | 8100.3453 | 8100.3453 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Data Systems L2 | Blaufuss | 1.76 | 23561.2941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23561.2941 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other Personnel |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Scientist | TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Salaries and Wages
|  |  | 31661.6394 | 8100.3453 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23561.2941 | 0 | 0 | 0 | 0 | 0
Fringe Benefits
|  |  | 9466.8302 | 2422.0032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7044.8269 | 0 | 0 | 0 | 0 | 0
Equipment
Descrip. | Qty | Unit Cost
Capital Equipment | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Capitalized Labor | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Eqpt
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Travel
Domestic |  |  | 3756.4641 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3756.4641 | 0 | 0 | 0 | 0 | 0
Foreign |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Travel
|  |  | 3756.4641 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3756.4641 | 0 | 0 | 0 | 0 | 0
Participant Support Costs
Descr | # participants |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Part. Supp.
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other Direct Costs
Materials and Supplies |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Computers/Office |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Software/licenses |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other categories |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
And other cats… |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Materials and Supplies
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Publication Costs/Documentation/Dissemination
Consultant Services Description |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Software/Programming |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Database consultant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Etc. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Consultant/Prof Services
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Computer Services |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subotal Computer Services
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subawards
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Subawards
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Leases |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Maint/Repair |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Shipping/Postage |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Other
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total - Direct Costs
|  |  | 44884.9337 | 10522.3485 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34362.5852 | 0 | 0 | 0 | 0 | 0
Indirect Costs
Indirect |  |  | 24462.2889 | 5734.6799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18727.6089 | 0 | 0 | 0 | 0 | 0
Other |  |  |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Indirect Costs |  |  | 24462.2889 | 5734.6799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18727.6089 | 0 | 0 | 0 | 0 | 0
0
Total - Direct and Indirect
|  |  | 69347.2225 | 16257.0284 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53090.1941 | 0 | 0 | 0 | 0 | 0

## PY7 1030 - UMD
Project Year | PY7 |  |  | 1.1.1 | 1.1.2 | 1.1.3 | 1.1.4 | 1.1.5 | 1.2.1 | 1.2.2 | 1.2.3 | 1.2.4 | 1.2.5 | 1.2.6 | 1.2.7 | 1.2.8 | 1.2.9 | 1.2.10 | 1.3.1 | 1.3.2 | 1.3.3 | 1.3.4 | 1.3.5 | 1.4.1 | 1.4.2 | 1.4.3 | 1.4.4 | 1.4.5 | 1.4.6 | 1.5.1 | 1.5.2 | 1.5.3 | 1.5.4 | 1.6.0 | 1.6.1 | 1.6.2 | 1.6.3 | 1.6.4 | 1.6.5
Institution | UMD |  |  | 1.1.1: 1.1 Project Office; 1.2.1: 1.2 Drilling and Installation; 1.3.1: 1.3 Deep Ice Sensor Modules; 1.4.1: 1.4 Comm/Power/Timing; 1.5.1: 1.5 Characterization and Calibration System; 1.6.0: 1.6 IceCube Data Systems Integration
|  |  |  | 1.1.1 Project Management | 1.1.2 Project Controls | 1.1.3 Quality and Safety | 1.1.4 Polar Operations | 1.1.5 Project Engineering | 1.2.1 Implementation Management & Systems Engineering | 1.2.2 Thermal Plant - Off-ice | 1.2.3 Tower Operations Site (TOS) - Off-ice | 1.2.4 Computing and Control System - Off-ice | 1.2.5 Power Generation & Distribution | 1.2.6 Water Handling Systems - Off-ice | 1.2.7 Support Equipment - Off-ice | 1.2.8 Drill Field Seasons - Antarctica | 1.2.9 Installation - Off-ice | 1.2.10 Installation Field Seasons - Antarctica | 1.3.1 mDOM | 1.3.2 D-Egg | 1.3.3 PDOM | 1.3.4 Ice Comms Module | 1.3.5 Special Devices | 1.4.1 Downhole Cables | 1.4.2 Surface Cables | 1.4.3 FieldHub | 1.4.4 CPT Central Infrastructure | 1.4.5 Northern Test System | 1.4.6 CPT Management (PY4 onward) | 1.5.1 Module Calibration | 1.5.2 Calibration Assemblies | 1.5.3 Array Calibration | 1.5.4 Calibration Management and Organization | 1.6.0 L2 Task Management | 1.6.1 Online Systems Software | 1.6.2 Offline Systems | 1.6.3 Simulation Software | 1.6.4 Computing Infrastructure | 1.6.5 Upgrade String Commissioning
Expense Description |  |  | Total Yr 5
Senior Personnel
Title | Last Name | Cal. Mo.
Principal Investigator | Sullivan | 0.3 | 8274.5027 | 8274.5027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Data Systems L2 | Blaufuss | 1.76 | 24067.862 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24067.862 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other Personnel |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Scientist | TBD | 0.42 | 3499.9357 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3499.9357
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Salaries and Wages
|  |  | 35842.3004 | 8274.5027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24067.862 | 0 | 0 | 0 | 0 | 3499.9357
Fringe Benefits
|  |  | 10916.3441 | 2474.0763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7196.2907 | 0 | 0 | 0 | 0 | 1245.9771
Equipment
Descrip. | Qty | Unit Cost
Capital Equipment | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Capitalized Labor | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Eqpt
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Travel
Domestic |  |  | 1918.614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1918.614 | 0 | 0 | 0 | 0 | 0
Foreign |  |  | 1918.614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1918.614 | 0 | 0 | 0 | 0 | 0
Subtotal - Travel
|  |  | 3837.2281 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3837.2281 | 0 | 0 | 0 | 0 | 0
Participant Support Costs
Descr | # participants |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Part. Supp.
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other Direct Costs
Materials and Supplies |  |  | 1012.6019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1012.6019 | 0 | 0 | 0 | 0 | 0
Computers/Office |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Software/licenses |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other categories |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
And other cats… |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Materials and Supplies
|  |  | 1012.6019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1012.6019 | 0 | 0 | 0 | 0 | 0
Publication Costs/Documentation/Dissemination
Consultant Services Description |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Software/Programming |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Database consultant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Etc. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Consultant/Prof Services
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Computer Services |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subotal Computer Services
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subawards
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Subawards
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Leases |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Maint/Repair |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Shipping/Postage |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Other
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total - Direct Costs
|  |  | 51608.4745 | 10748.579 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36113.9826 | 0 | 0 | 0 | 0 | 4745.9128
Indirect Costs
Indirect |  |  | 28126.6186 | 5857.9756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19682.1205 | 0 | 0 | 0 | 0 | 2586.5225
Other |  |  |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Indirect Costs |  |  | 28126.6186 | 5857.9756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19682.1205 | 0 | 0 | 0 | 0 | 2586.5225
0
Total - Direct and Indirect
|  |  | 79735.093 | 16606.5546 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55796.1031 | 0 | 0 | 0 | 0 | 7332.4354

## PY8 1030 - UMD
Project Year | PY8 |  |  | 1.1.1 | 1.1.2 | 1.1.3 | 1.1.4 | 1.1.5 | 1.2.1 | 1.2.2 | 1.2.3 | 1.2.4 | 1.2.5 | 1.2.6 | 1.2.7 | 1.2.8 | 1.2.9 | 1.2.10 | 1.3.1 | 1.3.2 | 1.3.3 | 1.3.4 | 1.3.5 | 1.4.1 | 1.4.2 | 1.4.3 | 1.4.4 | 1.4.5 | 1.4.6 | 1.5.1 | 1.5.2 | 1.5.3 | 1.5.4 | 1.6.0 | 1.6.1 | 1.6.2 | 1.6.3 | 1.6.4 | 1.6.5
Institution | UMD |  |  | 1.1.1: 1.1 Project Office; 1.2.1: 1.2 Drilling and Installation; 1.3.1: 1.3 Deep Ice Sensor Modules; 1.4.1: 1.4 Comm/Power/Timing; 1.5.1: 1.5 Characterization and Calibration System; 1.6.0: 1.6 IceCube Data Systems Integration
|  |  |  | 1.1.1 Project Management | 1.1.2 Project Controls | 1.1.3 Quality and Safety | 1.1.4 Polar Operations | 1.1.5 Project Engineering | 1.2.1 Implementation Management & Systems Engineering | 1.2.2 Thermal Plant - Off-ice | 1.2.3 Tower Operations Site (TOS) - Off-ice | 1.2.4 Computing and Control System - Off-ice | 1.2.5 Power Generation & Distribution | 1.2.6 Water Handling Systems - Off-ice | 1.2.7 Support Equipment - Off-ice | 1.2.8 Drill Field Seasons - Antarctica | 1.2.9 Installation - Off-ice | 1.2.10 Installation Field Seasons - Antarctica | 1.3.1 mDOM | 1.3.2 D-Egg | 1.3.3 PDOM | 1.3.4 Ice Comms Module | 1.3.5 Special Devices | 1.4.1 Downhole Cables | 1.4.2 Surface Cables | 1.4.3 FieldHub | 1.4.4 CPT Central Infrastructure | 1.4.5 Northern Test System | 1.4.6 CPT Management (PY4 onward) | 1.5.1 Module Calibration | 1.5.2 Calibration Assemblies | 1.5.3 Array Calibration | 1.5.4 Calibration Management and Organization | 1.6.0 L2 Task Management | 1.6.1 Online Systems Software | 1.6.2 Offline Systems | 1.6.3 Simulation Software | 1.6.4 Computing Infrastructure | 1.6.5 Upgrade String Commissioning
Expense Description |  |  | Total Yr 5
Senior Personnel
Title | Last Name | Cal. Mo.
Principal Investigator | Sullivan | 0.15 | 4226.2023 | 4226.2023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Data Systems L2 | Blaufuss | 0.88 | 12292.6605 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12292.6605 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other Personnel |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Scientist | TBD | 1.5467 | 2383.4562 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2383.4562
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Salaries and Wages
|  |  | 18902.319 | 4226.2023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12292.6605 | 0 | 0 | 0 | 0 | 2383.4562
Fringe Benefits
|  |  | 5787.6504 | 1263.6345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3675.5055 | 0 | 0 | 0 | 0 | 848.5104
Equipment
Descrip. | Qty | Unit Cost
Capital Equipment | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Capitalized Labor | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Eqpt
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Travel
Domestic |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Foreign |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Travel
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Participant Support Costs
Descr | # participants |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Part. Supp.
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other Direct Costs
Materials and Supplies |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Computers/Office |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Software/licenses |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other categories |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
And other cats… |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Materials and Supplies
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Publication Costs/Documentation/Dissemination
Consultant Services Description |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Software/Programming |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Database consultant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Etc. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Consultant/Prof Services
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Computer Services |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subotal Computer Services
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subawards
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Subawards
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Leases |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Maint/Repair |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Shipping/Postage |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Other
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total - Direct Costs
|  |  | 24689.9694 | 5489.8367 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15968.166 | 0 | 0 | 0 | 0 | 3231.9667
Indirect Costs
Indirect |  |  | 13456.0333 | 2991.961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8702.6505 | 0 | 0 | 0 | 0 | 1761.4218
Other |  |  |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Indirect Costs |  |  | 13456.0333 | 2991.961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8702.6505 | 0 | 0 | 0 | 0 | 1761.4218
0
Total - Direct and Indirect
|  |  | 38146.0027 | 8481.7977 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24670.8164 | 0 | 0 | 0 | 0 | 4993.3885